## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Piling | itp |  |  |  |  | Piling
section | Preliminary
checkpoint | Shop Drawings
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Approved shop drawings prior to fabrication
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - 5 Days before commencing fabrication
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Concrete Mix Design Approved
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Approval from Engineer
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Per Mix Design
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Pre cast Piles
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for each pile
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Abutment A Piles
checkpoint | Pile setout
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - After setout of each pile
label | ACCEPTANCE CRITERIA - As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Driving Of Piles
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - For each Pile
label | ACCEPTANCE CRITERIA - Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet
label | UCCL - W
label | WSP - W
section | Abutment B Piles
checkpoint | Pile setout
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - After setout of each pile
label | ACCEPTANCE CRITERIA - As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Driving Of Piles
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - For each Pile
label | ACCEPTANCE CRITERIA - Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet
label | UCCL - W
label | WSP - W
checklist | Abutment and Backwall | itp |  |  |  |  | Abutment and Backwall
section | Preliminary
checkpoint | Concrete Mix Design Approved
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Approval from Engineer
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Per Mix Design
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Abutment A Construction
checkpoint | Setout
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Enginner
label | TASK TIMING OR TASK FREQUENCY - For set out of each Abutment
label | ACCEPTANCE CRITERIA - As per IFC Drawings
label | UCCL - W
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Abutment B Construction
checkpoint | Setout
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - For set out of each Abutment
label | ACCEPTANCE CRITERIA - As per IFC Drawings
label | UCCL - W
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Abutment A Backwall Construction
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Abutment C Backwall Construction
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment backwall
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
section | Construction of Mortar Bearing Pad
checkpoint | Pre Pour Inspection
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Pre pour inspection for Abutment
label | ACCEPTANCE CRITERIA - Pre pour inspection checksheet
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checklist-flat | Structural Steel Works | [5 empty] | Structural Steel Works
checkpoint | Sub contractor's ITP
checklist | Timber Work | itp |  |  |  |  | Timber Work
section | Preliminary
checkpoint | Procurement
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Dockets
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - For any timber ordered for project
label | ACCEPTANCE CRITERIA - All timber to meet specified grade and Moisture content as specified in particular specification
label | UCCL - W
label | WSP - W
checkpoint | Installation
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Visual Inspection/Photos
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Random site visits
label | ACCEPTANCE CRITERIA - All timber and Fastners installed as per IFC Drawing
label | UCCL - W
label | WSP - W
checklist | Reinstate Approaches | itp |  |  |  |  | Reinstate Approaches
section | Preliminary
checkpoint | Backfill
label | SPECIFICATION REFERENCE - IFC Drawings / Particular Specification
label | TEST REQUIRED - Clegg Test
label | INSPECTION BY - UCCL/Engineer
label | TASK TIMING OR TASK FREQUENCY - 5 Tests per approach per layer
label | ACCEPTANCE CRITERIA - Clegg Impact value of 40
label | UCCL - W
label | WSP - W