## Table 1
|  |  |  | Inspection and Test Plan – Erosion & Sediment Controls | [10 empty] | Doc ID: ITP 1
Client: Iluka Resources Limited | [9 empty] | Prepared By: Simon Welsh
Project: Public Roads Upgrade | [9 empty] | Reviewed By: Joshua Kliemnt | [6 empty] | Date: 11/11//2024
Construction Process: Install Erosion & Sediment Controls | [9 empty] | Approved By: Simon Jaworksi | [6 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Lot No: | Lot Details: | [5 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. | Task/Activity Description |  | Inspection/Test | [8 empty] | Type | Responsib ility | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  |  |  | Client |  | Fulton Hogan |  |  | Comment | Date
1 | Preliminary
4 | Prepare a Environmental Control Plan (ECP) for the work area |  | Per Site | Prepare an ECP as well as the environmental risk sessement | EMP |  | Visual |  | Hold Point |  |  | IP | PE
5 | Install Erosion and Sediment Controls |  | Per Area | Installed in accordance to the approved progressive ESCP and guided by the BLUE BOOK. | EMP |  | Visual |  | Verification Checklist |  |  | IP | PE
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
HP | Hold Point | Work shall not proceed past the HP until released by the Project Verifier | [5 empty] | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [5 empty] | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Project Verifier | [5 empty] | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Project Verifier
Notes
This is an uncontrolled copy if photocopied or printed. Copyright © 2024, Fulton Hogan Ltd. All rights reserved.
Revised 12-06- 2012 Page 1 of 1
Content ID:AU_00002009 Revision: 1