## Table 1
|  |  |  | Inspection and Test Plan - Retroreflective Pavement Markers | [9 empty] | Doc ID: R142-RPM-ITP
Client: Iluka Resources Limited | [8 empty] | Prepared By: Simon Welsh
Project: Public Roads Upgrade | [8 empty] | Reviewed By: Joshua Kliemnt | [6 empty] | Date: 11/11//2024
Construction Process: Install Retroreflective Pavement Markers | [8 empty] | Approved By: Simon Jaworksi | [6 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Item No. | Task/Activity Description |  | Inspection/Test | [7 empty] | Type | Responsibility | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents |  | Inspecti on/ Test Method | Record of conformity |  |  |  |  | TfNSW |  | Fulton Hogan |  | PV | other
1 | Materials
2 | Obtain and submit conformance records |  | Per Area | Submission includes:  Recommendations of the raised pavement marker manufacturer on the materials and methods for the install of the RPM's  Product Data sheet and recommendation of adhesive use and handling  Method of protection of RPM's whilst adhesive is hardening  Material certification are ≤ 36 months old  Raised Pavement Markers conforms to AS1906.3 and have dimensions shown on Annex E  Made by the prequalified manufacture/s Annex F  Adhesive must comply with RTA 3354.  Submitted at least 7 days prior to proposed use | R142/D |  |  | Materials Compliance Certificate |  |  |  | Site Engineer
3 | Set out the works |  | Per Lot | The location of all raised pavement markers are as per Drawings, or directed by RMS and is within::  Longitudinal (±100mm)  Transverse (±25mm within 1.5m)  Direction (4° rotational) | R142.3 |  |  | Verification Checklist |  |  |  | Site Foreman
4 | Installation
5 | Commencement with application of Retroreflective Pavement Markers |  | Per Lot | For new Installations, set out the work to ensure all rpm's are placed in accordance with the nominated Plan and Drawings and to the tolerances required by the Specification | R142.3.1 |  |  | Hold Point |  |  | HP | Graduate Engineer
6 | Fix Retroreflective Pavement Markers |  | Per Lot |  RPM's are fixed with an adhesive to the surface of the pavement in accordance to the manufacturers recommendations.  Fixed at locations marked on the setout | R142.3.3 |  |  | Verification Checklist |  |  |  | Site Engineer
7 | Remove/replace non- functional/temporary markers |  | Per Area | Remove non functional markers only if the markers:  has a cracked body or lens, and by eye the night time headlight visibility appears unaffected, must not be replaced; or  has sunken into the pavement to make the removal difficult and give rise to excessive work in the repair of pavement. | R142.5.3 R141.6 |  |  | Verification Checklist |  |  |  | Site Engineer
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
HP | Hold Point | Work shall not proceed past the HP until released by the Project Verifier |  |  |  | IP | Inspection point |  |  | Formal Inspection to be done and recorded
HP* | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan |  |  |  | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Project Verifier |  |  |  | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Project Verifier
AP* | Fulton Hogan Approval Point | Written or verbal approval given by Fulton Hogan’s nominated personnel
Notes
|  |  |  | Inspection and Test Plan - Retroreflective Pavement Markers | [9 empty] | Doc ID: R142-RPM-ITP
Client: Iluka Resources Limited | [8 empty] | Prepared By: Simon Welsh
Project: Public Roads Upgrade | [8 empty] | Reviewed By: Joshua Kliemnt | [6 empty] | Date: 11/11//2024
Construction Process: Install Retroreflective Pavement Markers | [8 empty] | Approved By: Simon Jaworksi | [6 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component: