## Table 1
[7 empty] | Inspection and Test Plan – Pavement Marking and Raised Pavement Marking | [14 empty] | Doc ID: R145-PMW-ITP
Client: Iluka Resources Limited | [10 empty] | Prepared By: Simon Welsh | [10 empty] | Date: 15/10/2024
Project: Public Roads Upgrade | [10 empty] | Reviewed By: Joshua Kliemnt | [10 empty] | Date: 11/11//2024
Construction Process: Pavement Marking and Raised Pavement Marking | [10 empty] | Approved By: Simon Jaworksi | [10 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [12 empty] | Type |  | Responsibility |  |  |  | Checked/Verified by (initial/Date)
[5 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  |  |  | Inspection / Test Method |  | Record of conformity | [8 empty] | TfNSW |  | Fulton Hogan |  | PV |  | Date
1 |  | Preliminary
2 |  | Underlying lot conformance (if applicable) Lot No: …….. |  |  | Each lot |  | Underlying lots conform to applicable specifications |  | Previous Lot Record | [5 empty] | Lot conformance |  |  | R |  | Site Engineer
3 |  | Check if traffic controls are in place |  |  | Per Area |  |  Road Occupancy License Obtained if required;  Pedestrian and vehicular public traffic control planning measures established |  | G10.2.4 | [5 empty] | Approved TCP |  |  | IP |  | Site Engineer
4 |  | Painting Contractor Certification |  |  | Per Contractor |  |  Works carried out by organisation that is accredited to the “Painting Contractors Certification Program”. |  | R145.1.4 | [5 empty] | Certification |  |  | IP |  | Site Engineer
5 |  | Verify type of marking material as shown in drawings Waterborne paint thermoplastic paint Others ……………………… |  |  | Per Lot |  |  On concrete surfaces in the main carriageway and all local road – waterborne paint  Asphalt surface on the main carriageway – thermoplastic paint  Type as per relevant design drawings & R145 appendices  provide the TfNSW representative a list of material proposed for use and limitation to be used |  | R145.1.4 R145.2.1 AS 4049.3 AS 4049.2 3359 3360 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
6 |  | Verify the reflective glass beads conform to specs requirements |  |  | Per Material |  | (APAS) Specification APS0042 Clause 6.2 “Heavy metal content”. Obtain evidence of compliance. |  | R145.2.4 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
7 |  | Verify conformance of raised pavement markers & Adhesive |  |  | Per Material |  |  Use only retroreflective raised pavement markers prequalified by the TfNSW. Prequalified retroreflective raised pavement markers are listed in ATD 2015/01  For new installation and complete replacement |  | R142.2.1 3354.7 | [5 empty] | Verification Test Certificate |  |  | IP |  | Site Engineer
[7 empty] | Inspection and Test Plan – Pavement Marking and Raised Pavement Marking | [14 empty] | Doc ID: R145-PMW-ITP
Client: Iluka Resources Limited | [10 empty] | Prepared By: Simon Welsh | [10 empty] | Date: 15/10/2024
Project: Public Roads Upgrade | [10 empty] | Reviewed By: Joshua Kliemnt | [10 empty] | Date: 11/11//2024
Construction Process: Pavement Marking and Raised Pavement Marking | [10 empty] | Approved By: Simon Jaworksi | [10 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [12 empty] | Type |  | Responsibility |  |  |  | Checked/Verified by (initial/Date)
[5 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  |  |  | Inspection / Test Method |  | Record of conformity | [8 empty] | TfNSW |  | Fulton Hogan |  | PV |  | Date
works, all markers must be identifiable for at least twelve months after the initial installation.  For the adhesive provide a certificate of compliance verifying that the product complies with the specification, together with the results of the relevant tests.
8 |  | Sampling and Testing Plan |  |  | Per Contractor |  | Submit to PV contractors proposed sampling plan for assessing the pavement marking |  | R145.5 | [5 empty] | Sampling Plan |  |  | IP
9 |  | Application
10 |  | Prepare the Surface for marking |  |  | Per Lot |  |  The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material  The area around making area is also clean to avoid tracking into the marking area  Curing compound on marking areas of concrete pavements is removed by grinding or blasting.  Surface is compatible to the new line marking materials. |  | R145.3.1 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
11 |  | Set out the works for installation of pavement markings / raised markers |  |  | Per Lot |  | Notification made to the Project Verifier that the setting out to pavement markings and markers have been done in according with the design drawings |  | R145.3.4 | [5 empty] | Hold Point |  |  | HP |  | Site Engineer | [5 empty] | PV
12 |  | Supervise the application of pavement marking / markers |  |  | Per Lot |  |  Paints and markers installed as per manufacturer’s recommendations  The same materials used with those nominated in the certifications  All longitudinal lines have been applied by the nominated machine unless approved by Independent Verifier  Markings are straight or with smooth, even curves where intended  Edges are clean sharp cut off  Markings uniform in appearance, texture, width & thickness & free from unbeaded areas  Beads uniformly applied onto the material immediately after it has been applied to the pavement & while the material is still molten |  | R145.3.2.2 R145.3.4 R145.3.6 R145.4 R142.3 R142.4 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
[8 empty] | Inspection and Test Plan – Pavement Marking and Raised Pavement Marking | [14 empty] | Doc ID: R145-PMW-ITP
| Client: Iluka Resources Limited | [9 empty] | Prepared By: Simon Welsh | [11 empty] | Date: 15/10/2024
| Project: Public Roads Upgrade | [9 empty] | Reviewed By: Joshua Kliemnt | [11 empty] | Date: 11/11//2024
| Construction Process: Pavement Marking and Raised Pavement Marking | [9 empty] | Approved By: Simon Jaworksi | [11 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
| Item No. |  | Task/Activity Description |  |  | Inspection/Test | [12 empty] | Type |  | Responsibility |  |  |  | Checked/Verified by (initial/Date)
[6 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  |  |  | Inspection / Test Method |  | Record of conformity | [8 empty] | TfNSW |  | Fulton Hogan |  | PV |  | Date
 Retention of bead material is achieved  Markings are neat & free from traffic damage or other defects  Arrows/markings painted at correct direction  Marking protected from traffic until hardened  Makers installed at the designated locations
| 13 |  | Field test of the paint performance. |  |  | As Per Sampling Plan |  |  Thickness of non-profile marking≤6mm  Dry Retroreflectivity: min.250 mcd/lux/m2 up to 20 days after opening to traffic.  Wet Retroreflectivity: min.80 mcd/lux/m2  Skid resistance: min. 40BPN  Colour change: min.3  Luminance factor: ≥S 2500-N  Wear: ≤70% |  | R145.4 R145.5 AS 4049.5 | [5 empty] | Test Report |  |  | TP |  | Site Engineer
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Project Verifier | [6 empty] | IP | Inspection point |  |  |  |  | Formal Inspection to be done and recorded
| HP* |  | FH Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP | Test Point |  |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Project Verifier | [6 empty] | SCP | Survey conformance point |  |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Project Verifier | [6 empty] | SC | Survey Check
| R |  | Review
Notes