## Table 1
[7 empty] | Inspection and Test Plan – Stormwater Drainage | [9 empty] | Doc ID: R11-DRA-ITP
Client: Iluka Resources Limited | [16 empty] | Prepared By: Simon Welsh | [8 empty] | Date: 15/10/2024
Project: Public Roads Upgrade | [16 empty] | Reviewed By: Joshua Kliemnt | [8 empty] | Date: 11/11//2024
Construction Process: Stormwater Drainage | [16 empty] | Approved By: Simon Jaworksi | [8 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [12 empty] | Type |  | Responsibility |  | Checked/Verified by (initial/Date):
[5 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  |  |  | Inspection / Test Method |  | Record of conformity | [6 empty] | TfNSW |  | Fulton Hogan |  |  | PV | Date
1 |  | Preliminaries
2 |  | Check location of underground and above ground utilities |  |  | Per Area |  |  Before You Dig contacted  Excavation Permit is obtained |  | WHSMP | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
3 |  | Check the type, size and class of pipes and other drainage structures to be laid Size: ……. Class:……… |  |  | Per Delivery |  | Supplied items are:  To correct spec, class, size and quantity  Defect free, safely and securely stored  Markings have been made as required  Delivered 7 days after casting and concrete has reached specified 28 day strength |  | R11.2 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
4 |  | Supply of precast concrete members subject to traffic and/ or earth pressure loading, and water containing structures with capacity greater than 25,000 Litres |  |  | Per Type |  | Submitted design and manufacturing documentations to the Project Verifier for precast concrete structures which subject to traffic loads and/or earth pressure and water retaining structures with a capacity in excess of 25,000 litres. |  | R11.2.4.1 | [5 empty] | Hold Point |  |  | HP |  | Site Engineer |  |  |  | HP
5 |  | Incorporation into the works any supplied, manufactured drainage product. |  |  | Per Lot |  | Submit a Certificate of Conformity to the Project Verifier 7 days prior to incorporating into the works |  | R11.2.6 | [5 empty] | Hold Point |  |  | HP |  | Site Engineer |  |  |  | HP
6 |  | Verify conformance of BH (bedding & haunch) materials Material Conformance Lot:…. |  |  | G:1/ 50m³ PI:/100m³ |  | Grading limits as per Table 6 in AS 3725 except that ≤12% passing 75µm & PI < 6 |  | R11 3.1.1 R11/L Q6 8.1.1 |  |  |  | T201 T109 |  | NATA Test Report |  |  | TP |  | Site Engineer
7 |  | Verify conformance of SO (side & overlay) materials Material Conformance Lot:…. |  |  | G:1/ 50m³ PI:/100m³ |  | Max size 53mm, grading within limits in Table 7 of AS 3725 and PI >2 and < 12 |  | R11 3.1.2 R11/L Q6 8.1.1 |  |  |  | T201 T109 AS 3725 |  | NATA Test Report |  |  | TP |  | Site Engineer
8 |  | Verify conformance of material Adjacent to Weepholes |  |  | Per Delivery |  | Broken stone or river gravel of max size 53mm and < 5% passing 9.5mm sieve |  | R11 3.2 R11/L |  |  |  | T201 |  | NATA Test Report |  |  | TP |  | Site Engineer
9 |  | Subsurface drainage pipes |  |  | Per Delivery |  | Provide certificate of compliance accompanied by NATA certified test results in accordance with TfNSW 3552 not more than 6 months old |  | R11.4.4.5 TfNSW 3552 |  |  |  | T1505 T1506 |  | Certificate of Conformity |  |  | IP |  | Site Engineer
10 |  | Inspect supplied items upon delivery |  |  | Per Delivery |  | Supplied items are to correct spec, class, size and undamaged Steel Reinforced Pipes as per CL3.3 & 3.4 of AS4058 Fibre Reinforced Pipe as per CL9 & 10 AS4139 |  | QMP | [5 empty] | Receiving Inspection Checklist |  |  | IP |  | Site Engineer
11 |  | Trenching and Excavation
12 |  | Construction of each drainage system (1) |  |  | Per Lot |  | Set out the stormwater drainage systems as shown on the drawings in sufficient detail to identify:  the locations, lengths and levels at outlets and inlets of pipes and box culvert structures;  the locations and levels of gully pits, junction boxes, energy dissipaters, and inlet and outlet structures;  the locations and levels of the ends of wing walls and headwalls; and  the locations and levels of open drains. Notify PV that set out of drainage system has been completed. |  | R11.4.1.1 | [5 empty] | Hold Point |  |  | HP |  | Surveyor |  |  |  | HP
12 |  | Construction of each drainage system (2) |  |  | Per Lot |  | If set out is within 5 metres of an environmental sensitive area notify Environmental Manager |  | G36.4.12 | [5 empty] | Hold Point |  |  | HP |  | Surveyor | [6 empty] | HP
13 |  | Excavate trench to the underside of bedding to correct width |  |  | Per Lot |  |  Width and depth of pipe trench as per AS 3725 and standard drawings, refer to right table  For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater  Trenches > 1.5m deep are either shored or benched  The excavation is ≤ 50mm beyond the specified width and depths of the trench  For pipes under embankments - “Embankment Condition”: embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe - “Trench Condition”: Trenches done after the construct of the embankment to the level of the underside of the Selected Material Zone |  | R11.4.3 MD.R240-01 | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
14 |  | Foundation Compaction |  |  | Q6/L |  | Foundation to be compacted to 95%. (Standard compaction) |  | R11.4.9.2 R11.4.9.3 Q6 8.1.1 |  |  |  | T166 |  | Test Report |  |  | TP |  | Site Engineer
15 |  | Excavation for pipe installation and other drainage structures |  |  | Per Lot |  | Notify the Project Verifier of the anticipated date of completion of excavation and preparation of foundations. Not later than 24 hours, but not earlier than 5 working days. GDR to provide Geo-report to state that the foundation is suitable or need further treatment |  | R11.4.3 | [5 empty] | Witness Point |  |  | WP |  | Site Engineer |  |  |  | WP
16 |  | Remove & replace unsuitable materials, if directed by PV |  |  | Where required Q6/L |  | Replace with materials from cuttings or conforming material to full depth in 150mm layers and compact to 95% Standard Compaction |  | R11.4.3 Q6 8.1.1 |  |  |  | T166 |  | Test Report |  |  | TP |  | Site Engineer
17 |  | Replacement of inadequate foundation material. |  |  | Where required |  | Notification to the Project Verifier that inadequate foundation material has been excavated to the extent required. |  | R11.4.3.3 | [5 empty] | Witness Point |  |  | WP |  | Site Engineer |  |  |  | WP
18 |  | Placement of Pipes
19 |  | Place Bedding |  |  | Q6/L |  |  Bedding placed to a thickness of 100mm for pipes up to 1200mm dia pipes and 150mm for pipes greater than 120mm  Bedding compacted to 95% |  | R11 R240-01 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
20 |  | Install pipes in accordance to manufacturer’s instructions and design documentations |  |  | Per Lot |  |  Correct size and class of pipe installed  Pipes laid from inlet to outlet with socket laid upstream  Pipe support are Type HS3 conforming to AS3725 and MD R240-01  Pipe ends cleaned and rubber rings correctly installed  Where grade exceed 20%: anchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings  100mm dia Subsurface drainage installed at the discharge end of pipes 3m long, laid beside & 100mm above invert level of drainage pipe  All joints have rubber rings fitted and pipes butting against each other.  Connection to pits in accordance with MD R220-43 |  | R11.4.4 R240-01 R220-43 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
21 |  | Pit/headwall to pipe connection |  |  | Per connectio n |  |  Pit to pipe connections are to be flush along the pit wall, with minimal protrusions or depressions. |  | CMS 7.8 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
22 |  | Verify that completed pipeline against survey marks |  |  |  Per Lot |  |  Completed pipeline is inline and within ±200mm of location (plan)  Invert level are within 20mm of the design level at any point  To be checked at each pit and headwall |  | R11.5.1 Table R11.4 | [5 empty] | Survey Report |  |  | SC |  | Surveyor
23 |  | Construction of Drainage Structures (Other Than Pipes and Box Culverts)
24 |  | Construction of drainage structures other than pipes and box culverts. |  |  | Per Structure |  | The notification is to be at least 7 days prior to the date of installation work. |  | R11.4.7.2 | [5 empty] | Witness Point |  |  | WP |  | Site Engineer |  |  |  | WP
25 |  | Place bedding layer underneath pit, or plain concrete blinding to headwalls. Ensure correct survey tools have been used to transfer levels, i.e. dumpy level |  |  | Per Structure |  | The bedding materials consists either of: For Precast Pits 50mm layer DGB20 or CLSM; For other than precast a 50mm blinding layer |  | R11.4.7.2 | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
26 |  | Install precast drainage structures as specified on design documentations |  |  | Per Structure |  |  Installed within 14days after installation of associated pipes, box culverts or open drains  Where drainage structure abuts a structure or concrete pavement, a 10mm wide filler complying with TfNSW 3204 is installed as an isolation joint  Subsoil drainage pipe connected to downstream headwalls/pits  Lifting holes are sealed  Structure is level and plumb |  | R11.4.7 | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
27 |  | Install Cast In place drainage structures (incl. headwalls and curtain walls) as shown on design documentations R53-GCW Lot No: |  |  | Per Structure |  |  Constructed as per R53-GCW-ITP  Backfilled after 14 days of placing the concrete or when the 28 day compressive strength is achieved, whichever achieved earlier  Insitu curtain walls at the outer edge of the aprons are only for pipes between 300-1200mm diameter |  | R11.4.7 R11.4.7.3 | [5 empty] | R53-GCW Lots |  |  | IP |  | Site Foreman
28 |  | Verify that the finished drainage structures are within tolerance, check pipe gaps over joints are within allowance |  |  | Per Structure |  |  Within ± 200 mm longitudinally  Within ± 20mm laterally  Within ± 20mm of design invert level |  | R11.5 Table R11.4 | [5 empty] | Survey Report |  |  | SU |  | Site Engineer
29 |  | Install rung ladders if pits are > 600mm deep |  |  | Per Pit |  |  Top of uppermost rung < 600mm below the top of the pit.  Top of Bottom Rung is within 300 to 500mm above the invert of the pit.  Rung spacing is 300±50mm |  | R11.4.7.4 | [5 empty] | Verification Checklist |  |  | IP |  | Site Engineer
30 |  | Patch grout around pipes recesses as required |  |  | Per Structure |  |  Cementitious grout is placed evenly covering the entire recess of the pipe-pit connections if any |  | DRA-CMS | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
31 |  | Install weepholes in headwalls and wingwalls, if provided |  |  | Per Structure |  |  Material placed to height ≥ 450mm above the bottom of the weephole over a plan area ≥ 600mm along the wall by 300mm out from the wall (Located centrally of the weephole)  Enclosed it with geotextile filter fabric |  | R11.4.8 R63 | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
32 |  | Place scour protection / dissipator, if required |  |  | Per Outlet Structure |  |  Scour protection and installation of dissipater completed as details specified in design documentations |  | Design DWGS | [5 empty] | Verification Checklist |  |  | IP |  | Site Foreman
33 |  | Backfilling
34 |  | Place and spread haunch, side zone, overlay and backfill, compact and test to specified densities |  |  | Per Lot Q6/L |  |  Backfill placed in 150mm layers and compact to 95% std compaction (102% if within SMZ)  Testing frequency refer to Q6/L3.1 (every layer if within SMZ)  If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around pipe and the placed stabilised materials are firm a day after placement. Working time to be noted.  Stabilised sand not exempt from T166 in accordance with R11  Working times of stabilised sand should be considered (T147) |  | R11.4.9.1 TfNSW Q6 Annexure Q/L Q6 8.1.1 |  |  |  | T166 T120 T147 |  | Test Report |  |  | TP |  | Site Engineer
| 35 |  | CCTV Inspection |  |  | Per Line |  |  CCTV inspection of installed drainage completed after backfill of drainage line but before placement of pavements  Video footage and report in accordance with WSA05-2008 |  | R11.5.2 | [5 empty] | CCTV Report |  |  | IP |  | Site Engineer
| 36 |  | Moving heavy construction plant or vehicles over pipe or box culvert structures. |  |  | Per Location |  | Provide a certificate and verification of protective measures. |  | R11.4.11 | [5 empty] | Hold Point |  |  | HP |  | Site Engineer |  | = |  | HP
| 37 |  | Covering up of work subject to a conformity verification survey. |  |  | Per Lot |  | Survey Report verifying conformity. |  | G71.5.6.6 |  |  |  | Survey |  | Hold Point |  |  | SU |  | Surveyor |  |  |  | HP
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Project Verifier | [6 empty] | IP | Inspection point | [5 empty] | Formal Inspection to be done and recorded
| HP* |  | FH Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP | Test Point | [5 empty] | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Project Verifier | [6 empty] | SU | Survey conformance point | [5 empty] | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Project Verifier | [6 empty] | SC | Survey Check
Notes