## Table 1
[7 empty] | Inspection and Test Plan – General Fill | [18 empty] | Doc ID: R44-FIL-ITP
Client: Iluka Resources Limited | [17 empty] | Prepared By: Simon Welsh | [7 empty] | Date: 15/10/2024
Project: Public Roads Upgrade | [17 empty] | Reviewed By: Joshua Kliemnt | [7 empty] | Date: 11/11//2024
Construction Process: General Fill | [17 empty] | Approved By: Simon Jaworksi | [7 empty] | Date: 11/11//2024
Specifications: ETS100, 101, 102
Structure / Component:
Item No. |  | Task/Activity Description |  |  | Inspection/Test | [15 empty] | Type |  | Responsibility |  | Checked/Verified by (initial/Date):
[5 empty] | Frequency |  | Acceptance Criteria | [5 empty] | Reference Documents |  |  | Inspection / Test Method |  |  | Record of conformity | [5 empty] | TfNSW |  | Fulton Hogan |  | PV | Date
1 |  | Preliminary
2 |  | Verify Embankment Foundation treatment has been completed and is conforming |  |  | Per Lot |  | Refer to Embankment Foundation and Embankment Treatment LOTs | [5 empty] | R44.3 | [5 empty] | Foundation Verification Checklist/s |  | IP |  | Site Engineer
3 |  | Set out the works |  |  | Each Section |  | Establish Pegs (or equivalent) to identify the extend of filling | [5 empty] | Design DWGs Survey Management Plan | [5 empty] | Verification Checklist |  | IP |  | Surveyor
4 |  | Verify conformance of general fill material |  |  | As required |  | Material free from tree stumps, roots & refuse, moisture content deems acceptable | [5 empty] | R44.5.2.1 R44/L.2 |  |  | Visual |  |  | Verification Checklist |  | IP |  | Site Engineer
[7 empty] | Max. Layer Thickness (mm) |  | Min. Qty Rock (Vol) | Max. Rock Size (mm) |  | % Passing AS37.5m m Sieve
[7 empty] | 300 |  | Not specified | 200 |  | > 60%
[7 empty] | 500 |  | 25% > 200mm | 300 |  | > 60%
[5 empty] | 5 per 25000m3 |  | Imported General Fill Material: - CBR(10 Day) >2 - PI<30 | [5 empty] | T117 T109
5 |  | Placing General Fill in 500mm Layers |  |  | Per Source |  | Undertake a trial for each material source to prove construction methodology. - Provide Proposed Method prior to undertaking trial - Provide compaction results from trial for HP Release - Only applicable to general fill at least 600mm below bottom of UZF | [5 empty] | RFI-073 |  |  | T166 |  |  | Hold Point |  | HP |  | Site Engineer |  | HP
6 |  | Construction
7 |  | Place, spread fill material (parallel to the grade), compact and test to specified densities |  |  | Per Lot, Q6/L3.1 |  |  98% Std compaction (90% for earth mounds or spoil) with 60 - 90% of OMC  Minimum layer thickness after compaction ≥ 100mm  Maximum layer thickness after compaction <= 300mm unless otherwise approved  Ensure insitu sampling and testing for compaction conformity is undertaken in accordance with TfNSW Q6 Annexure L | [5 empty] | R44.5.1.3 R44.5.2.2 R44.7.2 R44.7.3 R44.7.4 R44/A5 |  |  | T166 |  |  | Test Report |  | TP |  | Site Engineer
| 8 |  | For hill side embankment foundation, terrace 1m wide of the hill side of embankment and ensure its free draining |  |  | Per Lot |  | Minimum Step Depth |  |  | Slope |  |  | R44.3.3 Fig R44.4 | [5 empty] | Verification Checklist |  | IP |  | Site Engineer
[8 empty] | 600mm |  |  | > 4H:1V
[8 empty] | 300mm |  |  | < 4H:1V
Terraces not required on slopes < 10H:1V
| 9 |  | Conduct Deflection Testing – Proof rolling Method within 1.5m underside of SMZ |  |  | Per Lot |  |  Must not exhibit deformation, yielding and/or show signs of distress or instability.  All embankment layers and other surface within 1.5m of underside of SMZ  With refer to RFI 436: Clause 3, Note B on T198 states that other equipment may be used, 1. Benkelman Beam truck (as per T160) 2. Loaded bogie truck 3. 12M Grader (or larger 4. 12t Roller (or larger) | [5 empty] | R44.7.6.1 |  |  | T198 |  |  | Witness Point |  | WP |  | Site Engineer |  |  |  | WP
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Project Verifier | [10 empty] | IP | Inspection point | [5 empty] | Formal Inspection to be done and recorded
| HP* |  | FH Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [10 empty] | TP | Test Point | [5 empty] | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Project Verifier | [10 empty] | SU | Survey conformance point | [5 empty] | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Project Verifier | [10 empty] | SC | Survey Check
Notes