## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 1 - Erosion & Sediment Control | itp |  |  |  |  | ITP 1 - Erosion & Sediment Control
section | 1 - Preliminary
checkpoint | 4 - Prepare a Environmental Control Plan (ECP) for the work area
label | FREQUENCY - Per Site
label | ACCEPTANCE CRITERIA - Prepare an ECP as well as the environmental risk sessement
label | REFERENCE DOCUMENTS - EMP
label | INSPECTION / TEST METHOD - Visual
label | RECORD OF CONFORMITY - Hold Point
label | IP
label | RESPONSIBILITY - PE
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Install Erosion and Sediment Controls
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Installed in accordance to the approved progressive ESCP and guided by the BLUE BOOK.
label | REFERENCE DOCUMENTS - EMP
label | INSPECTION / TEST METHOD - Visual
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - PE
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 2 - Clearing and Grubbing | itp |  |  |  |  | ITP 2 - Clearing and Grubbing
section | 1.0 - Preliminary
checkpoint | 1.01 - Prepare and submit EWMS for Clearing and Grubbing
label | FREQUENCY - Once
label | ACCEPTANCE CRITERIA - EWMS prepared & submitted to the Principal and any other relevant agencies at least 14 working days prior to the commencement of clearing works.
label | ○ Proposed changes to EWMS must be advised to TfNSW at least 14 days working days prior to being implemented.
label | REFERENCE DOCUMENTS - G36.3.2.4 & BMP Appendix A
label | RECORD OF CONFORMITY - Verification Checklist
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 1.02 - Prepare and submit Weed Management Plan
label | FREQUENCY - Once
label | ACCEPTANCE CRITERIA - Prepared & submit to the Principal a Weed Management Sub-Plan together with written notice that areas of weed infestation identified in the Ecologist/Weed Inspector’s report (Clause 2.4a) are marked, at least ten working days before starting any clearing.
label | REFERENCE DOCUMENTS - G40.6 & BMP Appendix F
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Working in or near Environmentally Sensitive Areas
label | FREQUENCY - Per Sensitive Area
label | ACCEPTANCE CRITERIA - At least 5 working days prior to commencing Physical Work on Site in or near an environmentally sensitive area, provide to the Principal a copy of the EWMS for working in or near the environmentally sensitive areas & written notice that the environmentally sensitive areas are clearly delineated with locations and boundaries signposted.
label | REFERENCE DOCUMENTS - G36.4.13
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Submission of PESCP for area to be cleared
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Drawings prepared progressively for sections of the Site where work is to commence.
label | ○ Submit PESC drawing(s) to the TfNSW Representative at least ten working days before disturbance of the surface of the section of the Site.
label | REFERENCE DOCUMENTS - G38.3.1.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Check location of underground & above ground utilities
label | FREQUENCY - Per area / activity
label | ACCEPTANCE CRITERIA - Dial Before You Dig contacted
label | ○ Ground Penetration Permit is obtained
label | ○ Working near Overhead Services permit is obtained
label | REFERENCE DOCUMENTS - WHSMP
label | RECORD OF CONFORMITY - Ground Penetration & Overhead Services Permits
label | AP
label | RESPONSIBILITY - Utilities Engineer
date | Date Completed:
checkpoint | 1.06 - Install delineation for clearing limits & sensitive areas / no-go zones with highly visible continuous barrier or tape
label | FREQUENCY - Per area as Per TfNSW BG Guide 2: Exclusion zones
label | ACCEPTANCE CRITERIA - At least 5 days prior to proposed commencement of clearing install highly visible markers such as bunting, nightline or other similarly robust and durable materials on each side of road formation, bridges and ancillary facilities as shown on the design drawings in a continuous line.
label | ○ Demarcate & implement exclusion zone in accordance with Biodiversity Guidelines – protecting and managing Biodiversity of TfNSW projects, Guide 2: exclusion zones (RMS 2011).
label | ○ Verify exclusion zones & no-go areas have been marked out by surveyor and installed fencing & signage is in accordance with G36 CL4.13 on the project work side to exclude all access for the duration of construction works.
label | ○ Areas within the assessed areas that do not need to be cleared to provide for construction activities are to be included as part of the exclusion areas and fenced accordingly
label | REFERENCE DOCUMENTS - G40.2.4, G36.4.8, G36.4.13, TPP & TfNSW BG Guide 2
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 1.07 - Engage Ecologist to conduct a pre-clearing assessment
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Assessment done at least 5 days prior to commencing any clearing works.
label | The inspection report must:
label | (a) includes a statement from a suitably qualified Ecologist that identifies the species & location of any weeds growing anywhere in the road reserve over the length to be cleared and grubbed;
label | (b) includes a map clearly showing vegetation boundaries, and exclusions / no-go zone, identifies all locations of threatened flora species and trees which have been marked or otherwise identified for preservation; and,
label | (c) list any trees identified by a suitably qualified arborist outside the limits of clearing which are unsound and likely to fall upon the roadway or onto private property.
label | REFERENCE DOCUMENTS - G36.4.8, G40.2.4 & & TfNSW BG Guide 4
label | RECORD OF CONFORMITY - Ecologist Report
label | AP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 1.08 - Notification for clearing any work area
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Notify the Principal of intention to clear & provide Clearing and Grubbing Plan (Annexure G40/D) and report on the presence of weeds and unsound trees together with written notice that limits of clearing and areas of weed infestation identified in the ecologist report (Clause 2.4 (a) are marked), at least five (5) days before starting any clearing.
label | REFERENCE DOCUMENTS - G40.2.4 & BMP
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.09 - Site walk-over with Principal to confirm clearing boundaries
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Undertake a site walk-over with the Principal and appropriate site personnel to confirm clearing boundaries and sensitive location before the start of work.
label | ○ Ensure there is no clearing outside the agreed boundaries without the prior approval of the Principal.
label | REFERENCE DOCUMENTS - G40.2.1, G40.2.4 & G36.4.8
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Foreman / Site Engineer
date | Date Completed:
checkpoint | 1.10 - Inspect the site for potential fauna habitat features
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - At least one week before commencing clearing of native vegetation, engage a qualified ecologist to inspect the site for potential fauna habitat features including vegetation, leaf litter and existing culverts.
label | ○ If any threatened fauna species are found, inform the Principal & arrange to have the threatened fauna species relocated by a qualified ecologist in accordance with a relocation plan that is acceptable by the Principal and in accordance with relevant statutory requirements.
label | ○ Obtain all necessary approvals prior to relocation of fauna
label | REFERENCE DOCUMENTS - G40.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 1.11 - Relocation of any threatened fauna species
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Relocation of any threatened fauna species in accordance with your approved relocation plan and any associated permits/approvals.
label | ○ Keep records of all fauna rescue events, including locations to where fauna have been relocated.
label | REFERENCE DOCUMENTS - G40.2.4
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 1.12 - Induction training for limits of vegetation clearing & weeds present on site
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Ensure all workforce team are informed of the limits of vegetation clearing and the areas of vegetation to be retained and working adjacent to sensitive locations.
label | ○ Ensure all site staff are made aware of the Noxious Weeds present on-site and requirements related to the listing under the Noxious Weeds Act 1993.
label | REFERENCE DOCUMENTS - G36.4.13 & G40.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
section | 2.0 - Weed Treatment
checkpoint | 2.01 - Remove weed infestation
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Weeds removed & disposed of in accordance with requirements of Council & details in the WRMP
label | ○ Removal & disposal of weeds growing in the road reserve outside the area to be cleared and grubbed may be directed by the Principal as a Variation.
label | REFERENCE DOCUMENTS - G40.2.4, G36.4.12 & WARMP
label | RECORD OF CONFORMITY - Pesticide Application Record
label | IP
label | RESPONSIBILITY - Environment al Rep.
date | Date Completed:
section | 3.0 - Clearing & Grubbing
checkpoint | 3.01 - Mark out the areas of formation
label | FREQUENCY - Every 10m
label | ACCEPTANCE CRITERIA - Unless shown otherwise on Drawings or restricted by exclusion zones, the area to be cleared for the formation is that which will be occupied by the completed formation plus a clearance of up to 4 m beyond tops of cuts and toes of embankments where the natural fall of the ground is towards the roadway and up to 2 m beyond the tops of cuts and toes of embankments where the natural fall of the ground either slopes away from roadway or is level provided that the cleared area does not extend beyond the road reserve or private property boundaries.
label | ○ Also, clear areas to be occupied by utility adjustment works & ancillary earth features on design dwgs, inc. sediment basins & traps, open drains and diversion banks.
label | REFERENCE DOCUMENTS - G40.2.1, G40.2.3, G40.2.4 & G71.5.1.1
label | RECORD OF CONFORMITY - Verification Checklist
label | SCP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 3.02 - Mark out areas to be cleared for Bridges
label | FREQUENCY - Per Bridge
label | ACCEPTANCE CRITERIA - At bridges all trees & stumps and all built structures must be removed within Annexure G40/A areas, except:
label | – where shown otherwise on the Design drawings; or
label | – marked to be preserved; or,
label | – within 5m of the bank of any stream or waterway.
label | ○ Trees outside this area but having branches overhanging the bridge must have these lopped to 3m clear of bridge.
label | REFERENCE DOCUMENTS - G40.2.3
label | RECORD OF CONFORMITY - Verification Checklist
label | SCP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 3.03 - Obtain internal Pre-clearing Permit
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Permit is obtained from the Environmental Manager or environmental delegate.
label | ○ Works Supervisor to review document.
label | ○ Ensure ‘PART D. APPROVAL’ is signed-off by all parties.
label | REFERENCE DOCUMENTS - BMP Appendix B
label | RECORD OF CONFORMITY - Permit
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3.04 - Prior to commencement of clearing ensure surveyor has checked exclusion zones & no-go areas
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - The location of clearing limit delineations have been checked and verified as correct by the project surveyor.
label | ○ All areas have been fenced off in accordance with G36 Clause 4.13 requirements and the Tree Protection Plan
label | REFERENCE DOCUMENTS - G40.2.4, G36.4.13 & TPP
label | RECORD OF CONFORMITY - Verification Checklist
label | SC
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 3.05 - Install erosion and sedimentation controls
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Before commencing clearing & grubbing all soil erosion and sedimentation controls required for C&G must be installed as per TfNSW G38.
label | ○ Insure these are installed in accordance with the approved area PESCP.
label | REFERENCE DOCUMENTS - G40.2.4 & G38.3.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 3.06 - Carry out clearing works
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Remove any rubbish on the Site prior to starting Work
label | ○ The method of clearing, the extent and sequencing of clearing must be in accordance with Guide 4: Clearing Vegetation and Bush Rock of the Biodiversity Guidelines: Protecting and managing biodiversity on TfNSW projects.
label | ○ Trees remaining within the road reserve, but outside limits of clearing, which the Principal has agreed to be unsound and are likely to fall upon the roadway or onto private property, must be cleared or pruned as per AS 4373.
label | ○ Any branch, overhanging the road formation, must be cut back flush with the tree trunk in accordance with AS 4373.
label | ○ Existing trees, grasses & other ground cover must be retained within 15 m of rivers, creeks, watercourses and in all drainage lines until immediately before construction commences in the area.
label | ○ An access track may be constructed across these areas on an alignment that will minimise erosion.
label | ○ Where existing ground cover is to be retained, all trees in these areas must be felled manually, leaving grasses and small understorey species wherever possible.
label | ○ Trees within 10 m of the bridge centreline and within 5 metres of the bank of any stream or other waterway must be cleanly cut off between 300 mm and 600 mm above the adjacent ground level so that stable vegetation is retained on the banks. This work must be undertaken in consultation with the Principal.
label | REFERENCE DOCUMENTS - BMP Appendix A G36.4.8, G40.2.1, G402.2, G40.2.3 & G40.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3.07 - Clearing in areas with bushland topsoil
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Where tree density does not allow effective slashing or the stripping of bushland topsoil remove trees and stumps in a manner that does not mix sub soil with bushland topsoil. Slash the understorey to within 50mm of ground level, leaving the slashed trash insitu.
label | REFERENCE DOCUMENTS - R178.2.1.1
label | RECORD OF CONFORMITY - Site Inspection Report / Verification Checklist
label | IP
label | RESPONSIBILITY - Environment al Scientist / Engineer
date | Date Completed:
checkpoint | 3.08 - Clearing of built structures
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Built structures, including stormwater drainage systems and concrete paving inc. roundabouts, medians & footpaths other than those marked or identified for preservation, must be completely removed, inc. footings.
label | ○ Built structures which are discovered during clearing & grubbing are to be retained until the Principal authorises their removal.
label | ○ Excavations must be backfilled with surplus material from excavations or other material acceptable to the Principal & compacted in accordance with R11.4.9.
label | REFERENCE DOCUMENTS - G40.2.5
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 3.09 - Carry out grubbing works
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - All trees & stumps, on or within the limits of clearing defined in G40 Cl’s 2.1, 2.2 and 2.3, which are unable to be felled and removed by clearing methods must be removed by grubbing
label | ○ Grubbing to be carried out to a depth of 0.5m below natural ground level and 1.5m below top of select material zone.
label | REFERENCE DOCUMENTS - G40.3
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Forman
date | Date Completed:
checkpoint | 3.10 - Fill holes after grubbing
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Holes remaining after trees & stumps have been grubbed and redundant drainage, and other structures removed must be backfilled promptly with sound material to prevent the infiltration and ponding of water. Backfilling material must be compacted to at least the relative compaction of the material existing in the adjacent ground.
label | ○ If the holes are outside the formation (refer to G40.2.2), the final 50mm of backfilling must be topsoil and surface vegetated within 7 days of removal of the stump and comply with TfNSW Spec R178
label | REFERENCE DOCUMENTS - G40.3
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
section | 4.0 - Production & Stockpiling of Mulch
checkpoint | 4.01 - Mulch
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Native trees removed during clearing & grubbing may be used in conjunction with soil ESC measures.
label | ○ All other native trees removed must be converted to mulch & stockpiled for use during landscape planting under the Contract. Subject to the following constraints:
label | (a) Where native vegetation on Site is insufficient to provide quantities of mulch needed during landscape planting, all native trees removed during clearing and grubbing must be mulched and stockpiled. Under no circumstances must the extent of clearing and grubbing be extended or weeds or exotic species used to make up any shortfall of mulch;
label | (b) Where the quantity of mulch produced exceeds the quantity required under the Contract, the excess mulch must be removed from the Site.
label | REFERENCE DOCUMENTS - G40.4.1, G40.4.2, G40.5 & G36.4.8
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | 4.02 - Mulch Stockpiles
label | FREQUENCY - Per Cleared Area
label | ACCEPTANCE CRITERIA - Ensure all much stockpiles are within designated areas.
label | ○ If stockpile site not shown on the Drawings, submit an application to the Principal ≥ 10 working days prior to commencement of stockpiling. State the max dimensions of the proposed stockpile in application.
label | ○ Stockpile sites must be located away from drainage lines & watercourses and must be arranged to minimise damage to natural vegetation & trees. Position stockpile so material may be transported away at any time.
label | ○ Temporary erosion and sediment control measures installed as required.
label | ○ Stockpiles must be monitored and turned over as required to avoid spontaneous combustion.
label | ○ Ensure risk of tannin leachate from mulch is controlled in accordance with site stockpile procedure.
label | REFERENCE DOCUMENTS - G40.4.2 & G38.3.6
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
section | 5.0 - Disposal of Materials
checkpoint | 5.01 - Waste Disposal
label | FREQUENCY - Per Cleared Area
label | ACCEPTANCE CRITERIA - All materials cleared, pruned and grubbed and redundant drainage, concrete structures (including concrete median and concrete pavement) removed in in accordance with G40 to be removed from the site for recycling or disposal.
label | ○ Disposal must be in accordance with your Waste Management Plan.
label | REFERENCE DOCUMENTS - G40.2.5, G40.5, G36.4.11.4 & WARMP
label | RECORD OF CONFORMITY - Waste Register
label | IP
label | RESPONSIBILITY - Environmental Rep.
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 3 - Stormwater Drainage | itp |  |  |  |  | ITP 3 - Stormwater Drainage
section | 1 - Preliminary
checkpoint | 2 - Check location of underground and above ground utilities
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Before You Dig contacted
label | ○ Excavation Permit is obtained
label | REFERENCE DOCUMENTS - WHSMP
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Check the type, size and class of pipes and other drainage structures to be laid
textbox | Size:
textbox | Class:
label | FREQUENCY - Per Delivery
label | ACCEPTANCE CRITERIA - Supplied items are:
label | ○ To correct spec, class, size and quantity
label | ○ Defect free, safely and securely stored
label | ○ Markings have been made as required
label | ○ Delivered 7 days after casting and concrete has reached specified 28 day strength
label | REFERENCE DOCUMENTS - R11.2
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Supply of precast concrete members subject to traffic and/ or earth pressure loading, and water containing structures with capacity greater than 25,000 Litres
label | FREQUENCY - Per Type
label | ACCEPTANCE CRITERIA - Submitted design and manufacturing documentations to the Project Verifier for precast concrete structures which subject to traffic loads and/or earth pressure and water retaining structures with a capacity in excess of 25,000 litres.
label | REFERENCE DOCUMENTS - R11.2.4.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Incorporation into the works any supplied, manufactured drainage product.
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Submit a Certificate of Conformity to the Project Verifier 7 days prior to incorporating into the works
label | REFERENCE DOCUMENTS - R11.2.6
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Verify conformance of BH (bedding & haunch) materials
textbox | Material Conformance Lot:
label | FREQUENCY - G:1/50m³ PI:/100m³
label | ACCEPTANCE CRITERIA - Grading limits as per Table 6 in AS 3725 except that ≤12% passing 75µm & PI < 6
label | REFERENCE DOCUMENTS - R11 3.1.1 R11/L Q6 8.1.1
label | INSPECTION / TEST METHOD - T201 T109
label | RECORD OF CONFORMITY - NATA Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 7 - Verify conformance of SO (side & overlay) materials
textbox | Material Conformance Lot:
label | FREQUENCY - G:1/50m³ PI:/100m³
label | ACCEPTANCE CRITERIA - Max size 53mm, grading within limits in Table 7 of AS 3725 and PI >2 and < 12
label | REFERENCE DOCUMENTS - R11 3.1.2 R11/L Q6 8.1.1
label | INSPECTION / TEST METHOD - T201 T109 AS 3725
label | RECORD OF CONFORMITY - NATA Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 8 - Verify conformance of material Adjacent to Weepholes
label | FREQUENCY - Per Delivery
label | ACCEPTANCE CRITERIA - Broken stone or river gravel of max size 53mm and < 5% passing 9.5mm sieve
label | REFERENCE DOCUMENTS - R11 3.2 R11/L
label | INSPECTION / TEST METHOD - T201
label | RECORD OF CONFORMITY - NATA Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 9 - Subsurface drainage pipes
label | FREQUENCY - Per Delivery
label | ACCEPTANCE CRITERIA - Provide certificate of compliance accompanied by NATA certified test results in accordance with TfNSW 3552 not more than 6 months old
label | REFERENCE DOCUMENTS - R11.4.4.5 TfNSW 3552
label | INSPECTION / TEST METHOD - T1505 T1506
label | RECORD OF CONFORMITY - Certificate of Conformity
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 10 - Inspect supplied items upon delivery
label | FREQUENCY - Per Delivery
label | ACCEPTANCE CRITERIA - Supplied items are to correct spec, class, size and undamaged Steel Reinforced Pipes as per CL3.3 & 3.4 of AS4058 Fibre Reinforced Pipe as per CL9 & 10 AS4139
label | REFERENCE DOCUMENTS - QMP
label | RECORD OF CONFORMITY - Receiving Inspection Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 11 - Trenching and Excavation
checkpoint | 12 - Construction of each drainage system (1)
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Set out the stormwater drainage systems as shown on the drawings in sufficient detail to identify:
label | – the locations, lengths and levels at outlets and inlets of pipes and box culvert structures;
label | – the locations and levels of gully pits, junction boxes, energy dissipaters, and inlet and outlet structures;
label | – the locations and levels of the ends of wing walls and headwalls; and
label | – the locations and levels of open drains.
label | ○ Notify PV that set out of drainage system has been completed.
label | REFERENCE DOCUMENTS - R11.4.1.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Construction of each drainage system (2)
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - If set out is within 5 metres of an environmental sensitive area notify Environmental Manager
label | REFERENCE DOCUMENTS - G36.4.12
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Excavate trench to the underside of bedding to correct width
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Width and depth of pipe trench as per AS 3725 and standard drawings, refer to right table
label | ○ For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater
label | ○ Trenches > 1.5m deep are either shored or benched
label | ○ The excavation is ≤ 50mm beyond the specified width and depths of the trench
label | ○ For pipes under embankments
label | – “Embankment Condition”: embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe
label | – “Trench Condition”: Trenches done after the construct of the embankment to the level of the underside of the Selected Material Zone
label | REFERENCE DOCUMENTS - R11.4.3 MD.R240-01
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 14 - Foundation Compaction
label | FREQUENCY - Q6/L
label | ACCEPTANCE CRITERIA - Foundation to be compacted to 95%. (Standard compaction)
label | REFERENCE DOCUMENTS - R11.4.9.2 R11.4.9.3 Q6 8.1.1
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 15 - Excavation for pipe installation and other drainage structures
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notify the Project Verifier of the anticipated date of completion of excavation and preparation of foundations.
label | ○ Not later than 24 hours, but not earlier than 5 working days.
label | ○ GDR to provide Geo-report to state that the foundation is suitable or need further treatment
label | REFERENCE DOCUMENTS - R11.4.3
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 16 - Remove & replace unsuitable materials, if directed by PV
label | FREQUENCY - Where required Q6/L
label | ACCEPTANCE CRITERIA - Replace with materials from cuttings or conforming material to full depth in 150mm layers and compact to 95% Standard Compaction
label | REFERENCE DOCUMENTS - R11.4.3 Q6 8.1.1
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 17 - Replacement of inadequate foundation material.
label | FREQUENCY - Where required
label | ACCEPTANCE CRITERIA - Notification to the Project Verifier that inadequate foundation material has been excavated to the extent required.
label | REFERENCE DOCUMENTS - R11.4.3.3
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 18 - Placement of Pipes
checkpoint | 19 - Place Bedding
label | FREQUENCY - Q6/L
label | ACCEPTANCE CRITERIA - Bedding placed to a thickness of 100mm for pipes up to 1200mm dia pipes and 150mm for pipes greater than 120mm
label | ○ Bedding compacted to 95%
label | REFERENCE DOCUMENTS - R11 R240-01
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 20 - Install pipes in accordance to manufacturer’s instructions and design documentations
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Correct size and class of pipe installed
label | ○ Pipes laid from inlet to outlet with socket laid upstream
label | ○ Pipe support are Type HS3 conforming to AS3725 and MD R240-01
label | ○ Pipe ends cleaned and rubber rings correctly installed
label | ○ Where grade exceed 20%: anchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings
label | ○ 100mm dia Subsurface drainage installed at the discharge end of pipes 3m long, laid beside & 100mm above invert level of drainage pipe
label | ○ All joints have rubber rings fitted and pipes butting against each other.
label | ○ Connection to pits in accordance with MD R220-43
label | REFERENCE DOCUMENTS - R11.4.4 R240-01 R220-43
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 21 - Pit/headwall to pipe connection
label | FREQUENCY - Per connectio n
label | ACCEPTANCE CRITERIA - Pit to pipe connections are to be flush along the pit wall, with minimal protrusions or depressions.
label | REFERENCE DOCUMENTS - CMS 7.8
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 22 - Verify that completed pipeline against survey marks
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Completed pipeline is inline and within ±200mm of location (plan)
label | ○ Invert level are within 20mm of the design level at any point
label | ○ To be checked at each pit and headwall
label | REFERENCE DOCUMENTS - R11.5.1 Table R11.4
label | RECORD OF CONFORMITY - Survey Report
label | SC
label | RESPONSIBILITY - Surveyor
date | Date Completed:
section | 23 - Construction of Drainage Structures (Other Than Pipes and Box Culverts)
checkpoint | 24 - Construction of drainage structures other than pipes and box culverts.
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - The notification is to be at least 7 days prior to the date of installation work.
label | REFERENCE DOCUMENTS - R11.4.7.2
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 25 - Place bedding layer underneath pit, or plain concrete blinding to headwalls. Ensure correct survey tools have been used to transfer levels, i.e. dumpy level
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - The bedding materials consists either of:
label | ○ For Precast Pits 50mm layer DGB20 or CLSM; For other than precast a 50mm blinding layer
label | REFERENCE DOCUMENTS - R11.4.7.2
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 26 - Install precast drainage structures as specified on design documentations
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Installed within 14days after installation of associated pipes, box culverts or open drains
label | ○ Where drainage structure abuts a structure or concrete pavement, a 10mm wide filler complying with TfNSW 3204 is installed as an isolation joint
label | ○ Subsoil drainage pipe connected to downstream headwalls/pits
label | ○ Lifting holes are sealed
label | ○ Structure is level and plumb
label | REFERENCE DOCUMENTS - R11.4.7
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 27 - Install Cast In place drainage structures (incl. headwalls and curtain walls) as shown on design documentations
textbox | R53-GCW Lot No:
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Constructed as per R53-GCW-ITP
label | ○ Backfilled after 14 days of placing the concrete or when the 28 day compressive strength is achieved, whichever achieved earlier
label | ○ Insitu curtain walls at the outer edge of the aprons are only for pipes between 300-1200mm diameter
label | REFERENCE DOCUMENTS - R11.4.7 R11.4.7.3
label | RECORD OF CONFORMITY - R53-GCW Lots
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 28 - Verify that the finished drainage structures are within tolerance, check pipe gaps over joints are within allowance
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Within ± 200 mm longitudinally
label | ○ Within ± 20mm laterally
label | ○ Within ± 20mm of design invert level
label | REFERENCE DOCUMENTS - R11.5 Table R11.4
label | RECORD OF CONFORMITY - Survey Report
label | SU
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 29 - Install rung ladders if pits are > 600mm deep
label | FREQUENCY - Per Pit
label | ACCEPTANCE CRITERIA - Top of uppermost rung < 600mm below the top of the pit.
label | ○ Top of Bottom Rung is within 300 to 500mm above the invert of the pit.
label | ○ Rung spacing is 300±50mm
label | REFERENCE DOCUMENTS - R11.4.7.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 30 - Patch grout around pipes recesses as required
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Cementitious grout is placed evenly covering the entire recess of the pipe-pit connections if any
label | REFERENCE DOCUMENTS - DRA-CMS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 31 - Install weepholes in headwalls and wingwalls, if provided
label | FREQUENCY - Per Structure
label | ACCEPTANCE CRITERIA - Material placed to height ≥ 450mm above the bottom of the weephole over a plan area ≥ 600mm along the wall by 300mm out from the wall (Located centrally of the weephole)
label | ○ Enclosed it with geotextile filter fabric
label | REFERENCE DOCUMENTS - R11.4.8 R63
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 32 - Place scour protection / dissipator, if required
label | FREQUENCY - Per Outlet Structure
label | ACCEPTANCE CRITERIA - Scour protection and installation of dissipater completed as details specified in design documentations
label | REFERENCE DOCUMENTS - Design DWGS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
section | 33 - Backfilling
checkpoint | 34 - Place and spread haunch, side zone, overlay and backfill, compact and test to specified densities
label | FREQUENCY - Per Lot Q6/L
label | ACCEPTANCE CRITERIA - Backfill placed in 150mm layers and compact to 95% std compaction (102% if within SMZ)
label | ○ Testing frequency refer to Q6/L3.1 (every layer if within SMZ)
label | ○ If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around pipe and the placed stabilised materials are firm a day after placement. Working time to be noted.
label | ○ Stabilised sand not exempt from T166 in accordance with R11
label | ○ Working times of stabilised sand should be considered (T147)
label | REFERENCE DOCUMENTS - R11.4.9.1 TfNSW Q6 Annexure Q/L Q6 8.1.1
label | INSPECTION / TEST METHOD - T166 T120 T147
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 35 - CCTV Inspection
label | FREQUENCY - Per Line
label | ACCEPTANCE CRITERIA - CCTV inspection of installed drainage completed after backfill of drainage line but before placement of pavements
label | ○ Video footage and report in accordance with WSA05-2008
label | REFERENCE DOCUMENTS - R11.5.2
label | RECORD OF CONFORMITY - CCTV Report
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 36 - Moving heavy construction plant or vehicles over pipe or box culvert structures.
label | FREQUENCY - Per Location
label | ACCEPTANCE CRITERIA - Provide a certificate and verification of protective measures.
label | REFERENCE DOCUMENTS - R11.4.11
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 37 - Covering up of work subject to a conformity verification survey.
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Survey Report verifying conformity.
label | REFERENCE DOCUMENTS - G71.5.6.6
label | INSPECTION / TEST METHOD - Survey
label | RECORD OF CONFORMITY - Hold Point
label | SU
label | RESPONSIBILITY - Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 4 - Open Drains | itp |  |  |  |  | ITP 4 - Open Drains
section | Details
checkpoint | 1 - Type of open drain to be constructed: Vegetated Channel drain, Concrete Catch Drain, Concrete Channel Drain, LWQB
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - As indicated on design drawing
label | REFERENCE DOCUMENTS - Design DWGS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2 - Obtain and submit mix design documentation from concrete supplier for approval
textbox | R53-MIX Lot No:
textbox | Hold Point No:
label | FREQUENCY - Per Product/Per Supplier
label | ACCEPTANCE CRITERIA - N25 Concrete
label | ○ Concrete mix design submitted to the PV 7 days prior to construction verifying the concrete, constituent materials and curing compounds comply with R53 specification
label | REFERENCE DOCUMENTS - R53.1.4 Design DWGs
label | RECORD OF CONFORMITY - R53-GCW-Mix Lot’s
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Set out the works
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notification that set out of drainage system has been completed. The Nominated Authority will inspect the set out prior to authorising the release of the Hold Point.
label | ○ Set out the location and level of open drains as shown on the Design Drawings.
label | REFERENCE DOCUMENTS - R11.4.1.1 Design DWGs
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Excavation for Drainage Structures
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Excavate to dimensions shown on drawings. Where dimensions are not shown, excavate to:
label | ○ Min 300mm depth
label | ○ Min waterway of 0.2 m²
label | ○ Batter slope ≤ 2H:1V steep
label | ○ Have a grade slope of ≥1%
label | ○ Extend open drains as necessary to natural drainage depressions or to a drainage system.
label | REFERENCE DOCUMENTS - R11.4.2.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 5 - Construction of open drains with grade less than 1%.
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notification that 1% minimum grade cannot be achieved.
label | ○ The PV will consider the matter, and will direct you further, prior to authorising the release of the Hold Point.
label | REFERENCE DOCUMENTS - R11.4.2.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Inadequate Foundation Material
label | FREQUENCY - Per lot
label | ACCEPTANCE CRITERIA - Notification to the PV that inadequate foundation material has been excavated to the extent required.
label | ○ Replace inadequate foundation material with materials from cuttings, or with other conforming material, and compact to the requirements of Clause 4.9.2 of this Specification.
label | REFERENCE DOCUMENTS - R11 4.3.3 R11 4.9.2
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 7 - Trim and compact open drains
label | FREQUENCY - Per Lot Q6/L.3.1
label | ACCEPTANCE CRITERIA - Trim open drains to produce a uniform surface free of irregularities.
label | ○ Trimmed surface of excavated open drains to a depth of 150 mm, before placing lining or spreading topsoil for vegetation or fill material in embankments of open drains
label | ○ Min. Relative Compaction 95%
label | REFERENCE DOCUMENTS - R11.4.2.1 R11.4.9.2
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 8 - Line open drains with organic fibre mat (jute mesh) Lining
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Unless otherwise shown on the Design Documentation drawings, line open drains with Jute Mesh and vegetation where the longitudinal grade of the completed drain lies between 1% and 5% inclusive
label | ○ Minimum 75mm topsoil with Jute mesh lining and bitumen emulsion, refer to landscape Dwg for vegetation details
label | ○ Jute mesh is lined and pinned in accordance to manufacturer’s instructions
label | ○ Minimum 75mm topsoil
label | REFERENCE DOCUMENTS - R11.4.2.3
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 9 - Line catch drains with 100mm concrete, line Type C channel with 150mm concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Only if longitudinal grade is <1% or >5% or shown on the drawings
label | ○ Install 20±5mm deep grooved movement joints to prevent cracking at 90°±5° to line of drain and spaced @ 3m intervals
label | ○ Install expansion joint complying with D&C TfNSW 3204 & DR-01 Drawing Package for full depth spaced @ 12m intervals.
label | ○ Carry out foundation inspection with GDR and determine if dowel detail at expansion joints can be removed as per RFI 384.
label | ○ Concrete must be colour matched to surroundings
label | REFERENCE DOCUMENTS - R11.4.2.3 R11.4.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 10 - Inspection of formwork and reinforcement before placing concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The PV may inspect the completed reinforcement and formwork prior to concrete placement
label | ○ Before commencing placement of concrete, remove all dirt, and other foreign matter from the forms.
label | ○ Gaps which are to be filled with mortar must be free of all dirt and other foreign matter.
label | ○ Prepare revetment mattresses, which are to be filled with grout, in accordance with the manufacturer’s recommendations.
label | ○ Reference to RFI 384: DSGR to assess channel foundation if intending to remove the dowel sleeve from the concrete-lined channel expansion joint detail (refer RFI384) and, if required, confirmation of foundation suitability to be provided to PV prior to closure of this hold point.
label | REFERENCE DOCUMENTS - R53.6.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Placing of Concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notify the Project Verifier, not less than 24 hours and not more than 3 clear working days prior to the intended time of commencing to place concrete, mortar or grout, when fixing of the formwork and reinforcement in position (if applicable) will be completed and when concrete, mortar or grout will be placed.
label | REFERENCE DOCUMENTS - R53.6.1
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 12 - Curing the concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Only suitable curing compound used
label | ○ After initial set of concrete apply curing and cure for at least 7 days
label | ○ Curing compound applied according to manufacturer’s recommendations or at a spray rate min. 0.2L/m2
label | ○ Ensure all exposed surfaces receive a uniform cover of the curing compound.
label | REFERENCE DOCUMENTS - R53.7
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 13 - Construct rock lined channels
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Use rock mattresses only where shown on the Dwg. Rock mattresses must comply with Specification TfNSW D&C R55
label | ○ Width and height to dimensions shown on Drawings
label | ○ Place Geofabric as detailed
label | ○ Rocks are placed in such a way to ensure good mechanical interlock
label | REFERENCE DOCUMENTS - R11.4.2.3 R55
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 14 - Construct LWQB
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Place Geofabric as detailed
label | ○ Install Filter Media as detailed
label | ○ Drainage Layer Specification
label | REFERENCE DOCUMENTS - DR-01-0011
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 15 - Construct LWQB inlets and spillways
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Install Inlets and spillways as per drawings
label | REFERENCE DOCUMENTS - Design Drawings
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 16 - LWQB Install pipes and fittings
label | ACCEPTANCE CRITERIA - Install ELLIS Pipes as per schedule, uPVC
label | REFERENCE DOCUMENTS - Design Drawings
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 17 - LWQB Install Bitumen - Impregnated Dam board
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - For water resistant bitumen – impregnated damn board apply durable paint coating. Refer to paint manufacturer for suitable paint, durability and maintenance requirements (20 years durability) 4m Long, 230mm deep 18 mm thick.
label | REFERENCE DOCUMENTS - Design Drawings
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 18 - Construction tolerance & inspection
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Verify catch drains have been constructed to tolerance in table R11.4
label | ○ Level is within 50 mm of the design level at any point provided that there is a continuous downgrade in the direction of flow not less than 1% at any point.
label | ○ Waterway area is not less than 95% of the design cross sectional area at any point.
label | REFERENCE DOCUMENTS - R11.5.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 5 - General Fill | itp |  |  |  |  | ITP 5 - General Fill
section | 1 - Preliminary
checkpoint | 2 - Verify Embankment Foundation treatment has been completed and is conforming
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Refer to Embankment Foundation and Embankment Treatment LOTs
label | REFERENCE DOCUMENTS - R44.3
label | RECORD OF CONFORMITY - Foundation Verification Checklist/s
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Set out the works
label | FREQUENCY - Each Section
label | ACCEPTANCE CRITERIA - Establish Pegs (or equivalent) to identify the extend of filling
label | REFERENCE DOCUMENTS - Design DWGs, Survey Management Plan
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 4 - Verify conformance of general fill material (1)
label | FREQUENCY - As required
label | ACCEPTANCE CRITERIA -
label | – – – – – – – – – – – – – – –
label | Material free from tree stumps, roots & refuse, moisture content deems acceptable
label | Max. Layer Thickness (mm) ¦¦ Min. Qty Rock (Vol) ¦¦ Max. Rock Size (mm) ¦¦ % Passing AS3 7.5mm Sieve
label | – – – – – – – – – – – – – – –
label | 300 ¦¦ Not specified ¦¦ 200 ¦¦ > 60%
label | 500 ¦¦ 25% > 200mm ¦¦ 300 ¦¦ > 60%
label | – – – – – – – – – – – – – – –
label | REFERENCE DOCUMENTS - R44.5.2.1 R44/L.2
label | INSPECTION / TEST METHOD - Visual
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Verify conformance of general fill material (2)
label | FREQUENCY - 5 per 25000m3
label | ACCEPTANCE CRITERIA - Imported General Fill Material:
label | ○ CBR(10 Day) >2
label | ○ PI<30
label | REFERENCE DOCUMENTS - T117 T109
label | INSPECTION / TEST METHOD - Visual
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 5 - Placing General Fill in 500mm Layers
label | FREQUENCY - Per Source
label | ACCEPTANCE CRITERIA - Undertake a trial for each material source to prove construction methodology.
label | ○ Provide Proposed Method prior to undertaking trial
label | ○ Provide compaction results from trial for HP Release
label | ○ Only applicable to general fill at least 600mm below bottom of UZF
label | REFERENCE DOCUMENTS - RFI-073
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Construction
checkpoint | 7 - Place, spread fill material (parallel to the grade), compact and test to specified densities
label | FREQUENCY - Per Lot, Q6/L3.1
label | ACCEPTANCE CRITERIA - 98% Std compaction (90% for earth mounds or spoil) with 60 - 90% of OMC
label | ○ Minimum layer thickness after compaction ≥ 100mm
label | ○ Maximum layer thickness after compaction <= 300mm unless otherwise approved
label | ○ Ensure insitu sampling and testing for compaction conformity is undertaken in accordance with TfNSW Q6 Annexure L
label | REFERENCE DOCUMENTS - R44.5.1.3, R44.5.2.2 R44.7.2, R44.7.3 R44.7.4 R44/A5
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 8 - For hill side embankment foundation, terrace 1m wide of the hill side of embankment and ensure its free draining
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA -
label | – – – – – – – – – – – – – – –
label | Minimum Step Depth ¦¦ Slope
label | – – – – – – – – – – – – – – –
label | 600mm ¦¦ > 4H:1V
label | 300mm ¦¦ < 4H:1V
label | Terraces not required on slopes < 10H:1V
label | – – – – – – – – – – – – – – –
label | REFERENCE DOCUMENTS - R44.3.3 Fig R44.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 9 - Conduct Deflection Testing – Proof rolling Method within 1.5m underside of SMZ
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Must not exhibit deformation, yielding and/or show signs of distress or instability.
label | ○ All embankment layers and other surface within 1.5m of underside of SMZ
label | ○ With refer to RFI 436: Clause 3, Note B on T198 states that other equipment may be used,
label | 1. Benkelman Beam truck (as per T160)
label | 2. Loaded bogie truck
label | 3. 12M Grader (or larger
label | 4. 12t Roller (or larger)
label | REFERENCE DOCUMENTS - R44.7.6.1
label | INSPECTION / TEST METHOD - T198
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 6 - Construction of verges | itp |  |  |  |  | ITP 6 - Construction of verges
section | 1 - Preliminary
checkpoint | 2 - Survey pick up prior to place verge material, surveyor to save model file
label | FREQUENCY - Each Section
label | ACCEPTANCE CRITERIA - Establish Pegs or equivalent to identify the extent of verges
label | ○ Survey pick up prior to place verge material and save to model file
label | REFERENCE DOCUMENTS - R44/A1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
section | 3 - Materials
checkpoint | 4 - Verify compliance of materials to be used in verges
label | FREQUENCY - Each Stockpile
label | ACCEPTANCE CRITERIA - Grading of material imported for the verges must meet the requirements of TfNSW D&C 3071 for Selected Material Type B
label | ○ CBR4 ≥19
label | ○ PI between 6 to12
label | ○ Where safety barriers, posts, subsurface drainage or services are to be installed, particle size to be ≤100mm
label | ○ Minimum frequency of stockpile testing as per TfNSW D&C 3071 Annexure 3071/L
label | ○ Site won Verge material
label | – have a CBR and PI as stated in annexure R44/A2.2
label | – free from stone larger than 53mm max Particle dimension.
label | – have no less than 50% passing the 19.0mm
label | ○ Imported verge material
label | – have a characterised CBR and PI as stated in annexure R44/A2.2.
label | REFERENCE DOCUMENTS - R44.2.8.6.2 R44/A2.2 D&C 3071 Annexure 3071/L
label | INSPECTION / TEST METHOD - T106 T117 T09
label | RECORD OF CONFORMITY - EWKS-MAT Lot
label | IP
label | RESPONSIBILITY - Materials Engineer
date | Date Completed:
checkpoint | 5 - Obtain material approval to placement of material for the verges
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Submit a Hold Point to the Project Verifier that proposed location, quantities and type of material, and verification of conformity.
label | ○ Verification that all possible sources of the material within the site have been exhausted, if imported verge material is proposed.
label | REFERENCE DOCUMENTS - R44.6.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Construction
checkpoint | 7 - Place, spread and compact verge material
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Visual check material moisture content is acceptable
label | ○ Placed parallel to the grade line in 100 – 200mm layers
label | ○ 98% std compaction @ 60-90% OMC
label | ○ For verge adjoining to concrete pavement, placement only after 10 days of concrete pour and joints sealed
label | REFERENCE DOCUMENTS - R44.6.2 R44.7.2
label | INSPECTION / TEST METHOD - T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 8 - Completion
checkpoint | 9 - Trim the top of the verge layer to specified levels
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Tolerance to be within +0/-20mm of design
label | ○ Clear loose materials laying on the surface following the backfilling of the edge and outlet drains
label | REFERENCE DOCUMENTS - R44.7.7
label | INSPECTION / TEST METHOD - Survey
label | RECORD OF CONFORMITY - Survey Report
label | SC
label | RESPONSIBILITY - Survey
date | Date Completed:
checkpoint | 10 - Covering up of work subject to a conformity verification survey.
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Survey Report verifying conformity.
label | REFERENCE DOCUMENTS - G71.5.6.6
label | INSPECTION / TEST METHOD - Survey
label | RECORD OF CONFORMITY - Hold Point
label | SU
label | RESPONSIBILITY - Survey or
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 7 - General Concrete Works | itp |  |  |  |  | ITP 7 - General Concrete Works
section | 1 - Preliminary
checkpoint | 2 - Verify relevant Hold point for production of each concrete mix has been released
label | FREQUENCY - Per Product / per Supplier
label | ACCEPTANCE CRITERIA - Documents submitted to TFNSW Representative 7 days prior to production
label | ○ Verify that the concrete manufacturing plant operates under a quality system in accordance with ISO 9001
textbox | Hold Point No:
textbox | CON-MIX Lot No.:
label | REFERENCE DOCUMENTS - R53.1.4
label | RECORD OF CONFORMITY - CON-MIX Lots
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Submit Certificate of conformity for supply of curing compound, and proposed curing compound application methodology, for TFNSW approval
label | FREQUENCY - Per Supplier
label | ACCEPTANCE CRITERIA - The curing compound must be:
label | ○ A hydrocarbon resin compound complying with AS 3799 Type 1-D, or
label | ○ A bitumen emulsion complying with TFNSW 3254
label | ○ Develop a methodology for application of curing compound and submit to TFNSW Representative along with certificate of conformity
label | REFERENCE DOCUMENTS - R53.7.1 R53.7.3
textbox | RECORD OF CONFORMITY - iTWOcx Transmittal No.:
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Obtain Certificate of conformity for reinforcement supply
label | FREQUENCY - Per Supplier
label | ACCEPTANCE CRITERIA - Comply with either AS/NZS 4671, AS 1311 or the supplier is accredited with ACRS
label | ○ Galvanizing comply with AS/NZS 4680
label | ○ Steel fibre reinforcement must be of a type recommended by the fibre manufacturer for the intended use
label | ○ Welding comply with AS 1554.3
label | REFERENCE DOCUMENTS - R53.4
label | RECORD OF CONFORMITY - Compliance Certificate
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 5 - Cement mortar and grout
label | FREQUENCY - Per Mix
label | ACCEPTANCE CRITERIA - Must be a mixture of 3 parts sand or fine aggregate to 1 part cement with sufficient water to produce suitable consistency
label | REFERENCE DOCUMENTS - R53.2.2
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 6 - Designate concrete truck washout area (s)
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Impermeable plastic lined or approved equivalent
label | REFERENCE DOCUMENTS - CEMP
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 7 - Pre-construction
checkpoint | 8 - Set out the works
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Establish Pegs (or equivalent) to identify location, length, and levels as per design dwgs
label | REFERENCE DOCUMENTS - Design dwgs CMS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 9 - Foundation preparation including blinding layer
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Foundation prepared & compacted (tested if required in relevant Specs.)
label | ○ When placing Concrete in earth excavation, pre-place 50mm of unreinforced concrete blinding layer
label | REFERENCE DOCUMENTS - R53.3.1 CMS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 10 - Check the formwork
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Unless otherwise shown on the drawings, formwork must:
label | ○ Be of Class 3 (AS 3610) for external surfaces, or Class 4 for permanently hidden surfaces
label | ○ Face step minimum spacings 2m horizontally, 1m vertically
label | ○ Be in the correct position, level and dimensions
label | ○ Erected so that fresh concrete is not placed directly against the sides of the excavation
label | ○ Embedment in correct position
label | ○ Fillets in correct position and level
label | ○ Joints constructed to prevent loss of mortar
label | ○ Formwork is clean, oiled, adequately supported
label | REFERENCE DOCUMENTS - R53.3 AS 3610
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 11 - Check the construction joints
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - If placing adjoining concrete, roughen the surface of constructions joints to remove all laitance and expose coarse aggregate (surface roughness profile ≥ 3 mm)
label | ○ Ensure projecting reinforcement surfaces are washed clean & all excess water and loose material removed
label | REFERENCE DOCUMENTS - R53.6.6 Design DWGs
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 12 - Check the movement joints
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Movement joints constructed as shown on design drawings and relevant specifications
label | REFERENCE DOCUMENTS - Design DWGs
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 13 - Check the reinforcement
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Unless otherwise shown on the drawings, reinforcement must comply with the following:
label | ○ Bar sizes and spacing correct
label | ○ Lapped splices length must be 35 bar diameters for 500N deformed steel, 50 bar diameters for plain steel, two outermost transverse wires overlapping for fabric or mesh, 90 strand diameters for 7-wire prestressing strands
label | ○ All reinforcement are firmly supported on concrete or plastic chairs & are secure
label | ○ Electrical, Hydraulic, Mechanical conduits/Services, etc. are securely in place
label | ○ Cover to formwork faces is ≥ 50mm, unless otherwise specified on design drawings
label | ○ Where a sheet of fabric has been cut so that the outermost wire parallel to an edge of the concrete is more than 20 mm from the end of the transverse wires or the wires are not parallel to the edge, tie a D500N12 bar to the edge of the fabric.
label | ○ Use concrete or plastic chairs only; where concrete chairs are used, ensure they are of the same compressive strength as the concrete mix design to be used in the pour
label | ○ Place caps over exposed ends of reo bars for WHS purposes, retain caps in place until ready to pour
label | REFERENCE DOCUMENTS - R53.4 Design Drawings
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 14 - Placement
checkpoint | 15 - Commence with pre pour planning activities
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Areas free of water & construction debris removed
label | ○ Rain not imminent, air temperature between 5-38°C
label | ○ Concrete tester arranged as required
label | ○ Penetrations securely covered or isolated
label | ○ Revetment mattress prepared if to be filled with grout
label | REFERENCE DOCUMENTS - R53.6.1 R53.6.3 CMS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 16 - Placing of concrete, mortar or grout
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notify TFNSW Representative, not less than 24 hours and not more than 3 clear working days prior to the intended time of commencing to place concrete, mortar or grout, when fixing of the formwork and reinforcement in position (if applicable) will be completed and when concrete, mortar or grout will be placed, and where washout of delivery vehicles & cleaning tools will take place
label | REFERENCE DOCUMENTS - R53.6.1
textbox | RECORD OF CONFORMITY - Witness Point No.:
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 17 - (Where nominated in the relevant specification) Hold Point for Placing of Concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notify TFNSW Representative, not less than 24 hours and not more than 3 clear working days prior to the intended time of commencing to place concrete, mortar or grout, when fixing of the formwork and reinforcement in position (if applicable) will be completed and when concrete, mortar or grout will be placed, and where washout of delivery vehicles & cleaning tools will take place
label | REFERENCE DOCUMENTS - R53.6.1
textbox | RECORD OF CONFORMITY - Hold Point No.:
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 18 - Carry out the concrete pour
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Concrete docket checked for correct mix
label | ○ Slump and cylinders sampled. For sprayed concrete test the compaction by using 75 mm diameter cores taken from the in-place sprayed concrete
label | ○ If concrete is placed in a deep formwork it is not allowed to drop freely inside the formwork more than 1.2m. Concrete is placed through a rigid tube to ensure it does not segregate due to aggregate hitting the reinforcement
label | ○ Concrete is being spread and compacted adequately to produce a homogeneous product monolithic between joints and edges
label | ○ No mortar leaks or movement in formwork, reo or embedment
label | ○ Ensure entrapped air is expelled and concrete surrounds all reinforcement & embedments
label | ○ Provide specified thickness, cover & surface finish
label | ○ Unless specified otherwise, do not finish unformed surface with wood float
label | ○ Monitor evaporation of water from concrete surface and prevent plastic shrinkage cracking
label | REFERENCE DOCUMENTS - R53.6 CMS
label | RECORD OF CONFORMITY - Concrete Pour Record Sheet
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 19 - Post Pour
checkpoint | 20 - Curing the concrete
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Only approved curing compound and approved curing compound application methodology to be used
label | ○ After initial set of concrete, apply curing and cure for at least 7 days
label | ○ Curing compound thoroughly mixed, applied according to manufacturer’s recommendations or at a spray rate of 0.2L/m2, whichever is greater
label | ○ Ensure all exposed surfaces receive a uniform cover of the curing compound
label | ○ For moist curing, ensure curing water is free from ingredients harmful to concrete
label | REFERENCE DOCUMENTS - R53.7 CMS
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 21 - Stripping formwork
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Minimum Stripping times:
label | ○ 7 MPa for vertical foTfNSW on external surfaces
label | ○ 80% of fc,min for vertical foTfNSW on permanently hidden surfaces
label | ○ After stripping and before applying curing compound, moisten formed surfaces by light spraying
label | ○ Apply curing within 30 minutes of removal of formwork if minimum curing period not served
label | ○ 2 days for vertical foTfNSW on external surfaces
label | ○ 1 day for vertical foTfNSW on permanently hidden surfaces
label | ○ 24 hrs notice will be provided to TFNSW Representative prior to removing formwork
label | REFERENCE DOCUMENTS - B80.5.9.2 R53.7.3 R53.3.3
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 22 - Inspect concrete Surface Finish/Class
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Surface finish is in compliance with Class 3 for external surfaces and Class 4 for hidden surfaces
label | ○ Cracks are less than 0.05 mm – any cracks to be identified as nonconformities and require NCR
label | ○ Finished unformed concrete surfaces to be neat, clean and specified texture
textbox | If any NCR required, NCR No.:
label | REFERENCE DOCUMENTS - R53.3.2 R53.6.4 R53.8
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 23 - Check the tolerance of finished level and dimensions where specified in relevant Specifications
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Finished level to be within tolerance where specified in Specifications or on design drawings
label | REFERENCE DOCUMENTS - R53.9 Design dwgs
label | RECORD OF CONFORMITY - Survey Report
label | SCP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 24 - Check conformance of concrete test results if required
label | FREQUENCY - R53/L
label | ACCEPTANCE CRITERIA - Test certificates received, reviewed and conforming to R53/E if Project Assessment Required:
label | ○ Slump (1 / first 3 batches at the start and then 1 per 4 batches)
label | ○ Compressive strength
label | ○ Compaction of sprayed concrete (1 pair per 50 m3 and min of 2 pair per pour)
label | ○ Grout compressive strength (1 pair per 20m3 and min of 2 pairs)
label | REFERENCE DOCUMENTS - R53/E
label | INSPECTION / TEST METHOD - AS1012.3. 1 AS1012.9
label | RECORD OF CONFORMITY - Test Reports
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP