## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 8 - Geotextile Materials | itp |  |  |  |  | ITP 8 - Geotextile Materials
section | 1.0 - Preliminary
checkpoint | 1.01 - General Material Requirements
label | FREQUENCY - Per Supplier
label | ACCEPTANCE CRITERIA - Woven geotextiles filaments interlaced in two sets, mutually at right angles. One set must be parallel to the longitudinal direction of geotextile.
label | ○ Nonwoven geotextiles filaments bonded by needle punching, heat or chemical bonding processes.
label | ○ Geotextiles must be free of flaws which may have an adverse effect on the physical & mechanical properties of the geotextile.
label | ○ Geotextiles must be stabilised against ultraviolet radiation to achieve a retained strength of at least 50% after 500 hours of test exposure, when tested as per AS 3706.11.
label | ○ Geotextiles may be manufactured under controlled conditions from recycled materials and must conform to the requirements of TfNSW R63, be identified as such on the Certificate of Compliance (refer R63.2.5), and must be homogeneous with respect to content of recycled material.
label | REFERENCE DOCUMENTS - R63.2.1
label | RECORD OF CONFORMITY - Suppliers Documentation / Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Confirm site specific details then select Geotextile Type:
bool | Type G1
bool | Type G2
bool | Type G3
bool | Type G4
bool | Type G5
bool | Type G6
label | FREQUENCY - Per Supplier / Per Type
label | ACCEPTANCE CRITERIA - Type G1: Separation under/within the Embankments (unsaturated ground) to prevent mixing of dissimilar soil types during construction appropriate for unsaturated soils where CBR > 3)
label | ○ Type G2: Separation under/within the Embankments (saturated ground) to prevent mixing of dissimilar soil types in saturated conditions in working platform/bridging layer applications for subgrade soils where CBR ≤ 3 and where filtration is not a critical function
label | ○ Type G3: Trench drains, edge drains, counterfort drains and drainage layers. To provide the combined functions of separation and filtration
label | ○ Type G4: Drainage and separation behind retaining structures including Rock filled mattresses and joints of pipes and arches. To provides the combined functions of separation and filtration.
label | ○ Type G5: Under Rock Armour Revetment Layer in Embankments.
label | ○ Type G6: Behind carriageway concrete pavement base layers. To provide separation from concrete base/lean mix sub-base layers and abutting unbound verge material
label | REFERENCE DOCUMENTS - R63.2.2, Table R63/A.1, R63/E1 & Design dwgs
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.03 - Confirm if the Geotextile Strength Class is suitable for its intended application:
label | Class:
bool | A
bool | B
bool | C
bool | D
bool | E
label | FREQUENCY - Each Type
label | ACCEPTANCE CRITERIA - Verify geotextiles for applications of separation and/or filtration meet the relevant Strength Class requirements of Table R63/E.2.
label | ○ Ensure geotextile survivability requirements consider the subgrade condition against which the geotextile will be placed, fill material particle size, fill placement and construction process.
label | REFERENCE DOCUMENTS - R63.2.2.1, Table R63/E2, Table R63/E1 & R63/A.1
label | INSPECTION / TEST METHOD - AS 1289.3.6.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.04 - Confirm the Geotextile Filtration Class is suitable for its intended application
label | Class:
bool | 1
bool | 2
bool | 3
bool | 4
bool | 5
label | FREQUENCY - Each Type
label | ACCEPTANCE CRITERIA - Verify the Geotextile meets the relevant filtration requirements of Table R63/E.1 for each application.
label | REFERENCE DOCUMENTS - R63.2.2.2 & Table R63/E1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - Obtain manufacturer’s product certification documentation
label | FREQUENCY - Each Batch
label | ACCEPTANCE CRITERIA - Manufacturer / Supplier to provide a Certificate of Compliance that geotextile complies with all requirements of TfNSW R63 for its specified usage together with NATA endorsed test reports not more than 12 months’ old.
label | REFERENCE DOCUMENTS - R63.2.5
label | RECORD OF CONFORMITY - Compliance Certificate
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.06 - Submission of product certification
label | FREQUENCY - Each Type
label | ACCEPTANCE CRITERIA - Submit Certificate of Compliance from the Supplier, & nominate where each strength and filtration class will be used.
label | ○ The Principal will consider submitted documents and may inspect geotextile or direct further action, such as site sampling & testing in accordance with TfNSW R63 Clause 2.4 prior to authorising the release of the Hold Point.
label | REFERENCE DOCUMENTS - R63.2.5.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Delivery & Storage
checkpoint | 2.01 - Inspect supplied items upon delivery
label | FREQUENCY - Each Delivery
label | ACCEPTANCE CRITERIA - Geotextile must be delivered to the site at least 14 days prior to commencement of installation.
label | ○ The protected geotextile rolls must be clearly labelled showing manufacturer, type of geotextile and batch number identification number.
label | REFERENCE DOCUMENTS - R63.3.3 & R63.3.2
label | RECORD OF CONFORMITY - Receival Inspection Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.02 - Protect delivered materials from water and UV radiation
label | FREQUENCY - Each Delivery
label | ACCEPTANCE CRITERIA - Geotextiles must be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
label | ○ Geotextiles must not be stored directly on the ground or in any manner in which they may be affected adversely by heat, dirt or damage.
label | ○ Method of storage must be in accordance with recommendations set by the manufacturer.
label | REFERENCE DOCUMENTS - R63.3.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
section | 3.0 - Site Sampling & Testing
checkpoint | 3.01 - Sampling and testing requirements
label | FREQUENCY - 1/10,000 then 1/20,000 m² Each Batch
label | ACCEPTANCE CRITERIA - Control testing to be carried out on each batch of geotextile delivered to site to ensure conformity of properties specified in Tables R63/E.1 & R63/E.2.
label | ○ Testing must include the mean weight of the geotextile, determined as per AS 3706.1 & AS 2001.2.13.
label | ○ Geotextiles which has not been verified by site sampling & testing to prove compliance with strength & filtration requirements must not be used in the Works.
label | REFERENCE DOCUMENTS - R63.2.4.1 & R63.2.4.2
label | INSPECTION / TEST METHOD - AS.3706 Cl.2 to Cl. 5 Inc., & AS 2001.2.13
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3.02 - Sampling of Geotextile on site
label | FREQUENCY - Per Site Test
label | ACCEPTANCE CRITERIA - Notify the Principal of location, date and time of sampling and person sampling.
label | REFERENCE DOCUMENTS - R63.2.4 & R63/E
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3.03 - Procedure for sampling & testing process
label | FREQUENCY - Per Test
label | ACCEPTANCE CRITERIA - Approx. 15m² is cut from each geotextile sample roll, but not within 2m of start or end of the roll. Where directed, provide samples to the Principal.
label | ○ Mark sample in accordance with TfNSW R63.2.4.3
label | ○ Ensure testing of geotextile sample will be done at an approved NATA registered laboratory accredited for the range of tests given in Table R63/E.1 & Table R63/E.2
label | ○ Provide associated documentation including geotextile supplier, geotextile type, batch identification, order represented by sample, sample date, roll directional markings, etc., to testing agency for their information, to be reported on or attach to the test reports.
label | ○ Not required if Principal accepts the batch is tested and verified from another project and hold point submitted under R63.2.5.2
label | REFERENCE DOCUMENTS - R63.2.4.3 & R63.2.4.4
label | RECORD OF CONFORMITY - NATA Test Reports / Verification Checklist
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3.04 - Submission of site sampling results
label | FREQUENCY - Per Test
label | ACCEPTANCE CRITERIA - Site sampling test results referred to in Clause 2.4 at least 14 days prior to placement of geotextile.
label | ○ The Principal will consider submitted test documents verifying conformity of the geotextile with TfNSW R63 and may inspect the geotextile.
label | ○ The Principal may require additional testing prior to authorising release of the Hold Point.
label | REFERENCE DOCUMENTS - R63.4.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 9 - Unbound Pavement Course | itp |  |  |  |  | ITP 9 - Unbound Pavement Course
section | 1 - Preliminary
checkpoint | 2 - Set out the works
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Establish Pegs (or equivalent) to identify the extent of pavement
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 3 - Check underlying lots are conforming and closed
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Check underlying drainage and earthwork lots are conforming and closed, Hold Points released
label | REFERENCE DOCUMENTS - R44.6.1.2 R11.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Obtain approval for nominated mix design
label | FREQUENCY - Per mix
label | ACCEPTANCE CRITERIA - At least 10 working days prior to commencement of the trial section of pavement construction, or commencement of the pavement works, submit to the Nominated Authority details of your nominated mix design(s) and test results verifying conformity of the nominated mix design(s).
label | REFERENCE DOCUMENTS - D&C 71 4.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Materials
checkpoint | 5 - Obtain approval for supply from certified stockpiles
label | FREQUENCY - Per Stockpile
label | ACCEPTANCE CRITERIA - Submit to PV with a statement verifying that the material from the certified stockpile meets the requirements of R71 and D&C 3051. Attach NATA endorsed test results to the statement, indicate the quantity of material represented by the test results.
label | REFERENCE DOCUMENTS - R71.2.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Construction
checkpoint | 7 - Check material upon delivery
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The material must be slightly damp and at the time of delivery
label | ○ Check delivery docket to ensure correct materials supplied
label | REFERENCE DOCUMENTS - R71.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 8 - Construction of trial section of pavement
label | FREQUENCY - Per Trial
label | ACCEPTANCE CRITERIA - Notify the PV at least 3 days prior to commencement.
label | REFERENCE DOCUMENTS - R71.6.3
label | RECORD OF CONFORMITY - Witness Point
label | WP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 9 - Construction of pavement
label | FREQUENCY - Per Trial
label | ACCEPTANCE CRITERIA - Construction of Pavement
label | ○ Submission of trial pavement conformance
label | REFERENCE DOCUMENTS - R71.6.3
label | RECORD OF CONFORMITY - Witness Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Placing, spreading, compaction and trimming the material
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Maintain field moisture content during placement and compaction within the target moisture content envelope
label | ○ Compacted layer to be 100-150mm thick
label | ○ For modified (sub)base, complete the construction within the Allowable Working Time
label | ○ No roller marks left after final trimming
label | ○ No delivery traffic allowed on the placed
label | ○ Trim the pavement course to design level
label | REFERENCE DOCUMENTS - R71.6.5
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 11 - Verify finished pavement properties
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Compaction to 102% std. (100% std. if HD modified base) - lot area ≤ 50 m2, 1 min per lot; 50-500m2, 3 min per lot; 500-1000m2, 4 min per lot; 1000-5000m2, 1 per 500m2(min. 5); >5000m2, 1 per 1000m2(min. 10)
label | ○ Moisture content ≤70% of OMC prior to seal – as relative compaction frequency
label | ○ Level within -0/+10mm (base), or -10/+0mm (subbase) - 1 per 20 linear metres, offset as per table G71.7
label | ○ Layer thickness within -0/+20mm (base), or -/+10mm (subbase) – at least one site per 75m, with a minimum of 2 per lot
label | ○ 3m straight edge: max. 5mm – minimum 1 per 20m2
label | ○ Pavement width ≥ design width – minimum 1 per 20 linear metres.
label | ○ Unconfined compressive strength is less than 1 MPa (accordance with T116)
label | ○ Minimum frequency of testing (T116 one pair per 400 tonnes or part thereof)
label | REFERENCE DOCUMENTS - R71.8 R71.8.4.2 R44.7.4
label | INSPECTION / TEST METHOD - T116 T173 T166
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 12 - Obtain approval for sealing of the pavement
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Submit to the Project Verifier with test results of above pavement properties
label | REFERENCE DOCUMENTS - R71.6.8
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Carry out Ride Quality Test
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Carry out ride quality test, refer to R116-IRI Lots
label | REFERENCE DOCUMENTS - R71.8.8
label | RECORD OF CONFORMITY - R116-IRI Lots
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 14 - Carry out base course surface assessment
label | FREQUENCY - As directed
label | ACCEPTANCE CRITERIA - The average ball penetration value of a sample location (Pes) is ≤ 3.0 mm; and the characteristic ball penetration value is ≤ 2.5 mm.
label | REFERENCE DOCUMENTS - R71.8.10 Q6/L3.2
label | INSPECTION / TEST METHOD - T271
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 15 - Obtain approval of treatment of non- conforming lots
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Submit to the Project Verifier a NCR and details of proposal to rectify or replace the Lot, prior to carry out the rectification works
label | REFERENCE DOCUMENTS - R71.8.12
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 10 - Heavily Bound Base | itp |  |  |  |  | ITP 10 - Heavily Bound Base
section | 1 - Preliminary
checkpoint | 2 - Set out the works
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Establish survey marks to identify the extend of pavement
label | REFERENCE DOCUMENTS - G71
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Surveyor
date | Date Completed:
checkpoint | 3 - Check underlying lots are conforming
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Check underlying drainage and earthwork lots are conforming, and Hold Points released Initial CCTV of drainage pipes completed without defects
label | REFERENCE DOCUMENTS - D&C R44.6.1.2 R11.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Obtain approval for nominated mix design
label | FREQUENCY - Per mix
label | ACCEPTANCE CRITERIA - At least 10 working days prior to commencement of the trial section of pavement construction, or commencement of the pavement works, submit to the Nominated Authority details of your nominated mix design(s) and test results verifying conformity of the nominated mix design(s).
label | REFERENCE DOCUMENTS - D&C R73 4.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Certified stockpile for MTBB (Where not Blended)
label | FREQUENCY - Per stockpile
label | ACCEPTANCE CRITERIA - Prior to the release of MTBB from a Certified Stockpile, submit to the PV Details of the stockpile, statement of conformity and documentation specified in TfNSW D&C 3051 regarding conformity. .
label | REFERENCE DOCUMENTS - D&C R73 2.2 3051
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Approval to supply where MTBB is blended from individual constituents
label | FREQUENCY - Per Supplier
label | ACCEPTANCE CRITERIA - Provide details of:
label | – Mixing Plant
label | – Plant Operation and
label | – Procedures
label | to ensure mix is conforming to TfNSW D&C 3051
label | REFERENCE DOCUMENTS - D&C R73.5.2
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Obtain approval for placement of bound pavement course in two layers. (when layer >250mm )
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Submit to the Project Verifier at least 10 days prior to commencement:
label | ○ Verification and test results demonstrating the MTBB is self- cementing,
label | ○ Details of work method and details of previous successful applications of the work methods.
label | REFERENCE DOCUMENTS - D&C R73.6.3.3
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Obtain approval for placement of bound pavement course in a single layer >250mm
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Submit to the TfNSW Representative at least 15 days prior to commencement:
label | ○ Details of work method and associated controls to achieve required compaction.
label | ○ Details of previous successful application of work method.
label | REFERENCE DOCUMENTS - D&C R73.6.3.5
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Obtain approval for placement of bound pavement course
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Submit to the Project Verifier that locations and types of proposed construction joints, locations of unsupported edges and details of rolling pattern
label | REFERENCE DOCUMENTS - D&C R73.6.6.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Obtain approval to the schedule of levels of the underlying surface
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - When finished surface levels are specified, submit to the Quality Manager that the Schedule of levels of the underlying surface at least 7 days before place HBB. The schedule need to highlight locations where the actual levels at the underlying surface are higher than the design levels
label | REFERENCE DOCUMENTS - D&C R73.7.2.1
label | RECORD OF CONFORMITY - Hold Point
label | HP*
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 11 - Construction Trial
checkpoint | 12 - Construction of trial section of bound pavement.
label | FREQUENCY - Per trial
label | ACCEPTANCE CRITERIA - Notification of the construction of the trial section of pavement at least 3 working days prior to commencement.
label | ○ Construct a trial section of pavement at an agreed location, using the same materials, equipment and methods described in the PROJECT QUALITY PLAN.
label | ○ The trial section of pavement must be between 100 m and 200 m long for the proposed Lot width.
label | REFERENCE DOCUMENTS - D&C R73 6.9.1
label | RECORD OF CONFORMITY - Witness Point
label | W P
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 13 - Submission of trial result
label | FREQUENCY - Per trial
label | ACCEPTANCE CRITERIA - Submit Documentation, including test results, verifying that the trial section of pavement conforms to the specified requirements.
label | REFERENCE DOCUMENTS - D&C R73 6.9.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 14 - Construction
checkpoint | 15 - Check the weather condition
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Do not carry out bound pavement construction when any of the following apply:
label | ○ when the temperature measured at a depth of 50 mm below the surface of the underlying course is below 10ºC or the air temperature measured in the shade is above 40ºC;
label | ○ in wet weather or in strong wind conditions
label | REFERENCE DOCUMENTS - D&C R73.6.2
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 16 - Check material upon delivery
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The material must be suitably damp and at the time of delivery
label | ○ Check delivery docket to ensure correct materials supplied and docket number provided
label | REFERENCE DOCUMENTS - D&C R73.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 17 - Placing, spreading, compaction and trimming the material
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Maintain field moisture content within target moisture content envelope during placement to ensure hydration and compaction Materials to be spread into 1 single layer up to 250mm thick unless otherwise approved. No slurry and delamination
label | ○ No roller marks left after final trimming Trimming of the pavement course to design level and compaction completed within the allowable working time.
label | REFERENCE DOCUMENTS - D&C R73.6 R73.8.4.3
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 18 - Construction joints
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Types and locations are as per design or approved in the Hold Point
label | ○ Joints prepared as specified method
label | ○ Cut back previously placed pavement at least:
label | ○ 75 mm along longitudinal joints; and
label | ○ 0.5 metres at transverse joints.
label | ○ For fresh longitudinal joint do not compact the 300mm of material of the first run adjacent to the second run until the it is ready to do so, keep moist to the joints
label | ○ Transverse joints formed at right angle s to the road centreline
label | ○ Longitudinal joints not at wheel paths, within 100mm from separation lines, and >300mm away from edge lines but within the shoulder area
label | ○ Induced longitudinal joints to be saw cut within 3 days of placement, 1/3 of the depth, 3mm wide
label | REFERENCE DOCUMENTS - D&C R73.6
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 19 - Curing and protection of the pavement course
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Commenced immediately after compaction and until seal
label | ○ Keep surface continuously damp without excessive water
label | ○ No non-essential traffics
label | REFERENCE DOCUMENTS - D&C R73.6.8
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 20 - Joint Survey
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - At least 3-Days prior to conformance survey provide PV with date, location, surveyor’s name, description of methods and equipment to be used.
label | REFERENCE DOCUMENTS - G71.2.10.1
label | INSPECTION / TEST METHOD - Survey
label | RECORD OF CONFORMITY - Survey Request & include PV
label | SU
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 21 - Certificate of Conformity
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Submit Weekly to the Project Verifier a signed certificate verifying conformity with the requirements of Clause 8. Where appropriate, submit with the certificate a summary of test results from a laboratory accredited by NATA. Additionally, submit daily to the Project Verifier the moisture content and relative density test results.
label | ○ Highlight any nonconforming Lots.
label | REFERENCE DOCUMENTS - R73 8.10
label | RECORD OF CONFORMITY - Test results & Non Conformanc e lots
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 22 - Verify finished pavement properties
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - UCS (7 day acc./28 days normal curing):
label | ○ Bound DGB = 3-8MPa
label | ○ Grave Laitier = 2MPa
label | ○ Compaction to 102% std as per Q6 L3.1
label | ○ Moisture content within target MC prior to compaction
label | ○ Level within -0/+10mm
label | ○ Layer thickness within -0/+20mm when use automated level control, +10/30mm when use without automated level control
label | ○ 3m straight edge test must be no more than 5mm at any direction
label | ○ Pavement width ≥ design width
label | ○ Compact the sample within 3 hours of sampling and within the mix’s allowable working time.
label | REFERENCE DOCUMENTS - D&C R73 4.1 R73.6.11 R73.8 Q6 L3.1 R73.8.4.4
label | INSPECTION / TEST METHOD - T120 T116 T166
label | RECORD OF CONFORMITY - Test Report Survey Report
label | TP
label | RESPONSIBILITY - Surveyor Site Engineer
date | Date Completed:
checkpoint | 23 - Obtain approval for sealing of the pavement
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Submit to the Project Verifier with test results of above pavement properties prior to seal Pavement shall be primed or sealed within 6 days of placement unless otherwise required and/or agreed under this HP.
label | REFERENCE DOCUMENTS - D&C R73.6.11
label | RECORD OF CONFORMITY - Hold Point & Survey Report
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 11 - Sprayed Bituminous Surfacing | itp |  |  |  |  | ITP 11 - Sprayed Bituminous Surfacing
section | 1.0 - Preliminary
checkpoint | 1.01 - Planning Documents
label | FREQUENCY - Once
label | ACCEPTANCE CRITERIA - Prepare CMS to address all the applicable items listed in Annexure 1061/D to be included as PQP requirements.
label | ○ Issue CMS via iTWOcx to TfNSW for their review.
label | REFERENCE DOCUMENTS - R106.1.2.4 & Annex R106/D
label | RECORD OF CONFORMITY - iTWOcx Transmittal
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.02 - Materials
label | FREQUENCY - Per Material Type
label | ACCEPTANCE CRITERIA - Materials
label | ○ Bituminous Materials as specified in Annexure R106/A modified in accordance with iTWOcx RFI#0080 - C240 bitumen, hence:
label | – Binder for seals & reseals conform to TfNSW 3253 (require doc evidence of binder conformity for each delivery used in the work).
label | – Refinery cutback bitumen conform to TFNSW 3261.
label | ○ Aggregate Precoating Agent And Bitumen Adhesion Agent
label | – Aggregate precoating agents conform to TfNSW 3258.
label | – Bitumen adhesion agents conform to TfNSW 3259.
label | ○ Oils for reducing the viscosity of bitumen must conform to AS 3568.
label | ○ Aggregate (7 mm)
label | – Supply & delivery of aggregate conform to TfNSW 3151
label | – Obtain test results for each Lot of aggregate, as per TFNSW 3151, before aggregate from the Lot is incorporated in the Project Works. When requested, provide a sample to the Principal from the same Lot by riffling or quartering samples. Amount of material obtained for each sample must be the nominal size of aggregate as per AS 1141.3.
label | ○ Stockpiles
label | – Arrange and manage aggregate stockpiles to TfNSW R106.2.4.2 requirements.
label | – Stockpiles that exhibit visible segregation, contamination or weathering rectify or replace.
label | REFERENCE DOCUMENTS - R106.2, Annex R106/A, RFI#0080, TfNSW 3253, 3261, 3258, 3259 & 3151
label | RECORD OF CONFORMITY - NATA Report/ Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.03 - Geotextile
textbox | R63-GEO-LOT No.:
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Geotextile must be a nonwoven needle punched fabric with a minimum melting point of 165oC, minimum mass of 130 g/m2 and a minimum bitumen saturation of 0.9 L/m2.
label | REFERENCE DOCUMENTS - R106.2.5 & G63
label | RECORD OF CONFORMITY - R63-GEO LOT
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.04 - Nominated materials & design of Bituminous Surfacing
label | FREQUENCY - Per Mix Design
label | ACCEPTANCE CRITERIA - Design in accordance with TfNSW form 395A or TfNSW form 395K as appropriate.
label | ○ Submit design details Inc. all results from texture testing for reseals & ball embedment tests for seals. Design application rates are "nominated application rates" and materials used for the design are "nominated materials".
label | ○ The proportion of constituents in any bituminous surfacing must conform to the limits as specified in Table R106.1.
label | REFERENCE DOCUMENTS - R106.3.1 & R106.3.2
label | RECORD OF CONFORMITY - Form 395A or Form 395K
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.05 - Verification of each Constituent Material
label | FREQUENCY - Per Material
label | ACCEPTANCE CRITERIA - Test results for all nominated materials, inc. stripping & initial adhesion for combination of nominated materials;
label | ○ Aggregates - source, geological type, particle size distribution, nominated average least dimension (ALD);
label | ○ Precoating agent and bitumen adhesion agent - types & proportions;
label | ○ Bitumen - refinery source;
label | ○ Cutback bitumen - refinery source of bitumen, source of cutter oil;
label | ○ Cutter Oil / Flux Oil - type and source; The sampling and testing of a nominated material must be carried out within the six months period prior to the date of submission to the Principal.
label | ○ Submit a statement signed by you stating that each design and its constituent materials meet the requirements of TfNSW R106 Clauses 2 & 3. The statement must include NATA endorsed test results for all specified tests. A copy of your completed verification checklist must be attached.
label | REFERENCE DOCUMENTS - R106.3.3.1, R106.3.3.2 & R106.3.3.3
label | RECORD OF CONFORMITY - NATA Test Reports / R106 Checklist Review Spreadsheet
label | AP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.06 - Submit the nominated mix design for approval
label | FREQUENCY - Each Mix Design
label | ACCEPTANCE CRITERIA - Documents referred to in R106.1.2.4 and proposed bituminous surfacing design together with certification for the nominated materials & design verification documents ≥ 7 days prior to commencement of sprayed bituminous surfacing work.
label | REFERENCE DOCUMENTS - R106.23.3.3
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Check if notification issued for covering base/subbase
textbox | Hold Point No.:
textbox | Relevant Lot No.:
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The notification has been made not less than 24 hours prior to covering or sealing a completed lot of subbase/base.
label | REFERENCE DOCUMENTS - R44.6.1.2, R71.6.8 & R73 6.11
label | RECORD OF CONFORMITY - Refer to R44, R71 & R73 Lots
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.08 - Review of nominated application rates
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Review bituminous surfacing design at each location based on actual ALD test result for actual aggregate to be used instead of ALD value of nominated aggregate & using appropriate TfNSW 395 design form.
label | ○ The revised application rates are “target application rates”
label | REFERENCE DOCUMENTS - R106.3.4
label | RECORD OF CONFORMITY - NATA Reports / Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.09 - Revised application rates
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Submission of aggregate Lot details and target application rates prior to application at each work location.
label | REFERENCE DOCUMENTS - R106.3.4
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Sampling & testing
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Ensure sampling & testing of materials is undertaken in accordance with relevant material specifications in TfNSW R106 .2 and AS 2008. Testing must comply with Annexure R106/L.
label | ○ The Principal may conditionally agree to a proposal to reduce specified minimum frequency of testing.
label | REFERENCE DOCUMENTS - R106.4.1 & Annex R106/L
label | RECORD OF CONFORMITY - NATA Reports / Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
section | 2.0 - Spray Seal Works
checkpoint | 2.01 - Check pre-coated aggregate
label | FREQUENCY - Per Delivery / Stockpile
label | ACCEPTANCE CRITERIA - Aggregate precoating provides complete, light, uniform, effective cover of all aggregate particles.
label | ○ Precoated aggregates covered from wet weather to prevent precoating material being washed from particles & prevented from settlement of dust or drying out of the precoating agent on stockpiled aggregate.
label | REFERENCE DOCUMENTS - R106.5.1
label | RECORD OF CONFORMITY - Subc. Records / Visual Inspection
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.02 - Preparation of pavement surface
label | FREQUENCY - Per Lot Area
label | ACCEPTANCE CRITERIA - Ensure pavement surface is swept with a rotary road broom or suction broom for a uniformly clean surface. If necessary, carry out additional sweeping by hand, using stiff bass or similar brooms. Sweeping must extend ≥ 300 mm beyond each edge of area to be sprayed.
label | ○ Pavement surface must be slightly damp for spraying of primer or primerbinder.
label | ○ Where work is carried out on localised areas or half pavement widths, remove remaining loose foreign material from pavement surface adjacent to swept area.
label | ○ Services & road fixtures are covered to prevent primer, primerbinder, binder, aggregate or other material used on the work from entering or adhering to them.
label | REFERENCE DOCUMENTS - R106.5.2 & R106.5.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
checkpoint | 2.03 - Pavement temperature & weather conditions
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Pavement Temperature at or above 10°C @ least 1 hr before commencement, and does not fall below specified min. pavement temperature for spraying during spraying.
label | ○ Spraying did not commence in wet pavement or while rain appears imminent or during strong winds.
label | REFERENCE DOCUMENTS - R106.5.3
label | RECORD OF CONFORMITY - Subc. Records / Verification Checklists
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.04 - Application Plant
label | FREQUENCY - Once Per Sprayer
label | ACCEPTANCE CRITERIA - The sprayer has a current Sprayer Certificate (TfNSW Form 354) issued or accepted by TfNSW.
label | ○ The sprayer nozzles are make & type endorsed on Sprayer Certificate.
label | ○ Spare nozzles available to replace damaged / worn ones
label | ○ Spreading equipment (including box spreaders) must be used to spread aggregate and must be capable of achieving a uniform spreading rate.
label | ○ Rollers used must be two or more dual axle smooth pneumatic tyred multi-wheel rollers of mass greater than 7 tonnes without ballast and minimum tyre pressure of 550 kPa.
label | REFERENCE DOCUMENTS - R106.6.1, R106.6.2 & R106.8
label | RECORD OF CONFORMITY - Subc. Records
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.05 - Supervise the application of primer, primerbinder or binder
label | FREQUENCY - Per Lot / 1 per 2 hours
label | ACCEPTANCE CRITERIA - Sprayer must maintain a constant road speed throughout length of each spray run.
label | ○ Areas not within 5% of target application rate of primer, primerbinder or binder constitute a ‘Nonconformity’ under the Contract.
label | ○ Where a sprayer is not able to satisfactorily spray small areas or areas of irregular shape, spray such areas by means of hand spray equipment attached to sprayer.
label | ○ Temperature is measured and record using a suitable thermometer accurate to within 2.5% of the correct temperature. Bituminous material temperatures are within upper and lower limits of TfNSW Spec. Tables R106.2 and R106.3. Any bituminous material that has been overheated must not be used in the work.
label | ○ Determine and record the proportion of cutter oil required for each sprayer load, using TfNSW Form 382 for seals / reseals and TfNSW Form 395A for primes / primerseals.
label | ○ Where bitumen adhesion agent and / or cutter oil have been added to binder, adjust application rate of the total binder at 15°C, using TfNSW Form 500A, to allow for the quantities of bitumen adhesion agent and/or cutter oil in the mixture.
label | ○ Determine hot applicable rate of total binder, including bitumen adhesion agent and/or cutter oil using TfNSW Form 382.
label | ○ Where refinery cutback bitumen is used as the binder, increase target application rate of binder to allow for the cutter oil in the mixture according to TfNSW Table R106.4
label | REFERENCE DOCUMENTS - R106.6.2, R106.6.3, R106.6.6, R106.6.7, R106.7.2 & R106.7.3
label | RECORD OF CONFORMITY - Subcontractor Records
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.06 - If Required: Apply geotextile
label | FREQUENCY - As Required
label | ACCEPTANCE CRITERIA - Apply geotextile fabric where nominated in Annexure R106/A or as directed.
label | ○ After tack coat application fix fabric to pavement smoothly and without wrinkles. Adjoining geotextile fabric overlap existing fabric by ≥ 100 mm.
label | ○ Joining fabric in the longitudinal direction under wheel path must be minimised.
label | REFERENCE DOCUMENTS - R106.6.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.07 - Application & incorporation of aggregates
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Only pre-coated aggregate for seal & primerseals.
label | ○ Application of aggregate, must proceed after spraying of the binder has commenced & be completed ≤ 15 minutes of spraying bitumen or cutback bitumen.
label | ○ Applied uniformly (spreader truck) @ nominated target spread rate. Method to determine actual aggregate spread rate TfNSW T274 or a method approved by the Principal.
label | ○ Initial rolling commenced with dual axle smooth pneumatic tyred multi-wheel rollers (>7T) without ballast and min. tyre pressure of 550 kPa. Continue initial rolling until aggregate is firmly embedded in primerbinder or binder.
label | ○ Pneumatic multi tyred roller are used with at least 8 passes within 1 hour of spraying.
label | ○ Any remaining loose aggregates are removed.
label | REFERENCE DOCUMENTS - R106.8
label | INSPECTION / TEST METHOD - T274
label | RECORD OF CONFORMITY - Subcontractor Records
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.08 - Obtain / verify subcontractor field record
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The following field records for conformity are checked on form 500A or 500C:
label | ○ Bitumen temperature: within limits in TfNSW R106.6.6
label | ○ Binder application rate: ±5% of target application rate
label | ○ Aggregate spread rate: as nominated
label | ○ Control charts are completed where 10 or more sprayer runs greater than 1000 L are required. Supply the Principal with a copy of each completed form.
label | REFERENCE DOCUMENTS - R106.6.6, R106.6.2, R106.4.3 & R106.4.4
label | RECORD OF CONFORMITY - Subcontractor Records / TfNSW Form 500A or 500C
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 12 - Retroreflective Pavement Markers | itp |  |  |  |  | ITP 12 - Retroreflective Pavement Markers
section | 1 - Materials
checkpoint | 2 - Obtain and submit conformance records
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Submission includes:
label | ○ Recommendations of the raised pavement marker manufacturer on the materials and methods for the install of the RPM's
label | ○ Product Data sheet and recommendation of adhesive use and handling
label | ○ Method of protection of RPM's whilst adhesive is hardening
label | ○ Material certification are ≤ 36 months old
label | ○ Raised Pavement Markers conforms to AS1906.3 and have dimensions shown on Annex E
label | ○ Made by the prequalified manufacture/s Annex F
label | ○ Adhesive must comply with RTA 3354.
label | ○ Submitted at least 7 days prior to proposed use
label | REFERENCE DOCUMENTS - R142/D
label | RECORD OF CONFORMITY - Materials Compliance Certificate
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Set out the works
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The location of all raised pavement markers are as per Drawings, or directed by RMS and is within::
label | ○ Longitudinal (±100mm)
label | ○ Transverse (±25mm within 1.5m)
label | ○ Direction (4° rotational)
label | REFERENCE DOCUMENTS - R142.3
label | RECORD OF CONFORMITY - Verification Checklist
label | RESPONSIBILITY - Site Foreman
date | Date Completed:
section | 4 - Installation
checkpoint | 5 - Commencement with application of Retroreflective Pavement Markers
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - For new Installations, set out the work to ensure all rpm's are placed in accordance with the nominated Plan and Drawings and to the tolerances required by the Specification
label | REFERENCE DOCUMENTS - R142.3.1
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Graduate Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Fix Retroreflective Pavement Markers
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - RPM's are fixed with an adhesive to the surface of the pavement in accordance to the manufacturers recommendations.
label | ○ Fixed at locations marked on the setout
label | REFERENCE DOCUMENTS - R142.3.3
label | RECORD OF CONFORMITY - Verification Checklist
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 7 - Remove/replace non- functional/temporary markers
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Remove non functional markers only if the markers:
label | ○ has a cracked body or lens, and by eye the night time headlight visibility appears unaffected, must not be replaced; or
label | ○ has sunken into the pavement to make the removal difficult and give rise to excessive work in the repair of pavement.
label | REFERENCE DOCUMENTS - R142.5.3 R141.6
label | RECORD OF CONFORMITY - Verification Checklist
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP 13 - Pavement Marking Works | itp |  |  |  |  | ITP 13 - Pavement Marking Works
section | 1 - Preliminary
checkpoint | 2 - Underlying lot conformance (if applicable)
textbox | Lot No:
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Underlying lots conform to applicable specifications
label | REFERENCE DOCUMENTS - Previous Lot Record
label | RECORD OF CONFORMITY - Lot conformance
label | R
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 3 - Check if traffic controls are in place
label | FREQUENCY - Per Area
label | ACCEPTANCE CRITERIA - Road Occupancy License Obtained if required;
label | ○ Pedestrian and vehicular public traffic control planning measures established
label | REFERENCE DOCUMENTS - G10.2.4
label | RECORD OF CONFORMITY - Approved TCP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 4 - Painting Contractor Certification
label | FREQUENCY - Per Contractor
label | ACCEPTANCE CRITERIA - Works carried out by organisation that is accredited to the “Painting Contractors Certification Program”.
label | REFERENCE DOCUMENTS - R145.1.4
label | RECORD OF CONFORMITY - Certification
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 5 - Verify type of marking material as shown in drawings
bool | Waterborne paint
bool | Thermoplastic paint
bool | Others
textbox | Other:
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - On concrete surfaces in the main carriageway and all local road – waterborne paint
label | ○ Asphalt surface on the main carriageway – thermoplastic paint
label | ○ Type as per relevant design drawings & R145 appendices
label | ○ provide the TfNSW representative a list of material proposed for use and limitation to be used
label | REFERENCE DOCUMENTS - R145.1.4 R145.2.1 AS 4049.3 AS 4049.2 3359 3360
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 6 - Verify the reflective glass beads conform to specs requirements
label | FREQUENCY - Per Material
label | ACCEPTANCE CRITERIA - (APAS) Specification APS0042, Clause 6.2 “Heavy metal content”. Obtain evidence of compliance.
label | REFERENCE DOCUMENTS - R145.2.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 7 - Verify conformance of raised pavement markers & Adhesive
label | FREQUENCY - Per Material
label | ACCEPTANCE CRITERIA - Use only retroreflective raised pavement markers prequalified by the TfNSW. Prequalified retroreflective raised pavement markers are listed in ATD 2015/01
label | ○ For new installation and complete replacement works, all markers must be identifiable for at least twelve months after the initial installation.
label | ○ For the adhesive provide a certificate of compliance verifying that the product complies with the specification, together with the results of the relevant tests.
label | REFERENCE DOCUMENTS - R142.2.1 3354.7
label | RECORD OF CONFORMITY - Verification Test Certificate
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 8 - Sampling and Testing Plan
label | FREQUENCY - Per Contractor
label | ACCEPTANCE CRITERIA - Submit to PV contractors proposed sampling plan for assessing the pavement marking
label | REFERENCE DOCUMENTS - R145.5
label | RECORD OF CONFORMITY - Sampling Plan
label | IP
date | Date Completed:
section | 9 - Application
checkpoint | 10 - Prepare the Surface for marking
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Curing compound on marking areas of concrete pavements is removed by grinding or blasting.
label | ○ Surface is compatible to the new line marking materials.
label | REFERENCE DOCUMENTS - R145.3.1
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 11 - Set out the works for installation of pavement markings / raised markers
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Notification made to the Project Verifier that the setting out to pavement markings and markers have been done in according with the design drawings
label | REFERENCE DOCUMENTS - R145.3.4
label | RECORD OF CONFORMITY - Hold Point
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Supervise the application of pavement marking / markers
label | FREQUENCY - Per Lot
label | ACCEPTANCE CRITERIA - Paints and markers installed as per manufacturer’s recommendations
label | ○ The same materials used with those nominated in the certifications
label | ○ All longitudinal lines have been applied by the nominated machine unless approved by Independent Verifier
label | ○ Markings are straight or with smooth, even curves where intended
label | ○ Edges are clean sharp cut off
label | ○ Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | ○ Beads uniformly applied onto the material immediately after it has been applied to the pavement & while the material is still molten
label | ○ Retention of bead material is achieved
label | ○ Markings are neat & free from traffic damage or other defects
label | ○ Arrows/markings painted at correct direction
label | ○ Marking protected from traffic until hardened
label | ○ Makers installed at the designated locations
label | REFERENCE DOCUMENTS - R145.3.2.2 R145.3.4 R145.3.6 R145.4 R142.3 R142.4
label | RECORD OF CONFORMITY - Verification Checklist
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 13 - Field test of the paint performance.
label | FREQUENCY - As Per Sampling Plan
label | ACCEPTANCE CRITERIA - Thickness of non-profile marking≤6mm
label | ○ Dry Retroreflectivity: min.250 mcd/lux/m2 up to 20 days after opening to traffic.
label | ○ Wet Retroreflectivity: min.80 mcd/lux/m2
label | ○ Skid resistance: min. 40BPN
label | ○ Colour change: min.3
label | ○ Luminance factor: ≥S 2500-N
label | ○ Wear: ≤70%
label | REFERENCE DOCUMENTS - R145.4 R145.5 AS 4049.5
label | RECORD OF CONFORMITY - Test Report
label | TP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP