## Table 1
Installation of Incline Ceiling Framing, Veneer battens, Autex insulation, perimeter pelmets.
Date:20/11/2024 | [5 empty] | Control Categories
Project Name: NFH |  |  |  | NFH |  | H = Inspection Hold Point |  | GM =General Manager
Scope: |  |  |  | Hospital St Feature ceiling |  | W = Witness Point |  | FM = Foreman
Client: |  |  |  | Multiplex Construction |  | S = Surveillance Point |  | PM = Project Manager
Location: |  |  |  | Ground Level |  | R = Review Document |  | QA = Quality Assurance
ITP prepared by: |  |  |  | Luke Lawry
Position: |  |  |  | Project Manager
Signature:
No: |  | Activity: | Acceptance Criteria: |  | Documentation: |  | CONTROL POINT |  |  | LL AUTHORISED PERSON
[7 empty] | LL |  | Multiplex
1 |  | Quality Assurance – Standards and Procedures | Submission for approval by the Primary Contractor (Client) Multiplex – Systems align with scope of works and contractual obligations - |  | LL installations Quality Assurance Plan and ITP’s – Contract |  | QA |  | R | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
| 2 | Issue Shop Drawings for Approval – | Review project documentation and specifications – Review Architects comments and revise until accepted. Engineering Computations where required - |  | Shop Drawings LL- NFH -001 to 004. Approved MODEL |  | QA |  | R | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
| 3 | Issue Shop Drawings for Construction- | Drawings have been reviewed by Architect, Multiplex and have been accepted – this may be in the form of approved with comments – Drawings are then updated and issued for construction- |  | IFC Shop Drawing – LL Installation Tracking Sheet – LL installation Shop Drawing Register – |  | QA |  | R | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
| 4 | Procure Materials | Samples are submitted to Multiplex and architect along with Tech Data – these need to be formally signed off by Multiplex prior to ordering any material – These materials need to be in accordance AS 1170.0-2002 AS 1170.1-2002 AS 1170.2-2011 AS 1170.4-2007 AS 4600 - 2005 AS 4100 -2020 NCC 2019 Volume 1 Building Regulations 2018 relative to their location and purpose. LL Installations to inspect supplier dockets to ensure to the use of the correct |  | Sample Submission Register – Formal approval Advice – Shop Drawings – Project Specifications – Purchase Order – Supplier Receipts & Sales Dockets – Warranties – Tech Data Sheets- Group Rating – |  | QA |  | R | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
material prior to manufacture and installation
5 |  | Set Fabrication sequence and Priority | Project Communications – Through collaboration and communication with Multiplex a program of works will be set, this will be formalised through the project communication platform Aconex- |  | Multiplex Project Program - Aconex Emails- LL Installation Tracking Sheet – LL installations Shop Drawing Register - |  | QA |  | R | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
[5 empty] | Relevant Trade ITP’s – |  | QA |  | H | PM
6 |  | Installation Of Acoustic Insulation- | Check surrounding area for safe working environment – to operate plant and perform the task – Multiplex has received partition contractors ITP’s and checked that wall framing complete and acceptable and in line with AS 4600 – Multiplex has also received all service trades ITP’s – The Ceiling framing is complete and fit for purpose and all preceding trades have completed their work including all acoustic requirements – the area is ready for the next sequential step and the area has been handover to LL installations by Multiplex – |  | Formal advice from the builder to proceed via Aconex- SWMS- Site Rules – As per Multiplex direction - |  | SIGN DATE |  | SIGN DATE | SIGN DATE
7 |  | Set out of Battens | Conforms with project documentation and approved shop drawings – Battens are set out to correct RL’s and dimensions from grid – All measuring instruments have been calibrated and a certificate of calibration has been forwarded to Multiplex - |  | IFC architectural drawings – Approved shop drawings – SWMS and Safety Documentation – Measuring Instrument Calibration Certification– |  | QA |  | W | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
8 |  | Installation of Battens - | Battens are installed as per approved shop drawings and project documentation, to the correct RL and dimensions off grid – Battens are plumb, level, square and in alignment – Battens are free of defects and are fit for purpose – Materials are correct to what has been specified - Multiplex has reviewed work and deems it acceptable – |  | IFC architectural drawings – Approved shop drawings – SWMS and Safety Documentation – Project Specifications – Material Certificates – Delivery Dockets- |  | QA |  | W | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
9 |  | Defect Rectification - | Multiplex formal sign off - Acceptance of works as completed -By Multiplex and Client - |  | IFC architectural drawings – Approved shop drawings – SWMS and Safety Documentation – Multiplex Enablon – O&M Manuals - Warranties- Reg 126 – where required – Engineer Certification – Where required - |  | H |  | H | PM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
10 | [6 empty] | QA |  | R | GM
[7 empty] | SIGN DATE |  | SIGN DATE | SIGN DATE
LL Installations PO BOX 942 Williamstown VIC 3016 I 35 Macaulay Street Williamtown North VIC 3016 I Ph: 03 9397 5647 I Fax: 03 9397 5305 I Mob: 0400 150 580 I ABN: 66 550 588 015