## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Installation of Incline Ceiling Framing, Veneer battens, Autex insulation, perimeter pelmets | itp
section | Details
checkpoint | 1 - Quality Assurance – Standards and Procedures
label | Acceptance Criteria - Submission for approval by the Primary Contractor (Client) Multiplex
label | ○ Systems align with scope of works and contractual obligations
label | Documentation - LL installations Quality Assurance Plan and ITP’s – Contract
label | Control Point: LL - QA
label | Control Point: Multiplex - R
label | LL Authorised Person - PM
checkpoint | 2 - Issue Shop Drawings for Approval
label | Acceptance Criteria - Review project documentation and specifications
label | ○ Review Architects comments and revise until accepted
label | ○ Engineering Computations where required.
label | Documentation - Shop Drawings LL- NFH -001 to 004. Approved MODEL
label | Control Point: LL - QA
label | Control Point: Multiplex - R
label | LL Authorised Person - PM
checkpoint | 3 - Issue Shop Drawings for Construction
label | Acceptance Criteria - Drawings have been reviewed by Architect, Multiplex and have been accepted – this may be in the form of approved with comments
label | ○ Drawings are then updated and issued for construction.
label | Documentation - IFC Shop Drawing. LL Installation Tracking Sheet. LL installation Shop Drawing Register.
label | Control Point: LL - QA
label | Control Point: Multiplex - R
label | LL Authorised Person - PM
checkpoint | 4 - Procure Materials
label | Acceptance Criteria - Samples are submitted to Multiplex and architect along with Tech Data – these need to be formally signed off by Multiplex prior to ordering any material
label | These materials need to be in accordance:
label | ○ AS 1170.0-2002
label | ○ AS 1170.1-2002
label | ○ AS 1170.2-2011
label | ○ AS 1170.4-2007
label | ○ AS 4600 - 2005
label | ○ AS 4100 -2020
label | ○ NCC 2019 Volume 1
label | ○ Building Regulations 2018
label | relative to their location and purpose.
label | LL Installations to inspect supplier dockets to ensure to the use of the correct material prior to manufacture and installation
label | Documentation - Formal approval Advice, Shop Drawings, Project Specifications, Purchase Order, Supplier Receipts & Sales Dockets, Warranties, Tech Data Sheets, Group Rating
label | Control Point: LL - QA
label | Control Point: Multiplex - R
label | LL Authorised Person - PM
checkpoint | 5 - Set Fabrication sequence and Priority
label | Acceptance Criteria - Project Communications – Through collaboration and communication with Multiplex a program of works will be set, this will be formalised through the project communication platform Aconex.
label | Documentation - Multiplex Project Program, Aconex Emails, LL Installation Tracking Sheet, LL installations Shop Drawing Register, Relevant Trade ITP’s
label | Control Point: LL - QA
label | Control Point: Multiplex - R
label | LL Authorised Person - PM
checkpoint | 6 - Installation Of Acoustic Insulation
label | Acceptance Criteria - Check surrounding area for safe working environment – to operate plant and perform the task
label | ○ Multiplex has received partition contractors ITP’s and checked that wall framing complete and acceptable and in line with AS 4600
label | ○ Multiplex has also received all service trades ITP’s – The Ceiling framing is complete and fit for purpose and all preceding trades have completed their work including all acoustic requirements – the area is ready for the next sequential step and the area has been handover to LL installations by Multiplex
label | Documentation - Relevant Trade ITP’s – Formal advice from the builder to proceed via Aconex, SWMS, Site Rules – As per Multiplex direction
label | Control Point: LL - QA
label | Control Point: Multiplex - H
label | LL Authorised Person - PM
holdpoint | HOLD POINT
checkpoint | 7 - Set out of Battens
label | Acceptance Criteria - Conforms with project documentation and approved shop drawings
label | ○ Battens are set out to correct RL’s and dimensions from grid
label | ○ All measuring instruments have been calibrated and a certificate of calibration has been forwarded to Multiplex -
label | Documentation - IFC architectural drawings, Approved shop drawings, SWMS and Safety Documentation, Measuring Instrument Calibration Certification
label | Control Point: LL - QA
label | Control Point: Multiplex - W
label | LL Authorised Person - PM
checkpoint | 8 - Installation of Battens
label | Acceptance Criteria - Battens are installed as per approved shop drawings and project documentation, to the correct RL and dimensions off grid
label | ○ Battens are plumb, level, square and in alignment – Battens are free of defects and are fit for purpose – Materials are correct to what has been specified
label | ○ Multiplex has reviewed work and deems it acceptable
label | Documentation - IFC architectural drawings, Approved shop drawings, SWMS and Safety Documentation, Project Specifications, Material Certificates, Delivery Dockets
label | Control Point: LL - QA
label | Control Point: Multiplex - W
label | LL Authorised Person - PM
checkpoint | 9 - Defect Rectification
label | Acceptance Criteria - Multiplex formal sign off
label | ○ Acceptance of works as completed By Multiplex and Client
label | Documentation - IFC architectural drawings, Approved shop drawings, SWMS and Safety Documentation, Multiplex Enablon, O&M Manuals, Warranties - Reg 126 – where required, Engineer Certification – Where required
label | Control Point: LL - H
label | Control Point: Multiplex - H
label | LL Authorised Person - PM
holdpoint | HOLD POINT