## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Curtain Wall Facade System Checklist |  | Curtain Wall Facade System Checklist | 6fb822f5-7e68-40ac-8576-ff955938aa39
| section | Pre-Install
| checkpoint | 1. Check Cast-In is acceptable
| checkpoint | 2. Check Structure opening pockets and soffit is correct and within design tolerance
| checkpoint | 3. Brackets are torqued (photos), Check the T bolts and Nuts are tightened.
| checkpoint | 4. Check bracket installed as per design (Bracket fixed to panel), if applicable, preferred to be checked by second person
| checkpoint | 5. Gutter plate and sleeve installed
| checkpoint | 6. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
| checkpoint | 7. Engage panel Sleeve across panel joint
| checkpoint | 8. Check façade pane is in good condition (photos), no damaged or defected. Any defect finding should be recorded. Document the rectification plan either repair or replace.
| checkpoint | 9. Glass cleaned ready for install
| checkpoint | 10. Apply the Safety glass stamp where is required but missed.
| section | Install
| checkpoint | 1. Panel in good caulking condition
| checkpoint | 2. Protection tape in good condition
| checkpoint | 3. No defects/scratch/dents/distortion/crack
| checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
| checkpoint | 5. Ensure bracket to panel hook locking screw installed (SS screw)
| checkpoint | 6. All Gaskets are installed and caulked neatly.
| checkpoint | 7. Gaps between concrete slab edge and façade panel insulation filled.
| checkpoint | 8. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
| checkpoint | 9. Check Panel and Expressed fin is aligning properly at the base of the façade.
| checkpoint | 10. Record panel ID on the floor plans or elevation
| section | Post-Install
| checkpoint | 1. Remove external protection and for gasket caulk only
| checkpoint | 2. check the curtain wall is in good condition. Address any defect issues and findings
| checkpoint | 3. Scratch or Damaged powdercoating surface are repaired.
| checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
| checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
| checkpoint | 6. Conduct Water test to stackhead (leave for 24hrs) as per inhabit required testing or minimum testing requirments
| checklist | Curtain Wall Facade System Checklist (L1) |  | Curtain Wall Facade System Checklist | e67beca3-8d0f-4a92-8899-c692d5677c72
| section | Pre-Install
| checkpoint | 1. Subsill and subhead in postion
| checkpoint | 2. Expansion bolts are fixed and nuts are tightened
| checkpoint | 3. Gaps between concrete and subsill subhead are sealed properly
| checkpoint | 4. Gutter plate and sleeve installed
| checkpoint | 5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
| checkpoint | 6. Check façade pane is in good condition
| checkpoint | 7. (For panels that require alteration), check mullion, aluminum panel and steel back-pan cut to right size
| checkpoint | 8. (For panels that require alteration), check transom is fixed to mullion properly
| checkpoint | 9. (For panels that require alteration), check aluminum panel and back-pan are fixed properly
| checkpoint | 10. (For panels that require alteration), check all joints are sealed properly (photo)
| checkpoint | 11. (For panels that require penetration), hole is cut as per request
| checkpoint | 12. Glass cleaned ready for install
| checkpoint | 13. Apply the Safety glass stamp where is required but missed.
| section | Install
| checkpoint | 1. Panel in good caulking condition
| checkpoint | 2. Protection tape in good condition
| checkpoint | 3. No defects/scratch/dents/distortion/crack
| checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
| checkpoint | 5. All Gaskets are installed and caulked neatly.
| checkpoint | 6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
| checkpoint | 7. Gaps between concrete and subsill subhead are sealed properly
| checkpoint | 8. Record panel ID on the floor plans or elevation
| section | Post-Install
| checkpoint | 1. Remove external protection and for gasket caulk only
| checkpoint | 2. check the curtain wall is in good condition. Address any defect issues and findings
| checkpoint | 3. Scratch or Damaged powdercoating surface are repaired.
| checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
| checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
| checkpoint | 6. (For panels that require penetration), hole is sealed properly
| checklist | Curtain Wall Facade System Post-Install Sign Off |  | Curtain Wall Facade System Post-Install Sign Off | d7d7ec4c-d677-46b1-bbcd-1d7f09672924
| section | Sign Off
| checkpoint | 7. Installer (Keystone) Sign off
| checkpoint | 8. Lingyun QC Sign off
| checkpoint | 9. Site supervisor Sign off