## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Window Wall Facade System Checklist | itp
section | Pre-Install
checkpoint | 1. Subsill and subhead in postion
checkpoint | 2. Expansion bolts are fixed and nuts are tightened
checkpoint | 3. Gaps between concrete and subsill subhead are sealed properly
checkpoint | 4. Gutter plate and sleeve installed
checkpoint | 5. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
checkpoint | 6. Check façade pane is in good condition
checkpoint | 7. Glass cleaned ready for install
checkpoint | 8. Apply the Safety glass stamp where is required but missed.
section | Install
checkpoint | 1. Panel in good caulking condition
checkpoint | 2. Protection tape in good condition
checkpoint | 3. No defects/scratch/dents/distortion/crack
checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
checkpoint | 5. All Gaskets are installed and caulked neatly.
checkpoint | 6. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
checkpoint | 7. Gaps between concrete and subsill subhead are sealed properly
checkpoint | 8. Record panel ID on the floor plans or elevation
section | Post-Install
checkpoint | 1. Remove external protection and for gasket caulk only
checkpoint | 2. Check the curtain wall is in good condition. Address any defect issues and findings
checkpoint | 3. Scratch or Damaged powdercoating surface are repaired.
checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
checklist | Curtain Wall Facade System Checklist | itp
section | Pre-Install
checkpoint | 1. Check Cast-In is acceptable
checkpoint | 2. Check Structure opening pockets and soffit is correct and within design tolerance
checkpoint | 3. Brackets are torqued (photos), Check the T bolts and Nuts are tightened.
checkpoint | 4. Check bracket installed as per design (Bracket fixed to panel), if applicable, preferred to be checked by second person
checkpoint | 5. Gutter plate and sleeve installed
checkpoint | 6. Check panels are correct size/type for the planning to be installed location. All nessecary items are in place.
checkpoint | 7. Engage panel Sleeve across panel joint
checkpoint | 8. Check façade pane is in good condition (photos), no damaged or defected. Any defect finding should be recorded. Document the rectification plan either repair or replace.
checkpoint | 9. Glass cleaned ready for install
checkpoint | 10. Apply the Safety glass stamp where is required but missed.
section | Install
checkpoint | 1. Panel in good caulking condition
checkpoint | 2. Protection tape in good condition
checkpoint | 3. No defects/scratch/dents/distortion/crack
checkpoint | 4. Panel installed and fixed in position as specified. Panels installed within tolerance (+/-1.5mm in plan, +/-1.5mm in elevation)
checkpoint | 5. Ensure bracket to panel hook locking screw installed (SS screw)
checkpoint | 6. All Gaskets are installed and caulked neatly.
checkpoint | 7. Gaps between concrete slab edge and façade panel insulation filled.
checkpoint | 8. Smoke flashing installed and sealed as per design. Overlap of sheeting and corretly caulked as per specifications
checkpoint | 9. Check Panel and Expressed fin is aligning properly at the base of the façade.
checkpoint | 10. Record panel ID on the floor plans or elevation
section | Post-Install
checkpoint | 1. Remove external protection and for gasket caulk only
checkpoint | 2.Check the curtain wall is in good condition. Address any defect issues and findings
checkpoint | 3. Scratch or Damaged powdercoating surface are repaired.
checkpoint | 4. Record defect panel on inspection report including panel ID. Mark the defect panel on the back of the panel
checkpoint | 5. Record un-installed panel and any un-installed item on the report. Clearly markup the items and ownership of left over items and place them into the safe place for future use.
checkpoint | 6. Conduct Water test to stackhead (leave for 24hrs) as per inhabit required testing or minimum testing requirments
checkpoint | 7. Installer (Keystone) Sign off
checkpoint | 8. Lingyun QC Sign off
checkpoint | 9. Site supervisor Sign off