## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-023 Light & Security Pole Foundations - Rev.1 | itp |  |  |  |  | INF-HSEQ CC0375-ITP-023 Light & Security Pole Foundations - Rev.1
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Drawings
label | Acceptance criteria - Check the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Set out
label | Ref docs - Drawings
label | Acceptance criteria - Setout to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.4 - DCP Test
label | Ref docs - Drawings Note 8
label | Acceptance criteria - Conduct DCP test for each pole location.
label | ○ Allowable minimum bearing capacity =100kPA must be verified by a qualified Geotechnical Engineer.
label | ○ Ground improvement shall be made If existing soil profile is inadequate.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Geo report
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Base Bore
checkpoint | 2.1 - Bore Excavation
label | Ref docs - Drawings
label | Acceptance criteria - Bore to the correct diameter and depth nominated on the drawings and remove any loose material at the base.
label | ○ 450mm – Light Pole & Joint Use Pole
label | ○ 600mm – Security Pole
label | ○ Depth to be verify by qualified Geotechnical Engineer.
label | ○ Base must be clean and dry to be inspected by the Superintendent.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Formwork Sleeve
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.3] Drawings
label | Acceptance criteria - Formwork to be set as per drawings and adequately supported and RL checked.
label | ○ Completed formwork to be inspected by the Superintendent prior to concrete placement.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pre-pour inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of reinforcement cage, HD Bolts and Earth Lugs (Supplied by Client)
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.5] Drawings
label | Acceptance criteria - Ensure that cage is clean and straight. Plunge the cage centrally to bore hole and ensure spacers are attached at correct locations.
label | Reinforcement cages and embedment to conform with drawings and specification.
label | ○ 4-M20 HD Bolts grade 8.8/S
label | ○ 500mm min embedment
label | ○ 130mm projection
label | Or
label | ○ 4-M24 Bolts grade 4.6/S
label | ○ 600 min embedment
label | ○ 150mm projection
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pre-pour inspection
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Concrete
checkpoint | 3.1 - Concrete supply and placement
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11] Drawings
label | Acceptance criteria - Concrete strength of cast in-situ units shall be min. Grade N32 or as otherwise stated on drawings.
label | ○ Design slump shall not exceed 75mm unless shown otherwise on the drawings.
label | ○ Ensure the temperature of freshly mixed concrete is maintained in between 5°C and 35°C. Ensure elapsed time between batching and discharge of the mix complies with the below table.
label | – – – – – – – – – – – – – – – –
label | Concrete temp at discharge (°C) ¦¦ Max elapsed time (hours)
label | – – – – – – – – – – – – – – – –
label | 10-24 ¦¦ 2.00
label | 24-27 ¦¦ 1.50
label | 27-30 ¦¦ 1.00
label | 30-32 ¦¦ 0.75
label | – – – – – – – – – – – – – – – –
label | ○ Concrete placed in layers ≤ 300mm thick and adequately vibrated avoiding over-vibration.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material dockets
checkpoint | 3.2 - Concrete sampling
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2]
label | Acceptance criteria - The nominal rate of sampling shall be taken:
label | (a) Compressive strength: One set per pour or as otherwise directed by the Superintendent;
label | (b) Slump: One per batch of concrete
label | ○ Average compressive strength at 28 days meets minimum design requirements. Slump within tolerances specified in AS 1379
label | – – – – – – – – – – – – – – – –
label | Specified Slump (mm) ¦¦ Tolerance (mm)
label | – – – – – – – – – – – – – – – –
label | <60 ¦¦ ± 10
label | ≥60 ≤80 ¦¦ ± 15
label | >80 ≤110 ¦¦ ± 20
label | >110 ≤150 ¦¦ ± 30
label | >150 ¦¦ ± 40
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material dockets
section | 4.0 Conformance check
checkpoint | 4.1 - Survey
label | Ref docs - Spec. 0003 Piling [3.10]
label | Acceptance criteria - All piles shall be constructed within the tolerance specified below:
label | ○ The centreline at the top of the piles shall be within 50mm of the specified position
label | ○ The tolerance on the level of the top of the piles shall be ± 10mm
label | ○ Piles shall be constructed to the minimum diameters specified on the drawings
label | ○ Length of pile/pile liner shall not be less than total length shown on drawings
label | ○ Review survey as build report.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - R
label | HPP QA Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As-Built Surveys
checkpoint | 4.2 - Concrete Test Results
label | Ref docs - Spec. 0002 [Cl 8.2]
label | Acceptance criteria - Certificates received, reviewed and conforming to requirements for each pour.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - R
label | HPP QA Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 4.3 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT