## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  | Yes | DG-QA-TP018 Inspection and Test Plan (ITP) | 45f2bc5c-246a-49b0-923f-48e53609874b
checkpoint-group |  |  | section | 1. Receiving Inspection
checkpoint-status |  |  | checkpoint | 1.1 - Service Locates
label | 6045ad6a-b573-5325-b704-71fa8eeb436e |  | note | Acceptance Criteria - Services located by Chorus and Delta prior to wokrs commencing
label | b3525edd-839b-55b4-a9b6-0e5ab7fc7b9e |  | note | Verifying Document - Photos
label | 0fad300b-f57a-537b-a09c-b28c1536e21d |  | note | Frequency - Once for each work location
label | 78b6f9a8-3424-5033-90d1-dea405906776 |  | note | Inspection Type (Visual, other) - Verification
label | f66a400a-bf2e-5752-900d-00543df0b5f1 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.2 - Temporary Traffic Management
label | e68c8162-3887-5256-8efa-586e6f634e3a |  | note | Inspection Point: Quality Control Activity - Temporary Traffic Management to be set up on site prior to any works commencing
label | fbf3213b-ecb3-52c6-b5db-305eebafb5dc |  | note | Acceptance Criteria - Temporary Traffic Management set up by qualified STMS according to approved plans
label | 13ff03fd-c3b4-5ed7-a425-8b094e2a542d |  | note | Verifying Document - Approved TM Plan
label | 2722667a-66ea-53ca-825c-3a5b286576d0 |  | note | Frequency - Daily
label | 57134c83-66af-5bed-8ac0-379b65484adb |  | note | Inspection Type (Visual, other) - Verification
label | c38cd082-f883-539d-b7be-f87c4105ece7 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.3 - Culvert Bedding
label | 54ac98e7-e2ea-540b-9412-95948af6592a |  | note | Inspection Point: Quality Control Activity - Scalas to be done on subgrade
label | 49988d8d-955b-52fc-9144-58b8a6d6aa37 |  | note | Acceptance Criteria - If scala test results lower than 3, add 100mm of compacted AP65
label | fd9f4b41-51b0-5e9e-96dc-eec787d62825 |  | note | Verifying Document - Photos, Field testing document
label | f09540a0-bde4-5fb1-a51d-a2502e066ac2 |  | note | Frequency - One lot of tests for each work location
label | 3a797265-f1ee-5f2b-b87a-a2f7df9f0fe6 |  | note | Inspection Type (Visual, other) - Hold Point
label | 0e8e5a55-50e8-5672-a3b9-42ef3ffeefb5 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.4 - AP65 Backfill
label | 65d4c908-52f4-538b-81dc-d944f18261b1 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | baae139e-6ef1-5605-afd6-b061b8f5f0fc |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 25
label | 6f3ee88b-e357-51a0-8dfc-d3fda5f58fac |  | note | Verifying Document - Photos, Field testing document
label | 8834281f-396c-518a-aa81-0d40edb36a22 |  | note | Frequency - Every 150mm lift
label | e43b16b3-ff51-5a91-a8e3-05229798d2c9 |  | note | Inspection Type (Visual, other) - Hold Point
label | a0e6e6a7-136d-5c1b-8589-6bce74d4b463 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.5 - AP40 Backfill
label | 2967c5b8-595d-5abd-8fe5-a0251daa99c1 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | 28a7fd18-656c-5419-8f4e-8cb41a4d815f |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | de3c786f-5f82-5301-b1fc-1867a0627307 |  | note | Verifying Document - Photos, Field testing document
label | 0e77f767-1dd7-55ee-8d83-60f84c907d4d |  | note | Frequency - Every 150mm lift
label | 97948f30-dd5f-58ea-bfb3-2ab30f0e03dc |  | note | Inspection Type (Visual, other) - Hold Point
label | 1cd7386a-021f-5157-83b5-da8c70136d32 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.6 - Pavement Strength
label | e33835f6-2856-5d1a-8f17-62660e0b629e |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on Pavement
label | 06834782-f401-5e2d-bddf-59e9eade8dae |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | 0b376344-9917-5c4a-bc46-fc7132990bf7 |  | note | Verifying Document - Photos, Field testing document
label | 07c982ed-2556-5943-a48d-5026ad09e2af |  | note | Frequency - One lot of tests for each work location
label | 2699fe34-8793-5ba1-88a8-21bbc98953a1 |  | note | Inspection Type (Visual, other) - Hold Point
label | 73f9effc-830e-5ace-a902-483bcf9d145c |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.7 - Alignment
label | e784c8cf-0e23-5199-9483-78af6e9c3346 |  | note | Inspection Point: Quality Control Activity - 3 metre straight edge
label | 5a689631-2d88-5cce-bdc5-00abd06d0515 |  | note | Acceptance Criteria - Maximum 10mm
label | debb4dd8-7b33-5a3a-8ff3-bfa2bb578038 |  | note | Verifying Document - Visual
label | 28d4823c-efe9-58f9-917f-11f05c436355 |  | note | Frequency - One lot of tests for each work location
label | 22726955-649b-5b97-a45d-80e0a2e5fb0c |  | note | Inspection Type (Visual, other) - Verification
label | 204b270c-7136-5b27-8b22-4f72166e7db1 |  | note | Inspection: By (Role Key) - Downer
checkpoint-group |  |  | section | 2. Culvert Grade
checkpoint-status |  |  | checkpoint | Culvert Grade
checkpoint-group |  |  | section | 3. Photos
checkpoint-status |  |  | checkpoint | Photos
checklist-sectioned |  |  | checklist | CC0394 - ITP-013 - Fencing and Acoustic Wall Construction REV01 |  |  |  |  | Yes | CC0394 - ITP-013 - Fencing and Acoustic Wall Construction REV01 | c1fec3c0-e516-450d-9fc2-b81571d209c8
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Safety
label | c5d9c5b2-e55b-5fbc-b74b-8ef09e4d0cb1 |  | note | Ensure that the following items have been actioned: SWMS if applicable; Plant Pre-start Inspection; Service locations identified; Traffic Management Plans (if required); All staff inducted
label | f5151e71-59a7-5031-82f3-0eb3d6cb2535 |  | note | Ref docs - SMP
label | a45688ca-947b-5bf3-82e6-1382eeb56c4e |  | note | Acceptance criteria - SWMS submitted reviewed and accepted if required. Plant inspections completed and entered. Pre-work briefings completed. Service Diagrams available and services located. Has all of the above been completed?
button | d1f65f37-ca58-5b29-a01f-df4b87e7c643 |  | button | Acceptance | Yes, No, N/A
label | 02ec33b9-1341-5296-8de0-02abf044a1d6 |  | note | Freq - Once (Pre-Start)
label | 6e8d6a36-4de8-5cce-838b-b842988acffe |  | note | Verification of acceptance by Symal - Key - H
label | c5de2983-265b-5a9d-9aca-5215001277d2 |  | note | Resp - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Relevant Permits Required
label | ace230d5-c0d9-537f-aeaf-0335ce600b9f |  | note | Ref docs - SMP
label | 3d9984a8-9920-5cfe-83ab-690d777c0e4c |  | note | Acceptance criteria:
boolean | c447a2df-b236-5d11-b504-20b349ad976d |  | tickbox | Permit to Work.
boolean | 1e3a5527-42b5-58c6-96c6-fb6eb3052006 |  | tickbox | Penetration Permit
boolean | 10da44ec-79c1-5f1a-8a00-f59396c298f9 |  | tickbox | Hot Works Permit
boolean | ef38e683-12a9-5d84-88e6-a20b74e3615b |  | tickbox | DBYD
boolean | 4be1f42f-a89a-5898-b7f8-d295777b3e13 |  | tickbox | Excavation Permit.
boolean | 00cdbb2c-4658-5d4f-8291-50be08c738ad |  | tickbox | Vegetation Removal Permit.
label | 22e2bab1-4710-5403-80c9-24e0f8b002b2 |  | note | Have any/all of the above permits been acquired/completed and signed off?
button | 47ca6468-b8ff-5928-836f-7dfc2eec8fa8 |  | button | Acceptance | Yes, No, N/A
label | 506830b0-c5c6-5553-87a9-1d5c99f6baf7 |  | note | Freq - Prior to start of works
label | a4811c51-ddbc-5370-8697-12c955801d99 |  | note | Verification of acceptance by Symal - Key - H
label | 38030f12-33c7-598f-b498-bdf40e452fab |  | note | Resp - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Fencing Materials
label | 177bc0dc-afa9-5de0-a14e-f33d6bb961d4 |  | note | Ref docs - IFC Drawings
label | 956d933d-37f0-5f79-b7d9-69009a525534 |  | note | Acceptance criteria - Fencing or acoustic wall Material complies with specifications and IFC Drawings. Do the construction materials comply with regulations and drawings?
label | 917d3291-d944-57ec-8315-272a1e30f022 |  | note | Fencing Type (Select 1):
boolean | 4debbabe-5065-533b-914d-14b5d9eaf899 |  | tickbox | 2900mm Palisade fence – Black powder coated
boolean | 1ff1a209-34f9-46f6-bfaf-b810dbdd3697 |  | tickbox | 3600mm Acoustic wall post & panel (including 1200mm retaining wall)
boolean | aad3f530-6537-48f1-b745-ac9e8f020df7 |  | tickbox | 4500mm Acoustic wall post & panel
boolean | aa27d82a-1db5-4621-a0ac-691ff552e441 |  | tickbox | 2400mm Acoustic wall post & panel
boolean | 97d31ba3-1eb0-42d1-861c-6fb0331a5185 |  | tickbox | 1800mm Chain mesh fence
boolean | 0a3ca4e7-d3eb-5a26-864b-51f70b7279a7 |  | tickbox | Palisade sliding gate
button | d6d1a04a-87be-5ad5-b3cc-4635c7510351 |  | button | Acceptance | Yes, No, N/A
label | 5334678d-dd7f-562b-8c48-090b39b247e7 |  | note | Freq - Prior to start of works
label | 4a15bb3a-d9d8-51a4-a324-239b4aefe3e8 |  | note | Verification of acceptance by Symal - Key - H
label | 2f34c946-9c5d-5301-8503-6857f0a8f3d2 |  | note | Resp - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Preparation
checkpoint-status |  |  | checkpoint | 2.1 - Clearing Fence Alignment
label | 36e926db-bccf-5d56-8713-442dc21dfb2c |  | note | Acceptance criteria - All logs, stumps, saplings, and undergrowth within 1 m of the fence line, and all trees which will interfere with the proper construction of the fence shall be removed and disposed of safely and correctly. High points shall be cut down to provide the clearance shown on IFC drawings and low spots shall be filled with surplus earth from holes and trimmings. Has all of the above been completed safely and correctly to IFC drawings?
button | 82224463-ebd6-5eb8-8bca-ac68e870edfe |  | button | Acceptance | Yes, No, N/A
label | 25fea686-d733-5828-9725-005d7567fc19 |  | note | Freq - Each possession
label | 846dca06-17b0-5cb3-89cc-a140b42fbad2 |  | note | Verification of acceptance by Symal - Key - I
label | be0ec81d-7305-5415-8f1f-2e3d4c918f1f |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - Set out
label | 5ed41ca6-4af5-5ec5-9af8-f07f5b0defe5 |  | note | Ref docs - IFC Drawings
label | 96654af6-6ddb-5bcc-81c7-3a6d5b29c1db |  | note | Acceptance criteria - Surveyor to set fencing alignment and individual post/sleeve set out in accordance with IFC alignment plan/design model. Has all of the above been completed safely and correctly to IFC drawings?
button | 4aa7abaf-8e1f-5652-b4c6-3fd858b988cf |  | button | Acceptance | Yes, No, N/A
label | 6e0c5e4e-517d-5aaf-a25f-0b22353fb366 |  | note | Freq - Each possession
label | 904543e3-c166-5a05-84e4-d9e3fa9d3a73 |  | note | Verification of acceptance by Symal - Key - I
label | 3cec873a-99fb-5f15-9f88-a73791c21251 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.3 - Checking fencing alignment
label | a15f061f-9763-579b-928f-cbc563be9f78 |  | note | Ref docs - IFC Drawings
label | 7073c44c-35a9-57d9-ab3c-4f41004741c9 |  | note | Acceptance criteria - Physically check survey set out of fencing alignment. Has the above been completed complies to IFC drawings ?
button | a6cdf53c-f51e-5dee-8165-8e4c9cf0eef4 |  | button | Acceptance | Yes, No, N/A
label | 12919959-5f76-5fff-8306-687c2f648e1a |  | note | Freq - Each possession
label | 2c2fb60d-f8aa-5d96-8f6d-1c22ebc50252 |  | note | Verification of acceptance by Symal - Key - I
label | 6a299cbe-84c3-5683-a52e-12a4d0c479be |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Footing and Post Construction
checkpoint-status |  |  | checkpoint | 1.2 - Set out
label | 1d10197b-9b2f-5621-b987-c187dced90a5 |  | note | Ref docs - IFC Drawings
label | 64e4da87-2d3b-5324-b4cd-c4e840b0cf55 |  | note | Acceptance criteria - Has the footing location and height been set out by a Surveyor?
button | dfa99a16-f8bb-51e8-9303-93d4f67b9e53 |  | button | Acceptance | Yes, No, N/A
label | 4584d2df-d455-5e5e-a784-68ee3627690c |  | note | Verification of acceptance by Symal - Key - S
checkpoint-status |  |  | checkpoint | 2.2 - Excavation of hole
label | ac047b35-247d-52f0-9ac5-badb91aa7bc6 |  | note | Ref docs - IFC Drawings
label | 22f8248f-3886-572a-943d-096aad315f89 |  | note | Acceptance criteria - Hole to be excavated to the depth and diameter specified in the design drawings. The design dimensions are:
text | 9b768947-0beb-5f1b-832f-1137d205c1a5 |  | textbox | Depth:
text | 31eea89a-3b19-5280-81a1-44d661a9c9d5 |  | textbox | Diameter:
label | 27e40e65-ca65-50e8-916d-09a76074c731 |  | note | Verification of acceptance by Symal - Key - S
checkpoint-status |  |  | checkpoint | 2.3 - Inspection of hole
label | 911cef4c-4f47-5954-b3e7-d4fbfa1f2d2d |  | note | Ref docs - IFC Drawings
label | f43d2fb9-b4e4-5988-841e-ee87c29c2dab |  | note | Acceptance criteria - Is the hole clean and free of debris & water?
button | aeae6087-8522-5e9d-a9d6-7c3f543b7275 |  | button | Acceptance | Yes, No, N/A
label | e01e8a05-aa1f-5fdb-a4b6-e7611a0067fa |  | note | Verification of acceptance by Symal - Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Concrete pour
label | 335bca2d-01b4-5250-a45f-a64874ccfdd3 |  | note | Ref docs - IFC Drawings
label | 11257bf8-4dea-5bbb-a20e-77a8b9c24ea4 |  | note | Acceptance criteria - Confirm concrete grade is 25 Mpa [KN3] or better.
button | 5bdb18fb-d90c-5a7d-9597-98a0dd320c1c |  | button | Acceptance | Yes, No, N/A
label | 261a9bfe-aa0b-575a-82fa-edd97488fddb |  | note | Verification of acceptance by Symal - Key - H
boolean | 2fa4e115-9e98-5cb2-8390-9df129a52668 |  | tickbox | Remarks/record - Concrete docket attached
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Installation of post
label | 625f4d6f-4618-51d5-98f8-e1d2d59255cb |  | note | Ref docs - IFC Drawings
label | 578f5e44-fa98-505e-8690-2e4195990afc |  | note | Acceptance criteria - The fence post will be inserted into the footing and measured for verticality with spirit level. Has all of the above been completed safely and correctly?
button | 7eded736-1e45-5aea-a9b5-999ec6765aee |  | button | Acceptance | Yes, No, N/A
label | 7b28113e-cd5e-5ac8-bd5d-ba357c0996f9 |  | note | Freq - Each possession
label | e639e25b-6e73-5bbd-b672-6069be12bcf2 |  | note | Verification of acceptance by Symal - Key - I
label | aaa8b1ef-3384-5465-ab08-08c47af013b2 |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0 Fence Construction
checkpoint-status |  |  | checkpoint | 4.1 - Concrete curing
label | 6e5f2a09-6f86-56c7-ae60-13d38fe3a3ec |  | note | Acceptance criteria - Has concrete been allowed to cure for at least 24hrs prior to proceeding?
button | bf95331b-0d65-53ec-999d-7d7fe2ffcce0 |  | button | Acceptance | Yes, No, N/A
label | 73e15420-e209-5a21-b6b9-10bdb6daba28 |  | note | Verification of acceptance by Symal - Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Installation of tension Wires and Bracing
label | f890fb3f-b7b5-5a83-9f8c-b743f8f79a75 |  | note | Ref docs - IFC Drawings
label | 45fe17e4-0c05-54de-b597-6fa2b7c9b317 |  | note | Acceptance criteria - Once post have been installed, tension wire is to be installed as per IFC drawing. CHS Brace to be installed at the end bays and Corners fixed at each end via approved proprietary post and rail clamps. Has all of the above been completed safely and correctly?
button | f400fb0f-b4c4-5285-a975-2e10aecfbf3e |  | button | Acceptance | Yes, No, N/A
label | 0c23e204-9cf6-5307-a977-08d271b22b4c |  | note | Freq - Each possession
label | 9e0d378c-18d9-5629-a4cd-01ecf46867b2 |  | note | Verification of acceptance by Symal - Key - I
label | 077db618-48df-563f-ade0-38a01f06ee31 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.3 - Installation of Wire Mesh
label | 5839959c-3760-5430-8872-9dc7a297ba5b |  | note | Ref docs - IFC Drawings
label | 3ed6c88b-b761-521e-aa5c-556bbb8af92b |  | note | Acceptance criteria - Chain mesh to be installed as per IFC Drawing. Chain wire mesh shall be tightened and securely fastened to posts and spaced at not more than 400 mm intervals online posts and at not more than 500 mm intervals online wires. Has all of the above been completed safely and correctly?
button | 5a2581d4-fec1-5ce4-bc96-308c51aed2e3 |  | button | Acceptance | Yes, No, N/A
label | a877ee4b-340e-5916-a978-7ceeb261d1c6 |  | note | Freq - Each possession
label | a307c58a-fcaa-5735-b55e-fd702b419166 |  | note | Verification of acceptance by Symal - Key - I
label | af4b49f3-8677-5f65-8919-751917ed74a7 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.4 - Installation of acoustic and retaining wall panels
label | bfe8d0e2-a5aa-5e87-b4cb-4c047712ce7d |  | note | Ref docs - IFC Drawings
label | 5e3e46ac-bf21-52f6-b85e-8297857d9518 |  | note | Acceptance criteria - Panels have been installed so that the faces between panels are flush at the joints. Panels have been checked for verticality using a spirit level.
button | 13f7c9ec-377d-56c2-bce2-1da889176f1e |  | button | Acceptance | Yes, No, N/A
label | cc375b90-aeb1-5665-9bac-9571518bb20a |  | note | Freq - Each possession
label | a1e7c052-b7a8-52c5-9aa1-b90ab9394291 |  | note | Verification of acceptance by Symal - Key - I
label | 9e0993a6-779e-5b09-8754-2b147c36b8ed |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.5 - Installation of Gates
label | ffa7b321-6531-520a-a1e4-57a388eec560 |  | note | Ref docs - IFC Drawings
label | 00124c88-100f-5c98-adee-081302abc7d1 |  | note | Acceptance criteria - Install gates of the type, size and location as specified on IFC Drawings. Gate posts are to be of the dimensions and firmly set in the ground to the depth specified on IFC drawings. All gates shall be hung with galvanized hinges securely attached to gate posts and be able to swing freely. Has all of the above been completed safely and correctly?
button | 5609be51-74fa-5592-ad48-4f86091c4077 |  | button | Acceptance | Yes, No, N/A
label | e286dd79-526d-5e04-aac1-2fd2275dda06 |  | note | Freq - Each possession
label | 8f2f2e7a-6cca-532f-9669-3ebdc0b6a8c3 |  | note | Verification of acceptance by Symal - Key - I
label | f28f6ba5-0fe9-5422-9c1d-d973e614fec9 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.6[KN4] - Earth grid
label | 8921a99b-0664-5a7c-b9c0-c12b50d6a44e |  | note | Ref docs - IFC Drawings
label | 96053640-a4a1-5e9a-b628-c1cf78093130 |  | note | Acceptance criteria - Have earth tabs been welded to the fence at every third post?
button | d1741e56-eeee-5510-ab74-7185fc237c7b |  | button | Acceptance | Yes, No, N/A
checkpoint-status |  |  | checkpoint | 4.7 - Backfill behind retaining wall panels
label | b69bb61d-2117-5f20-86d1-7783e29f97af |  | note | Ref docs - IFC Drawings
label | 9545baa7-2ebe-5283-ad04-a021620beb66 |  | note | Acceptance criteria - Has soil behind the retaining wall been compacted as per the IFC drawings:
text | 66a21988-80b9-5ef6-a311-107c49b41998 |  | textbox | Lift depth:
boolean | 9fe66aa0-ede2-5016-b5b2-3a8c01109328 |  | tickbox | Remarks/record - Compaction test report attached
checkpoint-status |  |  | checkpoint | 4.8 - Construction Tolerances
label | 82ce3f54-bb1d-56e0-a775-2a4937b652bb |  | note | Ref docs - IFC Drawings
label | c73a3144-d540-5d8e-991c-90640f6a5f64 |  | note | Acceptance criteria - Unless stated otherwise, tolerances for the construction of fencing shall be as follows: (a) the vertical tolerance on the height of fencing shall be ± 20 mm from the design line. (b) the longitudinal line tolerance for fencing shall be ± 20 mm in plan view; and (c) the tolerance on the verticality of fencing shall be 1 in 50. Has all of the above been completed safely and correctly?
button | 00946170-8082-59dc-a2a8-266cb983501b |  | button | Acceptance | Yes, No, N/A
label | 478c460a-dfef-5d7c-8ff9-edc593fadb8d |  | note | Freq - Each possession
label | c91ef68c-4c71-545e-92ff-127bcc1d2823 |  | note | Verification of acceptance by Symal - Key - I
label | 048c7646-e7e0-5c64-a6d1-f5b6aa8bf750 |  | note | Resp - SE
boolean | a8f6321a-053f-597a-9bb8-90edb8ddc01e |  | tickbox | Remarks/record - Survey Conformance Report
boolean | 501b05bb-38d5-5356-af7c-ff10ba5f9e19 |  | tickbox | Remarks/record - Third Party Compliance of installed fencing
checkpoint-status |  |  | checkpoint | 4.9 - Signage
label | 652f677c-182e-52e7-9aec-341aa4b0105f |  | note | Ref docs - IFC Drawings
label | 947e4d2f-a7b0-5882-87d5-4c3f4da4649c |  | note | Acceptance criteria - Have ‘Danger, High voltage, authorised personnel only’ signs been attached to the fence?
button | 87b17027-f142-5c2b-8193-a90c66425cee |  | button | Acceptance | Yes, No, N/A
label | d84943a0-a9e5-5ffa-8010-e85b966ecb90 |  | note | Verification of acceptance by Symal - Key - I
label | 1d6775ac-8688-5360-849a-8a0d515149ca |  | note | Resp - SE
checkpoint-group |  |  | section | 5.0 Work Lot Close Out
checkpoint-status |  |  | checkpoint | 5.1[KN5] - Quality Representative to check the above criteria and records to confirm
label | c70e1887-8d5a-514a-977a-a90581ef4d03 |  | note | Acceptance criteria - All above criteria met, and records identified attached.
button | dcc3d1d2-e8c5-53e3-90d7-f91f2aebca67 |  | button | Acceptance | Yes, No, N/A
label | 1ea2b7a6-5741-5b65-b69c-1e01679ec449 |  | note | Freq - Each lot
label | 7220aeca-d75a-54f8-bd1b-c2156ecedcfe |  | note | Verification of acceptance by Symal - Key - R
label | 79e4717f-5163-5fb5-82c5-7256b26a8edc |  | note | Resp - SE
label | 273738ce-f45e-5e89-983f-a7c9f04a50cc |  | note | Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint-status |  |  | checkpoint | 5.2 - As-Builts
label | 21c9b98f-a066-5fff-ae03-a3c8e52881f7 |  | note | Ref docs - IFC Drawings
label | f571be63-b7f8-5665-b5a4-a46890be2b21 |  | note | Acceptance criteria - As-built survey of work lot attached. All points within tolerance.
button | 33f2bc2a-72c3-5391-acce-37b6a1df4444 |  | button | Acceptance | Yes, No, N/A
label | 83458a18-5e98-51c8-a6e9-c3bf44c31dda |  | note | Freq - Each lot
label | c3aa7ecf-f458-528b-af91-c5b52004364f |  | note | Verification of acceptance by Symal - Key - H
label | 24a72560-d21f-552c-8846-a34df88bf9c1 |  | note | Resp - SE
boolean | 1a3900e9-d9e2-55f2-91b8-fb48fc1a6502 |  | tickbox | Remarks/record - As-Built Attached
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT