## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-110-CIV-SSB-Ground Improvement (Structural Fill)
ITP Description: |  | SSB-Ground Improvement (Structural Fill)
Discipline (e.g. CIV/STR/RAIL: |  | 110-CIV
Revision Number: |  | 0
Revision Date: |  | 2023-11-24
ITP created by: |  | Hiruni Wickramarathne
ITP approved for use by: |  | Victor Mera
Special Notes to ConQA Team : |  | ITP for Beaconsfield Project
Inspection & Test Plan - Ground Improvement Works (Structural Fill)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-11-24
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 204 (Dec 2015) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 |  | IFC Report and Drawings
1.3
2 | Preliminaries
2.1 | Material Approval | Section 204.04 Table 204.041 IFC drawings | Structural Fill Material shall meet the following requirements: Scale C CBR ≥ 6% Swell ≤ 1.5% Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided) PI (LL) = 6 - 25 Effective Friction Angle = 32* Effective Cohesion = 0-5kPa Unit weight ≥19kN/m3 Grading: % passing 75.0mm sieve = 100 % passing 4.75mm sieve = 40 - 80 % passing 0.075mm = 10 - 40 Enter: Teambinder Material Approval number [free text box] | Review and Verify | Once per material type prior to commence of works | HP | Nominated Authority | ConQA Hold Point Release
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | Section 204.03 IFC drawings | Survey pegs in place and clearly marks out the limits of the Works. | Measure Visual | Each element | IP | SE/Site Supervisor | Sign ITP
4 | Cut Activities
4.1 | Subgrade Level | Section 204.03 (g) Section 204.03 (h) IFC drawings | Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant Ground Improvement drawings within the following limits: For Scale C No point of subgrade surface shall be more than 10mm above or 30mm below the specified level. | Measure | Each lot | IP | Surveyor/SE/Site Supervisor | Sign ITP Survey Pick Up Report
4.2 | Founding Material testing | IFC Report and Drawings | DCP test to be carried out on the excavated surface to confirm the strength of the existing material is in accordance with Deisgn values for relevant chainages as below. Min DCP required /100mm 10000-10030 : 5 ( South) 10300-10320 : 7 (North) 10320-10360 : 6 (North) 10360-10400 : 5 (North) 10400-10410 : 3 (North) | Document Review | Each lot | HP | Third party Geotech Engineer /SE/Site Supervisor | ConQA Hold Point Release Test Report
4.3 | Proof Roll | Section 204.10 (b) Section 204.12 IFC drawings | Excavated subgrade to be compacted and proof rolled before any construction. Withstands Test rolling without visible deformation or springing. No fill to be placed until the area has been reviewed and approved. If Proof Roll fail go to section 4.4 | Visual | Each lot | HP | Nominated Authority | ConQA Hold Point Release
4.4 | Founding Material Inspection | IFC Report and Drawings | Geotechnical Engineer shall inspect founding material. Any areas in Ground Improvement footprint where proof roll test or bearing capacity are inadequate crushed rock shall be placed and compacted into the excavated surface under direction from geotech engineer Attach: Geotechnical Field Sheet or Report | Verify Document | Each lot | HP | Geotech Engineer /SE/Site Supervisor | ConQA Hold Point Release Geotech Report
5 | Fill Activities
5.1 | Structural Fill Placement | Section 204.10 (d) (ii) IFC Report and Drawings | Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Extent of fill placement to be as per IFC Report and Drawings | Visual | Each lot | IP | SE/Site Supervisor | Sign ITP
5.2 | Keying of Layers | Section 204.10(d)(i) | Each layer of fill shall be keyed into the layer above by creation of a textured surface. | Visual | Each lot | IP | SE/Site Supervisor | Sign ITP
5.3 | Proof Roll | Section 204.13 (b) (i) Section 204.12 | Withstands Test rolling without visible deformation or springing. No fill to be placed until the area has been reviewed and approved. | Visual | Each lot | HP | Nominated Authority | ConQA Hold Point Release
5.4 | Compaction Testing | Table 204.131 Section 204.13, 204.14 | Each Lot to be tested for compaction as Scale C requirements (3 tests per lot) Lot = One day's production or 5,000m2, whichever is the lesser Characteristic Density Ratio = 100% minimum | Document Review | Each Lot unless otherwise directed by Nominated Authority | HP | SE | Sign ITP Compaction Test Report
5.6 | Preparation of final surface | Section 204.15 | The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water. | Visual | Top layer | IP | SE/Site Supervisor | Sign ITP
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey | Section 204.03 (g), 204.16 | Scale C: Tolerance: No point surface shall be more than 10mm above or 30mm below the specified level | Document Review | Each lot | IP | Surveyor SE/PE/SPE | This ITP Survey Conformance Report
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /