## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) | itp |  |  |  |  | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-110-CIV-SSB-Ground Improvement (Structural Fill)
label | ITP Description: SSB-Ground Improvement (Structural Fill)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 110-CIV
label | Revision Number: 0
label | Revision Date: 27/11/2023
label | ITP created by: Hiruni Wickramarathne
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 204 (Dec 2015)
label | 1.2
label | Reference: IFC Report and Drawings
section | Preliminaries
checkpoint | 2.1 Material Approval
label | REFERENCE: Section 204.04 Table 204.041 IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
label | Scale C:
label | ○ CBR ≥ 6%
label | ○ Swell ≤ 1.5%
label | ○ Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided)
label | ○ PI (LL) = 6 - 25
label | ○ Effective Friction Angle = 32*
label | ○ Effective Cohesion = 0-5kPa
label | ○ Unit weight ≥19kN/m3
label | Grading:
label | ○ % passing 75.0mm sieve = 100
label | ○ % passing 4.75mm sieve = 40 - 80
label | ○ % passing 0.075mm = 10 - 40
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Review and Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once per material type prior to commence of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set-out
label | REFERENCE: Section 204.03 IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Cut Activities
checkpoint | 4.1 Subgrade Level
label | REFERENCE: Section 204.03 (g), Section 204.03 (h) IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant Ground Improvement drawings within the following limits:
label | ○ For Scale C: No point of subgrade surface shall be more than 10mm above or 30mm below the specified level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP, Survey Pick Up Report
date | Date Completed:
checkpoint | 4.2 Founding Material testing
label | REFERENCE: IFC Report and Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: DCP test to be carried out on the excavated surface to confirm the strength of the existing material is in accordance with Deisgn values for relevant chainages as below.
label | ○ Min DCP required /100mm
label | ○ 10000-10030 : 5 ( South)
label | ○ 10300-10320 : 7 (North)
label | ○ 10320-10360 : 6 (North)
label | ○ 10360-10400 : 5 (North)
label | ○ 10400-10410 : 3 (North)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Third party Geotech Engineer /SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release, Test Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Proof Roll
label | REFERENCE: Section 204.10 (b), Section 204.12 IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavated subgrade to be compacted and proof rolled before any construction.
label | ○ Withstands Test rolling without visible deformation or springing.
label | ○ No fill to be placed until the area has been reviewed and approved.
label | ○ If Proof Roll fail go to section 4.4
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 Founding Material Inspection
label | REFERENCE: IFC Report and Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Geotechnical Engineer shall inspect founding material.
label | ○ Any areas in Ground Improvement footprint where proof roll test or bearing capacity are inadequate crushed rock shall be placed and compacted into the excavated surface under direction from geotech engineer
label | Attach: Geotechnical Field Sheet or Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Geotech Engineer /SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release, Geotech Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Fill Activities
checkpoint | 5.1 Structural Fill Placement
label | REFERENCE: Section 204.10 (d) (ii) IFC Report and Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Extent of fill placement to be as per IFC Report and Drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.2 Keying of Layers
label | REFERENCE: Section 204.10(d)(i)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.3 Proof Roll
label | REFERENCE: Section 204.13 (b) (i) Section 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing. No fill to be placed until the area has been reviewed and approved.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Compaction Testing
label | REFERENCE: Table 204.131 Section 204.13, 204.14
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each Lot to be tested for compaction as Scale C requirements (3 tests per lot)
label | ○ Lot = One day's production or 5,000m2, whichever is the lesser
label | ○ Characteristic Density Ratio = 100% minimum
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot unless otherwise directed by Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP, Compaction Test Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Preparation of final surface
label | REFERENCE: Section 204.15
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Top layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As-built Survey
label | REFERENCE: Section 204.03 (g), 204.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Scale C: Tolerance: No point surface shall be more than 10mm above or 30mm below the specified level
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP