## Pre sheet Wall sign off
checklist | Pre-Sheet wall Sign-Off
checkpoint | Electrical - Apps Electrical - Pass once below is completed
button | Rough-in Complete | Yes / No / NA
button | Cutouts Marked | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
button | FR GPO boxes installed (where required) | Yes / No / NA
checkpoint | Electrical - Apps Electrical (Data)- Pass once below is completed
button | Rough-in Complete | Yes / No / NA
button | Cutouts Marked | Yes / No / NA
button | FR GPO boxes installed (where required) | Yes / No / NA
checkpoint | Hydraulics - Planet Plumbing - Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
button | Access panel / Valve box locations framed as marked | Yes / No / NA
button | Lagging complete | Yes / No / NA
checkpoint | Mechanical - Brolec - Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
button | Lagging complete | Yes / No / NA
checkpoint | Medical Gas - MedGas -Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Pressure box rough-in sealed (take photo where appliable) | Yes / No / NA
button | Access panel / Valve box locations framed as marked | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | Dry Fire - Jaycon -Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | Security- Honeywell - Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Pressure box rough-in sealed (take photo where appliable) | Yes / No / NA
button | Fire rated boxes installed | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | Data - SKS - Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Pressure box rough-in sealed (take photo where appliable) | Yes / No / NA
button | Fire rated boxes installed | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | AV - SKS - Pass once below is completed
button | Rough-in complete | Yes / No / NA
button | Pressure box rough-in sealed (take photo where appliable) | Yes / No / NA
button | Fire rated boxes installed (where required) | Yes / No / NA
button | Cut outs marked | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | Joinery - -Pass once below is completed
button | Noggins marked where required | Yes / No / NA
button | Cut outs framed as marked | Yes / No / NA
checkpoint | Sanitary Hardware - Casello - Pass once below is completed
button | Cut outs framed as marked (mental health) | Yes / No / NA
button | Noggins marked where required | Yes / No / NA
checkpoint | Plaster - Expo - Pass once below is completed
button | Wall cavity clean / no waste / vacuumed | Yes / No / NA | * mandatory photo
button | Door frames installed and filled when in fire rated wall (Take photo where applicable) | Yes / No / NA
button | Special door openings framing and noggins for autoclosers etc | Yes / No / NA
button | Insulation installed | Yes / No / NA
Sign off | Noggins installed as marked | Yes / No / NA
checkpoint | MPX FINAL SIGN-OFF
button | All services signed off | Yes / No / NA
button | Wall cavity clean and free of any rubbish / dust | Yes / No / NA
button | Photos taken of all walls prior to sheeting | Yes / No / NA | * mandatory photo