## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0040 Asphalt Primer/Spray Seal | itp |  |  |  | Yes | 1630-P200-SYM-QAC-ITP-0040 Asphalt Primer/Spray Seal
section | ITP Details
checkpoint | ITP Details
label | ITP No.
label | Rev No.
label | Date of Issue
label | ITP Type -
section | 1.0 Preliminaries
checkpoint | 1.1 - Commencement of works
label | Ref docs - Sec 408.04 (b), Sec 408.09 (d), Sec 173.02 1130.03d
label | Acceptance criteria - Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from Superintendent to any variation in the design rates of application to those provided under Cl. 408.13(a)
label | ○ Works shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit & ready for surfacing no more than 24 hours prior to works occurring
label | ○ V/R 310 shall be satisfied for initial seals
label | ○ Priming and initial sealing shall only be undertaken when the prevailing weather conditions, when assessed in accordance with AAPA HSE Guide No.8 – Environmental management when spraying bituminous materials, have a risk rating of ‘low’ or less and appropriate work practices to minimise risks are in place
label | ○ Unless otherwise specified, the extent of each lot shall not exceed one day's production
label | ○ Priming must not be carried out within 24 hours of forecast rain. (PS 3040.06h(viii)
label | A pre-sealing workshop is undertaken to present the below including the sealing subcontractor, the Superintendent and technical representatives from DTP prior to the preparation and sealing of any base course pavement layer.
label | (A) pavement surface preparation;
label | (B) assessment of priming and sealing application rates;
label | (C) the application of traffic on the sealed surface;
label | (D) proposed periods for sealing;
label | (E) protection of completed seals against rain or drop in temperature;
label | (F) removal of aggregate;
label | (G) Pavement Marking; and
label | (H) general maintenance of the newly sealed surface. (Table 1067.11, PS 3040.06)
label | i) Construction program includes details of the sealing works.
label | ii) a detailed program of planned sealing jobs on each day of the following week has been submitted on each preceding Thursday for Superintendent's review during the period of the contract. (VR 408.04b)
label | Key - H
label | VicRoads Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Aggregate Spreading (Forward facing)
label | Ref docs - Sec 408.13 (f), Sec 408.13 (d)
label | Acceptance criteria - Prior to commencing works - All aggregate spreading or discharge shall be undertaken using forward aggregate spreading & discharge plant.
label | ○ Minimum Temperature to meet criteria as set out in Table 408.131
label | ○ Minimum Temperature shall not apply to Strain Alleviating Membrane
label | ○ Forward aggregate spreading plants have been endorsed by the DTP - Chief Engineer (Roads). (408.13f)
label | ○ Aggregate stored at stacksites are managed to avoid contamination from other materials on the stacksite or from other sources such as vegetation, debris etc. (VR 408.12a)
label | For pre-coating material -
label | i) Pre-coating material is conforming to VR 831.07 requirements.
label | ii) Proposal to use alternative pre-coating material to the requirements of 831.07 are submitted for Superintendent's review minimum 10 days prior to use.
label | iii) Min. 3 years field performance has been submitted prior to using any proprietary material.
label | iv) Untried material has not been used without Superintendent's approval. (VR 408.09b, 831.07)
label | Key - S, I
checkpoint | 1.3 - Design Rates
label | Ref docs - Sec 408.13 (a), Sec 408.07, Sec 408.15
label | Acceptance criteria - The Contractor shall determine the design rates of application in accordance with the procedures set out in the Guide to Pavement Technology: Part 4K.
label | ○ Rates shall be expressed in L/m2 and residual binder at 15°C.
label | ○ At least 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
label | ○ Prior to commencing works Calibration Certificate to be provided.
label | ○ Detail design calculations are shown in design. (VR 408.13a)
label | ○ Variation in binder and aggregate application rate is calculated and submitted for acceptance of the work. VR 408.15
textbox | Acceptance: |  |  | litres/m2 at 15°C
button | Acceptance | Yes,No,N/A
label | Key - H
label | VicRoads Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Desing Rates received and attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Air temperature
label | Ref docs - Sec 408
label | Acceptance criteria - Is the air temperature suitable for the application?
label | Initial treatment:
label | Primes - 10
label | Primerseals (single/single) - 15
label | Primerseals (double/double) - 10
label | Reseal treatments:
label | C170 and crumb rubber modified PMBs - 15
label | Other PMBs - 20
label | Geotextile reinforced seals - 20
label | Recommendation - No rain forecast within 48 hours of sealing specially in routes of heavy traffic. (Pavement worktips-18)
label | Acceptance -
textbox | Air |  |  | °C
textbox | Pavement |  |  | °C
label | Key - H
label | VicRoads Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Written confirmation
label | Ref docs - Sec 408.03
label | Acceptance criteria - Has written confirmation of the works been sent to the Superintendent with confirmation received the day prior to application?
button | Acceptance | Yes,No,N/A
label | Key - R
label | VicRoads Key - R
checkpoint | 1.6 - Bitumen
label | Ref docs - Sec 408.08 (a), Sec 480.08 (b)
label | Acceptance criteria - Bitumen shall be Class 170 complying with the requirements of AS 2008
label | ○ C170 incorporating ≤ 5 Pts CR is considered to be an unmodified bituminous binder.
label | ○ Bitumen emulsion shall comply with the requirements of AS 1160
button | Acceptance | Yes,No,N/A
label | Key - R
label | VicRoads Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Compliance Certificate received and attached
checkpoint | 1.7 - Seal preparation
label | Ref docs - Sec 408.03
label | Acceptance criteria - Has area been inspected by Contractor and Superintendent and are both in agreement that road is fit to surface?
label | ○ Edge lines/lane lines are correctly marked prior to priming. (VR 310.02)
button | Acceptance | Yes,No,N/A
label | Key - H
label | VicRoads Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Materials supplied
label | Ref docs - VicRoads Sec408 Supplier Information, Sec 408 (c), Sec 408 (e), Sec 480.09 (a), Sec 408.09 (e)
label | Acceptance criteria - The bituminous material, crumb rubber, and aggregate supplied all conform to VicRoads as per supplier delivery?
label | ○ Cutback Bitumen - Cutback bitumen shall comply with the requirements of AS 2157
label | ○ Primer - Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
label | ○ Adhesion Agent - Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
label | ○ Geotextile Fabric - Non-woven needle punched fabric - min weight 135 g/m2 for seals of nominal size of 14mm and under, and 175 g/m2 for seals of nominal maximum size of larger than 14mm, melting point > 10 C above max binder spraying temp.
label | For sealing aggregate -
label | i) Each lot at the quarry has unique lot identification number and is mentioned on the delivery docket.
label | ii) Aggregate testing is done not more than 90 days prior to delivery. (VR 831.05b)
label | i) Cutter is conforming to testing requirements in Table 408.091.
label | ii) Min. 3 years field performance has been submitted prior to using any material non-conforming to Table 408.091.
label | iii) Untried material has not been used without Superintendent's approval. (VR 408.09d)
button | Acceptance | Yes,No,N/A
label | Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material documentation received and attached
checkpoint | 1.9 - Binders for treatment types
label | Ref docs - Sec 408.10 (a), (b)
label | Acceptance criteria - Initial Seal Binder - the binder to be used in Initial Seals shall be a suitable cutback bitumen, bitumen emulsion or a 9% (10 parts) crumb rubber modified binder. Other modified binders may be used subject to approval of the Superintendent.
label | ○ The Initial Seal shall be waterproof and capable of adhering to the pavement surface while retaining sufficient binder on the surface to hold the aggregate in place. Final Seal and Reseal Binders - Unless otherwise specified in Table 408.191, one of the following binder classes and seal sizes outlined in Table 408.101 shall be used.
label | ○ Pavement temperature is adopted instead of air temperature to decide the percentage of cutter to be added. Variation in cutter among shaded areas and unshaded areas are carefully considered.
label | ○ Prime is cured for at least 72 hours prior to sealing.
label | ○ Aggregate pre-coat should be dry. If the pre-coat is wet, amount of cutter is carefully reduced
button | Acceptance | Yes,No,N/A
label | Key - W, R
checkpoint | 1.10 - Aggregate
label | Ref docs - 408.09 (b) 408.11 (a), (b)
label | Acceptance criteria - Aggregate shall comply with the following Standard Specification Sections:
label | ○ 801 – Source Rock;
label | ○ 831 – Aggregate; and
label | ○ 832 – Sands
label | Maximum lot size 350t of same class and size
label | Acceptance of Aggregate - If all of the specified test results comply with the relevant requirements of Clauses 831.04(d), (e) and (f) the aggregate represented by the lot will be accepted
label | ○ Aggregate which does not meet the above acceptance criteria shall not be supplied or delivered.
label | Aggregate Pre-coating Materials - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | Supply plant pre-coated aggregate from supplier or field pre-coated aggregate from stack site
button | Acceptance | Yes,No,N/A
label | Key - H
label | VicRoads Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test Certificate received and attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - Conformance of previous layer
label | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes,No,N/A
label | Key - S
section | 3.0 Application of spray seal
checkpoint | 3.1 - Surface Pre-treatment
label | Ref docs - Sec 408.13 (b)
label | Acceptance criteria - Correct variable surface texture shall be allowed for by contractor and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Retention. Refer Tables 408.191, 408.152, 408.153
button | Acceptance | Yes,No,N/A
label | Key - S, I
checkpoint | 3.2 - Rolling of Aggregate
label | Ref docs - Sec 408.13 (g)
label | Acceptance criteria - Rolling of aggregate shall:
button | Acceptance: be undertaken over the full width of the pavement being sealed including any untrafficked areas | Yes,No,N/A
button | Acceptance: be undertaken by static rubber tyred rollers unless otherwise specified or approved by the Superintendent | Yes,No,N/A
label | Key - S, I
checkpoint | 3.3 - Sweeping of Road Surface
label | Ref docs - Sec 408.13 (h)
label | Acceptance criteria - All surfaces shall be inspected prior to the application of a sprayed seal treatment to ensure that a clean surface is available for sealing works that is free from dirt, loose aggregate and other detritus
label | ○ For multiple application treatments, intermediate sprayed seal layers shall be thoroughly swept to ensure that loose aggregate particles are removed prior to the application of the subsequent sprayed seal layers. This includes areas where an overlap of aggregate has occurred during the spreading operation
label | ○ Traffic speed is controlled as per VR 166 as long the sealed surface is not swept. (VR 408.14)
button | Acceptance | Yes,No,N/A
label | Key - H
label | VicRoads Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Geotextiles
label | Ref docs - Sec 408.13 (c)
label | Acceptance criteria - Geotextile fabric shall be fixed to the pavement surface free of wrinkles and/or folds.
label | ○ Transverse joins shall be butt jointed.
label | ○ Longitudinal joins shall be overlapped approximately 150mm and be located along lane lines.
label | ○ During placement of geotextile -
label | i) Additional binder as per seal design is added at the joints.
label | ii) Bond coat is applied as per seal design extending approximately 100mm beyond the geotextile.
label | ○ Recommendation - Geotextile Reinforced Seal is not programmed after 2nd week of March, when there is a rain forecast within 2 weeks and temperature is below 20°C. Coarse surface texture>2mm is corrected before applying Geotextile Reinforced Seal.
button | Acceptance | Yes,No,N/A
label | Key - I
checkpoint | 3.5 - Removal of loose aggregate
label | Ref docs - Sec 408.14
label | Acceptance criteria - All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
label | NB: For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
button | Acceptance | Yes,No,N/A
label | Key - I
checkpoint | 3.6 - Acceptance of work - Aggregate retention
label | Ref docs - Sec 408.15 (c)
label | Acceptance criteria - Does the seal meet the visual inspection for aggregate retention as per Table 408.151
button | Acceptance | Yes,No,N/A
label | Key - I
checkpoint | 3.7 - Acceptance of work - Visual uniformity
label | Ref docs - Sec408.15 (d)
label | Acceptance criteria - Is the seal uniform in colour and texture?
button | Acceptance | Yes,No,N/A
label | Key - I
checkpoint | 3.8 - Job completion report
label | Ref docs - Sec408.17
label | Acceptance criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
button | Acceptance | Yes,No,N/A
label | Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Attach job completion
checkpoint | 3.9 - Maintenance of seals
label | Ref docs - Sec408.16
label | Acceptance criteria - The contractor shall be responsible for the monitoring & maintenance of seals from the time of application until the end of the defects liability period.
label | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
label | ○ The Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
button | Acceptance | Yes,No,N/A
label | Key - S
label | VicRoads Key - S