## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Excavation and Support - 5.0 Construction (Bench) | itp |  |  |  |  | ITP - Excavation and Support - 5.0 Construction (Bench) Rev 2
section | 5.1. Excavation
checkpoint | 5.1.1 - PTT
label | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face.
label | ○ Tunnel excavation shall not commence on a shift until PTT has been signed off
label | Specifications and Standards - Technical Specifications C0650, Tunnel Sequential Excavation Section 5.1
label | Method/Description - PTT form
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - PTT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.2 - Face Mapping
label | Description - Recommend the required support type based on the Actual Ground Conditions.
label | ○ Determine any corrective measures required to ensure safety and stability of the excavation.
label | ○ Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required.
label | Specifications and Standards - Technical Specifications C0650, Tunnel Sequential Excavation Section 5.1
label | Method/Description - Geological mapping record
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - Required Excavation and support sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.3 - E-line control
label | Description - Control the E-Line before, during and after excavation is finished
label | Specifications and Standards - Drawing MMMA-DES-TUN-E1-DRG-8119
label | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance
label | Test frequency - Every advance
label | Conformance Criteria - Over excavation tolerance -0/+150mm
label | Constructor - H
label | CPS - W
label | Verifying Records - Survey As-built
section | 5.2. Shotcrete
checkpoint | 5.2.1 - Shotcrete Delivery and acceptance
label | Description - delivery dockets check, slump and temperature check
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.4, NZS 3109: 1997
label | Method/Description - Document Review
label | Test frequency - Each truck
label | Conformance Criteria - Slump range 200-240mm
label | ○ Temperature range 5-35 celcius
label | ○ Delivery dockets to include the following; Batch number,
label | ○ Batch temperature at time of dispatch and delivery, Mix designation, Date and time of mixing, Quantity delivered, The delivery truck number, Date and time the delivery truck left the batching plant, Amounts of water, ad mixture, or any other ingredients made after despatch, and time at which such additions are made, Steel fibre type and content, Micro fibre type and content, and, any other relevant information.
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Installation Record
checkpoint | 5.2.2 - Shotcrete Batching records
label | Description - batching, mixing and transport to comply with NZS3104
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.3, NZS 3104
label | Method/Description - Document Review
label | Test frequency - Each truck
label | Conformance Criteria - Compliance with NZS3104
label | Constructor - R
label | CPS - R
label | Verifying Records - Shotcrrete Batching records
checkpoint | 5.2.3 - Rock and Shotcrete Surface Preparation
label | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
label | Specifications and Standards - Technical Specification - C0650 - Tunnel Civil Works Section 5.4
label | Method/Description - Visual Inspection
label | Test frequency - Prior to spraying
label | Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying.
label | ○ Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means.
label | ○ Spalled, cracked, loose or contaminated shotcrete removed.
label | Constructor - H
label | CPS - W
label | Verifying Records - refer to checksheet in 5.2.9
checkpoint | 5.2.4 - Shotcrete Thickness As-built
label | Description - Provide control means to verify the thickness of final shotcrete layer
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8130
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 8131 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
checkpoint | 5.2.5 - Shotcrete Lining intrados As-built
label | Description - Provide control means to verify the intrados clearance of the shotcrete lining
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8131
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3131 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8120
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
checkpoint | 5.2.6 - Shotcrete Lining C-line As-built
label | Description - Provide control means to verify the C-line clearance of the shotcrete lining
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8132
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8121
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
checkpoint | 5.2.7 - Top heading to Bench Inspection
label | Description - Underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water and inspected by the designer's representative prior to placement of bench shotcrete.
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 Table 3.1
label | Method/Description - Visual Inspection
label | Test frequency - Every Construction Joint
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - refer to checksheet in 5.2.8
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.8 - Footing Inspection
label | Description - The footing invert (top heading and bench) shall be clean and clear of all debris and shotcrete rebound and inspected by designer's representative prior to placement of shotcrete.
label | Specifications and Standards - Drawing MMA-DES-TUN-E1-DRG-8129
label | Method/Description - Visual Inspection
label | Test frequency - Prior to each Spray
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - Shotcrete Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.9 - Curing
label | Description - Curing to be carried out in accordance with the Specification
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.5
label | Method/Description - Visual Inspection
label | Test frequency - Each Spray
label | Constructor - H
label | CPS - R
label | Verifying Records - refer to checksheet in 5.2.8
checkpoint | 5.2.10 - Lining Waviness Criteria
label | Description - To comply with the waviness criteria outlined in Drawing MMA-DES-TUN-E1-DRG-8119
label | Specifications and Standards - Drawing MMA-DES-TUN-E1-DRG-8119
label | Method/Description - Visual Inspection
label | Test frequency - Each Cut
label | Conformance Criteria - maximum deptth of depressions between peaks: 50mm
label | ○ Maximum gradient between peak and trough of irregularities: 1:20
label | Constructor - H
label | CPS - H
label | Verifying Records - Refer to asbuilt in 5.2.5
holdpoint | AUTHORITY HOLDPOINT
section | 5.3. Reinforcing mesh
checkpoint | 5.3.1 - Reinforcing mesh for primary lining
label | Description - To prove position, cover and overlap are achieved
label | Specifications and Standards - Drawing MMMA-DES-TUN-E1-DRG-8011
label | Method/Description - Visual inspection and survey
label | Test frequency - Every advance
label | Conformance Criteria - Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm)
label | ○ Min. cover 65mm at the extrados and 85mm at the intrados
label | Constructor - H
label | CPS - W
label | Verifying Records - Mesh Check Sheet, As-built
section | 5.4. Rockbolts
checkpoint | 5.4.1 - Drilling and Installation
label | Description - Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | ○ To ensure correct installation process for resin injection
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3
label | Method/Description - Survey
label | Test frequency - Each bolt
label | Conformance Criteria - bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | — The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. Dowels to be clean or any other physical damage at the time of installation
label | — Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | — Sufficient volume of resin to be used with each rock reinforcement installation in accordance with The approved project specific procedure developed during The trials. Daily records of all grouting works to be kept
label | — Bolts free of dirt, detrimental rust or any other deleterious substances
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record
checkpoint | 5.4.2 - Rockbolt As-built
label | Description - Bolts to be installed in the position specified on the drawings or as instructed by the designer
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3
label | Method/Description - Review
label | Test frequency - Each bolt
label | Conformance Criteria - bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | Constructor - H
label | CPS - R
label | Verifying Records - Rock Bolt As built Survey
checkpoint | 5.4.3 - Pull test
label | Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity.
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.5
label | Method/Description - Test
label | Test frequency - 1. The first nine installations of each type of rock bolt and the first nine installations of each type of rock dowel shall be tested in each ground type as it presents in production. At least one test location of each type shall be in the tunnel crown unless otherwise directed by the Designer’s Representative.
label | ○ 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting.
label | Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification.
label | ○ Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel
label | Constructor - H
label | CPS - W
label | Verifying Records - Testing records
section | 5.5. Ground water control
checkpoint | 5.5.1 - Strip drain installations
label | Description - Record location and ensure correct installation of materials
label | Specifications and Standards - Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5
label | Method/Description - Visual inspect and Review
label | Test frequency - Each installation
label | Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative
label | ○ Position checked to ensure shotcrete adequate cover
label | ○ Materials are free of damage before spraying strip drain and fittings adequately secured to the shotcrete
label | ○ Drainage holes installed as per instructions
label | ○ End of strip drains and hose protected
label | Constructor - H
label | CPS - H
label | Verifying Records - Refer to as-built in 5.5.2
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5.2 - Strip drain As-built
label | Description - As-built of strip drain location
label | Specifications and Standards - Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5
label | Method/Description - Review
label | Test frequency - Each installation
label | Conformance Criteria - Location sinstalled as per instructed on site by the Designer's representative as-built checked to ensure adequate cover
label | Constructor - H
label | CPS - H
label | Verifying Records - Survey As-Built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5.3 - Flushing Point installation
label | Description - surveyor to confirm vertical position prior to encasement in shotcrete. Flushing tube connection point with proprietary fitting and cap
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8145
label | Method/Description - Visual Inspection
label | Test frequency - Each installation
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - asbuilt
checkpoint | 5.5.4 - Strip drain Bench Connection
label | Description - underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water, and inspected by the designers rep prior to placement of the bench shotcrete
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8143
label | Method/Description - Visual Inspection
label | Test frequency - Each installation
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - Refer to as-built in 5.5.2
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5.5 - Bored drains drilling and installation
label | Description - Record location and ensure correct installation of materials
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8141
label | Method/Description - Visual inspection and Review
label | Test frequency - Each installation
label | Conformance Criteria - 4.5m long 76mm diameter holes drilled at 4m centres along the sides of the tunnel (location dependant on strip drains and rockbolt locations)
label | Constructor - W
label | CPS - R
label | Verifying Records - asbuilt
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 6.0 Tunnel Defects | itp |  |  |  |  | ITP - Excavation and Support - 6.0 Tunnel Defects Rev 2
section | 6.0 Tunnel Defects
checkpoint | 6.01 - Defect Repairing Methodology
label | Description - an approved methodology and materials for defect repair
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6
label | Method/Description - Submission
label | Test frequency - Before Repairing works
label | Conformance Criteria - Approved methodology and materials
label | Constructor - H
label | CPS - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02 - Shotcrete Defects
label | Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly.
label | ○ At the completion of the lining,
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6
label | Method/Description - Visual Inspection and Repair
label | Test frequency - Every defect on Every advance
label | Conformance Criteria - Cracks > 0.5mm to be repaired
label | ○ All core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified.
label | ○ The surface of the restored hole shall be similar to the surrounding surface in texture and colour.
label | Constructor - H
label | CPS - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03 - Groundwater (rectification)
label | Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
label | Specifications and Standards - Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6
label | Method/Description - Visual Inspection
label | Test frequency - Ongoing
label | Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed.
label | Constructor - H
label | CPS - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 7.0 Monitoring | itp |  |  |  |  | ITP - Excavation and Support - 7.0 Monitoring Rev 2
section | 7.0 Monitoring
checkpoint | 7.01 - Tunnel convergency (Extensometer)
label | Description - Monitoring and reading records of the tunnel extensometer
label | Specifications and Standards - Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily
label | Conformance Criteria - outlined in MMA-DES-TUN-E1-DRG-8180 Table 3
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
checkpoint | 7.02 - In-Tunnel Optical Survey Convergence
label | Description - Monitoring and reading records on the tunnel optical survey targets
label | Specifications and Standards - Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily
label | Conformance Criteria - outlined in MMA-DES-TUN-E1-DRG-8180 Table 3
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature