## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-010-002 ITP Retaining Wall 4 Permanent works | itp |  |  |  |  | DN1210-SP2-010-002 ITP Retaining Wall 4 Permanent works Rev 1
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL , PERSONNEL & THIRD PARTY APPROVALS (P&G / ESTABLISHMENT)
checkpoint | 3.1 - Methodology
label | Detail of Activity / Test - Method statement
label | Acceptance / Conformance Criteria - As Per Specification and IFC Drawings
label | Standard / Specification - PS- 22.3 Appendix V
label | Verifying Document - RW-04 Permanentworks Construction Work Pack Sign off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Reinforcement Modelling
label | Detail of Activity / Test - 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review
label | Acceptance / Conformance Criteria - Downer
label | Standard / Specification - Reinforcment shop drawings
label | Verifying Document - Each batch of reinforcement
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Steel Supply, Delivery and Storage
label | Detail of Activity / Test - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer.
label | Acceptance / Conformance Criteria - Design Drawings
label | Standard / Specification - AS/NZS 4671, PS 19.13
label | Verifying Document - Delivery Dockets / Mill Certs
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 3.4 - Concrete Mix Design
label | Detail of Activity / Test - Concrete mix design to be completed and reviewed by the contractor prior to use on site. The following criteria are to be satisfied:
label | ○ Strength: 50MPa
label | ○ Normal maximum aggregate size: 19mm
label | ○ Concrete materials and manufacturing are to comply with NZS3109
label | ○ Aggregate Used And Overall Mix Design (Including Additives) Shall Meet The Provisions Of 'Tr3 Alkali Silica Reaction 2003 (Ccatnz)'.
label | Acceptance / Conformance Criteria - NZS 3104 Design Drawings
label | Standard / Specification - PS 19.3.3
label | Verifying Document - Concrete Mix Design
label | Testing Quantity Required (based from schedule qtys) - All Mix Designs
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Subsoil Drainage
label | Detail of Activity / Test - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 21.5.17
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Granular Material (Imported Pumice Sand, GAP65/AP65)
label | Detail of Activity / Test - Confirm Specification and material in good condition.
label | ○ NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | ○ NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | ○ NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - Confirm Specification and material in good condition.
label | Standard / Specification - PS 22.4.1
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - ArmourFlow Drainage
label | Detail of Activity / Test - Installed as per the manufacturer’s installation guidelines and project drawings
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Manufacturer’s Product Data Sheet, Engineers Approval
label | Verifying Document - Manufacturer’s Product Data Sheet, Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Delivery Dockets
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - CONSTRUCTION ACTIVITY - CONCRETE BASE- Excavation and Subgrade Preparation
checkpoint | 4.1 - Cut Subgrade - Inspection
label | Detail of Activity / Test - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail of Activity / Test - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa, 2-3m deep
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 0.5m interval, 4 test per 400M2
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.3 - Cut Subgrade Testing - Non-Cohesive Soil Scala Penetrometer
label | Detail of Activity / Test - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.4 - Cut Subgrade - Import Structural fill Release of Hold Point
label | Detail of Activity / Test - To release the subgrade hold point in-order to start placing the Blinding Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITY - CONCRETE BASE + TOE + KICKER-CHAMFER - Steelworks
checkpoint | 5.1 - STEEL - Reinforcing Ties
label | Detail of Activity / Test - Tie bar diameter, grade, and length match shop drawings and bending schedule
label | ○ Spaced correctly as per design (e.g., 200mm c/c), full enclosure of longitudinal bars
label | Acceptance / Conformance Criteria - As per Drawing
label | Standard / Specification - NZS 3109, PS 19.13
label | Verifying Document - Delivery Dockets, Checksheet
label | Testing Quantity Required (based from schedule qtys) - During constuction
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 5.2 - STEEL - Onsite Cutting & bending
label | Detail of Activity / Test - Complies with bending schedule & radius limits
label | Acceptance / Conformance Criteria - As per Drawing
label | Standard / Specification - NZS 3109, PS 19.14
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - During constuction
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 5.3 - STEEL - Reinforcing Bars (lapping/starter bars/dowels)
label | Detail of Activity / Test - Correct bar size, spacing, cover, lapping as per shop drawings
label | ○ Min. lap length, staggered laps as per design
label | ○ Location, projection & alignment must match prior pour
label | Acceptance / Conformance Criteria - As per Drawing
label | Standard / Specification - NZS 3109, NZS 3604, PS 19.13
label | Verifying Document - Delivery Dockets, Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
section | SECTION 6 – CONSTRUCTION ACTIVITY - CONCRETE BASE + TOE + KICKER-CHAMFER - Concreteworks
checkpoint | 6.1 - CONCRETE - Unfavourable Conditions - Cold Weather
label | Detail of Activity / Test - Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing.
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS3901:1997 Cl 7.2
label | Verifying Document - Pre Pour
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.2 - CONCRETE - Unfavourable Conditions - Hot Weather
label | Detail of Activity / Test - Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS3901:1997 Cl. 7.2.1 & Cl. 7.2.2
label | Verifying Document - Pre Pour
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.3 - CONCRETE - Unfavourable Conditions - Rain
label | Detail of Activity / Test - Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement.
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS3901:1997 Cl. 7.1
label | Verifying Document - Pre / During Pour
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.4 - CONCRETE - Spacer Blocks
label | Detail of Activity / Test - Correct type, spacing, and fixity
label | ○ Shall be concrete spacer blocks made from concrete containing 8% Microsilica 10MPa
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS 3109
label | Verifying Document - Delivery Dockets, Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.5 - CONCRETE - Construction Joints
label | Detail of Activity / Test - Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6.
label | Acceptance / Conformance Criteria - Prepour Checklist, As per Drawing
label | Standard / Specification - NZS3109:1997 Cl 5.6, PS 19.5
label | Verifying Document - Photos/Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.6 - CONCRETE - Delivery Dockets
label | Detail of Activity / Test - Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant.
label | ○ Delivery dockets and other certified records of concrete quality and quantity shall be kept on site for inspection by the Engineer.
label | Acceptance / Conformance Criteria - Engineer Inspection
label | Standard / Specification - PS 19.4.1
label | Verifying Document - Dockets, Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.7 - CONCRETE - Slump Tests
label | Detail of Activity / Test - Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor
label | — — — — — — —
label | Table 9.1 - Tolerances for nominated slump
label | Nominated slump (mm) ¦¦ Tolerance for snatch sample
label | — — — — — — —
label | 60 or less ¦¦ ±20
label | 70 - 110 ¦¦ ±30
label | Greater than 110 ¦¦ ±40
label | — — — — — — —
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS3109 Table 9.1
label | Verifying Document - Photos/Visual Inspection or slumps and on-site records
label | Testing Quantity Required (based from schedule qtys) - Each Delivery
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 6.8 - CONCRETE - Time Limits
label | Detail of Activity / Test - Any addition of water or admixtures to the concrete mix subsequent to leaving the ready mix plant shall be only be undertaken by, or with the approval of, the ready mix plant supplier. Any such addition of water shall be strictly in accordance with clause 9.4.2.1 of NZS3109. All ready-mix concrete supplied shall be poured within 90 minutes of batching.
label | ○ For concrete mixes containing set accelerating admixtures the above times shall be halved.
label | Acceptance / Conformance Criteria - Prepour Checklist
label | Standard / Specification - NZS 3104, NZS3109 Cl 9.4.2.1, PS 19.4.3
label | Verifying Document - Dockets, Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 6.9 - CONCRETE - Compression Testing
label | Detail of Activity / Test - The Contractor shall have the off-site testing carried out by an approved IANZ-accredited laboratory at his own expense and shall supply copies of IANZ-endorsed test results to the Engineer.
label | ○ For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28-day compressive strength in an approved laboratory
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 50 Mpa
label | Standard / Specification - NZS3109, PS 19.4.2
label | Verifying Document - Compression Test Result
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 6.1 - CONCRETE - Curing
label | Detail of Activity / Test - After concrete has set sufficiently its exposed surfaces shall be kept continuously wet for a period of at least 7 days. Special attention shall be paid to curing in the early stages.
label | Acceptance / Conformance Criteria - Acceptance / Repair Details
label | Standard / Specification - NZS 3109:1997 Cl 7.1.3, PS 19.8
label | Verifying Document - Post Concreting/Compression Test Result
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 6.11 - CONCRETE - Finishes
label | Detail of Activity / Test - Concrete finishes are to be as specified by NZS3114 & AS/NZS 3661, scheduled as follows:
label | ○ Top surface of Base: U5 Brushed Finish
label | ○ Type B construction joints to NZS3109
label | Acceptance / Conformance Criteria - Drawings
label | Standard / Specification - NZS3114, NZS3109
label | Verifying Document - Photos/Approva/Repair Details
label | Testing Quantity Required (based from schedule qtys) - Post Concreting
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.12 - CONCRETE POSTPOUR - Falsework and Formwork Installation/Removal
label | Detail of Activity / Test - Formwork shall not be removed until the minimum periods set down in Table 5.3 of NZS3109 have elapsed.
label | ○ Design details, construction drawings, and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review
label | Acceptance / Conformance Criteria - As per Temporary works Drawings, Engineer Approval
label | Standard / Specification - NZS3109 Table 5.3, PS 19.11.3, Appendix XIX, Downer
label | Verifying Document - Approval
label | Testing Quantity Required (based from schedule qtys) - Before installation and removal of Falsework and Formwork
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 6.13 - CONCRETE POSTPOUR - Post Pour Inspection
label | Detail of Activity / Test - Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects.
label | Acceptance / Conformance Criteria - Downer
label | Standard / Specification - Site Photos
label | Verifying Document - Each pour
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - H
label | Hold Point (Internal)
label | (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point)
label | Verification Activity: By - PE/SE
checkpoint | 6.14 - CONCRETE POSTPOUR - Repair
label | Detail of Activity / Test - Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance.
label | ○ All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer.
label | Acceptance / Conformance Criteria -
label | Standard / Specification -
label | Verifying Document - Acceptance / Repair Details
label | Testing Quantity Required (based from schedule qtys) - Prior to Each Repair
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 7 – CONSTRUCTION ACTIVITY - STRUCTURAL BACKFILL, DRAINAGE AND ARMOURFLOW INSTALLATION
checkpoint | 7.1 - STRUCTURAL BACKFILL - Backfill Installation
label | Detail of Activity / Test - All backfill is to be installed in 400mm lifts and tested as below
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each layer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.2 - STRUCTURAL BACKFILL - Compaction - Clegg Hammer
label | Detail of Activity / Test - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill:
label | — Min CIV 18
label | — Ave CIV 20
label | ○ Non-Structural Fill
label | — Min CIV 10
label | — Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.3 - STRUCTURAL BACKFILL - Compaction - NDM
label | Detail of Activity / Test - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | ○ Non Granular Material
label | ○ Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.4 - STRUCTURAL BACKFILL - Subsoil Installation
label | Detail of Activity / Test - A 110mm Drainage pipe wrapped in filter sock is to be installed along the internal perimeter of the retaining wall.
label | Acceptance / Conformance Criteria - Engineer Inspection
label | Standard / Specification - PS 16.5.8
label | Verifying Document - Delivery Dockets/Installation Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 7.5 - STRUCTURAL BACKFILL - ArmourFlow Installation
label | Detail of Activity / Test - Free of damage, cracks or displacement prior to backfill
label | ○ Continuous placement behind retaining wall with correct orientation, tight joints, and tie-in to drainage pipe
label | Acceptance / Conformance Criteria - Engineer Inspection
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0417)
label | Verifying Document - Delivery Dockets/Installation Checksheet/Photos
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.1 - Survey As-Builts
label | Detail of Activity / Test - Quality Check on Nee pipeline and structure based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec as per drawings and capture any NCR or change to design.
label | Standard / Specification - Project Specifications
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 7.2 - Redline Drawings
label | Detail of Activity / Test - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Acceptance / Conformance Criteria - Drawings
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity -
label | Verification Activity: By -
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature