## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4e1e6d06-f5af-406c-bbd6-338ab99c8741 | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp | ITP-000 - Client Pre-Construction Checklist
6f50d619-23f7-4c05-8a0a-d2c4731af825 | section | Design and Submissions
f8bbaff2-c0bc-48cb-b1d8-74f504193c54 | checkpoint | 1.1 Submission & approval of concrete mix design prior to commencement of project
3578460f-22f4-51cd-8702-c887204af033 | note | FREQUENCY: Prior to first concrete pour
e3bfe8ac-771e-52de-8041-ff6956123cb9 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
1deff771-3fd1-5ca9-9438-ef1df31bc273 | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
04320675-5c9e-5c75-8b53-718415a57f1c | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
5ddf50f2-0825-5c42-89e6-8ba52ed72808 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
9e38ad18-5c35-560f-a46f-d3d47677e012 | note | INSPECTION/TEST METHOD: Verify
e78127ee-cf07-5b8c-b22b-11e7547fb50f | note | RECORD OF CONFORMITY: Mix Design ITP
00ecca0b-ccb8-5504-adfd-9c9df989d79e | note | HP
47171f80-b3ba-5c93-b59a-40d0b455efd5 | note | RESPONSIBILITY: FH Engineer / Superintendent
5b644ffb-42f6-5372-ae76-d90b6997aa77 | textbox | Date Completed:
bb25e924-dc6d-4814-83cb-6269ab562279 | signoff | AUTHORITY HOLDPOINT
1a0168a8-8af1-482a-bd91-801d50a129d8 | checkpoint | 1.2 Submission & approval of asphalt mix design prior to commencement of project
453c13d4-d2bb-531f-b588-fb5a4c711fb0 | note | FREQUENCY: Prior to commencing paving
dbf79abc-394f-50b6-b545-bce19ba2b3e3 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
f9b63f21-84fb-537f-a88a-981c3dc93be7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
fbb7737a-adf1-5cc5-8186-ec040807df04 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
07c2fe06-38ae-5837-8556-cbfd4494af79 | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
b8c16564-663e-55b2-800e-6190c226e7d0 | note | HP
3417f0ac-18e2-5e0b-b6ff-e21abf6100d0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
64828c5d-91a9-5c90-89cc-aef240abbd86 | textbox | Date Completed:
1672acaa-5116-41d3-9555-a3dfb347b036 | signoff | AUTHORITY HOLDPOINT
a4875955-6e3e-42cc-8e8b-e0dbac433756 | checkpoint | 1.3 Welders qualifications, competencies & work methodology
42e68029-c9f4-5ff0-9680-f15429b9f4a4 | note | FREQUENCY: Prior to commencing welding
7c003c92-7f00-558b-ae6d-dd62cd432a24 | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works.
ec3f40a9-184e-5fe0-9d6e-b87bf03c31b3 | note | ○ Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
9bc3cb1b-f14e-59bb-a74e-d516383e9a73 | note | — TLIW2012 Grind Rails
65536504-fc08-56a9-b1e9-73209e25e592 | note | — TLIW3015 Weld Rails using Aluminothermic welding process
a2e7271b-8dea-5f03-9386-3d141c050a03 | note | — TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
4d00149e-208e-5f07-998a-4f5c2bef6554 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
d482faa4-480c-53da-beb5-dfb1d2de4f9a | note | INSPECTION/TEST METHOD: Welding Methodology
5e978eca-b7f3-5327-bb96-7dea29821316 | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
215bd2f4-7777-5192-a834-a25c81a574fb | note | HP
a428db01-ac32-5d20-bdee-e8ee9e29dab8 | note | RESPONSIBILITY: FH Engineer / Superintendent
03ded966-9141-5370-b4d1-73511d7762a1 | textbox | Date Completed:
0118dcec-c5c7-4126-a3dc-72aa817e11ce | signoff | AUTHORITY HOLDPOINT
b7b537aa-7fd9-4090-800f-7fcb44dcc5f3 | checkpoint | Final Inspection
303472e7-1ef8-5368-a336-5e4bef6888a3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a395c62e-15f8-5c98-87c3-7154430eea5f | textbox | Print Name:
cc0eddbf-faad-5715-a1ae-b2fe2eb3d66f | textbox | Position:
d832c951-f8f6-5fca-bd53-3c09f10a6489 | textbox | Date:
59dd5455-9f13-47e8-a4ac-30c34396e448 | checklist | ITP-001 - Subgrade Preparation Rev0 | itp | ITP-001 - Subgrade Preparation
43a9fc3b-cfc7-4fc6-8266-0594dd64ddba | section | Preliminary Works
1dc5f8b0-1210-4277-9d9c-5e4fe0778fd7 | checkpoint | 1.1 Check for correct documentation
4a46a9fa-2193-5d27-aa4e-7a5ccb63a90c | note | FREQUENCY: Prior to commencing any activity
f118ac2e-0496-5544-8772-e9f6b2494293 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
cefb6019-7874-5ffc-ad0b-2da80580f8b0 | note | — using the correct and complete set of drawings
abfd320e-d2f8-5411-b8e2-89d66622753b | note | — all drawings are the latest revision
b9b0b14d-29ff-57e9-92fb-6836c70d3f16 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d6bf87e8-64d4-5021-bc89-5d28360ffaf7 | note | INSPECTION/TEST METHOD: Visual inspection
91f82c23-d872-5379-8595-9436cb08bf90 | note | RECORD OF CONFORMITY: This ITP signed off
444d3e9d-59c0-53f4-a076-01502115a8ee | note | WP
ae118292-43c4-5c24-a579-ecfec18e5b42 | note | RESPONSIBILITY: Fulton Hogan
c549e263-3f8b-5089-9fc6-a1fc193fa13f | textbox | Date Completed:
c2a74330-3832-49e0-9f1b-3d167dad438d | checkpoint | 1.2 Implementation of all measures and controls
9a2e5141-f766-575e-8f09-825821ee4509 | note | FREQUENCY: Prior to commencing any activity
31ec533b-35e9-5dde-8a04-7930827952ba | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
9de21b43-42ea-543b-af03-5de83c5c1c86 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8dbf4cd2-9479-5275-aa0d-494720577fd1 | note | INSPECTION/TEST METHOD: Visual Inspection
e31faa88-22dd-5ef5-ad86-2f8351432824 | note | RECORD OF CONFORMITY: This ITP signed off
d595151c-09a3-5da5-b83b-3ca93c6f43a0 | note | WP
38e9ab82-dedc-52fc-982c-313cbdbda103 | note | RESPONSIBILITY: Fulton Hogan
0b49f96a-0c02-5102-89b6-5ba1c8fa4fdf | textbox | Date Completed:
9b0e493f-948d-47d1-bdcd-cb85461cf470 | checkpoint | 1.3 Selection and approval of disposal site
47700a28-e09f-5cd4-8109-5576de88624d | note | FREQUENCY: Prior to commencing any activity
1a903da5-2e45-5c87-b8a3-c0f986c4608c | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
e76471fd-85b8-539c-86b3-c486b7ae35cc | note | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the authorities controlling disposal of material at that location.
56bca7b5-3c57-5953-96eb-a51def3b6ecb | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019-ST-0033 CL. 4.2.1.5.
ecfbffb9-71b2-5125-b675-05df3bc61bd6 | note | INSPECTION/TEST METHOD: Verify
55db2c5e-b8dd-5485-80f1-2fb8b5b60344 | note | RECORD OF CONFORMITY: This ITP signed off
730f153f-b6a5-5bca-8ef2-feed71de7439 | note | WP
8651ca52-2339-59c4-89df-a31dfa4aa940 | note | RESPONSIBILITY: Fulton Hogan
14741b2b-911e-5340-9c6e-9bb7b3e1ff9f | textbox | Date Completed:
197adeba-84ee-410e-9f93-35a047a4a729 | section | Construction Works
2039850e-57c3-4c1d-8ab6-0306284c52ca | checkpoint | 2.1 Excavation
dbed2e20-6ad4-525b-967d-1f550661c759 | note | FREQUENCY: Each lot
4a9b048a-c146-5b76-871c-46357244a781 | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task.
d77fbb20-7342-5960-9404-e0f786613752 | note | ○ Excavation operations shall not disturb areas outside the limit of works.
388542aa-b291-5a79-ae59-a587adafca34 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
dbebaa95-3c90-5d3a-a4be-5cce734ca83b | note | INSPECTION/TEST METHOD: Verify
a21354ee-c24a-5eaa-a3bf-1d597228ad2b | note | RECORD OF CONFORMITY: This ITP Signed Off
d1aaa39b-9c8d-5f48-b031-d1f3b3bd8ba2 | note | IP
3e13dada-65b0-5f05-a8c6-f4e522311381 | note | RESPONSIBILITY: Fulton Hogan
542e5ed7-a62b-5e5d-97ff-2385805557a6 | textbox | Date Completed:
7935d83e-e523-4b6d-a2bb-da73185e2e4f | checkpoint | 2.2 Excavation Permit
b128cb90-dae1-5459-9257-45cd8a735043 | note | FREQUENCY: Each lot
d0fca01f-92b5-5d92-aae4-9e2a9918beed | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
c42b960a-a422-51a1-80d3-3d2930791a52 | note | ○ Plant and equipment shall be appropriate for the task.
32b2bc80-a0ca-5e4d-8030-71d5e558651a | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
d6b49c50-ba97-52e3-b16a-b64c709e79aa | note | REFERENCE DOCUMENTS: Excavation permit
09a60d7f-0fa3-59cc-bdac-aafa4661ce72 | note | INSPECTION/TEST METHOD: Verify
976d7e5d-a1cc-57fd-a46c-4b76b2403167 | note | RECORD OF CONFORMITY: This ITP Signed Off
b1f3f29b-c351-5fbe-b0a4-aa1889a37855 | note | HP*
2b455bb9-bc9e-5e8d-9c9e-e8214f1d6566 | note | RESPONSIBILITY: Site Engineer
7f6913cd-28cb-55cb-a376-44d876f330dd | textbox | Date Completed:
f8f9bafd-18e5-403e-95d8-20d4306632c6 | checkpoint | 2.3 Reinstatement of bonds
c4f12eb4-91b4-5571-be44-56642b60403b | note | FREQUENCY:
15fb2aa9-63a5-5d2a-88d2-72185509fc65 | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
e5870d7e-609a-516f-9ca9-210090322eab | note | ○ All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
325e9723-1d26-530a-a268-489949e2e4f9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
2389c545-35f8-5b64-8d10-9e3d062cf626 | note | INSPECTION/TEST METHOD: Verify
1285b3ee-685c-5acf-9522-2a58a39e1467 | note | RECORD OF CONFORMITY: This ITP Signed Off
d9bd21ce-febd-5dd0-98ac-708dfb6e4e56 | note | IP
a7a9b900-8555-5385-a283-47fdaabe4658 | note | RESPONSIBILITY: Fulton Hogan
76e68391-d740-555d-9fa0-157c85675cfd | textbox | Date Completed:
b14bfaae-f99e-4df3-94ff-b18081698612 | checkpoint | 2.4 Inspection of subgrade material
cf34cb63-54b0-539f-bdf3-2b07d1f17f16 | note | FREQUENCY: Each lot
2c534c5a-b71f-5b37-8d53-3e1c9af854a3 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the standard.
d8302893-c90c-5646-86f0-0737a37c4840 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
4c0cd410-c387-53da-853d-f4a443a4fd64 | note | INSPECTION/TEST METHOD: Verify
5926aad2-0d0b-51bd-8873-bf05898c23f6 | note | RECORD OF CONFORMITY: This ITP Signed Off
6a11adfb-4d12-58f2-abbd-8bdf27210804 | note | HP
811d664e-c41d-57ea-a92f-af59f5273956 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
326c0e98-e7fa-50f1-acb3-ff10dbb9b3a2 | textbox | Date Completed:
231f288c-e53a-4097-b49d-801329058877 | signoff | AUTHORITY HOLDPOINT
4b94f321-ff4f-48ef-bd30-09624ef83c7e | checkpoint | 2.5 Width and level conformity
c3046608-a747-5a64-93fa-846e7ec9b6ec | note | FREQUENCY: Each lot
13ffbb1c-6e31-5cfe-bc26-32bba3bcb992 | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge.
e64870d3-f09c-5f11-8de8-be28cdf314ee | note | ○ Finished formation widths shall not vary more than -0 mm, +50mm from dimensions shown on the drawings
6e19b490-19c8-5d1a-845c-975000309f79 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
2ff05107-e56e-53ea-b7ac-d3090f1d848b | note | INSPECTION/TEST METHOD: Survey Report
2b18c231-2ef0-5c2d-86a7-2bbd65441559 | note | RECORD OF CONFORMITY: Survey Record
6a024413-589b-53a0-a448-3650f90f094c | note | IP
18fb3edf-3f00-5673-9bb2-6f14d7576b1d | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
531bff12-298b-5e54-9f3f-913e18bb116d | textbox | Date Completed:
d28daf45-8a65-4f83-ad05-46a0571c4113 | checkpoint | Final Inspection
30d2ef68-de00-567e-864f-1f8ad1752f06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e15950bc-7d75-5970-b347-62db625b48d5 | textbox | Print Name:
c9a97281-045c-5c62-b7ac-eda9c7e99805 | textbox | Position:
8e81ae6f-60b5-5311-b3be-7742a4c31458 | textbox | Date:
aac54ae1-ca8b-477e-99fb-5fcd68eee4c4 | checklist | ITP-002 - Feeder Conduits and Pits Rev0 | itp | ITP-002 - Feeder Conduits and Pits
4ec942d1-11aa-4751-96aa-354ae496ec85 | section | Preliminary Works
25807467-00dc-4cca-b38c-0d4dfb4bd51b | checkpoint | 1.1 Check for correct documentation
535b109b-cd67-5d2e-b90c-873f3bf530f0 | note | FREQUENCY: Prior to commencing any activity
5892fefc-a88c-5a54-acbc-768f31ba5ee5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
bb6fd18a-c06a-5b1c-94b0-693f6f97e5e0 | note | — using the correct and complete set of drawings
57baed9c-cc33-5eba-9122-a107b4b669b2 | note | — all drawings are the latest revision
e2929b03-c259-554f-bd62-65b8375b4778 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5ea591d9-2ba4-5f94-8daa-01e41022e4d6 | note | INSPECTION/TEST METHOD: Visual inspection
cc85bd4a-ba57-5d05-8d40-a1e1d4711109 | note | RECORD OF CONFORMITY: This ITP signed off
5ef394e8-efd4-5818-bb5f-62bffc243f18 | note | HP*
df6bc7d3-7d3d-55ac-a335-edf279d1c262 | note | RESPONSIBILITY: Fulton Hogan Engineer
091c8561-9fff-55a2-9d70-8c9e21e8f1f1 | textbox | Date Completed:
8dd7277c-2eac-4676-a895-61ee4234fc52 | checkpoint | 1.2 Implementation of all measures and controls
37a37713-3d81-5664-ad7a-1e26c245d794 | note | FREQUENCY: Prior to commencing any activity
03672aea-a642-5967-8278-7debe97a5229 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
87f69c3b-879e-5973-b749-c811a2713895 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
323ad4a6-e100-5b5e-914c-30a882753ede | note | INSPECTION/TEST METHOD: Visual Inspection
33ec9b47-7cf0-58e6-821a-700de575ee97 | note | RECORD OF CONFORMITY: This ITP signed off
eed0496e-bbac-5a91-90ce-7503c43afc89 | note | HP*
618f8c6d-ac05-5f9f-a85d-4c5dd7261a23 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed73a5e8-20de-541e-8f5b-dd49824a1eea | textbox | Date Completed:
a116781b-700d-4941-b381-340fa19abeb5 | checkpoint | 1.3 Materials
f18ed3d5-62ab-5174-8d42-0134c81f28d8 | note | FREQUENCY: Per batch
6a7f4301-fc21-5215-915f-fe6be7f23440 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be orange. (Heavy duty 100mm diameter UPVC)
c6d5c70e-a66f-5749-ac9f-75c69ca387bf | note | ○ Modula Stakka pits to be used for feeder pit, entries for conduits to be cut with hole saw.
e843d82e-d586-5a9b-a436-1aad698e656a | note | ○ All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
aaebeaec-9c37-57cb-b264-d41285f1a937 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4, AS 2053
b7b6cb17-efb6-57aa-8602-81bfca12c79c | note | INSPECTION/TEST METHOD: Verify
57609d56-3273-5f7b-94db-72d86195fedf | note | RECORD OF CONFORMITY: This ITP signed
fe8ae3cd-b4c6-5a28-8492-ec553e5ef5c2 | note | HP*
ac23a41e-aa2b-54c3-843a-8afeb6aa6433 | note | RESPONSIBILITY: Fulton Hogan Engineer
0cd9c0d0-14de-5529-ba57-97644919f0c0 | textbox | Date Completed:
705e7968-fa8e-4d16-9dbe-f9e764f5c258 | section | Construction Works
0cced63c-0c57-460c-b4bc-044a0e0f4edf | checkpoint | 2.1 Survey set-out
4cdc7c2a-da7f-53f5-bd25-780966862dbb | note | FREQUENCY: As required
72cc329f-c49d-5648-b795-6a6cc05520b0 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
7939ebd3-4906-5018-87b2-4f59300b82b2 | note | ○ Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
3d65114c-0fb3-5895-9f95-2617ca1a0ca2 | note | REFERENCE DOCUMENTS: Work procedure
a0336cfe-f09f-536f-8d55-46e57a032551 | note | INSPECTION/TEST METHOD: Verify
c5a487cd-112e-5c44-8b4e-84ef770ee119 | note | RECORD OF CONFORMITY: This ITP signed
591bb083-0cfe-53a5-9782-e951ef9d8e45 | note | HP*
853dc237-f654-5261-8e0e-2b209ec097fd | note | RESPONSIBILITY: Fulton Hogan Engineer
bd014e4e-0680-5c71-bc24-e7e70c7d3cb0 | textbox | Date Completed:
c633d6e0-06f7-4965-b195-eb205b2353ca | checkpoint | 2.2 Excavation and trenching
8bd7bac5-38ac-5c94-8916-5200bdbf5755 | note | FREQUENCY: Prior to installation
452cfe1d-e0d8-5732-99f8-76c0f172faa0 | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
78388d0c-12c7-56c0-bc94-b4f749af98a8 | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
2acdebf1-198f-518b-ac3d-6266d4b88b8f | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
e5fa2b9b-1444-5873-af71-b8bff87ba744 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
dc3e8618-6917-5445-b77f-29d921a41656 | note | INSPECTION/TEST METHOD: Verify
41f81144-2f6a-5a2f-a166-1f3442ede273 | note | RECORD OF CONFORMITY: This ITP signed
1e40a658-da67-5a6a-b003-5ae26972fcbc | note | WP
8a0e3e6b-c0b4-5b36-b475-f2cb40330a80 | note | RESPONSIBILITY: Fulton Hogan Engineer
3707450b-b8b7-5aa4-9f1f-e83c5bddd3ea | textbox | Date Completed:
fad1036f-1c19-41a0-a7e4-50c6eb3d42de | checkpoint | 2.3 Installation of conduits and pits
ec992536-e5d5-5411-be34-575cd21b8af4 | note | FREQUENCY: Each lot
41738d1f-e7b7-5b0c-a7b0-ec05440957f6 | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
b61fc287-481b-53ba-a4ec-0d2560a51d9d | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm sand
6f25cd8e-6938-53f2-88e8-c197451e3c3c | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
ad3d42a6-ec9c-5635-9111-d3c9edfdc090 | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
fc71a383-f4b9-55a7-8fa2-2b75fca265a0 | note | ○ Conduits shall not be subject to construction loadings
b679c795-67f6-5338-a25d-bc8ae78e705f | note | ○ Pits shall be constructed as to allow for class D rated covers
ef4b0a8f-475a-505e-9946-ed6a898b82f5 | note | ○ Conduits shall be placed a minimum of 100mm above pit floor.
5e41fdc8-fa12-5201-865b-64ac867c8581 | note | ○ A 50mm gap between conduits shall be maintained as they enter pit face.
b9aeded5-eb23-5fd2-b476-1c85ed7de782 | note | ○ Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
fb4aa4ab-c9dc-5b07-bed2-f40ef4d352e2 | note | ○ Conduits installed for future connections shall be installed to the track margin
c8801118-cab5-5436-929d-13a14b2e628b | note | ○ 100mm of concrete around and under pit lid to be installed for structural integrity
e9ea9218-8758-585f-b5c4-8d7156e51554 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
bba4f88b-8584-5058-8200-60a9404821ac | note | INSPECTION/TEST METHOD: Visual inspection
2b4f9611-12f6-566a-bb09-678c9973d766 | note | RECORD OF CONFORMITY: This ITP signed
5d2a95e4-1357-5d3d-abec-77b17af60232 | note | WP
68c680da-436a-5e42-b97f-486c5ed689ee | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
02b69a83-158a-5254-b881-c2efd0081581 | textbox | Date Completed:
ce72528d-e202-4177-868b-9f60d46ab5ea | checkpoint | 2.4 Inspection of conduit installation
3879a6ac-ebad-5899-a206-7b5e03ba8d0a | note | FREQUENCY: Each lot
5e498765-a8ea-5951-87a6-042b54bef8c1 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspected by superintendent and conform to design drawings before any backfilling is to commence.
2efe3ec2-afa5-54a3-9bc0-2cfcd95c2533 | note | REFERENCE DOCUMENTS: Work procedure
318f530e-4b44-5818-a2aa-7f7e38ace3e2 | note | INSPECTION/TEST METHOD: Visual Inspection
c8f0fd5f-d54f-5925-acfc-ddb276ac13f8 | note | RECORD OF CONFORMITY: This ITP Signed
7e14e642-a118-591b-b385-dbd27700f1e5 | note | HP
4776caaf-31fc-55ff-8189-58715b01457b | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
8853791d-86b3-56a4-9d22-169d67b5ac82 | textbox | Date Completed:
72be4b95-dcaf-4531-bdbb-04123e4efa22 | signoff | AUTHORITY HOLDPOINT
b40738d8-7916-4b1e-91b9-a3bc1bdfb98b | checkpoint | 2.5 Back fill of trenches
81e1b59b-af41-55a8-b982-bc64a1e3d353 | note | FREQUENCY: Each lot
bd50470d-743c-5f6b-b8e7-24e994f6f65d | note | ACCEPTANCE CRITERIA: Backfilling (only to be used for road crossing trenches)
5b50d62d-940b-55f1-9eda-235aec3dd189 | note | — Conduit trench shall be backfilled above marker tape with crushed rock or suitable material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
85101add-8292-5888-801b-88c39f0d5b80 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
5652f57e-8d9d-5563-b02e-a282c540d03b | note | INSPECTION/TEST METHOD: Verify
9dab2f3d-d4af-5dda-9b39-e90c49a18bf6 | note | RECORD OF CONFORMITY: This ITP signed
95ba804a-12ea-5cae-88b0-2872dbb5b73d | note | WP
24f36b7d-9f02-5bf0-a04e-1fafcdd7a23d | note | RESPONSIBILITY: Fulton Hogan Engineer
7542f548-1dd9-55ed-b656-ed175b753ea1 | textbox | Date Completed:
9c6c596b-a965-488b-bda1-5c82320aa9cf | checkpoint | 2.6 Installation of draw cords
87eb85c5-84b8-5f00-a080-ee8bdff23fdc | note | FREQUENCY: Each lot
ba30e44f-2625-58a5-8d1c-fea5aeb2f985 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'.
438145d6-d030-5bb7-be1c-620e1eb5ea3c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
93f28cc7-bb6d-5461-8323-156ae8dc51cc | note | INSPECTION/TEST METHOD: Verify
3c29fa3b-5493-5496-a4fd-9e5c0083c1cb | note | RECORD OF CONFORMITY: This ITP signed
00ac1255-15a1-5e1d-94e6-d811aa296b91 | note | WP
f197500a-9bab-50a9-a256-975826e108ce | note | RESPONSIBILITY: Fulton Hogan Engineer
0d908eb9-9961-5e25-aa3e-8f72254a84c8 | textbox | Date Completed:
076abba8-8a66-4ef7-9c59-b2e7fbce6953 | checkpoint | 2.7 Compaction
059ef433-3c77-587d-8d15-81197f23e197 | note | FREQUENCY: Each lot
2588b4b3-79c1-564a-b7c9-8e6d51384201 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant
bafab965-cb27-5ff2-abfc-dd4fff8c7bc2 | note | ○ During compaction optimum moisture content of bedding and select fill is within 85% to 115%
b206ef6f-91bf-538b-991b-f79ebdcd2072 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
7aa57e4a-bb8e-587f-bd08-d8774f3646cd | note | INSPECTION/TEST METHOD: Verify
98d3ff1d-6848-5769-9c58-eac99c079640 | note | RECORD OF CONFORMITY: This ITP signed
69bcb8b4-65d3-5947-9566-01d840ddc270 | note | IP
de23b773-4baa-5db7-abe7-572e85df38df | note | RESPONSIBILITY: Fulton Hogan Engineer
7649de86-0ede-5a6e-b1e2-fdcbab64b997 | textbox | Date Completed:
662e8388-28d7-4597-bf1c-06bf28cf0faa | checkpoint | 2.8 Feeder pits & pit lids
7c2321c2-8df7-5274-95ad-736ea03612ae | note | FREQUENCY: Each lot
c454deb5-7b27-5748-af0d-02e5f3076028 | note | ACCEPTANCE CRITERIA: Feeder pits to be constructed and installed as per drawings
c5616b5d-9861-5ba6-a4ce-c25b45e623a2 | note | ○ All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar.
14be7e6c-d815-5c13-88f1-590c4a2242fa | note | ○ Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
7d14f3da-e798-54e1-9a9c-77c6727e1bb8 | note | ○ Gatic pit lids shall be filled with structural grade concrete.
c7106aeb-39f8-5226-b458-839fd36f3164 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
b258e07b-1097-5f4c-bbbd-76e5670c4b85 | note | INSPECTION/TEST METHOD: Verify
cbbf498a-7b24-521f-b64e-723833b8ac87 | note | RECORD OF CONFORMITY: This ITP signed
b56cd7ad-a3e9-5586-b7ed-1a8831a43ae8 | note | WP
f4653ff9-b00d-5da5-b9ee-01291c01ea90 | note | RESPONSIBILITY: Fulton Hogan Engineer
8ae0f23a-7486-5cfa-8d7a-52d9b635302e | textbox | Date Completed:
791077de-0cfb-41b2-a72f-7f756bc8c324 | checkpoint | Final Inspection
593f3b04-64b9-54dc-9eb1-2e24198c99d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
af8eaf53-a16f-52bf-91af-8910a7eae9fa | textbox | Print Name:
8c95bb12-9cc5-5953-88bd-c5cc87417715 | textbox | Position:
700ad9cb-5d2f-5150-b22e-9a3c72be08ba | textbox | Date:
3e002970-de1b-4bbb-a862-96aef18b93ec | checklist | ITP-003 - Electrical and Communication Conduit Rev0 | itp | ITP-003 - Electrical and Communication Conduit
3f76849e-5d1e-4d28-b80f-7ca4a38a44c9 | section | Preliminary Works
a4c7e7ed-2850-4627-9c5f-7d8369692076 | checkpoint | 1.1 Check for correct documentation
32a2a393-0536-5fbb-bd36-e4624790ea85 | note | FREQUENCY: Prior to commencing any activity
c76ebc0e-0756-5a8f-8bae-d9694b0cf210 | note | ACCEPTANCE CRITERIA: Employees and sub contractors shall be issued with the most current and complete construction drawings
6273ea73-d7f3-5192-8314-0ba57ca943e3 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
273f7124-08bf-5fb0-be24-fe338693691d | note | INSPECTION/TEST METHOD: Visual inspection
f577ab11-d555-560e-bba6-207092fb3e54 | note | RECORD OF CONFORMITY: This ITP signed off
4a942b75-7039-5995-9d2a-67f58e3954b2 | note | HP*
d5ed1f96-dc70-53ae-bd71-3120de8f7b81 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a123c5d-6560-5a3e-8c96-e3edbae00816 | textbox | Date Completed:
1824364d-3336-457f-8a30-0fb3b0962bba | checkpoint | 1.2 Implementation of all measures and controls
4d8114b0-38f9-527c-9b6a-0c263944395c | note | FREQUENCY: Prior to commencing any activity
edcf1df8-2831-5a72-ad83-15b03166b111 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
2e875f45-2ad1-53cd-a674-5eebb1729af2 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
31301f99-8569-5f9f-8ae0-45a61622df3b | note | INSPECTION/TEST METHOD: Visual Inspection
d78af04a-a133-5010-8fef-2182c782115e | note | RECORD OF CONFORMITY: This ITP signed off
6d681095-1e90-57ce-85e8-c310f412dca7 | note | HP*
fdb3e60a-b957-5f13-8303-fdd37f97ce8a | note | RESPONSIBILITY: Fulton Hogan Engineer
770ea522-8b1d-5b39-87c0-ce0a86e0783c | textbox | Date Completed:
4be20747-d944-4e9f-b44d-d098a2859fb4 | checkpoint | 1.3 Materials
1aac4547-a9f5-5fa2-95f4-fcd14564e7d3 | note | FREQUENCY: Per Batch
4d359886-1e49-50e7-a79a-b35d83d4ef67 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required.
01704f6a-9021-56c3-aab6-73e226cb1d3a | note | ○ Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required as outlined in the drawings.
f20484c2-f8d1-547e-bd44-fdbc09f16f43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1, AS 2053
ad063aca-ed97-5a9b-9d70-0173ca4c2e41 | note | INSPECTION/TEST METHOD: Verify
59e29e63-aa5d-5523-9467-d396d73e164f | note | RECORD OF CONFORMITY: This ITP signed
3abd45f7-1018-543a-9a68-2c6f807fa764 | note | HP*
f967bc51-f443-5ff9-a6a5-e7e07abdfd83 | note | RESPONSIBILITY: Fulton Hogan Engineer
4e7a2367-ede4-5811-ae34-4adcbf896fe1 | textbox | Date Completed:
b32162a0-8d5d-4d67-a873-462db2fcb38a | section | Construction Works
db7b9f19-d3f6-4dfa-9f6a-2e505e673f6a | checkpoint | 2.1 Survey set-out
79de9372-37f0-5ccd-9647-8e50f0bd659a | note | FREQUENCY: As required
b211bd30-aed7-56b2-b3ae-0bdf58260fc7 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
2f0fe0c5-b702-5fe9-94ed-52d33dd3d7a3 | note | REFERENCE DOCUMENTS: Work procedure
7ed2d925-08e6-575e-80d7-bdc031a00d2e | note | INSPECTION/TEST METHOD: Verify
f17819ef-85b2-50af-9f59-eb987ad1b11f | note | RECORD OF CONFORMITY: This ITP signed
f8c95354-bb3c-59c5-a4d2-3439a7f30fc8 | note | HP*
d0058715-8fd5-59ee-b60c-6af369729ee9 | note | RESPONSIBILITY: Fulton Hogan Engineer
1d23bc2c-6423-5399-a44b-af62f5885287 | textbox | Date Completed:
98d3d84c-b320-4b09-9807-0ab9abe531c4 | checkpoint | 2.2 Excavation and Trenching
401cd34b-9081-55e7-aa7f-63c995efc412 | note | FREQUENCY: Prior to Installation
8d0559fc-1b03-5239-a801-59f63265ab66 | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
110c4d26-5e49-5e0b-81d8-d0f9f4332851 | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
14ce25ee-7b4a-56aa-8ea4-df5f33785f0b | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
685a6de7-971a-547b-9057-77472b0356a4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
075e69fb-a851-5ba0-b383-ddcf5fc5df10 | note | INSPECTION/TEST METHOD: Verify
f107feca-3ca6-56ec-bb0b-9d92c4756a7f | note | RECORD OF CONFORMITY: This ITP signed
1f497b13-81d2-5920-8c76-cb2f4ded62e7 | note | WP
6b541801-786b-5d76-b88a-6358549dbbfa | note | RESPONSIBILITY: Fulton Hogan Engineer
30490e2c-56b4-5dca-957e-75c89aee3694 | textbox | Date Completed:
ca5db87f-6476-441b-a8bf-6ed935411130 | checkpoint | 2.3 Installation of Conduits and pits
f8316da1-06d8-5ad7-b488-04bf7462f071 | note | FREQUENCY: Each Lot
f1496b34-0950-5ec8-9e25-e3362387b08c | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
d298efd6-6072-5274-9dd8-64297f0f9ae8 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
7dd8ace0-e5dd-5365-a500-b3191a98ba06 | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
aff2e8ca-6dcc-5bb4-83eb-f60bef501197 | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
4e4110d1-effe-5ea3-bb41-a5a4428bf76e | note | ○ Conduits shall not be subject to construction loadings
a6251226-d720-5c2f-991e-a9b3087b129c | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
4555f1dd-5480-56df-a7cd-34a42a6393c4 | note | ○ Conduits shall be capped with UPVC electrical caps
63d2b3d8-2543-57d6-b661-dfbc60ca5dfb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
2cdad154-0353-5545-bf79-cb41cc3b8aa6 | note | INSPECTION/TEST METHOD: Visual inspection
e262f4e7-47fc-5afd-8b17-83e3b30d995a | note | RECORD OF CONFORMITY: This ITP signed
00ab3183-971c-53f0-a53a-76d7d0cb3ce3 | note | WP
61c623b5-554c-579e-b199-c638d63ef02f | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
6b267bb3-ea49-50a9-8345-8b9ef5928f0d | textbox | Date Completed:
5c826401-c8a9-4499-9ed1-d5ac220ce93c | checkpoint | 2.4 Inspection of conduit installation
3b3ac2da-1fcf-5bce-9fa0-e0fb51957938 | note | FREQUENCY: Each Lot
9316d252-7e57-5710-94a7-254ffb7c3472 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
f562dd8a-f16b-55ae-a278-053899172b8a | note | REFERENCE DOCUMENTS: Work procedure
ee9b32aa-9322-5e8b-96f4-59b3686da0f1 | note | INSPECTION/TEST METHOD: Visual Inspection
da69af7e-a2f9-5215-8f01-bdce81759a5b | note | RECORD OF CONFORMITY: This ITP Signed
abd71ca6-e909-5912-a6ff-26a31ca623c9 | note | HP
72cf1ae9-b879-5c48-b0e4-7a94b5c58740 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
45ab6cce-44c1-59ce-b8db-52b4651da769 | textbox | Date Completed:
a1310fcb-b106-48f0-8f73-dacb07a4dcff | signoff | AUTHORITY HOLDPOINT
768f9792-af94-4ee1-90c1-261c984c4041 | checkpoint | 2.5 Back Fill of Trenches
4a0d70ea-5964-58f9-b1d2-9e7bdcd00c4d | note | FREQUENCY: Each Lot
1f3978a1-68f3-54c7-a208-ce7b8aff47bf | note | ACCEPTANCE CRITERIA: Backfilling (for trenching or road crossings)
0d3e1c18-bfea-5e0b-a37e-d38042597b59 | note | — Conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
a7c7c882-3574-5683-ba36-e348e3a24249 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
3c362695-88c2-584d-99e8-3d04d183e2a4 | note | INSPECTION/TEST METHOD: Verify
5d0a9d2e-27a3-586f-8844-35f054e02c6b | note | RECORD OF CONFORMITY: This ITP signed
cfed20d3-d2b6-54e7-8ab6-9db7dff6686d | note | IP
cb8f8e58-c032-5c6d-b2e2-35201613293e | note | RESPONSIBILITY: Fulton Hogan Engineer
d81acb42-ee94-5656-ac0f-176de83a9be4 | textbox | Date Completed:
78b39188-42db-47de-b480-62fc842b696e | checkpoint | 2.6 Installation of Draw Cords
d3f131dd-38ac-5ba8-b828-16cda14f09a5 | note | FREQUENCY: Each Lot
1fd69450-0254-5802-a307-10bbe76f2e7f | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
a3fc40fa-9f59-5a3b-9c2c-994e942c5910 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
143803bb-adfc-5265-aa1c-01bfb9b403b2 | note | INSPECTION/TEST METHOD: Verify
eec9fd94-8493-5bbc-9f74-551d2f0cac70 | note | RECORD OF CONFORMITY: This ITP signed
73ed4556-b82c-5e86-9f56-b8e7e252f7ba | note | IP
03bc95fd-e0df-5780-b113-0b96e363b019 | note | RESPONSIBILITY: Fulton Hogan Engineer
8b25d7e2-03c7-594f-b00e-0eb725e03e4a | textbox | Date Completed:
96e5c90d-bd5f-48c1-a596-19c354ff2bcc | checkpoint | 2.7 Compaction
6d7d6c54-2646-5166-894b-5f221d176d8f | note | FREQUENCY: Each Lot
57e60132-7f62-52a7-9dfb-e5c532e08ac8 | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
10effafe-a69e-5b16-87e7-8cbb8be01844 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
65408b3f-4262-5e5b-b716-9e95c7d656cb | note | INSPECTION/TEST METHOD: Verify
478b1e9f-ecfc-5ea5-b31b-68a6a80c7727 | note | RECORD OF CONFORMITY: This ITP signed
cc8ec27e-72a2-5323-ac4c-6465c41b873d | note | HP*
14f563ac-b352-58bb-afcf-834a7703e0ff | note | RESPONSIBILITY: Fulton Hogan Engineer
ee0c3906-50fe-54e8-8753-6ba26371f783 | textbox | Date Completed:
ed785e56-9163-4f6d-ae81-c5232e4310a2 | checkpoint | Final Inspection
b9b245aa-c395-5d09-b7ac-3916d9a389cb | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b7cd9645-9124-5ac7-bbd7-710eeda100e9 | textbox | Print Name:
1ddd18a6-09cd-5328-80dd-83675828f1a6 | textbox | Position:
7c04f0cd-2b52-5262-ba77-90081a417f44 | textbox | Date:
9b1767cb-4846-484c-89ba-d47af38f9338 | checklist | ITP-004a - Class 2 Base Course Placement Rev0 | itp | ITP-004a - Class 2 Base Course Placement
10e4938b-5557-4e63-a9d0-240b55dc4db3 | section | Preliminary Works
a80893aa-e99e-4861-80ce-43e95b240256 | checkpoint | 1.1 Check for correct documentation
340ee57d-daea-5591-a6e2-60d72f997d7f | note | FREQUENCY: Prior to commencing any activity
f188633c-33d3-5016-99a9-f3ae667afb6b | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
c0c211d7-fb9f-5808-b807-5661755eb394 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
cb9ea466-f271-5e9c-8c8d-d8b91b85a9b7 | note | INSPECTION/TEST METHOD: Visual inspection
9509757a-9551-55cd-83ba-dee1e92811c1 | note | RECORD OF CONFORMITY: This ITP signed
12bf3a8d-c591-5fb7-8b1b-4565d6cd6ebf | note | HP*
5eec070e-6985-5b1b-9973-47e80c09df48 | note | RESPONSIBILITY: FH Engineer
bef9c25c-5e11-54dc-a1b5-74fe53bd61ed | textbox | Date Completed:
d754f4c3-f24b-4298-b732-1980ae8faf17 | checkpoint | 1.2 Implementation of all measures and controls
c7bba5f0-3581-58a6-963f-c9520d43d1a4 | note | FREQUENCY: Prior to commencing any activity
aedc541c-1230-5c56-a803-8daa1f5094bb | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
f4cc9312-b984-5c48-8c23-a53f69a8b141 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
16c6abd0-0a3e-5bbf-8fa0-5ab17774177b | note | INSPECTION/TEST METHOD: Verify
92d40174-1b55-5bb4-a914-8fccf9fb18ac | note | RECORD OF CONFORMITY: This ITP signed
bb976d8e-7c4c-5d3c-87c4-10e6a6b46a1e | note | HP*
5b3f560a-4a13-5a81-b6c1-74f828004195 | note | RESPONSIBILITY: FH Engineer
082ffc1f-b4ae-5aff-b297-bf178a0c66eb | textbox | Date Completed:
0d0e002e-867a-4adc-ae5e-bf86d35dce20 | checkpoint | 1.3 Material Compliance
44ce27ac-bc57-55bc-ab1d-6a221a10a9ad | note | FREQUENCY: Prior to commencing any activity
e96e5361-43e1-5398-b99d-7a8a668b2b52 | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
876bae1b-dc7d-51e0-a34f-94fd27b3f7ef | note | REFERENCE DOCUMENTS: CE-019-ST-0033
80a9b794-51c5-5254-965f-9288f0e4009c | note | INSPECTION/TEST METHOD: Document Review
4b6e333c-fefb-58ec-825f-c2bf49c58524 | note | RECORD OF CONFORMITY: Test Reports from supplier
c3d259bc-02ec-51ea-8353-8237eabf7657 | note | HP*
972600e5-8e6f-5dbd-9a7e-6c1b4631f24e | note | RESPONSIBILITY: FH Engineer
9c05022d-1c22-5f92-a75c-e1d294bec75a | textbox | Date Completed:
bb423045-9a62-4884-a1de-211459e0697b | section | Construction Works
cf5c2167-402a-4d6c-b5e1-d1d4aa4737af | checkpoint | 2.1 Sub Base
bcf7396e-c0d5-53fb-9a11-ed1a154eb862 | note | FREQUENCY: Each Lot
dd30daf2-6381-5769-ad89-afa179234b42 | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
02162bcd-a39d-5510-b0fc-933205261de3 | note | ○ ITP-001 HP for subgrade inspection signed off
c88893ac-d40b-5a56-9302-308767926e8b | note | REFERENCE DOCUMENTS: VicRoads 173.03
32ff2ac4-6fdb-5e01-89a3-ddd74b495f87 | note | INSPECTION/TEST METHOD: Inspection / Test Method
b239e10b-eac9-500d-bf10-290a6c79d5d7 | note | RECORD OF CONFORMITY: This ITP signed
e46cc992-20a3-5385-b6b6-16eedea43ca9 | note | HP*
76221edf-ba52-577a-b39a-f50c27111c46 | note | RESPONSIBILITY: Fulton Hogan Engineer
8d3f0af8-dff4-55db-8a92-65ee28c3e13f | textbox | Date Completed:
eed0686a-9b02-4a3e-b993-fba0cf860562 | checkpoint | 2.2 Spreading material
e36eed1b-d0a2-53c7-8807-003b3ac6c704 | note | FREQUENCY: Each lot
298a4223-65d9-582c-8cb4-bcb5a2c8e8c1 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 150 mm in compacted thickness
efe144c8-7aec-509f-a27e-0d1cf597e2b4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
05140c27-dd0f-5b7b-89b6-b2bc37e369f9 | note | INSPECTION/TEST METHOD: Visual Inspection
06a4081f-dd4a-5a1b-b859-9d51d7aa1f0c | note | RECORD OF CONFORMITY: This ITP signed off
b0c51c27-baa1-5eb7-abac-c97efc7122f9 | note | IP
6ca2e4f3-713f-516a-b8d1-01451191d77b | note | RESPONSIBILITY: FH Engineer
046fa032-6507-5e16-91c6-70ff48ea307d | textbox | Date Completed:
58a28ac1-eb34-4304-a9bd-4d58ef56fc54 | checkpoint | 2.3 Compaction
24e09050-325a-58c8-b29e-223cc8b9a475 | note | FREQUENCY: Each lot
bbe10146-d1b1-5661-a350-73415fb783ff | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
2ea4fac6-aecb-5544-9fed-5911e01a50b0 | note | ○ Each layer of material shall be separately compacted to a density of not less than 95% Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
524e7553-d0df-5e1a-a422-42a5c17714a5 | note | ○ Compaction testing shall be carried out once per days production and shall comprise of three samples
76f32967-47c5-5ea8-b24d-7865eb305b44 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
a8a70741-6c05-5fae-92e6-73cb5f29d92c | note | INSPECTION/TEST METHOD: Visual Inspection
a003b387-2fa8-5529-96ed-63f2e856bcf6 | note | RECORD OF CONFORMITY: Test Results
6d5f115a-4c20-59bb-9179-6dcc8f2235d5 | note | TP
cab3d35e-c96e-50e0-aaf6-ef40f7c38432 | note | RESPONSIBILITY: FH Engineer
60ddd975-ae3b-5575-a6c8-499051b7cb2c | textbox | Date Completed:
10537d62-6f67-4eac-9daa-640fbfd3948c | checkpoint | 2.4 Level Checking and Conformance
c59e847d-9c6f-50d8-b4aa-4f136e05817a | note | FREQUENCY:
57f1b686-da73-55ff-9dc3-bd09994961e8 | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
8c8b51de-a60c-54fa-9164-f939668fdf20 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
5c448dbc-5b27-58c3-b419-0ef2f1b211d5 | note | INSPECTION/TEST METHOD: Verify
3abd4a6e-4f53-5486-8393-4e85e41301e7 | note | RECORD OF CONFORMITY: This ITP signed off
59837f1a-5f2f-5cd8-8ba6-7349d44fe3f0 | note | IP
a989394f-717b-5e10-b688-9c84f734fc83 | note | RESPONSIBILITY: FH Engineer
7b022863-c3c4-572d-b72d-410543089a15 | textbox | Date Completed:
bf5cdb84-704f-4582-8dd3-2001ef25d5a5 | checkpoint | 2.5 Finished surface
b9fc57d5-b4ad-5ff9-a791-39dc75bdde6c | note | FREQUENCY: Each lot
39036a78-31aa-5620-be8f-d9064a61c08e | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
3e3652e0-9523-578f-afcd-024723fc35b3 | note | ○ Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
28c10081-27c7-5f68-b97f-a0c5d3aaf379 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8
1a27a2d7-431d-5dab-acac-ca0130383bc3 | note | ○ Contract drawings
72ba95a1-68a0-5dfc-86d7-9d67cd6b2c87 | note | INSPECTION/TEST METHOD: Visual inspection
e8148a35-8eef-51d9-a975-d8faae788402 | note | RECORD OF CONFORMITY: This ITP signed off
85dbf55b-3c42-502c-8669-511d89227026 | note | SCP
66143f2d-ff69-56c6-b769-6eee478dc14a | note | RESPONSIBILITY: Surveyor/FH Engineer
4e94390f-58bb-599f-998f-da7aa348c3f6 | textbox | Date Completed:
dd073323-8979-4856-88ff-b39409b20eb4 | checkpoint | Final Inspection
009c307d-e07c-5dc5-93cc-3e67596930ce | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
aa685cfe-1b54-53cf-9ac3-5fbf8eb870b9 | textbox | Print Name:
a849abe0-c801-53e4-94c8-25836435eb36 | textbox | Position:
ff239eaf-2b9b-5c62-b9ff-bab10d122f12 | textbox | Date:
a5f5381f-177a-496b-97e9-24904fecd1ba | checklist | ITP-004b - Cement Treated Crush Rock Sub Base Rev0 | itp | ITP-004b - Cement Treated Crush Rock Sub Base
d4ba8cab-17b5-49ab-8baf-7fee98314320 | section | Preliminary Works
b6a9dab3-3d97-4c5d-81c9-9a1bd8dc0f6d | checkpoint | 1.1 Check for correct documentation
fe6de195-832e-5265-85e9-d987f0b3b4a4 | note | FREQUENCY: Prior to commencing any activity
ea2e139e-3b71-5194-bb9a-fb0a83882e13 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawing.
8396d6b6-b2f6-5399-8a53-58b52c190597 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c4490263-79c3-5f60-b750-f09d2c33c59d | note | INSPECTION/TEST METHOD: Visual inspection
ab604bb5-0504-5b15-95ae-843ef414e18a | note | RECORD OF CONFORMITY: This ITP signed
e6b5ae2d-f852-5e88-8e8d-ad69a0557302 | note | HP*
a15c0d1f-4abe-5af1-b4e1-f82c79cd6a7c | note | RESPONSIBILITY: Fulton Hogan Engineer
fa3d4f31-7096-53f9-a86d-5b8b86eeade2 | textbox | Date Completed:
6895abbb-4db6-4c56-ad3a-2baf49cb6754 | checkpoint | 1.2 Implementation of all measures and controls
57e85808-d8a9-587b-909d-9a49d99eb222 | note | FREQUENCY: Prior to commencing any activity
9ab105bb-970a-5b51-8914-349099e92b53 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
1256fdbb-e443-5ff6-bb29-819c9748050b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
c5e1a11a-a6b4-5e0f-81b3-b38c00106195 | note | INSPECTION/TEST METHOD: Visual Inspection
d74d5522-3d69-5906-bbc4-efa8c04ec47d | note | RECORD OF CONFORMITY: This ITP signed
63c88e14-339a-5f33-8de8-4f0639e74c30 | note | HP*
5b6b795d-a418-5568-bac7-5857667209c0 | note | RESPONSIBILITY: Fulton Hogan Engineer
4d6139c6-5aa5-553e-85a0-3b6d027ae9a9 | textbox | Date Completed:
66a7ef41-0bdf-4414-b417-bdcfe8ad6893 | checkpoint | 1.3 Confirm CTCR is appropriate mix
a2f2f255-74b8-526e-a5d3-6cae03544f1c | note | FREQUENCY: Prior to commencing any activity
726ae2c1-963f-5ff8-ac8f-34299049795f | note | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
f267eef4-9a15-5e55-826b-1a1d9f3994e7 | note | ○ CTCR shall be tested in accordance with 815.141 by supplier
ba193ab4-efba-5e6a-a4f7-ca31ba292aed | note | REFERENCE DOCUMENTS: Design mix specifications / delivery docket
c15cc7e0-69be-565d-a110-fb23ee58fbdf | note | INSPECTION/TEST METHOD: Inspection
62078614-28aa-593c-a4bf-e47fb34a2097 | note | RECORD OF CONFORMITY: This ITP signed
35a72ec9-dc8b-572a-9013-40b48a45f784 | note | HP*
b8d6414f-67ac-5afc-8af6-bf02d7195caf | note | RESPONSIBILITY: Fulton Hogan Engineer
934e8d8a-39a5-50a0-9fd4-3fc03f3e51b8 | textbox | Date Completed:
42c8444b-6138-49aa-8069-1d05d5c36205 | section | Construction Works
e5194035-07b3-4df9-a3f2-5434b744cae0 | checkpoint | 2.1 Sub base
c384b4ec-86fc-5f74-957d-2335655df6e1 | note | FREQUENCY: Each lot
2e05fc7b-8f6b-5977-84dd-774234a23bdc | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
3cbae13b-8bd3-5619-aeff-2fa7ada5466f | note | ○ ITP-001 HP for subgrade inspection signed off.
7be53d32-0662-57b1-8d30-7ac2e7f1da5f | note | REFERENCE DOCUMENTS: VicRoads 173.03
bc8a219d-7422-5e8d-8c43-4215ab0fc790 | note | INSPECTION/TEST METHOD: Inspection / Test Method
53de1f33-a988-5f42-91ba-4a22afbc50e4 | note | RECORD OF CONFORMITY: This ITP signed
6a4f7c1d-a5a1-5515-bbe3-d28dbe71236b | note | HP*
e193ef37-753e-5a14-88f5-a2a6c721349d | note | RESPONSIBILITY: Fulton Hogan Engineer
98c117d7-e3a1-504e-aee3-d46de046d5ba | textbox | Date Completed:
19690390-aeb3-431e-84f4-e9461af0fb52 | checkpoint | 2.2 Moisture content
5a5d7064-bf3b-5492-9b08-1e6518d52858 | note | FREQUENCY: Each lot
b765bb08-14a5-50f3-beb4-5959bd7668d2 | note | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
47aef018-3b9c-5d9d-964c-f1695025a4ba | note | REFERENCE DOCUMENTS: VicRoads 306.05
aeaf001f-513f-5916-9fc5-316aef88e942 | note | INSPECTION/TEST METHOD: Inspection / Test Method
bbeba48e-219b-5c2e-a566-92527ea1b27e | note | RECORD OF CONFORMITY: Record of conformity
482887ee-0cbc-5610-9cc0-5063ee7e7903 | note | IP
8941fe12-6369-542e-93f2-3efe6e061ea4 | note | RESPONSIBILITY: Fulton Hogan Engineer
0ccc1956-da1a-5fb2-965c-6474cdf1be8f | textbox | Date Completed:
d44e5c84-07b0-428e-84c9-339fed6ec8a2 | checkpoint | 2.3 Jointing
000e4484-b38c-5332-abb5-79fe411a385e | note | FREQUENCY: Each lot
63e14874-be07-5453-be46-a5561ee5929e | note | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins.
eae5be51-7fcb-589c-bea3-a8daa11bf701 | note | ○ Transverse joints in adjoining paver runs shall be offsset by >2m
db10d1c5-3e82-5d26-8413-1ac1afdc75ca | note | ○ Longitudinal joints shall be offset from each layer >150mm
5b39c126-867e-54c3-898b-eb3268acf094 | note | ○ Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
aa255b83-f635-5caf-bdee-f64549e7fff8 | note | REFERENCE DOCUMENTS: VicRoads 306.08
3ea8c35d-927f-55b3-a8df-0218669c1577 | note | INSPECTION/TEST METHOD: Visual inspection
7175edd9-0a0e-5d0a-87c0-24bc9bd4a25c | note | RECORD OF CONFORMITY: This ITP signed
3d8b6f0e-1ce7-54f4-9f84-ef94ef1fb87f | note | HP*
7ed712a3-076e-518c-ab74-0b3f2a91ee03 | note | RESPONSIBILITY: Fulton Hogan Engineer
934fc7dc-d397-5a6a-86e0-4135d0f72f72 | textbox | Date Completed:
c4864c65-0656-4861-8af1-f4736caef0a6 | checkpoint | 2.4 Conformity with drawings
000852b7-5520-5e79-9ecd-177450fea380 | note | FREQUENCY: Each lot
3533fc19-81bd-5116-8b45-626a0922f2c4 | note | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
7efe4fde-b88f-53e0-8e99-8a97e3960499 | note | ○ Surface of sub grade shall not lie more than 12mm below a 3m straightedge
a8c67f8d-04bd-5ccb-9788-f37f2071bfe7 | note | ○ Subgrade height shall lie within +15 to -25mm
f95bc24e-61c6-588f-92c1-5491b36fa70e | note | ○ Sub base height shall lie within +10 to -25mm
9acac0ab-160c-5e13-82dc-d938c980ff2c | note | REFERENCE DOCUMENTS: VicRoads 306.03, 306.11
f3d6643c-a053-51b2-83cf-68f132c1fe45 | note | INSPECTION/TEST METHOD: Visual inspection
1826f751-2b40-596a-91ee-039dcfd2bc8d | note | RECORD OF CONFORMITY: This ITP signed
8b48bb33-857f-565f-8551-b3d6bc639256 | note | WP
f3e89b5e-316b-5571-9ea8-e4fd23c4338f | note | RESPONSIBILITY: Fulton Hogan Engineer
82e930c5-5d02-5968-9493-df9d71aed577 | textbox | Date Completed:
1494e3c4-899c-4bea-addb-74d55d2bc370 | checkpoint | 2.5 Curing
cfec08de-447a-55ea-ae34-ba819162adc8 | note | FREQUENCY: Each lot
23d8cae3-f47d-5c09-bbeb-44dd0d2db434 | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
43d7ff6c-0f4f-57d9-8452-4e34b8191f30 | note | ○ As per VicRoads, 4000m2 shall be maximum lot size
7b966711-4061-55bb-95e5-b940a152a2d4 | note | ○ No trafficking before 24hrs unless approved by superintendent
8bbc1ce7-e9aa-50e8-ad3c-2dfec6e7fea8 | note | REFERENCE DOCUMENTS: VicRoads 306.11
cd9de153-ca7e-5466-b279-dc86a124dff2 | note | INSPECTION/TEST METHOD: Visual inspection
107495d4-441f-5726-b9c2-ca4487194f0a | note | RECORD OF CONFORMITY: This ITP signed
d877aaa7-2a65-5e65-a113-b7e0a471ca24 | note | IP
8b03abac-d614-5018-9cf7-ad551d27ffd2 | note | RESPONSIBILITY: Fulton Hogan Engineer
58057136-9a80-5b1c-a84f-403fa1dbe782 | textbox | Date Completed:
aa20b0a7-e096-40cb-af09-74ace3c218ed | checkpoint | 2.6 Compaction testing
32ae7356-f8dc-5674-8090-c4ab57824343 | note | FREQUENCY: Each lot
90caa38e-450a-57e0-91da-6a0535df85b9 | note | ACCEPTANCE CRITERIA: CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
de876c52-4e0d-538e-9d2d-cb3b58071eee | note | ○ At completion of compaction, any segregation shall be rectified
f2d55109-7836-504d-afc9-49a8ed330966 | note | ○ >500m2 96% modified compaction 6 tests
09e01c2c-80c6-5716-8dae-a2fa9220cde8 | note | ○ <500m2 98% modified compaction 3 tests
611bf62c-36e8-5950-beec-e4c126a5e041 | note | REFERENCE DOCUMENTS: VicRoads 306.09, 306.11
dee4213a-8bfb-5bee-bd91-3c62ffd50e79 | note | INSPECTION/TEST METHOD: Visual inspection
e42292df-a26c-5c75-9f9f-9c94d071d68f | note | RECORD OF CONFORMITY: This ITP signed
7e951758-0d1f-5292-ad60-88714adced3d | note | TP
0722eae4-3073-54e6-8fcf-ccbe9fd7a587 | note | RESPONSIBILITY: Fulton Hogan Engineer
54f7798d-ebd7-5695-9577-5843ccd5a23d | textbox | Date Completed:
dbf2a037-9cd3-43c5-9e03-3f335e32d52c | checkpoint | Final Inspection
dae7fd78-d820-5429-aebc-d52bdb577211 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0fe34e41-dc29-58be-8710-01c2e223206e | textbox | Print Name:
bd146059-a01e-5b55-aa82-0da5b49a51e7 | textbox | Position:
ff06f79e-dbb9-5bcf-a715-2cd822438544 | textbox | Date:
8db8df68-b917-4218-b838-6f3fe0d32438 | checklist | ITP-005 - Track Drainage Rev0 | itp | ITP-005 - Track Drainage
f211e8b4-f756-482a-956e-eb06c7167fbb | section | Preliminary Works
32f22014-01bd-452a-9680-0f806f9b7e54 | checkpoint | 1.1 Check for correct documentation
9b7779de-2edc-5325-a764-2a10373e1e96 | note | FREQUENCY: Prior to commencing any activity
81bbb47a-007a-5555-9bb3-e5e44a8e4476 | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
0b117031-cc00-547d-8674-55bf5bc790b0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1f88264c-94f2-5920-802f-33a97e6ce789 | note | INSPECTION/TEST METHOD: Visual inspection
8921fccd-b541-5dc5-b9e3-36cce7873422 | note | RECORD OF CONFORMITY: This ITP signed off
b13cdabc-61dc-59cb-b693-0189d2d845e9 | note | HP*
484ffb94-dd10-50bf-bc77-98d760db769b | note | RESPONSIBILITY: Fulton Hogan Engineer
e382e772-0bdc-507b-b0ec-e62a68c9d73b | textbox | Date Completed:
a6149a17-020c-423e-b5f1-673b8042f38a | checkpoint | 1.3 Materials Check
ac19f010-c5a5-5461-9978-9f422c639f21 | note | FREQUENCY: Prior to commencing any activity
288d1ca9-7da9-52b3-98d9-91aabfc5cdd5 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage
bfb91754-24a6-5104-a4fe-36b3ed961a4e | note | ○ Check triangle drains are of adequate quality, and are design according Ri57A rail profile
7ec85edb-6472-5919-b84f-cc2c2af85198 | note | ○ Ensure lid and j-bolts being used are in accordance with STD T9022
0c56c8e2-3cf9-5b02-8494-b024ca9999de | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A, STD T9020, STD T9022
affc0fdb-af95-51cf-ac0e-a19632558715 | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
aaba740a-ce1d-535e-8b7d-79e6192fe556 | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
ad31ed8e-e42b-5976-b680-9b7d2e57511c | note | HP*
561965bb-6788-5158-9bbc-856212a2d758 | note | RESPONSIBILITY: Fulton Hogan Engineer
31c3ae6c-602c-5cf2-9782-5789b613236d | textbox | Date Completed:
02d5ac73-b472-490d-ab43-125dac9172fa | checkpoint | 1.4 Bedding Sand
a9947a49-257f-557b-8509-30c5cb504f74 | note | FREQUENCY: Prior to commencing any activity
3cdc6c1e-277d-5c9b-ad85-f5cc6c2349d0 | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities, Consisting of hard durable particles, and well graded.
890be2f5-0a25-5259-bf65-f81f464dddf6 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
cef0e660-5c83-5c36-bd35-cc10e02b37c9 | note | INSPECTION/TEST METHOD: Visual inspection
dd96ac5e-d3e8-5192-8544-3ff9ac850386 | note | RECORD OF CONFORMITY: This ITP signed off
f1490965-5deb-5710-b80e-7d8f90aed889 | note | HP*
c7ecfe6b-865c-55eb-845d-fd1b625be8f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
58e7326f-a683-5f2a-9c1c-2e0fc679f45c | textbox | Date Completed:
a9a06c3e-313b-426a-a219-ab0e04cbcade | section | Construction Works
48f9a940-8bef-42af-a6f5-b0f05317bbd8 | checkpoint | 2.1 Set out drainage
7916a33b-c98c-5b4a-9801-8230a49c0096 | note | FREQUENCY: Prior to commencing any activity
84a88dd0-8d7e-550c-b4f7-189917c34fb2 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
f806a09f-88c4-54ef-90d4-eacdc40df267 | note | ○ Track drain locations are to be identified and based off IFC drawings and sections.
f43def90-595b-5526-a13d-545fc5d747d5 | note | REFERENCE DOCUMENTS: Design Drawings and Register
265da843-38a1-5e65-9468-a456b74da0a8 | note | INSPECTION/TEST METHOD: Visual inspection
54b0e355-9783-584f-8b6a-6c30bee30716 | note | RECORD OF CONFORMITY: This ITP signed off
704bc52c-057c-5506-b0ce-2fc456d1fcfa | note | HP*
b0f35b01-fe37-5a07-ba7a-267f2c0581e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
eda201db-8b3b-5004-a711-c58c309d1576 | textbox | Date Completed:
5cbbdf67-0f52-4d12-a0e6-00db05d6a3e7 | checkpoint | 2.2 Excavation (pipes)
60e152d2-99c1-5dde-8b91-6750cca837be | note | FREQUENCY: Each Trench
e08c8291-163b-5c6a-a5f8-59a1506c9179 | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
db096ee5-cb59-5689-842f-1c6ba285a447 | note | ○ Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
40eaa971-34f8-5be8-9821-76acdd2b8945 | note | REFERENCE DOCUMENTS: STD T9021, CE-021-ST-0044 cl 4.3
58d027ae-60c4-5d64-98b0-b7ac3754720c | note | INSPECTION/TEST METHOD: Visual Inspection
43ef87eb-ef13-5793-a85f-e6ad3b01ea89 | note | RECORD OF CONFORMITY: This ITP signed off
d989b0ed-1a4e-5a34-b2c9-77f6162d935a | note | IP
700a9200-6a7c-50ff-8c72-4b6fb3c08c0b | note | RESPONSIBILITY: Fulton Hogan Engineer
7bc1c302-c79a-5436-9229-171293543af7 | textbox | Date Completed:
95f500f8-4415-4d80-bd6d-4e3d2ed446ee | checkpoint | 2.3 Bedding
896c581f-b779-592d-aacd-f8358de1d612 | note | FREQUENCY: Each lot
67dda2b1-3e39-563b-a788-5442e9474135 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
fe850d6c-4352-5f06-98af-36d2cf4063c4 | note | REFERENCE DOCUMENTS: STD T9021A
51e5090f-18e1-539a-9f88-40351228b6d1 | note | INSPECTION/TEST METHOD: Visual inspection
26785b1f-5a2f-596c-8c0d-469caea86938 | note | RECORD OF CONFORMITY: This ITP signed off
3e411ca4-142d-539f-91cb-a4f9d91292e7 | note | IP
ca4f3e15-9abd-591e-bc57-5e3868001c3f | note | RESPONSIBILITY: Fulton Hogan Engineer
63e085c1-d904-5bf2-9da5-76a476a7de18 | textbox | Date Completed:
525ddf0f-dcd7-49e8-ba1a-c40aac545c5e | checkpoint | 2.4 Joining
3d064395-e935-5c95-817c-47522da72a2c | note | FREQUENCY: Eaach lot
2a38d54e-c802-5f50-9de3-2038939653c3 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
d9558c09-c755-58f2-91db-30b85498d52d | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
786af655-15c8-534d-84f7-440eaf21ddbd | note | INSPECTION/TEST METHOD: Verify
274699db-24a7-580f-b009-5c022beb2c1e | note | RECORD OF CONFORMITY: This ITP signed off
01ed5430-9914-587b-9aa0-1056dd7aac89 | note | IP
f9e24f12-be63-54ef-ab38-f9e17f7ca4a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ecf27016-17ab-5299-a3b9-f9a00ee9f078 | textbox | Date Completed:
1f97653e-6ae7-4ca8-a1e6-9fa750ae14a1 | checkpoint | 2.5 Track Drain Installation
6b30f7c7-bb36-500e-beee-3f2396773113 | note | FREQUENCY: Each Lot
c0948d58-131b-522a-8c87-b9be6743fccd | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter.
ca1f059a-8fb2-517a-afbe-b45acaeeb6c0 | note | ○ Weld shall be sealed after installation
18238f64-bbf8-545a-9406-211476a6860d | note | ○ Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
a9d3ba30-9ce8-5d65-953b-980f516cf1cc | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
f63fb71f-6be1-5386-a124-288a75fec61a | note | INSPECTION/TEST METHOD: Visual inspection
fdf40ef9-0ec3-58d4-afd2-94ec4298abdb | note | RECORD OF CONFORMITY: This ITP signed off
8886d214-139e-5b17-b334-c4b812c7a655 | note | IP
e5a8f316-90af-5e72-9537-4399dd32c155 | note | RESPONSIBILITY: Fulton Hogan Engineer
082b822d-027e-5414-8426-ea461ba4d557 | textbox | Date Completed:
b630f12c-95eb-4330-9bc9-b2dff8d88f2f | checkpoint | 2.6 Points Drainage
a157db1e-cca6-522a-a8fc-685737a936e0 | note | FREQUENCY: Where required
28ea0da0-53af-5cff-822b-8a2d5bd7519b | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
501766c7-2b83-55e0-9616-112d23fc004d | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304, STD T0305
27320a21-e124-5c10-8b42-ec39f7b141df | note | INSPECTION/TEST METHOD: Visual inspection
854ab0eb-8176-59c4-b581-831d1a3d8b99 | note | RECORD OF CONFORMITY: This ITP signed off
b32be08b-f296-5f7c-97a6-ce7ec1e96d0d | note | IP
88abbd22-637e-52c6-bef2-c1a0e279aff6 | note | RESPONSIBILITY: Fulton Hogan Engineer
46ceeb3e-2c3d-5af4-a87e-d23bc9943fd6 | textbox | Date Completed:
c39e879e-7775-426d-9c83-ff5d2f09d388 | checkpoint | 2.7 Concrete Pour
cd9d8bf9-2131-5e16-be10-94af972108e7 | note | FREQUENCY: Each Lot
d0e26c80-7562-5bfa-a7b9-c29cb064e003 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
7d6dcb1e-dc31-5a94-93f8-b93ced67fa90 | note | REFERENCE DOCUMENTS: STD T9021A
5bf80a2e-8138-50b4-81fd-f4226871528c | note | INSPECTION/TEST METHOD: Visual inspection
a2ffe3c5-565f-5c30-9561-ca47a32536c4 | note | RECORD OF CONFORMITY: This ITP Signed off
624d0e01-6fcb-57a9-acc7-43f688b199ea | note | IP
679975cf-7258-5c29-80e5-4e53f8b8a1e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
614ab9fc-e6a2-54c6-9c25-3ea769e99c37 | textbox | Date Completed:
b66a9432-9cf0-4a05-8ca3-c58adf2dcdd2 | checkpoint | 2.8 Connection to local drainage
55225dc2-96e8-52a5-924a-dd1269d386f5 | note | FREQUENCY: Each Lot
9007de5d-5a2c-53ac-a3f8-ef93bf51d46b | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
12bf3714-2c36-50ea-9d4a-ddde549f5730 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
ece9a43d-c9f0-5129-8771-c06dc4203131 | note | INSPECTION/TEST METHOD: Visual inspection
3a2eff1f-7b8b-5675-a93b-558f104ff304 | note | RECORD OF CONFORMITY: This ITP Signed off
0c224f1e-ef97-592a-982e-0cb7d795a42d | note | IP
058e4b3c-b523-5006-ba0a-a8add3078d4a | note | RESPONSIBILITY: Fulton Hogan Engineer
7cf971e1-57f3-58a8-a772-0085494ada92 | textbox | Date Completed:
52ac3633-0708-41dd-8434-ac75920f42dc | checkpoint | Final Inspection
85f27d61-d09c-5de1-afdd-86168555bae1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0027562f-7c2c-5c35-b13a-a4644669dd17 | textbox | Print Name:
c0564a88-0c86-5b29-8133-2478e04be5a6 | textbox | Position:
ae4842ef-4f83-5c47-96db-1735fbd75c86 | textbox | Date:
a935df5b-4993-415b-9338-e549bd90cf5c | checklist | ITP-006 - Track Placement Rev0 | itp | ITP-006 - Track Placement
ee9098a1-ac7f-40a4-8e2d-65c22e845241 | section | Preliminary Works
1ff2876e-2c6d-4345-aadd-d100d69c80b0 | checkpoint | 1.1 Check for correct documentation
c6359e05-8f8e-5439-8029-4c9627c6cd9a | note | FREQUENCY: Prior to commencing works
fd16ada8-a829-52f8-bc6e-370a3048a831 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
3f0562bb-7b1d-5c44-9b46-bf86b731ec7a | note | REFERENCE DOCUMENTS: Design Drawings and Register
8ee34719-ace0-5c0f-84c8-4c7697ec2366 | note | INSPECTION/TEST METHOD: Visual Inspection
e90f2847-bf76-5cf7-b666-6ad42af1bf16 | note | RECORD OF CONFORMITY: This ITP Signed Off
30c43d86-e5b5-5887-83d2-c974dff535ac | note | HP*
0ba42bad-e376-5376-af10-5111d0d95c50 | note | RESPONSIBILITY: Fulton Hogan Engineer
15c8e0f0-166b-525c-9b21-f8ba196aee86 | textbox | Date Completed:
ed9308b6-5a90-4d4e-a3ab-26d87cf63380 | checkpoint | 1.2 Check materials
f2db2366-90da-5f4a-b74d-0675c1b34d9f | note | FREQUENCY: Prior to commencing works
36478e70-b797-54ec-b9c3-4be01c45ecc1 | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
536aad0e-a663-500a-be81-df535a70e3bb | note | ○ Check condition of rail sleepers
055ec6fe-13de-5239-bf9f-5b1bcbd0a32c | note | ○ Ensure rail jewellery is of sound condition
2071c55d-4af2-50d2-be93-66915f1ef743 | note | REFERENCE DOCUMENTS: AS 1085
bef9d769-21e7-5c14-9e72-b76f4cc60465 | note | INSPECTION/TEST METHOD: Visual Inspection
d1921cc6-1a4a-59d9-bc5e-e58921f84cf1 | note | RECORD OF CONFORMITY: This ITP Signed Off
daf40a30-fc88-5b81-8021-12a1b3c10eda | note | HP*
8e54cec9-d29f-5741-9869-9bc1cf5bd493 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
5fa8ed6d-76a8-5516-b15d-ce2b75c6445e | textbox | Date Completed:
5e3940b0-3ff9-4554-b7f7-c03a51867e6a | checkpoint | 1.3 Check special works components
f227498b-a352-51f7-8152-2784f1d57d9a | note | FREQUENCY: Prior to commencing works
0868c953-ed7b-5dc7-8274-342a04df92db | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
0162c88e-e167-544f-a2dc-13ec23ac3fdf | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
85db6486-6225-5ada-b94f-4d3130c85650 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
026404c8-64e4-56aa-aa82-7b56c06c0658 | note | INSPECTION/TEST METHOD: Verify
29a91bc0-a561-59f3-938b-d03cce021506 | note | RECORD OF CONFORMITY: This ITP Signed Off
6b675641-ade6-5fa9-82e0-a936ca89f1ff | note | IP
d540d160-ebab-5757-abaa-c2e7709c8e18 | note | RESPONSIBILITY: Fulton Hogan Engineer
ed91ad85-bee3-503d-aba8-4b35a4da7302 | textbox | Date Completed:
76b5c9ea-98a2-499b-bf15-132563aa4d23 | checkpoint | 1.4 Check curved rail
fe680ed1-847f-53d6-815a-09634fe2f6f6 | note | FREQUENCY: Prior to commencing works
66994ac4-2a0c-57a5-b92b-cae1e9e2ff93 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
8803b545-ca6c-50b4-a8f3-7536fb6dc0d3 | note | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.
a48f8d45-51e4-53c2-919d-e9b5c76a94b6 | note | ○ This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
27dc0c93-d82f-5339-bd51-739d0219bc26 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
0fa09954-0b4f-54b3-b5a7-be2595d4c153 | note | INSPECTION/TEST METHOD: Verify
a8269841-7396-57c8-ae4a-a71c963c39bd | note | RECORD OF CONFORMITY: This ITP Signed Off
76f8e63c-8198-548f-80a9-4888ae25569b | note | HP*
d861c47f-95ca-551e-a8af-05db5151a824 | note | RESPONSIBILITY: Fulton Hogan Engineer
bd646b63-9737-579e-b78f-cb5a6e098f4c | textbox | Date Completed:
b6c7b87e-3bbb-42e6-9fa1-ecf6387137d1 | checkpoint | 1.5 Welders qualifications
e2c8438e-f1e5-54ec-a3a5-69979b337f49 | note | FREQUENCY: Prior to commencing works
53e8369c-f0ea-50fe-bd49-b008ad7d6ace | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
2aa1ad94-8030-5ac4-a79e-80773a341a7a | note | — TLIW2012 Grind Rails
4df68c2a-c58f-5ff5-aa4e-daef912b473a | note | — TLIW3015 Weld Rails using Aluminothermic welding process
95d370d9-7fa6-52c1-af25-e825f930013a | note | — TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
c4df7e04-2acf-5aac-95e0-82ac15bca5e8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
d0d8f763-9661-54e0-9338-746febcfa0bb | note | INSPECTION/TEST METHOD: Verify
9ae2af76-2ad8-5eb9-8cec-6430932d242b | note | RECORD OF CONFORMITY: This ITP Signed Off
ab07f14a-1768-525a-a8aa-ca78225c02ea | note | HP*
4eade9f2-ef7c-5194-ab76-eaad06bbd5b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
484cb35a-64e0-585d-970b-d45ebd4b75e1 | textbox | Date Completed:
d0df1a41-d823-4fd6-ad30-b9d0db4d1afd | checkpoint | 1.6 Ultrasonic testers qualifications
5a749d6d-95a7-5c6d-bbfc-6ca8a0c12663 | note | FREQUENCY: Prior to commencing works
d46b2f53-801a-5a3e-8129-5e16fd61abce | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
12e8665a-92e5-5245-af14-a51534c23383 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
97c7cbc6-aea1-5fbb-9356-545015354d47 | note | INSPECTION/TEST METHOD: Verify
efb0b0f2-c8f1-5695-afea-f8487010012e | note | RECORD OF CONFORMITY: This ITP Signed Off
8c7829cb-49b6-5113-b6d9-c03efa824a1b | note | HP*
3a14d0f7-9b75-54ee-950f-c29d4b5f4973 | note | RESPONSIBILITY: Fulton Hogan Engineer
80497af6-216c-5976-8ac0-fe9f0f7d2b29 | textbox | Date Completed:
28a5ee3d-0768-400d-a56c-bb47aa69d75a | section | Construction Works
17913085-6dcf-4b11-a98f-d8d7dad70cd6 | checkpoint | 2.1 Installation of sleeper
0718c046-eb97-51ca-8767-ed3305f572e4 | note | FREQUENCY: Each lot
f68af345-af42-5627-b1a4-b459c5cb2827 | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
05a7ab0f-c277-59b5-a13c-cae8c60ad83e | note | ○ Dual block sleepers shall also comply with the design offsets at each chainage
22cf9491-4345-537d-aa52-31ff2299dfef | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
21a079e1-8208-57c7-8bbf-812ce0770039 | note | INSPECTION/TEST METHOD: Visual Inspection
60b5c47f-8482-518d-b48b-2b5ff2a81a5f | note | RECORD OF CONFORMITY: This ITP Signed Off
0315cab7-2e71-5ce1-905c-ba0782336887 | note | IP
718220ab-4c8f-5323-ae0a-77f09e7951ad | note | RESPONSIBILITY: Fulton Hogan Engineer
c670ae43-6727-570f-a6d7-55062f1ef9f7 | textbox | Date Completed:
d04d9ad6-c246-4c15-bc59-1dc0814635c3 | checkpoint | 2.2 Placement of rail
6555a2b1-78cc-5959-a820-49da5d20ca24 | note | FREQUENCY: Each lot
652d410e-ea56-5a15-90ce-210b9d967fb2 | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
c51275bb-c07c-5799-91dc-cc8912e35e83 | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
bc8f09e3-4a31-5598-a6a7-3df589fa9de7 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
c2d9c168-4802-5a1e-90af-d0764320ebe4 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
1a67592b-ae5b-5344-a5f3-4c1999831a22 | note | ○ Geometry tolerances as follows:
ea64ec27-d9d8-5b15-9234-5f9fd239a58b | note | — Centreline location: +/- 3mm
9cfa7116-7754-539c-ba3f-d53d46d29e74 | note | — Level: +/- 3mm
944c8a72-dcd1-5d86-9875-dfd328e644bf | note | — Line measured (>10m chord): +/- 3mm
56d30f11-6203-5eaa-8836-955ee32ebcae | note | — Twist (3.5m chord): +/- 2mm
4ade00b2-9728-596f-ae3e-9ec1b9aa2409 | note | — Cant: +/- 3mm
076e49cc-3dab-5091-868a-c4ca9f120e6c | note | — Gauge (open track): +3mm, -0mm
7df42bc8-a093-5b6c-9d11-1a98be0feef5 | note | — Gauge,Turnouts (opposite crossings):+2, -0mm
6df26bfb-589b-5220-864e-524836f51d9c | note | — Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
5d8fa9d5-08e3-5814-be09-28943836eccf | note | ○ Note: Cant shall be applied uniformly over transitions
1bd7454f-08a7-5021-805b-3c083546dfa8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
4cc05c58-7e4a-57ae-af35-cb572aefa179 | note | INSPECTION/TEST METHOD: Visual Inspection
8e3c4d3f-8f4a-51c8-960f-b0960cda6218 | note | RECORD OF CONFORMITY: Completion of track charts
57e36add-b14f-574d-a8be-eb533a55bad2 | note | HP*
dfd39f2d-91b5-531f-bc1a-2353f0c97dfb | note | RESPONSIBILITY: Fulton Hogan Engineer
e7fe5546-c2fe-589d-a50f-f95eb45fa3c0 | textbox | Date Completed:
ac821188-6d97-4a55-abc2-fc83f89811e4 | checkpoint | 2.3 Placement of jewellery
013cb650-f02a-581b-a2b2-b310324cc15b | note | FREQUENCY: Each lot
6aa1ceb6-bb12-55c1-a613-441ba051b499 | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
a583bddf-71b8-54d2-afea-a49b0082b202 | note | ○ Clips shall be installed with panpuller or equivalent
1c94bbf7-46cf-53bb-b1b0-5ca2e61f1260 | note | ○All fasteners shall be sealed as per agreed method with Yarra Trams
b99f332a-cd39-51ed-8c63-de50f0b97831 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
c9448c03-05e8-59c9-b024-2cee5eb3cfb6 | note | INSPECTION/TEST METHOD: Visual Inspection
015462f1-575e-5613-8e8e-05ad8047803a | note | RECORD OF CONFORMITY: This ITP Signed Off
566cf37e-023f-54ce-91b7-a59bebb3b492 | note | WP
3fcc7eaa-9e61-568e-9bb0-7cf78131a071 | note | RESPONSIBILITY: Fulton Hogan Engineer
3c967bfa-bab3-5016-8dd7-0ec9a8d61f64 | textbox | Date Completed:
6773de23-8ab5-49c5-9631-f6899faca870 | checkpoint | 2.4 Rail end preparation
7d315609-4cd9-5fbc-84ae-90e8b5937a12 | note | FREQUENCY: Each lot
958471b6-da2a-5b1e-835f-2069edd4565c | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
876b69b0-d22b-5296-9a5d-32b477b39d37 | note | ○ Minimum closure length from proximity of welds shall be 2m
02cd4d10-de6c-5073-9731-735d93d35bc2 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
68aaa48f-ddd7-5ca8-b41c-e55fa63d3903 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
bd0d9ddb-f136-5745-8c11-8f79a54d6f7e | note | INSPECTION/TEST METHOD: Visual Inspection
845dc39a-2eed-5453-8342-d4477a0fc6eb | note | RECORD OF CONFORMITY: This ITP Signed Off
436b2f39-540c-526c-a1c6-4b00a0bed59f | note | WP
cd6901c7-5e16-5da2-b3b2-ff9d8b3dfa1a | note | RESPONSIBILITY: Fulton Hogan Engineer
9d46a68b-27d3-5c2c-985f-3f96902c7161 | textbox | Date Completed:
b4c47be1-b61c-4fe0-b56a-0acfe7d32e5b | checkpoint | 2.5 Welding of rail
2efff216-b27e-509f-87c7-4cc7f0a40f53 | note | FREQUENCY: Each lot
cd460458-e291-55e1-863c-fddf4b88fa80 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
e4c92ead-72b7-57e1-a17c-13f19914a06b | note | ○ Maximum skew at square joints shall be 65mm
e2edbfd6-d430-57d3-a5f7-dd8faf818a16 | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
2304205f-e44c-58c9-bb9f-34d5f106f8bf | note | ○ Welds shall not be within:
bc0aacfc-5004-5cfc-8ce9-f469f6b4ea20 | note | — 3m of another weld
595bcaac-99f0-575a-95db-a4baf98d56ed | note | — 3m of a rail end
c02bcaff-85c7-57ef-9864-8b742387a71d | note | — 1.5m of a glued insulation joint assembly
67f11609-771a-5a30-8496-ddc92568722d | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
a024cec0-0c0f-53a7-951b-b8f07f94d928 | note | ○ Weld Return forms shall be completed by qualified welder
4d3080d4-9a89-51d7-9c3b-e87e9205b24a | note | ○ Welds shall be grinded after 1 hour
66812e72-4a0d-5fd0-9b5f-064be6448cec | note | ○ Welds shall be free of water
d601105a-6f4b-59ba-8b65-a4d4e6dec934 | note | ○ Post grinding, welds shall be cleaned for visual inspection
4007f38c-7ca2-5ddb-ab4b-1214307c90b1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
58aef54d-6c14-58e9-8f68-69ffa7d74fd3 | note | INSPECTION/TEST METHOD: Visual Inspection
7a1b6bb1-e950-5836-863c-dcceea25965d | note | RECORD OF CONFORMITY: This ITP Signed Off
87f6b750-836d-5c46-8465-6245fa5c0da2 | note | TP
976bce30-8dd0-5964-8b76-76e7077e64f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
58f3faee-5ca5-5038-b97c-198bc113fc14 | textbox | Date Completed:
400ac366-5ac4-4102-9fae-b5be08e6a307 | checkpoint | 2.6 Grinding & cleaning welds
89d5da73-853e-5ab7-8332-1e092893af37 | note | FREQUENCY: Each lot
abade4a5-3255-5e13-ab15-67bc94a380a3 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
51dd8251-3c69-5d54-a0de-5ab27092345e | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
4d375bcf-3c29-50b8-9bc2-85fff2e05e82 | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
2e078d86-08c8-52dc-ab57-af11ab64d8a9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
306e2dfd-3349-5dfd-b81b-a488ba37274a | note | INSPECTION/TEST METHOD: Visual Inspection
23e6ee32-3cc5-5fa3-b0cb-67f588213f63 | note | RECORD OF CONFORMITY: This ITP Signed Off
3c063ff8-bc1a-5030-92ac-afebc8fbfc9b | note | IP
433bb815-972a-52b5-997c-2ad90858016f | note | RESPONSIBILITY: Fulton Hogan Engineer
fd42be1a-6960-5702-a69e-6a140c3a2590 | textbox | Date Completed:
47c209ef-aa0c-45bb-8f4f-35fc10d5f38d | checkpoint | 2.7 Track adjustment
1453fc47-512a-5cc7-ac74-9e1e42a9ead5 | note | FREQUENCY: Each lot
810e292c-525b-5ad5-bff3-6a9c5f6f99d7 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths, which shall be measured with an approved type of thermometer.
6a9798a3-b6fd-5737-b9a9-a0e5148448d5 | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
9e396fe0-2b9d-5490-8669-7d2c291335d6 | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
18a2b5eb-4e76-5e9c-98fc-804f5add1655 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
947111f5-a5bf-59bd-9f00-03409c95b8cb | note | INSPECTION/TEST METHOD: Visual Inspection
adf24cb0-c36b-56c1-9bea-88d048c0178b | note | RECORD OF CONFORMITY: This ITP Signed Off
93923b8a-d562-5e63-96d0-0a85c8d990d3 | note | IP
4de34778-96b6-55be-8b39-6967cdc7a115 | note | RESPONSIBILITY: Fulton Hogan Engineer
f74004cc-d0fb-5e32-9004-f6bdf5fb11f1 | textbox | Date Completed:
d703f74a-7b07-4f4f-91de-017f9a2d9754 | checkpoint | 2.8 Track bonds
37684e51-bbfb-5507-9345-a9f5f1cc5b07 | note | FREQUENCY: Each lot
47579734-60b6-5a81-92ea-1e065d4036b8 | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
52b7b015-fc32-50cd-975b-21a26a79f313 | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
028d31de-4c78-52c0-bb1b-caca5eeab1c8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
16b80fbc-5736-5878-94fe-4b8cf7af225b | note | INSPECTION/TEST METHOD: Inspection / Test Method
de626348-1a4a-5246-861a-94f20cc0fe2f | note | RECORD OF CONFORMITY: This ITP Signed Off
a90f4587-1ce7-5132-bbe5-66e13901968e | note | IP
54507da5-9fc2-5965-8c1f-4203b41d5660 | note | RESPONSIBILITY: Fulton Hogan Engineer
045c6d27-82c4-5fbc-b9a8-f628669eff0d | textbox | Date Completed:
62e87a24-eda5-4a1d-9fa0-553981740c2a | section | Testing
e028a8d4-a29b-4525-a4ed-d471a7fbaa44 | checkpoint | 3.1 Track testing
a969e71f-e44c-56dc-b5ee-ea15b8c919aa | note | FREQUENCY: Each weld
0d6f5b10-40da-5c3f-86ab-1f8bbb1f30ee | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
d2b5e523-592a-5134-941d-9eade4566754 | note | ○ Failed welds shall be cut out and replaced
cb2c7c4f-7bbb-5c62-8cba-f9d1a6554df6 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
5a66be1f-5758-596d-b5dc-25115dff0eb9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
27e33551-2f26-5e60-abb6-0352f99ed90c | note | INSPECTION/TEST METHOD: Inspection / Test Method
9961dc1c-9602-549a-b267-f8fb1ea7d8ea | note | RECORD OF CONFORMITY: This ITP Signed Off
9d8bb0af-0c6c-52f7-9f1f-27dda7717b0b | note | TP
ac9c4693-40a3-526c-a9fe-c01a799b5f11 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
5796cbfb-ab3f-5247-a96c-d9de61f86a3b | textbox | Date Completed:
4d6640e2-7924-4273-911f-9e54828a303f | checkpoint | Final Inspection
553cc05e-c9da-5154-98c2-c0944e64ff6b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9d2585d1-7513-50db-a1bc-dcf41565ef3c | textbox | Print Name:
8820b665-1001-52fa-8773-ed99d533f74e | textbox | Position:
e7dfd084-79ec-5332-bbe8-52b3fb1866d8 | textbox | Date:
aa431a15-15ae-473a-b4e2-9553852f0f0a | checklist | ITP-007 - Concrete Track Slab Pour Rev1 | itp | ITP-007 - Concrete Track Slab Pour
c9c38ed0-4e8d-4cf1-bf4d-5030fdf1c967 | section | Preliminary Works
839f42ea-13ea-4b8e-b691-16152b15383a | checkpoint | 1.1 Check for correct documentation
98ae07a9-b0e3-5f74-b337-bebf4b763c8a | note | FREQUENCY: Prior to commencing any activity
767faf34-07e7-5985-9d6f-4f8a022cd4ed | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f68941dc-a192-5b37-897d-4764df9f4136 | note | — using the correct and complete set of drawings
28b3975f-4e02-5f8a-97ea-d5f8c2cfc1f1 | note | — all drawings are the latest revision
dd96603b-7e83-5d6c-a029-97d296c9b713 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
14828eba-3180-52ec-8309-72413fda1015 | note | INSPECTION/TEST METHOD: Visual inspection
ed4129b0-676a-5284-b483-2cd552c92776 | note | RECORD OF CONFORMITY: This ITP signed off
45382a6f-c584-58e4-be7f-f45bba1f7f66 | note | HP*
6e36ccf4-c3a2-5dcb-b711-fddb4abdd538 | note | RESPONSIBILITY: Fulton Hogan Engineer
3f28c87e-a9d9-5a32-b825-751dbf48a0fe | textbox | Date Completed:
312735e7-c803-4509-91ab-e7dc9309d745 | checkpoint | 1.2 Submission & approval of concrete mix design prior to commencement of project
0310545f-41c8-536b-8e40-2e3659c46ce6 | note | FREQUENCY: Prior to first concrete pour
04167eff-0671-5ca3-ad2b-5c5da754ec60 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
580bc6b0-2ded-52ce-be0f-280fc2ae2138 | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
7637ba80-e27f-5a38-967c-5a21f7df05df | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
bc3916b8-a28e-5f27-a8cb-64a820004209 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
66a65dbc-d958-598f-8a3c-b85ece9fcafb | note | INSPECTION/TEST METHOD: Verify
5e1cb50a-4382-5ff2-a6af-6ef61593c10f | note | RECORD OF CONFORMITY: Mix Design ITP
ac946d9a-4287-539f-85b4-702e801e2846 | note | HP*
4262681b-877e-5510-8357-9a013182d7ef | note | RESPONSIBILITY: FH Engineer / Superintendent
a54cdb4a-16b5-585d-927e-8d810e67e129 | textbox | Date Completed:
9662dc00-c74b-4298-9fd4-5d1f04e4d13b | checkpoint | 2.1 Weather monitoring
2e2b4733-e3de-5708-b4df-268d1aae08d7 | note | FREQUENCY: Prior to start
2d692df4-9a14-5003-bc40-964f193dba99 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
1c77c87c-2749-5d53-8b60-6b2c0907e514 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
861eaf03-7570-5f30-bebc-e661ea66e2f2 | note | INSPECTION/TEST METHOD: Verify
530fe652-241c-5676-9087-f056bfe1a80f | note | RECORD OF CONFORMITY: This ITP signed off
a8393ba6-8f40-587f-b184-245d3496a22c | note | HP
1b8cb8d2-ea07-50fc-b3b2-8c63d5d5cbee | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
eb8934a6-9a27-5701-ae9d-3573ecf77aad | textbox | Date Completed:
f64055ab-a8de-4c03-85f0-f869fff20f7c | signoff | AUTHORITY HOLDPOINT
ebcc238c-b3bb-4b2f-952d-8ddd54bbdbc7 | checkpoint | 2.2 Surface preperation
fc88a271-b210-54ac-b70c-3f92c6a3ad7e | note | FREQUENCY: Prior to start
8adeb2d6-e2eb-5dae-810b-9dda86896ec7 | note | ACCEPTANCE CRITERIA: Crushed rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
61666396-e679-50d1-991f-7e16b9f12b2c | note | REFERENCE DOCUMENTS: CE-019-ST-0033
e47d11ec-b83f-5a39-8690-91be73aef88d | note | INSPECTION/TEST METHOD: Verify
35647008-2852-5462-9aef-135585b1116a | note | RECORD OF CONFORMITY: This ITP signed off
c6e18b18-57d7-5191-999f-3aed314c95a1 | note | HP*
dd3bafb7-477b-5444-a5e9-1f74945f944e | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
f563fdee-8439-59f2-854d-9a5ad632fb6d | textbox | Date Completed:
a6bd0bb0-820f-4ab3-9924-01bd38916760 | checkpoint | 2.3 Setting out
c1b1217a-f23e-5c18-b54f-300f606991f3 | note | FREQUENCY: Prior to start
6719bdf0-2a3b-5ec6-a372-f381a8924a52 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
25bdf470-293e-5874-8a9c-3cc58edb6a15 | note | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
ba0e8bc0-4448-579c-bfad-adff24367f9f | note | REFERENCE DOCUMENTS: CE-019-ST-0033
972d5904-83f9-512b-8487-d6a7f75301a9 | note | INSPECTION/TEST METHOD: Verify
950cfa6a-6460-5804-bab8-50206bdd936c | note | RECORD OF CONFORMITY: This ITP signed off
067b776b-98a0-50cc-a647-bd613c4856b7 | note | IP
ca73e5fd-9f52-52c5-bc2e-0224050b5c37 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
5b90b1ee-ecf1-516e-be16-abcb9857ad03 | textbox | Date Completed:
80ef8f45-dfa3-46b7-bf35-c38437669e28 | checkpoint | 2.4 Formwork
d8904650-5aba-5024-8912-e635d4fbbf1d | note | FREQUENCY: Prior to start
dac5595a-2f97-5816-9c35-2edab5affcee | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
d24f211f-c1a4-5286-a119-8953cc284604 | note | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
5bfb073f-7251-5c58-befd-1a8058d39e3c | note | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
ad264516-7bb0-521b-9a3e-14779365c89a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
71b1bf58-eff1-52af-bc8c-86bde0cc6854 | note | INSPECTION/TEST METHOD: Verify
7ea65d3e-d619-54d6-b0a1-e950ae9de120 | note | RECORD OF CONFORMITY: This ITP signed off
4d0a3509-f5b0-5a16-b184-4b397d7d261a | note | WP
c9fa1a2e-d9f2-5f7e-a66a-cd392abbb15b | note | RESPONSIBILITY: Fulton Hogan Engineer
06c8a8bb-b38b-520a-89dd-ae00e7c06e72 | textbox | Date Completed:
bb72f10a-d13d-4ba3-9955-ec88afd973aa | checkpoint | 2.5 Reinforcement
45e81698-3e42-5202-b771-f245e96d89f8 | note | FREQUENCY: Where Required
5e7a5e9c-5658-5185-9f57-af11014bcbe7 | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
acdf0524-2d57-52c8-a5e1-baf8c1a2aed5 | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
cee568db-1e18-542a-b3cb-9b892c2ca98b | note | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
387e57e4-4061-5cec-b60c-a69a00c75871 | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
0304298d-894c-5274-bebb-afe50533e0f4 | note | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
7bec1322-26cf-51f6-811d-1f3b5ecc51e3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
c3b81b7d-610f-5e87-b650-861787e0fa84 | note | INSPECTION/TEST METHOD: Verify
69867c71-4d4d-5c69-a78c-24ca6cad9bb4 | note | RECORD OF CONFORMITY: This ITP signed off
f12e5e27-f31e-50ce-9838-e710266362a8 | note | IP
edb59fc1-4600-556f-98ec-0d3e60072c7b | note | RESPONSIBILITY: Fulton Hogan Engineer
b0a599bc-4345-509c-9ad8-5633e5135a87 | textbox | Date Completed:
a12bc20b-04c3-406e-8c58-ad14401bf393 | checkpoint | 2.6 Dowels
338107eb-f440-5714-bcf3-d85e378220eb | note | FREQUENCY: Where Required
c2fc5fd9-b4a8-5cd9-a477-42541806f57a | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
b31237de-da56-5e85-a399-902d7b37718f | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
a013c9f7-360a-509b-a1b8-87ac156862cd | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
4fa9a816-33a1-5da0-a915-c9aa35988e33 | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
b67d22b2-411b-5b74-b68e-061c434dc46e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
d5a4c11b-1f55-5bb5-b437-7b646eab3b29 | note | INSPECTION/TEST METHOD: Verify
cde67a17-fbfb-5e45-bd08-930c7047f723 | note | RECORD OF CONFORMITY: This ITP signed off
79320b20-d20a-5b80-be9b-3bc606cd3469 | note | IP
7feed2a2-348d-5bc7-ba33-fd80d4c95943 | note | RESPONSIBILITY: Fulton Hogan Engineer
b58d4a58-2b32-516a-afee-e66683d7535e | textbox | Date Completed:
c4850e94-6353-4e1f-9b5f-57b9d8ca0f05 | checkpoint | 2.7 Pre pour inspection
da11898b-da9e-51e6-a078-c6e2ed47b092 | note | FREQUENCY: Prior to start
6ad1d72c-e970-5981-b8a3-1fbf97c9bfd4 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
109d0ce3-9926-5abc-8d79-f8e837f3cccc | note | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
557d373a-82f2-5565-bb27-da808ae1308e | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
bed66203-366e-52f2-8dd8-068e38688c40 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
69d7aa43-030d-5e39-a557-04df4922d024 | note | INSPECTION/TEST METHOD: Inspection / Test Method
e57b3145-01e5-5f6a-a705-7303fc80e338 | note | RECORD OF CONFORMITY: FH Track Inspection
901d6e2e-32b7-5667-b39a-9684b29ae5d5 | note | HP
bbead1d2-fdaf-5d53-8f05-8adfb5eff28a | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
13063cfc-eefa-5681-93bb-c45abd4b1f31 | textbox | Date Completed:
c6f07c06-71b4-41d2-8e6a-215164842188 | signoff | AUTHORITY HOLDPOINT
fe80f988-a090-4336-8383-b9af6f5ca026 | checkpoint | 2.8 Carry out sampling of concrete
c73e300f-c06f-5561-b40c-b53b219940d8 | note | FREQUENCY: Each concrete pour
11c8b079-91c0-5d47-b24c-2c7ca7f0287c | note | ACCEPTANCE CRITERIA: Slump: Concrete Slump shall be 100mm +/-20
3f0a9829-b447-55b4-b1e1-ab2e24dec81d | note | ○ Compressive Strength: Shall be measured in accordance with CE-019-ST-0033
e3eb8183-ccfb-53e6-a9af-760b82a3f576 | note | ○ Testing frquency =
8fe4dbcd-fcdd-5a94-8951-751b5d8d3407 | note | — 0-50m3, 1 sample
e5ef4d4d-2eb2-55aa-aaa6-a49c248ca1ac | note | — 50-100m3, 2 samples
5d60be05-cee6-58e2-9781-0ac661d9c10f | note | — 100m3+, 3 samples
1d1593ef-69cd-5c48-b055-b54e30d0eeed | note | ○ Each sample shall consist of 4 cylinders
0fb8d7ba-18bc-5d26-ab9e-4c131982d00d | note | ○ Test Results will be provided to the Superintendent
6e71e02c-d15c-5cfc-bdaf-0558526a5e4d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
896dbbfd-d8f9-5084-8fe4-c7518fd6673b | note | INSPECTION/TEST METHOD: Verify
6cf4ca00-385d-5837-84ae-9a4e5c8e3b31 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
b77d30a2-9be5-5ef6-80a5-d46ced16de6d | note | TP
cf8c16b2-d831-500b-8d8e-58e2b7cdaad3 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
170eaf36-2c6b-5bc2-91b0-fec37c2fcdb9 | textbox | Date Completed:
58f2cc72-5532-4d93-b35f-e426e18d56de | checkpoint | 2.9 Concrete placement
5256469d-5ded-5ecc-8340-b720b5e4dcb0 | note | FREQUENCY: Each Lot
5dac0433-465b-5221-b341-006daa3147f8 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
1648f3c1-00b3-5f9d-bb4d-dbc51a11dd64 | note | ○ Concrete shall be entirely discharged 60 minutes after batching,
d82b0c73-2526-52dc-96be-ea237613ee1c | note | ○ Ensure that pouring does not occur from a height greater than 1200mm
8081584b-81f4-5694-9a8b-66d3020cc8a3 | note | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
fb58f2f5-9d79-5aa5-8c89-a1f4a3ff6360 | note | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
d7675ecf-acbd-5bcb-94c9-951ac8bfcf21 | note | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
99939cd5-cdff-5c3f-9276-9fc7dd200431 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
cd3b7d01-f95c-5c47-b08e-96db12fed357 | note | INSPECTION/TEST METHOD: Visual Inspection
6e8ba9f8-c358-50a6-b1ed-08413b6f86bf | note | RECORD OF CONFORMITY: This ITP signed off
9b9c5abd-fc87-5307-ae4f-5c810899e2d9 | note | WP
284cc166-c29c-5515-896f-c3de8f001ddc | note | RESPONSIBILITY: Fulton Hogan Engineer
03555960-3ea7-5c79-8325-7043cdae17c3 | textbox | Date Completed:
349913f1-5768-4dbc-8be9-1fa210440ffd | checkpoint | 2.10 Compaction
4c382d39-7fc1-51e4-bc67-b2986f1458c8 | note | FREQUENCY: Each Lot
2bf17fe7-49b5-59fb-b0b0-9a47812d09a2 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
518acaf6-407b-5014-bcd1-f8dcc31ed529 | note | ○ Vibration shall take place until exposed concrete surface is free from air voids
2d15534b-9796-5d80-bdbc-c6b49b946fae | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
d2539ee1-35fa-52ef-b6fa-018c165579af | note | INSPECTION/TEST METHOD: Visual inspection
45672a62-5a38-5e87-a7a7-98a5a6fa8e54 | note | RECORD OF CONFORMITY: This ITP signed off
09859a78-c87a-5c0f-808e-796f01a4d031 | note | IP
3b2376e3-1236-5bfa-bd43-e8121a70b10f | note | RESPONSIBILITY: Fulton Hogan Engineer
0bdea186-9ebc-5c22-80b2-1f3190f9cb28 | textbox | Date Completed:
43630aec-2d61-48ad-bf3d-2e54d59bf950 | checkpoint | 2.11 Record location of each batch
442a8039-fdf5-5ee0-9cb0-3e2f3987f388 | note | FREQUENCY: Each concrete pour
c9c9104f-5b6a-5389-b63d-d4a912fadce5 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
3ef38001-1e78-5df7-a2f1-14b60d92675f | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a5c5dfb2-d348-5acd-8cf3-44ceaed24008 | note | INSPECTION/TEST METHOD: Checklist
dc6811e6-f718-5c40-b7fc-6bec873766a9 | note | RECORD OF CONFORMITY: This ITP signed off
c71478d8-ec84-53b4-acf0-45230a332d77 | note | IP
86959d0f-46d9-5492-a632-8b10bedf39f7 | note | RESPONSIBILITY: Fulton Hogan Engineer
0eff4fd1-bff2-5356-9a0d-2e5f38d4da89 | textbox | Date Completed:
0f3e3bba-7620-4239-9489-af27dbcd155d | checkpoint | 2.12 Curing
46e8d344-359c-546f-b6ed-33a939e1d6b7 | note | FREQUENCY: Each concrete pour
8322f589-7ce7-5835-8b1e-b7de956d6ef4 | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
6ad5f6dc-acc4-59f7-97f9-2323004c38a9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
d4226393-8a09-5e8f-8709-8d290ffc1712 | note | INSPECTION/TEST METHOD: Checklist
981741d7-2018-5b4e-893c-08bc7ea56535 | note | RECORD OF CONFORMITY: This ITP signed off
fad90094-40d2-5af3-836f-fa49edafc3e7 | note | IP
f713b80b-74ac-5e57-9225-6cce18d03219 | note | RESPONSIBILITY: Fulton Hogan Engineer
7df48777-889a-58fc-afac-c9a41074a328 | textbox | Date Completed:
59d0cb4c-8630-4012-9091-a3e453a82c78 | checkpoint | 2.13 Tolerances
80f0e7f1-bc31-544a-ac2a-b378054bdbea | note | FREQUENCY: Each concrete pour
2e229c81-ff79-5afa-a560-26c47544fd2b | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
7bb7caaa-af33-5b1f-b600-b9200d4eeebc | note | ○ Plan dimension of slab +10,-10mm
3f7483be-4bf4-5dbe-98fb-337378248ccd | note | ○ Thickness of slab +10,-10mm
ff08dbb7-198f-54ca-8006-1b7bfc8fa9f2 | note | ○ Cover to reinforcement +5,-3mm
6f10ecd1-e5ed-5ebd-8f9a-3a721ea329a6 | note | ○ Finished level of slab +3,-3mm
ac25381e-f384-5802-9abc-b5f58cd0cde6 | note | ○ Foundation level of slab +0,-20mm
19b649c6-60f2-5d75-b331-516f708a6f57 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
62308ab8-a862-5ded-83b1-415d7aef2ee3 | note | INSPECTION/TEST METHOD: Checklist
52993694-be67-572d-b436-847a266d08bd | note | RECORD OF CONFORMITY: This ITP signed off
93f005f0-d953-5c30-af46-6a6efe2f5608 | note | IP
9bb3977f-0a4c-55e7-85f2-4ff56a7758bb | note | RESPONSIBILITY: Fulton Hogan Engineer
1493cb37-8060-5bc3-8565-a3a00370e90e | textbox | Date Completed:
bfef2e94-4415-4438-baa3-6ada2edc992a | checkpoint | 2.14 Slab finish
8aecf005-5271-5b82-a7eb-3cf4f24be489 | note | FREQUENCY: Where appilcable - if track is Type 1 structure
20fc081e-becf-58a3-8922-8c65df8b4596 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C. The slab surfaces shall be broomed to provide a non-slip finish.
493c9954-9cd2-5ea6-ab7c-8c2aeba9bd6d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
bb86b84a-1289-5742-ab6d-87c169069a90 | note | INSPECTION/TEST METHOD: Checklist
bb557044-5b60-535b-b879-921f9e101b11 | note | RECORD OF CONFORMITY: This ITP signed off
3facc956-5f7f-5a88-80d4-1f5125de2c08 | note | IP
accfa8e0-61e9-55f0-80f2-7acb96c81ae9 | note | RESPONSIBILITY: Fulton Hogan Engineer
65e9d850-32f0-5d23-b09c-5f1478acac1e | textbox | Date Completed:
3a0b4a33-e4ae-44a2-a0d2-27a3969dcddb | checkpoint | 2.15 Post pour inspection
895d66d8-728e-5ef2-b91e-6a33ed924ddf | note | FREQUENCY: Each Lot
fa8c4e37-314f-5543-b4c8-8bd1b47c1880 | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
6766c3bb-475d-5654-8c34-83a46e00da04 | note | ○ Ensure no defects are present in slab
15b6c874-93d5-5df2-a92e-14857642106c | note | ○ Complete Fulton Hogan Post Pour Checklist
a21da81a-0f73-57d6-bac3-205d12d8fb68 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
544b8ba8-c51f-558e-ba03-becbfde6f94f | note | INSPECTION/TEST METHOD: Visual Inspection
59416a72-0fa7-5d72-be37-984a573f0f5a | note | RECORD OF CONFORMITY: Post pour checklist
d3a7b0b8-b3d7-5ffd-892f-fd81f0ff3b2b | note | IP
2edae32f-f12e-5e27-876c-5c5f989a0605 | note | RESPONSIBILITY: Fulton Hogan Engineer
97ef3eec-0d2a-5d56-996a-bb90ac11d5ce | textbox | Date Completed:
4c734e27-faa9-4547-8d46-f0310170f64b | checkpoint | Final Inspection
2a037636-72b3-5bb6-8ad8-4e8939faa63d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
44d52c2c-b66e-59c3-a750-e12bdeea779d | textbox | Print Name:
3ddd9bf2-4b29-5820-9316-859af21faa40 | textbox | Position:
eeb23e23-b081-55ec-8506-0315c10fcddd | textbox | Date:
6a2fc7db-5ba4-4857-bf0d-4f5b43ea2c29 | checklist | ITP-008 - Hot Mix Asphalt Rev0 | itp | ITP-008 - Hot Mix Asphalt
251df2ed-9b9c-42ff-9645-a78d23e70a6f | section | Construction Works
fde69d4b-2eec-4b34-9445-a60d4c040e4c | checkpoint | 1.1 Submission of Mix Design
38c08b62-467a-5711-bd86-8e197526507e | note | FREQUENCY: Prior to commencing paving
de722fc2-ab8a-5382-9bc6-1591ee048de6 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
ddf1dd18-2091-5d75-a81d-721b3042ab82 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
9692eac3-779f-5c99-805d-73fff24c8511 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
988b95dd-1690-53c2-ba8b-898549dcfe30 | note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
669793c1-81a3-5e97-adcd-a932a98e4eb2 | note | HP*
9c1eed39-c7aa-5787-9d67-b0afdfa8ace5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
bddfe6b5-461d-53ad-812c-165e4c1ff52e | textbox | Date Completed:
61b2a444-7e5a-4b75-a6aa-f7214ce61f2c | checkpoint | 1.2 Site Inspection and Base Condition
225a72cc-3026-5be6-9cf9-93f33109863e | note | FREQUENCY: Prior to commencing paving
c7a1a1e5-96f8-54f9-a8de-cb7f933cee6d | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
8314d6cc-1781-599e-8848-465978ddbe4c | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
5d9b4da6-b435-554b-b995-78318e3a380f | note | INSPECTION/TEST METHOD: Visual Inspection
9c0a37ec-95cd-5d64-8f1b-10c7551ca00a | note | RECORD OF CONFORMITY: ITP Signed
d2bc11ef-6d8e-5f0b-a45b-51fdecc1a8bd | note | WP
09634d1c-16d2-5b68-8ebb-f48701aa1cf2 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
ecb1dc57-f461-5e01-a10b-43e255ecd7c2 | textbox | Date Completed:
5816cb11-0ae1-4fd5-8885-c897c073d959 | checkpoint | 1.3 Ambient Conditions for Placing
00f040dc-790b-5c63-8dcd-800cea803ac8 | note | FREQUENCY: Prior to commencing paving
61ece293-a356-5d9e-9847-8a5acd902399 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
29e60616-7d77-52f1-90c2-abaa2383221d | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
ea96a909-86b8-5e3f-85b4-63f9bce9a1ca | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
fb81dcd1-0380-5e8a-8f23-6a293107be32 | note | REFERENCE DOCUMENTS: 407.13
6b5de756-e5c8-5fa7-9ee9-995b4866663f | note | INSPECTION/TEST METHOD: Verify
8405b0a5-ede3-5fda-8620-678009bdde1e | note | RECORD OF CONFORMITY: Thermometer
4048b854-1ab6-51cc-982f-94688caa7623 | note | IP
818f96ef-780b-505a-b09d-11b55c3b2862 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
e2afd264-3244-5eac-8493-0cf86733924c | textbox | Date Completed:
de388094-ec83-48f3-bf12-a4ef5b38a72c | checkpoint | 1.4 Planning of Joints
b26283b2-64fa-58cd-9ced-cf30b3a40ed0 | note | FREQUENCY: Prior to commencing paving
0c64bbc6-3f2e-56a0-9f19-c69118036401 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
070389e0-c52f-5d85-9439-a0c4098ebacf | note | ○ Transverse Joints Offset from layer to layer by at least 2m
25c4b750-2ac0-5ff0-9536-9dfea213c0e8 | note | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
2d3b49f6-61f0-5502-9f23-d8a24a2f5681 | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
58556417-570f-579b-8d6c-a251ae9889b1 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
2ffc2ff1-fd0f-5231-8aff-e1db2e26a286 | note | RECORD OF CONFORMITY: Paving Plan
37ffcbee-73e2-5c2a-aecd-422bbdba091a | note | WP
b0270cb9-08ba-596b-956e-138252dd2535 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
635f4f36-a25b-5cdc-8f6d-2bcb52d88d62 | textbox | Date Completed:
3d0020af-9bc9-46a4-be4c-1e699571ed13 | checkpoint | 1.5 Longitudinal Joints with existing Pavement
4dc2ba4b-5afc-5153-a42d-a4d3f289667a | note | FREQUENCY: Prior to commencing paving
aeca5d9f-2e6f-528d-b033-48131394827d | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
44f0b7c2-786f-5574-94f0-a5e9a490d940 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
81ff14b9-271c-5b3c-a0f3-e34d267c4176 | note | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
4507c1d5-bf3a-53d9-b165-5513e89116d2 | note | INSPECTION/TEST METHOD: Visual Inspection
5c2b72ae-ad7f-5ab8-9c1f-3aaa5ba350b4 | note | RECORD OF CONFORMITY: ITP Signed
2c137146-bfea-59b1-a94f-1d14432f6438 | note | WP
f897a9cc-a6a7-5af6-97b1-081db20858aa | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
258729ba-7496-53b8-b871-5b7e8fbe293d | textbox | Date Completed:
872a6bb1-2b0e-45de-bca7-e44365e6b0c6 | section | Asphalt Placement works
16ced654-f77b-4ce9-affa-a951eb90559e | checkpoint | 2.1 Tack Coat
87dc8d12-f373-54e3-99aa-72589d3898e9 | note | FREQUENCY: Prior to commencing paving
119c5bbb-d0a2-5fef-ad82-804d9a3d2e96 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen) or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b7a8d257-ee04-59cc-ac90-c1069ee70fe4 | note | REFERENCE DOCUMENTS: Vicroads Spec 407.19, AS2150 11
daed79dd-cfda-5c6e-8ae6-3a994e9b7d1c | note | INSPECTION/TEST METHOD: Visual Inspection
cfd552f5-9c02-5385-9fd2-198d07b93e92 | note | RECORD OF CONFORMITY: ITP Signed
0d89d861-09e5-5513-9b9f-ff8053cc299e | note | WP
1071d814-be45-5ee8-b2e2-4541d7e0a9af | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
19a57e4b-eb6d-560c-adc2-01e69f9dc5c3 | textbox | Date Completed:
30a1dbd7-c973-497b-a702-06219d048389 | checkpoint | 2.2 Commencement of Placing
8b9dce61-a8fa-5568-bca7-0ea91bf06b2a | note | FREQUENCY: Prior to commencing paving
ac887812-fde8-5877-83e3-abe77cc8bdcc | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
85938cf5-4ff7-5222-8f00-12a6f26b0c8b | note | REFERENCE DOCUMENTS: 407.18
6c6c361c-26ac-5dfd-8a8f-630d6a9db312 | note | INSPECTION/TEST METHOD: Visual Inspection
6bb43791-6101-54bd-b013-65d6e619cd1f | note | RECORD OF CONFORMITY: ITP Signed
2765b853-735c-52a7-a505-83d802306954 | note | HP
49bf420a-ca94-5c40-bd89-70c37ab0dc84 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
7b0a9478-ac40-5f09-be23-2a72ee396e8c | textbox | Date Completed:
effa4ade-93b8-4a36-b705-689438fb3aa4 | signoff | AUTHORITY HOLDPOINT
fb6df777-6c3a-4efa-a57c-22d398a016dc | checkpoint | 2.3 Mix design confirmation
f2c614f4-9a01-502d-8bb8-1a7fd0e1682b | note | FREQUENCY: Each lot
7c6e3a2b-61e9-5cab-a726-5b2209098650 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mixes shall be in accordance with Yarra Trams Track Structure standard drawing.
c4d8d75b-286e-5d7e-bbbb-e3320f1adfb3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06, STD_T9010 - Typical Track Structures
43ab6f90-eb3a-5fec-a1b9-3771f13393cd | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
d35ff290-a320-5470-899c-90e710d42482 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
834fde2a-501a-53e1-be95-d04ceb780947 | note | HP*
2a0244cc-9f62-55b6-9795-571e5ca61e87 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c9bf3699-6fd3-5ffb-afc0-fb034c48b656 | textbox | Date Completed:
90881f30-4e63-43b5-8783-e1f59e44470b | checkpoint | 2.4 Delivery of mix
1603cfaf-fdc8-5cae-8b88-0d27163073fd | note | FREQUENCY: Each load
8d014547-8f84-5861-82a9-158f77d1a89f | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9405f157-0691-554f-b62b-2e8f01901b9c | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
d59d3c46-e10c-5a93-980a-2b1c8746b8a2 | note | INSPECTION/TEST METHOD: Visual Inspection
4a2baaf3-03b2-51da-9d94-27e59924737e | note | RECORD OF CONFORMITY: Delivery Docket
ed962c05-5b82-50e3-96a7-bd15316be578 | note | WP
113c4b95-5cc5-5444-9b8b-44548bdc64f4 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
4d5841dc-80a6-524a-bf88-341aa778d1f0 | textbox | Date Completed:
ffc66678-9c5e-473e-85da-b22c75edb39b | checkpoint | 2.5 Traceability
8311e2b3-98fb-533d-a912-e256f49ed3e0 | note | FREQUENCY: Each lot
5024165d-842f-558c-acc6-a7276d9aab66 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
cad87559-1ea5-5ff2-89fa-b485b2f57979 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
a86af997-67ca-5ff3-b478-8afa2cffa0ce | note | INSPECTION/TEST METHOD: Verify
f70fa32c-7eaa-58de-9af9-7123280a515f | note | RECORD OF CONFORMITY: Daily Lot Record
0c6e8b1b-339a-5982-a39a-9d87e5a5b518 | note | IP
5874befd-fd76-583b-8693-7db434ee7212 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6be9d5b0-e25e-5fac-8104-0c04bfb81489 | textbox | Date Completed:
1db64ef2-b185-449b-bf5d-c5f3625be9d5 | checkpoint | 2.6 Layer thickness and level control
2c0f68d7-4c92-5a89-9224-7e337208d84c | note | FREQUENCY: Regularly during paving
ce442f55-b972-5f81-8712-6e6ce84a9592 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
6ab61bf5-5e17-55a9-834b-2a5dbf2927c0 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
ca2c62f4-d589-5420-9680-6a85605de8df | note | INSPECTION/TEST METHOD: Verify
bd85105f-02d2-5982-8f8b-30da1a45cb92 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
b337a980-f495-57a8-be6c-3ef5d7efe82f | note | WP
551cdc0c-2de3-59d9-903b-94b7e49463e0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
83557f9f-b847-589e-9e5a-c45a6f55a4bb | textbox | Date Completed:
bc7e9c0b-2e83-4f59-972c-a9914071f5df | checkpoint | 2.7 Surface finish of wearing course
89c75bfd-c4f4-5e2c-8e3b-8adfbf7fe459 | note | FREQUENCY: During paving and after final roll
aacd3d2a-a062-5e93-9511-e750dff9c942 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
6cf1c8bc-65d0-592f-8eac-98e47d66f77b | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
e9c32956-b77e-53ec-99ee-baf6feb3e2e1 | note | INSPECTION/TEST METHOD: Visual Inspection
7b5d9806-87e0-52a0-a2ea-f11b0b916047 | note | RECORD OF CONFORMITY: ITP Signed
3f702b6f-3251-5fd7-bfd6-25a5611b6404 | note | WP
cef0e37a-345c-5cf0-a5ef-729069c8145c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
24ad38bf-89f3-5eed-af36-e86e0c1cf975 | textbox | Date Completed:
eb2c0bfb-da48-43f9-af83-f5c5e1ede114 | checkpoint | 2.8 Alignment of layers not placed against concrete edge
ad3bc041-04b1-510f-8edd-83857bdd8e8b | note | FREQUENCY: During paving and at completion of work
bfd0aa38-89da-525d-8117-014fac1e1643 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
18190b8a-4ca5-5947-a505-bd7ce98662da | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
6ca372b4-46cd-5f0a-8690-50c74ec809d2 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
bd14b834-17ec-5ef5-b655-33b7e2c8b76f | note | INSPECTION/TEST METHOD: Visual Inspection
b3599a95-c555-52f8-a254-3c1b43df333f | note | RECORD OF CONFORMITY: ITP Signed
947a5ebb-8fc2-5a0d-a9bd-13b887f46b68 | note | IP
9749014d-a400-5e0a-8c43-79b0217f4b5f | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
9db8b153-06ac-5f8c-b30a-6e55ccb4e928 | textbox | Date Completed:
006726ab-57d5-4175-89cc-3a00bab846be | section | Testing
253c37b6-5343-4b9c-af17-6af1778405bb | checkpoint | 3.1 Compaction
0376006a-34b4-51ab-b3ae-3eb63a75f30f | note | FREQUENCY: Per Lot
2b291c34-4192-5fce-a2ad-28b004ecc58f | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
56c4439f-a90f-5094-b92a-908499d8d51d | note | ○ 94.0% or greater Accept lot
40e83970-3e9d-53e2-be0f-2a3ab6420b85 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate.
4cd85ccc-4243-5142-a97b-dd7ffeec4326 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
41449fc7-f983-5b42-a630-f54fbb459f35 | note | REFERENCE DOCUMENTS: Table 407.221
57d60ac9-6372-5429-9c1d-10de02e0ff7f | note | INSPECTION/TEST METHOD: Verify
f960ec6c-f6ab-594d-8759-e8273b70945b | note | RECORD OF CONFORMITY: Test Report
1970eba9-ac32-5808-94ca-39b05ec483fd | note | TP
750f2502-0f33-5b6c-be37-6e035cc52f55 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
5aff9a29-064e-5364-891c-f4507b5e89fd | textbox | Date Completed:
0a9f5fd9-0ecc-4bf4-b0c5-c891de6f39d7 | checkpoint | Final Inspection
35161440-6dc5-5f45-b09f-0a691212d753 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b13fdd17-e26c-57f1-acb3-18c14f8aa2aa | textbox | Print Name:
17bebb6d-e7e6-5c14-8bb6-0c8bcaf380b5 | textbox | Position:
70738481-5b9a-5442-b852-5ee6ea25a01e | textbox | Date:
01c7d24e-2589-4135-acab-39a7c53c17c8 | checklist | ITP-014 - Bluestone Kerb Installation (MCC) Rev0 | itp | ITP-014 - Bluestone Kerb Installation (MCC)
c1c4df48-f762-46cc-8e45-2dd5cd76fca6 | section | Preliminary Works
028881eb-f014-4304-a6d5-e4a331ff7ee8 | checkpoint | 1.1 Check for Correct Documentation
a9bb7796-92ca-5e71-9b57-bca2a55600c2 | note | FREQUENCY: Prior to Commencing Activity
8eccdbe4-48f2-5aaf-84c5-65542f72477f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
e3b96dde-9275-57aa-8b5b-d484fe4ae394 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
2979c089-8921-5285-893d-e45bc076edc4 | note | INSPECTION/TEST METHOD: Visual Inspection
7b2a4733-1623-53d8-9353-1cfa58ea06d8 | note | RECORD OF CONFORMITY: This ITP Signed off
4f6c6a03-cbd3-5d90-964c-6dd37f1d8b1f | note | HP*
de37fca4-d113-5e5e-976e-752834fd23e1 | note | RESPONSIBILITY: Fulton Hogan Engineer
e04a28b0-0f21-5185-937a-939378ec14b3 | textbox | Date Completed:
24df5e29-2872-4a5d-ad65-06669274128f | checkpoint | 1.2 Implementation of all measures and controls
6e7975a1-69f6-5571-a0e7-30f9652b9382 | note | FREQUENCY: Prior to Commencing Activity
3aae91ba-3710-583d-9b1a-a58cef914feb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
8dfcab30-586c-5599-a395-9e4537d88658 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
da123024-481c-540d-8478-b8eb49cd4504 | note | INSPECTION/TEST METHOD: Inspection
19124b6c-f255-5d7d-a410-387329256e14 | note | RECORD OF CONFORMITY: This ITP Signed off
53753dea-cb04-5e3f-a3c1-a464efd27121 | note | HP*
2b9caa6e-0b4f-5a30-8be0-5919a711efba | note | RESPONSIBILITY: Fulton Hogan Engineer
ab1e4f5d-88f4-59d3-88c3-0a433691cb80 | textbox | Date Completed:
7638ae28-d4da-4a01-a91a-94a7c5a0a6e6 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
6f480db3-993a-5a5f-9d19-7ec0bfcd4a52 | note | FREQUENCY: Each Lot
56db1bf6-2315-5d93-819a-1b32991d0c9b | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
38f2240b-05a5-5aa5-a325-a1faaa49e8a9 | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
a373a09f-e3dd-5505-8815-002b39783992 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment
9f8e3c1d-90e7-5e86-bfd0-3d03440612e5 | note | REFERENCE DOCUMENTS: Work Procedure
c10af8a9-8c4b-5582-9ac1-4ee59d10c8d8 | note | INSPECTION/TEST METHOD: Inspection
6edc8546-2bda-50e5-ab79-512ad7f2a392 | note | RECORD OF CONFORMITY: This ITP Signed off
51c77539-8970-53ac-98d2-2300c69069f6 | note | IP
dbd24bac-aa7b-5a0d-9090-b4d945dca101 | note | RESPONSIBILITY: Fulton Hogan Engineer
6eade1fd-02d0-53b1-bdcd-00d93d7cf77a | textbox | Date Completed:
bc339a79-a461-4caa-bf94-23b9d1c0dddf | checkpoint | 1.4 Setting out
5611afc9-3f15-5c24-b3a4-2b3b419b02b6 | note | FREQUENCY: Each Lot
f7d167dc-83db-50f4-817d-7656e546cb98 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
cd2ab12b-f131-5223-a68a-d1b3a97937d3 | note | ○ Alignment of new kerb shall be marked out using string line
171db9ed-735b-5915-a028-73cd4565e0fa | note | REFERENCE DOCUMENTS: Work Procedure
cd9231a8-0d91-54f9-9d9d-ee36534b473e | note | INSPECTION/TEST METHOD: Inspection
306a773b-921f-5831-9b83-da9a146f302a | note | RECORD OF CONFORMITY: This ITP Signed off
fad41a42-c5e4-5f07-a4cc-576c2af7857f | note | HP*
11b7efc3-5ea3-57b2-be79-51e0e76a1fe0 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9ee4fbe-c0f2-57b2-88aa-7369cecbab0b | textbox | Date Completed:
e67c0629-84fa-4c98-be4a-e28e1e43313d | section | Construction Works
894eb219-2166-4bc9-b2fa-622dadff6008 | checkpoint | 2.1 Saw cut (if required)
53d8110b-93a8-5ef6-972d-090ee2772516 | note | FREQUENCY: Each Lot
00741695-8e95-5ae2-a31f-8f7422254275 | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements:
8aa54cea-0620-5565-a121-61b37adfb8d6 | note | — Footpath: Minimum 75mm
96ba51d8-a56e-54fc-a206-9cb20855ea48 | note | — Roadway: Minimum 125mm
2939c0c5-6a5e-54fe-aa31-d6277f26a64d | note | ○ Excavate to allow for design heights
7a93e8da-5f94-5640-97fa-d4962451d506 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
1e76eb7f-592f-509c-987c-5693e775afd2 | note | INSPECTION/TEST METHOD: Visual Inspection
64ce21a4-0ccc-5315-ba2d-043b46d0fee6 | note | RECORD OF CONFORMITY: This ITP Signed off
d425e177-8294-5647-9b6b-d010a1be57ae | note | IP
71d16550-9717-51f7-a810-daa46fa63537 | note | RESPONSIBILITY: Fulton Hogan Engineer
7d6db488-acdf-5949-9c5d-1a3bdcedb3ab | textbox | Date Completed:
dd8ba02b-7515-45ba-b49e-7f39634c9757 | checkpoint | 2.2 Concrete Placement and Setting
d42a68c0-b5cb-50ab-a26e-558d0dd51d9e | note | FREQUENCY: Each Lot
6fe2dcaa-ff7d-5bdb-9067-8ae1984a4ef8 | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
c27cba2a-6c3c-50dc-a2c2-b175d6bf928e | note | ○ Gaps of >10-30mm< shall be provided and filled with mortar
6727d292-3dfa-58d0-b7e0-15041e337008 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
ac94fc0a-ddef-56b1-9c49-ad691efd2b3e | note | INSPECTION/TEST METHOD: Visual Inspection
3ea2ec43-5696-5834-9423-e7c72e54ae13 | note | RECORD OF CONFORMITY: This ITP Signed off
f2e7ab1a-eb41-59f7-b54e-f3e0d7a9ae8a | note | IP
af70dfa1-0892-5d8c-84d0-5515fd0cbe6f | note | RESPONSIBILITY: Fulton Hogan Engineer
2623c2b2-f903-5bba-a790-affd97b191e5 | textbox | Date Completed:
acaa495b-7f79-460d-a321-92f0b2cdeb35 | checkpoint | 2.3 Mortar Mix
f6f5fa67-1100-5de1-8dc7-7ff5c1af611a | note | FREQUENCY: Each Lot
02dac751-20c7-5aae-8e92-30f46cd740f1 | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
85de32bd-3732-5517-8bb1-e88075e13748 | note | — 16% cement
5c0c2fe8-8a19-58ea-b36a-c2cc73b5f759 | note | — 16% stonedust
2417d71c-1a81-5ee1-b3f8-b0aece25bb62 | note | — 67% blended wash sand
19502a22-dc0a-5d55-802d-7690742fc5d4 | note | — 1% lime ready mix grout
aa451bfc-379d-5a02-aced-976fa30c6ad0 | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972, CoM SD 1P 50406
d7bad48f-8fd2-56f8-93f9-085484d37cc8 | note | INSPECTION/TEST METHOD: Verify
adc66fcf-6a78-581f-8616-b34b970ef519 | note | RECORD OF CONFORMITY: This ITP Signed off
80cf2baa-c645-51c1-b12f-c95b51118b23 | note | IP
ca27eab4-01a5-5256-b04e-2d0ff0ebd788 | note | RESPONSIBILITY: Fulton Hogan Engineer
bb0862ab-578f-5b2b-937f-5e1e22218415 | textbox | Date Completed:
d53ca768-7005-472a-a282-2f253c78155b | checkpoint | Final Inspection
f2d96df8-d01c-512e-9d51-cccd8b1e3050 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
36646520-45e5-5f88-9c59-713b77e0f333 | textbox | Print Name:
14d25a64-4785-5c15-b0c8-366fbdc1125b | textbox | Position:
9f57be64-8c21-5e88-b3b3-1c40f4052185 | textbox | Date:
d344a2b8-5084-443b-94eb-b4c1fecdcd7b | checklist | ITP-015 - Sign Installation Rev1 | itp | ITP-015 - Sign Installation
98fe0ded-b0b2-4583-b743-ad2b438ef445 | section | Preliminary Works
3fea29b7-b3a1-4aeb-ae6c-daff4138e53e | checkpoint | 1.1 Check for correct documentation
0ab2a55a-190b-5f9b-a3f2-1bdd3db529f8 | note | FREQUENCY: Prior to commencing any activity
6ce858f7-e772-5a1b-b27c-8b862364a00d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
1d7c86d1-4b18-55d1-b17c-1417ab1b0a32 | note | — using the correct and complete set of drawings
d98076e9-e7ab-5afa-88ba-d5eed852c936 | note | — all drawings are the latest revision
30de7310-96f8-57e2-a4f9-53c0acdc7d93 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2165384b-332e-57aa-81b0-e6ea81b231ae | note | INSPECTION/TEST METHOD: Visual inspection
d8aac14b-4787-5bbc-8972-e31f03ea5752 | note | RECORD OF CONFORMITY: This ITP signed off
ce0b538c-72d0-592c-90ca-62f03272bb4f | note | WP
f04d3015-a716-5d8c-bff4-69c0b63bb4a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
071e54c6-04d1-5d6b-b2e6-2bdd75dc28ad | textbox | Date Completed:
3e62b637-e1ae-4757-9e39-b98a050c96e0 | checkpoint | 1.2 Implementation of all measures and controls
02c4ff47-f2db-5c67-b495-f9f0e9d3366a | note | FREQUENCY: Prior to commencing any activity
f3f6f631-3fc2-5c4e-b99e-b8708d2308bb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8ad873e8-4e42-5999-99d6-5fac2acb82fe | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3fc34b66-45ea-57e5-b798-3efc9214d73e | note | INSPECTION/TEST METHOD: Visual Inspection
63d3ab04-741d-5bb6-bdeb-5f66262bb811 | note | RECORD OF CONFORMITY: This ITP signed off
8d13b56f-544c-568b-af3a-e6bf664acaba | note | WP
75a8eeec-0217-5549-9969-4999b6e210e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
93617308-5eae-5d71-8ce7-616ffb9efa5e | textbox | Date Completed:
101158b7-b0ab-49d5-afba-d90e61a3326a | checkpoint | 1.3 Signage Conformance
d9f6eb1a-9520-5440-82a5-8bd7bfe2dbcd | note | FREQUENCY: Before commencement of activity
06e0d046-e307-5217-96be-82286968a51d | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
ec582648-3e91-59ad-aef1-dd058ee8bc48 | note | REFERENCE DOCUMENTS: Drawings AS 1742
30210bfd-2b1f-524d-b01a-0e7f391f3a12 | note | INSPECTION/TEST METHOD: Verify
1e23717e-c8aa-5969-86a5-596e930f905f | note | RECORD OF CONFORMITY: This ITP signed off
6d79482c-7c01-5571-bdd8-ee9baf0e65a1 | note | WP
1d13966e-3cf4-539a-8d64-36def92bc529 | note | RESPONSIBILITY: Fulton Hogan Engineer
b48f91e3-ea50-5f3c-b523-c585b8161afb | textbox | Date Completed:
b9a75ff4-393a-4561-a4f0-01965d1872ca | checkpoint | 1.4 Service Identification
c6b59267-8c71-5824-8426-b49cac54e82f | note | FREQUENCY: Prior to start
3bd2743e-a90c-59aa-89c1-dbadb312f763 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
825d7abe-84dc-5e62-ae71-8f7cc695a889 | note | REFERENCE DOCUMENTS: DBYD, Service chart
9811474d-10d0-54b5-ad5d-3537ca91ed6b | note | INSPECTION/TEST METHOD: Verify
b40b4cb1-a8c6-559f-b0ca-3424f6bf06c0 | note | RECORD OF CONFORMITY: This ITP signed off
8834dc0f-fd38-530d-9ed2-fa627e357a7b | note | WP
53f641ff-dca0-50d4-9a60-f8798bf08499 | note | RESPONSIBILITY: Fulton Hogan Engineer
43f45ee0-c113-5543-94d2-cbf10f0c5be8 | textbox | Date Completed:
444b3b31-664f-4dc8-8aa1-6e285cb61dac | section | Construction Works
40283d45-d9b1-4a92-a2d8-96dc8c243089 | checkpoint | 2.1 Setting Out
1ccc7ffe-1ce0-57ad-a41a-ea9aa7343704 | note | FREQUENCY: Prior to start
e4ab3524-d179-5832-851f-1f2d1b1a01b8 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
7425383f-e798-5ea4-8844-7a6e17e0c97b | note | REFERENCE DOCUMENTS: Drawings
5f7a9494-b845-5e6a-a38b-745f49673c4c | note | INSPECTION/TEST METHOD: Visual Inspection
83855724-0764-5c03-b180-3674dcc38ece | note | RECORD OF CONFORMITY: This ITP signed off
fd41de0b-2ba3-5c8f-9fd8-99bd15f3d426 | note | IP
ceb8b12c-4c29-5720-bc45-ce8e6ad87dd0 | note | RESPONSIBILITY: Fulton Hogan Engineer
3edea979-db2f-5e0b-b45e-ea11904275a3 | textbox | Date Completed:
602fe5b1-3ef2-47b9-8356-63ab6c1e1181 | checkpoint | 2.2 Post & Foundations
fc3c34b2-c8bf-5bcf-bfe1-46d74c295e57 | note | FREQUENCY: Prior to Start
53167746-26bf-589f-b0f9-5d28b1fa8d44 | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
addbd768-e884-577f-83d0-c046a219247e | note | REFERENCE DOCUMENTS: 714.06
06cba387-f843-5679-906a-5433f42c2cfe | note | INSPECTION/TEST METHOD: Visual inspection
e348dc9a-dab8-5e56-a65f-38689a69b2f6 | note | RECORD OF CONFORMITY: This ITP signed off
df44dc52-7f4e-57a5-8027-7d0bde035e5e | note | HP
e5fd33b3-7689-5f67-a0bb-9a5cc60b4c9d | note | RESPONSIBILITY: Superintendent
1a13aa0c-47fe-59d4-835b-5f8ef7d6af89 | textbox | Date Completed:
dfeb6c19-b9e8-4b6f-94a4-38baa5bd5225 | signoff | AUTHORITY HOLDPOINT
a2cdbbef-9816-4085-a6e7-56c09f138c5e | checkpoint | 2.3 Signage Install
cb697cef-0525-596c-b065-4770aa60c9e3 | note | FREQUENCY: Each Sign
4967b8c7-d671-5f2d-9e9b-d5f6c8f7398f | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
1ecb28b3-6cf0-5349-889f-72f9ea502a13 | note | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
1b7ed925-810a-59f2-b400-a4cf63ce29a2 | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
3ea463a1-f71c-5bed-8eb9-be9c19ead6a8 | note | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
13d1fb30-62d7-537c-9398-6f614cd657b8 | note | INSPECTION/TEST METHOD: Verify
c91875e9-6458-5101-9faf-dbbfbd9f8401 | note | RECORD OF CONFORMITY: This ITP signed off
c88f04a5-39c3-5329-a4ca-bcddec1d68b3 | note | WP
65492a06-8c58-5776-87ae-9778702aa7f4 | note | RESPONSIBILITY: Fulton Hogan Engineer
8072e538-92f1-5388-8580-70cdd017abb2 | textbox | Date Completed:
3983771a-d5d3-435b-b131-d54bdec0f54c | checkpoint | Final Inspection
5e85ca7e-879c-56c9-9fdf-bf571106151b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
905ee52e-6b79-5ff7-81b0-071242cd1de9 | textbox | Print Name:
97b822ab-65c1-5d97-8839-332fd4d59fd6 | textbox | Position:
7cbb447a-5aaa-548c-989e-bc7569ceb7b1 | textbox | Date:
12e3c3a3-ec10-47d0-94be-d6bd871b8197 | checklist | ITP-016 - Platform Bluestone Installation Rev0 | itp | ITP-016 - Platform Bluestone Installation
19664752-edbb-4e74-8513-a632a2ea4c23 | section | Preliminary Works
a067d37b-718f-44b0-a340-658e2ce9ea07 | checkpoint | 1.1 Check for Correct Documentation
aa6d3130-6f64-5587-bb39-fa271c837b4d | note | FREQUENCY: Prior to Commencing Activity
8153e7b8-0e1f-506c-bf10-0c6ed54e1776 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
ffa492a0-05c3-5d62-ae83-aa57bb1dc482 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
73b1f33d-389f-5fd4-b38a-cccd97023b51 | note | INSPECTION/TEST METHOD: Visual Inspection
6c65030c-aa21-5ede-a857-371f7d6fbff8 | note | RECORD OF CONFORMITY: This ITP Signed off
ea2fa670-ccdd-54fe-8a94-33a83f5fdccf | note | HP*
135655b8-6285-585f-8241-9ea088c33acf | note | RESPONSIBILITY: Fulton Hogan Engineer
3a50c677-494c-5e8f-9cec-699c948cb4fc | textbox | Date Completed:
a60bd2ca-c463-47b5-8ced-882bdcec9ede | checkpoint | 1.2 Implementation of all measures and controls
a99286af-1936-57a8-843e-58718b4e6fee | note | FREQUENCY: Prior to Commencing Activity
8508b0ef-0681-5fae-85f3-b0adb85b0d75 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
2aaadacc-bf95-50cc-a0b6-b4c2d2c00d5d | note | REFERENCE DOCUMENTS: Work Procedure
9e229759-1739-5707-9bbf-da03ef5bee0d | note | INSPECTION/TEST METHOD: Inspection
3d127233-5e05-579b-9f44-c28960651e23 | note | RECORD OF CONFORMITY: This ITP Signed off
8dffcd64-2513-52f3-80e2-282781bcbe37 | note | HP*
afe68237-c9b1-5614-86d5-7bf76cbbb89d | note | RESPONSIBILITY: Fulton Hogan Engineer
57f882e7-d0f5-5917-95e2-4418f1e8320b | textbox | Date Completed:
912e0039-4ae3-47aa-862d-524d13be55ba | checkpoint | 1.3 Check Condition of Material
952abfcd-05bd-50b9-8a10-00dc107f16ac | note | FREQUENCY: Prior to Commencing Activity
67f25cff-86a3-5e6a-84b8-86e15fb28528 | note | ACCEPTANCE CRITERIA: •All bluestones shall be inspected at delivery for visible damage
a41fb285-cb21-5dc9-b9d1-7348af26bde5 | note | REFERENCE DOCUMENTS: Work Procedure
1781445e-fb1c-5306-8fc8-044e734b6904 | note | INSPECTION/TEST METHOD: Inspection
66013cee-e66c-5aa4-9f8e-8a38f0a03941 | note | RECORD OF CONFORMITY: This ITP Signed off
4f843b8a-c753-55dc-a338-148857f4cd8c | note | HP*
e5a9c97b-81fb-584f-a374-47e76928c3f6 | note | RESPONSIBILITY: Fulton Hogan Engineer
479ea21c-3e9f-592d-a1ce-f061f165a515 | textbox | Date Completed:
731230ab-cf42-4f3b-ac53-653ba8e94e70 | checkpoint | 1.4 Lifting method
5048c1a9-0751-57d5-8e58-3422d9bfda6f | note | FREQUENCY: Prior to Commencing Activity
d61c5f8a-4ae7-5786-83cc-f83072b14ff4 | note | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
932363db-f43d-561b-9ffb-5d868faebe11 | note | REFERENCE DOCUMENTS: Work Procedure
6e5774b9-ef32-5614-b923-06e4dd61a8bd | note | INSPECTION/TEST METHOD: Inspection
4e81da26-292e-5004-addd-673b64242d48 | note | RECORD OF CONFORMITY: This ITP Signed off
8a96ae33-a89c-5045-be35-432bce70aebf | note | HP*
3f06bdf8-0cab-5fac-8432-9f1b06d3806c | note | RESPONSIBILITY: Fulton Hogan Engineer
ff21d8de-1802-5acf-ad1d-a98767551ed6 | textbox | Date Completed:
f85ff092-98a7-4a3b-9d8a-95e90cc939b5 | section | Construction Works
517bdfd5-8f6d-44c3-a582-c571af811f87 | checkpoint | 2.1 Base Course
dc58ab8c-838c-5be2-aa9c-93b00ff2917b | note | FREQUENCY: Each Lot
fab74217-7e7a-51b3-b0c8-e311fee8f215 | note | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to min 100mm thickness.
5208e68f-a8a5-5f31-b039-1d3a88b78639 | note | ○ Soft or areas deemed unsatisfactory shall be removed and rectified
b5da48d4-108a-5212-8e8a-b6f444b88309 | note | REFERENCE DOCUMENTS: STD_T6111
082e966d-029f-5d86-b4b9-ed19e1d9a59d | note | INSPECTION/TEST METHOD: Visual Inspection
4940cfed-0315-5dfb-8770-ec91578452af | note | RECORD OF CONFORMITY: This ITP Signed off
d78ba0c1-6918-53a4-a05c-8b0852a5ac5c | note | IP
45f5b830-95ad-5cd2-831a-02c2a48b84bb | note | RESPONSIBILITY: Fulton Hogan Engineer
6cb2d4ba-286a-5adb-8309-bbc0f2868c34 | textbox | Date Completed:
57bb3c3f-8794-440c-99af-0da8c868bd48 | checkpoint | 2.2 Concrete Placement
5da46d23-e7d7-5b96-b8be-279bf0647651 | note | FREQUENCY: Each Lot
18aecf91-d6d3-53a8-98fe-6c2fef58c934 | note | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate. To match the blinding layer of the edge beam
2c5a0929-302a-53f5-8715-3d60e7599a69 | note | REFERENCE DOCUMENTS: STD_T6111
ca9d779d-87af-510d-88c7-41356411c9f5 | note | INSPECTION/TEST METHOD: Visual Inspection
516f0ed5-95d9-5598-b2f9-b29c41a7b1b7 | note | RECORD OF CONFORMITY: This ITP Signed off
e7b02b9b-d514-597c-9cbc-6a46ad455f42 | note | WP
ff742359-6aba-520b-930c-9ddcd1b59fdd | note | RESPONSIBILITY: Fulton Hogan Engineer
da8d2ea8-eeda-5d1b-8239-c336ba5e850d | textbox | Date Completed:
e51dce3b-e70e-49ef-b0b2-db0746a8b87c | checkpoint | 2.3 Setting
ed06ae46-494a-53ac-b516-adae1007ba02 | note | FREQUENCY: Each Lot
427171c0-1489-52e6-b001-9bb1ede1e334 | note | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone
7d5b9663-c030-5ff0-ba48-c26ec265d5b6 | note | ○ Tie rods shall be installed with bond breaking compound specified by superintendent
b508e620-f9d1-58af-b569-a0fc3eafc5dd | note | ○ Bluestone shall be laid 150mm below finished surface level
e0221c15-f383-5c0d-a77f-5290005537c1 | note | REFERENCE DOCUMENTS: STD_T6111
9f93d94c-2aad-587f-b49a-d5bf23a3111d | note | INSPECTION/TEST METHOD: Visual Inspection
fe6aa346-1d8e-51b2-b8e6-76487fe5fc33 | note | RECORD OF CONFORMITY: This ITP Signed off
bb776e36-047c-518c-a7d0-4810821a44ad | note | WP
438b5449-7d8c-5de6-bc11-292c7fb447a3 | note | RESPONSIBILITY: Fulton Hogan Engineer
08d9951f-4b8f-5ff6-bffc-9036697ee295 | textbox | Date Completed:
26e7fb74-5f80-41b4-be2b-4e75d1f9ba69 | checkpoint | 2.4 Sealant
f4d93e9d-8153-5a65-adc7-0d9a8b40b546 | note | FREQUENCY: Each Lot
c3e01325-d533-5575-95de-8fb72ed21103 | note | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour
a62e4264-b05b-5f9c-93fd-ed41ea94afdf | note | ○ Loose materials shall be removed as not to impair adhesions
d1776327-4fab-5609-b160-af1cc2be7cac | note | REFERENCE DOCUMENTS: Work Procedure
b1e660a0-9a3e-56fe-bb3d-0b8f4855c890 | note | INSPECTION/TEST METHOD: Visual Inspection
ea3b39f6-0a68-5117-a912-878abbff3d95 | note | RECORD OF CONFORMITY: This ITP Signed off
13e76c9f-57a5-5d5a-a067-de695ee6e407 | note | WP
873b2a23-35df-55c2-b905-56e0827a375b | note | RESPONSIBILITY: Fulton Hogan Engineer
97db386a-abad-5d2a-b1c1-50efde1be485 | textbox | Date Completed:
3c0d97ab-75e4-4eb0-a276-a65fd0919b63 | checkpoint | 2.5 Platform line marking
ea7f1770-825e-530b-84b5-d926196f18ec | note | FREQUENCY: Each Lot
b5c105d2-4669-5c28-b44c-64f0c5ed03a2 | note | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
a3f815a3-e826-5df2-9d6a-7675beb5cd02 | note | REFERENCE DOCUMENTS: YT Construction Standard
a10cf6d7-3d3a-5dfb-8b95-de95cd85be3d | note | INSPECTION/TEST METHOD: Visual Inspection
abc207ca-48b1-5474-8050-7b92045fb6be | note | RECORD OF CONFORMITY: This ITP Signed off
cdcdcab7-3d6d-5753-9b43-bdf7b192e50d | note | WP
9b2a18f1-bda7-58fe-ba1c-74aba028804e | note | RESPONSIBILITY: Fulton Hogan Engineer
3e385f38-b1c1-5023-9829-2a758093d6cd | textbox | Date Completed:
45fd59a5-90cc-41b7-9775-d0c2b8c342d4 | checkpoint | Final Inspection
fbf85662-1a25-5a18-a706-d8c5421cffa6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
61e62fd7-8022-55fc-b6dc-525696eb2479 | textbox | Print Name:
e64bb99c-0fa8-501a-af87-da6f62204f4c | textbox | Position:
4ba89352-5a26-5d03-b2f0-3f780dcfd96b | textbox | Date:
52263389-394f-4307-8d73-ee0e0d106fdb | checklist | ITP-018 - Energy Absorbing Bollards Rev0 | itp | ITP-018 - Energy Absorbing Bollards
b5487692-f5ba-434c-8ea8-1a7d2c50e9a0 | section | Preliminary Works
598b58da-25d9-43ba-84db-e0d4776d436b | checkpoint | 1.1 Check for correct documentation
b3b5b3a0-9935-5255-b11e-7d2608435c35 | note | FREQUENCY: Prior to Commenciing any Activity
8e44dfae-9704-560e-9220-3aa2958629a9 | note | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
bb8e15eb-e41b-5fdd-b590-b0ca8b6216dc | note | REFERENCE DOCUMENTS: Design Drawings and Register
e4d8a095-171f-5584-9347-9a10c80f79fb | note | INSPECTION/TEST METHOD: Visual Inspection
6974d1a6-50fe-5685-83db-c0390cca98d7 | note | RECORD OF CONFORMITY: This ITP signed off
1a59f014-636f-52a3-bb98-88b8570bcd4f | note | HP*
55f836d4-cbe0-53ee-9fd0-e352d72e3c64 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c58f55e-54cf-559a-a873-13361849ec38 | textbox | Date Completed:
45501fbc-f90b-42d0-a1c1-c750012078d7 | checkpoint | 1.2 Implementation of all measures and controls
659f25a0-fda2-57af-9a50-01b8dc5e96b1 | note | FREQUENCY: Prior to Commenciing any Activity
dbd57120-bd1b-5406-bde5-e6a81327083e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
d7d94b24-290e-5b64-b9a9-9cadd3f7827b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
33ff6673-1773-5875-88a2-9581e3beab2e | note | INSPECTION/TEST METHOD: Visual Inspection
76e9a292-f1e5-546b-9177-b0bc12d29803 | note | RECORD OF CONFORMITY: This ITP signed off
8588a3df-490c-5d45-8f25-49a1b80ce918 | note | IP
a065bc27-81a4-58a1-a2bb-e8611ebb5fb2 | note | RESPONSIBILITY: Fulton Hogan Engineer
5afdc9d4-74f6-575e-b90d-6d53129ea80c | textbox | Date Completed:
209cab30-74d0-41bf-995d-3fdf2ecb70a2 | checkpoint | 1.3 Service proving
19321684-05e5-5f72-880b-92b36bef828c | note | FREQUENCY: Prior to Commenciing any Activity
8429f18e-547c-58a0-a937-41b949deaa6a | note | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
59bc4b5e-e720-525c-9d53-14afdba211a3 | note | REFERENCE DOCUMENTS: DBYD Service Locator, Service Chart
1eef8f89-6790-544f-872a-63e3abde8171 | note | INSPECTION/TEST METHOD: Verify
93a482b9-e26c-5213-a61c-5c2b6b6b9dd8 | note | RECORD OF CONFORMITY: This ITP signed off
df30d856-bb8f-5298-a7b5-4d6150108d30 | note | HP*
e2853ebc-f549-5019-b704-1e2a9c6496f1 | note | RESPONSIBILITY: Fulton Hogan Engineer
bdc0dfc9-b638-52dd-8d75-46f38d2fbd31 | textbox | Date Completed:
19cd95ef-7839-4eb8-814d-412985e59a00 | checkpoint | 1.4 Excavation permit
1de06a5d-1817-5066-a7a6-6dc1a3a9c91d | note | FREQUENCY: Prior to Commenciing any Activity
0de308ae-f7bc-5a17-aab7-1cdf5a52bfb8 | note | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
9760afc2-9a4a-5298-bd57-8b3f24b9d31b | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
becd8ab5-5f5b-5e1c-b773-973a2a95b49a | note | INSPECTION/TEST METHOD: Visual Inspection
984220a6-52d4-51b0-b925-b72e35607c39 | note | RECORD OF CONFORMITY: This ITP signed off
802d7810-de22-5e44-b470-d410402faa94 | note | HP*
4fb1086c-d47d-5fba-a829-b5f35e12e026 | note | RESPONSIBILITY: Fulton Hogan Engineer
d2b26659-90e8-5ef6-9245-85c68bf2db7d | textbox | Date Completed:
601d15b5-258d-4749-951b-9002391e129f | checkpoint | 1.5 Materials
9bc6a8df-6480-549f-b80b-0e624cc8d4c1 | note | FREQUENCY: Prior to Commenciing any Activity
647bc0eb-9ed0-5e45-b889-2c4563cab310 | note | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification
5bf3d765-eb2f-5a33-9203-0f3cf06c799b | note | ○ Ensure materials are not damaged
ac8c5049-5b42-5c5e-8f50-4d65dd778cc7 | note | REFERENCE DOCUMENTS: ASE TS
28d3d105-0fe7-5333-ab76-060eede8eed4 | note | INSPECTION/TEST METHOD: Verify
90a6066a-af72-588a-9313-2680810cf71a | note | RECORD OF CONFORMITY: This ITP signed off
ca558482-f1d5-5c35-a8c9-18759e644e86 | note | IP
2827478a-afe9-510d-8906-4ccd1784e3dd | note | RESPONSIBILITY: Fulton Hogan Engineer
b865f1a6-a7d3-5e23-aeaa-c7dfb1282fe2 | textbox | Date Completed:
8747ff35-0fc4-435b-a9dd-0c706eac5269 | checkpoint | 1.6 Setting out
dbf8ca3d-c88c-5220-a2ac-58203999b272 | note | FREQUENCY: Prior to Commenciing any Activity
db2ce086-4e93-5f1e-8e58-f642e6356b45 | note | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings
cc262df0-7d2b-5ed5-981b-97a3629d6d49 | note | ○ Mark hole centre position at location
7e5f82d0-a5ce-513b-a116-e1ce9fdbdde2 | note | REFERENCE DOCUMENTS: ASE TS cl1.1
752a7be6-1cb2-511a-b8e5-b3daa98391aa | note | INSPECTION/TEST METHOD: Visual Inspection
e03d94a2-8eae-5fd2-b925-438e62b55b49 | note | RECORD OF CONFORMITY: This ITP signed off
c2d08b05-d825-5304-a8e2-4b4298604d16 | note | WP
a2fec264-3782-5c30-a3dc-82bceadccfd8 | note | RESPONSIBILITY: Fulton Hogan Engineer
51fc1c5e-0e28-5899-bbda-b575d575bd3b | textbox | Date Completed:
b048c0df-aaee-41fe-89d1-3758e26f02a1 | section | Construction Works
4a4b0c3e-c02c-453a-a93f-37028081bf08 | checkpoint | 2.1 Excavation
a2ed8ad4-e00d-58f8-bede-9fa3ee0db35a | note | FREQUENCY: Each lot
a671c2a0-3e67-5bdc-bdcf-8222488c6de4 | note | ACCEPTANCE CRITERIA: Care shall be taken in excavation
82be7372-8f7b-59ab-b0c0-3ccdccd761cb | note | ○ Hole shall be minimum 600mm dia and 1000mm in depth
80564e9f-b47a-55a0-b044-832dd2b4b277 | note | REFERENCE DOCUMENTS: ASE TS 2.2
1b792fbb-8a55-5bc6-bae4-c9a6b53a3bfa | note | INSPECTION/TEST METHOD: Visual Inspection
e08b9b73-7254-5334-b504-455511b9e898 | note | RECORD OF CONFORMITY: This ITP signed off
fadd42bf-1bd5-5638-8653-928765ff4bc3 | note | IP
11fd2bc4-21a2-5f98-b8d0-38a2f01c31c7 | note | RESPONSIBILITY: Fulton Hogan Engineer
7ec5eaed-6023-5d02-b33b-9e9810e05323 | textbox | Date Completed:
dd127e86-5762-48ca-9464-89ced62be9ab | checkpoint | 2.2 Base preparation
dfda5bf9-2af0-5ee4-bbff-88e6a0be3beb | note | FREQUENCY: Each lot
ac9cb9bd-c1e9-53f9-9d3d-aebb5196b0ab | note | ACCEPTANCE CRITERIA: Ensure base is supported by solid ground, and block is level
d2f87251-481d-5f58-87dd-94b2a8f26e87 | note | REFERENCE DOCUMENTS: ASE TS 3.1
afb538b8-99c3-59a9-8fd5-1d18ee5eba73 | note | INSPECTION/TEST METHOD: Visual Inspection
b218bfea-3c1b-543f-9982-f7e46a3f1555 | note | RECORD OF CONFORMITY: This ITP signed off
5d7d7cc4-304e-5687-8e09-47d553c9f6fc | note | WP
4fc66742-d8b0-5b62-8489-06c6114b73b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
06eca031-56bf-5596-a7b9-185eb9b737e3 | textbox | Date Completed:
fd358501-46ab-4575-a8c5-c5fdc11d779d | checkpoint | 2.3 Installation of reo cage
7468181e-d0bf-5325-b770-e822e61248ef | note | FREQUENCY: Each lot
43dfa01f-be78-5b5c-9a6f-1bbaf95d3adb | note | ACCEPTANCE CRITERIA: EAB cage shall be placed level
d5522a1f-e884-5b98-8a95-02d373d8a7ed | note | REFERENCE DOCUMENTS: ASE TS 4.1
f3a03c81-5785-5f49-96d2-3e2a4538840f | note | INSPECTION/TEST METHOD: Visual Inspection
00492829-c4c1-57d0-b29e-857dc8ba569c | note | RECORD OF CONFORMITY: This ITP signed off
5ae52f69-2e59-59e3-9feb-67c8e2c737b7 | note | WP
0fc37a7c-d5ac-59b8-8f5f-c7531a85dbee | note | RESPONSIBILITY: Fulton Hogan Engineer
ab99f1dd-5dcd-5c62-9fe2-98829a758139 | textbox | Date Completed:
5e0b64c6-82e9-49b7-a03c-c105fac26203 | checkpoint | 2.4 Pre pour checklist
c8cf4ed3-a95e-59ee-9adc-d6adc8ecfd8e | note | FREQUENCY: Each lot
ef35a804-74a4-5b68-804f-5b6f597771a6 | note | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
514c94ac-8ec3-5ff3-8483-8e8ee4c2e69e | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
d2223589-ef53-562d-87a6-ea2b06837e8d | note | INSPECTION/TEST METHOD: Verify
539c2f6a-7087-5ab5-a230-5c810b30ec5e | note | RECORD OF CONFORMITY: This ITP signed off
182ddc71-0d47-5290-b202-c4d144dd6d24 | note | IP
e1d24bd6-0e17-5627-9a86-ec9d87373342 | note | RESPONSIBILITY: Fulton Hogan Engineer
fe1923c6-09dc-56fb-b1b3-8f24480555c3 | textbox | Date Completed:
5c86b8e7-5328-4398-b4b2-324415936c7e | checkpoint | 2.5 Concrete placement
c22e670a-0fc3-549a-8cfd-f00ca100b971 | note | FREQUENCY: Each lot
fcd1cd35-0636-525e-bd7b-f5af7a88ad49 | note | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cage and fill hole
2b7b6e0c-bb64-5ac0-8c4c-481e5f28fb48 | note | ○ Concrete shall be compacted by use of vibrator
8db88518-7286-5f4c-a5f5-f01bcaea2b2a | note | ○ If surface pavers are to be used, allow 25mm gap from finished surface
6061ca91-5f7f-5620-bcea-aefc17331033 | note | ○ Ensure reo cage is level post compaction
5ae7bc07-206a-5466-a238-57b4481a9419 | note | REFERENCE DOCUMENTS: ASE TS 4.2
39a7ba3f-7bf4-5bfb-8942-85e156aa14fb | note | INSPECTION/TEST METHOD: Visual Inspection
f77c3772-cf40-5e41-8feb-f776a2e502a4 | note | RECORD OF CONFORMITY: This ITP signed off
3c54aa44-089b-59e2-beab-77431bd18ecc | note | IP
b8498ea3-def1-5a86-b0b9-028757cf1947 | note | RESPONSIBILITY: Fulton Hogan Engineer
e937491c-ad21-5e70-98b8-70525a13a44f | textbox | Date Completed:
8f38bb39-565e-4d26-ab05-9fabb44fd409 | checkpoint | 2.6 Installation of Bollard
c15e40fa-79dc-5dab-8645-e7f4822e915e | note | FREQUENCY: Each lot
54f64929-298a-560c-868c-25cc0eefee3d | note | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately if required
e51a6154-fd7a-5a8d-93a6-c095d612f916 | note | ○ Concrete, pavers or bitumen shall be finished to specified requirements
98d205de-459d-557b-aa91-67b9ab91f8cd | note | REFERENCE DOCUMENTS: ASE TS 5.2
bed451c3-09e3-529c-874c-415ff7932917 | note | INSPECTION/TEST METHOD: Verify
aae5d3ee-0f57-5b19-9d5c-5177c95aa074 | note | RECORD OF CONFORMITY: This ITP signed off
e9689c2b-2202-5596-96d5-c4982fbaecdc | note | IP
0afd9ef3-580a-5a1a-92e1-f85619b09fe4 | note | RESPONSIBILITY: Fulton Hogan Engineer
44650c28-0e27-5b48-9e88-66c5f34c1dc4 | textbox | Date Completed:
cdd4ba35-cf68-4dca-a861-9cc1055e527a | checkpoint | Final Inspection
d690aaf3-4406-589b-afb8-0ab6eda4c0f5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
89ce8b63-534c-504f-859f-43d7be35ace5 | textbox | Print Name:
9a3a8800-f5a0-5d73-8025-00435d776dda | textbox | Position:
f5abb843-4e0b-5db4-89e9-362a3e5b7a44 | textbox | Date:
300f4845-7445-4e52-a533-0f748eb008e1 | checklist | ITP-019 - Fencing Installation Rev0 | itp | ITP-019 - Fencing Installation
098a04a9-cc5d-4bea-bc3d-b509c93d4f58 | section | Preliminary Works
bb2a81bf-3b5e-4121-b838-0350fc43baa4 | checkpoint | 1.1 Check for correct documentation
83c78b77-3453-5de7-940d-629dce4376ee | note | FREQUENCY: Prior to commencing any activity
9dbb48e7-8c3b-5418-9974-c92d4c8af6c9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
61e826a8-b09f-5633-a115-b4b3351df9c7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
30576ab4-17f3-5a96-8250-143360e710d9 | note | INSPECTION/TEST METHOD: Visual inspection
2f335d51-ad48-5774-a595-2819f3f27bf9 | note | RECORD OF CONFORMITY: This ITP signed off
94d0dd29-a77e-5026-9f5c-2cf62c5b2487 | note | HP*
8538c679-2246-52e3-8d39-e54376fcec26 | note | RESPONSIBILITY: Fulton Hogan Engineer
9fb26043-3fe5-5641-9f71-2c9589aa7830 | textbox | Date Completed:
7d80a72e-f52a-41fc-bec4-9c37e10081bf | checkpoint | 1.2 Implementation of all measures and controls
a650b247-a3c4-56a0-9726-78e6a4148a55 | note | FREQUENCY: Prior to commencing any activity
e34042b8-db1f-5977-8daf-f7160e71e817 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
130c069e-33b0-5681-a316-70bb870945e5 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
f91427ef-8dad-50d1-a004-2dad3e029f94 | note | INSPECTION/TEST METHOD: Visual Inspection
4261869b-0580-5313-ad13-4202f592d14c | note | RECORD OF CONFORMITY: This ITP signed off
d4e0e859-bcfc-5e0c-9603-0e7210ed6666 | note | HP*
27b5d781-3aec-5f1d-a16c-604d25b1aed3 | note | RESPONSIBILITY: Fulton Hogan Engineer
016c7d4f-65ca-5491-b857-5110c875c4b9 | textbox | Date Completed:
9dad9485-43ac-48ed-9052-12d234bb16f3 | checkpoint | 1.3 Check Materials
d3c76741-b519-5b74-8764-f44ed6a5252c | note | FREQUENCY: Prior to commencing any activity
a5af9122-81e8-56ff-ac49-ece116465ef1 | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished
97f97f5e-2b07-5a31-8dde-ecafcd232c83 | note | ○ Welding shall be in accordance with AS1554
66cbd277-a50c-58ea-ba5f-fe4b4a3fc1f4 | note | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
044a9612-9017-545e-96b8-9ccafe3e5018 | note | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
c898cdb3-7c82-59d1-85ad-2fdadc8eb4f4 | note | INSPECTION/TEST METHOD: Verify
18f0b3db-8fd5-58c8-a84c-945f5b686717 | note | RECORD OF CONFORMITY: This ITP signed off
73df81f9-4070-57cb-b6bb-3208d619733c | note | HP*
76e51076-ae7b-5628-9222-03f931b29dd3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6a531156-0e40-53ee-ade5-fbc6acea3d27 | textbox | Date Completed:
731faf05-8ac9-4ad4-b3c5-455f0234d7a5 | checkpoint | 1.4 Confirm Footings position
f77e89b4-7219-5909-b44a-05570d2d7512 | note | FREQUENCY: Prior to commencing any activity
55bb566c-eda0-5398-a06c-4099ded63d78 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
323af3de-c87d-5dc2-9472-0174bf4845bc | note | REFERENCE DOCUMENTS: Construction Drawings
04afa120-56b6-52ae-9b4a-e2b344f72807 | note | INSPECTION/TEST METHOD: Verify
63072cd0-24e1-5671-b2c6-0c6bd15a5ca6 | note | RECORD OF CONFORMITY: This ITP signed off
ba000b7b-6eb7-5c2d-be42-23092abbfb8f | note | HP*
16c37864-4529-57f8-a061-d4bb198b7663 | note | RESPONSIBILITY: Fulton Hogan Engineer
dccc2a4f-45b3-5e8e-929f-3f4d09e32447 | textbox | Date Completed:
4ef7576a-0f14-4cf5-8e2f-6a1997c228ff | checkpoint | 1.5 Bonds
a15cf881-156d-578d-9aff-3b71ab5ab210 | note | FREQUENCY: Prior to commencing any activity
5bbdde1d-ca7a-5a91-ad04-27d4f9737c0a | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation.
69c190c6-92fd-5eca-afd0-ce5e3e8d0128 | note | ○ Lug shall be fitted to baseplate at specified fencing location
5f8acf2c-262e-5507-8e77-30c249936756 | note | REFERENCE DOCUMENTS: STD_T6000
13d2c357-6561-51f7-a2b2-2e10d74aae04 | note | INSPECTION/TEST METHOD: Verify
f39fc6b2-9fcd-59b6-84e8-a066c10b8532 | note | RECORD OF CONFORMITY: This ITP signed off
655971fd-0d62-50a7-855e-beea98099e9d | note | HP*
e4aa838c-2b5e-5b8e-b165-484ac79919a7 | note | RESPONSIBILITY: Fulton Hogan Engineer
bcc0e064-59cb-5e5a-839c-f37b10f689d2 | textbox | Date Completed:
08c4ab0d-8f53-438b-9625-071e380e0e6f | section | Construction Works
31ff9ffa-1b47-4f20-8f16-75bb179d6349 | checkpoint | 2.1 Footing Installation
b0cacc02-7554-5ea0-8fb6-f54d01fad0e0 | note | FREQUENCY: Prior to Asphalt
ea68c376-28a4-5ed4-859d-4eea3f6bb2da | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
ff7640e3-a443-586e-a836-fe16e61c22fa | note | ○ 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
f49cca0c-6fb7-55ae-b081-2f6435b14881 | note | REFERENCE DOCUMENTS: STD_T6002
a8294f48-e4be-52b7-9ce9-a28b5aa4535e | note | INSPECTION/TEST METHOD: Verify
37b03e25-cc4c-5023-ba9b-29de9d893879 | note | RECORD OF CONFORMITY: This ITP signed off
2b45a48d-1616-51d1-9dc0-e27a9675dfd1 | note | IP
182692f5-2ec2-5e9a-86d1-b4bc5bf24039 | note | RESPONSIBILITY: Fulton Hogan Engineer
2c4a1f67-cc94-51e3-b970-a72bd3ef9d68 | textbox | Date Completed:
4ef8c849-566f-4cf9-b21a-9e96eb0eb3f2 | checkpoint | 2.2 Post Installation
356bf877-00f4-5a8d-8ee3-309449ccb3c1 | note | FREQUENCY: Each Lot
7a458ec3-7482-56d7-a973-c2e727491210 | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level
0a1f8752-ae02-5ea8-8553-6999492a27a7 | note | ○ Installed to footings with bolt assembly
7adaff87-36fc-5c60-808e-6cfd9026645c | note | ○ All bolts shall be insulated from base plates, using non metallic sleeves and washers
a17b9349-9d7f-59ae-8062-647b0035b94b | note | ○ The top of fence base plate shall be level with surrounding pavement
bdf5ef15-025a-5b57-ab97-7e4a2ca548d8 | note | REFERENCE DOCUMENTS: STD_T6002
a2770467-b99d-52b0-b860-888abeef0bd4 | note | INSPECTION/TEST METHOD: Verify
4aa13939-8061-53b4-acce-7acbd82cf681 | note | RECORD OF CONFORMITY: This ITP signed off
751fd8ee-4273-5712-9ca4-3e0cd33ff67a | note | IP
bce6b233-4797-5eb3-91a3-e5c10af85b35 | note | RESPONSIBILITY: Fulton Hogan Engineer
667e3a18-3086-5404-a513-86ef52b2a43a | textbox | Date Completed:
7f164db1-9ed0-4dcb-a9db-c580bb09774d | checkpoint | 2.3 Grout Installation
1228608c-004f-586c-bfaf-6c11140a6acc | note | FREQUENCY: Each Lot
ae5b39db-7dbc-5318-b5e0-b88a100e50f4 | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application
c473fddf-7604-590b-bac2-b3fda7137fcb | note | ○ 50mm of Non shrink dry pack grout shall be placed under base plate
eb081fe0-876e-5209-a1a2-0aaebfe427bc | note | REFERENCE DOCUMENTS: STD_T6002
53b443d2-4668-58d2-8daf-139ba0dae90d | note | INSPECTION/TEST METHOD: Visual inspection
00932a99-c7fc-5bd3-8f22-f398e07426dd | note | RECORD OF CONFORMITY: This ITP signed off
b359e4bb-e291-5549-8835-2e7d1ccdfebe | note | WP
c3775e02-7d27-5070-ac0f-95af0c306344 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c76e274-f933-573e-81ea-49f708e9d230 | textbox | Date Completed:
fefd6a72-6884-4122-b8fc-f7f6d5f4b526 | checkpoint | 2.4 Continuous Handrails
092a6fe6-021f-5c02-98c4-638b94a69704 | note | FREQUENCY: Each Lot
2e68c128-a4a2-52af-b7c1-14dd4e01b713 | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
8879e988-9918-5e71-a267-85af57f86433 | note | ○ All sections to be welded as per AS 1554
2ff13cd1-b910-5cb6-9483-6bebad35410a | note | ○ All sharp edges and welds to be ground back to smooth finish
c19fb0fb-9da3-57da-929f-8537be82890e | note | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
3c496473-029c-5e48-8141-f04b8f7fce8f | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
090a2a15-f339-5754-a8ef-b4057644dd78 | note | INSPECTION/TEST METHOD: Verify
0576bf27-bfc3-5ef3-b2b7-43fd1fa29dcc | note | RECORD OF CONFORMITY: This ITP signed off
5c382cb2-025e-5b4e-82cd-206ce46e6ea3 | note | IP
1314b2df-11b9-5f28-b514-3caaa8baf1d3 | note | RESPONSIBILITY: Fulton Hogan Engineer
003673c7-b85b-5dfe-936e-20578c516266 | textbox | Date Completed:
818ac75a-57c9-42fc-a28b-c7aece6657a9 | checkpoint | 2.5 Wire Rope Tensioners
859cede8-b540-59b9-9e38-b5feb9ab7e37 | note | FREQUENCY: Each Lot
775a1413-1964-56a7-8e91-c3087c921e1a | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
00c1babd-21a6-551d-8ebb-71cb998c1ea0 | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
ceb5e068-d0e7-5058-a938-38d674ae63fb | note | INSPECTION/TEST METHOD: Verify
4ee54e53-24b6-5719-973a-180b95f0e023 | note | RECORD OF CONFORMITY: This ITP signed off
ad0547e4-9a26-595d-ad6d-bcc32e62a821 | note | IP
2094285b-4928-5a28-a4ad-dbcb255d2523 | note | RESPONSIBILITY: Fulton Hogan Engineer
feeac012-1fa6-5aaa-a8ca-1e352f5b8b66 | textbox | Date Completed:
49a82191-0538-4dd2-b64f-ac78bf0442b1 | checkpoint | Final Inspection
50b07656-ff1b-5b7d-becc-65e85b3d696f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
784c7b1f-bf2f-51af-b046-54a9d86b6e24 | textbox | Print Name:
b872b33b-e280-505c-b6a5-aad26ad53a16 | textbox | Position:
be00647d-d284-562a-9064-9dcbc5a31e93 | textbox | Date:
eb0d84b0-c4aa-4f90-ac82-1e1701d3a0e3 | checklist | ITP-021 - Line Marking Rev0 | itp | ITP-021 - Line Marking
8c35366e-c162-4b37-a0e1-a00a8840d4d2 | section | Preliminary Works
68b17774-781a-43ac-8588-53bec90404cc | checkpoint | 1.1 Check for correct documentation
7e3b540f-9284-571f-adb2-ee13bc5f58a3 | note | FREQUENCY: Prior to commencing any activity
bda00bee-4075-58bb-b6fe-8319377faaef | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
17154a26-f564-5b92-85d9-15b8ea1f0f18 | note | — using the correct and complete set of drawings
c66a94f5-a3fb-584f-9cce-70ad849e6499 | note | — all drawings are the latest revision
becee304-0884-5cd8-8ebc-04286fba6961 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5e1f351e-6dbc-510f-8e48-4d45ddfdf99d | note | INSPECTION/TEST METHOD: Visual inspection
f256402b-0557-5181-a199-a3b12a9951a2 | note | RECORD OF CONFORMITY: This ITP signed off
b345a96a-ee00-568b-bd8a-3cc625a3c868 | note | WP
b75f5874-ee2c-5638-8a5c-11cfb8063cf5 | note | RESPONSIBILITY: Fulton Hogan Engineer
354b3572-9772-5392-948a-edfdf7a735e8 | textbox | Date Completed:
406d3468-4c90-4508-8cbe-8b96a960a20e | checkpoint | 1.2 Implementation of all measures and controls
74236532-d90a-5f8d-b18a-e46ad86d6c0e | note | FREQUENCY: Prior to commencing any activity
cf25d144-bb95-509d-a3d4-f53ab48b88e5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
19e243cb-1252-55c4-bfb7-81544a9be412 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e3ea692b-4f81-5f2e-8942-ddd3efc6a540 | note | INSPECTION/TEST METHOD: Visual Inspection
5655f9d0-b73a-56c5-92d6-53da4baaf3ad | note | RECORD OF CONFORMITY: This ITP signed off
76de2f2d-1593-55af-816d-59a84ec1b6ca | note | WP
b1bf8ebd-eac8-50d7-ae86-22dbff57b8ad | note | RESPONSIBILITY: Fulton Hogan Engineer
3177e0a9-1c07-5a80-aa53-31176f43ad2b | textbox | Date Completed:
a2ef3572-50d7-49fc-80d8-8f673cd305b0 | section | Construction Works
22c5d23a-9bf2-42e4-97f2-bc35b2a3713b | checkpoint | 2.1 Setting Out
0ac0365f-3c37-5dfb-bc1f-c910cb5cb7b3 | note | FREQUENCY: Prior to start
59f11346-bcde-51f8-8658-68ea00cfc2b6 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
2139bcb5-a701-5b7b-92f5-ddb0a3971a90 | note | REFERENCE DOCUMENTS: IFC Drawings
4161ab6b-24e0-5ef1-b49b-dce35a7df577 | note | INSPECTION/TEST METHOD: Visual Inspection
78a7ec52-de80-57dc-aed3-6ddea2a1baba | note | RECORD OF CONFORMITY: This ITP signed off
76bdc943-4937-5c86-b9f8-34ebf7c34d3a | note | IP
4ac7cc6f-93c7-54e5-b884-6d69a4247dd3 | note | RESPONSIBILITY: Fulton Hogan Engineer
63bdd4c6-1821-553a-8dfb-9b61f23e24d0 | textbox | Date Completed:
06d973d4-8467-4784-9b64-fd81ebfb6117 | checkpoint | 2.2 Position of Markings
3908189c-a843-52eb-a936-914a430edf92 | note | FREQUENCY: Prior to application
30796d87-8ae4-5e04-95ce-6551e9a352c2 | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
452d9f92-ea5f-57be-8dff-a2598bcc91f5 | note | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
41bfd6c5-c9ba-588c-87d5-12c09374ae7a | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
5118dccf-00ca-5971-912c-57722cfc0958 | note | INSPECTION/TEST METHOD: Visual inspection
dcde7566-2aea-503d-97d8-8334b13b0629 | note | RECORD OF CONFORMITY: This ITP signed off
fcc5f6f0-a154-51a4-855f-3253568e6b98 | note | HP
907bacc5-2baa-590a-8973-c916dc51e5e8 | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
5a82e327-06dc-5fb0-9cec-599da3ff407f | textbox | Date Completed:
3287b04e-e1eb-4f2a-a940-ddbd0ee9de43 | signoff | AUTHORITY HOLDPOINT
9733317f-9510-4915-97f3-82f126dd8728 | checkpoint | 2.3 Tolerance of Pavement Markings
8b9b7d5a-38df-5b70-9259-7322313a74ea | note | FREQUENCY: Each lot
7ca71bc1-d213-5f62-adc5-cdf8a61b8634 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
fce10099-ab27-5e9d-9046-b165afcdab72 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
ede2ffad-9849-5691-ac7e-e5818f5758a4 | note | INSPECTION/TEST METHOD: Visual inspection
777995d8-8225-542d-9ea9-27ba10dc0218 | note | RECORD OF CONFORMITY: This ITP signed off
8e16ec70-726d-5dd2-8e58-2e029d7f8929 | note | IP
9b388580-854f-51ff-ad91-454165d221cf | note | RESPONSIBILITY: Fulton Hogan Engineer
68bf9dc4-0a79-5e34-941f-d47821e6a24d | textbox | Date Completed:
44c9d3bb-eae4-4b52-8296-725c4b9c5e64 | checkpoint | 2.4 Raised Pavement Markings
7c21af35-928a-586d-9a14-60f924c0c39d | note | FREQUENCY: Each lot
4bfa58cb-1d3e-5e8e-898a-afdc2ad9bdbd | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
9c99527b-a914-5572-82c0-f77ff34ef3ca | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
f1566ad3-540c-5ec1-a6a1-2071452dcbe4 | note | INSPECTION/TEST METHOD: Visual inspection
776c1e57-06ac-5c90-8301-c0bb48b65e9b | note | RECORD OF CONFORMITY: This ITP signed off
04c5ec10-e7e4-54b4-84e2-548cc358c0a4 | note | IP
f139e0cf-fe22-5e42-9a00-2ff2e1bcf377 | note | RESPONSIBILITY: Fulton Hogan Engineer
648807de-e055-50f8-a8dd-f574ce9e346a | textbox | Date Completed:
43e19e02-6a77-4302-abe1-c28813a687f7 | checkpoint | Final Inspection
b6e1f9d8-cf27-5c8e-9f2a-f4d591ace82c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6c4f0238-4196-5c37-85a9-b5b5f2964ebb | textbox | Print Name:
36f7a0f1-61ed-5c44-8913-32defadfa0f0 | textbox | Position:
90020949-fe70-5c61-82eb-74ea38fef189 | textbox | Date:
cd515b05-3710-4560-802b-6430fcc6509b | checklist | ITP-025 - Structural Concrete Construction Rev1 | itp | ITP-025 - Structural Concrete Construction
7aa21dcd-1d75-4cfa-be0e-79a65e59138d | section | Design and Submissions
a0c0cc8a-c405-4051-95c6-3bb415d045d7 | checkpoint | 1.1 Check for correct documentation
a2203d7c-70f4-515b-b3f8-c394239d03ac | note | FREQUENCY: Prior to commencing any activity
dd71f354-9ad4-5d10-b2c1-102175682f36 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4ea75cf8-8fda-5da0-b353-fc018bff8138 | note | — using the correct and complete set of drawings
0e7c92c1-af63-5ac8-a5c0-432747febdd0 | note | — all drawings are the latest revision
2b1a74ef-8d37-5e66-9986-f16cf87ca5c7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c647195c-163e-54f7-94fd-4d23102637e3 | note | INSPECTION/TEST METHOD: Visual inspection
3aefadc6-b9db-571c-af36-37595f61b16c | note | RECORD OF CONFORMITY: This ITP signed
e4b0dc14-4dee-5f6a-b8d3-be3cf3b6b71c | note | HP*
1da92e11-9800-55e9-bacf-1270969f85e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
cafcd874-4beb-5b2b-8c99-5bc458cce581 | textbox | Date Completed:
6b7d2a11-a404-4018-972c-2d1e36d205a1 | checkpoint | 1.2 Implementation of all measures and controls
87145edf-3692-51fa-bd41-6776023be2f0 | note | FREQUENCY: Prior to commencing any activity
2cdfa8b4-208e-59a3-9b34-68c230a20496 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
e69e7b3d-53cb-5a02-88b7-ec22cb4465b6 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
3cb6d256-f46a-541c-8c48-68198e96cb72 | note | INSPECTION/TEST METHOD: Visual Inspection
c3f699e8-f259-5f1a-8bd4-ada5c748719f | note | RECORD OF CONFORMITY: This ITP signed
4aa1f449-dd89-54c0-bbec-102ed425515a | note | HP*
27357c7f-9444-5e21-a098-90d83fd697d0 | note | RESPONSIBILITY: Fulton Hogan Engineer
ab8c395f-8a40-54a2-a314-a4811c7c7961 | textbox | Date Completed:
34539ceb-c776-4c3f-a545-975b7db22b42 | checkpoint | 1.3 Approval of mix design
e069db5f-19f4-552b-8902-e10fdc02156f | note | FREQUENCY: Prior to the first concrete pour
51540b34-3ca5-59cb-b515-b23e330298c0 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
10d75f0f-1700-5bf1-817b-41f9670f6c6d | note | REFERENCE DOCUMENTS: 610.07
bf9e826a-1db8-5b58-8940-f5421a4e8297 | note | INSPECTION/TEST METHOD: Verify
179f38c3-d5ad-53fa-8f7c-9009afc47e2a | note | RECORD OF CONFORMITY: This ITP signed
8274498c-0ba3-5ae0-9143-648fad1ec135 | note | HP*
ba3c5ad3-45ca-5d21-b5f4-b8e56d40d4a8 | note | RESPONSIBILITY: Fulton Hogan Engineer
789d2646-afd8-53e8-9be7-3d7b524f1565 | textbox | Date Completed:
cecda3c4-2cb9-4a13-8427-a133c59d4fa5 | checkpoint | 1.4 Reinforcement schedule
16b7187c-65ff-56a9-9596-dbd9fe47b6d5 | note | FREQUENCY: Prior to concrete pour
590f3d07-428d-5455-b950-b3caa5ea2120 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
34a7fced-0ff0-5c1c-b8d8-bc5228a6b71f | note | REFERENCE DOCUMENTS: 611.04
9423f344-d342-5efc-9308-b801d88bee98 | note | INSPECTION/TEST METHOD: Verify
c92886a8-f305-5502-a6a6-69a6dada3bc5 | note | RECORD OF CONFORMITY: This ITP signed
f1674272-5e41-51fd-aae3-936348ce1485 | note | IP
481731c0-f749-54c5-b477-fa49aa64122b | note | RESPONSIBILITY: Fulton Hogan Engineer
02b4f349-0e7b-56a9-8102-1a1a4e7c68f1 | textbox | Date Completed:
677f6ee9-1c49-42fd-9f63-9192f4716c4f | section | Construction/Erection of Formwork
cc64207e-cd95-404e-8b0a-526f79979ea6 | checkpoint | 2.1 Excavation
c6455b26-607d-53de-8a59-1cc139335dc7 | note | FREQUENCY: Prior to concrete pour
1722315c-f404-5326-a3cd-73c00cce762a | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
9c2f7aa5-bf8c-57fd-bb8a-3ef1bde15981 | note | REFERENCE DOCUMENTS: Contract Drawings
dc3f1c40-b585-53cf-bfde-09ce9bec22ce | note | INSPECTION/TEST METHOD: Inspect
0e733736-d162-5ff7-88e0-01195663b53f | note | RECORD OF CONFORMITY: This ITP signed
6ae0db2b-5d97-5757-8100-7e81d64ea6bf | note | IP
7b1b0e55-efbd-5128-bd2a-cb2810c0a4de | note | RESPONSIBILITY: Fulton Hogan Engineer
5733fff9-814a-5dd2-bae0-e21cf2b88882 | textbox | Date Completed:
a280306d-1e16-481e-8758-357b0e6533fc | checkpoint | 2.2 Construction Methodology
069aa8be-1ef6-56ce-8388-051be357c264 | note | FREQUENCY: Prior to erection
31edb4d0-a55d-54a3-87c1-f49447ab4763 | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
2abb05fb-b2f3-5ecc-b1d8-0caa9ba4de79 | note | REFERENCE DOCUMENTS: 614.04, 614.06
1a973d99-df7b-5ee0-9117-9aaf249bdc6f | note | INSPECTION/TEST METHOD: Verify
ee36e91e-6b9c-5b8b-86c6-a210d4d95bc1 | note | RECORD OF CONFORMITY: This ITP signed
39f6a67b-c9b8-5ce6-95d0-f96dacf8ad26 | note | IP
b839e04a-171e-5371-bc6e-f19c9fd296fe | note | RESPONSIBILITY: Fulton Hogan Engineer
1790fbaf-6fa4-59d4-ba5e-c1b78cc42317 | textbox | Date Completed:
0cb3525b-1eb3-4158-be90-42e1885a557d | section | Pre-Pour Planning and Inspection
6976f3ac-cf31-4d42-934b-63d1982f4df4 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
13b7fa24-4eac-5714-bce9-cb4183c3a8d4 | note | FREQUENCY: Prior to concrete pour
2e8214b0-b58e-5ecf-ab5b-766cd8db97ac | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
1e85872c-efd5-5f32-9e51-0280052c1ffa | note | ○ Hold Point released by the Superintendent.
4524b049-4c59-5865-8ebd-e220c884fa75 | note | REFERENCE DOCUMENTS: 602.03
2bc3b7ae-c655-529e-b7db-12589f73183b | note | INSPECTION/TEST METHOD: Verify
c4be1ee1-38f4-57cc-9980-f2b82e322cee | note | RECORD OF CONFORMITY: This ITP signed
e582cfc8-95b8-5170-ac15-3d533f0c7000 | note | HP
fd14b18c-8cb4-5d3c-b911-9ad506bd6959 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
555fa9af-4c4f-5bfc-a658-5a58e2dc0b74 | textbox | Date Completed:
e222df9e-0861-4bd9-8c15-a34f023ff175 | signoff | AUTHORITY HOLDPOINT
249eb14e-0c01-4745-8b8b-e2c37d40a6a9 | checkpoint | 3.2 Formwork levels and position
784cd1bd-7737-591f-beac-a6476901f833 | note | FREQUENCY: Prior to concrete pour
b88eb08a-8f07-5487-b823-dab9d1e8d685 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
bdeb3100-7e74-5e3c-b7bd-3bdc8e948d5b | note | REFERENCE DOCUMENTS: 614.06
ba41cc45-5837-5ae2-8cba-5488dfa461be | note | INSPECTION/TEST METHOD: Verify
c1601fde-d054-588d-a5b0-2e62d2948b0a | note | RECORD OF CONFORMITY: This ITP signed
3199f3b4-0b64-5c38-842a-8bb8decc5c20 | note | SCP, HP*
12cf0853-2071-5dc4-8dde-4100c5e949fd | note | RESPONSIBILITY: Fulton Hogan Engineer
f5fd770f-f338-5230-8764-fc1701acecc2 | textbox | Date Completed:
c6be7fcf-1fa8-44b7-9e4a-1d604731f41c | checkpoint | 3.3 Location of splices
f983fc12-3b15-56dd-a707-252b0cdeecc1 | note | FREQUENCY: Schedule Review
1d07e487-393a-5acf-9185-eff1d1d75929 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
2af45739-3ce8-5815-8897-bff11cbadee1 | note | REFERENCE DOCUMENTS: 611.11
0cc72677-fcd4-5a9f-aad9-34cce8324d48 | note | INSPECTION/TEST METHOD: Inspect
0958c858-bb5e-567f-9f76-1c4188385b5b | note | RECORD OF CONFORMITY: This ITP signed
4ba55579-f1f4-5d4c-8fc2-5890d7be73eb | note | IP
6f538cd4-2f6e-5b78-9484-89f6017b012b | note | RESPONSIBILITY: Fulton Hogan
8cb48e9c-da68-519a-8fff-a0d8f4fcc65d | textbox | Date Completed:
f3940597-78ad-48ad-996a-8ce6910f0164 | checkpoint | 3.4 Cleaning formwork
c7e475f5-02bd-5dd8-b87e-dedf73fe90c3 | note | FREQUENCY: Each concrete pour
34237e8d-9a0d-532d-8007-157b11faea57 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
e7072963-5f4a-542e-861f-0ffc92ff58ed | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
eaff1f2d-3b86-50a0-818e-0a12197378c2 | note | INSPECTION/TEST METHOD: Verify
a9d9883f-ae1f-5dac-8df1-c63f7bf12cc4 | note | RECORD OF CONFORMITY: This ITP signed
44bc5494-7e5c-5bc0-8052-5d154c2906e5 | note | IP
3bbfcd72-a4ee-50dd-8f7a-5eacd953d411 | note | RESPONSIBILITY: Fulton Hogan
6fc831ba-b594-52b1-a173-79945a39aaf9 | textbox | Date Completed:
8c2d1e8d-d727-40fa-9641-c59778c76f58 | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
d54402bf-8360-5bc6-86eb-3df3ea7f3d81 | note | FREQUENCY: Prior to concrete pour
3ea71370-13b7-516b-9d5f-ce9880e22f90 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
39ca65d9-f2a6-5e76-bd74-782137fdb82d | note | ○ Pre-pour checklist completed and signed.
57271ddb-a985-5d9c-9877-c02e67d6dea3 | note | REFERENCE DOCUMENTS: 610.18 (a)
3d5ace5e-bc68-5a54-a8cf-6317a717682d | note | INSPECTION/TEST METHOD: Verify
45f76e47-032f-5da5-9b4e-c82e42c48b11 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
77034084-9fa1-5127-8e40-122409080937 | note | HP
1b18a160-235e-5ee1-9bb2-3eebab69b5d4 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
b2bcbafb-1578-5868-aea3-e97be0833f52 | textbox | Date Completed:
2c56f3b3-45a5-43ed-8cd7-377d3e0d3a38 | signoff | AUTHORITY HOLDPOINT
8497adc9-ca54-4acb-8894-e65ff69547f1 | checkpoint | 3.6 Reinforcement assembly of piles
d59f9468-b812-547b-ab2e-1a874d63b599 | note | FREQUENCY: Prior to concrete pour
ec8c6edd-34ca-5a50-a2cf-dd09ba6ec70f | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
5ace31f4-d2ea-5955-ab54-b974cc9d4be0 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
29b484ba-ac61-5a58-aaca-f79e21aed40e | note | INSPECTION/TEST METHOD: Verify
7bb6f4a7-c2f8-5552-81cf-c53a200c1ffb | note | RECORD OF CONFORMITY: This ITP signed
f72dee9d-9082-56f8-aa43-398a180c4201 | note | HP
5f63594f-d67c-5537-9c2a-8972ebc89f8e | note | RESPONSIBILITY: Fulton Hogan
5bdc2abe-6b4c-5f34-93b3-48cb3fc258fb | textbox | Date Completed:
11bbb727-e3e0-44b1-9204-f5d3cacfd11a | signoff | AUTHORITY HOLDPOINT
4f6feaad-5e23-430e-80d6-102fb4453ba8 | checkpoint | 3.7 Monitoring weather
0650fe0b-2dc9-54e8-be58-1b195639a87d | note | FREQUENCY: Prior to concrete pour
5306a10a-005f-5f31-b9e7-daae49038e36 | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
c3072aa3-4ba3-527b-a10a-64ff105d2a18 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
862bffd9-c5be-5ca8-9128-89833562248c | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
64d4eb59-397f-5620-a315-397febeb7b38 | note | INSPECTION/TEST METHOD: Verify
f6f67ff7-bea7-59ed-949f-3dd3013953de | note | RECORD OF CONFORMITY: This ITP signed
c613d9be-d04a-5e87-b0db-6bef2abb1f12 | note | IP
b36f7e6b-18bf-5324-800b-113304eb95d1 | note | RESPONSIBILITY: Fulton Hogan
ab1c1970-9122-5cf2-bedc-d94125998f0c | textbox | Date Completed:
1ef92403-f840-4b52-9ebd-50092762330f | section | Placing and Finishing Concrete
a0aff579-3ff7-4f6c-8885-0a440067a9e1 | checkpoint | 4.1 Carry out sampling of concrete
8384658b-3264-56f6-bd42-cf13b2558710 | note | FREQUENCY: Each concrete pour
93059847-3567-51f4-bf0b-39ca1f4b8eb6 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
a6e80016-7fb2-564c-a702-2bae40989cf7 | note | REFERENCE DOCUMENTS: 610.16
98e0b1b4-6a13-5007-bf71-14560721b4ba | note | INSPECTION/TEST METHOD: Checklist
93483756-b71d-53ca-8e0b-cf3e099c299b | note | RECORD OF CONFORMITY: This ITP signed
c5ff9291-ad49-5473-8192-f57d5763e78c | note | IP
1bbed5a3-2ce7-5b4d-b781-babb91ed7532 | note | RESPONSIBILITY: Fulton Hogan
1688b248-8802-5031-92fc-4f16e04d6ee9 | textbox | Date Completed:
fbc450df-e84f-4d7c-a5df-9979abd79dc4 | checkpoint | 4.2 Discharge time
8f7805b9-38be-5ff6-b830-704fc7e840ee | note | FREQUENCY: Each concrete pour
80eef849-1187-5ad1-be38-02cf8be8d60b | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
57815ff3-7126-5b54-9ba1-103324803ba7 | note | REFERENCE DOCUMENTS:
268d95f7-7c35-5dfe-be94-a37a1e196f30 | note | INSPECTION/TEST METHOD: Verify
3f043ae1-9039-56a1-b230-d5559757e128 | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
4fb2ffeb-dfd8-59f5-89f5-aeb320880dad | note | IP
6532c07f-dd65-5700-afb1-50fce4e86b91 | note | RESPONSIBILITY: Fulton Hogan
5be9c576-43f5-52eb-ba97-2e15fa1749b2 | textbox | Date Completed:
928bd899-9463-47ef-9864-55d2bdc8ca9c | checkpoint | 4.3 Methodology of placement (structural)
a08e4855-03c7-5cc7-98da-e10ad24a4bd5 | note | FREQUENCY: Each concrete pour
b5ece07a-5ec1-5c6a-aeb5-6d893f1de0e0 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
fc51aede-78c4-5988-8952-ccb63ad138f7 | note | ○ Concrete shall not be moved horizontally by vibrators
fb2c93be-fc00-5836-900a-29ed475ad205 | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
d0e0156c-1703-5645-954f-3d89b2b508d4 | note | REFERENCE DOCUMENTS: 610.18
76bfc801-5937-5533-9fa6-69c3787b5a0a | note | INSPECTION/TEST METHOD: Verify
3f84b3ea-6cf1-5d9c-9856-2bb592142cee | note | RECORD OF CONFORMITY: This ITP signed
0f59fc1b-ac9d-5b1e-813f-abe1028b15a1 | note | IP
6542bafc-68b6-56ab-8b85-701c540499ac | note | RESPONSIBILITY: Fulton Hogan
cd4f51ac-6ebb-584d-8167-143439801e4e | textbox | Date Completed:
ae344cf7-5ab1-4cd6-86f6-7fbceadff338 | section | Post-Pour Details and Inspection
38be79b2-34ce-4828-9973-fbaba91b24eb | checkpoint | 5.1 Curing
037ebf05-0b1a-5b26-acfb-946749740782 | note | FREQUENCY: Each concrete pour
b3b4f474-15a8-5535-b73a-aeb3382b7107 | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
b59c7ca2-d846-5577-abee-69bcfe1b2482 | note | REFERENCE DOCUMENTS: 610.23
e27c4eb3-c634-580a-a55e-5eb866de7b1f | note | INSPECTION/TEST METHOD: Verify
a440b1ed-d4c4-552e-b085-1a8fdad9724e | note | RECORD OF CONFORMITY: This ITP signed
79ae8e58-7356-5c46-b92a-842c40572488 | note | IP
db033870-21a4-578f-a9a2-53c7cc292031 | note | RESPONSIBILITY: Fulton Hogan
917ef68e-a76a-5073-ab53-e36c93412675 | textbox | Date Completed:
906748c5-ab98-4c97-b61f-ee539a7ad80a | checkpoint | 5.2 Formwork removal
539e80b6-e95e-565d-8e69-19a61feff4a7 | note | FREQUENCY: Each concrete pour
9103ab88-d976-53ec-b881-5a4bcbc14f1f | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
e8723046-47b9-5a2f-a896-e6466e2084c1 | note | REFERENCE DOCUMENTS: 610.25
84d15a03-eaa8-5fcf-9184-b36aff0dc80e | note | INSPECTION/TEST METHOD: Verify
f15e4b63-70a4-58c0-a5f4-98981dbd9cc8 | note | RECORD OF CONFORMITY: This ITP signed
caa60a6d-89a1-59af-bd68-8070427fd98a | note | IP
7c0231f1-8f99-5cb3-bd4f-d5db8ff8103a | note | RESPONSIBILITY: Fulton Hogan
d0a38b39-9487-5bab-a88e-266432d644da | textbox | Date Completed:
918aa4e8-86bb-451b-8203-35444098cae3 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
2203be87-fe19-5f65-93da-1f98cc6359be | note | FREQUENCY: Each concrete pour
2e6778aa-93b7-58b5-9a97-4b044b8a771f | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
75a89848-4dd3-50e7-845b-3a8c72e40d1e | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
5ed0fc0f-5777-5b60-914d-43bf30c8b84b | note | INSPECTION/TEST METHOD: Verify
656fa487-f235-5a44-bf5c-7f8844ce815d | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
69a3f97c-1418-544b-8924-5887663292cc | note | IP
92cb9549-bc20-506d-b75f-52a74744c22b | note | RESPONSIBILITY: Fulton Hogan
63236ac5-ee7d-5157-90f5-3706a587f798 | textbox | Date Completed:
58c3f61e-d861-4627-a0c0-6cbb00b3e97a | checkpoint | 5.4 Concrete Sampling and Testing
cc73a300-ff21-5269-8ded-2652e766dfb9 | note | FREQUENCY: Prior to lot closure
9e8c1f74-a460-582f-9469-f86a9f152797 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
34e36642-1696-5336-95f8-e62862d1351a | note | REFERENCE DOCUMENTS: 610.16
30c85fad-2005-5d44-a75b-43eb1b4a1fd1 | note | INSPECTION/TEST METHOD: Verify
9815bf03-c908-5d10-b305-3bbd5cdb2dcc | note | RECORD OF CONFORMITY: This ITP signed
8fcb0f43-2834-5c23-8237-c536ef215ffe | note | TP
f3459352-c133-51c6-b270-97eb4388042d | note | RESPONSIBILITY: Fulton Hogan
3ca370c9-148b-5808-9c6d-3fd4695354b5 | textbox | Date Completed:
e7c0b09e-4b95-49df-bd10-6d9e6280907c | checkpoint | 5.5 As Built Drawings
c23187ef-1fd6-5b82-a77e-d9a040468c92 | note | FREQUENCY: Prior to lot closure
083dd31c-b438-579c-9e20-bfb79a7e005c | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
d99edcc7-6c35-5e15-937c-379856c0603a | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
7622da7f-be97-5bb8-b2f6-3fadc86e90b8 | note | INSPECTION/TEST METHOD: Verify
1dcaa0c3-904d-5c0a-9257-be96253fbc36 | note | RECORD OF CONFORMITY: This ITP signed
7bf2022f-bc07-544b-9116-f81f23923e28 | note | IP
b6099f9c-f288-5338-b77d-bb555e00f1ef | note | RESPONSIBILITY: Fulton Hogan
f00df46e-04f0-5f55-b7f0-1c6ff2aae3de | textbox | Date Completed:
ec7d1f29-eba4-498f-99f2-51995f773b31 | checkpoint | Final Inspection
404b7d16-0e4c-5b39-8101-2aa47ba5f05c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
46cd13a7-eee6-5be3-bae7-390f2f9f9db1 | textbox | Print Name:
f318aee5-3e5f-5748-9a9c-515bc4b51d0f | textbox | Position:
bb7b8f40-b3fb-5319-aa3b-4e0e24a73cb8 | textbox | Date:
f81b70c2-e899-4438-8d7f-2df53507f795 | checklist | ITP-028 - Street Furniture (Supply & Installation) Rev1 | itp | ITP-028 - Street Furniture (Supply & Installation)
9e03d9eb-c909-42dc-b29a-88a45e5054a6 | section | Preliminary Works
bffff3bb-b170-46ea-b951-5a7d84399f20 | checkpoint | 1.1 Check for correct documentation
3b825047-edd9-5747-b5c0-e39d0349050b | note | FREQUENCY: Prior to commencing any activity
4ccaf0bc-7846-5dc8-8c71-2489580a279d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
d27bd9d1-9555-53fb-b045-782d70b10974 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
521850d2-4fe4-58f9-9081-46ab03905894 | note | INSPECTION/TEST METHOD: Visual inspection
05f420c1-da41-5d26-9481-1e6db5dbd982 | note | RECORD OF CONFORMITY: This ITP signed off
f71f107a-2594-5c28-85f2-3538d45333f7 | note | HP*
9c504223-70b2-5daa-96d0-85ebce079200 | note | RESPONSIBILITY: Fulton Hogan Engineer
5935d788-f3e8-5300-98c7-841ca2f31b66 | textbox | Date Completed:
817faf4e-439c-4df7-8198-8ce916e4a58a | checkpoint | 1.2 Implementation of all measures and controls
3b644cae-55b7-5a02-bb54-18a99761aea8 | note | FREQUENCY: Prior to commencing any activity
1c6d4edb-38bd-5c95-aa27-164c286d9d79 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, SWMS & WP
e70d2008-ae51-5bc1-92cc-d4ab7c25090c | note | REFERENCE DOCUMENTS: EMP, SWMS, WP
53cdec9d-e7b1-5907-b1fc-267fdc7cb788 | note | INSPECTION/TEST METHOD: Visual Inspection
163e7bf2-8536-5e97-ba88-e182722a92cd | note | RECORD OF CONFORMITY: This ITP signed off
2d72c797-8bbf-5391-8374-e8a40e7ebbd7 | note | HP*
5f853a0f-7f24-555d-b9ce-048b3eb3822e | note | RESPONSIBILITY: Fulton Hogan Engineer
960e348f-2aa9-531b-b230-ebf7402ae2d8 | textbox | Date Completed:
3370d891-55c9-41b9-ace4-21f6ba74e998 | checkpoint | 1.3 Check Materials
6945fada-addf-521c-9151-b8ba1358835a | note | FREQUENCY: Prior to commencing any activity
2a591a0c-f80e-5124-914e-fafb79390c68 | note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished
2f4dd615-2f1f-5acf-9b4e-477bb71e9298 | note | ○ Welding shall be in accordance with AS1554
8ffe84bf-2204-549e-8946-32cbfaa23323 | note | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
ee08044e-4ab4-53d5-85ee-374564d93d62 | note | REFERENCE DOCUMENTS: STD_T6000 CE-021-ST-0012 cl 4.3.1.4
2096bc47-8224-5c16-b912-969c51edb3fd | note | INSPECTION/TEST METHOD: Verify
9167881e-d4b8-5761-a1d6-14fe506aac43 | note | RECORD OF CONFORMITY: This ITP signed off
a1c45fef-ef0c-5434-af55-a9c003dfdf38 | note | HP*
e8783d73-bb40-5d2f-8859-51526271b581 | note | RESPONSIBILITY: Fulton Hogan Engineer
268fd9b2-3a9b-5c0d-b0d4-0ed845265b87 | textbox | Date Completed:
90787dd4-7913-4841-acfe-773247c510b9 | checkpoint | 1.4 Confirm Footings position
180f85f6-7bb9-5748-80ae-53680fff14fa | note | FREQUENCY: Prior to commencing any activity
e625c0ad-e4ca-5fb7-81b2-8aff0f7198c0 | note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
124babae-9e7a-5e6c-a015-8467e959b53b | note | REFERENCE DOCUMENTS: Construction Drawings
4ce9d82f-ea64-57f9-a5c5-31effd2be6a8 | note | INSPECTION/TEST METHOD: Verify
fd2a2dbc-009c-5b65-9a40-726069c2a702 | note | RECORD OF CONFORMITY: This ITP signed off
0f9e8428-86ab-5f21-8406-aae46d6a0852 | note | HP*
da0c0e8d-b428-5514-8c5f-7ee9e936a460 | note | RESPONSIBILITY: Fulton Hogan Engineer
0ad28442-1e7d-5a8d-b930-7348a2fdafc7 | textbox | Date Completed:
6ddceda7-6a14-444d-8e75-80f54b593bb5 | checkpoint | 1.5 Bonds
bf1c36e8-7ac5-5830-820c-a0c56dc92927 | note | FREQUENCY: Prior to commencing any activity
4a210c56-fbb5-50df-98c1-14a84a547abb | note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation.
fe0edb36-9275-5258-b6b6-c0e6169eb666 | note | ○ Lug shall be fitted to baseplate at specified fencing location
2f4ac7d4-53d2-5320-bf6f-ce29e935139b | note | REFERENCE DOCUMENTS: STD_T6000
64c2e20b-4d86-5ed2-a382-ddf19f1b8e71 | note | INSPECTION/TEST METHOD: Verify
b81c5f98-0e31-539b-8f84-33e30edb1f07 | note | RECORD OF CONFORMITY: This ITP signed off
30f44635-7a65-57c7-b77e-1933392efa25 | note | HP*
7224f9c1-2f6e-5431-84c0-56d4250561e3 | note | RESPONSIBILITY: Fulton Hogan Engineer
d487fef3-f4d2-571d-986f-85d95e10da45 | textbox | Date Completed:
c185eef6-1310-4b84-a1a0-c468eb7946af | section | Construction Works
092148f1-8222-4098-9059-8b5918a3d8ac | checkpoint | 2.1 Footing Installation
1af9fd54-f108-57e0-9736-50558ec129c4 | note | FREQUENCY: Prior to Asphalt
b3308df3-9e05-5657-b47d-b3a0aee5d65d | note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
6bac4b46-febe-5d28-8553-0a90b13599b3 | note | ○ 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
ec433d17-4fc2-5731-a709-abf161988faa | note | REFERENCE DOCUMENTS: STD_T6002
c11b0661-7276-5072-9427-271f5fbb1ab6 | note | INSPECTION/TEST METHOD: Verify
7373a01e-39ce-5cb5-9564-43f726ef9b01 | note | RECORD OF CONFORMITY: This ITP signed off
21aa9ee7-f7d8-558f-80fc-1a7e2c63f79e | note | IP
8123b4e8-038d-5436-9b69-5eca888f360e | note | RESPONSIBILITY: Fulton Hogan Engineer
be56dcdf-c527-5234-a89d-f7ac670cef1b | textbox | Date Completed:
55f50e19-14dc-4206-b769-ef5486a3ca9b | checkpoint | 2.2 Post Installation
676d3403-d73b-5f0f-bf2b-8499a0198d7b | note | FREQUENCY: Each Lot
9869b236-c24b-5b8a-8173-5e292b514935 | note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level
4832de39-95d7-585a-a4be-0806112af15b | note | ○ Installed to footings with bolt assembly
7f805089-8fb6-5c0f-9bc3-bf1b402c04db | note | ○ All bolts shall be insulated from base plates, using non metallic sleeves and washers
6362d6fa-e8a7-58a7-90b9-90458cc81909 | note | ○ The top of fence base plate shall be level with surrounding pavement
c93d7be8-ebb2-5b12-81fb-8d3e3a8e94e8 | note | REFERENCE DOCUMENTS: STD_T6002
72837ab3-b55f-5e19-a82a-6299d49de293 | note | INSPECTION/TEST METHOD: Verify
d714ed8f-1837-561e-bb52-72af0488ea6d | note | RECORD OF CONFORMITY: This ITP signed off
66decbc2-de5b-5001-bb1c-5ced189b7cb7 | note | IP
6ac5c8fc-c592-5c95-9167-ab097aa0b76f | note | RESPONSIBILITY: Fulton Hogan Engineer
49bbcbe7-534a-573d-b230-d87776766ce0 | textbox | Date Completed:
8b3eb4db-5818-414b-a74d-3871d3683788 | checkpoint | 2.3 Grout Installation
5f28ff7b-d368-507f-8263-f21536318424 | note | FREQUENCY: Each Lot
350dbf94-50f7-563e-8e1d-f412f41ef464 | note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application
b6e8c9e9-278c-5330-8f46-bf73fa435de0 | note | ○ 50mm of Non shrink dry pack grout shall be placed under base plate
6ed2d8e5-a2be-50ce-b3b2-20676cf8d349 | note | REFERENCE DOCUMENTS: STD_T6002
35bfc644-d76b-5211-ad22-8d51699a60c9 | note | INSPECTION/TEST METHOD: Visual inspection
a54c2d1b-c98f-53a3-b524-3536096a4b13 | note | RECORD OF CONFORMITY: This ITP signed off
ed5c2686-a4c7-571c-a383-cc89959494d7 | note | WP
a8e61056-68f7-57c4-b802-cefc0862a658 | note | RESPONSIBILITY: Fulton Hogan Engineer
24f964fc-7da8-5093-b298-8b03abac5d4e | textbox | Date Completed:
be0d8fac-ebe7-4536-8915-76d4e17efd58 | checkpoint | 2.4 Continuous Handrails
7ddfe9e9-533c-52e5-9a6c-aa7e2c4224ee | note | FREQUENCY: Each Lot
c326537f-a891-5cf5-8507-19b8e3262caa | note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
9e2e008d-3b5a-5a12-b002-72144b6d5bda | note | ○ All sections to be welded as per AS 1554
33a1a6c1-230a-5b4c-aadb-20a74d929ddf | note | ○ All sharp edges and welds to be ground back to smooth finish
4dee3308-b3cc-5c34-853a-54c55a8cbaf0 | note | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
e458f502-0819-5b1a-87c4-3612d89f6189 | note | REFERENCE DOCUMENTS: STD_T6001 & T6002
e4214745-07cd-52c1-8598-07c5a3006284 | note | INSPECTION/TEST METHOD: Verify
299bd3e7-e582-5fb7-8d93-174992e8e8d1 | note | RECORD OF CONFORMITY: This ITP signed off
5fb0a4fb-79f7-5a0a-bf1f-e0f4a1da0254 | note | IP
b742968a-dffe-56e0-aec0-fe4f4388d4b2 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc37ab3-c5a6-53ec-959c-c25fdb30dbff | textbox | Date Completed:
3a6b26e1-f92d-4be0-8ce0-bfbd6eb7386b | checkpoint | 2.5 Wire Rope Tensioners
e6416d14-f193-5a9d-a68c-ccd75dd46356 | note | FREQUENCY: Each Lot
adf7f286-2e3a-5c2b-8d02-673814f4302c | note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
69ed6a2d-2f1a-5f06-8ab0-494b16778785 | note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
ac4a72b0-8684-50be-b0b7-e71d1d34ee9f | note | INSPECTION/TEST METHOD: Verify
e67c746a-6416-5109-91e1-6ab1207a27ff | note | RECORD OF CONFORMITY: This ITP signed off
14dcb990-1f95-5f89-b9ab-91f6e2ab5fd7 | note | IP
c12a6ac2-732e-5b61-850b-8128335d19fd | note | RESPONSIBILITY: Fulton Hogan Engineer
e0abd5c7-4cfb-51ce-b6a3-17ff5f29d9b5 | textbox | Date Completed:
95afd524-ea5e-4a21-98cb-fce2c6998ee8 | checkpoint | Final Inspection
c74eb7d5-3983-51dd-b8b8-517c3c2ec223 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ae0bd643-2a41-5cc2-85db-7595c4c8e2b5 | textbox | Print Name:
74423900-a2fb-55ba-9e74-ea4bb63bc486 | textbox | Position:
f690c326-6cc6-5ae9-ae26-174158e99789 | textbox | Date:
61871263-8136-4a74-ad2a-770c2572ac52 | checklist | ITP-029 - PVC TGSI Installation Rev0 | itp | ITP-029 - PVC TGSI Installation
1016b291-4db2-41db-8d2d-8f259f2a1e08 | section | Preliminary Works
c6f38aa9-98cb-4c76-86d5-ba08a53884a5 | checkpoint | 1.1 Check for Correct Documentation
46ca14b3-05a7-5ff1-ba4c-4638dbee3e35 | note | FREQUENCY: Prior to Commencing Activity
fe525f0b-0d58-5bbf-8f4e-6e43ad248f79 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
661e3510-20c6-5b08-85ef-5225cc45652c | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
a582ff91-5ae9-5b56-96d9-19b1b18a2bbd | note | INSPECTION/TEST METHOD: Visual Inspection
1c04e31d-d154-58c2-90f3-894ca8de0732 | note | RECORD OF CONFORMITY: This ITP Signed off
8bb19138-4082-51eb-883a-0aa17a62e2f2 | note | HP*
212a1175-79e8-58b0-8972-cad9cb424310 | note | RESPONSIBILITY: Fulton Hogan Engineer
5cea1135-836e-5ca6-af40-8762d0cea69a | textbox | Date Completed:
943372ba-adfd-44c2-8652-111c39228307 | checkpoint | 1.2 Implementation of all measures and controls
2e93f8db-72ca-5bb3-8bb8-004c3f6d0c75 | note | FREQUENCY: Prior to Commencing Activity
48d914ba-8529-565c-adb4-7b416c2af63a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
13e21817-c5fd-5ad9-b99f-1723a221ef76 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
a135b45f-42a3-5e17-a04a-74fee5ae3848 | note | INSPECTION/TEST METHOD: Inspection
05617d9f-3d57-5c82-b5a8-176e0c39ba6e | note | RECORD OF CONFORMITY: This ITP Signed off
46b62e5d-ea11-5a18-92fc-130103383f21 | note | IP
9e857fe3-c9d8-564d-8e47-f8c0f10e9dd4 | note | RESPONSIBILITY: Fulton Hogan Engineer
dff50010-095d-5ef2-be5b-697a5902defd | textbox | Date Completed:
a3dfbf29-8377-4d8f-a70e-a078b61252c5 | checkpoint | 1.3 Check Materials
f823cb74-625e-596f-a2a3-391e3fbd1525 | note | FREQUENCY: Prior to Commencing Activity
23bd59da-fd15-5ae8-8026-44f61f34ac78 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
dd1f9523-3227-560b-be7e-d2fd303f65d6 | note | REFERENCE DOCUMENTS: Receivable Inspection List
8b3f9916-a61b-5a21-8b0f-a963ffa42627 | note | INSPECTION/TEST METHOD: Visual Inspection
20ea6399-adc1-5fe9-af07-50a47872feef | note | RECORD OF CONFORMITY: This ITP Signed off
172ad151-3271-5af9-85da-73ed99d335f0 | note | HP*
53cf06a8-48e4-570c-ab7d-e21ceec59349 | note | RESPONSIBILITY: Fulton Hogan Engineer
89b850ff-72fb-5617-870a-c4ab2d219ae1 | textbox | Date Completed:
62a78bcd-6960-4257-a455-e1f47065cc80 | checkpoint | 1.4 Setting out
3e4be390-67db-5ab3-b249-1d9fdac6eb8a | note | FREQUENCY: Each Lot
da848d02-9e7b-5146-808d-bfc054cbacc2 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
62b4eb3f-7481-5807-84c9-82c57f976326 | note | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
8025d751-4448-58c8-bbcc-3b6e79fc0bfe | note | REFERENCE DOCUMENTS: Work Procedure
f3dcf5bd-0428-5734-9f1e-6098a40ed3e6 | note | INSPECTION/TEST METHOD: Inspection
7b7f9ddb-f010-517d-bc3d-e990af95b6f2 | note | RECORD OF CONFORMITY: This ITP Signed off
aa64b924-2120-504d-9173-0b8f057f26b9 | note | WP
be5e2d4f-91c2-52a6-98d8-2fd92f220598 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
731838cb-d799-5f26-a696-e8a2a26d1bd2 | textbox | Date Completed:
8fb95bd2-a6de-442e-89fa-e1132aab36ee | section | Construction
d9ff8221-4755-4176-8750-de9d084997d5 | checkpoint | 2.1 Base preparation
1106a8a3-8fa6-57a2-832b-fe4b1da1df61 | note | FREQUENCY: Each lot
04f374a6-7490-5015-a02a-14e5707d2de7 | note | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
c07c7576-a092-527b-b680-1d73763745fd | note | REFERENCE DOCUMENTS: IFC Drawings
a254a293-5509-5980-9c64-7673893c0e84 | note | INSPECTION/TEST METHOD: Visual Inspection
91cc8ab5-176a-55dd-9095-f6f381896b17 | note | RECORD OF CONFORMITY: This ITP signed off
039c8d32-f3c7-5c2f-9f24-6adf0746f4ca | note | IP
54f97965-12c9-5d0f-9eae-aa7941253530 | note | RESPONSIBILITY: Fulton Hogan Engineer
7b9c0122-bf98-5f27-ad21-8dd6a2e9d6e4 | textbox | Date Completed:
c35f4885-0dae-4023-97d9-9670ad218b48 | checkpoint | 2.2 Placement of TGSI
e451b06b-80e3-5e64-866d-d0a95b8de3f8 | note | FREQUENCY: Each lot
950048ef-69fa-5fd9-8a4c-dd3814abb62c | note | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
b062d0c8-e314-58ce-8f20-4f1f8412ffbb | note | REFERENCE DOCUMENTS: IFC Drawings
9efc6c34-8a1d-5fe1-9197-ce4275ebe488 | note | INSPECTION/TEST METHOD: Visual Inspection
3738cf07-6841-5951-8eea-9d4be5b38721 | note | RECORD OF CONFORMITY: This ITP Signed off
45f51e28-79fd-5295-8ff7-f0acdc6a5963 | note | HP
ffa8df47-edbe-5a20-9cbf-d6978b1e4279 | note | RESPONSIBILITY: Fulton Hogan Engineer
89570556-9d5a-5ee3-b5bd-224faad8b52f | textbox | Date Completed:
6a2e1a0d-f638-4658-be74-499e72e3de06 | signoff | AUTHORITY HOLDPOINT
96dec8a8-14bb-4ce8-9df1-4e8c42ad2045 | section | Completion
ccbca6f6-a699-48c8-8ccb-50abe1d8359a | checkpoint | 3.1 Completion
32b60774-51ee-5a5c-a651-a08d9bc10f96 | note | FREQUENCY: Each lot
a484c6e6-e252-5dbc-a2d2-1eedbdba1204 | note | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
c1143684-1fb6-5e4a-9b4b-9e8ec8483585 | note | REFERENCE DOCUMENTS: Visual Inspection
8b05c7d2-1201-5f5a-9b12-eb27b5857770 | note | INSPECTION/TEST METHOD: Visual Inspection
53754f70-f468-5c72-948c-8c705ef26956 | note | RECORD OF CONFORMITY: This ITP Signed off
720a1024-9797-50b2-9fe8-1de7a8b71456 | note | IP
c180812f-c319-5948-a8f7-e53c1bc91f16 | note | RESPONSIBILITY: Fulton Hogan Engineer
96b810b0-8c9b-5951-b6ee-511ba37314e2 | textbox | Date Completed:
26e1b131-49a2-4063-9c69-eb4c0c17bf07 | checkpoint | Final Inspection
766913d8-3c34-5b0a-8b76-0c105a14d2a8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
28a187e4-676f-5b3d-803b-bc230a94766f | textbox | Print Name:
62018ac6-8e96-5d84-905d-f1bb82d84942 | textbox | Position:
b8bab378-1411-556c-997b-888a0321012c | textbox | Date:
49653ed8-f14d-4330-bbd7-f976e2d66a57 | checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath Rev1 | itp | ITP-036 - Kerb Access Ramp Bluestone Footpath
110e4b8a-8895-4131-8239-72a75b6dd162 | section | Preliminary Works
18567cda-2dc6-40e2-b227-852e28b523b5 | checkpoint | 1.1 Check for Correct Documentation
c50d68ec-b0cd-5a65-b638-7a2c71eb19e1 | note | FREQUENCY: Prior to Commencing Activity
c292c871-6753-50ac-9d34-0b329f1f433f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
c29d9657-c968-59f2-8086-31b3fdb735b2 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
897ef541-b01f-52b7-b783-4c7ade418dfa | note | INSPECTION/TEST METHOD: Visual Inspection
e75c67bd-4178-51da-b73a-f86ce99bdbc2 | note | RECORD OF CONFORMITY: This ITP Signed off
3cc3fc89-5443-5e1b-b722-7fe96c5279e8 | note | HP*
7a749312-adfd-500c-9ac6-2f55e8ceb026 | note | RESPONSIBILITY: Fulton Hogan Engineer
ca3053ea-bc5e-55ea-a50c-bf1ae8839dbe | textbox | Date Completed:
7d9a3b42-b7f4-49a7-b1bc-2319f02959bc | checkpoint | 1.2 Implementation of all measures and controls
452ea2da-445f-5906-bd55-ac445256cf1a | note | FREQUENCY: Prior to Commencing Activity
ae151cea-2ec3-5f2d-8d59-cd8736dfeb1e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
c15ec887-47b2-5a1e-9c15-8bfeb1284ccf | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
2a3bfa92-5e84-5ed9-a331-90fc4630a8c1 | note | INSPECTION/TEST METHOD: Inspection
8ef060bf-85c2-5a14-83f2-79fa2ebf8879 | note | RECORD OF CONFORMITY: This ITP Signed off
23300a1b-f3fe-5113-a93a-fe889fa54c9b | note | HP*
3877cc2e-85ae-5cc6-9cd2-59bfd0e71a19 | note | RESPONSIBILITY: Fulton Hogan Engineer
d6463add-0d04-504d-aad1-5c3b60f04152 | textbox | Date Completed:
5f96f5ac-082c-47a5-9354-e01b0810cecc | checkpoint | 1.3 Existing Bluestone Kerb Demolition
bc269494-cd5b-541f-b080-4eb2ad6f8e5b | note | FREQUENCY: Each Lot
b8cf299f-227d-5d66-8a7e-2e95aacdb09f | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
4a12fe27-e814-5918-8657-840bbac6e94d | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
6204d5af-f648-519c-bf5d-e29a0e4a09f1 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
22eb7462-9b06-5b35-8dcb-19d9c9ab9e8c | note | REFERENCE DOCUMENTS: Work Procedure
71a2f896-e374-5ca5-be21-13a16c7e52fc | note | INSPECTION/TEST METHOD: Inspection
efed75ff-11a4-5432-b770-fb8af3872726 | note | RECORD OF CONFORMITY: This ITP Signed off
910a025b-00e4-5150-88bd-7bc8c6f5948a | note | IP
b69a901c-147e-5fbf-a827-e149e6da45ce | note | RESPONSIBILITY: Fulton Hogan Engineer
de3d1c24-7568-5c3d-bd58-96ac2984dcee | textbox | Date Completed:
cf0bd34d-bdf0-4aaf-aa87-452a1b3cfe54 | checkpoint | 1.4 Check Materials
362fd004-5a58-56d0-b20d-61ce1a244e22 | note | FREQUENCY: Prior to Commencing Activity
980698aa-e4ff-59a4-9224-df6aab32328b | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
a8d9f493-8c32-5d30-9925-13499acf8ddb | note | REFERENCE DOCUMENTS: Receivable Inspection List
32411d0f-48e1-5d3d-bd99-743d2c4ef7a1 | note | INSPECTION/TEST METHOD: Visual Inspection
cb0ab996-6b68-5d93-a21e-bf16258c719b | note | RECORD OF CONFORMITY: This ITP Signed off
dc77e805-5ae5-54bd-8bc1-c5835ca88b59 | note | IP
5476da7a-7067-5884-b43d-5314de4e8200 | note | RESPONSIBILITY: Fulton Hogan Engineer
b241b0d7-6c5b-52c2-8e97-de85f485c609 | textbox | Date Completed:
09529bdc-7775-4fac-b094-ad64c7b337f2 | checkpoint | 1.5 Setting out
45b9faf7-77d8-5ce5-8bfb-3de092bd9966 | note | FREQUENCY: Each Lot
3bb02648-f9b8-5632-bbc0-c9743b0c01d8 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
6641d996-3b4b-5756-a35c-d42e593c0a5a | note | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
6ff17b4f-ec0f-5fd0-841f-bbb52b875a94 | note | REFERENCE DOCUMENTS: Work Procedure
c86dd5f5-1eab-5965-a315-dcb26971c95f | note | INSPECTION/TEST METHOD: Inspection
cd90a677-fe5e-5008-9a7f-a424c4132acc | note | RECORD OF CONFORMITY: This ITP Signed off
5d37b818-c02d-5923-a050-7cc18d761be2 | note | HP*
e92bf193-8255-5311-999e-c172502cb205 | note | RESPONSIBILITY: Fulton Hogan Engineer
bc8047f8-22c5-56bd-a9c9-0845abafa451 | textbox | Date Completed:
611445e9-887c-42c1-b76a-3974fabc698a | section | Construction of Access Ramp Bluestone Footpath
a2824161-8ff9-4965-8e57-ebf0035a74cd | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
b2115313-379c-5c40-b7e3-95891591d077 | note | FREQUENCY: Each Lot
d105954f-05f8-59e2-8992-f95a6a8a5735 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
71bbb412-fc3e-5cad-9435-31c39a8f115c | note | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
a93b0d32-0216-5bcc-9800-97e03f4f6d2a | note | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
d3c5754c-1074-51fd-8e67-119ba8d0b13d | note | INSPECTION/TEST METHOD: Visual Inspection
79646961-cd64-5a58-9629-ee7a5b134c7c | note | RECORD OF CONFORMITY: This ITP Signed off
2a96f6fb-7633-517d-b6a5-e3cc83cb0fe5 | note | IP
c26807ea-f743-5fd4-ace6-d63022efc128 | note | RESPONSIBILITY: Fulton Hogan Engineer
786820c1-3beb-59e1-bf45-5b2bfef9d698 | textbox | Date Completed:
37949937-e89f-41fb-94b5-bf827d106484 | checkpoint | 2.1 Base preparation
4af0ef40-f7ba-52d3-8b2e-811afe5b7835 | note | FREQUENCY: Each lot
7a317dd3-1e3e-524c-a286-a8b5050592b9 | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
39a7c460-c528-5d14-ac8d-71220164f7b6 | note | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
d651e17e-1a9f-5986-a453-8471df41875d | note | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
8d9db6e1-5780-5491-96ad-84c556ad1a1e | note | INSPECTION/TEST METHOD: Visual Inspection
bf2b6f22-1874-59cc-a18a-75765c123fac | note | RECORD OF CONFORMITY: This ITP signed off
b1e2bc9d-4813-58e5-ad05-e0ebd9e1fca4 | note | IP
de71fa6c-3899-5297-b768-4178fb067c5f | note | RESPONSIBILITY: Fulton Hogan Engineer
b7ae8d90-7a27-50ba-93c8-2b8db3d4d12f | textbox | Date Completed:
14736045-8d13-47db-ac45-bb93e255382d | checkpoint | 2.3 Mortar Bed
c46d29bc-6e02-548c-b709-c8ee9f1032d2 | note | FREQUENCY: Each lot
39651f0e-57b9-5dc5-8882-50a2c93f0897 | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
dc9d54eb-0bd1-5a7e-a8a0-7910eb632b23 | note | ○ All pavers shall be coated in mortar slurry on rear face before laying
59c911d7-e1e6-519a-a8ef-c84c5a05d385 | note | REFERENCE DOCUMENTS: Dwg 1P50201
5c91c30e-1ebe-52ea-a887-b779358b6862 | note | INSPECTION/TEST METHOD: Visual Inspection
fcf8eac5-a1ea-5263-bd22-a7e165aeac44 | note | RECORD OF CONFORMITY: This ITP Signed off
e14786cf-0f6d-587b-97aa-ea32fcd8f637 | note | IP
ae43df83-1a58-5046-bc93-b67277a78054 | note | RESPONSIBILITY: Fulton Hogan Engineer
0595e5ff-be22-5b9d-aa78-42e5b4c895f8 | textbox | Date Completed:
9abf5bfd-11b4-45d7-a554-f919c643bdae | checkpoint | 2.5 Cutting of Pavers
ae0464a7-7cf5-53cd-b187-79195b19afff | note | FREQUENCY: Each lot
828b13ea-5bc6-5ab8-a6dd-6504d00db9b8 | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
55235d3a-57be-5c6a-8b20-bedb2157afc6 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
23984cf2-8d9c-5cf5-ae5e-cd0dc365ffd0 | note | INSPECTION/TEST METHOD: Visual Inspection
3b11ab4b-ba45-5f0c-8edd-640d32d85a9f | note | RECORD OF CONFORMITY: This ITP Signed off
8c3b4304-e0e6-556d-ac6b-d3e696f06356 | note | IP
e2b8c4af-a600-5f9f-a05e-ae8706320ec3 | note | RESPONSIBILITY: Fulton Hogan Engineer
53ecbdae-586a-511e-9bcc-6057c24d0887 | textbox | Date Completed:
0b1d2a9d-5554-4460-8ef7-2011f9ffc928 | checkpoint | 2.6 Placement of bluestone pavers
a0bc6eee-9fdd-5f52-8073-d151b7899796 | note | FREQUENCY: Each lot
58001b49-2918-5293-a586-f1b7d16a9b38 | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
dc302dd8-a1f0-560f-880e-0a94a426742f | note | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
48363e80-51de-5f9a-a3cf-16df422fbea2 | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
a4a2de3b-d042-5e73-addc-1f50fdaa816e | note | INSPECTION/TEST METHOD: Visual Inspection
a4bf3423-f940-5674-8dec-1ce8447dd805 | note | RECORD OF CONFORMITY: This ITP Signed off
747fb568-2d04-51cd-8965-206a8cc71b96 | note | HP*
1ebb656d-5e00-5dd6-8f44-87f04bc828b8 | note | RESPONSIBILITY: Fulton Hogan Engineer
8285e247-a67e-5a57-8d7b-ed41b6242af3 | textbox | Date Completed:
c1127a2b-15d2-49d0-803c-5f6ec0736a1b | checkpoint | 2.7 Curing
9f86c554-ee93-54cd-a0b1-5dde8c2500bf | note | FREQUENCY: Each lot
c9749cc4-5f42-5830-adff-a201c923ee80 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
05b08b90-d25a-5073-89c5-1a82f6cd5a9c | note | ○ Where required, ply shall be laid over area of works
ee20c188-2eb5-5796-b163-8120e6acffb9 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
bcc07259-b142-55dd-89ef-007e0913db0d | note | INSPECTION/TEST METHOD: Visual Inspection
391f2d9c-844f-5bb3-9f77-4c04b12f5f9a | note | RECORD OF CONFORMITY: This ITP Signed off
d6cb210d-e2b1-59d1-a374-33e997ddde29 | note | IP
6b3e318c-cd9e-593e-8497-1277b27db604 | note | RESPONSIBILITY: Fulton Hogan Engineer
b2cd52de-2c43-5b5d-82f0-31851df84a69 | textbox | Date Completed:
d9cfb40b-1b62-48e9-9146-f5df09d1323a | checkpoint | 2.8 Grouting
82a59822-f163-5296-984f-c1a47112ef69 | note | FREQUENCY: Each lot
9253d9fd-ba00-55fa-afe5-a33119fb5e8c | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
6b32708d-ceea-591c-b31c-78b6a797b0dc | note | REFERENCE DOCUMENTS: Manufacturers Specifications
6c3dbdc1-cf2e-5b0f-8aa1-922ab667b581 | note | INSPECTION/TEST METHOD: Visual Inspection
977ba507-24d9-5b9c-80b6-76fd7bfda583 | note | RECORD OF CONFORMITY: This ITP Signed off
f52211ba-7840-5628-8ffc-e0aaa03975b9 | note | IP
b40469f0-0524-5f6d-84a7-8890b3d0e05e | note | RESPONSIBILITY: Fulton Hogan Engineer
00766d95-8e5b-5d25-b949-2071849f3cc3 | textbox | Date Completed:
5281b2fc-4f89-4510-b405-04bd1baec707 | checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
e2611695-2a87-5565-bd11-72cc98a33578 | note | FREQUENCY: Each Lot
049b52d6-df04-598e-9b74-f2f8c4d394de | note | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
e5f33505-0757-55b3-b5cb-d6b6a20790ef | note | REFERENCE DOCUMENTS: Dwg 1P50201
a57583eb-0922-5e9d-b5b9-8fcbbb0e7351 | note | INSPECTION/TEST METHOD: Verify
e39e4a08-1dfc-5d95-b68f-6cf76a646053 | note | RECORD OF CONFORMITY: This ITP Signed off
81df1a40-933f-5733-b24c-5eb14fe50181 | note | IP
8eee2c55-a2d6-50fe-8898-cda364603491 | note | RESPONSIBILITY: Fulton Hogan Engineer
0a5b2acb-2c20-5d66-87b4-d63dc01c98ea | textbox | Date Completed:
f19e7c96-23fd-4093-be52-09fe59906cd9 | section | Completion
03938fee-f43c-4c6c-8415-6ccd29a4d355 | checkpoint | 4.1 Completion
fbc581d1-9d42-584b-99ec-31496c4a94bd | note | FREQUENCY: Each lot
9b14d169-eee6-5b1a-9440-35bbc8978bb9 | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
76deb446-93e8-57f4-9c60-d6e00ab7926e | note | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
d1aa6367-8741-53de-9d50-9cef189cac76 | note | REFERENCE DOCUMENTS: Visual Inspection
580b825d-be4a-5131-b2e2-51eafa12148b | note | INSPECTION/TEST METHOD: Visual Inspection
747f66e9-1180-5b25-981d-21cca9bba35b | note | RECORD OF CONFORMITY: This ITP Signed off
dc2b2b70-41b2-574a-9df8-341fd9232898 | note | IP
21bdf8bc-79a5-55d7-a696-39b992dfc47d | note | RESPONSIBILITY: Fulton Hogan Engineer
53c2cfab-3fed-508e-80c8-39aeb40c36d7 | textbox | Date Completed:
b1c4d1c1-42f9-493a-82d5-20259e27cbb9 | checkpoint | Final Inspection
43abedcc-c31a-5dd9-95fd-596fa42dbc40 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e014a8f0-5869-50ad-926f-6c1c897a27eb | textbox | Print Name:
664d6c5d-1669-5884-854c-1c1fd4c3b597 | textbox | Position:
4064c1a8-6308-5033-a0a5-ed7687130e4b | textbox | Date: