## Table 1
|  |  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-015 Revision : 2 Date : 15/09/25
Client: |  |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  | Vic & Eliz St Stage 2 |  | Road Sign Installation |  | Name: Brandon Iredale |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Contract No: |  |  | 8B5600 |  | Specifications: VicRoads Section 714 - Sign Installation. Austalian Standard 1742 Structure / Component: Signage |  | Signed : |  | Signed : |  |  | Signed :
[5 empty] | Location: Vic and Elizabeth St |  | Date : 15/09/25 |  | Date : 15/09/25 |  |  | Date : 15/09/25
Lot No: Lot Details: Lot Size/ Quantity:
Item No. |  | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1 |  | Preliminary Works
1.1 |  | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.2 |  | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PHSCP, PCMP, EMP, ECP, QMP, SWMS | PHSCP, PCMP, EMP, ECP, QMP, SWMS | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.3 |  | Signage Conformance |  | Before commencement of activity | Ensure sign size and immage correspond with contract drawings and meets specification | Drawings AS 1742 | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.4 |  | Service Identification |  | Prior to start | Check for any services in proximity to points of installation or coring for spigots | DBYD, Service chart | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2 |  | Construction Works
2.1 |  | Setting Out |  | Prior to start | Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections. | Drawings | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 |  | Post & Foundations |  | Prior to Start | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences. | 714.06 | Visual inspection | This ITP signed off | HP | Superintendent |  |  | N/A
2.3 |  | Signage Install |  | Each Sign | Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition | AS 1742 TS 1313 Drawings | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend
HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point |  | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point |  | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point |  | Written or verbal approval given by the Superintendent