## Table 1
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-025 Revision : 01 Date : 15/09/25
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Vic & Eliz St Stage 2 |  | Structural Concrete Construction |  | Name: Brandon Iredale |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Contract No: |  | 8B5600 |  | Specifications: AS 3600-2018, VicRoads Standard Specification Section 606, 607, 610, 611, 614 Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Vic and Elizabeth St |  | Date : 15/09/25 |  | Date : 15/09/25 |  |  | Date : 15/09/25
Lot No: Lot Details: Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Approval of mix design |  | Prior to the first concrete pour | Structural Concrete Design & Submission ITP completed and signed | 610.07 | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Reinforcement schedule |  | Prior to concrete pour | Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations | 611.04 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction/Erection of Formwork
2.1 | Excavation |  | Prior to concrete pour | Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation | Contract Drawings | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Construction Methodology |  | Prior to erection | Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry | 614.04 614.06 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
3 | Pre-Pour Planning and Inspection
3.1 | Excavation/Foundation – Blinding, sealing or foundation concrete |  | Prior to concrete pour | Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent. | 602.03 | Verify | This ITP signed | HP | Fulton Hogan |  |  | N/A
3.2 | Formwork levels and position |  | Prior to concrete pour | A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete | 614.06 | Verify | This ITP signed | SCP HP* | Fulton Hogan Engineer | N/A |  | N/A
3.3 | Location of splices |  | Schedule Review | In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained. | 611.11 | Inspect | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.4 | Cleaning formwork |  | Each concrete pour | Concrete shall not be placed until all foreign material has been completely removed from the forms | 610.18 (a) (iii) | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.5 | Correct forms, reinforcements, rag bolt assembly and embedments |  | Prior to concrete pour | Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications. | 610.18 (a) | Verify | This ITP signed | HP | Fulton Hogan |  |  | N/A
3.6 | Reinforcement assembly of piles |  | Prior to concrete pour | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent. | 610.17 (b),( c), (d) | Verify | This ITP signed | HP | Fulton Hogan | N/A |  | N/A
3.7 | Monitoring weather |  | Prior to concrete pour | Concrete shall not be place when temperature is <5°C or > 35°C All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed | 610.17 (b),( c), (d) | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4 | Placing and Finishing Concrete
4.1 | Carry out sampling of concrete |  | Each concrete pour | Sampling in accordance with 610.16 | 610.16 | Checklist | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
4.2 | Discharge time |  | Each concrete pour | Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. |  | Verify | This ITP signed. Accurate Site Notes & Load Mapping | IP | Fulton Hogan | N/A |  | N/A
4.3 | Methodology of placement (structural) |  | Each concrete pour | Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials Concrete shall not be moved horizontally by vibrators In continuous pours the max. time lag between truckloads on site is 25 minutes | 610.18 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5 | Post-Pour Details and Inspection
5.1 | Curing |  | Each concrete pour | Sufficient time shall be given for the concrete to cure prior to loading. | 610.23 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5.2 | Formwork removal |  | Each concrete pour | Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation | 610.25 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
5.3 | Positional tolerance and dimensions of concrete members and piles |  | Each concrete pour | Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40) | AS3600 Cl 17.5 607.06 | Verify | This ITP signed Post Pour Checklist completed | IP | Fulton Hogan | N/A |  | N/A
5.4 | Concrete Sampling and Testing |  | Prior to lot closure | Concrete sampled and tested for Compressive Strength, and Slump. | 610.16 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
5.5 | As Built Drawings |  | Prior to lot closure | Recorded of as-built drawings | Fulton Hogan Procedure | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent