## Table 1
|  |  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-028 Revision : 01 Date : 15/09/25
Client: |  |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  | Vic & Eliz St Stage 2 |  | Fencing and Furniture Installation |  | Name: Brandon Iredale |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Contract No: |  |  | 8B5600 |  | Specifications: Yarra Trams Infrastructure - Tram Stop Platform Design Standard Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
[5 empty] | Location: Victoria and Elizabeth St |  | Date : 15/09/25 |  | Date : 15/09/25 |  |  | Date : 15/09/25
Lot No: Lot Details: Lot Size/ Quantity:
Item No. |  | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1 |  | Preliminary Works
1.1 |  | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 |  | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: EMP, SWMS & WP | EMP, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 |  | Check Materials |  | Prior to commencing any activity | •Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished •Welding shall be in accordance with AS1554 •Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000 | STD_T6000 CE-021-ST- 0012 cl 4.3.1.4 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 |  | Confirm Footings position |  | Prior to commencing any activity | •Confirm footings are set out to locations specified on design drawings | Construction Drawings | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.5 |  | Bonds |  | Prior to commencing any activity | •Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location | STD_T6000 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 |  | Construction Works
2.1 |  | Footing Installation |  | Prior to Asphalt | •Concrete shall be of minimum strength N20 •4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing | STD_T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 |  | Post Installation |  | Each Lot | •Post shall be installed to designated height and level •Installed to footings with bolt assembly •All bolts shall be insulated from base plates, using non metallic sleeves and washers •The top of fence base plate shall be level with surrounding pavement | STD_T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 |  | Grout Installation |  | Each Lot | •Footing surface shall be cleaned and roughened before application •50mm of Non shrink dry pack grout shall be placed under base plate | STD_T6002 | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.4 |  | Continuous Handrails |  | Each Lot | •5mm cap plate on handrail returns •All sections to be welded as per AS 1554 •All sharp edges and welds to be ground back to smooth finish •Domed buttons to be welded on top of handrail 150mm from the post centreline | STD_T6001 & T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.5 |  | Wire Rope Tensioners |  | Each Lot | Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock) | STD_T6000, T6001 & T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend
HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point |  | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point |  | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point |  | Written or verbal approval given by the Superintendent