## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
249f5dda-68e7-480b-bf7b-3cfaf722430a | checklist | ITP-010 - Preliminary & Civil Works - Tallarook Rev1 | itp | ITP-010 - Preliminary & Civil Works - Tallarook
ca8370eb-42ea-4dab-81ca-b274711eb60d | section | 1 - Preliminary Works
1a46a150-ef80-485b-be46-3970ff3a91a0 | checkpoint | 1.1 - Submission of Project Management Documentation
d4dedb5e-67e6-5429-b231-bb4ce46b16a4 | note | FREQUENCY: 2 weeks prior to commencement
96266570-b151-516e-baa2-cb214eb6a4f5 | note | ACCEPTANCE CRITERIA: Receival of all relevant documentation including HSMP/OHS/QMP/TMPEMP/Procedures
bda14116-cdf3-51f7-86df-a4e56d4295f6 | note | REFERENCE DOCUMENTS: Cl 160.A4 Cl 176.A3
ed11191d-0fc4-56d0-aeae-1d84a5134012 | note | INSPECTION/TEST METHOD: ITP Signed
5baa7464-777a-5528-917c-f0cea51d55df | note | RECORD OF CONFORMITY: Completed ITP
cfa9fff4-c354-5064-b675-80eba9ec4809 | note | HP
6b9d3a6f-c429-5250-9ee6-be078854c786 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
9dc54742-5f08-5dad-ac70-592a41b4a34a | date | Date Completed:
7b87f5da-1eaf-4919-8964-43be2ee7077a | signoff | AUTHORITY HOLDPOINT
1eb50727-ed7c-4b2a-86ef-0264f425a62c | checkpoint | 1.2 - Site confirmation and vegetation removal
62c4d42c-2a9b-54ed-885f-d6d16391c516 | note | FREQUENCY: Prior to commencement
d9f66d90-3c95-52cb-9862-6bb65a9a5ae8 | note | ACCEPTANCE CRITERIA: Joint site inspection to determine agreed scope of work including extent of drainage / vegetation work
77017ae2-ace1-58ec-bde3-1651088dcaa0 | note | REFERENCE DOCUMENTS: Cl 176.I1, Cl 100.5, Cl 100.10
9188f238-d39f-5b1c-bfd0-02d302a0012f | note | INSPECTION/TEST METHOD: ITP Signed
52cf22d2-656b-5b44-8d37-8a70abb943d9 | note | RECORD OF CONFORMITY: Completed ITP
cd65d4cf-c8fe-527e-a9eb-cea6d44d85ee | note | HP
d207c217-8b19-5fb9-865b-f83b450666bb | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
506b2367-3632-59fc-90c0-f93924fced62 | date | Date Completed:
6d427e5b-dbb7-48de-9270-1240af4e06b0 | signoff | AUTHORITY HOLDPOINT
71d938d7-9c8a-42de-9939-c89f4eba253a | checkpoint | 1.3 - Placement of VMS boards
1bac93b3-9266-5f36-a5ef-a7470982a306 | note | FREQUENCY: 2 weeks prior to commencement
dfc00f1d-8fbf-5f50-a2f3-6d1f9929be1c | note | ACCEPTANCE CRITERIA: Approval of installation location for VMS boards
541142c0-9d2b-5bc9-bf25-c605501eb157 | note | REFERENCE DOCUMENTS: Cl 100.11
f620f1c4-5afb-5ba7-a133-6142031bb1c5 | note | INSPECTION/TEST METHOD: ITP Signed
9cc139ca-04ba-551c-a445-0feb4be193ea | note | RECORD OF CONFORMITY: Completed ITP
e2d9fdfe-b340-54a3-b20b-d85b7aa8d70f | note | HP
0f071828-3605-527b-8681-f6f487ab1b3f | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
8475ce5e-5b42-50ec-a6a5-3c278d95387a | date | Date Completed:
f5ac70f0-61f4-4e19-aede-ad11d9bdbc05 | signoff | AUTHORITY HOLDPOINT
62ae4655-0cc5-460c-9e96-e69b15a80385 | checkpoint | 1.4 - Service location
c032c619-113d-57b2-aaa7-7768814726a9 | note | FREQUENCY: Prior to commencement
ad2ac770-3560-5397-a12d-78eb6c631868 | note | ACCEPTANCE CRITERIA: All services marked out and located on site
8dfc3dc2-21cc-5f76-9a38-2ebf7efa0808 | note | REFERENCE DOCUMENTS: Cl 100.13
8141d658-fb8b-576d-8f09-75286ae64671 | note | INSPECTION/TEST METHOD: ITP Signed
a135b8c3-a31f-57b7-a3f3-11723cabd1e5 | note | RECORD OF CONFORMITY: Completed ITP
008498a1-62fd-5eb4-911f-81e9edb9c747 | note | HP
6a2ef366-a637-5145-b2ff-f1976afd7951 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
be2584a0-4ece-52a0-a303-2802aea28d6f | date | Date Completed:
852b8a12-a638-4019-b13f-e89f28710f3f | signoff | AUTHORITY HOLDPOINT
767420c1-82df-4d4e-b2d9-3e01d0ff77c0 | checkpoint | 1.5 - Product approval
74cb427f-01f1-5e36-acae-737ba19c53d5 | note | FREQUENCY: Prior to commencing works
16e1c942-49e1-5146-b0e5-dde471c47c6b | note | ACCEPTANCE CRITERIA: Approval of products / materials
a23d2ac9-73f6-5cc6-a05f-85024eeb7767 | note | REFERENCE DOCUMENTS: Sec 663
4aceeac4-7430-578d-b259-e2a0dc9cd484 | note | INSPECTION/TEST METHOD: ITP Signed
44661014-dadd-5c5e-be0b-948883559476 | note | RECORD OF CONFORMITY: Completed ITP
85e7fa50-7770-519c-ac5c-14c2ad1cac54 | note | HP
7885c47e-eaa7-5e1b-b86a-2f33f2893ad1 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
49379379-5efd-5b59-9d44-c05ccc63453d | date | Date Completed:
a5c99a0c-3951-41d8-bc88-4319ce06c522 | signoff | AUTHORITY HOLDPOINT
3d7867cb-c4ed-4b6d-a077-6f492c2a227e | checkpoint | 1.6 - Methodology and works sequence approved
8335d076-34bd-5838-baa8-5558c83b5bfb | note | FREQUENCY: Prior to commencing works
6a6dd5d2-5db0-5db4-9b94-93f1cd209746 | note | ACCEPTANCE CRITERIA: Approval of methodology and works sequence
591751a5-62b2-5df4-9432-9d130cf37565 | note | REFERENCE DOCUMENTS: Sec 660
63ac924c-9635-54c4-98ed-987814c70366 | note | INSPECTION/TEST METHOD: ITP Signed
9d80b06e-613d-5fda-a972-a63d1b233590 | note | RECORD OF CONFORMITY: Completed ITP
7b80bf51-eec8-550b-a556-e8ed575a2819 | note | HP
d40014e4-2b26-58aa-b330-e17113d86594 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
dff94f27-4d40-5afd-9b72-9896edeed59e | date | Date Completed:
73a30eaa-ff90-496b-889c-18a8e86a85b3 | signoff | AUTHORITY HOLDPOINT
76243fa7-6d7d-4d8b-aa01-f2a11d97c502 | section | 2 - Civil Works
a1015b71-423b-4e03-a185-85d520f0d55d | checkpoint | 2.1 - Vegetation and verge removal
0e87bbdf-4c25-5f76-b12f-5c3abe099245 | note | FREQUENCY: Prior to asphalting
5ec614fb-0a8e-57ed-b5d5-40c803c466cd | note | ACCEPTANCE CRITERIA: All approved vegetation and verge stripping works completed
d35aeb94-ac4c-5f31-8abd-efd65c262cda | note | REFERENCE DOCUMENTS: Cl 100.1, Cl 204.03
5900b302-60d8-53ca-8b32-92b3dba09ca0 | note | INSPECTION/TEST METHOD: Inspection
d430c381-d1d2-5426-8c78-0bdbda7067a2 | note | RECORD OF CONFORMITY: Completed ITP
e11815f2-049e-5f73-8be5-2e33e6089c36 | note | IP
868a9397-1660-5d2a-8b95-2aa007d2d3c3 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
e1f9052f-bdae-5b70-9954-d217945129ef | date | Date Completed:
| checkpoint | 2.2 - If applicable, acceptance from Professional Engineer on bridge deck repairs in accordance with 'AST 5340 Cementitious Patch Repair of Concrete'
| note | ACCEPTANCE CRITERIA: Signoff required from a professional consultant in accordance with AST 5340
| date | Date Completed:
4fb36df5-220a-491e-a42a-bfb65935d231 | checkpoint | 2.3 - Drain clearing
b3e68f7b-48f8-5de5-9a7a-971a6b56cf3d | note | FREQUENCY: Prior to asphalting
cdf4b93c-294e-5031-979e-0f7cdb14dd4e | note | ACCEPTANCE CRITERIA: Drain cleared and reshaped appropriately
9eb398bb-7862-5f4a-94e2-610ce957678c | note | REFERENCE DOCUMENTS: Cl 100.1, Cl 700.1
f911990d-e630-5abb-a5ce-4386f5b2d9f8 | note | INSPECTION/TEST METHOD: Inspection
c499feda-166e-5c59-8e3d-6e14af4063ef | note | RECORD OF CONFORMITY: Completed ITP
40aac4d5-d488-5c06-a3d6-d6d7fa7d60a9 | note | IP
f842f3dc-199a-558c-b8ca-5dfb16659fef | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
a8a88867-4749-598d-b4ce-f6bec8651300 | date | Date Completed:
77a481b7-d484-4f2d-ac9a-c1538dd57a47 | section | 2 - Expansion Joint Demolition & Installation
13d833bb-e7ca-4387-b977-d289fa3d55b6 | checkpoint | 2.1 - Saw cutting and removal of existing nosing
2e648f0f-5215-5d76-b6db-95c8df4cb092 | note | FREQUENCY: Prior to new nosing installation
a53fba8f-c18d-5bbc-b1b4-598d1817a69b | note | ACCEPTANCE CRITERIA: Sawcutting of all existing asphalt completed and all loose material removed from existing recess and a clear base and sides present to pour new nosing. Sand / grit blasting recommended
f79de941-addb-5ad8-a115-a91eda56d88a | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
f1db3ece-d9d5-5e5f-9c53-3269c7e77c26 | note | INSPECTION/TEST METHOD: Inspection
c2af18a2-eef7-5246-908e-9ef742fd0193 | note | RECORD OF CONFORMITY: Completed ITP
051f6090-4cda-59b9-b51d-24046366a55e | note | HP*
c2d29187-e0c2-5750-bd59-83d77f57fed8 | note | RESPONSIBILITY: Project Engineer / Foreman
d8eb276e-74dd-5a3e-83ff-831b3808d9a7 | date | Date Completed:
e6f7ba91-e116-4ad3-b97f-51ec7b87efce | checkpoint | 2.2 - Preparation and pouring of nosing
7d0e90cf-85c3-5153-bb19-3bc76849b583 | note | FREQUENCY: After sawcutting / demolition works completion
e3c5e5df-0bdd-5cc9-903b-8ca5904c8216 | note | ACCEPTANCE CRITERIA: Once the recess is clear of debris, insert styrofoam gap former, mix and pour the nosing polymer as per manufactuers specification
a9d6fe64-5904-5abf-8aef-cc864e0a7e53 | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
64de54af-dfd2-5856-8c90-83477c6e6cf5 | note | INSPECTION/TEST METHOD: Approval Correspondance
6b6a5bda-dc70-5896-ba0a-618f6c401f0b | note | RECORD OF CONFORMITY: Completed ITP
86b0a42e-3c36-5665-a3f2-d27a4905380d | note | IP
fae0c2c9-dd1a-55f4-813e-686345e90c0a | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
f3173d02-0f41-5ee5-b83c-eb76662e6d82 | date | Date Completed:
4fa1eb77-5ff5-4e9e-9728-25fe9685a71c | checkpoint | 2.3 - Preparation for joint seal
8f55e734-1178-5edb-8387-40b1a93d20c0 | note | FREQUENCY: After nosing has been poured and set
93164fc4-01a5-5a91-8675-486889e3cfe3 | note | ACCEPTANCE CRITERIA: Once the polymer has cured, styrofoam filler can be removed. 5mm x 5mm chamfer to be cut into edges of nosing. Undertake further grit blasting, prime the surface and install backing rod
14cf11cd-c0d5-56e3-bd77-35f891596ab4 | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
4813d71c-6114-5523-8a24-8f820f12a6e8 | note | INSPECTION/TEST METHOD: Approval Correspondance
052ea710-d627-5840-b28c-d9df67167e63 | note | RECORD OF CONFORMITY: Completed ITP
10778258-520d-536f-af7e-ea14ba9f6357 | note | IP
4c3b8038-8eea-5f18-b212-a6aed8e5ad43 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
ccb4616b-84be-55a3-9d1f-c48c8f105bb0 | date | Date Completed:
42121e75-35c1-42cd-9d5d-f2a096a0dc9c | checkpoint | 2.4 - Pouring of silicone sealant
bc4f2ff8-f0ae-5be4-b0d9-2eb5d0d229c1 | note | FREQUENCY: After backing rod has been inserted
d594d745-0049-54dd-944a-6cb34b63384d | note | ACCEPTANCE CRITERIA: Mix and install approved sealant as per manufactuers specification, ensuring a 12mm recess below pavement level
de01b78e-0807-501c-a1b7-ecc18a7c00fa | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
f420d20a-bed2-592e-8e34-f6ce19f07782 | note | INSPECTION/TEST METHOD: Approval Correspondance
0377bfdd-da64-5544-b89d-0f574fb198d5 | note | RECORD OF CONFORMITY: Completed ITP
be38635a-e03b-587b-856a-236e9ca0a190 | note | IP
5271dac2-3cc8-5cf1-9d76-b5d1230a746e | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
f32581ea-61e4-5bb0-9216-d93827030a5b | date | Date Completed:
23bebd54-3b09-47e2-9aa1-9f5750a625ad | checkpoint | Final Inspection
235baed7-8d19-515a-94ed-3ac365bbfb14 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f50028a3-fd95-5b59-b600-49512e886094 | textbox | Print Name:
31fa033c-3a0d-507c-8ef9-9c37e7087d44 | textbox | Position:
dc010fcd-9cfd-5314-975a-f2b42fc8ad2d | date | Date: