## Table 1
[12 empty] | Form Name: |  | Inspection and Test Plan | [5 empty] | Form Ref. | QF 024
[12 empty] | Project Name: |  | Lake Terrace Rehab, Taupo | [5 empty] | Project No.
ITP No: 1 |  |  |  | Task Analysis Ref: TBC | [7 empty] | Method Statement Ref: TBC | [7 empty] | Rev. | 2025-10-09
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance.
Activity / Specification: | [11 empty] | Area Location / Work Breakdown:
Item | Material or Construction Step |  | Applicabl e Standard or Specificati on |  | Acceptance criteria and testing | [7 empty] | Verification method and responsible inspectorate for hold points | [6 empty] | Verifying Records Checklists, Test and Supplier Certificates | Certified complete
[13 empty] | Method I,W,R, H |  |  | Responsible [tick]
[9 empty] | Method | Frequency | [5 empty] | HEB | ENG. | lab
1 | Site enabling works |  | — |  | HEB to carry out Site inspection checks prior to establishment of Paving/Milling |  |  |  | — | — |  |  | I |  |  | HEB | — | — |  | B4UDIG, Dig Permit, Critical Controls
2 | Service location and piloting |  | — |  | All services within work area to be located and piloted. |  |  |  | Service located and scope of works outside of restricted area | Prior to site/Phase establishm ent |  |  | I |  |  | HEB | — | — |  | —
3 | Mix Design Approval |  | NZTA M10 |  | JMF to be approved by Engineer prior to surfacing |  |  |  | As per NZTA M10 | Once, prior to surfacing |  |  | R |  |  | HEB | — | — |  | Supplier JMF
HOLD POINT: Above signed off by Engineer prior to milling and surfacing
1 | Level Control |  | NZTA M10 TNZ M/1 |  | Matanga Projects to mark out design |  |  |  | Survey/ Stringline sheet | every after 5M |  |  | I/W |  |  | HEB | ENG. | — |  | As-Builts
|  |  | Technical Specificati on - 9.3.3 |  | heights via GPS for milling and paving
2 | Asphalt Concrete – AC20 H Grade & AC14 V Grade |  | NZTA M10:2020 |  | Temperature, Spread rate |  |  |  | Temperature Probe/Gun, Site calc for Spread rate | every site |  |  | R |  |  | HEB | — | — |  | Temp Sheet, Site Asphalt record data, NDM results
3 | AC14 PMB Production Tests (Binder & Grading) |  | NZTA M10 |  | Sampling Bituminous Paving mixtures |  |  |  | M10 – Table 5.2 | One test per 200 t of asphalt plant production |  |  | R |  |  | HEB | — | — |  | IANZ Lab Report
3 | AC20 H Grade Production Tests (Binder & Grading) |  | NZTA M10 |  | Sampling Bituminous Paving mixtures |  |  |  | M10 – Table 5.2 | One test per 600 t of asphalt plant production |  |  | R |  |  | HEB | — | — |  | IANZ Lab Report
4 | AC20 H Grade - Asphalt Compaction/De nsity Tests/Thickness |  | NZTA M10 |  | -NDM - Core testing shall be performed by a laboratory accredited to NZS ISO/IEC 17025 |  |  |  | M10 – 9.9.1 | One per Production over 30T |  |  | R |  |  | HEB | — | — |  | IANZ Lab Report
*Note – NDM to Core
[6 empty] | Correlation to be | f
provided in lieu o
cores after first 3 sets
of core results
4.1 | AC14 V Grade – Asphalt Compaction/De nsity |  | NZTA M10 |  | NDM Only |  |  |  | — | Every Shift of FWC |  |  | R |  |  | HEB | — | — |  | HEB records
This ITP has been prepared by | [5 empty] | Reviewed by [as applicable] | [8 empty] | Approved by [as applicable]
[6 empty] | Name: |  | Signature: |  |  | Date: |  |  |  | Name: |  |  |  | Signature: |  | Date:
Name: |  | Gene Scrimshaw
Signature: |  | G.Scrimshaw | [12 empty] | ITP Issued to [Superintendent / Supervisor / PE]
Date: |  | 2025-09-09