## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 | itp
section | Details
checkpoint | 1.0 - Site enabling works
label | Acceptance criteria and testing - HEB to carry out Site inspection checks prior to establishment of Paving/Milling
label | Verification method and responsible inspectorate for hold points: Method - I
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - B4UDIG, Dig Permit, Critical Controls
checkpoint | 2.0 - Service location and piloting
label | Acceptance criteria and testing - All services within work area to be located and piloted.
label | Method - Service located and scope of works outside of restricted area
label | Frequency - Prior to site/Phase establishm ent
label | Verification method and responsible inspectorate for hold points: Method - I
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
checkpoint | 3.0 - Mix Design Approval
label | Applicable Standard or Specification - NZTA M10
label | Acceptance criteria and testing - JMF to be approved by Engineer prior to surfacing
label | Method - As per NZTA M10
label | Frequency - Once, prior to surfacing
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - Supplier JMF
holdpoint | HOLD POINT: Above signed off by Engineer prior to milling and surfacing
checkpoint | 1.0 - Level Control
label | Applicable Standard or Specification - NZTA M10 TNZ M/1 Technical Specification - 9.3.3
label | Acceptance criteria and testing - Matanga Projects to mark out design heights via GPS for milling and paving
label | Method - Survey/ Stringline sheet
label | Frequency - every after 5M
label | Verification method and responsible inspectorate for hold points: Method - I/W
label | Verification method and responsible inspectorate for hold points: Responsible - HEB, ENG.
label | Verifying Records Checklists, Test and Supplier Certificates - As-Builts
checkpoint | 2.0 - Asphalt Concrete – AC20 H Grade & AC14 V Grade
label | Applicable Standard or Specification - NZTA M10:2020
label | Acceptance criteria and testing - Temperature, Spread rate
label | Method - Temperature Probe/Gun, Site calc for Spread rate
label | Frequency - every site
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - Temp Sheet, Site Asphalt record data, NDM results
checkpoint | 3.0 - AC14 PMB Production Tests (Binder & Grading)
label | Applicable Standard or Specification - NZTA M10
label | Acceptance criteria and testing - Sampling Bituminous Paving mixtures
label | Method - M10 – Table 5.2
label | Frequency - One test per 200 t of asphalt plant production
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - IANZ Lab Report
checkpoint | 3.0 - AC20 H Grade Production Tests (Binder & Grading)
label | Applicable Standard or Specification - NZTA M10
label | Acceptance criteria and testing - Sampling Bituminous Paving mixtures
label | Method - M10 – Table 5.2
label | Frequency - One test per 600 t of asphalt plant production
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - IANZ Lab Report
checkpoint | 4.0 - AC20 H Grade - Asphalt Compaction/De nsity Tests/Thickness
label | Applicable Standard or Specification - NZTA M10
label | Acceptance criteria and testing - NDM
label | — Core testing shall be performed by a laboratory accredited to NZS ISO/IEC 17025
label | *Note – NDM to Core Correlation to be provided in lieu of cores after first 3 sets of core results
label | Method - M10 – 9.9.1
label | Frequency - One per Production over 30T
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - IANZ Lab Report
checkpoint | 4.1 - AC14 V Grade – Asphalt Compaction/Density
label | Applicable Standard or Specification - NZTA M10
label | Acceptance criteria and testing - NDM Only
label | Frequency - Every Shift of FWC
label | Verification method and responsible inspectorate for hold points: Method - R
label | Verification method and responsible inspectorate for hold points: Responsible - HEB
label | Verifying Records Checklists, Test and Supplier Certificates - HEB records
checkpoint | This ITP has been prepared by
textbox | Reviewed by [as applicable]
textbox | Approved by [as applicable]
button | ITP Issued to | Superintendent,Supervisor,PE
signoff | Signature: