## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
bcf35f5f-0606-4d1f-9b10-25c81e7edb09 | checklist | QA - Civil - Retaining walls |  | QA - Civil - Retaining walls
41d1d836-a3bb-490c-89c6-ab80cf18f588 | section | Details
56550ff3-3282-4c10-87ff-945aa1c0d6b0 | checkpoint | Retaining wall(s) setout/heights confirmed
873fbec6-48e8-4166-9c59-78ac787d4be8 | checkpoint | Services Located
7135bb83-73af-4b26-bd4f-91dbf245c084 | checkpoint | Profiles set out level and rigid. Ensure boundary is encompassed within profile.
2d84e85d-db55-4d29-9a8f-469fa9aecedf | checkpoint | Finished heights are set hole spacing and pole sizes depending on retained height
868b82c5-0c0d-5b98-886c-387cf70b360e | tickbox | Excavation correct
f06adf6d-496a-51e3-b34b-1b88528e34a1 | tickbox | correct hole size
62a59c69-6cf5-5394-8e31-6c0d14954b3d | tickbox | correct pole size
037706ce-bb12-5390-bdab-e5d30297af13 | tickbox | correct depth
d1295259-afa7-56e8-879e-d4907a74b1cd | tickbox | All pile holes are inside boundary
365e57dd-3d1f-429f-ac10-75f6e6e6233b | checkpoint | General install photos and observations attached
5c3f6f04-85c4-4fd0-990b-0d34b6221d74 | checkpoint | Geotech Pre-pour Inspection
c9dcba91-6c18-41ed-9494-80ba7dbe6813 | checkpoint | Structural Engineer Inspection
778d90e7-28d7-4149-b0b3-77fc85954a1d | checkpoint | Lagging to be arissed on visible side.
828d6415-6163-4a8b-9555-ea9b3963b89a | checkpoint | Correct screws/nails used, galvanised/stainless steel etc
60da5227-dd67-475b-87d3-24b09196e85c | checkpoint | Backfill completed - correct materials and compaction methodology used
f129e806-97ff-4925-8c1a-c32eca46fe85 | checklist | QA - Concrete Surface |  | QA - Concrete Surface
5b7abdd5-d50a-4583-aa59-e13f4f10680b | section | Concrete Right of Way
330e3a59-44e2-40de-982a-9b85bdf630bc | checkpoint | Setout complete and checked
842874cf-75ca-42c0-b471-ad0b08649375 | checkpoint | Services Located and before you dig plans checked
41055ec7-7ed0-4a9f-945d-c4e5feb9e7d4 | checkpoint | Stringline set out
cabfdd83-3f6f-52f9-a9bb-ac6af1223802 | tickbox | String checked for fall
f07d495d-ff65-5d9c-8dde-86af6c934f60 | tickbox | Driveway checked for correct width
6aae2c49-233c-4391-92da-44701fb58fdb | checkpoint | Excavation correct depth
e24c1869-ffcf-41f0-b36a-294f2e481362 | checkpoint | Metal correct depth (Photos required)
344f5b7e-2c39-4f23-8909-62eff3070880 | checkpoint | Metal compacted
0932aa66-d769-46b2-a0a7-2699256ec582 | checkpoint | Lids set
2ed52f27-f5c9-45b3-a565-94f5068adef6 | checkpoint | Steel placed
73eb0bd0-8584-4a90-8b1b-98e45b1b80f0 | checkpoint | Engineer Inspection
cb85dc3c-b154-4a69-8232-23a7a3bf7080 | checkpoint | Boxing stripped
1adc0c49-fd2f-4b60-84dd-a6ad93652326 | checkpoint | Topsoil placed (if required)
634d86c5-338b-4d36-bfa5-c383bd131a80 | checklist | QA - Detailed Excavation |  | QA - Detailed Excavation
1ac83e63-37b6-469b-aec2-543548c6b4d7 | section | Details
6f1582dc-6296-4774-8871-123b372598fe | checkpoint | Services Located
2d4b1fc3-6a34-4461-878a-d398fb5960d7 | checkpoint | Location accurate
d5ff8f8a-d829-47a7-91ea-e8f967c294df | checkpoint | Topsoil stripped completely
3fc88ce4-b951-4cb1-852b-744aef37790e | checkpoint | Building pads set out correctly with RLs as required for cut/fill
c0880d2a-eb75-4253-b7ae-2d8d2e7defc9 | checkpoint | Correct cut back for walls/foundations
c1017b27-0125-4779-b0de-06351e87a786 | checkpoint | Geotech Engineer Inspection
af914a66-b167-4c1b-8bd8-bff16c14ce5b | checkpoint | Detailed excavation completed, reviewed and approved
ba32c889-f798-49e3-b279-09fc4cf01be9 | checklist | QA - Drainage - Manhole Install Checklist |  | QA - Drainage - Manhole Install Checklist
77f4bd9b-835d-4f1e-832e-dc7dc7cb768e | section | Manhole Install
25e20c89-39ac-461f-9cd4-4aac941e02a2 | checkpoint | Latest consented drawings
4e361725-7f91-5985-aa67-f28434c640f8 | textbox | Drawing Ref No.
d57ad29e-99a1-4bdf-86c3-5057abef9370 | checkpoint | Setout an manhole sizing checked
676a2584-c306-4242-a5aa-7b3f2d4e678b | checkpoint | Services Located and before you dig plans checked
5037f12a-8d12-4ff9-b18e-a765fc9f31d5 | checkpoint | MHS measured onsite. Prep height determined from Lid Level.
2d616cb6-efa5-5421-b10d-0bf514e6a666 | textbox | Lid Level RL
6c62bd12-5886-53da-9fd3-021a0a699d7b | tickbox | Lid level confirmed as correct
88d0b2f4-528a-5eb0-b54b-cde2f6ff30bc | textbox | Manhole System allow 50mm play
9bb6122d-687e-526e-b686-c841aea43ba1 | textbox | Prep height RL
e8d8790c-475e-5f29-9a1e-f235be51085c | textbox | Outlet RL
fbad716e-6f3f-557a-a074-8a1f5e8dd3a0 | tickbox | Outlet RL is 200mm greater than Prep height RL
d765c4c8-6935-55f7-9a5d-d8c34705e07f | tickbox | Throat height checked to be less than 450mm
10a436a7-7b96-5e15-8a7e-11fae9fd1be7 | tickbox | Concrete lid will be underneath future works
5c7eb749-5325-4280-80f1-d8cb5544f2be | checkpoint | Benching/shield required if >1.5m
b543c165-44ad-496e-8efc-893eb57f6420 | checkpoint | Ground conditions checked & acceptable
24db27f5-a7bc-414a-ba12-277cb022c960 | checkpoint | Bedding depth and material correct & compacted (Photo Required)
241cb051-b4ff-48fc-8991-5a87a5c2ac05 | checkpoint | Cut in Manhole Shearbands ( Photos required)
1ebdd2ac-bb14-4753-819a-a8d3753e190e | checkpoint | Manhole Risers epoxyed (if applicable Photo required)
5f9ac062-674f-42ce-a464-40682ccf8a42 | checkpoint | Inside of starters epoxyed all the way around
e7a939ff-e697-41bd-945b-8c66aadfc7d3 | checkpoint | Manhole benching completed and acceptable (Photo required)
1f5b2273-3fac-4273-bac6-35c771b33f7d | checkpoint | Concrete Lid Installed, Correct orientation and sealed
55a96942-8b8d-4dc3-a676-51ed061942a8 | checkpoint | Cast Iron Lid Raised and Installed at 90 degrees to steps
656a4461-b501-4b68-bd30-57f926fffb25 | checkpoint | Epoxy completed inside lid and
7fe84ec1-ab1e-447d-b28d-8395ee09b5d5 | checkpoint | Stormwater lids to be spray painted blue
295e87bb-7bff-4136-869c-d04a7674e302 | checkpoint | Sewer manhole safety grille installed
215efdef-6456-47f4-98a4-86fb5da96e33 | checklist | QA - Pipeline Installation Checklist |  | QA - Pipeline Installation Checklist
8eb18e86-5066-4842-a8bf-1171395a2b49 | section | Pipe Laying
092eb983-0463-46c0-852b-4e118c63b1a5 | checkpoint | Latest consented drawings
116ec4ef-17ff-5962-a74c-05b10e0f144c | textbox | Drawing Ref No.
60c3f781-f357-48c6-9e6a-95e0cbcf335d | checkpoint | Setout completed checked and accurate
05195a11-d08c-444e-922c-5397b759c833 | checkpoint | Services Located and before you dig plans checked
a6a6a012-ba22-4cb0-9f3a-ded964bff0f6 | checkpoint | All junctions marked out and run through with operator
1960341b-6f34-443a-bf08-aad272cfb404 | checkpoint | Laser grade checked. Correct +/-. Benching required if >1.5m
bce04ea4-8194-5adc-b608-3c90024712cd | textbox | Design Grade %
e4381571-a445-42de-affe-39dd5e0e1188 | checkpoint | Laser checked for line with string line
318b6bad-2f08-44a4-b5bd-99c911e7ee4f | checkpoint | Correct trench width for pipe size
230b2c53-e1b8-4887-a9ca-706619c7798a | checkpoint | Starter checked for fall. Starter epoxyed to seal from water.
fccd2afa-e5af-4b05-b9c4-1b92f7ddc771 | checkpoint | Corbel installed with suitable bedding around pipe (Photo Required)
34530865-d9e8-4080-9044-02d015d90902 | checkpoint | Ground Conditions Checked & Acceptable
7a741e04-cc00-47d0-a6df-edf2b09016d6 | signoff | HOLD POINT
91922209-0227-4aef-96b2-2126514d0919 | checkpoint | General photos during pipe laying
3e8445bd-80b7-4196-8985-5b8903513559 | checkpoint | Pipe Laying Completed
cfbbffa9-ea91-5480-8ee8-c3701c758a0e | textbox | Laid by
ed0c3316-da4b-52d6-8c60-53e9a7670dcb | tickbox | Trench Compacted
fb6b9509-1e80-5b7d-9ac2-9972799962e2 | tickbox | Vehicle Areas or Road Reserve Hard Filled
008ef149-2b4d-4250-b0ce-4c4bfd6f9332 | signoff | HOLD POINT
7d3f18a0-ecd8-4218-b8ac-32cae0057ff6 | checkpoint | CCTV Completed
38bc92e9-910d-4275-8be7-de48fffa34c5 | checklist | QA - Sewer Junction |  | QA - Sewer Junction
6f9bb0f1-bb1e-4963-9690-3490bb7814be | section | Sewer Junction
ddfb5473-7353-4ca9-9ccd-908db1794577 | checkpoint | Correct Junction SN16 Y Junction or SN16 Z Junction
2902cfe6-8040-4503-8a63-544076d7f66f | checkpoint | Target Checked on Junction
2412b3d2-ffc6-46e2-94e7-65b88339b817 | checkpoint | Fall Checked with level
27a8b27b-fa37-4067-8303-2d577772d6ce | checkpoint | Angle of Junction between 30 and 60 degrees (Photo Required)
357b0801-fde5-4bfb-ae2d-2331b0d7d4cd | checkpoint | Junction Pegged and Sprayed Red
f17ed6af-943a-4ca1-be4a-267686945665 | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
5da1ac80-4db4-4183-b4ba-0caa52a6aa74 | checklist | QA - Stormwater Concrete Junction |  | QA - Stormwater Concrete Junction
f8fbf8bc-9a21-4d7e-93fd-81bfc3956eb9 | section | Stormwater Concrete Junction
25492d4b-d8fb-4555-95fd-9f651ea3d983 | checkpoint | Correct sized junction
cfdabbe5-e30f-4569-952f-9ce352dbf4fd | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
e5bab760-6675-4b04-a4ca-036e267880aa | checkpoint | Expoxy inside and out
28facb2e-16b7-42f8-a6db-9eb50cea5524 | checkpoint | Shear band connection (Photo required)
3d025223-4d8f-4ffe-9668-a6d80f77cbaf | checkpoint | Junction Pegged and Sprayed Blue
e1ed8050-b769-46b6-9da4-2d592a14ce27 | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
470eec69-a926-4606-8118-9b4033e90b16 | checklist | QA - Stormwater PVC Junction |  | QA - Stormwater PVC Junction
6a2b6e16-3968-4307-b022-019a0a3e831d | section | Stormwater PVC Junction
c28d8b74-c5f7-4708-9976-1587d9cc4ff0 | checkpoint | Correct Junction SN16 London Junction or SN16 Y Junction
a7ad74d4-9b3e-46cb-b567-e3f99eedffe7 | checkpoint | Target Checked on Junction
985090db-5433-4d4c-83c3-8f299dc6e9f9 | checkpoint | Fall Checked with level
632347d6-5cc1-4173-8216-0bff2b5d9640 | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
f9cf69dc-980f-4475-8341-7d94d2ed0827 | checkpoint | Junction Pegged and Sprayed Blue
3f3ef59b-bacb-4fe4-a84b-ad9dd73e4b8e | checkpoint | Inspection straight if connecting to private drainage (Photo Required)