## Sheet1
1.1 | If the work is under a consent, has the pre-commencement meeting with the relative council been completed and approval to start works issued? | HP |  | 1.1 - If the work is under a consent, has the pre-commencement meeting with the relative council been completed and approval to start works issued? | Inspection Type - HP | Comments - | 1.1 - If the work is under a consent, has the pre-commencement meeting with the relative council been completed and approval to start works issued?
1.2 | Has the site Geotech report been reviewed to identify soil types and ground water level? | IP |  | 1.2 - Has the site Geotech report been reviewed to identify soil types and ground water level? | Inspection Type - IP | Comments - | Inspection Type - HP
1.3 | Has the trenching and installation methodology been confirmed to cater for the ground conditions? | IP |  | 1.3 - Has the trenching and installation methodology been confirmed to cater for the ground conditions? | Inspection Type - IP | Comments - | Comments -
1.4 | Is the SSSP been witnessed by the client | WP |  | 1.4 - Is the SSSP been witnessed by the client | Inspection Type - WP | Comments - | 1.2 - Has the site Geotech report been reviewed to identify soil types and ground water level?
1.5 | Has the JSEA been completed and witnessed? | WP |  | 1.5 - Has the JSEA been completed and witnessed? | Inspection Type - WP | Comments - | Inspection Type - IP
1.6 | Have the IFC drawings been issued | HP |  | 1.6 - Have the IFC drawings been issued | Inspection Type - HP | Comments - | Comments -
1.7 | Send all IFC drawings and design files to the surveyor for site set-out requirements | HP |  | 1.7 - Send all IFC drawings and design files to the surveyor for site set-out requirements | Inspection Type - HP | Comments - | 1.3 - Has the trenching and installation methodology been confirmed to cater for the ground conditions?
2.1 | Site is set-up and work area is fenced off before excavations start | IP | Attach Photos | 2.1 - Site is set-up and work area is fenced off before excavations start | Inspection Type - IP | Comments - Attach Photos | Inspection Type - IP
2.2 | Check service plans for any underground assets that may come in contact with trenching operations and all plans are on site. | HP | Attach Photos | 2.2 - Check service plans for any underground assets that may come in contact with trenching operations and all plans are on site. | Inspection Type - HP | Comments - Attach Photos | Comments -
2.3 | Are there any services within your excavation area? | IP | Attach Photos | 2.3 - Are there any services within your excavation area? | Inspection Type - IP | Comments - Attach Photos | 1.4 - Is the SSSP been witnessed by the client
2.4 | If 'Yes' to the above; have the services been marked out and located? | IP | Attach Photos | 2.4 - If 'Yes' to the above; have the services been marked out and located? | Inspection Type - IP | Comments - Attach Photos | Inspection Type - WP
2.5 | If there is a high-value or high-risk service (Power/Gas/Stategic Fibre), has the asset been located by hand digging or hydrovac excavation? | HP | Attach Photos | 2.5 - If there is a high-value or high-risk service (Power/Gas/Stategic Fibre), has the asset been located by hand digging or hydrovac excavation? | Inspection Type - HP | Comments - Attach Photos | Comments -
2.6 | Have all required materials been delivered to site and inspected for damage prior to installation? | IP | Attach Photos | 2.6 - Have all required materials been delivered to site and inspected for damage prior to installation? | Inspection Type - IP | Comments - Attach Photos | 1.5 - Has the JSEA been completed and witnessed?
2.7 | Has survey set-out been completed? | IP | Attach Photos | 2.7 - Has survey set-out been completed? | Inspection Type - IP | Comments - Attach Photos | Inspection Type - WP
2.8 | Have all persons involved in the work been inducted onto the site? | IP | Attach Photos | 2.8 - Have all persons involved in the work been inducted onto the site? | Inspection Type - IP | Comments - Attach Photos | Comments -
2.9 | Has the JSEA been signed by all persons involved in the works? | IP | Attach Photos | 2.9 - Has the JSEA been signed by all persons involved in the works? | Inspection Type - IP | Comments - Attach Photos | 1.6 - Have the IFC drawings been issued
2.1 | Has all plant and machinery been established to site? | IP | Attach Photos | 2.1 - Has all plant and machinery been established to site? | Inspection Type - IP | Comments - Attach Photos | Inspection Type - HP
2.11 | Have all pre-start checks been completed on the plant and machinery being used for the job? | IP | Attach Photos | 2.11 - Have all pre-start checks been completed on the plant and machinery being used for the job? | Inspection Type - IP | Comments - Attach Photos | Comments -
3.1 | Excavation completed to line and level as per survey set-out | IP | Attach Photos | 3.1 - Excavation completed to line and level as per survey set-out | Inspection Type - IP | Comments - Attach Photos | 1.7 - Send all IFC drawings and design files to the surveyor for site set-out requirements
3.2 | Ground conditions checked and subgrade tested to ensure competent substrate before laying. Soft sports to be raised with PM for further instruction. | HP | Attach scala sheet | 3.2 - Ground conditions checked and subgrade tested to ensure competent substrate before laying. Soft sports to be raised with PM for further instruction. | Inspection Type - HP | Comments - Attach scala sheet | Inspection Type - HP
3.3 | If required, complete undercut as per engineers' instruction and take photos. | IP | Attach Photos | 3.3 - If required, complete undercut as per engineers' instruction and take photos. | Inspection Type - IP | Comments - Attach Photos | Comments -
3.4 | Place and compact granular foundation as per drawings | IP | Attach Photos | 3.4 - Place and compact granular foundation as per drawings | Inspection Type - IP | Comments - Attach Photos | 2.1 - Site is set-up and work area is fenced off before excavations start
4.1 | Install MH structure to the line and level as indicated by the design making allowances for benching thickness and internal inverts. | IP | Attach Photos | 4.1 - Install MH structure to the line and level as indicated by the design making allowances for benching thickness and internal inverts. | Inspection Type - IP | Comments - Attach Photos | Inspection Type - IP
4.2 | Make pipe connections to manhole to line and invert level detailed on the approved drawings and record as-built invert levels. | IP | Attach Photos and record invert levels | 4.2 - Make pipe connections to manhole to line and invert level detailed on the approved drawings and record as-built invert levels. | Inspection Type - IP | Comments - Attach Photos and record invert levels | Comments - Attach Photos
4.3 | Remove burs on cut pipe |  |  | 4.3 - Remove burs on cut pipe | Inspection Type - | Comments - | 2.2 - Check service plans for any underground assets that may come in contact with trenching operations and all plans are on site.
4.4 | Complete concrete corbel connections to outside of MH on all main connections | IP | Attach Photos | 4.4 - Complete concrete corbel connections to outside of MH on all main connections | Inspection Type - IP | Comments - Attach Photos | Inspection Type - HP
4.5 | Form concrete benching inside manhole and ensure that benching is not flatter than 1 in 3 and haunching of intersecting pipes provide curved channel to ensure streamlined flow. | IP | Attach Photos | 4.5 - Form concrete benching inside manhole and ensure that benching is not flatter than 1 in 3 and haunching of intersecting pipes provide curved channel to ensure streamlined flow. | Inspection Type - IP | Comments - Attach Photos | Comments - Attach Photos
4.6 | Install stainless steel manhole safety steps and epoxy the back of the bolts and around the base of the step penetrations. | IP | Attach Photos | 4.6 - Install stainless steel manhole safety steps and epoxy the back of the bolts and around the base of the step penetrations. | Inspection Type - IP | Comments - Attach Photos | 2.3 - Are there any services within your excavation area?
4.7 | Install MH riser rigns, additional steps, mahole sealing strip and seal each riser with epoxy on both sides of the manhole riser joint. | IP | Attach Photos | 4.7 - Install MH riser rigns, additional steps, mahole sealing strip and seal each riser with epoxy on both sides of the manhole riser joint. | Inspection Type - IP | Comments - Attach Photos | Inspection Type - IP
4.8 | Leak test manhole and confirm that the structure of the manhole is not leaking. | IP | Attach Photos Record leak test results and attach | 4.8 - Leak test manhole and confirm that the structure of the manhole is not leaking. | Inspection Type - IP | Comments - Attach Photos Record leak test results and attach | Comments - Attach Photos
4.9 | Backfill manhole excavation and compact in layers and test | IP | Attach Photos CHAR(AMP) Scala Sheet | 4.9 - Backfill manhole excavation and compact in layers and test | Inspection Type - IP | Comments - Attach Photos CHAR(AMP) Scala Sheet | 2.4 - If 'Yes' to the above; have the services been marked out and located?
4.1 | Install concrete manhole lid and casting | IP | Attach Photos | 4.1 - Install concrete manhole lid and casting | Inspection Type - IP | Comments - Attach Photos | Inspection Type - IP
4.11 | Once pavement layers have been placed to height, raise steel castings and throats to height and check throat depth is no more than 350mm. |  |  | 4.11 - Once pavement layers have been placed to height, raise steel castings and throats to height and check throat depth is no more than 350mm. | Inspection Type - | Comments - | Comments - Attach Photos
4.12 | Once pavement has been constructed and all vibratory activities completed; complete all sealing work around manhole lid with expoxy | IP | Attach Photos | 4.12 - Once pavement has been constructed and all vibratory activities completed; complete all sealing work around manhole lid with expoxy | Inspection Type - IP | Comments - Attach Photos | 2.5 - If there is a high-value or high-risk service (Power/Gas/Stategic Fibre), has the asset been located by hand digging or hydrovac excavation?
4.13 | Complete all internal plastering work and expoxy sealing on the benching, pipe penetrations and riser rings to ensure that the manhole is leak proof. | IP | Attach Photos | 4.13 - Complete all internal plastering work and expoxy sealing on the benching, pipe penetrations and riser rings to ensure that the manhole is leak proof. | Inspection Type - IP | Comments - Attach Photos | Inspection Type - HP
4.14 | Install bungs on all pipe inlets and outlets and perform preliminary leak test on manhole. | IP | Attach Photos Record leak test results and attach | 4.14 - Install bungs on all pipe inlets and outlets and perform preliminary leak test on manhole. | Inspection Type - IP | Comments - Attach Photos Record leak test results and attach | Comments - Attach Photos
4.15 | Complete leak test under witness from a council inspection engineer. | WP | Attach Photos Record leak test results and attach | 4.15 - Complete leak test under witness from a council inspection engineer. | Inspection Type - WP | Comments - Attach Photos Record leak test results and attach | 2.6 - Have all required materials been delivered to site and inspected for damage prior to installation?
4.16 | Paint steel casting 'white' as per TCC requirements | IP | Attach Photos | 4.16 - Paint steel casting 'white' as per TCC requirements | Inspection Type - IP | Comments - Attach Photos | Inspection Type - IP
4.17 | Complete final visual inspection with Engineer CHAR(AMP) Council Inspector | WP | Attach Photos | 4.17 - Complete final visual inspection with Engineer CHAR(AMP) Council Inspector | Inspection Type - WP | Comments - Attach Photos | Comments - Attach Photos
4.18 | Complete as-builts and submit to engineer | IP | Submit electronic as-built | 4.18 - Complete as-builts and submit to engineer | Inspection Type - IP | Comments - Submit electronic as-built | 2.7 - Has survey set-out been completed?
4.19 | If connecting to existing line; complete council connection application form and have the responsible drainlayer sign the form | HP | Submit completed form to the engineer | 4.19 - If connecting to existing line; complete council connection application form and have the responsible drainlayer sign the form | Inspection Type - HP | Comments - Submit completed form to the engineer | Inspection Type - IP
Comments - Attach Photos
2.8 - Have all persons involved in the work been inducted onto the site?
Inspection Type - IP
Comments - Attach Photos
2.9 - Has the JSEA been signed by all persons involved in the works?
Inspection Type - IP
Comments - Attach Photos
2.1 - Has all plant and machinery been established to site?
Inspection Type - IP
Comments - Attach Photos
2.11 - Have all pre-start checks been completed on the plant and machinery being used for the job?
Inspection Type - IP
Comments - Attach Photos
3.1 - Excavation completed to line and level as per survey set-out
Inspection Type - IP
Comments - Attach Photos
3.2 - Ground conditions checked and subgrade tested to ensure competent substrate before laying. Soft sports to be raised with PM for further instruction.
Inspection Type - HP
Comments - Attach scala sheet
3.3 - If required, complete undercut as per engineers' instruction and take photos.
Inspection Type - IP
Comments - Attach Photos
3.4 - Place and compact granular foundation as per drawings
Inspection Type - IP
Comments - Attach Photos
4.1 - Install MH structure to the line and level as indicated by the design making allowances for benching thickness and internal inverts.
Inspection Type - IP
Comments - Attach Photos
4.2 - Make pipe connections to manhole to line and invert level detailed on the approved drawings and record as-built invert levels.
Inspection Type - IP
Comments - Attach Photos and record invert levels
4.3 - Remove burs on cut pipe
Inspection Type -
Comments -
4.4 - Complete concrete corbel connections to outside of MH on all main connections
Inspection Type - IP
Comments - Attach Photos
4.5 - Form concrete benching inside manhole and ensure that benching is not flatter than 1 in 3 and haunching of intersecting pipes provide curved channel to ensure streamlined flow.
Inspection Type - IP
Comments - Attach Photos
4.6 - Install stainless steel manhole safety steps and epoxy the back of the bolts and around the base of the step penetrations.
Inspection Type - IP
Comments - Attach Photos
4.7 - Install MH riser rigns, additional steps, mahole sealing strip and seal each riser with epoxy on both sides of the manhole riser joint.
Inspection Type - IP
Comments - Attach Photos
4.8 - Leak test manhole and confirm that the structure of the manhole is not leaking.
Inspection Type - IP
Comments - Attach Photos Record leak test results and attach
4.9 - Backfill manhole excavation and compact in layers and test
Inspection Type - IP
Comments - Attach Photos CHAR(AMP) Scala Sheet
4.1 - Install concrete manhole lid and casting
Inspection Type - IP
Comments - Attach Photos
4.11 - Once pavement layers have been placed to height, raise steel castings and throats to height and check throat depth is no more than 350mm.
Inspection Type -
Comments -
4.12 - Once pavement has been constructed and all vibratory activities completed; complete all sealing work around manhole lid with expoxy
Inspection Type - IP
Comments - Attach Photos
4.13 - Complete all internal plastering work and expoxy sealing on the benching, pipe penetrations and riser rings to ensure that the manhole is leak proof.
Inspection Type - IP
Comments - Attach Photos
4.14 - Install bungs on all pipe inlets and outlets and perform preliminary leak test on manhole.
Inspection Type - IP
Comments - Attach Photos Record leak test results and attach
4.15 - Complete leak test under witness from a council inspection engineer.
Inspection Type - WP
Comments - Attach Photos Record leak test results and attach
4.16 - Paint steel casting 'white' as per TCC requirements
Inspection Type - IP
Comments - Attach Photos
4.17 - Complete final visual inspection with Engineer CHAR(AMP) Council Inspector
Inspection Type - WP
Comments - Attach Photos
4.18 - Complete as-builts and submit to engineer
Inspection Type - IP
Comments - Submit electronic as-built
4.19 - If connecting to existing line; complete council connection application form and have the responsible drainlayer sign the form
Inspection Type - HP
Comments - Submit completed form to the engineer