## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7d2d3d1b-a1ef-4d0c-885f-9bb63d575e90 | checklist | ITP - Paharakeke - Stage 4 Rev 1 | itp | ITP - Paharakeke - Stage 4
597101fe-561b-4c8a-940c-3f8a4c854bc2 | section | 1 - Site Safety & Traffic Management
543f44d2-f024-47c6-828f-9561738c549d | checkpoint | Safety Plan (1)
8d091727-f4dc-5e56-a21e-105e00a47358 | note | Frequency - Prior to works starting
18769719-0a88-58a7-a2af-feabd535e243 | note | Inspection / Test Method - Engineer to review Contractor's Plan
f04ce529-2ce7-5855-b4ae-c2abef7fd62e | note | Acceptance Criteria - Meets contract requirements
ead0bd13-3ecc-560a-b3ab-c06b8ccda89b | note | Verifying Documents - NTC acknowledging Safety Plan
23747cf5-65e4-587f-8ccd-7251b1e39c98 | note | Engineer / Client - H
b035ba1e-551b-418a-873a-8badc0663e54 | signoff | HOLD POINT
02078962-9d2e-4785-95d6-fa1ca80f07b4 | checkpoint | Safety Plan (2)
177db21c-32b4-5297-889f-83339e373e79 | note | Frequency - Daily
9d2eda95-eef2-537e-ac97-59a8fac63894 | note | Inspection / Test Method - Compliance monitored by the Contractor
ecc791d9-39d3-58fa-ba61-86bc99d6aad3 | note | Acceptance Criteria - Site Safety Plan is updated to reflect changes in the work place. Excavations are protected.
c04c8ab1-84fd-5d39-8863-7e7c63d7b771 | note | ○ Site Safety requirements are met.
270a7bf8-76e9-55bf-af44-ddcfee866a6e | note | ○ Pedestrian access is clearly defined and signage is in place. Accident reports have been completed.
681e3c07-f554-51cc-bddc-50028b6d6f39 | note | ○ Compliance report is completed.
fd16d9bc-7ad6-590a-96b4-712cc10f1a6c | note | Verifying Documents - Included in weekly report
fd8c64a0-03fe-44e1-b256-4bcc925759b5 | checkpoint | Traffic Management Plan (1)
35a6c709-592a-5d9c-89e1-051331596ace | note | Frequency - Prior to works starting
8f5f6460-ac2c-5ff8-896a-9d4a7146258a | note | Inspection / Test Method - Contractors TMP to be approved by the RCA (Road Controlling Authority) and a copy provided to the Engineer.
873e9b6e-6ea0-5aaf-9b09-c0d7acc273aa | note | Acceptance Criteria - Meets contract requirements
4ff17241-1f57-50e4-9f88-00b057b7df62 | note | Verifying Documents - NTC acknowledging Traffic Management Plan
631ab6a7-26ed-52b9-8536-5d28f69edf1f | note | Engineer / Client - H
218f4be1-94ab-49f7-8a7a-4070d1356ed4 | signoff | HOLD POINT
ed9351b7-e317-404e-8670-2fd9170941f5 | checkpoint | Traffic Management Plan (2)
5ff29b12-a1df-5db7-8688-2997b81a3f92 | note | Frequency - Daily
cc219488-dfed-5e59-84ff-eca53dfe5cb6 | note | Inspection / Test Method - Compliance monitored by the Contractor
17a33048-2159-52d6-8f0f-87d7052b450b | note | Acceptance Criteria - Traffic Management Plan is updated to reflect changes in work. Signage and devices are clean and set out appropriately.
bd75db89-cab9-576e-8956-9d3ade4ed6d1 | note | ○ Detour and single lane requirements have been met. Compliance report is completed.
8124b682-5c5a-50e7-b3fe-6c4bee81f5c7 | note | Verifying Documents - Included in weekly report
7986f884-4a4d-4414-987b-08f502814a8a | section | 2 - Quality Assurance & As-Built Information
9cc84b3a-995e-4b48-ab6a-4d90758ccb3a | checkpoint | Quality Plan
e66a4b5d-5cf6-56aa-b101-c7f2ff215273 | note | Frequency - Prior to works starting
414dc1dd-afab-5089-a793-fd775d14c103 | note | Inspection / Test Method - Engineer to review Contractor's Plan
005d9e2e-0d06-5d32-acdc-cdab2966046e | note | Acceptance Criteria - Meets contract requirements
06a3de2d-f6a4-5425-b115-de8ea2b7ebd8 | note | Verifying Documents - NTC acknowledging Quality Plan
62b43781-1376-5ce3-b448-7f9b16858895 | note | Engineer / Client - H
8806d523-1503-48f3-b2b8-c0f24f88e782 | signoff | HOLD POINT
96287ad9-4da7-403c-a6e8-8bb2432fba6f | checkpoint | Setting Out
38b423bf-2d69-5f52-96e5-a2d065fb9646 | note | Frequency - As works progress
e525bbb4-89ba-5770-98dd-51b784f12c2a | note | Inspection / Test Method - Survey control report
e0baa2ce-d9f3-52ea-90e5-c16a102e1cf2 | note | Acceptance Criteria - Meets construction tolerances
d7672d69-dd46-5bad-971b-d295d51d765c | note | Verifying Documents - Survey control report
8776071e-02bb-4c3a-b914-a35fa87bd2b2 | checkpoint | Construction
3cb85b6f-285e-5e42-ab52-e0cdaf9e656e | note | Frequency - Weekly
e2bbb0f3-df17-5e6a-bd39-a951b5caf1e6 | note | Inspection / Test Method - Progress report
ad6383de-0421-5d7f-b948-726a34002ff0 | note | Acceptance Criteria - Meets programme
8fb6a92a-aa61-530d-86c1-81c8c0656199 | note | Verifying Documents - Included in weekly report
f06d1df9-7471-40ac-ac44-36c293b503ae | checkpoint | Traffic Management
8036b1a0-b74e-54ac-abe0-c42282dd7744 | note | Frequency - Weekly
84314bcd-9f20-5afe-bbee-77721c56f7cf | note | Inspection / Test Method - Monitoring report
12273023-88fd-50ce-a235-561ad3ee51af | note | Acceptance Criteria - Safe traffic management
75959b9a-328a-524d-823e-183878e5fb64 | note | Verifying Documents - Included in weekly report
c3bcc66e-bc1e-40d2-b1ed-7dc9ea13081f | checkpoint | Site Safety
389ff9c7-c8e1-56c0-adc0-e168614e3012 | note | Frequency - Weekly
453efba1-376f-5004-9d15-917ee0db9326 | note | Inspection / Test Method - Monitoring report
933bce69-3424-5a15-84f3-c61b17f74019 | note | Acceptance Criteria - Safe site
30d0a084-8d2a-5a12-b02b-cb62576e6173 | note | Verifying Documents - Included in weekly report
7ed9e95b-f9db-4cf0-a490-445f0d05b479 | checkpoint | Water works
99155822-6c4b-5fc9-800c-e1f821005883 | note | Frequency - As works progress and on completion
d51dcad1-a009-5783-a76f-84037f781ab1 | note | Inspection / Test Method - Construction reports
dee0214b-8ef6-503d-bd91-1e93f9183b39 | note | Acceptance Criteria - Meets contract requirements
371ea685-5b5e-5592-a4e8-bdb1d0713b1f | note | Verifying Documents - Included in weekly report
b3355bad-d338-4e3f-8fef-71f96dd4492c | checkpoint | Stormwater works
8eed9208-f7cb-573c-83f7-19ad6e1b81dc | note | Frequency - As works progress and on completion
93d09031-839f-5501-91d4-f440c16ab98e | note | Inspection / Test Method - Construction reports
65fc2bb6-573f-5029-915c-7d10786919d3 | note | Acceptance Criteria - Meets contract requirements
64db1bf3-dee0-5c4f-b9ec-e91e4248d885 | note | Verifying Documents - Included in weekly report
eb08b342-5cb1-4192-abff-76a0ad535b5d | checkpoint | Sewer works
ad2a1dea-f982-54e9-b8e5-c74104c6742e | note | Frequency - As works progress and on completion
cb6aeee2-d183-58d6-aaa9-23cf86e5e1ec | note | Inspection / Test Method - Construction reports
f620ba31-2901-5033-9265-c37de0cd1706 | note | Acceptance Criteria - Meets contract requirements
3a99a32d-2911-583b-8663-1e8bb2dc9289 | note | Verifying Documents - Included in weekly report
fe531c8d-e427-48dd-bc8a-6a8edba8f696 | checkpoint | Earth works (1)
aef832d2-fc7e-516c-ae94-9aa53636b3f9 | note | Frequency - Prior to earthworks
0971e10f-a3ec-5ea1-a350-fbd00b68ff3d | note | Inspection / Test Method - Manhole inspection
3e31b890-6a7f-57bb-91aa-037bdf3d8164 | note | Acceptance Criteria - Temporary floors kept in place
1eb70682-5d4a-582a-8f99-ed8425b2354c | note | Verifying Documents - Visual inspection
6cfa5148-ad17-44e8-9689-5c28da7f6746 | checkpoint | Earth works (2)
53dbf641-78fe-5beb-8dc9-9b8a816ebf9d | note | Inspection / Test Method - Service cover location
d9125299-1e79-5508-a70c-656a668a4b51 | note | Acceptance Criteria - Lids marked and kept clear for use
b92390c1-ad43-5bd8-8e79-432ec8813ef7 | note | Verifying Documents - Visual inspection
a193b856-3ce5-4eac-bd41-040bc8bfaf1e | checkpoint | Earth works (3)
097f9879-6706-5c02-81e2-22d9bd6b7afb | note | Frequency - Prior to sub-base construction
914a5b82-4a73-5614-9109-bf0ce931ea72 | note | Inspection / Test Method - Construction reports
c7e30a85-f1d0-5c90-82d1-0ad0c2b9731f | note | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
14821574-fd44-58eb-b00d-4ea2e5e5f2a8 | note | Verifying Documents - Included in weekly report and visual inspection
d19b1d9b-871b-4d68-9449-58ddf553dd2f | checkpoint | Sub-base works
068b6f9f-acc4-59aa-8e06-27a3a925d111 | note | Frequency - Prior to top course construction
7afc0cb2-1bb0-5875-b2fa-57e58d21d79a | note | Inspection / Test Method - Construction reports
a8445120-4903-5ea4-a530-a9acedab3e2a | note | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
f5a716ac-1d4b-5440-8821-d7acae6d4a6e | note | Verifying Documents - Included in weekly report and visual inspection
281d1b66-ba63-4aab-8fcc-2b564ba3c9e7 | checkpoint | Basecourse works
ff2b7a67-8570-5c9f-91a0-4199f0a668aa | note | Frequency - Prior to sealing or construction of kerbing and paths
a61e1a35-ddc0-5ba5-8857-81feb05dd3f6 | note | Inspection / Test Method - Construction reports
06105f31-3ff2-5358-9a52-c16438439b7a | note | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
37540039-949c-5c22-982e-434708a1851a | note | Verifying Documents - Included in weekly report and visual inspection
3b484bf5-35fc-45f7-814a-7a6b4a6c7f85 | checkpoint | Sealing works (1)
e94087cb-d76b-5164-b62f-f04819536158 | note | Frequency - Material tests and seal design prior to sealing. Seal reports on completion
f0280b1c-c659-5e31-81e4-77cb462c8c10 | note | Inspection / Test Method - Construction reports
b3e29a0a-2220-5ed6-b66d-babafbf36e06 | note | Acceptance Criteria - Meets construction tolerances Services covers exposed and marked. Service boxes clean and fit for use
6bc78cec-8c12-5446-964e-cce7e487d88a | note | Verifying Documents - NTE including material tests and seal design
5c289f71-0d1f-480a-8dcd-ab36b4f6e579 | checkpoint | Sealing works (2)
e3ac7f05-3908-5aca-8cd6-a8f7849bbf90 | note | Frequency - On completion of sealing
8f38f83a-faa5-561e-85de-fd9711ccb4c3 | note | Inspection / Test Method - Inspection of service lids and covers
b4d76fa9-5bcf-5a5a-943a-abd4ee87a179 | note | Acceptance Criteria - Temporary floors removed from all manholes
34d1c34a-d3ec-593a-850d-3ef6916c08dc | note | Verifying Documents - Visual inspection
b720c06c-0b22-4bcd-bd02-2868fc685c77 | checkpoint | Footpath, berm, kerbing and traffic island works
18aa1007-00eb-56a4-9881-57c5f0f5ce3a | note | Frequency - As works progress
e651d5ca-d5d0-51f4-9ace-e11696da5046 | note | Inspection / Test Method - Construction reports
37c732ce-0110-5b3c-95df-873d19f5ce38 | note | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
e0e3743c-029e-5462-8eea-f065ed31ee5b | note | Verifying Documents - Included in weekly report and visual inspection
99b6bc0a-fb19-4328-a464-502c0425ffdf | checkpoint | Water works
e87a01fb-b25e-59e0-b7f3-748757117521 | note | Frequency - As works progress
cb2822d4-8364-56f5-ba85-111d05aad42d | note | Inspection / Test Method - Construction reports
247e3300-5d03-5786-b990-18f37bb8ba44 | note | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked, Service boxes clean and fit for use.
1e0d1e56-a4c8-52f2-bbeb-81c5673820d0 | note | Verifying Documents - Included in weekly report and visual inspection
5d1be857-257f-4150-9dcc-3e791cd072b5 | checkpoint | Sewer works
24050260-7245-574c-9a62-7e7f1e38673f | note | Frequency - As works progress
73ac2d2d-36c2-5fd7-982a-f9f6a9651a4b | note | Inspection / Test Method - Construction reports
3e634419-f98f-4076-ab36-be101128da4b | checkpoint | Stormwater works
b8f6ada8-ee88-5f58-8dd4-cbfeaa45880f | note | Frequency - As works progress
d6797b2c-b751-55cd-889b-4f5d6953c030 | note | Inspection / Test Method - Construction reports
b06fb3c1-71bd-44e6-8a90-1a180ad5036e | checkpoint | As built information
94c3a51d-9765-5d72-99ef-b32c1c06239a | note | Frequency - Completion of works Condition of Practical Completion
f5b120ec-05a7-5d9e-8e03-0d6202856890 | note | Inspection / Test Method - Levels and coordinates of nominated features in terms of datum and construction drawings.
4e235ad8-a8e2-5b12-b3c7-39d355c91aad | note | ○ RAMM data sheets.
de8cd4a8-59f3-5d3e-aec2-ef0b4f5ea36e | note | Acceptance Criteria - Horizontal +/- 50mm Vertical +/- 5mm
b0dc7f33-2fc8-52f4-8950-fad22b39bba1 | note | Verifying Documents - NTE with asbuilts in PDF and DWG
3ec39d77-f6ea-5576-97ce-7c2df1aeebc3 | note | Engineer / Client - H (Required for issue of PC)
79994e83-3b3e-484d-9224-f303847568d1 | signoff | HOLD POINT
b290c464-0620-43b0-ba9f-f4309356a6f0 | section | 3 - Environmental Management
9341b09c-e4ed-4daf-a3d3-cc1559849d4d | checkpoint | Environmental Management Plan
d0495a62-c2f9-5ac7-9299-9bf0dad3f437 | note | Frequency - Prior to works starting
5a2d8494-727d-57d5-9d9c-a6858024c2ea | note | Inspection / Test Method - Engineer to review Contractor's Plan
f33c0d16-fe5d-5c43-9ee6-d3700ecacb90 | note | Acceptance Criteria - Meets contract requirements
1c2d3adf-12d2-5ef0-8122-f0012e03c37b | note | Verifying Documents - NTC acknowledging Environmental Management Plan
78a45753-4704-5dbe-8e30-1e003fdf1367 | note | Engineer / Client - H
0cc91218-626e-49a1-8013-bd98e8c245a3 | signoff | HOLD POINT
e5238fad-2c96-438e-bc79-77b0961db566 | checkpoint | Contractor’s Resource consents
54d7e70a-2308-5c69-97ab-076b60479a05 | note | Frequency - Regular monitoring during contract
8e509b07-f074-5811-b32c-6d857b0fd62c | note | Inspection / Test Method - Contractor to review and test
cdf8caf5-772b-5ed5-be39-82cff0c4adf3 | note | Acceptance Criteria - Meets consent requirements
850a6a43-d731-525e-b92d-1447e021687f | note | Verifying Documents - Test records supplied on request
766428ef-8227-46ca-9005-dd8567964cc2 | checkpoint | Principal’s Resource consents
fb06c730-fd18-5bcc-96c5-047f9aa214ed | note | Frequency - Regular monitoring during contract
611def21-4655-5db5-8f6a-b050c0c738a4 | note | Inspection / Test Method - Engineer to review and audit
f7dc1d94-2bef-5b9b-af70-5d5ee0da144f | note | Acceptance Criteria - Meets consent requirements
f57a1c29-a946-48f8-93ea-96070bd0c3e3 | checkpoint | Environmental risks
983c981d-0d95-50fc-8868-19223046fac3 | note | Frequency - Regular monitoring during contract
fefda2cb-adce-57ea-93f5-d8dfb81ab622 | note | Inspection / Test Method - Contractor to review and test
c3464cff-a097-5109-a824-e59eb3993ad8 | note | Acceptance Criteria - Risks identified with mitigation measures in place and implemented
8f9edfcf-8a9c-5caa-817f-c6db0698e6d7 | note | Verifying Documents - Included in weekly report
f41f78bb-f85c-4701-9be8-a7d5f4c219dd | checkpoint | Water run off
d0621387-8135-5abc-a863-0244060da44b | note | Frequency - Daily discharge checks
50a412dc-1884-5cd8-8239-e02c5f3c352a | note | Inspection / Test Method - Visual
3bb09ef3-fbf7-5f5a-9474-dd4971c1221e | note | Acceptance Criteria - Silt traps in place with clear discharge down-stream to drainage systems
739e7a12-c4de-5289-9608-01ec0e3d1700 | note | Verifying Documents - Visual inspection
38ac4c40-505f-49da-ab90-349b916e67a2 | checkpoint | Dust and noise
2fca6f4b-e841-5a1b-a910-f7c24d108165 | note | Frequency - Daily nuisance and dust checkA
fa170dc8-f493-5985-92e2-192a540cf909 | note | Inspection / Test Method - udio and visual
6af1944d-6b41-5d12-af80-8dd2ef2f9ab7 | note | Acceptance Criteria - Site observance with mitigation of dust and noise nuisance
07228e82-c817-5782-ae9f-a66520b695f2 | note | Verifying Documents - Visual inspection
755ba8e3-40ba-4a99-b5ab-46e1a8f78492 | checkpoint | Fuel and oil spills
0abaa10a-a17d-5214-abc8-dbd9910235e4 | note | Frequency - Daily
e56df5af-8429-50a7-8725-172979bff837 | note | Inspection / Test Method - Visual
534e8312-47a9-53b5-9c2e-022c5ead9662 | note | Acceptance Criteria - Site observance with spill mitigation measures in place and implemented
aa074834-6161-5fd2-a8e3-3875ff30d4d5 | note | Verifying Documents - Visual inspection
e4d8b75b-003f-4887-9ee4-436b0d95ab09 | checkpoint | Concrete and seal cutting
11375ec3-8aaf-56bc-a0aa-1fd83f11bc4c | note | Frequency - Daily
20b5a21e-0837-552a-891b-ed33215faf11 | note | Inspection / Test Method - Visual
a947de94-7abf-5d01-830d-92acea3c9f13 | note | Acceptance Criteria - Contaminate traps in place with clear discharge down-stream to drainage systems
8296690c-f11e-5860-9e25-277d8132380c | note | Verifying Documents - Visual inspection
d915dc93-1c3e-4fd2-be65-d69b25d89710 | section | 4 - Pipe Trenches
53e2bb78-7c2e-496b-827b-9c911ba9cfd1 | checkpoint | Qualifications of Personnel
5fe58a9b-8330-5c34-9f7d-adbbbdd78c10 | note | Activity Description - Refer to Specification F100 Preliminary and General
6b09fa12-a8a5-5a55-bf76-a3b0144b76be | note | Frequency - Contract Start
03395a9d-0bb5-5c5a-a2a5-4f144338e64d | note | Acceptance Criteria - Evidence of Qualification and personnel on-site.
21424757-355c-5b1a-b9fa-7b81e2dc605c | note | Verifying Documents - Provide evidence where not previously provided or personnel change
72f4b4d2-33a1-559a-834a-5dd04c9fca7d | note | Engineer / Client - H
3b4360ad-54a5-4b58-a928-3566f5c78e2e | signoff | HOLD POINT
3b568ead-482a-4a8d-b3a6-367e27a5055f | checkpoint-no-value | Materials - Refer Section 2
53d86913-5bb1-450b-83ba-ed810186f931 | checkpoint | Selected fill
9b591827-5e65-5d18-91ad-1105881b88d7 | note | Activity Description - Grading, sand. Equivalent, CBR
2b4b0d57-3747-5590-af5f-4b23d776b144 | note | Inspection / Test Method - Lab testing
0915dc8d-41a4-5273-ab55-2f467533ce33 | note | Acceptance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
91f609ef-9fb2-52f4-89a4-ac58e4a68811 | note | Verifying Documents - Lab results to be supplied to Engineer
6b2a2728-2f81-5c4e-94d7-915284b919c4 | note | Engineer / Client - H
9c5223de-b16a-4df2-9740-438095b91404 | signoff | HOLD POINT
4ca9f8a7-2c51-42e7-8273-15144ea7161d | checkpoint-no-value | Ground conditions
6c13ad55-42f4-4d01-ae6d-4a4fc07b7126 | checkpoint | Firm formation level
16759b9e-3e37-504d-9d31-3ddc695de4d7 | note | Activity Description - Bearing capacity of base
c01ebcf6-e976-5327-9748-527e25cd5ed9 | note | Inspection / Test Method - Inspection
002e8aa3-8a61-5d47-b6a6-a236d4d513bd | note | Acceptance Criteria - Bearing greater than 50 kPa
c00fecad-953f-54ee-9d89-dc6f1f6d9dbc | note | Verifying Documents - Inspection records available for review
96ca65cd-04c3-4ee1-90a9-9430dfdbc16b | checkpoint-no-value | Tolerances - Refer Section 3.8.3
216ff18b-8e34-49f4-85ac-c01b589f3e34 | checkpoint | Trench excavation (1)
c994b156-07ab-5989-a6b0-ff2fe602ed38 | note | Activity Description - Minimum to maximum range of trench width
2ec8ddbf-2a6d-5051-94f7-3fac83bf8fc0 | note | Inspection / Test Method - Survey
da6e3510-8832-5a24-91d5-3767ca8db34b | note | Acceptance Criteria - Tolerance range as per section 3.9.3
39ce7df2-88a1-5bf0-bbb1-dca326aac097 | note | Verifying Documents - Visual inspection and measurement on site
3d1320a2-4a7a-4361-8beb-9823530d60a3 | checkpoint | Trench excavation (2)
b12bc8c8-b777-5580-ac55-44cffff69e13 | note | Activity Description - Side slope of trench wall
7750edac-e3c2-534b-b3f7-c8b92a3e8970 | note | Inspection / Test Method - Survey
2c342a98-ea76-5fc8-ba37-b467db1e0436 | note | Acceptance Criteria - Near vertical
efccb91c-9792-5b10-86f3-cde9887c989b | note | Verifying Documents - Visual inspection
80804933-8f39-4a4a-a5e9-b184918c94bd | checkpoint-no-value | Inspection and Testing - Refer Section 3.10
4d750e69-5a87-41ee-a724-236b4fd4cb9a | section | 5 - Retaining Walls
ecdfa7b2-c5a8-4233-96fc-d18165d5237c | checkpoint-no-value | Methodology
0e9cd2bf-cf2d-4423-ad76-43c512e4904c | checkpoint | Review of Retaining wall construction methodology
eef3a273-f1f1-5db4-934a-39c842812c9d | note | Activity Description - Engineer to comment where required, on the proposed construction methodology and review aborist assessment. Refer to drawing DRG-WA-21802 (C02)
5c2c5997-bd25-5096-b774-1f837c8986b6 | note | Inspection / Test Method - Engineers review
3c941f83-ba06-50f6-9523-85194d052984 | note | Acceptance Criteria - Engineers acceptance
8ce09836-a33e-5017-852b-793e064b85e4 | note | Verifying Documents - Approved CMP
4d2fa38b-8584-5064-99ff-2160a7b047b4 | note | Engineer / Client - H
2dcb5399-ddd1-4e35-9cfb-283fdfdb8618 | signoff | HOLD POINT
81e0d640-81da-4e17-b999-0386ad3c5cb0 | checkpoint-no-value | Materials
c5dd7246-21be-4fe2-81bd-50fd4088a1a2 | checkpoint | Review Contractors supply of materials and QA documentation
1c46e02c-50b9-562a-9696-129e7770c9d5 | note | Activity Description - Engineers rep to review QA documentation for timber piles, timber lagging, concrete and drainage backfill. Refer to drawing DRG-WA-21802 (C02)
09a248c9-79ee-53b9-9384-bfd04413e818 | note | Frequency - 10 days prior to beginning work
7a36b466-a6af-5ee3-8865-7bd42772c78b | note | Inspection / Test Method - Engineers review
f85edfbf-8d31-5459-8504-fcfed5b22cae | note | Acceptance Criteria - Engineers acceptance
e4a9e31a-8258-549d-af30-1db8bb9ac1ce | note | Verifying Documents - Provide evidence of material spec.
b74d3da9-f292-54c9-b611-40b9d288badf | note | Engineer / Client - H
7cd1ebe3-484c-4203-bfd6-a85b70b0f155 | signoff | HOLD POINT
ba0e467c-78cf-4577-8601-74dce70f3907 | checkpoint | Confirmation / approval of any alternative materials
a2ffcce2-13f7-54e2-b99f-de9d38995b54 | note | Activity Description - Engineers rep to confirm acceptance of any alternative materials requested by Contractor. Refer to drawing DRG-WA-21802 (C02)
38d240ab-d0cc-5ad0-9261-c0ad753e2a27 | note | Frequency - 10 days prior to beginning work
f323aa0e-93c0-5281-bb8f-284665fd554b | note | Inspection / Test Method - Engineers review
bbba4d05-b29b-5a0f-9b15-dcf15dec049d | note | Acceptance Criteria - Engineers acceptance
b19cd13d-be06-5b47-b526-fcc7682f91d6 | note | Verifying Documents - Provide specs of any alternative materials
cebee1a1-1711-529c-b037-37108e320e9c | note | Engineer / Client - H
034f48f3-03b0-4000-bf7c-e5a6f77151b7 | signoff | HOLD POINT
e365d321-e9d1-4412-ae3b-e3b2b6740c8c | checkpoint-no-value | Setout
76dac771-5ce8-43b4-aa5f-e08364c2b28b | checkpoint | Site visit to approve set out of retaining wall
76c2de7c-cf41-536e-bda4-ca4c99070c8a | note | Activity Description - Engineers rep to provide site inspection report sheet with photos of set out and description of site conditions encountered and any issues relating to design. Contractor to provide survey data co- ordinates for set out of four piles at pipe crossing location. DRG- WA-21802 (C02)
b7d0d1bd-f8a6-5da3-8a63-5ea41c732ddb | note | Frequency - Once, after excavation to founding level and following survey set out
59510ba3-c3be-579f-b944-0950e89425ae | note | Inspection / Test Method - Survey
4fa1a3b8-8a08-508f-8eb9-93b1439d1368 | note | Acceptance Criteria - Engineers acceptance
56633076-5dfb-5942-8efa-bd3372d38819 | note | Verifying Documents - Site Report sheets
bd09c346-b3b3-5eae-8062-7f600f752fcc | note | Engineer / Client - H
eab3992d-1776-4cf5-b3b6-1a69a1973927 | signoff | HOLD POINT
1056103b-a487-4750-a2e8-ad15144c2501 | checkpoint-no-value | Piling
ecb9daef-a28e-4773-8498-7e01e61a15f8 | checkpoint | Inspection of augered pile holes
e4424d5b-04ca-59be-8d43-fc285a8aade5 | note | Activity Description - Engineers rep to witness installation of first two piles for each retaining wall and provide site visit report sheet detiling materials encountered, drill rate and any problems encountered and how they were resolved. Contractor shall record a pile log for all installed piles. This shall record the depth of hole, material encountered, comments on drill rate, if water was encountered and any temporary measures such as if pile casings were used, or any other issues that occured and how these were resolved. DRG-WA-21802 (C02)
7cbe6e87-abc3-5bc1-aff3-1a89527818d3 | note | Frequency - Once, after installation of first two piles on each side.
c7616c23-113b-5ab3-92ea-0610220833f2 | note | Inspection / Test Method - Engineers inspection
61de6f6f-e786-5379-aa49-b6374d29dcc8 | note | Acceptance Criteria - Engineers acceptance
5409ef6a-c4a0-5211-9e13-229957945bc1 | note | Verifying Documents - Site Report sheets
0690d1d3-54aa-5596-9374-1be415df915c | note | Engineer / Client - H
6d467fb5-d43c-49ca-908c-ace41efcf286 | signoff | HOLD POINT
28698b87-b3b7-4003-9b07-4d2d3589fafa | checkpoint-no-value | DN375 Stormwater
a650e76f-a3c6-47d3-9365-5df21467cfb9 | checkpoint | Inspection of DN375mm Stormwater pipe outlet
488ae737-26df-5f87-a657-6777287be926 | note | Activity Description - Contractor to provide photos of the pipe outlet location showing construction process of lagging and drainage material around the pipe. DRG-WA-21802 (C02)
d13b7078-23a9-5a8d-93fc-c1b147052160 | note | Frequency - Throughout pipe outlet construction
005d0de8-b187-5de9-9888-27305ff05e01 | note | Inspection / Test Method - Photos (Contractor)
d0ad5961-caf5-5f57-b6f4-7dfc6b2bc46e | note | Acceptance Criteria - Engineers acceptance (based on photos)
3555adba-7a11-539d-85da-3bd12de94485 | note | Verifying Documents - Photos
92482f0d-db1d-5825-95e4-3474cad1724b | note | Engineer / Client - H
4e7f265e-d33c-4bd0-bf7e-e5bcb7c1f9dc | signoff | HOLD POINT
7e4dbb16-fe4c-45e0-b351-c0bf776f8a06 | checkpoint-no-value | Retaining Walls
0d69ffa0-f67c-4c23-a3b4-94460c210a19 | checkpoint | Inspection of retaining wall at OD813 wastewater pipe crossing location
bff6a52b-0c8d-56b0-8965-8502ac71c9bd | note | Activity Description - Engineers rep to inspect pipe crossing location at each retaining wall prior to any drainage backfill being placed above the pipe. Engineers rep to provide site report sheet summarising inspection. DRG-WA-21802 (C02)
c05b5f7c-e2c6-56e4-9fae-bf1a138a01d3 | note | Frequency - Once, following installation of steel pipe crossing
13e95c20-b6d9-5d66-8a9b-a12a09d3e976 | note | Inspection / Test Method - Engineers inspection
f2d46587-49f5-5498-841c-547bfcc7a0da | note | Acceptance Criteria - Engineers acceptance
25a655e2-7c2e-5332-b045-a113fb52d4d2 | note | Verifying Documents - Site Report sheets
6331a082-37a4-57db-b0dc-8d12ce775fc9 | note | Engineer / Client - H
a33d0c4b-fbee-421d-ae9e-2e7a0188967e | signoff | HOLD POINT
bf63f391-351b-4efd-ba39-36757a7e4c8e | checkpoint | Inspection of lagging at 50% completion.
4657593c-903b-5627-8582-acecb2ade36b | note | Activity Description - Engineers rep to inspect lagging at 50% complete and summarise inspection in site report sheet. DRG-WA-21802
7c822ce6-9f6e-5407-8b18-fce51c15dfbb | note | Frequency - Once following installation of lagging to 50% height
bcd044b0-624a-562c-bfce-ac343f7e3407 | note | Inspection / Test Method - Engineers inspection
246c656c-176e-5c6a-94ee-7ac387b3cc2b | note | Acceptance Criteria - Engineers acceptance
3c24ead2-0c52-574f-aef6-961c048ae125 | note | Verifying Documents - Site Report sheets
7820c396-e25f-5261-80ad-5ca8ad8f6a2d | note | Engineer / Client - H
435f53ee-3e84-47e6-a983-a5c519c9b44d | signoff | HOLD POINT
f58ead3c-90f2-41c2-8634-fe6858a15470 | checkpoint | Inspection of drainage installation and determining subsoil outlet location
cc162e2f-7ca3-5673-8b0d-93961c7341c5 | note | Activity Description - Engineers rep to inspect drainage backfill and determine the location of the subsoil drain outlet for each wall. Engineers rep to provide site report sheet summarising inspection. DRG-WA- 21802 (C02)
1f53c7fb-ec30-50e4-8d39-f21587029fe4 | note | Frequency - Once, following drainage backfill for each wall
190c2d41-d170-5532-90c2-dcff2f6bf946 | note | Inspection / Test Method - Engineers inspection
33d587fb-3cd8-5eb6-be17-0e161f40315a | note | Acceptance Criteria - Engineers acceptance
3f0530fc-3ccb-57da-8b07-0177d1f86a96 | note | Verifying Documents - Site Report sheets
9c3fb4ed-cb0d-5b4f-aeec-687313f526ec | note | Engineer / Client - H
2bb8da9f-4eb6-4d6c-935b-18047bd74a82 | signoff | HOLD POINT
bc367b6c-b8a8-4796-9791-e33bad98eb4f | checkpoint | Final finished surface of site to be inspected
37f0b936-0bb0-52c6-88de-40f463b8b522 | note | Activity Description - Engineers rep to conduct final inspection of retaining walls and provide photos with site report sheet. DRG-WA-21802 (C02)
766be8d0-9b82-52ec-8e4e-1288243c5f4b | note | Frequency - Following retaining wall construction and all reinstatement works
70b63d2d-e318-5d83-a98b-8cabebcae2b3 | note | Inspection / Test Method - Engineers inspection
cc96ed2a-b00b-5a0e-9929-109dfba2c68d | note | Acceptance Criteria - Engineers acceptance
d6f46efc-31f1-58aa-aa5d-f7f959da8a22 | note | Verifying Documents - Site Report sheets
5d65c076-fb38-56ca-8f0b-772aa71f645a | note | Engineer / Client - H
48b21a3c-49a8-40c2-abfd-f425f5eddcc4 | signoff | HOLD POINT
5b798a5a-7e48-427d-b3fb-9e73d335452d | section | 6 - Gravity Pipelines
52731ea2-1c9d-44e5-955b-0557224d9321 | checkpoint | Qualifications of Personnel
cced81dc-52ba-50de-a3b5-d68c4aacf08c | note | Activity Description - Refer to Specification F100 Preliminary and General
ca9bc033-a2dc-5124-84ba-203461eb60e8 | note | Frequency - Contract Start
417f6f37-6f08-5193-ad69-7c55157cbb95 | note | Verifying Documents - Provide evidence where not previously provided or personnel change
9a3b0983-8747-58f4-a734-154a71e56d48 | note | Engineer / Client - H
c4f942eb-9ba0-4669-adc2-0165bd5144a2 | signoff | HOLD POINT
be6c766b-9b6c-41ba-b8e4-8586b974e2b4 | checkpoint-no-value | Materials - Refer Section 2
a12366df-b903-4eda-81bc-8ff9920b93e4 | checkpoint | Embedment Material
17d0d993-d9bf-5a67-98c9-a4159a6f4d3e | note | Activity Description - Grading
f09654e1-b7d6-5294-9e73-4d2e545c878a | note | Frequency - Contract Start
0b596c64-9f78-5f30-a7ed-6bff516bbd89 | note | Inspection / Test Method - Lab testing
f1cab953-46fd-5058-b0fa-f1c7487cae58 | note | Acceptance Criteria - Comply with grading specification
7e6054dc-cc27-5fbf-a86f-214eba46595c | note | Verifying Documents - Test results to be provided
4d2c98a5-1f7f-5d19-9181-890917456cf4 | note | Engineer / Client - H
59878d63-7dc5-4f12-b624-25adc7a84c7b | signoff | HOLD POINT
3bf43fd5-2c2a-42fd-b574-3bf5e11aa809 | checkpoint | Material Acceptance
280a8f78-aa10-5ad4-ae33-6ac1fcb92085 | note | Activity Description - Pipes and fittings
f4a18a90-260b-5e8a-bee8-4ec7de4020c5 | note | Frequency - Prior to use
4b6f04d4-c0fc-5092-8073-1c8bf2dae406 | note | Inspection / Test Method - Inspection
a6ef3176-c378-5d95-a7d7-c5076e8ad6cc | note | Acceptance Criteria - Comply with Section 3 AS/NZS2566.2
50864738-0446-5023-825d-d0b2f6c5f14c | note | Verifying Documents - Visual inspection
75c91924-848d-4ba1-a8e9-b1045bbf2fd3 | checkpoint-no-value | Bedding, Laying, Jointing and Manholes - Refer Section 3.3
d6bead91-5830-4dfb-8087-6346f8175aed | checkpoint | Pipe Jointing (1)
a79541fd-4cfc-51f9-a877-43444053966e | note | Activity Description - Clean and Dry
692baf44-3628-5b3d-8d7f-074f657aba63 | note | Frequency - During Jointing
8df9cb6b-aade-5903-a485-64410447a0ca | note | Inspection / Test Method - Inspection
e94ec86a-6643-58b4-a952-538cdfee263a | note | Acceptance Criteria - Workspace and materials clean and dry
3a829f7a-d562-5138-913c-a014774bfadc | note | Verifying Documents - Visual inspection
658e117b-746e-4b70-adc5-170cc9bd5d28 | checkpoint | Pipe Jointing (2)
287183bf-bcc5-58e9-b8e0-eeb920e46354 | note | Activity Description - Completed Joints
dfa17a8b-d181-5609-8ff2-b847568561b1 | note | Frequency - At completion of jointing
abb35650-a2e2-5476-89e3-a6fd3545d04e | note | Inspection / Test Method - Inspection
cc109cc2-25a9-5ed0-b56f-5895f64f329d | note | Acceptance Criteria - All fittings snug and firm no movement or leakage to Manufacturers' requirements
95879177-1be5-5ce2-87b7-7f8f59a9724d | note | Verifying Documents - Visual inspection
ede7bde2-9952-42cd-9e23-5333004044fa | checkpoint | Joints at Manholes and other fittings
7420d8a3-3aa5-50ef-b07e-acf098199d91 | note | Activity Description - Spacing and type of joint
85eea99c-fdff-5e59-a56f-862a762fabc1 | note | Frequency - Prior to Backfill around Manhole
b4af5cd0-93e5-5060-9c63-52d25a604863 | note | Inspection / Test Method - Inspection
99b52685-d286-528a-bfcf-60357bef3a53 | note | Acceptance Criteria - Comply with drawings
d24b0120-b626-5748-ba15-541b7f54fb33 | note | Verifying Documents - Visual inspection
051a4af0-1116-46a4-b002-6ac69c3409de | checkpoint | Manhole Benching
425ce5fc-32ef-5363-a123-23565e351ac4 | note | Activity Description - Finish
973a6a0f-a7c9-5993-a9e8-d2486d162472 | note | Frequency - At completion of manhole
895a7871-0bcc-53ea-a5e4-a7a999c92ad9 | note | Inspection / Test Method - Inspection
2c2da1b9-8256-5631-a420-9f4858c61f19 | note | Acceptance Criteria - Smooth and minimum turbulence
6596f1e0-90ab-524d-b62e-1df9b323d58c | note | Verifying Documents - Visual inspection
0ba9592e-d335-4a96-b231-4e8f06f18df2 | checkpoint-no-value | Tolerances - Refer Section 3.5
1a276030-0309-4a8b-887d-b0a558a8ac24 | checkpoint | Horizontal Tolerances
cc57e73d-21df-56e4-876e-970cf5818776 | note | Activity Description - Manholes and Structures
8a25d555-983d-5e33-8c5d-b76137895ce6 | note | Frequency - Set-out and Installation
e1a5f341-3e9b-5fa2-bf11-26d81bcccee7 | note | Inspection / Test Method - Survey
1dd3bb15-95d4-53f2-9195-8e1435836fcc | note | Acceptance Criteria - +/ – 100mm of design or where applicable +/ – 50mm of design
549a8ab3-4cba-5e22-9ed4-3c452ff06a21 | note | Verifying Documents - Asbuilts except where re- design is necessary
ea3e6219-97de-4f0a-b18e-3c599635a8a8 | checkpoint | Vertical Tolerances (1)
5f33303c-137b-5dce-b74c-3bd787a4c90b | note | Activity Description - Invert Level
b40c4827-e8ee-577f-b1e7-cb44abada494 | note | Frequency - Set-out and Installation
9e5c5ef1-5955-584c-a33f-ad457adcb0b0 | note | Inspection / Test Method - Survey
12458723-c01c-5347-ad0b-5bad8c42992a | note | Acceptance Criteria - +/ – 25mm of design level
60074593-fbb7-53cc-844c-c8c322ec87a1 | note | Verifying Documents - Asbuilts except where re-design is necessary
0966650d-04e5-4460-a97e-e6e1d8d5fa30 | checkpoint | Vertical Tolerances (2)
25795ccc-d1d3-5ab6-84b8-e100766c1851 | note | Activity Description - Pipe Grade
d081bd65-985f-53b9-8d52-91617d675a26 | note | Frequency - Set-out and Installation
8c02b0b7-fe3f-5a7d-a0d7-89b095e7d0fc | note | Inspection / Test Method - Survey
249fb39d-02dd-503f-b864-c18baf1a7098 | note | Acceptance Criteria - +/– 10%
64feb4a0-c206-582c-b127-d6ac6db36ea7 | note | Verifying Documents - Asbuilts except where re- design is necessary
8cd72661-21a8-4987-a9eb-828b7d508d21 | checkpoint | Verticality
2efc2dc1-26d5-5a1b-aa0c-5aa803997ceb | note | Activity Description - Structures and Manholes
d2f8e367-85c7-594a-ab45-865dd21e984e | note | Frequency - Installation
e517db3b-158c-5499-becd-697df1ba9bcb | note | Inspection / Test Method - Measure
1b105c89-8032-5664-81ea-a3731be89c46 | note | Acceptance Criteria - +/- 10mm /1m
920a7c87-92cb-567c-8f65-b2c4dae26e60 | note | Verifying Documents - Visual inspection and measurement on site
39531bbc-9e29-4fa9-b583-f5e6075b96ee | checkpoint-no-value | Inspection and Testing - Refer Section 3.6
a3fe00de-af10-47ce-833f-20cc13be9061 | checkpoint | Leakage Testing
32a4a019-3e8a-5f96-bb28-8797664203bd | note | Activity Description - Pipes and manholes
b08f2e3b-0962-597b-864e-8da119a92b7a | note | Frequency - Completion
11f369e4-2f0d-5578-84aa-92447b6d0fa1 | note | Inspection / Test Method - Low Pressure Air or hydrostatic
737cd07d-eab2-58e1-8b9d-09ed374a00e5 | note | Acceptance Criteria - Holds Pressure
943e3fed-7000-57d3-ba62-5f4393935029 | note | Verifying Documents - Test sheets from the Contract to be completed - Engineer to be present for testing
ab4c036f-a40e-5f7a-8723-e5bb003cf3ca | note | Engineer / Client - H
e4373308-b355-4f5b-b48a-2c7595e5e04c | signoff | HOLD POINT
684bd8be-210e-4eb9-a96f-4562075bd805 | checkpoint | CCTV or Internal Inspection
2311c1cc-a74c-5f54-b84e-5d72a881a80c | note | Activity Description - Section 3.6.5
2c827dbe-a22a-58a6-920c-fae486e42f39 | note | Frequency - Completion
90f2dd43-deb4-5557-a901-470635990357 | note | Inspection / Test Method - Inspection
5f9f9327-5e44-5dc6-a9a6-93bb1f58327b | note | Acceptance Criteria - No significant defects
8d3cb6de-7491-547d-bab9-a6f9a5d0f8b3 | note | Verifying Documents - CCTV to be provided prior to Practical Completion being issued
f17ffa4d-081e-5d1a-928c-670ee8cd7325 | note | Engineer / Client - H
d1bb0119-87e3-44b9-968a-fa9c5c34b1e8 | signoff | HOLD POINT
9e35a158-c4a8-45f4-bfd8-380cd27f2a2b | checkpoint | Concrete works
46c32aa3-1244-562a-bd2b-92de0e4359ea | note | Activity Description - Section 3.6.4
007fa039-b61c-510e-ba3a-4a7e01a9c57c | note | Frequency - Installation
4c6faa57-3c26-5fe0-9375-681e00c426ae | note | Inspection / Test Method - Lab testing
6a3fcd3d-76f4-57d8-a119-68bc2a8baedd | note | Acceptance Criteria - NZS 3104
416e16a4-1558-539a-b188-02bc5e4a9dfc | note | Verifying Documents - Test results to be provided
40c2d664-52bc-5181-9710-7d69a47a05a1 | note | Engineer / Client - H
a82e6198-d7ac-4094-aea1-e735e4f05d71 | signoff | HOLD POINT
c6d38aeb-df99-4a7a-b9a8-4c72902f647f | section | 7 - Pavement Construction
39c13484-c38a-4328-afd3-9f07fd730cba | checkpoint | Earthworks
59d7c777-196e-557a-a3da-5c538fdd532f | note | Activity Description - Set-out level and alignment
faacf434-23c6-5c73-89ef-f76996d3f7f8 | note | Frequency - After excavation and prior to sub- base construction and/or laying filter cloth
e8653ec5-7d18-5665-9fdd-474b3b14e594 | note | Inspection / Test Method - Survey check, and string line depth check
24a9e029-cd2a-5e45-9326-1c551f17ed92 | note | Acceptance Criteria - Horizontal -20mm / + 100mm Vertical -20mm / +5mm
cc4a2014-880d-5926-92e4-a7bfdc6c7788 | note | Verifying Documents - Survey & data sheets available for review
a44e56a4-31e2-44be-8546-9cefaa039100 | checkpoint | Sub-base layer construction (1)
fd9e2f44-2e4f-5f57-be9c-442c24745bc4 | note | Activity Description - Imported sub-base aggregate
59eb0a94-091a-557d-8b49-41d8df1d6312 | note | Frequency - At least 10 days prior to construction
3e5a7f1c-6e3b-5f73-81f9-1353496c0962 | note | Inspection / Test Method - Lab testing
c8dac4c7-7e52-53a0-bdf4-776e41eeedc2 | note | Acceptance Criteria - NZS 4402
09f33fb6-8156-57f8-9ccb-e44cea76489b | note | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
c89a5b87-19c7-5310-8d05-e55785d866a9 | note | Engineer / Client - H
1c992c76-6785-4d57-aeee-25da8f309ba6 | signoff | HOLD POINT
78295536-3952-4397-82d2-5bfa862e6c53 | checkpoint | Sub-base layer construction (2)
7da3b68b-fc25-59e3-81c9-f89b3bf44078 | note | Activity Description - Set-out level and alignment
a3aad418-e9fe-5c40-9ad7-af4e995a43f0 | note | Frequency - After sub-base construction and prior to forming topping layers
2e4846b6-6d7f-5d95-bba0-aa043674abf0 | note | Inspection / Test Method - Survey check, depth check
9bd5e4f6-43e5-5c64-9548-882d358fe3ea | note | Acceptance Criteria - Horizontal: -20mm / +100mm
8978b8d3-523a-58e1-98e8-5493e760a326 | note | ○ Vertical: -20mm / +5mm
f640c58d-203e-5d7a-a7ae-7c2b62895416 | note | Verifying Documents - Survey & data sheets available for review
190d2a58-a478-4332-96d5-f47ed8b76960 | checkpoint | Sub-base layer construction (3)
acbcb90d-ee52-5498-aee9-1d90f82f1dbc | note | Activity Description - Compaction
47e4aa8d-e29c-5671-b47d-f6e0cac72476 | note | Frequency - After sub-base construction and prior to forming topping layers
7afdc08d-01a5-5fb7-bd79-ea961d6aa688 | note | Inspection / Test Method - Density testing
615358e0-0f7f-5ecf-b0e4-0bdf3aa54588 | note | Acceptance Criteria - TNZ B/2 – Clause 7
723af306-6585-5194-a455-9d9dfef49aeb | note | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
4f84647f-7bf9-5633-827b-9cdcb4bbf064 | note | Engineer / Client - H
04ac47e0-8d01-4ea3-b2a1-20c8a295a12a | signoff | HOLD POINT
e278d62c-57a6-43d5-9d22-4a23a4440986 | checkpoint | Basecourse layer construction (1)
2695043a-9d8f-5772-a06b-aa291000302c | note | Activity Description - Basecourse aggregate grading tests
85358a6c-9062-5239-b442-1789a542491a | note | Frequency - Annual source tests, pre- delivery tests results to Engineer 10 days prior to use
785f3741-121e-53f9-ae1e-dfa792f1f1a0 | note | Inspection / Test Method - NZS 4407: 1991
a7db0627-c691-5f1d-90e2-52c443cd6fd5 | note | Acceptance Criteria - TNZ M/4 – Clause 4 Table 4 (Napier River Gravels)
c1bea3ff-0469-511f-8dcb-97833c959f42 | note | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
07adc2a4-0ab5-59bb-8155-18da219b3073 | note | Engineer / Client - H
4503cfa0-c1d6-40ce-91c5-25161e4ecd5f | signoff | HOLD POINT
9b7f2e46-cbc8-4253-b6c2-2f521189f460 | checkpoint | Basecourse layer construction (2)
cedfd3fd-3c19-5abc-8751-48d05fc5a943 | note | Activity Description - Level and alignment
d7831c0b-83f9-5d44-b09b-31720c8f0428 | note | Frequency - After basecourse construction and prior to forming topping layers
550d0120-d27f-5cde-b024-cca38880a84f | note | Inspection / Test Method - Survey check, and string line depth check
b67ff012-8d96-59c1-b293-01af4c5d73e6 | note | Acceptance Criteria - TNZ B/2 – Clause 5
5ae243f8-b7a9-5aea-81c0-1dbef8538281 | note | Verifying Documents - Survey & data sheets available for review
fa6a086c-4407-4808-b5d9-845f1a798329 | checkpoint | Basecourse layer construction (3)
c0cc890d-132e-5058-a2af-54b1519ff298 | note | Activity Description - Compaction
e0ad905a-38ed-5c9b-abbe-6f715abd3a60 | note | Frequency - After basecourse construction and prior to forming topping layers.
1bcb0282-bc09-572e-86ab-41352ecef5c4 | note | Inspection / Test Method - Nuclear densometer density testing
5ed25269-ae3d-5280-9c60-9d67a6159e99 | note | Acceptance Criteria - TNZ B/2 – Clause 7
1cea3866-d2fe-50a5-b41f-6efd3fe24cba | note | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
34ecfe85-0c54-581d-a2ab-4aced930d432 | note | Engineer / Client - H
bf478859-8cb3-4155-87a4-3219cc7c25f3 | signoff | HOLD POINT
9ecec579-7e0e-4afb-9bfb-1709638898ba | checkpoint | Basecourse layer construction (4)
97facc10-e442-5bf5-a3dd-6a24c061f560 | note | Activity Description - Compaction
2b70b3f0-2879-5055-836f-c8be5164df6f | note | Frequency - After basecourse construction and prior to forming topping layers.
2feafd89-9a31-5c6b-ab0c-106faea4f4d2 | note | Inspection / Test Method - Clegg impact test
b7ec8f71-76b4-562e-a7ba-a14b45da4ef3 | note | Acceptance Criteria - Refer to Section 4 below
c1ce4a44-3b63-5746-9acb-0c0f6a870e63 | note | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
4b1512d3-6417-551a-9c04-1a77c0548eb7 | note | Engineer / Client - H
3b5ae813-b7ad-4972-8a87-7f063a8c9c72 | signoff | HOLD POINT
b68afc5d-5580-4e6e-a1a7-a4f32d7986ed | checkpoint | Basecourse layer construction (5)
a71fd9b9-20dd-50ff-99ca-06d706a26cf7 | note | Activity Description - Surface shape
10e833e9-57b9-5fe4-9293-c0c051439e10 | note | Frequency - After basecourse construction and prior to forming topping layers
b1e486bb-be7d-5058-9e6a-da46b2161bff | note | Inspection / Test Method - 3m straight edge, string line check
1aa3b883-f2da-5202-8f34-bec3b93c6ad8 | note | Acceptance Criteria - TNZ B/2 – Clause 7
11b5f8e7-903b-5980-b8b5-daea963c6f76 | note | Verifying Documents - Density and DOS Test results and Data Result Sheets, results should demonstrate they comply
3f7ba58d-d9c6-5535-adc3-fa951f6e8dd7 | note | Engineer / Client - H
4ae000ff-c39a-4fb2-9d28-d49ad6b76982 | signoff | HOLD POINT
79b042dc-3db9-4a8a-ab9a-1e7ddacc36dd | section | 8 - Kerb, Concrete Path & Landscape Construction
517a463e-7874-458d-a34e-2a57728cb020 | checkpoint | Earthworks
f45479e5-2f76-5ad9-8a4e-cde2d280ba11 | note | Activity Description - Set-out level and alignment
19be212f-93e3-559d-9394-90cf983ab827 | note | Frequency - After excavation and prior to sub- base construction and/or laying filter cloth
e5d283e7-f52c-5a60-a65d-4933ab9ca258 | note | Inspection / Test Method - Survey check, depth check
cc88e227-cb41-5a59-ae6a-6cdd5a8f712c | note | Acceptance Criteria - Horizontal: -20mm / +100mm Vertical: -20mm / +5mm
23c7337e-08a2-5f7e-aac7-dfe60cd3fc21 | note | Verifying Documents - Survey & data sheets available for review
218a7198-57bd-4d41-9c3a-a46ebb948024 | checkpoint | Basecourse layer construction (1)
ed925f48-23f1-58ce-9002-cf97e8751db9 | note | Activity Description - Basecourse aggregate grading tests
58f93dc2-e276-5434-825e-a669cd643cda | note | Frequency - Annual source tests Pre- delivery tests Results to Engineer 10 days prior to use
b73f36bc-faff-569e-a35d-dcba32b38074 | note | Inspection / Test Method - NZS 4407: 1991
b00f2400-ee24-5c05-acbe-a066ebae90d4 | note | Acceptance Criteria - TNZ M/4 – Clause 4 Table 4 (Napier River Gravels)
3e7f9526-0116-52b9-91d6-642f85db3b33 | note | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
dda7b546-f26c-58a7-9556-1095e7cd5071 | note | Engineer / Client - H
c2eb8474-b744-49be-8b54-8bed8a3b563d | signoff | HOLD POINT
3f373514-878a-49f5-a8f8-bdb5d9e51d11 | checkpoint | Basecourse layer construction (2)
b2269965-f9d5-5036-a376-9323da75f011 | note | Activity Description - Level and alignment
38dc3a05-4ffc-52c6-87bd-2649322b1749 | note | Frequency - After basecourse construction and prior to forming topping layers
f3a9c828-dd9e-53b6-b835-7d467c3f5500 | note | Inspection / Test Method - Survey check, depth check
ffe7d650-2dc1-5bb0-a3a5-7c7e2ffa824c | note | Acceptance Criteria - TNZ B/2 – Clause 5
fe7e78aa-4e9e-5fdb-b951-3c69ff887ce5 | note | Verifying Documents - Data Sheets available for review
f97e8391-c26b-42cf-9554-d29350d91910 | checkpoint | Basecourse layer construction (3)
834ea3b9-78c6-5339-824b-2f2babf741a6 | note | Activity Description - Compaction
acf9ffe7-be6f-5dc4-b382-597342dcd7dd | note | Frequency - After basecourse construction and
65664976-7d07-586f-9ace-a99986750a9a | note | Inspection / Test Method - Nuclear densometer density testing
43aa1463-bdd2-5231-b352-2de54e9109d0 | note | Acceptance Criteria - TNZ B/2 – Clause 7
3cf6132e-1591-5bd0-93d9-8388cb570780 | note | Verifying Documents - Test results to be provided to demonstrate they comply
1cacbd60-69a0-57ce-a173-69d866191e5f | note | Engineer / Client - H
7a5c6d5b-3a12-4c94-94da-d1a5512e2278 | signoff | HOLD POINT
af7753f4-f509-4a35-8afd-98892bd4e0ed | checkpoint | Basecourse layer construction (4)
d222e239-c3ab-5ffb-a467-49f3c973689d | note | Activity Description - Compaction
abdcf721-ac32-5162-a911-6aae7690b7f3 | note | Frequency - After basecourse construction and
a195d606-d506-5808-8267-a01fe98c078d | note | Inspection / Test Method - Clegg impact test
6c6c5d9a-c7a1-57b5-9ddb-6642b9ade9af | note | Acceptance Criteria - HDC Specification Pavement Construction: Section 4
35b04c11-e69e-50a0-8efd-cafd9836211e | note | Verifying Documents - Test results to be provided to demonstrate they comply
45f61cf9-f4ba-5bb0-9b24-ab1613b9798b | note | Engineer / Client - H
e269bb6e-fc93-4dc8-aaf1-7d736b61f4f3 | signoff | HOLD POINT
19f8296c-1e80-4c0d-b7e0-de706c215093 | checkpoint | Basecourse layer construction (5)
af8ce578-ead7-5a89-99c9-e2ebad2623d3 | note | Activity Description - Surface shape
b977542d-ac86-538f-aa8c-8746067c35a9 | note | Frequency - After basecourse construction and prior to forming topping layers
17bed8d9-e8ff-56f6-af6a-d8ed6fef8963 | note | Inspection / Test Method - Survey check
c9661b5b-e1aa-5d59-9511-74552d677161 | note | Acceptance Criteria - TNZ B/2 – clause 5
d9aa71ff-b99d-52ce-8e14-70cfe154c98d | note | Verifying Documents - Result Sheets to demonstrate they comply
f459984f-22e8-5439-ab35-e0d4e3c3ccd9 | note | Engineer / Client - H
62f2068f-3c91-4359-a0c0-819ed624eef0 | signoff | HOLD POINT
3e7370b7-a6af-4da7-a1cf-34a66e889204 | checkpoint | Kerbing
a118f5e3-ddf7-5ec1-8222-bf01589e40dc | note | Activity Description - Set-out level and alignment
bfd59224-cb19-5443-b60b-35ee5e95b2e9 | note | Frequency - After base construction and prior to placement of concrete
029da09a-2fa6-5409-a891-0da258d78a18 | note | Inspection / Test Method - Survey check
9c033d4a-d9b9-5980-b6f2-9ec2a04ec211 | note | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
9fb6abb9-b99b-5c21-b8c7-feb75ce7b98a | note | Verifying Documents - Survey & data sheets available for review
9b99b674-58dc-45ab-8817-d08b42fb9d49 | checkpoint | Concrete Works
34827aee-ffc2-55db-85c7-fa3357e4632f | note | Activity Description - Section 2.1
f074b260-5639-5c70-8c06-67e7b0f93db2 | note | Frequency - Prior to placement of concrete
9ccdeb62-138f-5244-a52a-015d5f95be8a | note | Inspection / Test Method - Lab testing
3ea2f8ee-11e5-53e5-95ba-d26256360249 | note | Acceptance Criteria - NZS 3104
8286232d-996d-5e5d-b405-de082ca3e197 | note | Verifying Documents - Test results to be provided
c4a648be-26b4-5673-a461-e7bb09b1361e | note | Engineer / Client - H
95576985-98f0-4313-a61d-c738e66d757c | signoff | HOLD POINT
2465e4fd-a0b7-400c-bfaa-a1f45d4df436 | checkpoint | Paths
6f47f81e-1164-5afb-bfe6-7f38bd4859d7 | note | Activity Description - Set-out level and alignment
a10e8749-8d94-5118-97ac-d155b3e7f8db | note | Frequency - After base construction and prior to- placement of concrete
71f30b47-9fc8-5b2d-b641-20114075f5cc | note | Inspection / Test Method - Survey check
4df06e67-2b4a-57d0-977a-b4e39c97410d | note | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
6dfaddf6-0372-564a-b9f5-7f2bae7c8184 | note | Verifying Documents - Survey & data sheets available for review
74025ac7-005e-4872-92f7-d732d8b972c7 | checkpoint | Prepping on for grassing
cc4329b2-42e5-5a7f-b8d1-3b55ee42918c | note | Activity Description - Set-out level and alignment
353195d9-76e6-56cb-9947-a306636c17fd | note | Frequency - After base preparation and prior to- placement of top soil
d08d452d-b9a2-5ca8-a2b0-106e20326216 | note | Inspection / Test Method - Survey check
a5f68215-eb3c-5e01-b7ea-41281a3378ee | note | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
8db80100-d41b-532a-97c0-d6f137f36b07 | note | Verifying Documents - Data Sheets available for review
6a171d5e-88e7-466b-8737-debf1ce12a72 | checkpoint | Insitu seeding and turfing
6aec5b5b-d525-52f2-846c-39b4468824aa | note | Activity Description - Suitability of soil
68c5c23a-c906-5f01-a3b3-dc5a1413f073 | note | Frequency - After placement of top soil and before grassing
c454d25c-de67-5446-951a-4150aeb5b86b | note | Inspection / Test Method - Visual material check
bccd66ed-1c45-5369-ab40-547e26b8d99e | note | Acceptance Criteria - Soil is free of weeds, stone and other hard materials
1da3d3f8-4bfc-519c-aef5-aa70abaafe45 | note | Verifying Documents - Visual inspection
fd9cbd14-8e71-496a-aa2a-d4d7bf243b0c | section | 9 - Adjustment of Service Covers
f8b8dd20-eac7-4066-ba54-446e2a6d2fcd | checkpoint | Service covers and manholes in road (1)
ac7a40a5-2954-513c-9182-44902e50ee14 | note | Activity Description - Level, securely fitted and clear of debris
2a515bc0-cd73-56e6-b067-bc67fe04bc77 | note | Frequency - After basecourse and prior to sealing
d1ca98c4-4b99-5bd5-9de0-3f8e071df8d2 | note | Inspection / Test Method - 3m straight edge laid on final surface
eb4d7baa-9db5-5355-9ed5-85e50afc7391 | note | Acceptance Criteria - Vertical: +10mm and - 0mm
14d169d4-4523-522c-a26e-9c331e0259c4 | note | ○ Reinstatement of pavement to match adjacent levels
70496ebf-a0b3-5fc0-9e4e-a2a5876a8c2d | note | Verifying Documents - Visual inspection
0ca3586a-9502-4ff9-b324-52d73f2011d6 | checkpoint | Service covers and manholes in road (2)
268b1db5-ffa7-5cac-9f47-94e42700f155 | note | Activity Description - Level, securely fitted and clear of debris
f4f9b98a-a316-5e2f-9613-a67b908ee413 | note | Frequency - After basecourse and prior to sealing
0e93382e-1bbd-5425-b5a0-2efc43dfe02d | note | Inspection / Test Method - Visual inspection
b74c7216-0968-5226-b204-499436209d80 | note | Acceptance Criteria - Access and internal space is clear of debris. No rocking
be3f9248-7034-517a-8354-aab85739f253 | note | Verifying Documents - Visual inspection
bd0646b8-d40e-4aa3-9af8-6bf76275ce1a | checkpoint | Service covers and manholes in path (1)
3d64e5f2-ae0d-59fc-8857-83d4cc2ba582 | note | Activity Description - Level, securely fitted and clear of debris
6a499ff9-dea4-5abf-8242-7add631dadc9 | note | Frequency - After basecourse construction and prior to concrete
0c8e518e-191d-51a1-a4c7-d9ed3cac5648 | note | Inspection / Test Method - 3m straight edge laid on final surface
664e3542-6483-5670-9dac-c96b56044787 | note | Acceptance Criteria - Vertical: + 10mm and - 0mm
58e3e84a-3542-515e-83a3-543db719668f | note | Verifying Documents - Visual inspection
e46e4cce-86c3-4876-acb4-1c0de8910b1f | checkpoint | Service covers and manholes in path (2)
58f46dd8-d209-54c9-af21-85161751f66e | note | Activity Description - Level, securely fitted and clear of debris
daa4c5a8-4e0a-5971-938c-4fe7cceb9f9e | note | Frequency - After basecourse construction and prior to concrete
71c366a4-b31b-5ca4-a803-458bdd587beb | note | Inspection / Test Method - Visual inspection
b118f8ff-874a-5061-b3a6-96ffdc135fb9 | note | Acceptance Criteria - Access and internal space is clear of debris. No rocking
bd1e1426-7c1a-5133-82c8-8a8ec187e8cf | note | Verifying Documents - Visual inspection
1810ce7b-7191-4495-b704-7080cc407452 | checkpoint | Service covers and manholes in berm (1)
7d581b13-6ccd-5921-a88e-0d2eabeb65a7 | note | Activity Description - Level, securely fitted and clear of debris
5e31afc3-5bd0-54b8-bb37-8dd0ccfa76e3 | note | Frequency - After topsoil and prior to grassing
e332e510-4563-52eb-9f9c-e6cd7000218b | note | Inspection / Test Method - 3m straight edge laid on final surface
664493a2-a0f3-58cf-8387-85b7538154b3 | note | Acceptance Criteria - Vertical: + 10mm and - 0mm
1ad738df-dc40-575d-9d12-5ee0047e0f2e | note | Verifying Documents - Visual inspection
b1f7b938-bef4-4ce3-b604-c05e3c139794 | checkpoint | Service covers and manholes in berm (2)
546cad58-d9a3-567a-8b72-74522930e8e4 | note | Activity Description - Level, securely fitted and clear of debris
1e12c48d-6661-573e-8182-e837b8c2cc89 | note | Frequency - After topsoil and prior to grassing
30247501-8b2f-5a82-a9a2-5103a43adbe8 | note | Inspection / Test Method - Visual inspection
6f50414a-789d-5e2b-8c15-285bb7e125f2 | note | Acceptance Criteria - Access and internal space is clear of debris. No rocking
68df0e0b-b49d-5e9a-825d-04cb2a620029 | note | Verifying Documents - Visual inspection
9b61b990-1092-4f0b-9fb9-73f5d190ac98 | section | 10 - Surfacing Construction (Evenden Rd)
bb39d6fc-7501-4008-8c6e-f2a1db9e471e | checkpoint | Surfacing Materials
8966f2e3-1614-5fcf-a347-f467f33d2595 | note | Activity Description - Materials
a6e53c53-639a-5aa3-ae11-f65bfd845f3c | note | Frequency - Prior to surfacing
8f367a63-18de-56df-9f23-bbfa5dbefa93 | note | Inspection / Test Method - Supply of surfacing materials (chip test results, asphaltic concrete materials)
7d165113-ab81-51f2-bedc-ac654892ff94 | note | Acceptance Criteria - NZTA M/6: 2011 specification for sealing chip NZTA M/10: 2014 Dense Graded and Stone Mastic asphalt
539e5f58-9597-5f4f-b33d-5322f75250c9 | note | Verifying Documents - Test results to be provided to demonstrate they comply
42a79996-3d69-5823-903c-0a1c35ed177d | note | Engineer / Client - H
c24b1be2-b75a-4d65-a036-a71f90efabfd | signoff | HOLD POINT
32fbf3a9-b2a9-46ac-a223-3e9685385f9d | checkpoint | Surfacing Design
6530b365-7a5a-55fd-a566-b5667835137b | note | Activity Description - Design
2179899e-8095-5521-b25e-55da5fa6a4b4 | note | Frequency - Seal design prior to sealing.
60ae34a4-9e7e-5449-a7b9-c85ed04407f3 | note | Inspection / Test Method - Chip Seal Design/JMF
567b4bc1-648c-5ea5-a0fd-0f88459cb484 | note | Acceptance Criteria - NZTA P/3: 1995: specification for first coat sealing NZTA M/10: 2014 Dense Graded and Stone Mastic asphalt
7aa38c0e-645f-551f-ada0-afb494b3b429 | note | Verifying Documents - Design provided 48 hours prior to application
e4b0f1bc-aad3-5ce9-a7ed-16c0080d4a72 | note | Engineer / Client - H
5e68ffb2-c032-40fd-988d-3ef020efc82a | signoff | HOLD POINT
bb047b24-a61c-4a37-886f-9980f40f20c4 | checkpoint | Sealing works (1)
34f8ff22-0f1a-54ce-b64a-73bbb670c7c2 | note | Activity Description - Preparedness for sealing
bc9db761-6368-5ed0-9c8d-31e341b113c7 | note | Frequency - After sweeping and prior to sealing
012ec344-8f74-516e-9d07-8fe3b2ab31ee | note | Inspection / Test Method - Visual check
1e50a06d-a841-53dd-b31f-42ffb3ed7fce | note | Acceptance Criteria - Clean aggregate mix exposed to accept binder coat
bb68bf45-3e63-52e3-854e-5ef470fde828 | note | Verifying Documents - Visual inspection
9c2b03ab-a65f-5bbd-930a-dbd60919bd30 | note | Engineer / Client - H
691fad30-d3b3-42f5-83f2-8d98b3aed960 | signoff | HOLD POINT
4c80f6ed-58fa-444a-9a08-4694bb761177 | checkpoint | Sealing works (2)
1fa31cc9-c6d9-536a-a20b-e927b23eb4f7 | note | Activity Description - Reporting
ab4edb6b-6249-5e1e-abbc-86440c1cdf3d | note | Frequency - Seal reports on completion
379295b3-31ca-5ba6-a18d-fe9448848a5b | note | Inspection / Test Method - Construction reports
72c1aa6c-c9e4-5c1e-9756-c73dddd178e6 | note | Acceptance Criteria - Meets construction tolerances Services covers exposed and marked. Service boxes clean and fit for use
73db1a2b-0b5f-4baa-a038-a5183747500f | checkpoint | Sealing works (3)
76e208eb-5589-5c79-9790-8437d818f7e1 | note | Activity Description - Service lids and covers
b7fc1893-f5e2-5563-90c1-77f6fd7d9e5e | note | Frequency - On completion of sealing
ddc5fde3-a537-5d0a-8a72-5543d501efd0 | note | Inspection / Test Method - Inspection of service lids and covers
3456ace2-1d63-5c1d-ac53-b9cb13043854 | note | Acceptance Criteria - Temporary floors removed from all manholes
cb03b164-fd3e-5954-8911-2900b3e4ba92 | note | Verifying Documents - Visual inspection
6556e663-abc5-458b-abc6-9aee688f2b7c | checklist | ITP - ROADING Rev 0 | itp | ITP - ROADING
c1d115a8-371d-48eb-af2e-093f474e14d9 | section | 1 - PRELIMINARY / GENERAL
cd697fc6-52f3-4e3d-9f26-28d4f6a2bd78 | checkpoint | 1.1 - Subgrade testing
689f64e8-1952-543e-b26d-37ea9148fb39 | note | Inspection / Test Method - Beam testing / proof rolling or scala
795fbdaf-0411-5b44-86d1-939621c97996 | note | Acceptance Criteria - Consistent with design assuptions.
180ae465-5df0-5a88-8a2f-e66187d8b5b7 | note | Frequency - Prior to construction
b9fe2c8a-c965-505f-a9d2-ea1aeec1b23f | note | Verifying Documents - Test results
e7ce3be5-2cfa-5616-b089-db58dad75550 | note | Sub Contractor - H
1547ebfa-64a9-511f-8530-8ae864727100 | note | Head Contractor - H
a7a31ee8-75a7-5b88-98aa-002306da23f2 | note | Engineer / Client - R
c6c1117b-50a3-58fe-9b9f-342a5ec6c61c | note | Comments - Required to confirm assumed CBR.
6a577b2f-0567-413b-bdbf-41edaaa7abfb | signoff | HOLD POINT
e7523f49-9309-49f0-89c5-3067b031584d | section | 2 - MATERIALS
d5e1cfd0-484a-4574-81ff-e55cf14952b5 | checkpoint | 2.1 - Sub Base
e68e497b-313a-50d4-aa8c-579279e5615a | note | Inspection / Test Method - Production testing to NZS 4407
c77fc88f-fbdd-581f-9a7b-df55e6894c9b | note | Acceptance Criteria - Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN.
15424312-560b-5b12-bf77-cd359100a4b0 | note | Frequency - 1 test prior to placement
e1116520-d0e8-545a-8e0f-e0c43ad4561e | note | Verifying Documents - IANZ Lab report
484428b5-8f2a-5657-b1ea-a2e17dd028e8 | note | Sub Contractor - H
219eb646-6740-515e-854d-f2d6e0bd42e4 | note | Engineer / Client - R
eb1b91e1-b024-4071-b2cd-6209c7f7e796 | signoff | HOLD POINT
8ffb60cc-668c-4e7f-bfa2-a3c36c525017 | checkpoint | 2.2 - Base Course
63125cfb-4ef4-5467-ac7f-042491df2e12 | note | Inspection / Test Method - TNZ M/4
da435cc8-af18-5240-a6e7-be7ff0c2def6 | note | Acceptance Criteria - Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run".
93bb2d1b-4e65-5eb1-96f4-ada828dffa6f | note | Frequency - 1 test per 500m3 prior to placement
518ab208-da20-5899-a398-a8def8408c32 | note | Verifying Documents - IANZ Lab report
8e222499-14b9-5b68-b091-5686a65555b3 | note | Sub Contractor - H
f2619816-fe8b-5497-b7c1-9a1b4aec5190 | note | Engineer / Client - R
1b22b829-3527-4ec9-9056-d803aa741d03 | signoff | HOLD POINT
2705f10f-2430-49e5-9658-021a3f1fac91 | checkpoint | 2.3 - Ashphaltic concrete surfaceing
d262de53-6ad3-50ff-ac98-653846e539ec | note | Inspection / Test Method - TNZ M/10
c7d85d44-6edc-5892-8881-19e2853790fb | note | Acceptance Criteria - Job mix formula
ca777020-6bbf-5b6e-b422-28007b13d84c | note | Frequency - Prior to placement
a9b5709e-9fe2-57f0-8c25-eb738acdd2ca | note | Verifying Documents - Mix design
1a973db4-f42f-5419-bc68-df224f497ac2 | note | Sub Contractor - H
e485ee75-2898-569a-ac3f-ce3aaebe72da | note | Head Contractor - H
db92ea7e-1392-5b2c-b68a-f47dce73053a | note | Engineer / Client - R
85aec5eb-c1b2-4720-956d-943c8399ede5 | signoff | HOLD POINT
51375abc-8594-4565-9b66-c6472a07934d | checkpoint | 2.4 - Chip seal
d723333b-d73b-5c00-b69a-85e2e584067f | note | Inspection / Test Method - TNZ M/01, P/3 & M/06
5b7156c6-db03-57ce-a6e7-c0cf9d3b9399 | note | Acceptance Criteria - Job mix formula
ce9c95ea-0c42-5b4a-886b-774d1a939abd | note | Frequency - Prior to placement
517eef3c-7e47-5d1c-8017-bcc508e164bf | note | Verifying Documents - Mix design
1ffebb62-2780-5795-a647-0e70f3c28751 | note | Sub Contractor - H
5d4ac8ed-52f4-557b-9216-47d201db201a | note | Head Contractor - H
0e900e80-a396-5125-bcc0-85ebef2f8469 | note | Engineer / Client - R
c2a4e719-a2fa-484a-aa67-e4a0810096b7 | signoff | HOLD POINT
39d09650-3b97-4cbc-93ee-90653d314d36 | checkpoint | 2.5 - Concrete
93dca821-92c4-52e5-8f37-944f04e6d915 | note | Inspection / Test Method - NZS 3109
fd8e6583-4208-5fec-8590-2bc7c311b4b2 | note | Acceptance Criteria - 25MPa concrete at 28 days.
c6bbb6e5-f17d-54b7-b739-841faf559f7c | note | Sub Contractor - H
ccdc12f1-8f46-523a-a285-04f6f1d816df | note | Head Contractor - H
5df40a0d-6d6f-5de3-979b-aaa54132ee47 | note | Engineer / Client - R
ecca6ecd-c935-4ca3-9f44-7e16952b80e8 | signoff | HOLD POINT
781c47ef-449d-4566-b873-c6117360e644 | checkpoint | 2.6 - Vehicle crossings
326b8c44-c256-5a67-a794-4999d8c286f4 | note | Inspection / Test Method - NZS 3109
1453c6e3-46b9-531f-b9d2-f6ecc414b1e6 | note | Acceptance Criteria - 30MPa concrete at 28 days
057d810e-7f4c-5c2e-89b7-0745a7d2270f | note | Engineer / Client - R
27de04be-66cc-421d-972b-d20c4ba30dd3 | checkpoint | 2.7 - Kerb and channel, nibs and dish channels
12201359-21bd-5efc-b0e5-b005b8f0faca | note | Inspection / Test Method - NZS 3109
12d1b4b2-29ae-5d25-8fe2-c506213036bb | note | Acceptance Criteria - 20MPa concrete at 28 days
f0d25c11-67ec-5dd3-998a-a889935763f0 | note | Engineer / Client - R
43e1613e-5150-489c-a482-459cee246397 | checkpoint | 2.8 - Traffic signs and name plates
94075036-23b3-5edb-a5d4-70ef701c2288 | note | Inspection / Test Method - Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA
97c1028b-a3ce-5a7c-a33d-7f48f6f52f5b | note | Acceptance Criteria - Compliance with the standard.
a9ca0260-9d11-562b-80f1-b0e589bb0ad7 | note | Engineer / Client - R
480669da-7276-42f4-966d-5b12eef3052a | checkpoint | 2.9 - Road marking paint
66459134-4cc3-5902-a1c9-4ba0ede16e52 | note | Inspection / Test Method - TNZ M/7
e345edd9-23df-5c6b-84ae-9304ef141102 | note | Acceptance Criteria - Compliance with the standard.
abcbc296-b77a-5104-92e0-c8f42666383d | note | Engineer / Client - R
7f146cf0-35ed-4e1d-8b93-71ae8f855976 | section | 3 - SUB BASE CONSTRUCTION
8d0b3972-0832-4406-993d-ca4dece45da7 | checkpoint | 3.1 - Topsoil stripping
0d639608-bcee-5a80-8162-996cde8f223c | note | Inspection / Test Method - Inspection
be3f7575-1535-579a-aa85-6b4598d4026f | note | Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed.
dbc4bc04-1262-5e7c-8031-eed227c800bd | note | Frequency - Prior to fill.
1e3fa040-893a-5391-9140-61c4ef6e6b74 | note | Verifying Documents - Engineer approval.
c9eb63b4-a47b-5aee-b7b5-9dd385dff9bb | note | Sub Contractor - H
4a9331b4-6ae0-5f90-b0c3-189f10247fa1 | note | Head Contractor - H
84c01d52-7197-5476-a4fe-7e66d8e635d4 | note | Engineer / Client - W
44000d97-f619-429f-a160-142fa3fa1be5 | signoff | HOLD POINT
3801b257-4fe6-4227-8d4e-ee3b05576783 | checkpoint | 3.2 - Surface finish and levels.
1d921746-2f2d-50c7-a4c1-2c1d1ef3468e | note | Inspection / Test Method - Survey / string lines at 10m centres.
a68f5c17-5377-5239-a81c-45e20c5a68bc | note | Acceptance Criteria - Surface finish in accordance with TNZ F/1, section 11
8aa97ab0-3e89-56ea-b501-d7f542b1e47c | note | Frequency - Prior to fill.
d5dba03a-8878-5382-8427-70aa40575693 | note | Verifying Documents - Engineer approval.
b3efe1d1-b0c3-5e61-a8ad-b0e5b09e3de4 | note | Sub Contractor - H
b6e5c8fd-8c8b-568c-ac26-47394d5e6018 | note | Head Contractor - H
9fad2662-3f43-56bd-aeda-d5ce92319c88 | note | Engineer / Client - W
ca039fac-c295-4e0b-b575-db0f21874460 | signoff | HOLD POINT
bd9db7dd-c89f-421d-b0b4-1f97aa73a97e | checkpoint | 3.3 - Density testing
8545d821-f10f-5530-b17e-0eeeb33dd34f | note | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 20m intervals staggered between lanes.
12847a0f-e179-5791-b0dc-bb6fcb6df66d | note | Acceptance Criteria - 95% SMDD mean, 92% minimum
84b8281d-ce91-58f3-a3a9-179bb0216301 | note | Frequency - Prior to basecourse placement.
e4f9150a-e494-5b89-9a02-c76f78b6fdc4 | note | Verifying Documents - IANZ Lab report
783e3086-24aa-580d-a8e6-ea0296c21b18 | note | Sub Contractor - H
6668f787-81fd-5e9f-b415-d5681b46f2c7 | note | Head Contractor - H
f77cc251-4a36-5b0d-a67b-edb279aa5928 | note | Engineer / Client - R
fc4c6ead-a174-4c46-b972-ad3557172a08 | signoff | HOLD POINT
911617ed-f0e6-44e3-b0f4-18033c042b18 | checkpoint | 3.4 - Sub base surface finish
17901d6e-f5d2-58ae-bbf7-016207a5fd0e | note | Inspection / Test Method - TNZ B/2
3ee8172a-4dbd-5709-afad-7c338a7cdc7d | note | Acceptance Criteria - Visual inspection - tight mosaic finish.
6727c281-61a1-534b-a8d3-7f86a0d4686b | note | Frequency - Prior to placement of bascourse
9f207cf0-9bf7-57f6-baaa-fdaffd61f321 | note | Verifying Documents - Engineer approval.
80928195-c223-5747-89b4-5a3d04df54be | note | Sub Contractor - H
5e0ec391-10f1-5575-9f43-12f84a37454c | note | Head Contractor - H
a564b7ec-af7c-54ff-9921-4924c10e761c | note | Engineer / Client - W
44d49fb0-33c9-4d27-9a55-7aa9a470f267 | signoff | HOLD POINT
23c84810-76b6-438d-813e-4306b6c49050 | section | 4 - BASECOURSE CONSTRUCTION
8d5ac045-7c11-4682-96f1-57c4e4db2d6d | checkpoint | 4.1 - Basecourse finished level setout
9c1f6c9c-14e9-51dc-8ba4-28ab3df921aa | note | Inspection / Test Method - Survey / string lines at 10m centres
f35798a7-6385-5277-8988-28bcb98a885e | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
366a9473-314b-5928-94e6-f0f8c577265a | note | Frequency - Prior to basecourse placement.
daace5cf-1cec-5779-95c9-7b638854cd9a | note | Verifying Documents - Engineer approval.
5e2fca6b-13a7-5300-8dd1-654255eec28a | note | Sub Contractor - H
7ec90ede-921e-506f-b625-23d2a4850af9 | note | Head Contractor - H
2a56dd5e-1f2b-568b-beac-23d3454c2309 | note | Engineer / Client - W
ee594d00-99ed-40ca-aabb-0083f99a6f10 | signoff | HOLD POINT
5fbd072c-391b-497d-8ccb-354723193d2d | checkpoint | 4.2 - Density testing
0601bd47-af69-5b63-ac38-051077ad09ff | note | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 20m intervals staggered between lanes.
0ed92dfb-90fd-5929-b033-246b7880035d | note | Acceptance Criteria - 98% SMDD mean, 95% minimum
7a757544-b373-5a45-87e2-296cba126693 | note | Frequency - Prior to surfacing.
51bf75d8-738b-529e-9b16-90b59cacffaf | note | Verifying Documents - IANZ Lab report
f572ee53-6bd7-544b-a6a7-43a957e58dbb | note | Sub Contractor - H
8b92454e-0854-52c2-9e1f-e94da6b20bee | note | Head Contractor - H
f1a71b75-6b59-542d-8511-54195d87c724 | note | Engineer / Client - R
c34c3215-3352-4af9-99d3-da5e7c7695eb | signoff | HOLD POINT
8a6d42e1-fbe6-4902-a6f2-760425b83009 | checkpoint | 4.3 - Beam testing
53d1f33a-5e9a-5335-97aa-ac5e004eba8b | note | Inspection / Test Method - TNZ T/1
baa26be8-c685-538c-8ddf-58a0bccffb5b | note | Acceptance Criteria - Average: 1.5mm, Maximum 1.8mm
3dab875c-0bc6-5220-832e-0c62aadac5c4 | note | Frequency - Prior to surfacing.
83cea8ae-7701-5f6f-8ca5-298c7b6578b8 | note | Verifying Documents - Test results.
8fc46b7e-a66e-52d2-b421-69bcc4474f4c | note | Sub Contractor - H
13611042-158a-5f4a-8ac8-b0d74e707916 | note | Head Contractor - H
d47667e2-e9f7-5d76-8833-8fd4a5640197 | note | Engineer / Client - R
a50fa93c-765f-44ce-8152-c0798056dab1 | signoff | HOLD POINT
c8f3e799-e46e-4fef-8c25-9330c0381f84 | checkpoint | 4.4 - Surface finish
c2d50d9b-4f42-513e-a72a-8fad3b748e22 | note | Inspection / Test Method - TNZ M/4
ab5cd343-c135-5f9d-bdc3-be617deaa1bc | note | Acceptance Criteria - Visual inspection
26fd9724-1088-5d4a-99c7-3b0e5b1b0aad | note | Frequency - Prior to surfacing.
52125bc2-52e8-5186-b0e7-e9ce265d99e2 | note | Verifying Documents - Engineer approval.
a9d66dde-a0e2-5b54-961c-bb92c38e0cb4 | note | Sub Contractor - H
993fd4aa-173b-5af0-8cb8-41babb72402a | note | Head Contractor - H
c15c53a4-4425-5ec9-84af-90fc678d3260 | note | Engineer / Client - W
6ccb79a2-c0cf-4892-8ac1-35c426c1eb7f | signoff | HOLD POINT
2d508a45-9ed9-4e16-b2d9-e103fde0b715 | section | 5 - ASHPHALT SURFACING
cf5d0483-1cb7-42ef-a15f-8291bd76f5e0 | checkpoint | 5.1 - Ashphaltic concrete finished level setout
d5eba0f1-f7fb-5f61-86a4-1ee8eb61052d | note | Inspection / Test Method - Survey / string lines
74e7be0c-ba83-5263-a83b-078acc1ba189 | note | Acceptance Criteria - 10m centres, 3m straight edge.
1138f4b8-caf4-5c79-97c2-5c1263a81b71 | note | Frequency - Prior to surfacing
c0daa566-33bb-5d6d-b7e9-a2e1af7d7f3e | note | Verifying Documents - +10mm / -0mm from finished design.
0e6bf4bf-878c-552a-a7e3-d32f44188231 | note | Sub Contractor - H
16197256-e1d5-53f1-9d9f-55e5d4226098 | note | Head Contractor - H
f277a065-a19e-5960-b5ad-dd5ce0e899c3 | note | Engineer / Client - W
b17e7400-7125-42c1-bdbe-414243bea5e5 | signoff | HOLD POINT
ad756b03-c57f-4afd-bf27-60b192fea3b3 | section | 6 - CHIP SEAL SURFACING
7549af16-70c1-4f3c-9f4b-0ae771f97567 | checkpoint | 6.1 - Chip Seal finished level setout
6867057c-ce6a-5fff-8984-fd9cd4b9ce50 | note | Inspection / Test Method - Survey / string lines
48631de6-c961-542a-a0d2-fd323a98b590 | note | Acceptance Criteria - 10m centres, 3m straight edge.
07171023-d127-5507-96c2-4fbb6d562c84 | note | Frequency - Prior to surfacing
07c85805-dfbe-5b57-94fd-1b203d9e878e | note | Verifying Documents - +10mm / -0mm from finished design.
14814e2e-8ee5-5453-823d-9e6fcaa3ffbb | note | Sub Contractor - H
b55fef57-c2a3-5506-ad3f-af396896d864 | note | Head Contractor - H
56dfc93d-3740-5973-9ea5-2e58ab546d2d | note | Engineer / Client - W
3ce4947f-335a-4ccd-8f9d-ab0ab9b3538a | signoff | HOLD POINT
96d1e473-748f-419f-8edf-347ae3946ef4 | section | 7 - FOOTPATH AND VEHICLE CROSSINGS
ef91866b-fbe2-42ef-9e8c-ae2792848873 | checkpoint | 7.1 - Setout
67d17722-86bc-5978-8bc9-ebd1b7929d5b | note | Inspection / Test Method - Survey / string lines
0fa65e10-61d3-5aaf-a0e4-8159ad6592f0 | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
321ecf77-0af3-5f58-a7cd-52c5f4038da2 | note | Frequency - Prior to pour.
e127ee96-941c-5a27-9e38-8a65d0a9c182 | note | Verifying Documents - Engineer approval.
004fcf93-9e4d-552b-902c-b7ce9105f730 | note | Sub Contractor - H
bfa3dcb0-63e1-508e-8463-8b7ce0e10ea3 | note | Head Contractor - H
daf5572d-15ed-531c-a408-dd5811d70ef1 | note | Engineer / Client - W
9c949514-2335-4ce6-b1c7-3fde42b45e0b | signoff | HOLD POINT
b6869076-8c03-4a03-ad43-78ca2eb0c7ad | checkpoint | 7.2 - Basecourse compaction
84bff7a2-349b-5f62-9964-a415bc374ea9 | note | Inspection / Test Method - Clegg
8b02d626-2293-5c73-ad0e-f40d63687d5b | note | Acceptance Criteria - Mimimum 25.
d239d3f2-11ad-5e0d-986f-e6d1e1651693 | note | Frequency - Prior to pour.
f6e272b4-b0b5-54c3-a8f8-b9b8cff6bbc6 | note | Verifying Documents - Engineer approval.
387857d3-9654-57e4-8f3d-794aa24496b4 | note | Sub Contractor - H
6d1a981f-b879-5eed-9240-ec5e13bf043a | note | Head Contractor - H
3f58a517-4876-53ef-8af5-e5aafeb21f08 | note | Engineer / Client - W
dcec040a-b8cd-4556-9efa-8e7c8e73c89f | signoff | HOLD POINT
6b2384a5-fef9-4514-9e96-a19889872726 | section | 8 - KERB AND CHANNEL, NIB, DISH CHANEL
7d4771fd-515f-4337-a16d-297f3d05bccd | checkpoint | 8.1 - Setout
dcff8ac9-e9f6-5401-a1fd-3bb1275e53a4 | note | Inspection / Test Method - Survey / string lines
5b852951-08e8-5589-a838-e63e9486804d | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
d2db8573-e185-56c3-b431-a0baaf8634f6 | note | Frequency - Prior to pour.
6957509a-8a13-59d7-8194-3462f94cfa63 | note | Verifying Documents - Engineer approval.
5c0a4c93-4bc0-550e-ae47-b86a6b2fc029 | note | Sub Contractor - H
1d536144-b774-5ac2-922e-1c716b1e7e51 | note | Head Contractor - H
de967489-e35b-5b00-8a6e-4d7120dfcd41 | note | Engineer / Client - W
a21e8d26-bb44-49ca-b03e-afce642fa53e | signoff | HOLD POINT
5412efda-0d17-4acf-85ea-ed22486530a4 | checkpoint | 8.2 - Basecourse compaction
e54a7603-ec03-5f1e-b43f-ce1bfb36b8ff | note | Inspection / Test Method - Clegg
6f39eef7-6072-52a7-9076-fd787cabf51e | note | Acceptance Criteria - Mimimum 35.
362a1494-4ef6-5962-a578-d73227c5685c | note | Frequency - Prior to pour.
e903fdc4-4ae8-586d-9d08-fd6af39e421c | note | Verifying Documents - Engineer approval.
0470467d-4676-5c23-94ca-0968295ac167 | note | Sub Contractor - H
dc679742-1c6b-55d9-852c-2bc6bd535f52 | note | Head Contractor - H
24171d4a-8af9-51d9-89e8-a26f5c084f28 | note | Engineer / Client - W
dad047a8-7d32-4efd-808a-fa116915c910 | signoff | HOLD POINT
f84d917d-22d0-409d-bb9c-934c16ff58fe | section | 9 - ROAD MARKING
be626532-7242-4439-94bd-62542ff47c5d | checkpoint | 9.1 - Road marking paint
0f16ba97-e6a9-5436-ab73-4742ebe4f3b9 | note | Inspection / Test Method - Mark out on site
528d2c3b-4bfb-58f4-b4e4-18608865c7a2 | note | Acceptance Criteria - Mark out dimensionally in conformance with the design.
aea5c4f2-ba18-522c-9c9e-b8aa87db05ee | note | Frequency - Prior to application of paint
1b7fff52-b99c-5925-9db4-138b5362368a | note | Verifying Documents - Engineer approval.
ccdd9e84-24f2-5c6e-b6de-6bb60066e735 | note | Sub Contractor - H
0490216b-9077-572f-9179-a838c5b6d0b5 | note | Head Contractor - H
03efc0c1-d0b9-5808-be1c-e7c97b80ac2c | note | Engineer / Client - S
d61d71df-a099-4c3f-bff2-075ce7de3718 | signoff | HOLD POINT
655918dd-cfd3-46db-b1f8-3266477f03d9 | section | 10 - CLOSEOUT
35b69e24-be13-456a-bbe3-86ec061d8f48 | checkpoint | 10.1 - Collate and supply Producer Statements / Waranty Schedules
1fb8a57e-1170-5e33-8364-edf7917b5331 | note | Inspection / Test Method - Document review
25cb1263-c848-51e3-af13-dee649e95e84 | note | Acceptance Criteria - Collate and supply producer statements
4b2683f3-f4c6-5ab8-bcba-91d031633488 | note | Frequency - Upon completion of bulk roadworks
5282353e-2981-5de6-b9e1-a247fecd7ae1 | note | Verifying Documents - Producer statements
4214b7d2-c1d3-57cf-8a93-59758378e251 | note | Sub Contractor - H
bac84f81-5ece-577e-943f-47fb80d7d6fc | note | Head Contractor - H
e7e070e0-c8b2-57f7-83d5-f458d9445497 | note | Engineer / Client - H
9a64f6e3-b0b5-48dc-ba32-5a19715e9a02 | signoff | HOLD POINT
8d1e3178-b940-44dd-9a10-21496916803b | checkpoint | 10.2 - Collate and supply as builts
3a094e5a-cda3-5ad6-a8e6-edc88cfd6928 | note | Inspection / Test Method - Documate review / as builts
a2319dc3-ac86-5576-9cc7-e74ffb78570c | note | Acceptance Criteria - Collate and supply as-builts.
46f1203e-1512-51b8-bc04-97190f66bec3 | note | Frequency - Upon completion of roadworks
5063b72b-53ad-50a8-8fc9-b37fcfaf90ba | note | Verifying Documents - As-builts
37b42837-c4e6-5c6a-9bcf-d59b77319819 | note | Head Contractor - H
cf48d140-733b-5490-8e7f-99ed2f8a0b21 | note | Engineer / Client - S
3568527f-e325-475c-aca2-d82d2dc9660d | signoff | HOLD POINT
0bd1cfaf-75de-4850-9821-d8e8e66eda29 | checklist | ITP - SERVICE TRENCHING AND DUCTING Rev 0 | itp | ITP - SERVICE TRENCHING AND DUCTING
a4fc94e2-1cec-441a-9917-bcfde8d14e17 | section | 1 - PRELIMINARY / GENERAL
de3e1ab5-a0b4-4ddc-b44a-90f5628913b0 | checkpoint | 1.1 - Consents and trench opening notices
09e44d24-db8e-53ae-b7f2-5d8c8fb48de7 | note | Inspection / Test Method - Document review
9bf00256-40d6-5a7a-ade7-bfe476472237 | note | Acceptance Criteria - Authority approvals.
75dae00b-4a73-572a-9f65-fb078354a2d6 | note | Frequency - Prior to excavation
89726ac6-c31d-591d-8985-60140288342b | note | Verifying Documents - Approval from relevant authorities.
5c4856b1-213d-576a-9bf8-00080e22dc9b | note | Engineer / Client - R
0a8fe6b9-b934-46a5-b90a-f334f8731c24 | section | 2 - MATERIALS
0290ec06-9ec1-4d89-a8f6-6103c07c549a | checkpoint | 2.1 - PVC ducts
ba1a6cde-0229-5701-a86e-0b285e7976ba | note | Inspection / Test Method - Document review
4cb28cd3-f7b1-538b-b956-e6929756da12 | note | Acceptance Criteria - New and in good condition and compliant.
d2499481-9d14-5264-934c-850af4126a78 | note | Frequency - Prior to order
3857a01b-ab2a-5255-a65f-3149e43c18b1 | note | Verifying Documents - Technical documents.
7b337ed2-0358-5132-b96c-bb258ded96a4 | note | Engineer / Client - R
fd2db748-153b-4f78-84f0-c44de6ae3248 | checkpoint | 2.2 - Chambers / pits
ec9e46fc-1e94-5ddc-9906-51761436b471 | note | Inspection / Test Method - Document review
36de8f99-f5bb-589b-88ce-ed59d62287be | note | Acceptance Criteria - ACO type pits with class D covers in accordance with the specifications.
c1e0db28-d939-515e-9f86-e7c5a049ada1 | note | Frequency - Prior to order
ae10e2c1-d827-5efd-a9d0-d15a262122fc | note | Verifying Documents - Technical documents.
3113c8f0-ec2b-5b72-a8f8-950b6b129429 | note | Engineer / Client - R
564280f8-2fe4-4723-9c66-442d02eed686 | checkpoint | 2.3 - Backfill material
4242c5b6-3c9d-48a7-a9c4-75df5f56efdb | checkpoint | 2.3.1 - Bedding haunching and overlay.
8ad41e5e-d5bd-58a5-948a-42a5124a6d6d | note | Inspection / Test Method - Inspection
eb78aaa9-4624-5b0d-ac8c-c4200bb1c190 | note | Acceptance Criteria - 5-14mm clean washed granualr mix.
89dbd2d3-dd09-57eb-9c34-19b99792e601 | note | Frequency - Prior to placement.
21455bff-9ee5-5c1e-be36-954c0073802e | note | Sub Contractor - H
aabdda04-b444-52fb-9c9a-dbc015151957 | note | Head Contractor - H
10dd18da-c8d4-4df4-a3e4-47756d314c80 | signoff | HOLD POINT
180ffc7c-c3e2-42a3-870a-dfd30ce52e84 | checkpoint | 2.3.2 - Fill to subbase
273d083a-0699-5c60-95ea-8e4dbac0f153 | note | Inspection / Test Method - Inspection
14c8eef5-6cf3-5e97-ad8b-fcece91ff804 | note | Acceptance Criteria - AP65 of other approved imported material.
7fa1ab46-4333-5909-a63e-acc20c3b488c | note | Frequency - Prior top placement.
d74c2b49-a702-5a4d-addc-a28687860827 | note | Sub Contractor - H
63bd70a7-7921-5cbe-a3c1-b9089d63e388 | note | Head Contractor - H
311ca08f-64bf-4324-984a-fc6e2655795b | signoff | HOLD POINT
d2c0f6f2-613f-405f-a980-42c3339c46e1 | section | 3 - CONSTRUCTION
24624f9a-9625-4a2a-a74a-5d4e3fb20071 | checkpoint | 3.1 - Set out
c3b56029-f3a0-5467-9eb3-f716630d9f2a | note | Inspection / Test Method - Document review.
706b957b-143e-5730-9f01-b2eb727615b2 | note | Acceptance Criteria - Survey setout of chambers / pits in accordance with the design - marked on site
0452319b-bd4d-5cad-a817-c6f69c15f986 | note | Frequency - Prior to excavation.
69e93275-b4b1-5c3b-aa02-ab24311cfc8b | note | Verifying Documents - Survey file / site inspection.
562df309-1b65-5645-9db3-1e42121a08e1 | note | Engineer / Client - R
7c35f53c-cd30-4415-9184-0eb4c1ad44d3 | checkpoint | 3.2 - Trenching
5670116d-0fe9-5e0c-bd44-4325e3c35d3f | note | Inspection / Test Method - Site inspection.
02f01c86-4010-59e2-b5e5-23bb50d5c595 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications.
8fda2a54-7def-5d2d-a170-264440583458 | note | Frequency - Prior to pipe laying
7f26f0a1-a8c3-54a9-ab2f-fabe38277016 | note | Verifying Documents - Engineer approval.
c020a9c3-6015-5ff4-9a1b-e0bc0d1f6839 | note | Engineer / Client - W
ef7c26cc-6ebc-4cc3-b7c7-77d5b1aad813 | checkpoint | 3.3 - Pipe bedding / haunching / overlay
1d69a4a7-0560-52d3-8de8-d58d14dd71a3 | note | Inspection / Test Method - Document review site inspection.
52641b79-040e-5cb3-987e-fedda38655cb | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
a86b6119-7f27-5004-b10e-1cd4be71b1ac | note | Frequency - Prior to backfill.
135d623f-74d0-5695-95df-191b00fe4af9 | note | Verifying Documents - Photos or site inspection.
d801bfd1-c6ae-5827-8390-99dd36060576 | note | Engineer / Client - W
c7abacc8-b2ab-42ab-9cf4-5b1a72e0d08e | checkpoint | 3.4 - Backfill
fed24ffb-f815-5672-b2cc-1ce0b7eaeadb | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
6152e951-d32f-5e31-9839-ddf0405d085b | note | Acceptance Criteria - Minimum 20 Clegg reading
4ed84c30-8c3b-510a-930c-eb427b234c37 | note | Frequency - Prior to placement of each layer of backfill.
15ae9123-5985-579b-8b33-73af01d92926 | note | Verifying Documents - Test records.
ed9bd38e-2e1c-5303-b281-4db61a0331a3 | note | Engineer / Client - W
ade47a6d-eafb-483f-b12a-dc74e7bd39f9 | section | 4 - CLOSEOUT
b7928382-b1c0-4d63-a2af-f5495a46dba4 | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
b2729f4f-d1f3-55c6-9b4e-a1dc61d3cf6f | note | Inspection / Test Method - Document review
60081bf4-95ea-588d-bd4d-1fb9c1eb6690 | note | Acceptance Criteria - Collate and supply producer statements
50e15224-f009-5a5e-b4b0-1e72f4fed981 | note | Frequency - Upon completion of Water supply works.
3eb19f47-2b9c-59ba-8c4b-adbd36bec176 | note | Verifying Documents - Producer statements
16489dff-2c88-50c4-9a21-da90f7ba8606 | note | Sub Contractor - H
1257ee1b-6080-511d-99cb-50efd49ea024 | note | Head Contractor - H
7ab8031e-6426-5eb6-b4fa-f54ee6707687 | note | Engineer / Client - H
ed88b46f-0de4-4184-9685-2153a8adc232 | signoff | HOLD POINT
9b320714-c79f-4d21-9ee6-d30526eff9de | checkpoint | 4.2 - Collate and supply Council inspection reports.
3d04c3f2-00db-5532-b459-6e4aedb18e4c | note | Inspection / Test Method - Document review.
4696b1c4-d57e-5fc4-a9e9-c3d09b62190d | note | Acceptance Criteria - Collate and supply Council inspection reports.
195606ac-2108-560a-b7fb-4b0748c14f1f | note | Frequency - Upon completion of water supply works.
1163cdb4-2466-5380-92d3-4dd62186595f | note | Verifying Documents - Inspection records.
888d85fc-922a-59c0-9d4e-2097cf06ea85 | note | Sub Contractor - H
132d92c4-a8c1-50ad-b2b2-dde6c4c0b19b | note | Head Contractor - H
a682ab14-a73d-5251-916d-b5b8cf897204 | note | Engineer / Client - S
73153704-fd85-4bf2-a689-fa58fa068be9 | signoff | HOLD POINT
73272210-fd4b-4aa2-8258-35256a7adc9d | checkpoint | 4.3 - Collate and supply compaction records.
b19f506a-51f5-5965-9c21-9cbb2e01c112 | note | Inspection / Test Method - Document review.
7fbfd2e3-8496-5236-9594-8fbe2c812fee | note | Acceptance Criteria - Collate and supply compaction records.
be3724e2-1103-5071-8378-14e5a7cdae25 | note | Frequency - Upon completion of water supply works.
ad1fff5c-3f30-55c3-8938-ae796d3452f7 | note | Verifying Documents - Inspection records.
c9297d29-a2a7-56aa-a9a1-05498b912ffb | note | Sub Contractor - H
09412ac6-b763-5daa-b627-676ed3ebdf6b | note | Head Contractor - H
d7446c41-ccbe-5f9a-bc2e-3a51c16dc941 | note | Engineer / Client - S
10f4fa18-8858-48b6-b9a3-09d681d0f453 | signoff | HOLD POINT
3e229892-8a40-4c7e-959f-671e94f7c7f6 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
4d1f035d-4144-528f-a91d-96a19004cdb7 | note | Inspection / Test Method - Document review / as builts
ce2d8471-19b9-501b-afa8-c3e42484bcc1 | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
acc6a862-7042-54ad-bc0c-131ae066c031 | note | Frequency - Upon completion of water supply works.
b71faa56-79b3-5c90-b2c7-2bbd8219a409 | note | Verifying Documents - As-builts / test records.
d90154ea-08fa-5c70-94bc-b1391cc36483 | note | Sub Contractor - H
bff972b1-b7f6-523f-b4f6-e97227c1562e | note | Head Contractor - H
727177f6-9283-529e-a19e-a7f1881d27dc | note | Engineer / Client - S
e2fc9e61-ec90-44c1-bd6b-19716a1e319e | signoff | HOLD POINT
49427f2c-6b44-4184-894f-f9e5bdb69664 | checklist | ITP - STORMWATER Rev 0 | itp | ITP - STORMWATER
6efda515-9255-4745-9070-7a4eb5a0c875 | section | 1 - PRELIMINARY / GENERAL
32f79df0-f5fd-4427-a882-273ed19561f9 | checkpoint | 1.1 - Consents and trench opening notices
58d11952-dbf5-5f38-b535-2b9d16c88758 | note | Inspection / Test Method - Document review
42d67a46-5b96-5b31-bcb7-39669913f022 | note | Acceptance Criteria - Authority approvals.
d32be9be-2c2d-56e8-a4f2-a8c4c6709570 | note | Frequency - Prior to excavation
d7a85298-8a8d-5ddc-b9ae-ab0b48f6fa67 | note | Verifying Documents - Approval from relevant authorities.
a4950221-4860-5a06-92c5-678508c28c37 | note | Engineer / Client - R
12f40e6c-78de-4c16-928b-635afbeb84ec | checkpoint | 1.2 - Drainlayer registration
ebd47d2b-5ef3-5d9f-8cad-35d78b377c8b | note | Inspection / Test Method - Document review
25a2ecd1-5b18-5619-b872-82be6193252b | note | Acceptance Criteria - Certification
e02a62e1-101f-56aa-b1a4-1b5c13fe1cd3 | note | Frequency - Prior to drain laying works.
f23deca5-b35b-51f3-b31c-5bdbb26cdd2b | note | Verifying Documents - Scanned copy
01fd5c88-4d35-54df-a79f-30aa23d7bee2 | note | Engineer / Client - R
a44b3b45-f616-4684-a70e-571533443482 | section | 2 - MATERIALS
d4b30362-07f8-4305-a526-57af89eba3e7 | checkpoint | 2.1 - Concrete pipes
aa1f8a49-ad54-59d4-9533-9d112413d79a | note | Inspection / Test Method - Document review
24ccdaaa-2509-57b7-a105-5b6d89ceb0c0 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS4058 reinforced cast rubber ring jointed, class 2 uless otherwise noted.
ec70cbd2-179d-5545-8624-7d2cbd7f884d | note | Frequency - Prior to order
63901067-6636-5d9e-b5c9-ba1a8cae60fc | note | Verifying Documents - Technical documents.
84cc1046-dbd3-50ef-91e4-868fd188bc5b | note | Engineer / Client - R
92946b5e-3dc3-468d-876d-bac85a6eb966 | checkpoint | 2.2 - PVC pipes
74b27791-3e41-5336-8292-b943c6316cc8 | note | Inspection / Test Method - Document review
70bfbd9d-adfc-58e6-8cf3-3858799519ec | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
a1485e0f-292e-54e5-b92b-b8a034d64ffc | note | Frequency - Prior to order
4d8c4e6f-eca3-5d84-aab2-78f331f573c2 | note | Verifying Documents - Technical documents.
c1f55f65-94ee-5a7b-8b7b-a9046b2ffd93 | note | Engineer / Client - R
7ac42ece-6be4-4ea3-ad21-14b959854391 | checkpoint | 2.3 - Precast chambers
c9223381-ea0d-5119-a257-38fb45300839 | note | Inspection / Test Method - Document review
d4466fd1-c9e1-5b11-929d-2624991217c7 | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN- HO-72 traffic loadings in roads.
821b054c-7e59-5172-a306-046ed9da39dc | note | Frequency - Prior to order
b89900a6-e030-58ea-9539-569831a1ccbc | note | Verifying Documents - Technical documents.
d404b5bf-19f4-54df-a51e-91c01f6ed72c | note | Engineer / Client - R
703f493b-34c3-4b43-b675-e5b7522f4db9 | checkpoint | 2.4 - Access covers and frames
f3c644b9-1841-57b7-8d9a-147a4c9206b4 | note | Inspection / Test Method - Document review
6485c2ca-b3a9-5a3c-9e2c-34c7c539a021 | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
6695fc37-816f-5a38-896d-c7ee1b904028 | note | ○ Designed to minimum AS 3996 Class D or better.
3833b5dd-d6a1-568f-bf2f-13672b88c743 | note | Frequency - Prior to order
65821d13-3c9a-5154-9562-4a88d4cb5a21 | note | Verifying Documents - Technical documents.
faea6b0a-dee7-5378-b585-978bc6b017a5 | note | Engineer / Client - R
1e9ac5ea-d70a-438c-8903-4ec20d1963bb | checkpoint | 2.5 - Sump grates
b02602d7-66fc-5d2c-b7de-25baaca7760d | note | Inspection / Test Method - Document review
3eeed869-622a-5d2a-bfcd-cb4cf1ff306b | note | Acceptance Criteria - Complaince with HDC ECoP.
c4b54dbc-8835-5f6e-b93e-dd6c7935bdf2 | note | Frequency - Prior to order
057d551a-e7eb-5025-a63c-7d88a25bab25 | note | Verifying Documents - Technical documents.
b3b4b7cf-8cd0-5dab-a3e8-4aa789a1bda3 | note | Engineer / Client - R
ed7e9e55-3227-4420-b1ed-049adacfe8bf | checkpoint | 2.6 - Concrete Wing wall
a4ab638e-e7e7-56e2-bc9f-f41babf6654d | note | Inspection / Test Method - Document review
99839714-b9e1-5a9c-b2c1-145ff9e21198 | note | Acceptance Criteria - Compliance with NZS 3109 with surface finishes to
d5b87b76-e838-59f8-b7ca-d41a67e479be | note | Frequency - Prior to order
f23da868-e468-56ca-8b53-d45af0522e2d | note | Verifying Documents - Technical documents.
616e061b-f8eb-58d6-9c5d-2c30b01f2fd5 | note | Engineer / Client - R
fff9b4a0-93fb-40cd-9570-419bac23e2dc | checkpoint | 2.7 - Backfill material
2574e841-6f17-4beb-8443-b345f2364484 | checkpoint | 2.7.1 - Bedding haunching and overlay.
ab405247-ab55-5d58-84e9-f698537b0a24 | note | Inspection / Test Method - Inspection
5a8921f1-f385-52b3-8531-a4d6cec236d8 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
58fa8204-c58a-5a0b-9aae-298492c452e2 | note | Frequency - Prior to placement.
f300875f-72c5-5036-9c5f-9ff6215c487b | note | Verifying Documents - Engineer approval.
14ad3d38-9c7f-5308-b93b-f9bfa8f82405 | note | Sub Contractor - H
940170a4-8cd4-5a70-80f6-7277da7de549 | note | Head Contractor - H
2c6520b7-94e3-52ba-81ce-4555686ba101 | note | Engineer / Client - W
56290811-51dd-4e01-aa57-e87ad2fd8e79 | signoff | HOLD POINT
56a085a0-b1f1-4caf-91c4-2eed7aae1772 | checkpoint | 2.7.2 - Fill to subbase
bca348d4-20e6-55b9-ad64-69676b35eee1 | note | Inspection / Test Method - Inspection
92debe69-b413-5b82-a198-295b153a254c | note | Acceptance Criteria - AP65 of other approved imported material.
a00df213-fa29-5bed-896b-c2e3fcf06db8 | note | Frequency - Prior to placement.
cbef8e06-dcd3-5186-9207-e688bd2475a7 | note | Verifying Documents - Engineer approval.
5487dfba-2e75-5052-8a02-25b65e81e169 | note | Sub Contractor - H
880d47b8-218b-5cca-9777-a3a95e08f23a | note | Head Contractor - H
a2cbd304-4722-524c-ac40-22449f200fb4 | note | Engineer / Client - W
bf73fcd2-6324-43fa-848e-9ed8331f8847 | signoff | HOLD POINT
3f4f959a-69e9-4099-8dba-ad9ee947f9cb | section | 3 - CONSTRUCTION
7c8d18b0-ff89-4674-afd6-55444aa339a0 | checkpoint | 3.1 - Set out
f101e1ec-d5bc-5fed-86e4-676f122eea5f | note | Inspection / Test Method - Document review.
06085c63-d0a6-59ed-87ba-2e6a99e47d23 | note | Acceptance Criteria - Survey setout information in accordance with the design.
b6667fb8-dd8d-5e00-8f2c-825ed26bffea | note | Frequency - Prior to excavation.
9c2d194f-072e-50e9-ab6d-7d7277c3d7a4 | note | Verifying Documents - Survey file.
e152f3c2-5939-58dd-8081-f8c10ce03e1a | note | Engineer / Client - R
cfd24eb1-c807-4654-bd44-f47a95c2d95e | checkpoint | 3.2 - Trenching
e7e2186c-967d-5840-b3ad-422df060d58d | note | Inspection / Test Method - Site inspection.
205a8ffa-8083-54b9-8822-9b1449842a51 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
cbbf4617-64a1-54c8-85fb-2d0b00287fd8 | note | ○ Min widths:
564f72b0-c6e8-5de0-b7ad-9e86682fb3ad | note | — pipe dia DN75 - DN150 = 350mm width,
8c65fd3b-a317-5072-b3a0-5ef6035c1f1c | note | — pipe dia DN150 - DN300 = 450 - 600mm width,
6a74031a-1ac3-5541-9119-41648f705810 | note | — pipe dia DN300 - DN400mm = 700 - 850mm width.
840a14b2-060b-5054-9752-aedd1e4c2fbd | note | Frequency - Prior to pipe laying
84ed7905-bf01-525d-a84f-921a433408e3 | note | Verifying Documents - Engineer approval.
09537064-7ddf-580b-97b2-7d269d8a9c18 | note | Sub Contractor - H
29d4f169-451d-5347-9aa0-84a91d08ae70 | note | Head Contractor - H
203049b5-ba47-5e61-ba75-8756554529dc | note | Engineer / Client - W
909416a4-2b20-46dc-bdfe-a777509f6c87 | signoff | HOLD POINT
99688c7f-a4c2-4af1-b717-15dcc191552e | checkpoint | 3.3 - Pipe laying
22218bc8-1f7c-5ce1-b3c7-0b9a8214280f | note | Inspection / Test Method - Survey
948b10df-aa9c-5288-8e56-e08d663fabe0 | note | Acceptance Criteria - Record level of main upstream and downstream of each chamber.
e2775b21-edba-5483-adcb-f393ce47b452 | note | ○ Maximum discrepancy +- 10% of design gradient, and maximum +-15mm from design level.
5e9e8b91-10f3-583d-835c-27050fe9d4b3 | note | Frequency - Prior to backfill.
9acebefd-d7a0-5bbc-8695-b0e792644433 | note | Verifying Documents - Survey as builts
5d0b24ca-e9e2-5ccd-aa27-c88a9e780707 | note | Engineer / Client - R
21beb6ea-0faa-496b-b23c-f7724c073a3b | checkpoint | 3.4 - Chambers / sumps / wingwalls
242cc820-467a-55a1-a752-973a4ea429df | note | Inspection / Test Method - Survey / site inspection.
a3b61a4c-a286-5f1a-884f-b7b85307f827 | note | Acceptance Criteria - Benching in accordance with specifcations and drawings. Position in accordance with the design
6f1f69b5-ab91-5d77-a170-f728d65f34ad | note | Frequency - Prior to backfill.
52494458-c4e3-51ed-8fc4-2c6261531e5f | note | Verifying Documents - Engineer approval.
fe092234-18a4-5937-ad58-08463c32b8fc | note | Sub Contractor - H
0e0dd57b-15fe-51e9-8142-d35fe46d836f | note | Head Contractor - H
22650b4b-216c-5b3d-988c-4e3f1474b3e0 | note | Engineer / Client - W
0b4a07d8-db8e-4df2-a4d5-3fddcdeedc61 | signoff | HOLD POINT
08a0a230-9b7c-40f5-8973-6941bde1e871 | checkpoint | 3.5 - Pipe bedding / haunching /overlay
08ba39bf-f6fb-5f4e-b596-81edd5e877e9 | note | Inspection / Test Method - Document review site inspection.
9662b84a-f841-5591-83f0-2c41eeb57e5f | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines and AS/NZS 3725 for concrete pipelines.
59a477a3-9787-535c-abff-fc748119478b | note | ○ Bedding minimum 100mm up to 450 diamter pipe and 150mm pipes > 450mm.
95fddc14-0416-5f18-8066-0a0548566cad | note | ○ For PVC overlay >100mm over pipe and for concrete 1/3 diamter of pipe.
475c2992-64ee-5c25-8039-c515819bccdf | note | Frequency - Prior to backfill.
22f081c2-8b71-5b31-821a-b52943c65c33 | note | Verifying Documents - Photos or site inspection.
3fea2789-7327-52d4-87e5-81193cec0643 | note | Sub Contractor - H
da75e263-3091-5e6f-a6dd-60935927fdbc | note | Head Contractor - H
56e506ef-cd06-5684-ae5d-6a7ac6d87c33 | note | Engineer / Client - W
c4a9f4fb-a22d-40d1-94de-666fac3fb83c | signoff | HOLD POINT
e9363d36-d550-4c80-b201-0cb5767a6d72 | checkpoint | 3.6 - Backfill
eead4c03-41ff-560a-8741-3d5ff99b666d | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
aa738d67-1da7-5ccc-ae2f-09b7427a4c5a | note | Acceptance Criteria - Minimum 20 Clegg reading
8cc089fd-20f1-5fbe-adc0-06a3c900708e | note | Frequency - Prior to placement of each layer of backfill.
653c29cb-583a-50ac-bcd9-712a6501527e | note | Verifying Documents - Test records.
ccc2375f-021f-576e-8c5e-72d6bd14458b | note | Sub Contractor - H
45709f23-1652-50be-94ad-a243d59be49b | note | Head Contractor - H
f612a2cc-c804-52e1-9959-923fc56fb096 | note | Engineer / Client - W
28651bb5-20ea-4f23-b642-e9b4fbe97120 | signoff | HOLD POINT
a5379bff-9f33-4419-a5d5-f937994a5b5d | checkpoint | 3.7 - Hydrostatic testing
8fdd2ce2-00db-5c02-8d40-72db7a68ddbf | note | Inspection / Test Method - Document review site inspection.
b95d34a3-d27d-53ea-8616-9b876803ae28 | note | Acceptance Criteria - In accordance with NCC CoP and Engineer specification
b793225b-4d10-5964-be54-da971576e6ef | note | Frequency - After backfill/prior to road seal.
88b8dd49-701e-5424-9f8e-c820eb2b25eb | note | Verifying Documents - Test records and Council inspection records.
b8475ef4-0208-51c4-af06-5d06b6ecca10 | note | Sub Contractor - H
dad3d8ba-8562-5af8-b86d-8582b282fc81 | note | Head Contractor - H
4a63df0f-8ca2-5bb8-a4f6-f4cace3b9e9a | note | Engineer / Client - H
8f3f9fd2-9549-4aca-8809-82c59127e44f | signoff | HOLD POINT
dd1c2f4a-2dc6-4b10-ac9a-e6435e5cc20f | checkpoint | 3.8 - CCTV
b7f6d865-1cff-5cd2-8102-55d11555bcd1 | note | Inspection / Test Method - Document/video review
d3e8993c-7888-5f45-90cc-ce957b950ee2 | note | Acceptance Criteria - In accordance with NCC CoP and Engineer specification
3bfc018b-05b5-5720-9a07-c054f6b14c16 | note | Frequency - After backfill/prior to road seal.
970ed23e-adae-5cec-a4ad-a1345f4cfa48 | note | Verifying Documents - Test records and Council inspection records.
432a4544-778d-5cf2-b153-bb289a9dc14a | note | Sub Contractor - H
a06f92a6-b700-5423-9400-237cb8b15e75 | note | Head Contractor - H
703d0e60-8ceb-5cef-beb9-7f7b5b1c7ec6 | note | Engineer / Client - H
6aa40378-2fd2-4a0e-b046-96b08e0f9beb | signoff | HOLD POINT
1cd8afd5-ad0a-4213-9311-6d6a0d655e20 | section | 4 - CLOSEOUT
1b33dbab-9df9-4a3b-af19-3174cca34acd | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
2388ecc2-6ec9-5bfe-a64f-dc4b0be0fa74 | note | Inspection / Test Method - Document review
f6bab6c1-f9c9-531f-b8a4-554be46738af | note | Acceptance Criteria - Collate and supply producer statements
00a038d9-b485-56c3-aa22-ebc586377011 | note | Frequency - Upon completion of stormwater works.
2ba5c23e-7329-5a90-abdb-b1abf23e2379 | note | Verifying Documents - Producer statements
e948b87c-90c4-53eb-a5a7-2bde2ca6f66c | note | Sub Contractor - H
881c093d-79aa-5da3-916c-20d88c9c6d5d | note | Head Contractor - H
cd4066bc-97d1-5dd8-b23e-3b11a7a00ba4 | note | Engineer / Client - H
b3d29d88-c124-42d1-b6ef-09408bdcd194 | signoff | HOLD POINT
58445cdf-8fe5-4401-8b9b-ef008d12c6a8 | checkpoint | 4.2 - Collate and supply Council inspection reports.
acec829e-5b7b-57ea-ae28-8ffa7e0121ad | note | Inspection / Test Method - Document review.
ee322a41-82e0-50fe-aaa3-8168c9106ebc | note | Acceptance Criteria - Collate and supply Council inspection reports.
e134e30d-8e30-54cb-a919-a0d1e9d6bed0 | note | Frequency - Upon completion of stormwater works.
9a19ba1d-10e5-5e64-bc0c-3fef642de386 | note | Verifying Documents - Inspection records.
5df2fbbd-99dc-5c48-85c7-0d1773dfedfa | note | Sub Contractor - H
a48c4957-7e90-5c2c-9dd9-726f8ca05cb7 | note | Head Contractor - H
58ba9933-6aaf-5c82-94cd-23c0d6632b7d | note | Engineer / Client - S
eeb4f109-4e88-4e19-b35c-60ad3758d28a | signoff | HOLD POINT
0f5e2420-292e-42d1-84c8-1c8de7a0ffe5 | checkpoint | 4.3 - Collate and supply compaction records.
93e6891f-b494-54dc-9e85-8c8f5d2967a2 | note | Inspection / Test Method - Document review.
0c540fa0-f116-56ff-b581-7e0166c08d16 | note | Acceptance Criteria - Collate and supply compaction records.
c11519c6-62b8-5c7c-a883-61feacee325a | note | Frequency - Upon completion of stormwater works.
ebe5595d-6ccf-5602-8da5-6f27ce8b410b | note | Verifying Documents - Inspection records.
e7862053-2451-51ce-92e1-ff8731d6ff69 | note | Sub Contractor - H
fbcfb3c5-735d-571f-be19-ae73d503cfc5 | note | Head Contractor - H
28172e24-dcc0-521c-91b0-6d573dcb2ad3 | note | Engineer / Client - S
713e2164-b452-48d5-94f1-bdb31e73ec81 | signoff | HOLD POINT
c8478371-ba0f-44cd-9019-ce80a4876ab3 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
c341d11b-11b4-5233-8420-f971ca39c19c | note | Inspection / Test Method - Document review / as builts
96130006-285a-52a7-a50e-33238d7c225e | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
a42d7ba1-641d-5561-9bb3-88ceb0f17e69 | note | Frequency - Upon completion of stormwater works.
2dd2f2e6-0a16-510a-9275-66c710b79847 | note | Verifying Documents - As-builts
ad892a19-b8b6-5f5a-ae0f-cb6f1b9f4c89 | note | Sub Contractor - H
375b648d-13a9-532c-a2f9-3a06deb39a11 | note | Head Contractor - H
f3906a81-f43b-5e8e-85f5-baf983714d52 | note | Engineer / Client - S
9280a581-7fe7-4c00-ba37-a3dbfce383bb | signoff | HOLD POINT
32fd55e8-d7e5-4b3b-a843-b28a1cc27bac | checklist | ITP - WASTEWATER Rev 0 | itp | ITP - WASTEWATER
2e6d10ea-8e17-4e37-8dc9-83bc2da8d3b0 | section | 1 - PRELIMINARY / GENERAL
e00f95c6-d8f9-429b-8f13-8e850667abc1 | checkpoint | 1.1 - Consents and trench opening notices
ca3b44fe-d278-533c-9881-ecddef257738 | note | Inspection / Test Method - Document review
a0042fb8-beb1-5c1a-87c8-1fc950c083b4 | note | Acceptance Criteria - Authority approvals.
c3286326-4ccc-5ded-a7a6-caeb447c8668 | note | Frequency - Prior to excavation
f20cd56d-6c1b-5e10-b145-f6e51dcb567f | note | Verifying Documents - Approval from relevant authorities.
39b05a4f-0101-5da2-afb8-3bc216c581f9 | note | Engineer / Client - R
bc584036-de48-4f1d-811c-6a3554547c9a | checkpoint | 1.2 - Drainlayer registration
9798dad3-0a74-5626-92a1-7ba9c2b9a677 | note | Inspection / Test Method - Document review
94593d99-720c-5eeb-8411-aca3242b065b | note | Acceptance Criteria - Certification
21c8d843-da1b-5766-b0d5-cefd8c05889c | note | Frequency - Prior to drain laying works.
e319d118-205a-5437-a8ab-7c1a44410b85 | note | Verifying Documents - Scanned copy
13ff70d3-7b0d-5ee2-bbcc-13a5c6f34fdd | note | Engineer / Client - R
17b11906-0735-4bd8-984b-8885dd370e40 | section | 2 - MATERIALS
ec447603-4cca-4a66-ad2d-8bdda4104d31 | checkpoint | 2.1 - PVC pipes
bd14cac6-4435-514f-ab56-5969cceda724 | note | Inspection / Test Method - Document review
fc5aaa91-6810-5e63-a3dc-783481993f5e | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
88ae99e6-722a-58e1-ae4a-4a9820a6f392 | note | Frequency - Prior to order
3ce168fc-ded6-5a84-9026-306998578798 | note | Verifying Documents - Technical documents.
2ec236dd-4317-5a25-84d2-3703909615ff | note | Engineer / Client - R
1a3db6ab-2ff0-423c-b577-201fbbf5ab79 | checkpoint | 2.2 - Precast chambers
97249ef4-3f3f-5d9c-aa3a-c07d269b5c19 | note | Inspection / Test Method - Document review
0d6f8efd-dbbb-5ecd-a196-44f504106534 | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads.
5fe9c02f-e971-57ff-8387-08a3e953f348 | note | Frequency - Prior to order
94f48030-00b9-5c6b-b4b9-b28d22cf8d28 | note | Verifying Documents - Technical documents.
dc42f56b-8b9c-5676-a148-fff2454e9f4f | note | Engineer / Client - R
e9625223-65f6-4242-8348-01dd48f4d8dc | checkpoint | 2.3 - Access covers and frames
e6ced649-9eab-548c-9615-804b29d059dd | note | Inspection / Test Method - Document review
78f5ece6-caff-5dcc-8d52-33c9549de17b | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
97c20740-b845-553a-b5ee-8195e675bb40 | note | ○ Designed to minimum AS 3996 Class D or better.
adbfd1f7-9170-5946-980e-b677950e3fab | note | Frequency - Prior to order
0e684c10-39c3-506e-9d79-8863612bfee4 | note | Verifying Documents - Technical documents.
2550a466-a4c9-506f-af4f-ce9ffc02a741 | note | Engineer / Client - R
c1610bbc-c390-4360-b8c2-a0bdd9979620 | checkpoint | 2.7 - Backfill material
b37ecc2f-8c96-4ceb-bee2-0887268dbe05 | checkpoint | 2.7.1 - Bedding haunching and overlay.
5055ff4f-e5e9-540b-8612-696a35eb7ca7 | note | Inspection / Test Method - Inspection
960f1749-b6b5-543f-8e3f-c13600a173b5 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
0f011d28-81b8-548f-91be-0e6e7cb71219 | note | Frequency - Prior to placement.
737abfe3-6529-5d3d-8c3e-efa89d8c439d | note | Sub Contractor - H
00b06631-bf21-55f4-b86a-511086b26c75 | note | Head Contractor - H
6f1f7d53-b543-56a4-9fc9-9aacc751f17e | note | Engineer / Client - W
b7b5247d-dad3-4571-b5dc-2b403531292e | signoff | HOLD POINT
66841fbf-dfc1-4092-8876-3ad40bb6055e | checkpoint | 2.7.2 - Fill to subbase
e9b36a28-a6ca-5951-bc97-f90807eb4561 | note | Inspection / Test Method - Inspection
2b05d3e6-4411-58cf-8755-10f165d7fc60 | note | Acceptance Criteria - AP65 of other approved imported material.
2e8743ea-d34d-518e-bfb5-74196c4dfd89 | note | Frequency - Prior to placement.
83b696d1-8379-5a4a-bbb6-287d7c505e1b | note | Sub Contractor - H
930c9c75-b037-5a65-a522-625b4c3f0a90 | note | Head Contractor - H
37bc440a-6955-5d61-94db-74802d8aa618 | note | Engineer / Client - W
1a52b660-3a3c-4aea-a017-9fb18fd74bd4 | signoff | HOLD POINT
78014230-c7d5-4e7c-a649-e97cb1ca04d3 | section | 3 - CONSTRUCTION
5fb7e7bc-2d57-4041-aca9-24ec37560055 | checkpoint | 3.1 - Set out
8e8a46a4-9d49-52f6-9b15-cdc2102cb9df | note | Inspection / Test Method - Document review.
e293f279-bab2-58f9-a7a0-b42255cdeb2c | note | Acceptance Criteria - Survey setout information in accordance with the design.
fa684904-b0e1-5773-9fa5-c4c3b54bbecc | note | Frequency - Prior to excavation.
f8952537-c633-52e5-978b-d26b1ad42980 | note | Verifying Documents - Survey file.
7f4cc063-c13c-5ac5-8efd-6da7c5e34a99 | note | Engineer / Client - R
5f2832c4-5e5c-4bcb-a915-0e76510022d5 | checkpoint | 3.2 - Trenching
31ed9eec-1242-5334-9ebd-4e40b4ee0f1f | note | Inspection / Test Method - Site inspection.
3bc9f590-abc9-5574-99fc-a81bfd35b3c8 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
37d65701-bff5-5250-8992-c1b9c6c401a7 | note | ○ Min widths:
d1d43754-2839-58b9-83f3-2b235f7f0205 | note | — pipe dia DN75 - DN150 = 350mm width.
b66806b5-f978-521a-98e6-169b3b4081d8 | note | Frequency - Prior to pipe laying
f505f140-5fab-5812-a101-3ee8e59bf4d3 | note | Verifying Documents - Engineer approval.
34edad07-1197-5b35-8495-fb7b65761816 | note | Sub Contractor - H
f2f59524-128b-5d12-93b1-dd6c4686ba52 | note | Head Contractor - H
4d2f4106-1f56-57e2-8a14-cf39647a8eb5 | note | Engineer / Client - W
5b432648-921a-4654-9a6f-769f6a000f02 | signoff | HOLD POINT
ede1c453-3193-4c73-a793-34e948f5c4cb | checkpoint | 3.3 - Pipe laying
55abef82-babe-5044-9e72-7b8b5d1ef386 | note | Inspection / Test Method - Survey
13026fc2-8097-533d-b5bd-a3e2bc25b056 | note | Acceptance Criteria - Record level of main upstream and downstream of each chamber.
29df168e-cb2c-533a-a6f5-8d5c0d0ab607 | note | ○ Maximum discrepancy +- 10% of design gradient, and maximum +-15mm from design level.
87903c20-5477-5f7d-9095-cc04e7e846fb | note | Frequency - Prior to backfill.
d146e1bc-d938-5004-9e79-c28108977b25 | note | Verifying Documents - Survey as builts
68268765-fc0f-5928-a535-297e9f71a620 | note | Engineer / Client - R
891fe4cf-f6a5-4548-ac0e-19aecd0f404b | checkpoint | 3.4 - Pipe bedding / haunching /overlay
7416da3c-e428-5e71-b640-6e6720cf78f7 | note | Inspection / Test Method - Document review site inspection.
659abc82-b0c7-5624-89cf-85f07c0abf5a | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
e8cd2b73-cc65-5ccc-8db3-e011b2717cb4 | note | Frequency - Prior to backfill.
67570f73-4929-5297-973b-97428fe9a324 | note | Verifying Documents - Photos or site inspection.
1324f7e5-9fc6-5371-8585-b0379b2f39e9 | note | Sub Contractor - H
5b7f01ba-5435-52c2-b9de-d3fcb436c7af | note | Head Contractor - H
7c89a5bc-b36b-57df-a67f-1f5f05fc39d5 | note | Engineer / Client - W
8a91f547-24e4-4329-8801-4a1c2bc762e4 | signoff | HOLD POINT
833825e5-de91-404c-a979-23ae882d16fb | checkpoint | 3.5 - Backfill
023428a9-5e28-5fa1-8c22-c0ecdbb77f12 | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
c9ec3e59-2a08-5f52-90cb-52099f31cccc | note | Acceptance Criteria - Minimum 20 Clegg reading
151db822-98fd-51a6-998a-1de3f3f2de63 | note | Frequency - Prior to placement of each layer of backfill.
cc29ac21-09a7-5af9-9f4f-d3cf85ed0cd4 | note | Verifying Documents - Test records.
b44f8c8e-2aca-5e59-8d33-3f716cfa347c | note | Sub Contractor - H
dfdab83e-b364-55cb-8ff8-7d9f7d7c848c | note | Head Contractor - H
d9f91c0f-4523-532b-9244-213abbe87a00 | note | Engineer / Client - W
057c2a46-9506-4d4a-9ac9-9acffa1aab5d | signoff | HOLD POINT
4da3956c-d1be-4222-bcea-4a40da8550f7 | checkpoint | 3.6 - Hydrostatic testing
8939252f-61ca-54fe-abda-9fee032489e1 | note | Inspection / Test Method - Document review
f088790e-575d-5d26-8e77-77ba66d5ed14 | note | Acceptance Criteria - In accordance with AS/NZS 3500.2 section 15.2
f91735b9-9fb9-5b16-b33e-e2bcb6075311 | note | Frequency - Prior to backfill.
e1b41c43-14e2-5570-9695-ef8c3e9e0dc3 | note | Verifying Documents - Test records and Council inspection records.
015344b4-945c-50b9-8df7-9ab36660f8e3 | note | Sub Contractor - H
0664c263-7e88-5c1a-9236-9f33a9db85ef | note | Head Contractor - H
df82f9d2-f081-5828-97c5-a7748f082d25 | note | Engineer / Client - H
8dae0c69-255e-419c-a943-f1c812ea8d39 | signoff | HOLD POINT
75e84767-cc83-4385-95ac-0185614745e1 | checkpoint | 3.7 - CCTV
95202881-dacb-5739-a6e5-7d4deca3da99 | note | Inspection / Test Method - Document/video review
23439e17-224b-57a3-abc9-54fe52be2dbb | note | Acceptance Criteria - In accordance with AS/NZS 3500.2 2018 section D1
cf4eba89-84f1-59e0-9685-bad2f5292701 | note | Frequency - After backfill/prior to road seal.
b059c2e2-dbbe-599e-90e9-dc800a38e3ef | note | Verifying Documents - Test records and Council inspection records.
80649fc2-608e-5b89-b209-eedee14ede09 | note | Sub Contractor - H
c19136df-b719-5da4-b534-9f6863f316c4 | note | Head Contractor - H
1d4ed319-eb0d-5cfc-a9e2-4ad98549321e | note | Engineer / Client - H
2f9c8cda-d6ac-4012-ae3e-a1d2b98d433b | signoff | HOLD POINT
b52b1a24-5de4-44f3-903c-7271acf1ed91 | section | 4 - CLOSEOUT
5afc3cc3-ab16-4e64-accc-d48228c7c1ef | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
f0000280-4c84-57d0-9679-ef40a230aa90 | note | Inspection / Test Method - Document review
a02cf704-875e-5975-b67e-cb2e58d135cb | note | Acceptance Criteria - Collate and supply producer statements
a21956c0-2dd7-5e7f-a873-7baca7056f96 | note | Frequency - Upon completion of wastewater works.
3bf0e7aa-0bc0-5238-a2a6-468a0a6ffb05 | note | Verifying Documents - Producer statements
24e316f7-0436-523e-b35e-3f2a1b3e74d3 | note | Sub Contractor - H
4d19524e-5cce-5510-9134-9b32d9f8fbd3 | note | Head Contractor - H
6633e728-db56-582e-a68d-6430fc92a8c1 | note | Engineer / Client - H
60beff78-1bc9-44c2-be16-bd5d535477c2 | signoff | HOLD POINT
c2cfe096-783a-4a08-857d-d0b1ca331ad3 | checkpoint | 4.2 - Collate and supply Council inspection reports.
93e757e4-5312-520a-8fe5-ee40783593ce | note | Inspection / Test Method - Document review.
54d0a837-3818-53f2-8efb-9226778cb628 | note | Acceptance Criteria - Collate and supply Council inspection reports.
4ffcb963-4e5f-5abe-93d0-7d3c58cbdb74 | note | Frequency - Upon completion of wastewater works.
e0a2d829-9f58-50f8-babd-cace7883af0a | note | Verifying Documents - Inspection records.
79dbebd7-0c12-5207-8aed-afd96330ade5 | note | Sub Contractor - H
d92ebbf9-896d-5a96-8c2b-7ee076718e89 | note | Head Contractor - H
7e7f1b12-30c6-5c7d-b43f-225bbf557df5 | note | Engineer / Client - S
3e1cfc6a-d129-44b0-a770-61e3403f0012 | signoff | HOLD POINT
a3e8b589-6352-4ce0-bfeb-5a413a1f5269 | checkpoint | 4.3 - Collate and supply compaction records.
65613270-cd6d-507b-a7e3-34c3dd1cad2f | note | Inspection / Test Method - Document review.
ce5b88a7-0dfe-5bd7-a881-43c054c1294a | note | Acceptance Criteria - Collate and supply compaction records.
ab1896a7-ad73-564d-a709-fdd80c029228 | note | Frequency - Upon completion of wastewater works.
a3c1fdcc-97ef-544d-a033-d3374cacde1e | note | Verifying Documents - Inspection records.
101a5a3f-f0f1-5804-94d4-e027da434839 | note | Sub Contractor - H
1c0983b8-c67b-5e2c-adda-b2160a7b4e99 | note | Head Contractor - H
6bd3d11d-3077-5da4-9010-0d553131d9fc | note | Engineer / Client - S
6eb4ae19-7f2e-4833-a45c-e041f6a3cb3d | signoff | HOLD POINT
b002334b-c235-4ee3-90f5-97522dd422d4 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
d5b11304-dbc9-5442-8490-956da6536213 | note | Inspection / Test Method - Document review / as builts
ed50f8ad-e584-5f42-a047-889035da9dfc | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
2dafbbf5-dc0c-51d0-80ec-d213946b6213 | note | Frequency - Upon completion of wastewater works.
153e0484-b269-5dd7-8e9c-b8e8e2da81fc | note | Verifying Documents - As-builts / test records.
d9b95000-a529-578d-8ef1-59ad5a3e3822 | note | Sub Contractor - H
c10c0593-fd6e-5fb1-bd4e-dfda440def4a | note | Head Contractor - H
8e7cee4f-6da8-5ed2-b0fd-0177ddebf654 | note | Engineer / Client - S
6be52e7c-6e28-467e-81ab-b5e548f15440 | signoff | HOLD POINT
cd5be06b-5b35-4309-8186-fc235fcf8bf6 | checklist | ITP - WATER SUPPLY Rev 0 | itp | ITP - WATER SUPPLY
b88719dd-75fe-4ac6-8bf0-1057701d6ab3 | section | 1 - PRELIMINARY / GENERAL
e31b1149-9703-4e8b-8366-28553f9c2929 | checkpoint | 1.1 - Consents and trench opening notices
301d3b90-8eb1-561a-b809-ed1034ffd7a2 | note | Inspection / Test Method - Document review
a1a53d2e-ade6-5b2e-b3ce-3178fd333b51 | note | Acceptance Criteria - Authority approvals.
803b00b7-427b-5d85-bb6e-39b93b897d15 | note | Frequency - Prior to excavation
a5734aa1-a88c-534b-b711-38def942ba6f | note | Verifying Documents - Approval from relevant authorities.
8c95c261-d389-564c-9e06-288c50cf79b6 | note | Engineer / Client - R
d4b9c87a-b86e-4a3f-bc6f-5d57bcaec72d | checkpoint | 1.2 - Installer registration
6702c1ac-d996-57e1-9110-c33a8c44bbdd | note | Inspection / Test Method - Document review
b52a288c-2d5c-54af-95b8-a27348f1828a | note | Acceptance Criteria - Certification
758709ca-8100-58cf-aaa9-93f0b34dceb1 | note | Frequency - Prior to drain laying works.
68ca1828-b43e-5a62-8042-1d01e14387c9 | note | Verifying Documents - Scanned copy
0ce4a512-3362-5f03-8979-8f2b0efbdee8 | note | Engineer / Client - R
61cd6317-6eb2-41c0-94d3-3c4779177d84 | section | 2 - MATERIALS
bc150cd2-eb2e-4b5e-8ec3-dfe1d2b196af | checkpoint | 2.1 - PVC pipes
3928c9fc-722e-5e88-ad5c-65ee7a91835c | note | Inspection / Test Method - Document review
74e7fb1c-baa2-5526-bd13-7910f43dea95 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1477 (min PN9)
7850e5a4-8c58-5912-af18-5f8bfcb3a017 | note | Frequency - Prior to order
65c89fa2-65bd-56b3-ba62-b008ef948ba1 | note | Verifying Documents - Technical documents.
cc3cd22c-00bf-5a96-99a2-75c515322433 | note | Engineer / Client - R
9a5b84f4-b523-4fc4-9c44-b6c22af65246 | checkpoint | 2.2 - PE pipes
f463d83d-f903-5ed1-852a-887b608bb7a5 | note | Inspection / Test Method - Document review
08bf5b05-6c2e-59c5-a9a7-69edecb357a1 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1430 (min PN12.5)
eab6fb76-3875-5ebe-81b2-748d523c38eb | note | Frequency - Prior to order
18148193-7ce3-5118-a3b0-ff06a43e2462 | note | Verifying Documents - Technical documents.
c58875d9-bfb4-5b3e-840f-5c140837f091 | note | Engineer / Client - R
6e426b94-5b4a-4ea4-a80e-0c94efa4dacb | checkpoint | 2.3 - Precast chambers
9de80f3a-5aa3-5b82-8416-8fcf3094ee94 | note | Inspection / Test Method - Document review
6d182712-9c6f-5bf8-b5c1-83ac353074ae | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN- HO-72 traffic loadings in roads.
09a84ea6-91c8-55a3-8b25-911a1f258ae3 | note | Frequency - Prior to order
1f05c52f-1dfa-5eb6-84a0-b0241adba06e | note | Verifying Documents - Technical documents.
e694d4b8-a58d-5bed-ac0f-8ec33f2cf35b | note | Engineer / Client - R
e3973a6a-d247-41aa-8022-cdb42e9451b7 | checkpoint | 2.4 - Access covers and frames
f7ef8d45-01bf-513e-a935-9b0c182f1094 | note | Inspection / Test Method - Document review
17d79faa-b004-504c-965a-7b9e0cf7b749 | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
b60352ff-1679-5ce5-a88a-1794514aa49d | note | ○ Designed to minimum AS 3996 Class D or better.
a9e5aeac-e762-5ab8-adcb-c65a07c0d316 | note | Frequency - Prior to order
50cd80a8-9ea5-5a07-9f57-7fae2793aa40 | note | Verifying Documents - Technical documents.
bd05f74a-a8be-50b1-ac6c-48dd73f1c10f | note | Engineer / Client - R
d1b90265-599c-4038-a34d-0b64dd138d12 | checkpoint | 2.5 - Backfill material
889f1774-926e-475c-9865-257cf0eab3b8 | checkpoint | 2.5.1 - Bedding haunching and overlay.
2d457acd-308f-5ed8-82ef-50468935651d | note | Inspection / Test Method - Inspection
0dbd665d-1a1c-5f8b-8e15-b831f4f97a71 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
3376dc14-f95a-550e-a02d-c43a12445d71 | note | Frequency - Prior to placement.
8ea6d8f3-4c76-598d-b59a-6ac575cf57cb | note | Sub Contractor - H
ac5d9f86-0f57-50d8-b14c-9f6c19954ac5 | note | Head Contractor - H
06ff516a-70f2-5207-b9c2-8ad78d8158de | note | Engineer / Client - W
a3b73e27-171b-4a1c-8f9a-55faaf2a5311 | signoff | HOLD POINT
648643d1-031a-4e20-af57-883215364519 | checkpoint | 2.5.2 - Fill to subbase
de30777d-bb53-5d40-9404-6cd7b1eea03c | note | Inspection / Test Method - Inspection
9389e161-cfe8-524c-8473-988d394d8896 | note | Acceptance Criteria - AP65 of other approved imported material.
3215c92c-41af-59a3-9b4e-a07cbc4d82cf | note | Frequency - Prior top placement.
fd73e1fd-8ad2-5a8f-b0b5-a20f903abfcc | note | Sub Contractor - H
c87afcdc-fd09-54d7-b3c8-035c744ffa22 | note | Head Contractor - H
c89225ff-617c-5db9-b517-75eef710f4ac | note | Engineer / Client - W
2652384c-3076-493e-8be8-e68423e73bf5 | signoff | HOLD POINT
f7d7a0cc-a66c-44b2-af34-e498f5169252 | section | 3 - CONSTRUCTION
8d87835e-d229-4ac3-ad58-3a1fa3e8bcfb | checkpoint | 3.1 - Set out
e5eedafb-a3e7-54d0-acd5-6967432736b5 | note | Inspection / Test Method - Document review.
920faeb7-837d-566b-bd0f-d69709a3ace4 | note | Acceptance Criteria - Survey setout information in accordance with the design.
69be2a4c-9f26-51ed-8f88-4da0afd13065 | note | Frequency - Prior to excavation.
947866d1-b661-5ecb-83cc-25b24ed00ce1 | note | Verifying Documents - Survey file.
8b5c52ff-b46c-500f-bb23-252234add5f2 | note | Engineer / Client - R
eafa1727-3dc2-4721-aca9-71b694cf5f0b | signoff | HOLD POINT
75b3fe88-4486-4e76-b3ac-6b1d9408b458 | checkpoint | 3.2 - Trenching
948b0007-6fec-5198-85e6-7b609d5e354d | note | Inspection / Test Method - Site inspection.
41402c0a-4c63-55fa-8fc2-e26031ad5986 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
beee5484-d69b-52c1-a0bf-a5a35ac3df9e | note | ○ Min widths:
705ff340-153d-5872-8ddf-38a6f3dc94e9 | note | — pipe dia DN75 - DN150 = 350mm width.
1ecb597f-8ea4-547e-a914-05b1470feeac | note | Frequency - Prior to pipe laying
bb9fe77a-c44c-5296-b774-3fe9886650e4 | note | Verifying Documents - Engineer approval.
7f9c0a6b-a800-512b-bfc8-823233c85dd3 | note | Sub Contractor - H
e98d97f6-769c-54ec-8b9d-70bb3a0ca92b | note | Head Contractor - H
59443726-fc64-5e92-bbe8-a9f94585161e | note | Engineer / Client - W
a0ce76b0-65d4-450e-b29e-7bb7aa80ff87 | signoff | HOLD POINT
44ef1b12-aae1-4116-b1ab-a3893fc13c19 | checkpoint | 3.3 - Pipe laying
aba4a7b9-1b79-5bf9-9cba-dc510e7b047c | note | Inspection / Test Method - Survey
ae6b0b36-a9cf-59ff-bcbc-44c4ad8431df | note | Acceptance Criteria - Alignment +-50mm from design, surface cover in accordance with HDC ECoP.
d1b8539a-afb9-5408-8aa3-18761cd03d07 | note | Frequency - Prior to backfill.
a051c48a-5d0f-50be-8a6b-490534c73a3d | note | Verifying Documents - Survey as builts
2409d02b-4afa-54bf-ad50-5d6746eeb0d1 | note | Engineer / Client - R
42730ddd-bfa5-4391-b67e-b62962c0debf | checkpoint | 3.4 - Pipe bedding / haunching /overlay
fd6c709a-6983-56d2-8267-e99496601fac | note | Inspection / Test Method - Document review site inspection.
9325be03-9916-5672-99db-35534e101da3 | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
d101fd6d-716f-5715-9c7c-b5e6c6ce9b1b | note | Frequency - Prior to backfill.
038e3795-c001-5081-982e-35e63664f23c | note | Verifying Documents - Photos or site inspection.
9c8b7a33-dd36-5a12-8bd4-b9394cbeb2f0 | note | Sub Contractor - H
9460ba6e-42df-5723-9de9-4c9b2171c9de | note | Head Contractor - H
f6c3a304-00d6-538e-9c76-3717e59c67b2 | note | Engineer / Client - W
547e2702-b23c-490b-812b-fafb4c9440fe | signoff | HOLD POINT
76743a2e-8a9d-423e-8f6d-7c71e11cafcc | checkpoint | 3.5 - Pressure test
b65ecf39-e6ef-5056-a70d-2450cedbbc34 | note | Inspection / Test Method - Inspection.
9cfbdd33-b668-57e4-b57c-ca446f5e649f | note | Acceptance Criteria - In accordance with section C3 of NZS4404 and AS/NZS 2556.
6b6ebffb-0647-504c-9852-55d22538a28f | note | ○ To a pressure no less than 800kPa and no greater than 25% above the rated pressure of the pipeline.
bbd094f9-4908-5d97-afd3-d0bdb652d4ac | note | Frequency - Prior to backfill over joints and fittings wherever possible.
11ec79c6-4c17-5acb-8e98-cd3a60671f9a | note | Verifying Documents - Test records.
65808ed2-efb3-57e3-be37-bf5cd149ce0b | note | Sub Contractor - H
593ef8f7-4261-5d3c-b7a6-bd4fb56f7e7d | note | Head Contractor - H
258c5a60-1dad-5e83-86d2-acf29f0e9da2 | note | Engineer / Client - W
35fee1c9-c7b1-4799-baef-21662221d9b3 | signoff | HOLD POINT
382bef28-91dc-4e3c-a542-168ce7a8a59f | checkpoint | 3.6 - Backfill
a4378638-c51a-5482-9821-d484d4ddd098 | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
207ced84-3a95-5964-bb65-8659e00283a9 | note | Acceptance Criteria - Minimum 20 Clegg reading
53ac6581-7140-5faa-b0b7-82822ea3d4e6 | note | Frequency - Prior to placement of each layer of backfill.
a54d1feb-3a4f-5794-94a7-45f03bb9ebc5 | note | Verifying Documents - Test records.
b134ac90-74ef-59e7-ac4e-7036abbe6f53 | note | Sub Contractor - H
102a7a6e-b36c-580a-9eb4-0276380ff225 | note | Head Contractor - H
c10dedde-b0b7-5d7d-9962-9199b85953c8 | note | Engineer / Client - W
1178c717-5f82-47d5-a41e-13396c9c57ab | signoff | HOLD POINT
8262e00c-5298-4d56-a3cf-4075fda795e7 | checkpoint | 3.7 - Disinfection
8092669e-cfca-501b-b5a2-ac9dc28b595d | note | Inspection / Test Method - Inspection.
edd85623-a9e6-5e95-8c21-36102ed7ee80 | note | Acceptance Criteria - Carried out in accordance with NCC ECoP (amended appendix D of NZS4404:2010).
d884f516-e89d-5d89-ad22-6fe9ae253875 | note | Frequency - Prior to connectioun to mains supply
fa070a54-41e5-5e46-b571-c16c041c0be1 | note | Verifying Documents - Test records.
0fc29ea0-fa24-53e3-8bc9-cf1d0138b730 | note | Sub Contractor - H
4cbcd581-9487-5182-9afa-c6de3816ca16 | note | Head Contractor - H
27edc78c-562e-5da9-bcfc-dec87b5de5ce | note | Engineer / Client - W
c9acec5c-6445-4760-af95-3ea38f5cc4bc | signoff | HOLD POINT
efe753dd-2b43-4ad0-8808-501d88f8652c | section | 4 - CLOSEOUT
0e6f0932-d70a-4006-8aab-553a149ac90b | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
203bc3fd-67c6-5de8-aacd-89f230c7f48e | note | Inspection / Test Method - Document review
ef90fc23-08e6-5429-9578-eadcc8ecc905 | note | Acceptance Criteria - Collate and supply producer statements
6be25895-7afb-53d0-9536-b911afc4b4e3 | note | Frequency - Upon completion of Water supply works.
db3eeb1d-6f53-5380-a692-dd8d402e3baf | note | Verifying Documents - Producer statements
656a8ca6-f062-57dd-9cc0-f96b541882bb | note | Sub Contractor - H
2e8b8e40-4653-5d8f-afb4-ba93aed26efb | note | Head Contractor - H
b2b7e6fb-2c72-56f3-833f-d3fae60523b0 | note | Engineer / Client - H
49778f2d-e6ca-4cd1-8f87-b6c35a044030 | signoff | HOLD POINT
f34dddb7-01ff-4418-83fb-f7fa2ec416a1 | checkpoint | 4.2 - Collate and supply Council inspection reports.
cb72db69-09f1-5d93-a84b-3d4606c5aa5f | note | Inspection / Test Method - Document review.
522c382d-c29b-573c-a51e-df9d2c895750 | note | Acceptance Criteria - Collate and supply Council inspection reports.
87bea0ad-ed10-53c3-938e-b2cf1e4cbf10 | note | Frequency - Upon completion of water supply works.
f32a60b4-6811-520f-b4f1-413f02901ad8 | note | Verifying Documents - Inspection records.
9881d7ff-809e-5d97-8399-e83966f92ceb | note | Sub Contractor - H
1bc5a14c-cc92-5086-b807-bd1f9c5de943 | note | Head Contractor - H
1b15dc71-c989-59ed-8fac-4c6fa19d2fcc | note | Engineer / Client - S
b308ce9c-df3a-4237-a57d-68329332fd99 | signoff | HOLD POINT
898d2a82-a9c2-490d-9b49-91bd8413b714 | checkpoint | 4.3 - Collate and supply compaction records.
5a34c1f4-2af5-50f6-98c7-6e39e5b3d861 | note | Inspection / Test Method - Document review.
0f591a11-c32e-57b0-8b95-729ae47189ae | note | Acceptance Criteria - Collate and supply compaction records.
8e8647c7-3f40-5a57-9cc8-fc467a1f69ab | note | Frequency - Upon completion of water supply works.
8379a8af-8ae5-5e43-9d91-70419edf187a | note | Verifying Documents - Inspection records.
c2ecdb27-d3b8-50e7-9b79-68c2addaf106 | note | Sub Contractor - H
c608d2a0-93f9-522c-a321-88eae091daf6 | note | Head Contractor - H
85b800ec-1892-5bf5-8b3d-a94915e6b1ca | note | Engineer / Client - S
2357af77-1978-4fde-86f0-1ced026205cb | signoff | HOLD POINT
e48e1f36-9cb7-4767-b519-1ec9f19a8217 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
dcf885a3-56ad-5776-98da-e907bb08c162 | note | Inspection / Test Method - Document review / as builts
01e0cffc-cab0-5080-bb14-f3116d550528 | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
4f36e4b1-d7d9-545f-881e-9899fd99d392 | note | Frequency - Upon completion of water supply works.
e9076ce0-0305-51c5-a4b3-8cd8758c4448 | note | Verifying Documents - As-builts / test records.
8c7a450a-9266-59f2-bc83-1839954a3a39 | note | Sub Contractor - H
618cc32e-bd35-5b73-bc8d-d1a302c3ef03 | note | Head Contractor - H
773e3af0-bcea-5941-8981-1da5dc275de9 | note | Engineer / Client - S
e4697d7c-b46b-4c10-80f3-c0d095fdaeeb | signoff | HOLD POINT