## Sheet1
1.1 | Consents and trench opening notices | Document review | Authority approvals. | Prior to excavation | Approval from relevant authorities. | — | — | R | — | 1.1 - Consents and trench opening notices | Inspection / Test Method - Document review | Acceptance Criteria - Authority approvals. | Frequency - Prior to excavation | Verifying Documents - Approval from relevant authorities. | Sub Contractor - — | Head Contractor - — | Engineer / Client - R | Comments - — | 1.1 - Consents and trench opening notices
2.1 | PVC ducts | Document review | New and in good condition and compliant. | Prior to order | Technical documents. | — | — | R | — | 2.1 - PVC ducts | Inspection / Test Method - Document review | Acceptance Criteria - New and in good condition and compliant. | Frequency - Prior to order | Verifying Documents - Technical documents. | Sub Contractor - — | Head Contractor - — | Engineer / Client - R | Comments - — | Inspection / Test Method - Document review
2.2 | Chambers / pits | Document review | ACO type pits with class D covers in accordance with the specifications. | Prior to order | Technical documents. | — | — | R | — | 2.2 - Chambers / pits | Inspection / Test Method - Document review | Acceptance Criteria - ACO type pits with class D covers in accordance with the specifications. | Frequency - Prior to order | Verifying Documents - Technical documents. | Sub Contractor - — | Head Contractor - — | Engineer / Client - R | Comments - — | Acceptance Criteria - Authority approvals.
2.3 | Backfill material | — | — | — | — | — | — | — | — | 2.3 - Backfill material | Inspection / Test Method - — | Acceptance Criteria - — | Frequency - — | Verifying Documents - — | Sub Contractor - — | Head Contractor - — | Engineer / Client - — | Comments - — | Frequency - Prior to excavation
2.3.1 | Bedding haunching and overlay. | Inspection | 5-14mm clean washed granualr mix. | Prior to placement. | — | H | H | — | — | 2.3.1 - Bedding haunching and overlay. | Inspection / Test Method - Inspection | Acceptance Criteria - 5-14mm clean washed granualr mix. | Frequency - Prior to placement. | Verifying Documents - — | Sub Contractor - H | Head Contractor - H | Engineer / Client - — | Comments - — | Verifying Documents - Approval from relevant authorities.
2.3.2 | Fill to subbase | Inspection | AP65 of other approved imported material. | Prior top placement. | — | H | H | — | — | 2.3.2 - Fill to subbase | Inspection / Test Method - Inspection | Acceptance Criteria - AP65 of other approved imported material. | Frequency - Prior top placement. | Verifying Documents - — | Sub Contractor - H | Head Contractor - H | Engineer / Client - — | Comments - — | Sub Contractor - —
3.1 | Set out | Document review. | Survey setout of chambers / pits in accordance with the design - marked on site | Prior to excavation. | Survey file / site inspection. | — | — | R | — | 3.1 - Set out | Inspection / Test Method - Document review. | Acceptance Criteria - Survey setout of chambers / pits in accordance with the design - marked on site | Frequency - Prior to excavation. | Verifying Documents - Survey file / site inspection. | Sub Contractor - — | Head Contractor - — | Engineer / Client - R | Comments - — | Head Contractor - —
3.2 | Trenching | Site inspection. | Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications. | Prior to pipe laying | Engineer approval. | — | — | W | — | 3.2 - Trenching | Inspection / Test Method - Site inspection. | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications. | Frequency - Prior to pipe laying | Verifying Documents - Engineer approval. | Sub Contractor - — | Head Contractor - — | Engineer / Client - W | Comments - — | Engineer / Client - R
3.3 | Pipe bedding / haunching /overlay | Document review site inspection. | In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe. | Prior to backfill. | Photos or site inspection. | — | — | W | — | 3.3 - Pipe bedding / haunching /overlay | Inspection / Test Method - Document review site inspection. | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe. | Frequency - Prior to backfill. | Verifying Documents - Photos or site inspection. | Sub Contractor - — | Head Contractor - — | Engineer / Client - W | Comments - — | Comments - —
3.4 | Backfill | Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. | — | — | W | — | 3.4 - Backfill | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Acceptance Criteria - Minimum 20 Clegg reading | Frequency - Prior to placement of each layer of backfill. | Verifying Documents - Test records. | Sub Contractor - — | Head Contractor - — | Engineer / Client - W | Comments - — | 2.1 - PVC ducts
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of Water supply works. | Producer statements | H | H | H | — | 4.1 - Collate and supply Producer Statements / Waranty Schedules | Inspection / Test Method - Document review | Acceptance Criteria - Collate and supply producer statements | Frequency - Upon completion of Water supply works. | Verifying Documents - Producer statements | Sub Contractor - H | Head Contractor - H | Engineer / Client - H | Comments - — | Inspection / Test Method - Document review
4.2 | Collate and supply Council inspection reports. | Document review. | Collate and supply Council inspection reports. | Upon completion of water supply works. | Inspection records. | H | H | S | — | 4.2 - Collate and supply Council inspection reports. | Inspection / Test Method - Document review. | Acceptance Criteria - Collate and supply Council inspection reports. | Frequency - Upon completion of water supply works. | Verifying Documents - Inspection records. | Sub Contractor - H | Head Contractor - H | Engineer / Client - S | Comments - — | Acceptance Criteria - New and in good condition and compliant.
4.3 | Collate and supply compaction records. | Document review. | Collate and supply compaction records. | Upon completion of water supply works. | Inspection records. | H | H | S | — | 4.3 - Collate and supply compaction records. | Inspection / Test Method - Document review. | Acceptance Criteria - Collate and supply compaction records. | Frequency - Upon completion of water supply works. | Verifying Documents - Inspection records. | Sub Contractor - H | Head Contractor - H | Engineer / Client - S | Comments - — | Frequency - Prior to order
4.4 | Collate and supply as builts / CCTV inspections / water tests | Document review / as builts | Collate and supply as-builts and inspection records. | Upon completion of water supply works. | As-builts / test records. | H | H | S | — | 4.4 - Collate and supply as builts / CCTV inspections / water tests | Inspection / Test Method - Document review / as builts | Acceptance Criteria - Collate and supply as-builts and inspection records. | Frequency - Upon completion of water supply works. | Verifying Documents - As-builts / test records. | Sub Contractor - H | Head Contractor - H | Engineer / Client - S | Comments - — | Verifying Documents - Technical documents.
Sub Contractor - —
Head Contractor - —
Engineer / Client - R
Comments - —
2.2 - Chambers / pits
Inspection / Test Method - Document review
Acceptance Criteria - ACO type pits with class D covers in accordance with the specifications.
Frequency - Prior to order
Verifying Documents - Technical documents.
Sub Contractor - —
Head Contractor - —
Engineer / Client - R
Comments - —
2.3 - Backfill material
Inspection / Test Method - —
Acceptance Criteria - —
Frequency - —
Verifying Documents - —
Sub Contractor - —
Head Contractor - —
Engineer / Client - —
Comments - —
2.3.1 - Bedding haunching and overlay.
Inspection / Test Method - Inspection
Acceptance Criteria - 5-14mm clean washed granualr mix.
Frequency - Prior to placement.
Verifying Documents - —
Sub Contractor - H
Head Contractor - H
Engineer / Client - —
Comments - —
2.3.2 - Fill to subbase
Inspection / Test Method - Inspection
Acceptance Criteria - AP65 of other approved imported material.
Frequency - Prior top placement.
Verifying Documents - —
Sub Contractor - H
Head Contractor - H
Engineer / Client - —
Comments - —
3.1 - Set out
Inspection / Test Method - Document review.
Acceptance Criteria - Survey setout of chambers / pits in accordance with the design - marked on site
Frequency - Prior to excavation.
Verifying Documents - Survey file / site inspection.
Sub Contractor - —
Head Contractor - —
Engineer / Client - R
Comments - —
3.2 - Trenching
Inspection / Test Method - Site inspection.
Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications.
Frequency - Prior to pipe laying
Verifying Documents - Engineer approval.
Sub Contractor - —
Head Contractor - —
Engineer / Client - W
Comments - —
3.3 - Pipe bedding / haunching /overlay
Inspection / Test Method - Document review site inspection.
Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
Frequency - Prior to backfill.
Verifying Documents - Photos or site inspection.
Sub Contractor - —
Head Contractor - —
Engineer / Client - W
Comments - —
3.4 - Backfill
Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
Acceptance Criteria - Minimum 20 Clegg reading
Frequency - Prior to placement of each layer of backfill.
Verifying Documents - Test records.
Sub Contractor - —
Head Contractor - —
Engineer / Client - W
Comments - —
4.1 - Collate and supply Producer Statements / Waranty Schedules
Inspection / Test Method - Document review
Acceptance Criteria - Collate and supply producer statements
Frequency - Upon completion of Water supply works.
Verifying Documents - Producer statements
Sub Contractor - H
Head Contractor - H
Engineer / Client - H
Comments - —
4.2 - Collate and supply Council inspection reports.
Inspection / Test Method - Document review.
Acceptance Criteria - Collate and supply Council inspection reports.
Frequency - Upon completion of water supply works.
Verifying Documents - Inspection records.
Sub Contractor - H
Head Contractor - H
Engineer / Client - S
Comments - —
4.3 - Collate and supply compaction records.
Inspection / Test Method - Document review.
Acceptance Criteria - Collate and supply compaction records.
Frequency - Upon completion of water supply works.
Verifying Documents - Inspection records.
Sub Contractor - H
Head Contractor - H
Engineer / Client - S
Comments - —
4.4 - Collate and supply as builts / CCTV inspections / water tests
Inspection / Test Method - Document review / as builts
Acceptance Criteria - Collate and supply as-builts and inspection records.
Frequency - Upon completion of water supply works.
Verifying Documents - As-builts / test records.
Sub Contractor - H
Head Contractor - H
Engineer / Client - S
Comments - —