## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Paharakeke - Stage 4 | itp |  |  |  |  | ITP - Paharakeke - Stage 4 Rev 1
section | 1 - Site Safety & Traffic Management
checkpoint | Safety Plan (1)
label | Frequency - Prior to works starting
label | Inspection / Test Method - Engineer to review Contractor's Plan
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - NTC acknowledging Safety Plan
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Safety Plan (2)
label | Frequency - Daily
label | Inspection / Test Method - Compliance monitored by the Contractor
label | Acceptance Criteria - Site Safety Plan is updated to reflect changes in the work place. Excavations are protected.
label | ○ Site Safety requirements are met.
label | ○ Pedestrian access is clearly defined and signage is in place. Accident reports have been completed.
label | ○ Compliance report is completed.
label | Verifying Documents - Included in weekly report
checkpoint | Traffic Management Plan (1)
label | Frequency - Prior to works starting
label | Inspection / Test Method - Contractors TMP to be approved by the RCA (Road Controlling Authority) and a copy provided to the Engineer.
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - NTC acknowledging Traffic Management Plan
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Traffic Management Plan (2)
label | Frequency - Daily
label | Inspection / Test Method - Compliance monitored by the Contractor
label | Acceptance Criteria - Traffic Management Plan is updated to reflect changes in work. Signage and devices are clean and set out appropriately.
label | ○ Detour and single lane requirements have been met. Compliance report is completed.
label | Verifying Documents - Included in weekly report
section | 2 - Quality Assurance & As-Built Information
checkpoint | Quality Plan
label | Frequency - Prior to works starting
label | Inspection / Test Method - Engineer to review Contractor's Plan
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - NTC acknowledging Quality Plan
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Setting Out
label | Frequency - As works progress
label | Inspection / Test Method - Survey control report
label | Acceptance Criteria - Meets construction tolerances
label | Verifying Documents - Survey control report
checkpoint | Construction
label | Frequency - Weekly
label | Inspection / Test Method - Progress report
label | Acceptance Criteria - Meets programme
label | Verifying Documents - Included in weekly report
checkpoint | Traffic Management
label | Frequency - Weekly
label | Inspection / Test Method - Monitoring report
label | Acceptance Criteria - Safe traffic management
label | Verifying Documents - Included in weekly report
checkpoint | Site Safety
label | Frequency - Weekly
label | Inspection / Test Method - Monitoring report
label | Acceptance Criteria - Safe site
label | Verifying Documents - Included in weekly report
checkpoint | Water works
label | Frequency - As works progress and on completion
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - Included in weekly report
checkpoint | Stormwater works
label | Frequency - As works progress and on completion
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - Included in weekly report
checkpoint | Sewer works
label | Frequency - As works progress and on completion
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - Included in weekly report
checkpoint | Earth works (1)
label | Frequency - Prior to earthworks
label | Inspection / Test Method - Manhole inspection
label | Acceptance Criteria - Temporary floors kept in place
label | Verifying Documents - Visual inspection
checkpoint | Earth works (2)
label | Inspection / Test Method - Service cover location
label | Acceptance Criteria - Lids marked and kept clear for use
label | Verifying Documents - Visual inspection
checkpoint | Earth works (3)
label | Frequency - Prior to sub-base construction
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
label | Verifying Documents - Included in weekly report and visual inspection
checkpoint | Sub-base works
label | Frequency - Prior to top course construction
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
label | Verifying Documents - Included in weekly report and visual inspection
checkpoint | Basecourse works
label | Frequency - Prior to sealing or construction of kerbing and paths
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
label | Verifying Documents - Included in weekly report and visual inspection
checkpoint | Sealing works (1)
label | Frequency - Material tests and seal design prior to sealing. Seal reports on completion
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances Services covers exposed and marked. Service boxes clean and fit for use
label | Verifying Documents - NTE including material tests and seal design
checkpoint | Sealing works (2)
label | Frequency - On completion of sealing
label | Inspection / Test Method - Inspection of service lids and covers
label | Acceptance Criteria - Temporary floors removed from all manholes
label | Verifying Documents - Visual inspection
checkpoint | Footpath, berm, kerbing and traffic island works
label | Frequency - As works progress
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked. Service boxes clean and fit for use.
label | Verifying Documents - Included in weekly report and visual inspection
checkpoint | Water works
label | Frequency - As works progress
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances. Services covers exposed and marked, Service boxes clean and fit for use.
label | Verifying Documents - Included in weekly report and visual inspection
checkpoint | Sewer works
label | Frequency - As works progress
label | Inspection / Test Method - Construction reports
checkpoint | Stormwater works
label | Frequency - As works progress
label | Inspection / Test Method - Construction reports
checkpoint | As built information
label | Frequency - Completion of works Condition of Practical Completion
label | Inspection / Test Method - Levels and coordinates of nominated features in terms of datum and construction drawings.
label | ○ RAMM data sheets.
label | Acceptance Criteria - Horizontal +/- 50mm Vertical +/- 5mm
label | Verifying Documents - NTE with asbuilts in PDF and DWG
label | Engineer / Client - H (Required for issue of PC)
holdpoint | HOLD POINT
section | 3 - Environmental Management
checkpoint | Environmental Management Plan
label | Frequency - Prior to works starting
label | Inspection / Test Method - Engineer to review Contractor's Plan
label | Acceptance Criteria - Meets contract requirements
label | Verifying Documents - NTC acknowledging Environmental Management Plan
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Contractor’s Resource consents
label | Frequency - Regular monitoring during contract
label | Inspection / Test Method - Contractor to review and test
label | Acceptance Criteria - Meets consent requirements
label | Verifying Documents - Test records supplied on request
checkpoint | Principal’s Resource consents
label | Frequency - Regular monitoring during contract
label | Inspection / Test Method - Engineer to review and audit
label | Acceptance Criteria - Meets consent requirements
checkpoint | Environmental risks
label | Frequency - Regular monitoring during contract
label | Inspection / Test Method - Contractor to review and test
label | Acceptance Criteria - Risks identified with mitigation measures in place and implemented
label | Verifying Documents - Included in weekly report
checkpoint | Water run off
label | Frequency - Daily discharge checks
label | Inspection / Test Method - Visual
label | Acceptance Criteria - Silt traps in place with clear discharge down-stream to drainage systems
label | Verifying Documents - Visual inspection
checkpoint | Dust and noise
label | Frequency - Daily nuisance and dust checkA
label | Inspection / Test Method - udio and visual
label | Acceptance Criteria - Site observance with mitigation of dust and noise nuisance
label | Verifying Documents - Visual inspection
checkpoint | Fuel and oil spills
label | Frequency - Daily
label | Inspection / Test Method - Visual
label | Acceptance Criteria - Site observance with spill mitigation measures in place and implemented
label | Verifying Documents - Visual inspection
checkpoint | Concrete and seal cutting
label | Frequency - Daily
label | Inspection / Test Method - Visual
label | Acceptance Criteria - Contaminate traps in place with clear discharge down-stream to drainage systems
label | Verifying Documents - Visual inspection
section | 4 - Pipe Trenches
checkpoint | Qualifications of Personnel
label | Activity Description - Refer to Specification F100 Preliminary and General
label | Frequency - Contract Start
label | Acceptance Criteria - Evidence of Qualification and personnel on-site.
label | Verifying Documents - Provide evidence where not previously provided or personnel change
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Materials - Refer Section 2
checkpoint | Selected fill
label | Activity Description - Grading, sand. Equivalent, CBR
label | Inspection / Test Method - Lab testing
label | Acceptance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
label | Verifying Documents - Lab results to be supplied to Engineer
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Ground conditions
checkpoint | Firm formation level
label | Activity Description - Bearing capacity of base
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - Bearing greater than 50 kPa
label | Verifying Documents - Inspection records available for review
checkpoint-no-status | Tolerances - Refer Section 3.8.3
checkpoint | Trench excavation (1)
label | Activity Description - Minimum to maximum range of trench width
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Tolerance range as per section 3.9.3
label | Verifying Documents - Visual inspection and measurement on site
checkpoint | Trench excavation (2)
label | Activity Description - Side slope of trench wall
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Near vertical
label | Verifying Documents - Visual inspection
checkpoint-no-status | Inspection and Testing - Refer Section 3.10
section | 5 - Retaining Walls
checkpoint-no-status | Methodology
checkpoint | Review of Retaining wall construction methodology
label | Activity Description - Engineer to comment where required, on the proposed construction methodology and review aborist assessment. Refer to drawing DRG-WA-21802 (C02)
label | Inspection / Test Method - Engineers review
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Approved CMP
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Materials
checkpoint | Review Contractors supply of materials and QA documentation
label | Activity Description - Engineers rep to review QA documentation for timber piles, timber lagging, concrete and drainage backfill. Refer to drawing DRG-WA-21802 (C02)
label | Frequency - 10 days prior to beginning work
label | Inspection / Test Method - Engineers review
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Provide evidence of material spec.
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Confirmation / approval of any alternative materials
label | Activity Description - Engineers rep to confirm acceptance of any alternative materials requested by Contractor. Refer to drawing DRG-WA-21802 (C02)
label | Frequency - 10 days prior to beginning work
label | Inspection / Test Method - Engineers review
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Provide specs of any alternative materials
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Setout
checkpoint | Site visit to approve set out of retaining wall
label | Activity Description - Engineers rep to provide site inspection report sheet with photos of set out and description of site conditions encountered and any issues relating to design. Contractor to provide survey data co- ordinates for set out of four piles at pipe crossing location. DRG- WA-21802 (C02)
label | Frequency - Once, after excavation to founding level and following survey set out
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Piling
checkpoint | Inspection of augered pile holes
label | Activity Description - Engineers rep to witness installation of first two piles for each retaining wall and provide site visit report sheet detiling materials encountered, drill rate and any problems encountered and how they were resolved. Contractor shall record a pile log for all installed piles. This shall record the depth of hole, material encountered, comments on drill rate, if water was encountered and any temporary measures such as if pile casings were used, or any other issues that occured and how these were resolved. DRG-WA-21802 (C02)
label | Frequency - Once, after installation of first two piles on each side.
label | Inspection / Test Method - Engineers inspection
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | DN375 Stormwater
checkpoint | Inspection of DN375mm Stormwater pipe outlet
label | Activity Description - Contractor to provide photos of the pipe outlet location showing construction process of lagging and drainage material around the pipe. DRG-WA-21802 (C02)
label | Frequency - Throughout pipe outlet construction
label | Inspection / Test Method - Photos (Contractor)
label | Acceptance Criteria - Engineers acceptance (based on photos)
label | Verifying Documents - Photos
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Retaining Walls
checkpoint | Inspection of retaining wall at OD813 wastewater pipe crossing location
label | Activity Description - Engineers rep to inspect pipe crossing location at each retaining wall prior to any drainage backfill being placed above the pipe. Engineers rep to provide site report sheet summarising inspection. DRG-WA-21802 (C02)
label | Frequency - Once, following installation of steel pipe crossing
label | Inspection / Test Method - Engineers inspection
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Inspection of lagging at 50% completion.
label | Activity Description - Engineers rep to inspect lagging at 50% complete and summarise inspection in site report sheet. DRG-WA-21802
label | Frequency - Once following installation of lagging to 50% height
label | Inspection / Test Method - Engineers inspection
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Inspection of drainage installation and determining subsoil outlet location
label | Activity Description - Engineers rep to inspect drainage backfill and determine the location of the subsoil drain outlet for each wall. Engineers rep to provide site report sheet summarising inspection. DRG-WA- 21802 (C02)
label | Frequency - Once, following drainage backfill for each wall
label | Inspection / Test Method - Engineers inspection
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Final finished surface of site to be inspected
label | Activity Description - Engineers rep to conduct final inspection of retaining walls and provide photos with site report sheet. DRG-WA-21802 (C02)
label | Frequency - Following retaining wall construction and all reinstatement works
label | Inspection / Test Method - Engineers inspection
label | Acceptance Criteria - Engineers acceptance
label | Verifying Documents - Site Report sheets
label | Engineer / Client - H
holdpoint | HOLD POINT
section | 6 - Gravity Pipelines
checkpoint | Qualifications of Personnel
label | Activity Description - Refer to Specification F100 Preliminary and General
label | Frequency - Contract Start
label | Verifying Documents - Provide evidence where not previously provided or personnel change
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint-no-status | Materials - Refer Section 2
checkpoint | Embedment Material
label | Activity Description - Grading
label | Frequency - Contract Start
label | Inspection / Test Method - Lab testing
label | Acceptance Criteria - Comply with grading specification
label | Verifying Documents - Test results to be provided
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Material Acceptance
label | Activity Description - Pipes and fittings
label | Frequency - Prior to use
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - Comply with Section 3 AS/NZS2566.2
label | Verifying Documents - Visual inspection
checkpoint-no-status | Bedding, Laying, Jointing and Manholes - Refer Section 3.3
checkpoint | Pipe Jointing (1)
label | Activity Description - Clean and Dry
label | Frequency - During Jointing
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - Workspace and materials clean and dry
label | Verifying Documents - Visual inspection
checkpoint | Pipe Jointing (2)
label | Activity Description - Completed Joints
label | Frequency - At completion of jointing
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - All fittings snug and firm no movement or leakage to Manufacturers' requirements
label | Verifying Documents - Visual inspection
checkpoint | Joints at Manholes and other fittings
label | Activity Description - Spacing and type of joint
label | Frequency - Prior to Backfill around Manhole
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - Comply with drawings
label | Verifying Documents - Visual inspection
checkpoint | Manhole Benching
label | Activity Description - Finish
label | Frequency - At completion of manhole
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - Smooth and minimum turbulence
label | Verifying Documents - Visual inspection
checkpoint-no-status | Tolerances - Refer Section 3.5
checkpoint | Horizontal Tolerances
label | Activity Description - Manholes and Structures
label | Frequency - Set-out and Installation
label | Inspection / Test Method - Survey
label | Acceptance Criteria - +/ – 100mm of design or where applicable +/ – 50mm of design
label | Verifying Documents - Asbuilts except where re- design is necessary
checkpoint | Vertical Tolerances (1)
label | Activity Description - Invert Level
label | Frequency - Set-out and Installation
label | Inspection / Test Method - Survey
label | Acceptance Criteria - +/ – 25mm of design level
label | Verifying Documents - Asbuilts except where re-design is necessary
checkpoint | Vertical Tolerances (2)
label | Activity Description - Pipe Grade
label | Frequency - Set-out and Installation
label | Inspection / Test Method - Survey
label | Acceptance Criteria - +/– 10%
label | Verifying Documents - Asbuilts except where re- design is necessary
checkpoint | Verticality
label | Activity Description - Structures and Manholes
label | Frequency - Installation
label | Inspection / Test Method - Measure
label | Acceptance Criteria - +/- 10mm /1m
label | Verifying Documents - Visual inspection and measurement on site
checkpoint-no-status | Inspection and Testing - Refer Section 3.6
checkpoint | Leakage Testing
label | Activity Description - Pipes and manholes
label | Frequency - Completion
label | Inspection / Test Method - Low Pressure Air or hydrostatic
label | Acceptance Criteria - Holds Pressure
label | Verifying Documents - Test sheets from the Contract to be completed - Engineer to be present for testing
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | CCTV or Internal Inspection
label | Activity Description - Section 3.6.5
label | Frequency - Completion
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - No significant defects
label | Verifying Documents - CCTV to be provided prior to Practical Completion being issued
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Concrete works
label | Activity Description - Section 3.6.4
label | Frequency - Installation
label | Inspection / Test Method - Lab testing
label | Acceptance Criteria - NZS 3104
label | Verifying Documents - Test results to be provided
label | Engineer / Client - H
holdpoint | HOLD POINT
section | 7 - Pavement Construction
checkpoint | Earthworks
label | Activity Description - Set-out level and alignment
label | Frequency - After excavation and prior to sub- base construction and/or laying filter cloth
label | Inspection / Test Method - Survey check, and string line depth check
label | Acceptance Criteria - Horizontal -20mm / + 100mm Vertical -20mm / +5mm
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Sub-base layer construction (1)
label | Activity Description - Imported sub-base aggregate
label | Frequency - At least 10 days prior to construction
label | Inspection / Test Method - Lab testing
label | Acceptance Criteria - NZS 4402
label | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Sub-base layer construction (2)
label | Activity Description - Set-out level and alignment
label | Frequency - After sub-base construction and prior to forming topping layers
label | Inspection / Test Method - Survey check, depth check
label | Acceptance Criteria - Horizontal: -20mm / +100mm
label | ○ Vertical: -20mm / +5mm
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Sub-base layer construction (3)
label | Activity Description - Compaction
label | Frequency - After sub-base construction and prior to forming topping layers
label | Inspection / Test Method - Density testing
label | Acceptance Criteria - TNZ B/2 – Clause 7
label | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (1)
label | Activity Description - Basecourse aggregate grading tests
label | Frequency - Annual source tests, pre- delivery tests results to Engineer 10 days prior to use
label | Inspection / Test Method - NZS 4407: 1991
label | Acceptance Criteria - TNZ M/4 – Clause 4 Table 4 (Napier River Gravels)
label | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (2)
label | Activity Description - Level and alignment
label | Frequency - After basecourse construction and prior to forming topping layers
label | Inspection / Test Method - Survey check, and string line depth check
label | Acceptance Criteria - TNZ B/2 – Clause 5
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Basecourse layer construction (3)
label | Activity Description - Compaction
label | Frequency - After basecourse construction and prior to forming topping layers.
label | Inspection / Test Method - Nuclear densometer density testing
label | Acceptance Criteria - TNZ B/2 – Clause 7
label | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (4)
label | Activity Description - Compaction
label | Frequency - After basecourse construction and prior to forming topping layers.
label | Inspection / Test Method - Clegg impact test
label | Acceptance Criteria - Refer to Section 4 below
label | Verifying Documents - Test results - should also show the design criteria to demonstrate that the work complies with the design
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (5)
label | Activity Description - Surface shape
label | Frequency - After basecourse construction and prior to forming topping layers
label | Inspection / Test Method - 3m straight edge, string line check
label | Acceptance Criteria - TNZ B/2 – Clause 7
label | Verifying Documents - Density and DOS Test results and Data Result Sheets, results should demonstrate they comply
label | Engineer / Client - H
holdpoint | HOLD POINT
section | 8 - Kerb, Concrete Path & Landscape Construction
checkpoint | Earthworks
label | Activity Description - Set-out level and alignment
label | Frequency - After excavation and prior to sub- base construction and/or laying filter cloth
label | Inspection / Test Method - Survey check, depth check
label | Acceptance Criteria - Horizontal: -20mm / +100mm Vertical: -20mm / +5mm
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Basecourse layer construction (1)
label | Activity Description - Basecourse aggregate grading tests
label | Frequency - Annual source tests Pre- delivery tests Results to Engineer 10 days prior to use
label | Inspection / Test Method - NZS 4407: 1991
label | Acceptance Criteria - TNZ M/4 – Clause 4 Table 4 (Napier River Gravels)
label | Verifying Documents - Test Results - criteria should be overlayed over the results to demonstrate that the material complies
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (2)
label | Activity Description - Level and alignment
label | Frequency - After basecourse construction and prior to forming topping layers
label | Inspection / Test Method - Survey check, depth check
label | Acceptance Criteria - TNZ B/2 – Clause 5
label | Verifying Documents - Data Sheets available for review
checkpoint | Basecourse layer construction (3)
label | Activity Description - Compaction
label | Frequency - After basecourse construction and
label | Inspection / Test Method - Nuclear densometer density testing
label | Acceptance Criteria - TNZ B/2 – Clause 7
label | Verifying Documents - Test results to be provided to demonstrate they comply
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (4)
label | Activity Description - Compaction
label | Frequency - After basecourse construction and
label | Inspection / Test Method - Clegg impact test
label | Acceptance Criteria - HDC Specification Pavement Construction: Section 4
label | Verifying Documents - Test results to be provided to demonstrate they comply
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Basecourse layer construction (5)
label | Activity Description - Surface shape
label | Frequency - After basecourse construction and prior to forming topping layers
label | Inspection / Test Method - Survey check
label | Acceptance Criteria - TNZ B/2 – clause 5
label | Verifying Documents - Result Sheets to demonstrate they comply
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Kerbing
label | Activity Description - Set-out level and alignment
label | Frequency - After base construction and prior to placement of concrete
label | Inspection / Test Method - Survey check
label | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Concrete Works
label | Activity Description - Section 2.1
label | Frequency - Prior to placement of concrete
label | Inspection / Test Method - Lab testing
label | Acceptance Criteria - NZS 3104
label | Verifying Documents - Test results to be provided
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Paths
label | Activity Description - Set-out level and alignment
label | Frequency - After base construction and prior to- placement of concrete
label | Inspection / Test Method - Survey check
label | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
label | Verifying Documents - Survey & data sheets available for review
checkpoint | Prepping on for grassing
label | Activity Description - Set-out level and alignment
label | Frequency - After base preparation and prior to- placement of top soil
label | Inspection / Test Method - Survey check
label | Acceptance Criteria - Horizontal: ± 20mm Vertical: ± 5mm
label | Verifying Documents - Data Sheets available for review
checkpoint | Insitu seeding and turfing
label | Activity Description - Suitability of soil
label | Frequency - After placement of top soil and before grassing
label | Inspection / Test Method - Visual material check
label | Acceptance Criteria - Soil is free of weeds, stone and other hard materials
label | Verifying Documents - Visual inspection
section | 9 - Adjustment of Service Covers
checkpoint | Service covers and manholes in road (1)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After basecourse and prior to sealing
label | Inspection / Test Method - 3m straight edge laid on final surface
label | Acceptance Criteria - Vertical: +10mm and - 0mm
label | ○ Reinstatement of pavement to match adjacent levels
label | Verifying Documents - Visual inspection
checkpoint | Service covers and manholes in road (2)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After basecourse and prior to sealing
label | Inspection / Test Method - Visual inspection
label | Acceptance Criteria - Access and internal space is clear of debris. No rocking
label | Verifying Documents - Visual inspection
checkpoint | Service covers and manholes in path (1)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After basecourse construction and prior to concrete
label | Inspection / Test Method - 3m straight edge laid on final surface
label | Acceptance Criteria - Vertical: + 10mm and - 0mm
label | Verifying Documents - Visual inspection
checkpoint | Service covers and manholes in path (2)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After basecourse construction and prior to concrete
label | Inspection / Test Method - Visual inspection
label | Acceptance Criteria - Access and internal space is clear of debris. No rocking
label | Verifying Documents - Visual inspection
checkpoint | Service covers and manholes in berm (1)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After topsoil and prior to grassing
label | Inspection / Test Method - 3m straight edge laid on final surface
label | Acceptance Criteria - Vertical: + 10mm and - 0mm
label | Verifying Documents - Visual inspection
checkpoint | Service covers and manholes in berm (2)
label | Activity Description - Level, securely fitted and clear of debris
label | Frequency - After topsoil and prior to grassing
label | Inspection / Test Method - Visual inspection
label | Acceptance Criteria - Access and internal space is clear of debris. No rocking
label | Verifying Documents - Visual inspection
section | 10 - Surfacing Construction (Evenden Rd)
checkpoint | Surfacing Materials
label | Activity Description - Materials
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Supply of surfacing materials (chip test results, asphaltic concrete materials)
label | Acceptance Criteria - NZTA M/6: 2011 specification for sealing chip NZTA M/10: 2014 Dense Graded and Stone Mastic asphalt
label | Verifying Documents - Test results to be provided to demonstrate they comply
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Surfacing Design
label | Activity Description - Design
label | Frequency - Seal design prior to sealing.
label | Inspection / Test Method - Chip Seal Design/JMF
label | Acceptance Criteria - NZTA P/3: 1995: specification for first coat sealing NZTA M/10: 2014 Dense Graded and Stone Mastic asphalt
label | Verifying Documents - Design provided 48 hours prior to application
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Sealing works (1)
label | Activity Description - Preparedness for sealing
label | Frequency - After sweeping and prior to sealing
label | Inspection / Test Method - Visual check
label | Acceptance Criteria - Clean aggregate mix exposed to accept binder coat
label | Verifying Documents - Visual inspection
label | Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | Sealing works (2)
label | Activity Description - Reporting
label | Frequency - Seal reports on completion
label | Inspection / Test Method - Construction reports
label | Acceptance Criteria - Meets construction tolerances Services covers exposed and marked. Service boxes clean and fit for use
checkpoint | Sealing works (3)
label | Activity Description - Service lids and covers
label | Frequency - On completion of sealing
label | Inspection / Test Method - Inspection of service lids and covers
label | Acceptance Criteria - Temporary floors removed from all manholes
label | Verifying Documents - Visual inspection