## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6556e663-abc5-458b-abc6-9aee688f2b7c | checklist | ITP - ROADING Rev 0 | itp | ITP - ROADING
c1d115a8-371d-48eb-af2e-093f474e14d9 | section | 1 - PRELIMINARY / GENERAL
cd697fc6-52f3-4e3d-9f26-28d4f6a2bd78 | checkpoint | 1.1 - Subgrade testing
689f64e8-1952-543e-b26d-37ea9148fb39 | note | Inspection / Test Method - Beam testing / proof rolling or scala
795fbdaf-0411-5b44-86d1-939621c97996 | note | Acceptance Criteria - Consistent with design assuptions.
180ae465-5df0-5a88-8a2f-e66187d8b5b7 | note | Frequency - Prior to construction
b9fe2c8a-c965-505f-a9d2-ea1aeec1b23f | note | Verifying Documents - Test results
e7ce3be5-2cfa-5616-b089-db58dad75550 | note | Sub Contractor - H
1547ebfa-64a9-511f-8530-8ae864727100 | note | Head Contractor - H
a7a31ee8-75a7-5b88-98aa-002306da23f2 | note | Engineer / Client - R
c6c1117b-50a3-58fe-9b9f-342a5ec6c61c | note | Comments - Required to confirm assumed CBR.
6a577b2f-0567-413b-bdbf-41edaaa7abfb | signoff | HOLD POINT
e7523f49-9309-49f0-89c5-3067b031584d | section | 2 - MATERIALS
d5e1cfd0-484a-4574-81ff-e55cf14952b5 | checkpoint | 2.1 - Sub Base
e68e497b-313a-50d4-aa8c-579279e5615a | note | Inspection / Test Method - Production testing to NZS 4407
c77fc88f-fbdd-581f-9a7b-df55e6894c9b | note | Acceptance Criteria - Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN.
15424312-560b-5b12-bf77-cd359100a4b0 | note | Frequency - 1 test prior to placement
e1116520-d0e8-545a-8e0f-e0c43ad4561e | note | Verifying Documents - IANZ Lab report
484428b5-8f2a-5657-b1ea-a2e17dd028e8 | note | Sub Contractor - H
219eb646-6740-515e-854d-f2d6e0bd42e4 | note | Engineer / Client - R
eb1b91e1-b024-4071-b2cd-6209c7f7e796 | signoff | HOLD POINT
8ffb60cc-668c-4e7f-bfa2-a3c36c525017 | checkpoint | 2.2 - Base Course
63125cfb-4ef4-5467-ac7f-042491df2e12 | note | Inspection / Test Method - TNZ M/4
da435cc8-af18-5240-a6e7-be7ff0c2def6 | note | Acceptance Criteria - Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run".
93bb2d1b-4e65-5eb1-96f4-ada828dffa6f | note | Frequency - 1 test per 500m3 prior to placement
518ab208-da20-5899-a398-a8def8408c32 | note | Verifying Documents - IANZ Lab report
8e222499-14b9-5b68-b091-5686a65555b3 | note | Sub Contractor - H
f2619816-fe8b-5497-b7c1-9a1b4aec5190 | note | Engineer / Client - R
1b22b829-3527-4ec9-9056-d803aa741d03 | signoff | HOLD POINT
2705f10f-2430-49e5-9658-021a3f1fac91 | checkpoint | 2.3 - Ashphaltic concrete surfaceing
d262de53-6ad3-50ff-ac98-653846e539ec | note | Inspection / Test Method - TNZ M/10
c7d85d44-6edc-5892-8881-19e2853790fb | note | Acceptance Criteria - Job mix formula
ca777020-6bbf-5b6e-b422-28007b13d84c | note | Frequency - Prior to placement
a9b5709e-9fe2-57f0-8c25-eb738acdd2ca | note | Verifying Documents - Mix design
1a973db4-f42f-5419-bc68-df224f497ac2 | note | Sub Contractor - H
e485ee75-2898-569a-ac3f-ce3aaebe72da | note | Head Contractor - H
db92ea7e-1392-5b2c-b68a-f47dce73053a | note | Engineer / Client - R
85aec5eb-c1b2-4720-956d-943c8399ede5 | signoff | HOLD POINT
51375abc-8594-4565-9b66-c6472a07934d | checkpoint | 2.4 - Chip seal
d723333b-d73b-5c00-b69a-85e2e584067f | note | Inspection / Test Method - TNZ M/01, P/3 & M/06
5b7156c6-db03-57ce-a6e7-c0cf9d3b9399 | note | Acceptance Criteria - Job mix formula
ce9c95ea-0c42-5b4a-886b-774d1a939abd | note | Frequency - Prior to placement
517eef3c-7e47-5d1c-8017-bcc508e164bf | note | Verifying Documents - Mix design
1ffebb62-2780-5795-a647-0e70f3c28751 | note | Sub Contractor - H
5d4ac8ed-52f4-557b-9216-47d201db201a | note | Head Contractor - H
0e900e80-a396-5125-bcc0-85ebef2f8469 | note | Engineer / Client - R
c2a4e719-a2fa-484a-aa67-e4a0810096b7 | signoff | HOLD POINT
39d09650-3b97-4cbc-93ee-90653d314d36 | checkpoint | 2.5 - Concrete
93dca821-92c4-52e5-8f37-944f04e6d915 | note | Inspection / Test Method - NZS 3109
fd8e6583-4208-5fec-8590-2bc7c311b4b2 | note | Acceptance Criteria - 25MPa concrete at 28 days.
c6bbb6e5-f17d-54b7-b739-841faf559f7c | note | Sub Contractor - H
ccdc12f1-8f46-523a-a285-04f6f1d816df | note | Head Contractor - H
5df40a0d-6d6f-5de3-979b-aaa54132ee47 | note | Engineer / Client - R
ecca6ecd-c935-4ca3-9f44-7e16952b80e8 | signoff | HOLD POINT
781c47ef-449d-4566-b873-c6117360e644 | checkpoint | 2.6 - Vehicle crossings
326b8c44-c256-5a67-a794-4999d8c286f4 | note | Inspection / Test Method - NZS 3109
1453c6e3-46b9-531f-b9d2-f6ecc414b1e6 | note | Acceptance Criteria - 30MPa concrete at 28 days
057d810e-7f4c-5c2e-89b7-0745a7d2270f | note | Engineer / Client - R
27de04be-66cc-421d-972b-d20c4ba30dd3 | checkpoint | 2.7 - Kerb and channel, nibs and dish channels
12201359-21bd-5efc-b0e5-b005b8f0faca | note | Inspection / Test Method - NZS 3109
12d1b4b2-29ae-5d25-8fe2-c506213036bb | note | Acceptance Criteria - 20MPa concrete at 28 days
f0d25c11-67ec-5dd3-998a-a889935763f0 | note | Engineer / Client - R
43e1613e-5150-489c-a482-459cee246397 | checkpoint | 2.8 - Traffic signs and name plates
94075036-23b3-5edb-a5d4-70ef701c2288 | note | Inspection / Test Method - Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA
97c1028b-a3ce-5a7c-a33d-7f48f6f52f5b | note | Acceptance Criteria - Compliance with the standard.
a9ca0260-9d11-562b-80f1-b0e589bb0ad7 | note | Engineer / Client - R
480669da-7276-42f4-966d-5b12eef3052a | checkpoint | 2.9 - Road marking paint
66459134-4cc3-5902-a1c9-4ba0ede16e52 | note | Inspection / Test Method - TNZ M/7
e345edd9-23df-5c6b-84ae-9304ef141102 | note | Acceptance Criteria - Compliance with the standard.
abcbc296-b77a-5104-92e0-c8f42666383d | note | Engineer / Client - R
7f146cf0-35ed-4e1d-8b93-71ae8f855976 | section | 3 - SUB BASE CONSTRUCTION
8d0b3972-0832-4406-993d-ca4dece45da7 | checkpoint | 3.1 - Topsoil stripping
0d639608-bcee-5a80-8162-996cde8f223c | note | Inspection / Test Method - Inspection
be3f7575-1535-579a-aa85-6b4598d4026f | note | Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed.
dbc4bc04-1262-5e7c-8031-eed227c800bd | note | Frequency - Prior to fill.
1e3fa040-893a-5391-9140-61c4ef6e6b74 | note | Verifying Documents - Engineer approval.
c9eb63b4-a47b-5aee-b7b5-9dd385dff9bb | note | Sub Contractor - H
4a9331b4-6ae0-5f90-b0c3-189f10247fa1 | note | Head Contractor - H
84c01d52-7197-5476-a4fe-7e66d8e635d4 | note | Engineer / Client - W
44000d97-f619-429f-a160-142fa3fa1be5 | signoff | HOLD POINT
3801b257-4fe6-4227-8d4e-ee3b05576783 | checkpoint | 3.2 - Surface finish and levels.
1d921746-2f2d-50c7-a4c1-2c1d1ef3468e | note | Inspection / Test Method - Survey / string lines at 10m centres.
a68f5c17-5377-5239-a81c-45e20c5a68bc | note | Acceptance Criteria - Surface finish in accordance with TNZ F/1, section 11
8aa97ab0-3e89-56ea-b501-d7f542b1e47c | note | Frequency - Prior to fill.
d5dba03a-8878-5382-8427-70aa40575693 | note | Verifying Documents - Engineer approval.
b3efe1d1-b0c3-5e61-a8ad-b0e5b09e3de4 | note | Sub Contractor - H
b6e5c8fd-8c8b-568c-ac26-47394d5e6018 | note | Head Contractor - H
9fad2662-3f43-56bd-aeda-d5ce92319c88 | note | Engineer / Client - W
ca039fac-c295-4e0b-b575-db0f21874460 | signoff | HOLD POINT
bd9db7dd-c89f-421d-b0b4-1f97aa73a97e | checkpoint | 3.3 - Density testing
8545d821-f10f-5530-b17e-0eeeb33dd34f | note | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 20m intervals staggered between lanes.
12847a0f-e179-5791-b0dc-bb6fcb6df66d | note | Acceptance Criteria - 95% SMDD mean, 92% minimum
84b8281d-ce91-58f3-a3a9-179bb0216301 | note | Frequency - Prior to basecourse placement.
e4f9150a-e494-5b89-9a02-c76f78b6fdc4 | note | Verifying Documents - IANZ Lab report
783e3086-24aa-580d-a8e6-ea0296c21b18 | note | Sub Contractor - H
6668f787-81fd-5e9f-b415-d5681b46f2c7 | note | Head Contractor - H
f77cc251-4a36-5b0d-a67b-edb279aa5928 | note | Engineer / Client - R
fc4c6ead-a174-4c46-b972-ad3557172a08 | signoff | HOLD POINT
911617ed-f0e6-44e3-b0f4-18033c042b18 | checkpoint | 3.4 - Sub base surface finish
17901d6e-f5d2-58ae-bbf7-016207a5fd0e | note | Inspection / Test Method - TNZ B/2
3ee8172a-4dbd-5709-afad-7c338a7cdc7d | note | Acceptance Criteria - Visual inspection - tight mosaic finish.
6727c281-61a1-534b-a8d3-7f86a0d4686b | note | Frequency - Prior to placement of bascourse
9f207cf0-9bf7-57f6-baaa-fdaffd61f321 | note | Verifying Documents - Engineer approval.
80928195-c223-5747-89b4-5a3d04df54be | note | Sub Contractor - H
5e0ec391-10f1-5575-9f43-12f84a37454c | note | Head Contractor - H
a564b7ec-af7c-54ff-9921-4924c10e761c | note | Engineer / Client - W
44d49fb0-33c9-4d27-9a55-7aa9a470f267 | signoff | HOLD POINT
23c84810-76b6-438d-813e-4306b6c49050 | section | 4 - BASECOURSE CONSTRUCTION
8d5ac045-7c11-4682-96f1-57c4e4db2d6d | checkpoint | 4.1 - Basecourse finished level setout
9c1f6c9c-14e9-51dc-8ba4-28ab3df921aa | note | Inspection / Test Method - Survey / string lines at 10m centres
f35798a7-6385-5277-8988-28bcb98a885e | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
366a9473-314b-5928-94e6-f0f8c577265a | note | Frequency - Prior to basecourse placement.
daace5cf-1cec-5779-95c9-7b638854cd9a | note | Verifying Documents - Engineer approval.
5e2fca6b-13a7-5300-8dd1-654255eec28a | note | Sub Contractor - H
7ec90ede-921e-506f-b625-23d2a4850af9 | note | Head Contractor - H
2a56dd5e-1f2b-568b-beac-23d3454c2309 | note | Engineer / Client - W
ee594d00-99ed-40ca-aabb-0083f99a6f10 | signoff | HOLD POINT
5fbd072c-391b-497d-8ccb-354723193d2d | checkpoint | 4.2 - Density testing
0601bd47-af69-5b63-ac38-051077ad09ff | note | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 20m intervals staggered between lanes.
0ed92dfb-90fd-5929-b033-246b7880035d | note | Acceptance Criteria - 98% SMDD mean, 95% minimum
7a757544-b373-5a45-87e2-296cba126693 | note | Frequency - Prior to surfacing.
51bf75d8-738b-529e-9b16-90b59cacffaf | note | Verifying Documents - IANZ Lab report
f572ee53-6bd7-544b-a6a7-43a957e58dbb | note | Sub Contractor - H
8b92454e-0854-52c2-9e1f-e94da6b20bee | note | Head Contractor - H
f1a71b75-6b59-542d-8511-54195d87c724 | note | Engineer / Client - R
c34c3215-3352-4af9-99d3-da5e7c7695eb | signoff | HOLD POINT
8a6d42e1-fbe6-4902-a6f2-760425b83009 | checkpoint | 4.3 - Beam testing
53d1f33a-5e9a-5335-97aa-ac5e004eba8b | note | Inspection / Test Method - TNZ T/1
baa26be8-c685-538c-8ddf-58a0bccffb5b | note | Acceptance Criteria - Average: 1.5mm, Maximum 1.8mm
3dab875c-0bc6-5220-832e-0c62aadac5c4 | note | Frequency - Prior to surfacing.
83cea8ae-7701-5f6f-8ca5-298c7b6578b8 | note | Verifying Documents - Test results.
8fc46b7e-a66e-52d2-b421-69bcc4474f4c | note | Sub Contractor - H
13611042-158a-5f4a-8ac8-b0d74e707916 | note | Head Contractor - H
d47667e2-e9f7-5d76-8833-8fd4a5640197 | note | Engineer / Client - R
a50fa93c-765f-44ce-8152-c0798056dab1 | signoff | HOLD POINT
c8f3e799-e46e-4fef-8c25-9330c0381f84 | checkpoint | 4.4 - Surface finish
c2d50d9b-4f42-513e-a72a-8fad3b748e22 | note | Inspection / Test Method - TNZ M/4
ab5cd343-c135-5f9d-bdc3-be617deaa1bc | note | Acceptance Criteria - Visual inspection
26fd9724-1088-5d4a-99c7-3b0e5b1b0aad | note | Frequency - Prior to surfacing.
52125bc2-52e8-5186-b0e7-e9ce265d99e2 | note | Verifying Documents - Engineer approval.
a9d66dde-a0e2-5b54-961c-bb92c38e0cb4 | note | Sub Contractor - H
993fd4aa-173b-5af0-8cb8-41babb72402a | note | Head Contractor - H
c15c53a4-4425-5ec9-84af-90fc678d3260 | note | Engineer / Client - W
6ccb79a2-c0cf-4892-8ac1-35c426c1eb7f | signoff | HOLD POINT
2d508a45-9ed9-4e16-b2d9-e103fde0b715 | section | 5 - ASHPHALT SURFACING
cf5d0483-1cb7-42ef-a15f-8291bd76f5e0 | checkpoint | 5.1 - Ashphaltic concrete finished level setout
d5eba0f1-f7fb-5f61-86a4-1ee8eb61052d | note | Inspection / Test Method - Survey / string lines
74e7be0c-ba83-5263-a83b-078acc1ba189 | note | Acceptance Criteria - 10m centres, 3m straight edge.
1138f4b8-caf4-5c79-97c2-5c1263a81b71 | note | Frequency - Prior to surfacing
c0daa566-33bb-5d6d-b7e9-a2e1af7d7f3e | note | Verifying Documents - +10mm / -0mm from finished design.
0e6bf4bf-878c-552a-a7e3-d32f44188231 | note | Sub Contractor - H
16197256-e1d5-53f1-9d9f-55e5d4226098 | note | Head Contractor - H
f277a065-a19e-5960-b5ad-dd5ce0e899c3 | note | Engineer / Client - W
b17e7400-7125-42c1-bdbe-414243bea5e5 | signoff | HOLD POINT
ad756b03-c57f-4afd-bf27-60b192fea3b3 | section | 6 - CHIP SEAL SURFACING
7549af16-70c1-4f3c-9f4b-0ae771f97567 | checkpoint | 6.1 - Chip Seal finished level setout
6867057c-ce6a-5fff-8984-fd9cd4b9ce50 | note | Inspection / Test Method - Survey / string lines
48631de6-c961-542a-a0d2-fd323a98b590 | note | Acceptance Criteria - 10m centres, 3m straight edge.
07171023-d127-5507-96c2-4fbb6d562c84 | note | Frequency - Prior to surfacing
07c85805-dfbe-5b57-94fd-1b203d9e878e | note | Verifying Documents - +10mm / -0mm from finished design.
14814e2e-8ee5-5453-823d-9e6fcaa3ffbb | note | Sub Contractor - H
b55fef57-c2a3-5506-ad3f-af396896d864 | note | Head Contractor - H
56dfc93d-3740-5973-9ea5-2e58ab546d2d | note | Engineer / Client - W
3ce4947f-335a-4ccd-8f9d-ab0ab9b3538a | signoff | HOLD POINT
96d1e473-748f-419f-8edf-347ae3946ef4 | section | 7 - FOOTPATH AND VEHICLE CROSSINGS
ef91866b-fbe2-42ef-9e8c-ae2792848873 | checkpoint | 7.1 - Setout
67d17722-86bc-5978-8bc9-ebd1b7929d5b | note | Inspection / Test Method - Survey / string lines
0fa65e10-61d3-5aaf-a0e4-8159ad6592f0 | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
321ecf77-0af3-5f58-a7cd-52c5f4038da2 | note | Frequency - Prior to pour.
e127ee96-941c-5a27-9e38-8a65d0a9c182 | note | Verifying Documents - Engineer approval.
004fcf93-9e4d-552b-902c-b7ce9105f730 | note | Sub Contractor - H
bfa3dcb0-63e1-508e-8463-8b7ce0e10ea3 | note | Head Contractor - H
daf5572d-15ed-531c-a408-dd5811d70ef1 | note | Engineer / Client - W
9c949514-2335-4ce6-b1c7-3fde42b45e0b | signoff | HOLD POINT
b6869076-8c03-4a03-ad43-78ca2eb0c7ad | checkpoint | 7.2 - Basecourse compaction
84bff7a2-349b-5f62-9964-a415bc374ea9 | note | Inspection / Test Method - Clegg
8b02d626-2293-5c73-ad0e-f40d63687d5b | note | Acceptance Criteria - Mimimum 25.
d239d3f2-11ad-5e0d-986f-e6d1e1651693 | note | Frequency - Prior to pour.
f6e272b4-b0b5-54c3-a8f8-b9b8cff6bbc6 | note | Verifying Documents - Engineer approval.
387857d3-9654-57e4-8f3d-794aa24496b4 | note | Sub Contractor - H
6d1a981f-b879-5eed-9240-ec5e13bf043a | note | Head Contractor - H
3f58a517-4876-53ef-8af5-e5aafeb21f08 | note | Engineer / Client - W
dcec040a-b8cd-4556-9efa-8e7c8e73c89f | signoff | HOLD POINT
6b2384a5-fef9-4514-9e96-a19889872726 | section | 8 - KERB AND CHANNEL, NIB, DISH CHANEL
7d4771fd-515f-4337-a16d-297f3d05bccd | checkpoint | 8.1 - Setout
dcff8ac9-e9f6-5401-a1fd-3bb1275e53a4 | note | Inspection / Test Method - Survey / string lines
5b852951-08e8-5589-a838-e63e9486804d | note | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
d2db8573-e185-56c3-b431-a0baaf8634f6 | note | Frequency - Prior to pour.
6957509a-8a13-59d7-8194-3462f94cfa63 | note | Verifying Documents - Engineer approval.
5c0a4c93-4bc0-550e-ae47-b86a6b2fc029 | note | Sub Contractor - H
1d536144-b774-5ac2-922e-1c716b1e7e51 | note | Head Contractor - H
de967489-e35b-5b00-8a6e-4d7120dfcd41 | note | Engineer / Client - W
a21e8d26-bb44-49ca-b03e-afce642fa53e | signoff | HOLD POINT
5412efda-0d17-4acf-85ea-ed22486530a4 | checkpoint | 8.2 - Basecourse compaction
e54a7603-ec03-5f1e-b43f-ce1bfb36b8ff | note | Inspection / Test Method - Clegg
6f39eef7-6072-52a7-9076-fd787cabf51e | note | Acceptance Criteria - Mimimum 35.
362a1494-4ef6-5962-a578-d73227c5685c | note | Frequency - Prior to pour.
e903fdc4-4ae8-586d-9d08-fd6af39e421c | note | Verifying Documents - Engineer approval.
0470467d-4676-5c23-94ca-0968295ac167 | note | Sub Contractor - H
dc679742-1c6b-55d9-852c-2bc6bd535f52 | note | Head Contractor - H
24171d4a-8af9-51d9-89e8-a26f5c084f28 | note | Engineer / Client - W
dad047a8-7d32-4efd-808a-fa116915c910 | signoff | HOLD POINT
f84d917d-22d0-409d-bb9c-934c16ff58fe | section | 9 - ROAD MARKING
be626532-7242-4439-94bd-62542ff47c5d | checkpoint | 9.1 - Road marking paint
0f16ba97-e6a9-5436-ab73-4742ebe4f3b9 | note | Inspection / Test Method - Mark out on site
528d2c3b-4bfb-58f4-b4e4-18608865c7a2 | note | Acceptance Criteria - Mark out dimensionally in conformance with the design.
aea5c4f2-ba18-522c-9c9e-b8aa87db05ee | note | Frequency - Prior to application of paint
1b7fff52-b99c-5925-9db4-138b5362368a | note | Verifying Documents - Engineer approval.
ccdd9e84-24f2-5c6e-b6de-6bb60066e735 | note | Sub Contractor - H
0490216b-9077-572f-9179-a838c5b6d0b5 | note | Head Contractor - H
03efc0c1-d0b9-5808-be1c-e7c97b80ac2c | note | Engineer / Client - S
d61d71df-a099-4c3f-bff2-075ce7de3718 | signoff | HOLD POINT
655918dd-cfd3-46db-b1f8-3266477f03d9 | section | 10 - CLOSEOUT
35b69e24-be13-456a-bbe3-86ec061d8f48 | checkpoint | 10.1 - Collate and supply Producer Statements / Waranty Schedules
1fb8a57e-1170-5e33-8364-edf7917b5331 | note | Inspection / Test Method - Document review
25cb1263-c848-51e3-af13-dee649e95e84 | note | Acceptance Criteria - Collate and supply producer statements
4b2683f3-f4c6-5ab8-bcba-91d031633488 | note | Frequency - Upon completion of bulk roadworks
5282353e-2981-5de6-b9e1-a247fecd7ae1 | note | Verifying Documents - Producer statements
4214b7d2-c1d3-57cf-8a93-59758378e251 | note | Sub Contractor - H
bac84f81-5ece-577e-943f-47fb80d7d6fc | note | Head Contractor - H
e7e070e0-c8b2-57f7-83d5-f458d9445497 | note | Engineer / Client - H
9a64f6e3-b0b5-48dc-ba32-5a19715e9a02 | signoff | HOLD POINT
8d1e3178-b940-44dd-9a10-21496916803b | checkpoint | 10.2 - Collate and supply as builts
3a094e5a-cda3-5ad6-a8e6-edc88cfd6928 | note | Inspection / Test Method - Documate review / as builts
a2319dc3-ac86-5576-9cc7-e74ffb78570c | note | Acceptance Criteria - Collate and supply as-builts.
46f1203e-1512-51b8-bc04-97190f66bec3 | note | Frequency - Upon completion of roadworks
5063b72b-53ad-50a8-8fc9-b37fcfaf90ba | note | Verifying Documents - As-builts
37b42837-c4e6-5c6a-9bcf-d59b77319819 | note | Head Contractor - H
cf48d140-733b-5490-8e7f-99ed2f8a0b21 | note | Engineer / Client - S
3568527f-e325-475c-aca2-d82d2dc9660d | signoff | HOLD POINT
0bd1cfaf-75de-4850-9821-d8e8e66eda29 | checklist | ITP - SERVICE TRENCHING AND DUCTING Rev 0 | itp | ITP - SERVICE TRENCHING AND DUCTING
a4fc94e2-1cec-441a-9917-bcfde8d14e17 | section | 1 - PRELIMINARY / GENERAL
de3e1ab5-a0b4-4ddc-b44a-90f5628913b0 | checkpoint | 1.1 - Consents and trench opening notices
09e44d24-db8e-53ae-b7f2-5d8c8fb48de7 | note | Inspection / Test Method - Document review
9bf00256-40d6-5a7a-ade7-bfe476472237 | note | Acceptance Criteria - Authority approvals.
75dae00b-4a73-572a-9f65-fb078354a2d6 | note | Frequency - Prior to excavation
89726ac6-c31d-591d-8985-60140288342b | note | Verifying Documents - Approval from relevant authorities.
5c4856b1-213d-576a-9bf8-00080e22dc9b | note | Engineer / Client - R
0a8fe6b9-b934-46a5-b90a-f334f8731c24 | section | 2 - MATERIALS
0290ec06-9ec1-4d89-a8f6-6103c07c549a | checkpoint | 2.1 - PVC ducts
ba1a6cde-0229-5701-a86e-0b285e7976ba | note | Inspection / Test Method - Document review
4cb28cd3-f7b1-538b-b956-e6929756da12 | note | Acceptance Criteria - New and in good condition and compliant.
d2499481-9d14-5264-934c-850af4126a78 | note | Frequency - Prior to order
3857a01b-ab2a-5255-a65f-3149e43c18b1 | note | Verifying Documents - Technical documents.
7b337ed2-0358-5132-b96c-bb258ded96a4 | note | Engineer / Client - R
fd2db748-153b-4f78-84f0-c44de6ae3248 | checkpoint | 2.2 - Chambers / pits
ec9e46fc-1e94-5ddc-9906-51761436b471 | note | Inspection / Test Method - Document review
36de8f99-f5bb-589b-88ce-ed59d62287be | note | Acceptance Criteria - ACO type pits with class D covers in accordance with the specifications.
c1e0db28-d939-515e-9f86-e7c5a049ada1 | note | Frequency - Prior to order
ae10e2c1-d827-5efd-a9d0-d15a262122fc | note | Verifying Documents - Technical documents.
3113c8f0-ec2b-5b72-a8f8-950b6b129429 | note | Engineer / Client - R
564280f8-2fe4-4723-9c66-442d02eed686 | checkpoint | 2.3 - Backfill material
4242c5b6-3c9d-48a7-a9c4-75df5f56efdb | checkpoint | 2.3.1 - Bedding haunching and overlay.
8ad41e5e-d5bd-58a5-948a-42a5124a6d6d | note | Inspection / Test Method - Inspection
eb78aaa9-4624-5b0d-ac8c-c4200bb1c190 | note | Acceptance Criteria - 5-14mm clean washed granualr mix.
89dbd2d3-dd09-57eb-9c34-19b99792e601 | note | Frequency - Prior to placement.
21455bff-9ee5-5c1e-be36-954c0073802e | note | Sub Contractor - H
aabdda04-b444-52fb-9c9a-dbc015151957 | note | Head Contractor - H
10dd18da-c8d4-4df4-a3e4-47756d314c80 | signoff | HOLD POINT
180ffc7c-c3e2-42a3-870a-dfd30ce52e84 | checkpoint | 2.3.2 - Fill to subbase
273d083a-0699-5c60-95ea-8e4dbac0f153 | note | Inspection / Test Method - Inspection
14c8eef5-6cf3-5e97-ad8b-fcece91ff804 | note | Acceptance Criteria - AP65 of other approved imported material.
7fa1ab46-4333-5909-a63e-acc20c3b488c | note | Frequency - Prior top placement.
d74c2b49-a702-5a4d-addc-a28687860827 | note | Sub Contractor - H
63bd70a7-7921-5cbe-a3c1-b9089d63e388 | note | Head Contractor - H
311ca08f-64bf-4324-984a-fc6e2655795b | signoff | HOLD POINT
d2c0f6f2-613f-405f-a980-42c3339c46e1 | section | 3 - CONSTRUCTION
24624f9a-9625-4a2a-a74a-5d4e3fb20071 | checkpoint | 3.1 - Set out
c3b56029-f3a0-5467-9eb3-f716630d9f2a | note | Inspection / Test Method - Document review.
706b957b-143e-5730-9f01-b2eb727615b2 | note | Acceptance Criteria - Survey setout of chambers / pits in accordance with the design - marked on site
0452319b-bd4d-5cad-a817-c6f69c15f986 | note | Frequency - Prior to excavation.
69e93275-b4b1-5c3b-aa02-ab24311cfc8b | note | Verifying Documents - Survey file / site inspection.
562df309-1b65-5645-9db3-1e42121a08e1 | note | Engineer / Client - R
7c35f53c-cd30-4415-9184-0eb4c1ad44d3 | checkpoint | 3.2 - Trenching
5670116d-0fe9-5e0c-bd44-4325e3c35d3f | note | Inspection / Test Method - Site inspection.
02f01c86-4010-59e2-b5e5-23bb50d5c595 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications.
8fda2a54-7def-5d2d-a170-264440583458 | note | Frequency - Prior to pipe laying
7f26f0a1-a8c3-54a9-ab2f-fabe38277016 | note | Verifying Documents - Engineer approval.
c020a9c3-6015-5ff4-9a1b-e0bc0d1f6839 | note | Engineer / Client - W
ef7c26cc-6ebc-4cc3-b7c7-77d5b1aad813 | checkpoint | 3.3 - Pipe bedding / haunching / overlay
1d69a4a7-0560-52d3-8de8-d58d14dd71a3 | note | Inspection / Test Method - Document review site inspection.
52641b79-040e-5cb3-987e-fedda38655cb | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
a86b6119-7f27-5004-b10e-1cd4be71b1ac | note | Frequency - Prior to backfill.
135d623f-74d0-5695-95df-191b00fe4af9 | note | Verifying Documents - Photos or site inspection.
d801bfd1-c6ae-5827-8390-99dd36060576 | note | Engineer / Client - W
c7abacc8-b2ab-42ab-9cf4-5b1a72e0d08e | checkpoint | 3.4 - Backfill
fed24ffb-f815-5672-b2cc-1ce0b7eaeadb | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
6152e951-d32f-5e31-9839-ddf0405d085b | note | Acceptance Criteria - Minimum 20 Clegg reading
4ed84c30-8c3b-510a-930c-eb427b234c37 | note | Frequency - Prior to placement of each layer of backfill.
15ae9123-5985-579b-8b33-73af01d92926 | note | Verifying Documents - Test records.
ed9bd38e-2e1c-5303-b281-4db61a0331a3 | note | Engineer / Client - W
ade47a6d-eafb-483f-b12a-dc74e7bd39f9 | section | 4 - CLOSEOUT
b7928382-b1c0-4d63-a2af-f5495a46dba4 | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
b2729f4f-d1f3-55c6-9b4e-a1dc61d3cf6f | note | Inspection / Test Method - Document review
60081bf4-95ea-588d-bd4d-1fb9c1eb6690 | note | Acceptance Criteria - Collate and supply producer statements
50e15224-f009-5a5e-b4b0-1e72f4fed981 | note | Frequency - Upon completion of Water supply works.
3eb19f47-2b9c-59ba-8c4b-adbd36bec176 | note | Verifying Documents - Producer statements
16489dff-2c88-50c4-9a21-da90f7ba8606 | note | Sub Contractor - H
1257ee1b-6080-511d-99cb-50efd49ea024 | note | Head Contractor - H
7ab8031e-6426-5eb6-b4fa-f54ee6707687 | note | Engineer / Client - H
ed88b46f-0de4-4184-9685-2153a8adc232 | signoff | HOLD POINT
9b320714-c79f-4d21-9ee6-d30526eff9de | checkpoint | 4.2 - Collate and supply Council inspection reports.
3d04c3f2-00db-5532-b459-6e4aedb18e4c | note | Inspection / Test Method - Document review.
4696b1c4-d57e-5fc4-a9e9-c3d09b62190d | note | Acceptance Criteria - Collate and supply Council inspection reports.
195606ac-2108-560a-b7fb-4b0748c14f1f | note | Frequency - Upon completion of water supply works.
1163cdb4-2466-5380-92d3-4dd62186595f | note | Verifying Documents - Inspection records.
888d85fc-922a-59c0-9d4e-2097cf06ea85 | note | Sub Contractor - H
132d92c4-a8c1-50ad-b2b2-dde6c4c0b19b | note | Head Contractor - H
a682ab14-a73d-5251-916d-b5b8cf897204 | note | Engineer / Client - S
73153704-fd85-4bf2-a689-fa58fa068be9 | signoff | HOLD POINT
73272210-fd4b-4aa2-8258-35256a7adc9d | checkpoint | 4.3 - Collate and supply compaction records.
b19f506a-51f5-5965-9c21-9cbb2e01c112 | note | Inspection / Test Method - Document review.
7fbfd2e3-8496-5236-9594-8fbe2c812fee | note | Acceptance Criteria - Collate and supply compaction records.
be3724e2-1103-5071-8378-14e5a7cdae25 | note | Frequency - Upon completion of water supply works.
ad1fff5c-3f30-55c3-8938-ae796d3452f7 | note | Verifying Documents - Inspection records.
c9297d29-a2a7-56aa-a9a1-05498b912ffb | note | Sub Contractor - H
09412ac6-b763-5daa-b627-676ed3ebdf6b | note | Head Contractor - H
d7446c41-ccbe-5f9a-bc2e-3a51c16dc941 | note | Engineer / Client - S
10f4fa18-8858-48b6-b9a3-09d681d0f453 | signoff | HOLD POINT
3e229892-8a40-4c7e-959f-671e94f7c7f6 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
4d1f035d-4144-528f-a91d-96a19004cdb7 | note | Inspection / Test Method - Document review / as builts
ce2d8471-19b9-501b-afa8-c3e42484bcc1 | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
acc6a862-7042-54ad-bc0c-131ae066c031 | note | Frequency - Upon completion of water supply works.
b71faa56-79b3-5c90-b2c7-2bbd8219a409 | note | Verifying Documents - As-builts / test records.
d90154ea-08fa-5c70-94bc-b1391cc36483 | note | Sub Contractor - H
bff972b1-b7f6-523f-b4f6-e97227c1562e | note | Head Contractor - H
727177f6-9283-529e-a19e-a7f1881d27dc | note | Engineer / Client - S
e2fc9e61-ec90-44c1-bd6b-19716a1e319e | signoff | HOLD POINT
49427f2c-6b44-4184-894f-f9e5bdb69664 | checklist | ITP - STORMWATER Rev 0 | itp | ITP - STORMWATER
6efda515-9255-4745-9070-7a4eb5a0c875 | section | 1 - PRELIMINARY / GENERAL
32f79df0-f5fd-4427-a882-273ed19561f9 | checkpoint | 1.1 - Consents and trench opening notices
58d11952-dbf5-5f38-b535-2b9d16c88758 | note | Inspection / Test Method - Document review
42d67a46-5b96-5b31-bcb7-39669913f022 | note | Acceptance Criteria - Authority approvals.
d32be9be-2c2d-56e8-a4f2-a8c4c6709570 | note | Frequency - Prior to excavation
d7a85298-8a8d-5ddc-b9ae-ab0b48f6fa67 | note | Verifying Documents - Approval from relevant authorities.
a4950221-4860-5a06-92c5-678508c28c37 | note | Engineer / Client - R
12f40e6c-78de-4c16-928b-635afbeb84ec | checkpoint | 1.2 - Drainlayer registration
ebd47d2b-5ef3-5d9f-8cad-35d78b377c8b | note | Inspection / Test Method - Document review
25a2ecd1-5b18-5619-b872-82be6193252b | note | Acceptance Criteria - Certification
e02a62e1-101f-56aa-b1a4-1b5c13fe1cd3 | note | Frequency - Prior to drain laying works.
f23deca5-b35b-51f3-b31c-5bdbb26cdd2b | note | Verifying Documents - Scanned copy
01fd5c88-4d35-54df-a79f-30aa23d7bee2 | note | Engineer / Client - R
a44b3b45-f616-4684-a70e-571533443482 | section | 2 - MATERIALS
d4b30362-07f8-4305-a526-57af89eba3e7 | checkpoint | 2.1 - Concrete pipes
aa1f8a49-ad54-59d4-9533-9d112413d79a | note | Inspection / Test Method - Document review
24ccdaaa-2509-57b7-a105-5b6d89ceb0c0 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS4058 reinforced cast rubber ring jointed, class 2 uless otherwise noted.
ec70cbd2-179d-5545-8624-7d2cbd7f884d | note | Frequency - Prior to order
63901067-6636-5d9e-b5c9-ba1a8cae60fc | note | Verifying Documents - Technical documents.
84cc1046-dbd3-50ef-91e4-868fd188bc5b | note | Engineer / Client - R
92946b5e-3dc3-468d-876d-bac85a6eb966 | checkpoint | 2.2 - PVC pipes
74b27791-3e41-5336-8292-b943c6316cc8 | note | Inspection / Test Method - Document review
70bfbd9d-adfc-58e6-8cf3-3858799519ec | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
a1485e0f-292e-54e5-b92b-b8a034d64ffc | note | Frequency - Prior to order
4d8c4e6f-eca3-5d84-aab2-78f331f573c2 | note | Verifying Documents - Technical documents.
c1f55f65-94ee-5a7b-8b7b-a9046b2ffd93 | note | Engineer / Client - R
7ac42ece-6be4-4ea3-ad21-14b959854391 | checkpoint | 2.3 - Precast chambers
c9223381-ea0d-5119-a257-38fb45300839 | note | Inspection / Test Method - Document review
d4466fd1-c9e1-5b11-929d-2624991217c7 | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN- HO-72 traffic loadings in roads.
821b054c-7e59-5172-a306-046ed9da39dc | note | Frequency - Prior to order
b89900a6-e030-58ea-9539-569831a1ccbc | note | Verifying Documents - Technical documents.
d404b5bf-19f4-54df-a51e-91c01f6ed72c | note | Engineer / Client - R
703f493b-34c3-4b43-b675-e5b7522f4db9 | checkpoint | 2.4 - Access covers and frames
f3c644b9-1841-57b7-8d9a-147a4c9206b4 | note | Inspection / Test Method - Document review
6485c2ca-b3a9-5a3c-9e2c-34c7c539a021 | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
6695fc37-816f-5a38-896d-c7ee1b904028 | note | ○ Designed to minimum AS 3996 Class D or better.
3833b5dd-d6a1-568f-bf2f-13672b88c743 | note | Frequency - Prior to order
65821d13-3c9a-5154-9562-4a88d4cb5a21 | note | Verifying Documents - Technical documents.
faea6b0a-dee7-5378-b585-978bc6b017a5 | note | Engineer / Client - R
1e9ac5ea-d70a-438c-8903-4ec20d1963bb | checkpoint | 2.5 - Sump grates
b02602d7-66fc-5d2c-b7de-25baaca7760d | note | Inspection / Test Method - Document review
3eeed869-622a-5d2a-bfcd-cb4cf1ff306b | note | Acceptance Criteria - Complaince with HDC ECoP.
c4b54dbc-8835-5f6e-b93e-dd6c7935bdf2 | note | Frequency - Prior to order
057d551a-e7eb-5025-a63c-7d88a25bab25 | note | Verifying Documents - Technical documents.
b3b4b7cf-8cd0-5dab-a3e8-4aa789a1bda3 | note | Engineer / Client - R
ed7e9e55-3227-4420-b1ed-049adacfe8bf | checkpoint | 2.6 - Concrete Wing wall
a4ab638e-e7e7-56e2-bc9f-f41babf6654d | note | Inspection / Test Method - Document review
99839714-b9e1-5a9c-b2c1-145ff9e21198 | note | Acceptance Criteria - Compliance with NZS 3109 with surface finishes to
d5b87b76-e838-59f8-b7ca-d41a67e479be | note | Frequency - Prior to order
f23da868-e468-56ca-8b53-d45af0522e2d | note | Verifying Documents - Technical documents.
616e061b-f8eb-58d6-9c5d-2c30b01f2fd5 | note | Engineer / Client - R
fff9b4a0-93fb-40cd-9570-419bac23e2dc | checkpoint | 2.7 - Backfill material
2574e841-6f17-4beb-8443-b345f2364484 | checkpoint | 2.7.1 - Bedding haunching and overlay.
ab405247-ab55-5d58-84e9-f698537b0a24 | note | Inspection / Test Method - Inspection
5a8921f1-f385-52b3-8531-a4d6cec236d8 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
58fa8204-c58a-5a0b-9aae-298492c452e2 | note | Frequency - Prior to placement.
f300875f-72c5-5036-9c5f-9ff6215c487b | note | Verifying Documents - Engineer approval.
14ad3d38-9c7f-5308-b93b-f9bfa8f82405 | note | Sub Contractor - H
940170a4-8cd4-5a70-80f6-7277da7de549 | note | Head Contractor - H
2c6520b7-94e3-52ba-81ce-4555686ba101 | note | Engineer / Client - W
56290811-51dd-4e01-aa57-e87ad2fd8e79 | signoff | HOLD POINT
56a085a0-b1f1-4caf-91c4-2eed7aae1772 | checkpoint | 2.7.2 - Fill to subbase
bca348d4-20e6-55b9-ad64-69676b35eee1 | note | Inspection / Test Method - Inspection
92debe69-b413-5b82-a198-295b153a254c | note | Acceptance Criteria - AP65 of other approved imported material.
a00df213-fa29-5bed-896b-c2e3fcf06db8 | note | Frequency - Prior to placement.
cbef8e06-dcd3-5186-9207-e688bd2475a7 | note | Verifying Documents - Engineer approval.
5487dfba-2e75-5052-8a02-25b65e81e169 | note | Sub Contractor - H
880d47b8-218b-5cca-9777-a3a95e08f23a | note | Head Contractor - H
a2cbd304-4722-524c-ac40-22449f200fb4 | note | Engineer / Client - W
bf73fcd2-6324-43fa-848e-9ed8331f8847 | signoff | HOLD POINT
3f4f959a-69e9-4099-8dba-ad9ee947f9cb | section | 3 - CONSTRUCTION
7c8d18b0-ff89-4674-afd6-55444aa339a0 | checkpoint | 3.1 - Set out
f101e1ec-d5bc-5fed-86e4-676f122eea5f | note | Inspection / Test Method - Document review.
06085c63-d0a6-59ed-87ba-2e6a99e47d23 | note | Acceptance Criteria - Survey setout information in accordance with the design.
b6667fb8-dd8d-5e00-8f2c-825ed26bffea | note | Frequency - Prior to excavation.
9c2d194f-072e-50e9-ab6d-7d7277c3d7a4 | note | Verifying Documents - Survey file.
e152f3c2-5939-58dd-8081-f8c10ce03e1a | note | Engineer / Client - R
cfd24eb1-c807-4654-bd44-f47a95c2d95e | checkpoint | 3.2 - Trenching
e7e2186c-967d-5840-b3ad-422df060d58d | note | Inspection / Test Method - Site inspection.
205a8ffa-8083-54b9-8822-9b1449842a51 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
cbbf4617-64a1-54c8-85fb-2d0b00287fd8 | note | ○ Min widths:
564f72b0-c6e8-5de0-b7ad-9e86682fb3ad | note | — pipe dia DN75 - DN150 = 350mm width,
8c65fd3b-a317-5072-b3a0-5ef6035c1f1c | note | — pipe dia DN150 - DN300 = 450 - 600mm width,
6a74031a-1ac3-5541-9119-41648f705810 | note | — pipe dia DN300 - DN400mm = 700 - 850mm width.
840a14b2-060b-5054-9752-aedd1e4c2fbd | note | Frequency - Prior to pipe laying
84ed7905-bf01-525d-a84f-921a433408e3 | note | Verifying Documents - Engineer approval.
09537064-7ddf-580b-97b2-7d269d8a9c18 | note | Sub Contractor - H
29d4f169-451d-5347-9aa0-84a91d08ae70 | note | Head Contractor - H
203049b5-ba47-5e61-ba75-8756554529dc | note | Engineer / Client - W
909416a4-2b20-46dc-bdfe-a777509f6c87 | signoff | HOLD POINT
99688c7f-a4c2-4af1-b717-15dcc191552e | checkpoint | 3.3 - Pipe laying
22218bc8-1f7c-5ce1-b3c7-0b9a8214280f | note | Inspection / Test Method - Survey
948b10df-aa9c-5288-8e56-e08d663fabe0 | note | Acceptance Criteria - Record level of main upstream and downstream of each chamber.
e2775b21-edba-5483-adcb-f393ce47b452 | note | ○ Maximum discrepancy +- 10% of design gradient, and maximum +-15mm from design level.
5e9e8b91-10f3-583d-835c-27050fe9d4b3 | note | Frequency - Prior to backfill.
9acebefd-d7a0-5bbc-8695-b0e792644433 | note | Verifying Documents - Survey as builts
5d0b24ca-e9e2-5ccd-aa27-c88a9e780707 | note | Engineer / Client - R
21beb6ea-0faa-496b-b23c-f7724c073a3b | checkpoint | 3.4 - Chambers / sumps / wingwalls
242cc820-467a-55a1-a752-973a4ea429df | note | Inspection / Test Method - Survey / site inspection.
a3b61a4c-a286-5f1a-884f-b7b85307f827 | note | Acceptance Criteria - Benching in accordance with specifcations and drawings. Position in accordance with the design
6f1f69b5-ab91-5d77-a170-f728d65f34ad | note | Frequency - Prior to backfill.
52494458-c4e3-51ed-8fc4-2c6261531e5f | note | Verifying Documents - Engineer approval.
fe092234-18a4-5937-ad58-08463c32b8fc | note | Sub Contractor - H
0e0dd57b-15fe-51e9-8142-d35fe46d836f | note | Head Contractor - H
22650b4b-216c-5b3d-988c-4e3f1474b3e0 | note | Engineer / Client - W
0b4a07d8-db8e-4df2-a4d5-3fddcdeedc61 | signoff | HOLD POINT
08a0a230-9b7c-40f5-8973-6941bde1e871 | checkpoint | 3.5 - Pipe bedding / haunching /overlay
08ba39bf-f6fb-5f4e-b596-81edd5e877e9 | note | Inspection / Test Method - Document review site inspection.
9662b84a-f841-5591-83f0-2c41eeb57e5f | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines and AS/NZS 3725 for concrete pipelines.
59a477a3-9787-535c-abff-fc748119478b | note | ○ Bedding minimum 100mm up to 450 diamter pipe and 150mm pipes > 450mm.
95fddc14-0416-5f18-8066-0a0548566cad | note | ○ For PVC overlay >100mm over pipe and for concrete 1/3 diamter of pipe.
475c2992-64ee-5c25-8039-c515819bccdf | note | Frequency - Prior to backfill.
22f081c2-8b71-5b31-821a-b52943c65c33 | note | Verifying Documents - Photos or site inspection.
3fea2789-7327-52d4-87e5-81193cec0643 | note | Sub Contractor - H
da75e263-3091-5e6f-a6dd-60935927fdbc | note | Head Contractor - H
56e506ef-cd06-5684-ae5d-6a7ac6d87c33 | note | Engineer / Client - W
c4a9f4fb-a22d-40d1-94de-666fac3fb83c | signoff | HOLD POINT
e9363d36-d550-4c80-b201-0cb5767a6d72 | checkpoint | 3.6 - Backfill
eead4c03-41ff-560a-8741-3d5ff99b666d | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
aa738d67-1da7-5ccc-ae2f-09b7427a4c5a | note | Acceptance Criteria - Minimum 20 Clegg reading
8cc089fd-20f1-5fbe-adc0-06a3c900708e | note | Frequency - Prior to placement of each layer of backfill.
653c29cb-583a-50ac-bcd9-712a6501527e | note | Verifying Documents - Test records.
ccc2375f-021f-576e-8c5e-72d6bd14458b | note | Sub Contractor - H
45709f23-1652-50be-94ad-a243d59be49b | note | Head Contractor - H
f612a2cc-c804-52e1-9959-923fc56fb096 | note | Engineer / Client - W
28651bb5-20ea-4f23-b642-e9b4fbe97120 | signoff | HOLD POINT
a5379bff-9f33-4419-a5d5-f937994a5b5d | checkpoint | 3.7 - Hydrostatic testing
8fdd2ce2-00db-5c02-8d40-72db7a68ddbf | note | Inspection / Test Method - Document review site inspection.
b95d34a3-d27d-53ea-8616-9b876803ae28 | note | Acceptance Criteria - In accordance with NCC CoP and Engineer specification
b793225b-4d10-5964-be54-da971576e6ef | note | Frequency - After backfill/prior to road seal.
88b8dd49-701e-5424-9f8e-c820eb2b25eb | note | Verifying Documents - Test records and Council inspection records.
b8475ef4-0208-51c4-af06-5d06b6ecca10 | note | Sub Contractor - H
dad3d8ba-8562-5af8-b86d-8582b282fc81 | note | Head Contractor - H
4a63df0f-8ca2-5bb8-a4f6-f4cace3b9e9a | note | Engineer / Client - H
8f3f9fd2-9549-4aca-8809-82c59127e44f | signoff | HOLD POINT
dd1c2f4a-2dc6-4b10-ac9a-e6435e5cc20f | checkpoint | 3.8 - CCTV
b7f6d865-1cff-5cd2-8102-55d11555bcd1 | note | Inspection / Test Method - Document/video review
d3e8993c-7888-5f45-90cc-ce957b950ee2 | note | Acceptance Criteria - In accordance with NCC CoP and Engineer specification
3bfc018b-05b5-5720-9a07-c054f6b14c16 | note | Frequency - After backfill/prior to road seal.
970ed23e-adae-5cec-a4ad-a1345f4cfa48 | note | Verifying Documents - Test records and Council inspection records.
432a4544-778d-5cf2-b153-bb289a9dc14a | note | Sub Contractor - H
a06f92a6-b700-5423-9400-237cb8b15e75 | note | Head Contractor - H
703d0e60-8ceb-5cef-beb9-7f7b5b1c7ec6 | note | Engineer / Client - H
6aa40378-2fd2-4a0e-b046-96b08e0f9beb | signoff | HOLD POINT
1cd8afd5-ad0a-4213-9311-6d6a0d655e20 | section | 4 - CLOSEOUT
1b33dbab-9df9-4a3b-af19-3174cca34acd | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
2388ecc2-6ec9-5bfe-a64f-dc4b0be0fa74 | note | Inspection / Test Method - Document review
f6bab6c1-f9c9-531f-b8a4-554be46738af | note | Acceptance Criteria - Collate and supply producer statements
00a038d9-b485-56c3-aa22-ebc586377011 | note | Frequency - Upon completion of stormwater works.
2ba5c23e-7329-5a90-abdb-b1abf23e2379 | note | Verifying Documents - Producer statements
e948b87c-90c4-53eb-a5a7-2bde2ca6f66c | note | Sub Contractor - H
881c093d-79aa-5da3-916c-20d88c9c6d5d | note | Head Contractor - H
cd4066bc-97d1-5dd8-b23e-3b11a7a00ba4 | note | Engineer / Client - H
b3d29d88-c124-42d1-b6ef-09408bdcd194 | signoff | HOLD POINT
58445cdf-8fe5-4401-8b9b-ef008d12c6a8 | checkpoint | 4.2 - Collate and supply Council inspection reports.
acec829e-5b7b-57ea-ae28-8ffa7e0121ad | note | Inspection / Test Method - Document review.
ee322a41-82e0-50fe-aaa3-8168c9106ebc | note | Acceptance Criteria - Collate and supply Council inspection reports.
e134e30d-8e30-54cb-a919-a0d1e9d6bed0 | note | Frequency - Upon completion of stormwater works.
9a19ba1d-10e5-5e64-bc0c-3fef642de386 | note | Verifying Documents - Inspection records.
5df2fbbd-99dc-5c48-85c7-0d1773dfedfa | note | Sub Contractor - H
a48c4957-7e90-5c2c-9dd9-726f8ca05cb7 | note | Head Contractor - H
58ba9933-6aaf-5c82-94cd-23c0d6632b7d | note | Engineer / Client - S
eeb4f109-4e88-4e19-b35c-60ad3758d28a | signoff | HOLD POINT
0f5e2420-292e-42d1-84c8-1c8de7a0ffe5 | checkpoint | 4.3 - Collate and supply compaction records.
93e6891f-b494-54dc-9e85-8c8f5d2967a2 | note | Inspection / Test Method - Document review.
0c540fa0-f116-56ff-b581-7e0166c08d16 | note | Acceptance Criteria - Collate and supply compaction records.
c11519c6-62b8-5c7c-a883-61feacee325a | note | Frequency - Upon completion of stormwater works.
ebe5595d-6ccf-5602-8da5-6f27ce8b410b | note | Verifying Documents - Inspection records.
e7862053-2451-51ce-92e1-ff8731d6ff69 | note | Sub Contractor - H
fbcfb3c5-735d-571f-be19-ae73d503cfc5 | note | Head Contractor - H
28172e24-dcc0-521c-91b0-6d573dcb2ad3 | note | Engineer / Client - S
713e2164-b452-48d5-94f1-bdb31e73ec81 | signoff | HOLD POINT
c8478371-ba0f-44cd-9019-ce80a4876ab3 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
c341d11b-11b4-5233-8420-f971ca39c19c | note | Inspection / Test Method - Document review / as builts
96130006-285a-52a7-a50e-33238d7c225e | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
a42d7ba1-641d-5561-9bb3-88ceb0f17e69 | note | Frequency - Upon completion of stormwater works.
2dd2f2e6-0a16-510a-9275-66c710b79847 | note | Verifying Documents - As-builts
ad892a19-b8b6-5f5a-ae0f-cb6f1b9f4c89 | note | Sub Contractor - H
375b648d-13a9-532c-a2f9-3a06deb39a11 | note | Head Contractor - H
f3906a81-f43b-5e8e-85f5-baf983714d52 | note | Engineer / Client - S
9280a581-7fe7-4c00-ba37-a3dbfce383bb | signoff | HOLD POINT
32fd55e8-d7e5-4b3b-a843-b28a1cc27bac | checklist | ITP - WASTEWATER Rev 0 | itp | ITP - WASTEWATER
2e6d10ea-8e17-4e37-8dc9-83bc2da8d3b0 | section | 1 - PRELIMINARY / GENERAL
e00f95c6-d8f9-429b-8f13-8e850667abc1 | checkpoint | 1.1 - Consents and trench opening notices
ca3b44fe-d278-533c-9881-ecddef257738 | note | Inspection / Test Method - Document review
a0042fb8-beb1-5c1a-87c8-1fc950c083b4 | note | Acceptance Criteria - Authority approvals.
c3286326-4ccc-5ded-a7a6-caeb447c8668 | note | Frequency - Prior to excavation
f20cd56d-6c1b-5e10-b145-f6e51dcb567f | note | Verifying Documents - Approval from relevant authorities.
39b05a4f-0101-5da2-afb8-3bc216c581f9 | note | Engineer / Client - R
bc584036-de48-4f1d-811c-6a3554547c9a | checkpoint | 1.2 - Drainlayer registration
9798dad3-0a74-5626-92a1-7ba9c2b9a677 | note | Inspection / Test Method - Document review
94593d99-720c-5eeb-8411-aca3242b065b | note | Acceptance Criteria - Certification
21c8d843-da1b-5766-b0d5-cefd8c05889c | note | Frequency - Prior to drain laying works.
e319d118-205a-5437-a8ab-7c1a44410b85 | note | Verifying Documents - Scanned copy
13ff70d3-7b0d-5ee2-bbcc-13a5c6f34fdd | note | Engineer / Client - R
17b11906-0735-4bd8-984b-8885dd370e40 | section | 2 - MATERIALS
ec447603-4cca-4a66-ad2d-8bdda4104d31 | checkpoint | 2.1 - PVC pipes
bd14cac6-4435-514f-ab56-5969cceda724 | note | Inspection / Test Method - Document review
fc5aaa91-6810-5e63-a3dc-783481993f5e | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
88ae99e6-722a-58e1-ae4a-4a9820a6f392 | note | Frequency - Prior to order
3ce168fc-ded6-5a84-9026-306998578798 | note | Verifying Documents - Technical documents.
2ec236dd-4317-5a25-84d2-3703909615ff | note | Engineer / Client - R
1a3db6ab-2ff0-423c-b577-201fbbf5ab79 | checkpoint | 2.2 - Precast chambers
97249ef4-3f3f-5d9c-aa3a-c07d269b5c19 | note | Inspection / Test Method - Document review
0d6f8efd-dbbb-5ecd-a196-44f504106534 | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads.
5fe9c02f-e971-57ff-8387-08a3e953f348 | note | Frequency - Prior to order
94f48030-00b9-5c6b-b4b9-b28d22cf8d28 | note | Verifying Documents - Technical documents.
dc42f56b-8b9c-5676-a148-fff2454e9f4f | note | Engineer / Client - R
e9625223-65f6-4242-8348-01dd48f4d8dc | checkpoint | 2.3 - Access covers and frames
e6ced649-9eab-548c-9615-804b29d059dd | note | Inspection / Test Method - Document review
78f5ece6-caff-5dcc-8d52-33c9549de17b | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
97c20740-b845-553a-b5ee-8195e675bb40 | note | ○ Designed to minimum AS 3996 Class D or better.
adbfd1f7-9170-5946-980e-b677950e3fab | note | Frequency - Prior to order
0e684c10-39c3-506e-9d79-8863612bfee4 | note | Verifying Documents - Technical documents.
2550a466-a4c9-506f-af4f-ce9ffc02a741 | note | Engineer / Client - R
c1610bbc-c390-4360-b8c2-a0bdd9979620 | checkpoint | 2.7 - Backfill material
b37ecc2f-8c96-4ceb-bee2-0887268dbe05 | checkpoint | 2.7.1 - Bedding haunching and overlay.
5055ff4f-e5e9-540b-8612-696a35eb7ca7 | note | Inspection / Test Method - Inspection
960f1749-b6b5-543f-8e3f-c13600a173b5 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
0f011d28-81b8-548f-91be-0e6e7cb71219 | note | Frequency - Prior to placement.
737abfe3-6529-5d3d-8c3e-efa89d8c439d | note | Sub Contractor - H
00b06631-bf21-55f4-b86a-511086b26c75 | note | Head Contractor - H
6f1f7d53-b543-56a4-9fc9-9aacc751f17e | note | Engineer / Client - W
b7b5247d-dad3-4571-b5dc-2b403531292e | signoff | HOLD POINT
66841fbf-dfc1-4092-8876-3ad40bb6055e | checkpoint | 2.7.2 - Fill to subbase
e9b36a28-a6ca-5951-bc97-f90807eb4561 | note | Inspection / Test Method - Inspection
2b05d3e6-4411-58cf-8755-10f165d7fc60 | note | Acceptance Criteria - AP65 of other approved imported material.
2e8743ea-d34d-518e-bfb5-74196c4dfd89 | note | Frequency - Prior to placement.
83b696d1-8379-5a4a-bbb6-287d7c505e1b | note | Sub Contractor - H
930c9c75-b037-5a65-a522-625b4c3f0a90 | note | Head Contractor - H
37bc440a-6955-5d61-94db-74802d8aa618 | note | Engineer / Client - W
1a52b660-3a3c-4aea-a017-9fb18fd74bd4 | signoff | HOLD POINT
78014230-c7d5-4e7c-a649-e97cb1ca04d3 | section | 3 - CONSTRUCTION
5fb7e7bc-2d57-4041-aca9-24ec37560055 | checkpoint | 3.1 - Set out
8e8a46a4-9d49-52f6-9b15-cdc2102cb9df | note | Inspection / Test Method - Document review.
e293f279-bab2-58f9-a7a0-b42255cdeb2c | note | Acceptance Criteria - Survey setout information in accordance with the design.
fa684904-b0e1-5773-9fa5-c4c3b54bbecc | note | Frequency - Prior to excavation.
f8952537-c633-52e5-978b-d26b1ad42980 | note | Verifying Documents - Survey file.
7f4cc063-c13c-5ac5-8efd-6da7c5e34a99 | note | Engineer / Client - R
5f2832c4-5e5c-4bcb-a915-0e76510022d5 | checkpoint | 3.2 - Trenching
31ed9eec-1242-5334-9ebd-4e40b4ee0f1f | note | Inspection / Test Method - Site inspection.
3bc9f590-abc9-5574-99fc-a81bfd35b3c8 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
37d65701-bff5-5250-8992-c1b9c6c401a7 | note | ○ Min widths:
d1d43754-2839-58b9-83f3-2b235f7f0205 | note | — pipe dia DN75 - DN150 = 350mm width.
b66806b5-f978-521a-98e6-169b3b4081d8 | note | Frequency - Prior to pipe laying
f505f140-5fab-5812-a101-3ee8e59bf4d3 | note | Verifying Documents - Engineer approval.
34edad07-1197-5b35-8495-fb7b65761816 | note | Sub Contractor - H
f2f59524-128b-5d12-93b1-dd6c4686ba52 | note | Head Contractor - H
4d2f4106-1f56-57e2-8a14-cf39647a8eb5 | note | Engineer / Client - W
5b432648-921a-4654-9a6f-769f6a000f02 | signoff | HOLD POINT
ede1c453-3193-4c73-a793-34e948f5c4cb | checkpoint | 3.3 - Pipe laying
55abef82-babe-5044-9e72-7b8b5d1ef386 | note | Inspection / Test Method - Survey
13026fc2-8097-533d-b5bd-a3e2bc25b056 | note | Acceptance Criteria - Record level of main upstream and downstream of each chamber.
29df168e-cb2c-533a-a6f5-8d5c0d0ab607 | note | ○ Maximum discrepancy +- 10% of design gradient, and maximum +-15mm from design level.
87903c20-5477-5f7d-9095-cc04e7e846fb | note | Frequency - Prior to backfill.
d146e1bc-d938-5004-9e79-c28108977b25 | note | Verifying Documents - Survey as builts
68268765-fc0f-5928-a535-297e9f71a620 | note | Engineer / Client - R
891fe4cf-f6a5-4548-ac0e-19aecd0f404b | checkpoint | 3.4 - Pipe bedding / haunching /overlay
7416da3c-e428-5e71-b640-6e6720cf78f7 | note | Inspection / Test Method - Document review site inspection.
659abc82-b0c7-5624-89cf-85f07c0abf5a | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
e8cd2b73-cc65-5ccc-8db3-e011b2717cb4 | note | Frequency - Prior to backfill.
67570f73-4929-5297-973b-97428fe9a324 | note | Verifying Documents - Photos or site inspection.
1324f7e5-9fc6-5371-8585-b0379b2f39e9 | note | Sub Contractor - H
5b7f01ba-5435-52c2-b9de-d3fcb436c7af | note | Head Contractor - H
7c89a5bc-b36b-57df-a67f-1f5f05fc39d5 | note | Engineer / Client - W
8a91f547-24e4-4329-8801-4a1c2bc762e4 | signoff | HOLD POINT
833825e5-de91-404c-a979-23ae882d16fb | checkpoint | 3.5 - Backfill
023428a9-5e28-5fa1-8c22-c0ecdbb77f12 | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
c9ec3e59-2a08-5f52-90cb-52099f31cccc | note | Acceptance Criteria - Minimum 20 Clegg reading
151db822-98fd-51a6-998a-1de3f3f2de63 | note | Frequency - Prior to placement of each layer of backfill.
cc29ac21-09a7-5af9-9f4f-d3cf85ed0cd4 | note | Verifying Documents - Test records.
b44f8c8e-2aca-5e59-8d33-3f716cfa347c | note | Sub Contractor - H
dfdab83e-b364-55cb-8ff8-7d9f7d7c848c | note | Head Contractor - H
d9f91c0f-4523-532b-9244-213abbe87a00 | note | Engineer / Client - W
057c2a46-9506-4d4a-9ac9-9acffa1aab5d | signoff | HOLD POINT
4da3956c-d1be-4222-bcea-4a40da8550f7 | checkpoint | 3.6 - Hydrostatic testing
8939252f-61ca-54fe-abda-9fee032489e1 | note | Inspection / Test Method - Document review
f088790e-575d-5d26-8e77-77ba66d5ed14 | note | Acceptance Criteria - In accordance with AS/NZS 3500.2 section 15.2
f91735b9-9fb9-5b16-b33e-e2bcb6075311 | note | Frequency - Prior to backfill.
e1b41c43-14e2-5570-9695-ef8c3e9e0dc3 | note | Verifying Documents - Test records and Council inspection records.
015344b4-945c-50b9-8df7-9ab36660f8e3 | note | Sub Contractor - H
0664c263-7e88-5c1a-9236-9f33a9db85ef | note | Head Contractor - H
df82f9d2-f081-5828-97c5-a7748f082d25 | note | Engineer / Client - H
8dae0c69-255e-419c-a943-f1c812ea8d39 | signoff | HOLD POINT
75e84767-cc83-4385-95ac-0185614745e1 | checkpoint | 3.7 - CCTV
95202881-dacb-5739-a6e5-7d4deca3da99 | note | Inspection / Test Method - Document/video review
23439e17-224b-57a3-abc9-54fe52be2dbb | note | Acceptance Criteria - In accordance with AS/NZS 3500.2 2018 section D1
cf4eba89-84f1-59e0-9685-bad2f5292701 | note | Frequency - After backfill/prior to road seal.
b059c2e2-dbbe-599e-90e9-dc800a38e3ef | note | Verifying Documents - Test records and Council inspection records.
80649fc2-608e-5b89-b209-eedee14ede09 | note | Sub Contractor - H
c19136df-b719-5da4-b534-9f6863f316c4 | note | Head Contractor - H
1d4ed319-eb0d-5cfc-a9e2-4ad98549321e | note | Engineer / Client - H
2f9c8cda-d6ac-4012-ae3e-a1d2b98d433b | signoff | HOLD POINT
b52b1a24-5de4-44f3-903c-7271acf1ed91 | section | 4 - CLOSEOUT
5afc3cc3-ab16-4e64-accc-d48228c7c1ef | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
f0000280-4c84-57d0-9679-ef40a230aa90 | note | Inspection / Test Method - Document review
a02cf704-875e-5975-b67e-cb2e58d135cb | note | Acceptance Criteria - Collate and supply producer statements
a21956c0-2dd7-5e7f-a873-7baca7056f96 | note | Frequency - Upon completion of wastewater works.
3bf0e7aa-0bc0-5238-a2a6-468a0a6ffb05 | note | Verifying Documents - Producer statements
24e316f7-0436-523e-b35e-3f2a1b3e74d3 | note | Sub Contractor - H
4d19524e-5cce-5510-9134-9b32d9f8fbd3 | note | Head Contractor - H
6633e728-db56-582e-a68d-6430fc92a8c1 | note | Engineer / Client - H
60beff78-1bc9-44c2-be16-bd5d535477c2 | signoff | HOLD POINT
c2cfe096-783a-4a08-857d-d0b1ca331ad3 | checkpoint | 4.2 - Collate and supply Council inspection reports.
93e757e4-5312-520a-8fe5-ee40783593ce | note | Inspection / Test Method - Document review.
54d0a837-3818-53f2-8efb-9226778cb628 | note | Acceptance Criteria - Collate and supply Council inspection reports.
4ffcb963-4e5f-5abe-93d0-7d3c58cbdb74 | note | Frequency - Upon completion of wastewater works.
e0a2d829-9f58-50f8-babd-cace7883af0a | note | Verifying Documents - Inspection records.
79dbebd7-0c12-5207-8aed-afd96330ade5 | note | Sub Contractor - H
d92ebbf9-896d-5a96-8c2b-7ee076718e89 | note | Head Contractor - H
7e7f1b12-30c6-5c7d-b43f-225bbf557df5 | note | Engineer / Client - S
3e1cfc6a-d129-44b0-a770-61e3403f0012 | signoff | HOLD POINT
a3e8b589-6352-4ce0-bfeb-5a413a1f5269 | checkpoint | 4.3 - Collate and supply compaction records.
65613270-cd6d-507b-a7e3-34c3dd1cad2f | note | Inspection / Test Method - Document review.
ce5b88a7-0dfe-5bd7-a881-43c054c1294a | note | Acceptance Criteria - Collate and supply compaction records.
ab1896a7-ad73-564d-a709-fdd80c029228 | note | Frequency - Upon completion of wastewater works.
a3c1fdcc-97ef-544d-a033-d3374cacde1e | note | Verifying Documents - Inspection records.
101a5a3f-f0f1-5804-94d4-e027da434839 | note | Sub Contractor - H
1c0983b8-c67b-5e2c-adda-b2160a7b4e99 | note | Head Contractor - H
6bd3d11d-3077-5da4-9010-0d553131d9fc | note | Engineer / Client - S
6eb4ae19-7f2e-4833-a45c-e041f6a3cb3d | signoff | HOLD POINT
b002334b-c235-4ee3-90f5-97522dd422d4 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
d5b11304-dbc9-5442-8490-956da6536213 | note | Inspection / Test Method - Document review / as builts
ed50f8ad-e584-5f42-a047-889035da9dfc | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
2dafbbf5-dc0c-51d0-80ec-d213946b6213 | note | Frequency - Upon completion of wastewater works.
153e0484-b269-5dd7-8e9c-b8e8e2da81fc | note | Verifying Documents - As-builts / test records.
d9b95000-a529-578d-8ef1-59ad5a3e3822 | note | Sub Contractor - H
c10c0593-fd6e-5fb1-bd4e-dfda440def4a | note | Head Contractor - H
8e7cee4f-6da8-5ed2-b0fd-0177ddebf654 | note | Engineer / Client - S
6be52e7c-6e28-467e-81ab-b5e548f15440 | signoff | HOLD POINT
cd5be06b-5b35-4309-8186-fc235fcf8bf6 | checklist | ITP - WATER SUPPLY Rev 0 | itp | ITP - WATER SUPPLY
b88719dd-75fe-4ac6-8bf0-1057701d6ab3 | section | 1 - PRELIMINARY / GENERAL
e31b1149-9703-4e8b-8366-28553f9c2929 | checkpoint | 1.1 - Consents and trench opening notices
301d3b90-8eb1-561a-b809-ed1034ffd7a2 | note | Inspection / Test Method - Document review
a1a53d2e-ade6-5b2e-b3ce-3178fd333b51 | note | Acceptance Criteria - Authority approvals.
803b00b7-427b-5d85-bb6e-39b93b897d15 | note | Frequency - Prior to excavation
a5734aa1-a88c-534b-b711-38def942ba6f | note | Verifying Documents - Approval from relevant authorities.
8c95c261-d389-564c-9e06-288c50cf79b6 | note | Engineer / Client - R
d4b9c87a-b86e-4a3f-bc6f-5d57bcaec72d | checkpoint | 1.2 - Installer registration
6702c1ac-d996-57e1-9110-c33a8c44bbdd | note | Inspection / Test Method - Document review
b52a288c-2d5c-54af-95b8-a27348f1828a | note | Acceptance Criteria - Certification
758709ca-8100-58cf-aaa9-93f0b34dceb1 | note | Frequency - Prior to drain laying works.
68ca1828-b43e-5a62-8042-1d01e14387c9 | note | Verifying Documents - Scanned copy
0ce4a512-3362-5f03-8979-8f2b0efbdee8 | note | Engineer / Client - R
61cd6317-6eb2-41c0-94d3-3c4779177d84 | section | 2 - MATERIALS
bc150cd2-eb2e-4b5e-8ec3-dfe1d2b196af | checkpoint | 2.1 - PVC pipes
3928c9fc-722e-5e88-ad5c-65ee7a91835c | note | Inspection / Test Method - Document review
74e7fb1c-baa2-5526-bd13-7910f43dea95 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1477 (min PN9)
7850e5a4-8c58-5912-af18-5f8bfcb3a017 | note | Frequency - Prior to order
65c89fa2-65bd-56b3-ba62-b008ef948ba1 | note | Verifying Documents - Technical documents.
cc3cd22c-00bf-5a96-99a2-75c515322433 | note | Engineer / Client - R
9a5b84f4-b523-4fc4-9c44-b6c22af65246 | checkpoint | 2.2 - PE pipes
f463d83d-f903-5ed1-852a-887b608bb7a5 | note | Inspection / Test Method - Document review
08bf5b05-6c2e-59c5-a9a7-69edecb357a1 | note | Acceptance Criteria - New and in good condition and compliant with AS/NZS1430 (min PN12.5)
eab6fb76-3875-5ebe-81b2-748d523c38eb | note | Frequency - Prior to order
18148193-7ce3-5118-a3b0-ff06a43e2462 | note | Verifying Documents - Technical documents.
c58875d9-bfb4-5b3e-840f-5c140837f091 | note | Engineer / Client - R
6e426b94-5b4a-4ea4-a80e-0c94efa4dacb | checkpoint | 2.3 - Precast chambers
9de80f3a-5aa3-5b82-8416-8fcf3094ee94 | note | Inspection / Test Method - Document review
6d182712-9c6f-5bf8-b5c1-83ac353074ae | note | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN- HO-72 traffic loadings in roads.
09a84ea6-91c8-55a3-8b25-911a1f258ae3 | note | Frequency - Prior to order
1f05c52f-1dfa-5eb6-84a0-b0241adba06e | note | Verifying Documents - Technical documents.
e694d4b8-a58d-5bed-ac0f-8ec33f2cf35b | note | Engineer / Client - R
e3973a6a-d247-41aa-8022-cdb42e9451b7 | checkpoint | 2.4 - Access covers and frames
f7ef8d45-01bf-513e-a935-9b0c182f1094 | note | Inspection / Test Method - Document review
17d79faa-b004-504c-965a-7b9e0cf7b749 | note | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs).
b60352ff-1679-5ce5-a88a-1794514aa49d | note | ○ Designed to minimum AS 3996 Class D or better.
a9e5aeac-e762-5ab8-adcb-c65a07c0d316 | note | Frequency - Prior to order
50cd80a8-9ea5-5a07-9f57-7fae2793aa40 | note | Verifying Documents - Technical documents.
bd05f74a-a8be-50b1-ac6c-48dd73f1c10f | note | Engineer / Client - R
d1b90265-599c-4038-a34d-0b64dd138d12 | checkpoint | 2.5 - Backfill material
889f1774-926e-475c-9865-257cf0eab3b8 | checkpoint | 2.5.1 - Bedding haunching and overlay.
2d457acd-308f-5ed8-82ef-50468935651d | note | Inspection / Test Method - Inspection
0dbd665d-1a1c-5f8b-8e15-b831f4f97a71 | note | Acceptance Criteria - 5-14mm clean washed granular mix.
3376dc14-f95a-550e-a02d-c43a12445d71 | note | Frequency - Prior to placement.
8ea6d8f3-4c76-598d-b59a-6ac575cf57cb | note | Sub Contractor - H
ac5d9f86-0f57-50d8-b14c-9f6c19954ac5 | note | Head Contractor - H
06ff516a-70f2-5207-b9c2-8ad78d8158de | note | Engineer / Client - W
a3b73e27-171b-4a1c-8f9a-55faaf2a5311 | signoff | HOLD POINT
648643d1-031a-4e20-af57-883215364519 | checkpoint | 2.5.2 - Fill to subbase
de30777d-bb53-5d40-9404-6cd7b1eea03c | note | Inspection / Test Method - Inspection
9389e161-cfe8-524c-8473-988d394d8896 | note | Acceptance Criteria - AP65 of other approved imported material.
3215c92c-41af-59a3-9b4e-a07cbc4d82cf | note | Frequency - Prior top placement.
fd73e1fd-8ad2-5a8f-b0b5-a20f903abfcc | note | Sub Contractor - H
c87afcdc-fd09-54d7-b3c8-035c744ffa22 | note | Head Contractor - H
c89225ff-617c-5db9-b517-75eef710f4ac | note | Engineer / Client - W
2652384c-3076-493e-8be8-e68423e73bf5 | signoff | HOLD POINT
f7d7a0cc-a66c-44b2-af34-e498f5169252 | section | 3 - CONSTRUCTION
8d87835e-d229-4ac3-ad58-3a1fa3e8bcfb | checkpoint | 3.1 - Set out
e5eedafb-a3e7-54d0-acd5-6967432736b5 | note | Inspection / Test Method - Document review.
920faeb7-837d-566b-bd0f-d69709a3ace4 | note | Acceptance Criteria - Survey setout information in accordance with the design.
69be2a4c-9f26-51ed-8f88-4da0afd13065 | note | Frequency - Prior to excavation.
947866d1-b661-5ecb-83cc-25b24ed00ce1 | note | Verifying Documents - Survey file.
8b5c52ff-b46c-500f-bb23-252234add5f2 | note | Engineer / Client - R
eafa1727-3dc2-4721-aca9-71b694cf5f0b | signoff | HOLD POINT
75b3fe88-4486-4e76-b3ac-6b1d9408b458 | checkpoint | 3.2 - Trenching
948b0007-6fec-5198-85e6-7b609d5e354d | note | Inspection / Test Method - Site inspection.
41402c0a-4c63-55fa-8fc2-e26031ad5986 | note | Acceptance Criteria - Trench widths ok and no unsuitable materials present.
beee5484-d69b-52c1-a0bf-a5a35ac3df9e | note | ○ Min widths:
705ff340-153d-5872-8ddf-38a6f3dc94e9 | note | — pipe dia DN75 - DN150 = 350mm width.
1ecb597f-8ea4-547e-a914-05b1470feeac | note | Frequency - Prior to pipe laying
bb9fe77a-c44c-5296-b774-3fe9886650e4 | note | Verifying Documents - Engineer approval.
7f9c0a6b-a800-512b-bfc8-823233c85dd3 | note | Sub Contractor - H
e98d97f6-769c-54ec-8b9d-70bb3a0ca92b | note | Head Contractor - H
59443726-fc64-5e92-bbe8-a9f94585161e | note | Engineer / Client - W
a0ce76b0-65d4-450e-b29e-7bb7aa80ff87 | signoff | HOLD POINT
44ef1b12-aae1-4116-b1ab-a3893fc13c19 | checkpoint | 3.3 - Pipe laying
aba4a7b9-1b79-5bf9-9cba-dc510e7b047c | note | Inspection / Test Method - Survey
ae6b0b36-a9cf-59ff-bcbc-44c4ad8431df | note | Acceptance Criteria - Alignment +-50mm from design, surface cover in accordance with HDC ECoP.
d1b8539a-afb9-5408-8aa3-18761cd03d07 | note | Frequency - Prior to backfill.
a051c48a-5d0f-50be-8a6b-490534c73a3d | note | Verifying Documents - Survey as builts
2409d02b-4afa-54bf-ad50-5d6746eeb0d1 | note | Engineer / Client - R
42730ddd-bfa5-4391-b67e-b62962c0debf | checkpoint | 3.4 - Pipe bedding / haunching /overlay
fd6c709a-6983-56d2-8267-e99496601fac | note | Inspection / Test Method - Document review site inspection.
9325be03-9916-5672-99db-35534e101da3 | note | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
d101fd6d-716f-5715-9c7c-b5e6c6ce9b1b | note | Frequency - Prior to backfill.
038e3795-c001-5081-982e-35e63664f23c | note | Verifying Documents - Photos or site inspection.
9c8b7a33-dd36-5a12-8bd4-b9394cbeb2f0 | note | Sub Contractor - H
9460ba6e-42df-5723-9de9-4c9b2171c9de | note | Head Contractor - H
f6c3a304-00d6-538e-9c76-3717e59c67b2 | note | Engineer / Client - W
547e2702-b23c-490b-812b-fafb4c9440fe | signoff | HOLD POINT
76743a2e-8a9d-423e-8f6d-7c71e11cafcc | checkpoint | 3.5 - Pressure test
b65ecf39-e6ef-5056-a70d-2450cedbbc34 | note | Inspection / Test Method - Inspection.
9cfbdd33-b668-57e4-b57c-ca446f5e649f | note | Acceptance Criteria - In accordance with section C3 of NZS4404 and AS/NZS 2556.
6b6ebffb-0647-504c-9852-55d22538a28f | note | ○ To a pressure no less than 800kPa and no greater than 25% above the rated pressure of the pipeline.
bbd094f9-4908-5d97-afd3-d0bdb652d4ac | note | Frequency - Prior to backfill over joints and fittings wherever possible.
11ec79c6-4c17-5acb-8e98-cd3a60671f9a | note | Verifying Documents - Test records.
65808ed2-efb3-57e3-be37-bf5cd149ce0b | note | Sub Contractor - H
593ef8f7-4261-5d3c-b7a6-bd4fb56f7e7d | note | Head Contractor - H
258c5a60-1dad-5e83-86d2-acf29f0e9da2 | note | Engineer / Client - W
35fee1c9-c7b1-4799-baef-21662221d9b3 | signoff | HOLD POINT
382bef28-91dc-4e3c-a542-168ce7a8a59f | checkpoint | 3.6 - Backfill
a4378638-c51a-5482-9821-d484d4ddd098 | note | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
207ced84-3a95-5964-bb65-8659e00283a9 | note | Acceptance Criteria - Minimum 20 Clegg reading
53ac6581-7140-5faa-b0b7-82822ea3d4e6 | note | Frequency - Prior to placement of each layer of backfill.
a54d1feb-3a4f-5794-94a7-45f03bb9ebc5 | note | Verifying Documents - Test records.
b134ac90-74ef-59e7-ac4e-7036abbe6f53 | note | Sub Contractor - H
102a7a6e-b36c-580a-9eb4-0276380ff225 | note | Head Contractor - H
c10dedde-b0b7-5d7d-9962-9199b85953c8 | note | Engineer / Client - W
1178c717-5f82-47d5-a41e-13396c9c57ab | signoff | HOLD POINT
8262e00c-5298-4d56-a3cf-4075fda795e7 | checkpoint | 3.7 - Disinfection
8092669e-cfca-501b-b5a2-ac9dc28b595d | note | Inspection / Test Method - Inspection.
edd85623-a9e6-5e95-8c21-36102ed7ee80 | note | Acceptance Criteria - Carried out in accordance with NCC ECoP (amended appendix D of NZS4404:2010).
d884f516-e89d-5d89-ad22-6fe9ae253875 | note | Frequency - Prior to connectioun to mains supply
fa070a54-41e5-5e46-b571-c16c041c0be1 | note | Verifying Documents - Test records.
0fc29ea0-fa24-53e3-8bc9-cf1d0138b730 | note | Sub Contractor - H
4cbcd581-9487-5182-9afa-c6de3816ca16 | note | Head Contractor - H
27edc78c-562e-5da9-bcfc-dec87b5de5ce | note | Engineer / Client - W
c9acec5c-6445-4760-af95-3ea38f5cc4bc | signoff | HOLD POINT
efe753dd-2b43-4ad0-8808-501d88f8652c | section | 4 - CLOSEOUT
0e6f0932-d70a-4006-8aab-553a149ac90b | checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
203bc3fd-67c6-5de8-aacd-89f230c7f48e | note | Inspection / Test Method - Document review
ef90fc23-08e6-5429-9578-eadcc8ecc905 | note | Acceptance Criteria - Collate and supply producer statements
6be25895-7afb-53d0-9536-b911afc4b4e3 | note | Frequency - Upon completion of Water supply works.
db3eeb1d-6f53-5380-a692-dd8d402e3baf | note | Verifying Documents - Producer statements
656a8ca6-f062-57dd-9cc0-f96b541882bb | note | Sub Contractor - H
2e8b8e40-4653-5d8f-afb4-ba93aed26efb | note | Head Contractor - H
b2b7e6fb-2c72-56f3-833f-d3fae60523b0 | note | Engineer / Client - H
49778f2d-e6ca-4cd1-8f87-b6c35a044030 | signoff | HOLD POINT
f34dddb7-01ff-4418-83fb-f7fa2ec416a1 | checkpoint | 4.2 - Collate and supply Council inspection reports.
cb72db69-09f1-5d93-a84b-3d4606c5aa5f | note | Inspection / Test Method - Document review.
522c382d-c29b-573c-a51e-df9d2c895750 | note | Acceptance Criteria - Collate and supply Council inspection reports.
87bea0ad-ed10-53c3-938e-b2cf1e4cbf10 | note | Frequency - Upon completion of water supply works.
f32a60b4-6811-520f-b4f1-413f02901ad8 | note | Verifying Documents - Inspection records.
9881d7ff-809e-5d97-8399-e83966f92ceb | note | Sub Contractor - H
1bc5a14c-cc92-5086-b807-bd1f9c5de943 | note | Head Contractor - H
1b15dc71-c989-59ed-8fac-4c6fa19d2fcc | note | Engineer / Client - S
b308ce9c-df3a-4237-a57d-68329332fd99 | signoff | HOLD POINT
898d2a82-a9c2-490d-9b49-91bd8413b714 | checkpoint | 4.3 - Collate and supply compaction records.
5a34c1f4-2af5-50f6-98c7-6e39e5b3d861 | note | Inspection / Test Method - Document review.
0f591a11-c32e-57b0-8b95-729ae47189ae | note | Acceptance Criteria - Collate and supply compaction records.
8e8647c7-3f40-5a57-9cc8-fc467a1f69ab | note | Frequency - Upon completion of water supply works.
8379a8af-8ae5-5e43-9d91-70419edf187a | note | Verifying Documents - Inspection records.
c2ecdb27-d3b8-50e7-9b79-68c2addaf106 | note | Sub Contractor - H
c608d2a0-93f9-522c-a321-88eae091daf6 | note | Head Contractor - H
85b800ec-1892-5bf5-8b3d-a94915e6b1ca | note | Engineer / Client - S
2357af77-1978-4fde-86f0-1ced026205cb | signoff | HOLD POINT
e48e1f36-9cb7-4767-b519-1ec9f19a8217 | checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
dcf885a3-56ad-5776-98da-e907bb08c162 | note | Inspection / Test Method - Document review / as builts
01e0cffc-cab0-5080-bb14-f3116d550528 | note | Acceptance Criteria - Collate and supply as-builts and inspection records.
4f36e4b1-d7d9-545f-881e-9899fd99d392 | note | Frequency - Upon completion of water supply works.
e9076ce0-0305-51c5-a4b3-8cd8758c4448 | note | Verifying Documents - As-builts / test records.
8c7a450a-9266-59f2-bc83-1839954a3a39 | note | Sub Contractor - H
618cc32e-bd35-5b73-bc8d-d1a302c3ef03 | note | Head Contractor - H
773e3af0-bcea-5941-8981-1da5dc275de9 | note | Engineer / Client - S
e4697d7c-b46b-4c10-80f3-c0d095fdaeeb | signoff | HOLD POINT