## Project Checklist Templates
Type | Name
checklist | Deckwork
checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint | Fire Collars are secured properly
checkpoint | Q/A been done to ensure all collars and pipework is in place and in correct postion (Plan attached)
checkpoint | Fire collars are approved for there application
signoff | Signed off by Commodore Plumbing & RCC
checklist | Fit Off
section | Details
checkpoint | Pipe Work
checkpoint | Installation
checkpoint | Test
checkpoint | Commission
checkpoint | Final inspection
signoff | Signed off by Commodore Plumbing & RCC
checklist | In Ground Pressure Services Checklist
checkpoint | The correct drawing has been used and it is issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint | Pipework bedding is correct material and depth
checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint | Pipework has been pressure tested for 24 hours - attach photo of pressure gauge
checkpoint | All open ends are capped off/taped off
signoff | Signed off by Commodore Plumbing & RCC
checklist | In Ground Sewer Checklist
checkpoint | The correct drawing has been used and it is issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint | Pipework bedding is correct material and depth
checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint | All floor wastes are charged by a fixture
checkpoint | All open ends are capped off/taped off
signoff | Signed off by Commodore Plumbing & RCC
checklist | In Ground Stormwater Checklist
checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint | Pipework is secured properly, penetrations through pits are correct (pits by others)
checkpoint | Q/A been done to ensure all pipework is in place and in correct position (Plan attached)
checkpoint | Pipework has been tested and are all open ends capped/taped off
signoff | Signed off by Commodore Plumbing & RCC
checklist | Rough In
section | Details
checkpoint | Plans
checkpoint | Rough In
checkpoint | Set Out
checkpoint | Pressure Tested
checkpoint | Cross Connection Checked
checkpoint | Meter mark provided by MLP
signoff | Signed off by Commodore Plumbing & RCC
checklist | Stacks Checklist
checkpoint | Has the correct drawing been used. Is it issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Pipework is co-ordinated with other trades and finished ceiling heights
checkpoint | Pipework has correct fall and is sized correctly
checkpoint | Stackwork has been water tested and visual inspection for leaks
checkpoint | Stack cap has been removed
checkpoint | Stackwork has been clipped as per ASNZS3500
checkpoint | Stackwork is acoustically lagged if applicable
signoff | Signed off by Commodore Plumbing & RCC
checklist | Trade Waste Checklist
checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint | Pipework is secured properly
checkpoint | Q/A been done to ensure all pipework is in place and in correct postion (Plan attached)
checkpoint | Pipework has been tested and are all open ends capped/taped off
signoff | Signed off by Commodore Plumbing & RCC
checklist | Wall and Ceiling Pressure Services Checklist
checkpoint | The correct drawings have been used and issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint | Meter marks have been issued by RCC and works have been completed off them
checkpoint | Q/A been done to ensure all pipework/fittings is in place and in correct position
checkpoint | All pipework is installed and secured as per AS/NZS 3500
checkpoint | Pipework has been pressure tested for 24 hours - attach photo of pressure gauge
checkpoint | Stud grommets are installed and pipes through studs are siliconed
checkpoint | Check for cross connections
signoff | Signed off by Commodore Plumbing & RCC
checklist | High Level Pressure Service Checklist
checkpoint | The correct drawing has been used and it is issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint | Pipework clipped correctly
checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint | Pipework pressure tested as per AS3500
checkpoint | All open ends are capped off/taped off
signoff | Signed off by Commodore Plumbing & RCC