## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | High Level Pressure Service Checklist
section | Details
checkpoint | The correct drawing has been used and it is issued for construction
checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint | Pipework clipped correctly
checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint | Pipework pressure tested as per AS3500
checkpoint | All open ends are capped off/taped off
signoff | Signed off by Commodore Plumbing & RCC