## Asphalt ITP
| Site Name | [7 empty] | Development Date:
| Carriageway width (m) | 8 |  |  | Surface pre-treatment type |  |  |  | Role | Name
| Surfacing Type | AC |  |  | Milling depth |  |  |  | Downer Contract Engineer | Saino Jacob
| Kerb and Channel | Yes |  |  | Target area |  |  |  | Supervisor | Johan Hartslief
| Target area |  |  |  | Target tonnage |  |  |  | CCA Project Engineer | Pratibha
| Layer depth minimum thickness | [7 empty] | CCA Project Manager | George issac
Mean Profile Thickness
Mix specific density
JMF Air void target
ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
|  |  |  | Office | Weather |  | Consistent dry weather with no significant rainfall. | Prior to construction commencing | Ground temperature 5˚C min for structural asphalt. 10˚C min for wearing course. |  | Hold Point | Downer Contract Engineer
2 | Milling |  | 1.01 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 NZTA M10:2020 10.1 | String line or GPS rover | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge |  | QA Sheet | Supervisor
|  |  | 1.02 | Field | Surface Inspection | NZTA M10:2020 9.2 | Visual Inspection | 100% of Surface Prior to paving | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. |  | Hold Point | Supervisor
|  |  | 1.03 | Field | Does the surface pre-treatment meet project requirments? | NZTA M27:2020 9.3 NZTA M10:2020 9.2 NZTA SP-M-032 | Design requirements Visual confirmation after milling NZTA SP-M-032: Step 4 Bond and Seal | 100% of Surface Prior to paving | Is the suggested surface pre-treatment still suitable after inspectiing the milled surface? |  | Hold Point | Supervisor
3 | Surface pre-treatment Membrane or Chipseal | Compliance | 2.01 | PQE | Seal Design | NZTA M27:2020 9.3 NZTA M10:2020 9.2 NZTA SP-M-032 | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | CCA Project Engineer
|  | Compliance | 2.02 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PE | Prior to construction commencing | Material meets project requirements |  | Hold Point | CCA Project Engineer
|  |  | 2.03 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | Supervisor
|  |  |  | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | Supervisor
|  |  |  | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | Supervisor
|  |  |  | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | Supervisor
|  |  | 2.04 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | Downer Contract Engineer
4 | DG and AC Mixes NZTA M10:2020 SMA Mixes NZTA M27:2020 PA Mixes TNZ P/11 | Compliance | 3.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation |  | Hold Point | CCA Project Engineer
|  | Production Testing and Cores | 3.02 | Lab | In-situ mat density calibration cores | NZTA M10:2020 9.9.1 NZTA M27:2020 9.9.1 | ASTM D5361 | One test per 900 t of asphalt plant production | Characteristic value - mix design air void +3% -2% Thickness as per specified nominal depth |  | Hold Point | Downer Contract Engineer
|  |  | 3.03 | Lab | Grading (Particle Size Distribution) | NZTA M10: 2020 Table 5.2 NZTA M27:2020 Table 5.2 TNZ P/11:2007 Table 7.1 | NZS 4407:2015 test 3.8 |  | Tolerance from nominated JMF grading as per NZTA M10 Table 5.3 NZTA M27 Table 5.3 TNZ P/11 Table 7.1 |  | Test record | Downer Contract Engineer
|  |  |  | Lab | Binder content |  | ASTM D2172 |  | Tolerance on JMF |  |  | Downer Contract Engineer
|  |  |  | Lab | Air Voids |  | ASTM D3203-22 |  | As specified for each mix type |  |  | Downer Contract Engineer
|  |  |  | Lab | Maximum Theoratical Specific Gravity |  | ASTM D2041 |  | Report Value |  |  | Downer Contract Engineer
|  |  | 3.07 | Field | Load Locate | Downer Procedures | Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Every Load | All data is collected |  | QA Sheet | Supervisor
|  |  | 3.08 |  | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | "Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer" | N/A |  | Hold Point | Downer Contract Engineer
|  |  | 3.09 | Field | NDM Density Testing On-Site Mat and Joint | NZTA M10:2020 9.9.1 and 9.9.2 NZTA M27:2020 9.9.1 and 9.9.2 | ASTM D2950 ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 |  | Test Record | Supervisor
|  |  | 3.1 | Field | Straight Edge | NZTA M10:2020 10.2 NZTA M27: 2020 10.2 Downer Procedures | NZTA M/10 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | No more than 5mm deviation from a 3m straight edge |  | Survey record | Downer Contract Engineer
|  |  | 3.11 | Field | Post Surfacing Inspection and Safety Audit | CCA Procedures | Contract Specifications | 100% of site After surfacing (within 5 days) | Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers |  | Survey record | CCA Engineer / Downer Contract Engineer
5 | Post Construction | Compliance | 4.01 | PQE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | Downer Contract Engineer

## SMA (hidden)
INSPECTION AND TEST PLAN TEMPLATE - Surfacing - (SMA & DG Mixes)
Item No | Material Type | Typical Use | Item ID | Lab, Supplier or Field | Material Properties Required for Acceptability for Permanent Works | [7 empty] | Completed/Checked
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptiance Criteria (Method) | Material Test Frequency* | Target Criteria | link | Action Point | Responisbility
| Milling |  | 2.08 | Field | Surface Level- Stringline checks for validation | NZTA M10 Cl. 10.1 | NZTA M/10 | Each 10m cross-section with a minimum of two readings per traffic lane. | Tolerance on each layer (except for top layer adjacent to kerb). ±10mm Tolerance for top layer adjacent to kerb AC level ≥ Kerb lip level +0mm AC level ≤ Kerb lip level +5mm |  | Survey record
|  |  | 2.09 | Field | Post Construction Inspection - Surface Defects - Surface Shape - Straight Edge | Appendix A7 Minimum Requirements - Pavement | Visual Inspection | Entire surface of all pavements |  |  | Hold Point
|  | Treatment Design | 1.02 | Supplier | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation |  | Hold Point | site/projecect engineer
|  | Compliance | 1.03 |  | Has the underlying layer been tested and results acceptable? |  |  | Prior to paving works commencing | All underlying layers been tested. Results accepted and meet requirements |  | Hold Point | site/projecect engineer
|  |  | 1.04 |  | Tack Coat Requirement | NZTA M27 and M10 Clause 9.3.1 |  | Tack-coat Required for main alignment | Between .0.2and0.6L/m². Tack coat application rates shall be within ±0.1 L/m² of the specified rate |  | Hold Point | site/projecect engineer
|  |  | 1.05 |  | Paving plan | NZTA M27 and M10 Clause 9.5.1 |  | Prior to paving works commencing | Line markings to be set-out and followed by paver , Rolling patterns to be discussed and followed |  | For Information | site/projecect engineer
|  |  | 1.06 |  | Membrane Seal | contract specification or design report |  | before paving | Membrane applied as basecourse hit .Application rate,chip type and binder as per memberane seal design |  | Hold Point | site/projecect engineer
|  |  | 1.07 |  | Joint Preseal Inspection |  |  | Prior to paving works commencing | Surface is ready to seal |  | Hold Point | site/projecect engineer
| Dense Graded Mix | Production Testing | 2.01 | Supplier | Grading (Particle Size Distribution) | NZTA M10 | NZS 4407:2015 test 3.8 | 1 test sample per 300 tonnes(where process is demonstrated to be under statistical control) otherwise 1 test sample per 200 tonnes (individual results and rolling averages should be reported for each lot) | Tolerance from nominated JMF grading as per NZTA M10 Table 5.4 |  | Test record | site/projecect engineer
|  |  | 2.02 | Supplier | Binder content | NZTA M10 | ASTM D2172 |  | Tolerance on JMF Individual ±0.5 , Rolling Average of 3 ±0.3%
|  |  | 2.03 | Supplier | Mixing Discharge Temperature | NZTA M10 | Spec C0214.3.2 |  | As specified for each mix type
|  |  | 2.04 | Supplier | Maximum Theoratical Specific Gravity | NZTA M10 | ASTM D2041 |  | Report Value
|  |  | 2.05 | External Lab | In-situ mat density (Cores, air voids) | NZTA M10 Cl. 9.8.1 | ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) | Lot characteristic value - mix design air void +3% -2% |  | Hold Point
|  |  | 2.06 | External Lab | In-situ joint density (Cores, air voids) | NZTA M10 Cl. 9.8.2 | ASTM D5361 | 1 test per 100m per layer length (min 3 / Construction lot) | Lot characteristic value - mix design air void +5% -2% |  | Hold Point
|  |  | 2.07 | Field | NDM Density Testing On-Site | NZS 4407 Test 4.2/4.3 |  | Process Control Check only | Report Only |  | Test record
|  |  | 2.08 | Field | Surface Level- Stringline checks for validation | NZTA M10 Cl. 10.1 | NZTA M/10 | Each 10m cross-section with a minimum of two readings per traffic lane. | Tolerance on each layer (except for top layer adjacent to kerb). ±10mm Tolerance for top layer adjacent to kerb AC level ≥ Kerb lip level +0mm AC level ≤ Kerb lip level +5mm |  | Survey record
|  |  | 2.09 | Field | Post Construction Inspection - Surface Defects - Surface Shape - Straight Edge | Appendix A7 Minimum Requirements - Pavement | Visual Inspection | Entire surface of all pavements | No visible cracking is observed No obvious defects related to poorly constructed longitudinal or transverse joints No flushing No area of completed surface shall have any depression that allow water to pond Shall not deviate more than 5mm from a 3m straight edge |  | Hold Point
| SMA | Production Testing | 3.01 | Supplier | Grading (Particle Size Distribution) | NZTA M27 Cl. 5.2, Table 5.2 | NZS 4407:2015 test 3.8 | 1 test sample per 300 tonnes(where process is demonstrated to be under statistical control) otherwise 1 test sample per 200 tonnes (individual results and rolling averages should be reported for each lot) | Tolerance from nominated JMF grading as per NZTA M10 Table 5.4 M27 Table 5.3 |  | Test record | site/projecect engineer
|  |  | 3.02 | Supplier | Binder content | NZTA M27 Cl. 5.2, Table 5.2 | ASTM D2172 |  | Tolerance on JMF Individual ±0.5 , Rolling Average of 3 ± 0.4% 0.3%
|  |  | 3.03 | Supplier | Mixing Discharge Temperature | NZTA M27 Cl. 5.2, Table 5.2 |  |  | As specified for each mix type
|  |  | 3.04 | Supplier | Maximum Theoratical Specific Gravity | NZTA M27 Cl. 5.2, Table 5.2 | ASTM D2041 |  | Report Value
|  |  | 3.05 | Supplier | Air Voids | NZTA M27 Clause 5.2 , Table 5.2 |  | 1 test sample per 900 tonnes(where process is demonstrated to be under statistical control) otherwise 1 test sample per 600 tonnes (individual results and rolling averages should be reported for each lot) | Tolerance on JMF air voids value: Individual +2.0,-1.0 % , Rolling average +1.2 , -.6% |  | Test Record | site/projecect engineer
|  | On-site Field Testing | 3.06 | External Lab | Thickness | NZTA M27 Cl. 9.7, Cl 10.4 | coring to a recognised random sampling plan. | set of cores per lot | lower characteristic value (LCV) for the set of core specimens for the lot shall not be less than the specified minimum thickness. |  | Witness Point
|  |  | 3.07 | External Lab | In-situ mat density (Cores, air voids) | NZTA M27 Cl. 9.9.1 | ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) | Lot characteristic value - mix design air void +3% -2% |  | Hold Point
|  |  | 3.08 | External Lab | In-situ joint density (Cores, air voids) | NZTA M27 Cl. 9.9.2 | ASTM D5361 | 1 test per 100m per layer length (min 3 / Construction lot) | Lot characteristic value - mix design air void +5% -2% |  | Hold Point
|  |  | 3.09 | Field | NDM Density Testing On-Site | NZS 4407 Test 4.2/4.3 | Process Control Check only | per paving shift | Report Only |  | Test record | site/projecect engineer
|  |  | 3.1 | Field | Surface Level- Topographic survey plus random stringline checks for validation | NZTA M27 Cl. 10.2 | NZTA M27 Cl. 10.2 | Each 10m cross-section with a minimum of two readings per traffic lane. | Tolerance for top layer adjacent to kerb AC level ≥ Kerb lip level +0mm AC level ≤ Kerb lip level +5mm |  | Survey record
|  |  | 3.11 | Field | Post Construction Inspection - Surface Defects - Surface Shape - Straight Edge | Appendix A7 Minimum Requirements - Pavement | Visual Inspection | Entire surface of all pavements | No visible cracking is observed No obvious defects related to poorly constructed longitudinal or transverse joints No flushing No area of completed surface shall have any depression that allow water to pond Shall not deviate more than 5mm from a 3m straight edge |  | Hold Point
|  | Post Construction Testing | 3.12 | External Lab | Roughness - NAASRA | Appendix A7 Minimum Requirements - Pavement | A7.3b Performance Requirements | measurement at 20m intervals | For each 100 metre section lane of all carriageways with finished surfacing of OGPA or SMA shall not exceed a NAASRA count of 50 counts/km as a 95th percentile value. |  | Test record
|  |  | 3.13 | External Lab | High speed rutting measurement |  | Independent Testing Specialist using a high speed laser profilometer | All lanes at 20m interval in each wheel path and staggered by 10m between wheel paths , Entire surface of all pavements at the following milestones: - After 12 months of trafficking - At the end of defects liabilty | Any rutting exceeding '5mm' threshold shall be reported to the designer |  | Test record | site/projecect engineer
|  |  | 3.14 | External Lab | Falling Weight Deflectometer |  | ASTM D4694, 2006b | 20m intervals in each traffic lane including shoulder staggered in each wheel path immediately after completion of final surfacing | Report only |  | Test record (Electronic form)
|  |  | 3.15 | External Lab | Surface Texture | NZTA M27 Cl.9.8 | Technical Agency Technical Memorandum TM 5003 V1 - laser based direct measurement of MPD | Test locations in accordance to Transport Agency Standard Spec T/4 in outer and inner wheel paths between wheel paths and centreline At the following intervals : - Upon completion of asphalt surfacing - End of the period of defects liability | Mean Profile Depth (MPD) to be greater than 0.9mm where the design speed is more than 70 km/hr |  | Test record

## Sheet1 (hidden)
Source Material Property Testing | 1.01 | Supplier | Bituminous Binder Testing |  | NZTA M1 for penetration grade binder testing and NZTA M1-A for polymer modified binder testing | Once initially Repeat binder penetration test as per CCNZ RNZ 9803 |  | Test record
Source Material Property Testing - Coarse Aggregates for Dense Graded Asphalt | 2.01 | Supplier | Dry Sieve | Spec C0214.3.2 NZTA M10 Specification Clause 2.1.2 , | NZS 4407 Test 3.8 | Daily or 1 test per 1,000 m³ | Tolerance from nominated JMF grading | Test record
| 2.02 |  | Cleanness Value |  | NZS 4407 Test 3.9 | Once initially and repeat as per CCNZ/RNZ 9805 , every 1000 m³ or yearly whichever is less | Grade 2= Min. 89 , Grade 3 = Min. 87 , Grade 4 = Min. 85 | Test record
| 2.03 |  | Crushing Resistance |  | NZS 4407 Test 3.10 | Once initially and repeat as per CCNZ/RNZ 9805 , every 10,000 m³ or yearly whichever is less | 200kN min | Test record
| 2.04 |  | Weathering Quality Index |  | NZS 4407 Test 3.11 |  | AA or BA | Test record
| 2.05 |  | Single Broken Face |  | NZS 4407 Test 3.14 |  | 98% Min | Test record | One test per Quarry as per WEXHS-RFI-000811
| 2.06 |  | Two Broken Faces |  | NZS 4407 Test 3.14 |  | 60% Min | Test record | One test per Quarry as per WEXHS-RFI-000811
|  |  | Petrographic Examination in RNZ 9805 |  | RNZ 9805 | Once per Source | Report Value | Test Record
| 2.07 |  | Los Angeles Abrasion Loss |  | AS 2758 Part 5 or NZS 4407 Test 3.12 | Once per annum | Report Value | Test record
| 2.08 |  | Wet / Dry Strength Variation |  | AS 1141.22: 2008 |  | Report Value | Test record
| 2.09 |  | Water Absorption |  | AS1141 or ASTM C127 |  | Report Value | Test record
| 2.1 |  | Polished Stone Value (for wearing course only) |  | BS EN 1097 Part 8 | One test per aggregate source and repeat once per annum | As per Specific Contract Requirements | Test record
| 2.11 |  | Aggregate density (Oven dry, Saturated surface dry and apparent density) |  | NZS4407 Test 3.7.1 | One test per 1000m3 of each type of mineral aggregate used or one test month, whichever is lesser | Report Value | Test record
Source Material Property Testing - Coarse Aggregates for SMA | 3.01 | Supplier | Dry Sieve | Spec C0214.3.2 NZTA M27 Specification Clause 2.1.2 , | NZS 4407 Test 3.8 | Daily or 1 test per 1,000 m³ | Tolerance from nominated JMF grading | Test record
| 3.02 |  | Cleanness Value |  | NZS 4407 Test 3.9 | Once initially and repeat as per CCNZ/RNZ 9805 ,every 10,000 m³ or yearly whichever is less | N/A | Test record
| 3.03 |  | Crushing Resistance |  | NZS 4407 Test 3.10 |  | 230kN min | Test record
| 3.04 |  | Weathering Quality Index |  | NZS 4407 Test 3.11 |  | AA or BA | Test record
| 3.05 |  | Weak Particles |  | AS1141.32 |  | 1.0 % Max. | Test record
|  |  | Single Broken Face |  | NZS 4407 Test 3.14 |  | 98% Min | Test record | One test per Quarry as per WEXHS-RFI-000811
| 3.06 |  | Particle Shape |  | NZS 4407 Test 3.13 |  | 2.25 Max | Test record
|  |  | Petrographic Examination in RNZ 9805 |  | RNZ 9805 |  | Report | Test Record
| 3.07 |  | Two Broken Faces |  | NZS 4407 Test 3.14 |  | 98% Min | Test record | One test per Quarry as per WEXHS-RFI-000811
| 3.08 |  | Los Angeles Abrasion Loss |  | AS 2758 Part 5 or NZS 4407 Test 3.12 | Once per annum | Report Value | Test record
| 3.09 |  | Wet / Dry Strength Variation |  | AS 1141.22: 2008 |  | Report Value | Test record
| 3.1 |  | Water Absorption |  | AS1141 or ASTM C127 |  | Report Value | Test record
| 3.11 |  | Polished Stone Value (for wearing course only) |  | BS EN 1097 Part 8 | One test per aggregate source and repeat once per annum | As per Specific Contract Requirements | Test record
| 3.12 |  | Aggregate density (Oven dry, Saturated surface dry and apparent density) |  | NZS4407 Test 3.7.1 | One test per 1000m3 of each type of mineral aggregate used or one test month, whichever is lesser | Report Value | Test record
Source Material Property - Fine Aggregate DG and SMA | 4.01 | Supplier | Crushing Resistance (if not the same source as coarse aggregate) | Spec C0214.3.2 NZTA M10 Specification Clause 2.1.3 | NZS 4407 Test 3.10 | Once initially and repeat CCNZ/RNZ 9805 , then every 10,000 m³ or yearly , whichever is less | 200kN Min | Test record
| 4.02 |  | Sand Equivalent or Clay Index |  | NZS 4407 Tets 3.5 or NZS 4407 Test 3.6 |  | SE : 35 Min or CI : 3 Max | Test record
| 4.03 |  | Water Absorption |  | AS 1141 or ASTM C128 | Once per annum | Report Value | Test record
| 4.04 |  | Degradation Factor |  | AS 1141.25.3 |  | Report Value | Test record
| 4.05 |  | Aggregate density (Oven dry, Saturated surface dry and apparent density) |  | ASTM C127 & C128 | One test per 1000m3 of each type of mineral aggregate used or one test month, whichever is lesser | Report Value | Test record
Source Material Property - Recycled Asphalt Pavement (RAP) | 5.01 | Supplier | Wet Seive (RAP Grading) | Spec C0214.3.2 | NZS 4407 Test 3.8 | One test per 200t of RAP used |  | Test record
| 5.02 |  | Binder content (RAP) |  | ASTM D2172 |  | Report Value | Test record
Source Material Property - Mineral Filler | 6.01 | Supplier | Wet Sieve | Spec C0214.3.2 | NZS 4407 Test 3.8 | Once initially then at least once per annum |  | Test record
| 6.02 |  | Clay Index |  | NZS 4407 Test 3.5 |  | Report Value | Test record