## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
46d26f3a-d988-427d-9c92-9e1916dd95ea | checklist | ITP - ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN Rev 1 | itp | ITP - ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN
45a6e25c-2181-425a-8558-d6c6d8426aec | section | Milling
c7cd0ea0-3367-4b99-b37d-77926a52e654 | checkpoint | 1.01 - Field
5eb17e16-6356-5f43-a14b-79dafd28ecce | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
c13a3f16-f236-58a5-9e71-384ca82b6f43 | note | Reference Documents - RITS Table 3.24, NZTA M10:2020 10.1
8505615c-e2b6-5615-a277-ab2a2d93647a | note | Material Acceptance Criteria (Method) - String line or GPS rover
565479aa-f30d-55fc-8215-bc93083f6cd4 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency, Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
1ff1e347-0ad1-52fb-848b-56966e927462 | note | Target Criteria - +10mm/-0mm from design or nominated level, No more than 8mm deviation from a 3m straight edge
0817965a-86a6-510c-a2aa-ade0a05c30b6 | note | Action Point Records Required - Survey record
48d7e28f-e00f-54e1-a643-3466125c790e | note | Responsibility - QA / SE / PE
2b1fb752-ec48-4e55-abff-db9113c5fdbd | checkpoint | 1.02 - Field
825f2aa7-8b1d-594c-8cfc-9105e6682714 | note | Material Test Method Requirement - Surface Inspection
2d3b74d9-e5d2-51f4-9f67-9846278eacee | note | Reference Documents - NZTA M10:2020 9.2
b85949d8-b3f0-581c-829c-6b2612e1800b | note | Material Acceptance Criteria (Method) - Visual Inspection
a80fda84-103a-522e-90ab-034c797e1ae5 | note | Material Test Frequency - 100% of Surface Prior to paving
290466be-8ed3-5a53-9bd8-0cec0f1a6d46 | note | Target Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping.
be6a2bae-d61e-5245-af2e-68e5c2160e5c | note | Action Point Records Required - Hold Point
033b0fd7-9876-59d0-96a0-aae5c6ff57d6 | note | Responsibility - QA / SE / PE
ad0d20e0-af61-4df6-8331-16d763702b5b | signoff | AUTHORITY HOLDPOINT
8f84aa6b-25c2-4df6-a55c-55fbbd551932 | checkpoint | 1.03 - Field
f4a515d3-e0fe-57d4-a902-6273f72ec948 | note | Material Test Method Requirement - Does the surface pre-treatment meet project requirments?
7ad8e5a7-63ec-52d8-9de2-587e7a52acd0 | note | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
aafc4526-210c-5ad6-a4e2-8b080feea4b3 | note | Material Acceptance Criteria (Method) - Design requirements
55871c60-190f-5b93-afaf-6f78e9955dd7 | note | ○ Visual confirmation after milling
4883d1f5-ee39-565a-a1c9-73238813f513 | note | ○ NZTA SP-M-032: Step 4 Bond and Seal
954f4976-9018-5842-b879-d7e30c05660e | note | Material Test Frequency - 100% of Surface Prior to paving
ba05650e-be1d-57ae-83f3-51f52e9e99d1 | note | Target Criteria - Is the suggested surface pre-treatment still suitable after inspectiing the milled surface?
ce557bf1-ec02-5566-95d6-f748068db3ed | note | Action Point Records Required - Hold Point
9fc7821b-20bc-5288-accb-eb7b01f6a694 | note | Responsibility - SE / PE / PM / PQE / ER
4e23f22b-df71-4607-bd08-fa8b86d40b2a | signoff | AUTHORITY HOLDPOINT
725231dc-1e68-482c-aef3-8140af598ae9 | section | Surface pre-treatment, Membrane or Chipseal
8d548c71-cb3a-42c8-80a8-3962960b648d | checkpoint | 2.01 - PQE.
998fdbf9-fce2-5d08-b114-5ccac6c51042 | note | Material Test Method Requirement - Seal Design
8312b036-1596-5ac2-9964-2d5d2072dfae | note | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
cc1d4dfd-b6ff-5dcf-a8b4-7a32f8cbf5d0 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
44021ff5-774b-5733-8c1b-018423f3ccb2 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
054acfa0-8424-5514-8ab0-259dba396d79 | note | Target Criteria - Meets project requirements
af7d89fb-d591-5cc9-9b59-9585262cd72d | note | Action Point Records Required - Hold Point
d69b33c9-8e51-5c25-b7af-18a5760fa58b | note | Responsibility - SE / PE / PM / PQE / ER
08fe023c-441f-4b40-bbe8-bce371838151 | signoff | AUTHORITY HOLDPOINT
43360eb9-d5da-4e8c-bd6d-e8d52cac8c88 | checkpoint | 2.02 - PQE
d325cb04-ca58-54dc-be48-0fdca4672891 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
0db1327d-7452-56e9-bb00-f17628d75a32 | note | Reference Documents - Insert Material Testing
a0a03dc2-e10a-5a8e-8086-e5f1f7fff21e | note | Material Acceptance Criteria (Method) - See PQE
c087094f-3910-52e7-85a3-5024614e7570 | note | Material Test Frequency - Prior to construction commencing
07256a70-4ef2-5b22-9613-f18fec6c86dc | note | Target Criteria - Material meets project requirements
e8a551f7-c010-590d-a8f0-9565d715ca4a | note | Action Point Records Required - Hold Point
ae0c1b28-39ef-56f3-9147-dc5fa7392f2d | note | Responsibility - SE / PE / PM / PQE
e24da715-7fc0-40d4-936a-5fb78505fc28 | signoff | AUTHORITY HOLDPOINT
c988bdb0-45fe-4cae-945f-80c3665f0b87 | checkpoint | 2.03 - Field
757820b9-3d88-5b32-a20d-c8fd336cb8b2 | note | Material Test Method Requirement - Preseal Inspection
41c308e9-9484-5247-97d7-af7ca39b4ec9 | note | Reference Documents - TNZ B/02: 2005
9865a0d0-3511-5961-95b8-78f581a4bc1b | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
3ca3f856-e536-51c4-899b-ef17b085e792 | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
48768ea7-324c-5a1b-a01c-d032e5752ccd | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
47b355be-345f-5626-a57c-6e366a2e627b | note | Action Point Records Required - Test Record
8bf132b7-97ce-57c8-abb0-a59844d153f2 | note | Responsibility - FM /QA / SE / PE
3da0cf21-6590-4744-b41e-cdd2cd62fb96 | checkpoint | 2.04 - Field
a0cc64cd-e86d-5bb8-bf93-fc84a06ff3b0 | note | Material Test Method Requirement - Road temp
69cc7b3b-1ecd-5a9d-82c5-b2576e7b304c | note | Reference Documents - TNZ P3:1995.18
2ee4b2b0-b7a7-525f-8348-b10f4dd469a6 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
d360f6d5-75ca-5eee-bc16-9b3799b18353 | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
fa50cbb0-73f2-5190-8c54-2132adf67db4 | note | Target Criteria - Air temp >10°C
350c0314-6d10-5a85-9c21-3e7e32332451 | note | Action Point Records Required - Spray sheet
30fbd2ab-e5fa-5c8e-b024-54f3c788488b | note | Responsibility - QA / SE / PE
87db939d-9b07-4e5a-b0f1-9a09991f34f1 | checkpoint | 2.05 - Field
eccbd2d3-0e23-52e3-a196-d03c461d7907 | note | Material Test Method Requirement - Application Rate
bdb09615-275b-50c3-b7e9-d631cd305f05 | note | Reference Documents - TNZ P/3 : 1995.18
1b7a5e9e-6bcf-5200-9fab-623076154b24 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
13b0fa3a-c5d2-5050-a5e2-1124731c8862 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
82aacfe7-40dc-58a6-9e6a-02e5ea497c1a | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
df13b87e-4824-5525-a50c-7cba2670c97f | note | Action Point Records Required - Spray Sheet
09fbfd8f-62b1-52be-b743-c6d24b6a3e4b | note | Responsibility - QA / SE / PE
fdbfd898-fcd0-4027-a583-cf02e575ba24 | checkpoint | 2.06 - Field
9eead763-bb81-5f95-b6ad-a480dfb6a110 | note | Material Test Method Requirement - Chip spread rate
27902cfa-4d06-5a21-9f65-b2172ff9d6f3 | note | Reference Documents - TNZ P3: 1995.21
3dc2237c-1baf-5d01-882e-c94d117aef25 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
1e028cf2-2009-5568-8d81-29e213ff364d | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
b0306c23-aa20-5e80-a84f-ef9022a6437e | note | Target Criteria - Visual checks meets seal design requirements
eed007a3-1d5e-5202-830b-1d40917abe5c | note | Action Point Records Required - Witness Point/Spray sheet
4712ffa8-d8c3-5236-8c5c-523531b60dee | note | Responsibility - QA / SE / PE
e8bc7fb7-6bed-4ffa-9d00-adf7b548136e | checkpoint | 2.07 - Field
03a05a92-e34f-5732-ae9b-254ad18a2534 | note | Material Test Method Requirement - Post Seal Inspection
6186982e-05ce-5dcc-956c-b41e3fc1a68c | note | Reference Documents - TNZ P3: 1995
18a4d7a0-549e-56a6-a566-a5f4280334be | note | Material Acceptance Criteria (Method) - Engineers Inspection
ee65d32c-3083-5c4a-9c4f-7789d1bbc79d | note | Material Test Frequency - After sealing
0b60c547-0fb3-5652-8d7c-e6c0487a6755 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
a24de70f-78d5-5c6f-9a5e-5df9ae8b1c37 | note | Action Point Records Required - Witness Point
79ed917e-6995-5a3f-9ab9-ac0a4f23058f | note | Responsibility - QA / SE / PE
4915f92b-548d-4c85-a0d4-534821d36965 | section | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
aebfe5a6-7870-4692-a822-f5b587a53b6f | checkpoint | 3.01 - PQE
c5bf000c-72cc-549e-a295-c0bb6fed2742 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
94373dd6-8b53-53c4-b8bf-e894d9ac4040 | note | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
09259de6-da47-5a54-aaae-2f1d807fc8a4 | note | Material Acceptance Criteria (Method) - Approved Treatment Design
bf79692b-2d1e-50a1-bfbc-4785fb8e0c21 | note | Material Test Frequency - Prior to paving works commencing
f6a42ef4-82da-54ee-b53d-114115a2c91b | note | Target Criteria - Treatment Design validation
8443c5ec-274f-5306-9bde-e850b693f7ee | note | Action Point Records Required - Hold Point
10e40936-ff7f-5436-92d2-c9344680ac7e | note | Responsibility - SE / PE / PM / PQE
594b861d-b1fe-4b87-a855-5b6bef630b70 | signoff | AUTHORITY HOLDPOINT
33e0d238-1d6a-4c02-86f3-cf6c96f72feb | checkpoint | 3.02 - Lab
a4f5c5c7-fe92-5d5c-8bfc-24bd130b8e91 | note | Material Test Method Requirement - In-situ mat density calibration cores
20cdc890-ad47-589e-8993-762c0975bc12 | note | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
cf13b34a-d441-5a00-b41a-80681f1ac24b | note | Material Acceptance Criteria (Method) - ASTM D5361
d199c698-0a10-573a-98ea-cbec21dcd63c | note | Material Test Frequency - One test per 900 t of asphalt plant production
603a3046-0179-5fbd-9dcb-905a515c2a6a | note | Target Criteria - Characteristic value - mix design air void +3% -2%
fdaa83ec-3a30-55c3-a2e8-dab1258143e9 | note | Action Point Records Required - Hold Point
3c60383a-0832-5e02-8be1-25f86040042e | note | Responsibility - SE / PE / PM / PQE
6d591efc-b2ba-485e-b394-00c434cb93ad | signoff | AUTHORITY HOLDPOINT
bf1c7566-648e-4a0d-a5e6-fcd079d73052 | checkpoint | 3.03 - Lab
d7b1d990-2a9a-5e0d-bff6-617ac4db1d3e | note | Material Test Method Requirement - Grading (Particle Size Distribution)
1b41b44c-5fd2-5398-86b6-4a631f1451ca | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
3fa5c590-7bab-57eb-9479-71c250af685c | note | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
1a942bcd-39b9-510a-9a00-649889cbef4a | note | Material Test Frequency - One test per 900 t of asphalt plant production
852cb67a-ced8-5e34-97db-1d7c61df1e17 | note | Target Criteria - Tolerance from nominated JMF grading as per NZTA M10 Table 5.3, NZTA M27 Table 5.3, TNZ P/11 Table 7.1
391bec09-6a0c-5495-81e1-0539c4a745ad | note | Action Point Records Required - Test record
67e0547a-f474-557d-9f9e-8dd38da2012f | note | Responsibility - SE / PE / PM / PQE
c544b488-66b5-4445-a801-15b6eabb4eab | checkpoint | 3.04 - Lab
235b163c-96a4-50e0-8097-024f1221451f | note | Material Test Method Requirement - Binder content
c07a6e3a-15d0-5656-8424-6ce0fe5a29d6 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
b67f44d2-609d-5392-9cc8-605663ee99c2 | note | Material Acceptance Criteria (Method) - ASTM D2172
bf4506f1-1d72-5d35-9e03-e7c99bb32465 | note | Material Test Frequency - One test per 900 t of asphalt plant production
0f25dc4d-d643-5fa2-8ab4-0ae020a5766e | note | Target Criteria - Tolerance on JMF
5d3e29c0-c7e9-5917-8f5b-9c5297e7a2bf | note | ○ Individual ±0.5 (All)
813a7025-5add-54f4-809c-6f1c609ea07c | note | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
828bdd78-db57-56aa-8c1b-85bb340e4f3e | note | ○ Rolling Average of 3 ±0.4% (PA)
4fecd764-9f81-5b18-a291-14e11284b12b | note | Action Point Records Required - Test record
521db5ed-a18e-5876-8431-7b0ffe1deed0 | note | Responsibility - SE / PE / PM / PQE
dcd6b6fa-a413-487e-af21-ab9b5f340170 | checkpoint | 3.05 - Lab
7540e9d7-0b41-52d0-b6f3-f36d6f0111ec | note | Material Test Method Requirement - Air Voids
199f555a-f534-5f87-ae5f-849288b4e26e | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
2431c7c0-817d-5d91-b2e3-233c29c28c40 | note | Material Acceptance Criteria (Method) - ASTM D3203-22
8f22e512-dda0-5207-bfe0-e3300c8d8861 | note | Material Test Frequency - One test per 900 t of asphalt plant production
c232bc42-ba42-5ae8-bc72-9d619cbb015c | note | Target Criteria - As specified for each mix type
3e5e9f2f-ea48-5311-a93d-3426cfd20bed | note | Action Point Records Required - Test record
e66e2f87-b3ea-5222-9718-260aeee7840a | note | Responsibility - SE / PE / PM / PQE
2468c041-bcec-45ed-b993-0b315fecd9f3 | checkpoint | 3.06 - Lab
8978a9ce-eb37-520b-8fb6-bd91f6a2d213 | note | Material Test Method Requirement - Maximum Theoratical Specific Gravity
247620ba-62af-59b6-9993-c655adfc10d5 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
42168385-52ce-5395-a66b-17b18cb69922 | note | Material Acceptance Criteria (Method) - ASTM D2041
29042750-93e5-57a8-94a0-e6201e3a1846 | note | Material Test Frequency - One test per 900 t of asphalt plant production
c1c24439-b8c0-5ed8-abd0-9f99140a8162 | note | Target Criteria - Report Value
e134cf91-4fb3-59d9-bc8d-2721c851ad1d | note | Action Point Records Required - Test record
9904b3cd-a831-5eef-9a28-4e41afdf56f9 | note | Responsibility - SE / PE / PM / PQE
2dcb4a03-97af-4a58-a16f-f365bf78b95f | checkpoint | 3.07 - Field
3d632441-e774-565f-8e99-b91521f602e0 | note | Material Test Method Requirement - Load Locate
efce3b20-2754-5918-8e77-a7134a33f5c3 | note | Reference Documents - Downer Procedures
d270ffa0-072d-59ba-a123-de067c8802d8 | note | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
19a97b9d-6795-5a7b-b833-58d14319c3ed | note | – Truck ID/Rego/Driver
7c104b5c-e3a2-53f1-bfeb-a74522777659 | note | – Depart Plant Time
972fed59-6f11-5f4b-9864-470bbc2d1d70 | note | – Arrive Site Time
280f3d6d-3fb0-5163-9d86-1ac7053bdb7c | note | – AC Temp on Arrival
c8d3d334-77e3-5339-b03a-165a5964a3c0 | note | – Ground Temp on Arrival
55b57fbf-cf18-594f-a79b-dfc70871a98a | note | – Tonnage
b7cc4af8-88a8-551f-a268-01d315b9fe6b | note | – Run Width
50843712-e0fa-5f5d-9c57-67fdfbad54b4 | note | – Estimated Run Length
9132ee5c-05ee-553c-98f7-c3286d54767e | note | – Calculated Area
caa88c2c-9738-585a-9540-f3cd1e992b33 | note | – Calculated Average Depth
145b4590-2f1d-56dd-be02-7726d6a3d378 | note | Material Test Frequency - Every Load
7dc53dfe-4e50-580e-a1e2-07b242e3e855 | note | Target Criteria - All data is collected
0bc1de29-0574-5520-bd88-8eac1be6a39f | note | Action Point Records Required - QA Sheet
6aaa0c5b-c8ab-5049-b8d8-9c5412d807e9 | note | Responsibility - QA / SE / PE
f0a4f357-db41-4a91-a90a-15199cd2c548 | checkpoint | 3.08 - Field
73b67a13-6897-5e4f-9354-4b8919dfaf33 | note | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
5350e8f8-c232-598d-bcab-4ba9aa37e093 | note | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
a5102807-94ae-5f26-834b-4242b85c9c09 | note | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
b7643fe2-7171-5038-88ee-d7e2fd290518 | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot), 1 test per 100m per layer length (min 3 / Construction lot)
0db149ce-bab7-53e0-81a7-45be97560448 | note | ○ Target Criteria - Mat: Mean air voids JMF +3,-2
ea70ede9-a3cc-5409-be2e-7d2b8369dddb | note | Join: Mean air voids JMF +5,-2
a638b9b8-9ea7-5bd2-8d28-482b0f890ac8 | note | Action Point Records Required - Test record
3fa17434-d9b0-5b22-b4b9-99dcf4895778 | note | Responsibility - QA / SE / PE
76589503-969d-4b3e-bc9b-40ddb74b0f86 | checkpoint | 3.09 - Field
e45f342c-fce6-5272-bf0c-3fefd882c89b | note | Material Test Method Requirement - Surface Level- Stringline checks for validation
5775823b-cadd-5d86-b99d-25ab9b9a6baa | note | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2, Downer Procedures
4c23532f-f5f8-5a15-852c-e14abe288133 | note | Material Acceptance Criteria (Method) - NZTA M/10
1aa115e3-5b4c-50d9-b372-78fdbf788b46 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
9891bcb7-aa87-59c8-88b0-8e64391b611b | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
ea35fe0d-2c4e-58a4-8847-20273823f4bb | note | Target Criteria - +10mm/-0mm from design or nominated level
b10d5889-22e8-5ace-a0d1-8761d905d6a1 | note | ○ No more than 8mm deviation from a 3m straight edge
d12fc970-46a6-5344-a20f-486c60895f5c | note | Action Point Records Required - Survey record
b21cc13c-c95d-5a23-b0bd-838d5d61b4e4 | note | Responsibility - QA / SE / PE
35bdd6e7-613e-4d04-82a1-b7f02308e3e1 | checkpoint | 3.10 - Field
3a2d1bc5-45af-5509-be5f-431be3347a0a | note | Material Test Method Requirement - Post Surfacing Inspection
61f6680f-f2dd-5631-b6c7-27a69d217a93 | note | Reference Documents - CCA Procedures
2e85d106-682b-58ca-83b2-a5b9158694d1 | note | Material Acceptance Criteria (Method) - Contract Specifications
c191eff2-39de-5f63-962a-cd072584a249 | note | Material Test Frequency - 100% of site After surfacing (within 5 days)
418a9a28-6a95-5d81-a077-6cf605a205df | note | Target Criteria - Line marking has been reinstated
8c70c758-60a4-52a4-a05a-105a82f9a578 | note | ○ All excess material has been removed from site
020b12a0-b4b9-50f0-8ace-38bab4243533 | note | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
12630793-c98e-5130-92c2-389c76e765b0 | note | Action Point Records Required - Hold Point
04227ab6-f853-50bf-a5e5-b1286562ac02 | note | Responsibility - QA / SE / PE
a3c4df5d-67dc-4162-a005-9536e59cc2af | signoff | AUTHORITY HOLDPOINT
1a48cb7d-7980-4939-a5cb-5e0eb5e1164c | section | Post Construction
279c28ec-2830-42b2-afd4-122d34b200d9 | checkpoint | 4.01 - PQE
dbee78e7-37d2-5401-9079-2c3a174d1e65 | note | Material Test Method Requirement - Asbuilt and RAMM Data
68f015fd-de63-5a10-82e7-dda66196b970 | note | Reference Documents - RAMM Update sheet
c62c202a-8855-5c38-aca0-a9776f4d7f00 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
8e870826-f534-5a50-8eba-3af45fe71da4 | note | Material Test Frequency - After works complete
a70ebe0a-86dd-5e24-8e1b-c5913a72aeb4 | note | Target Criteria - RAMM sheet 100% complete and accurate .
4f5dfa48-6376-5cdf-95ed-52895c5190a8 | note | Action Point Records Required - RAMM Asset Update sheet
57cc7457-7534-5450-822c-c17067a69e75 | note | Responsibility - SE / PE / PM / PQE
a6a4bd03-9b92-4889-9ac6-f7bfea9fbad7 | checklist | ITP - Chipseal Surfacing | itp | ITP - Chipseal Surfacing
ae33bc86-15c9-4622-9910-1766cf900ffc | section | Design
77885afd-b89d-4f1e-ae12-92d3c42d24fd | checkpoint | Treatment Selection
b8bac416-3ddd-5c3d-b85d-151c0429ab82 | note | VERIFICATION ACTIVITY - Physical / Site video/photographic record
b10d49bf-6fda-5dc1-8f29-890621070ada | note | METHODS OR REFERENCE - Asset Team - Base Preservation
a865c83c-1e5b-5930-a75b-1bcf16130cf8 | note | FREQUENCY - Annually Pre-reseal
e91b13de-7645-5ab4-9645-373575abbae5 | note | ACCEPTANCE CRITERIA - Documented approval from at time of Tender -Team/Client
6e364dfe-e39e-5492-ac9d-172fc0578849 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client Approval
fecc251a-e28b-53b2-ad13-e5624044e1a5 | note | RECORDS - Approved Seal Designs
7900daf3-eabc-568e-b26e-294de13c8d24 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
e712f751-18d0-481e-9d8b-94cc5b27bde0 | signoff | AUTHORITY HOLDPOINT
f77ebbcc-1e61-4a94-971d-dc2f4c02f219 | checkpoint | Chipseal Design
32125593-e49a-56a9-82d6-3a16526d4915 | note | VERIFICATION ACTIVITY - Peer review by Authorised Seal Design Approver
5d9ff096-a346-52f6-aadc-00d04b4bed4f | note | METHODS OR REFERENCE - Chipsealing in NZ
3d0a53ad-054f-5794-a334-86db72bb408d | note | FREQUENCY - One per design prior to commencing onsite
5b96cc67-f61a-5c1f-a1aa-6069f69fc78d | note | ACCEPTANCE CRITERIA - Design meets requirements of P17
1bcf2598-49cd-54a3-be59-63475ef59ec9 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
e12e15e2-af08-5358-8c8a-eef0dc16791b | note | RECORDS - Peer Reviewed Seal Designs
0109c951-c53d-57f2-9143-a5a7e8f9f5df | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
f604e18e-1b87-47d9-8985-21cfd9b0f4bf | signoff | AUTHORITY HOLDPOINT
6c387542-cee7-467a-8586-c9a3aaa1c208 | section | Materials Testing
5a0616b4-d95b-4cc3-8526-70d744231674 | checkpoint | Size (Grades 2-5) & Shape (Grades 2-4)
6a8116cf-f838-5d22-92d3-24ff0752bf3a | note | VERIFICATION ACTIVITY - Lab Test
37cc380c-eedc-58a6-91eb-d2897e1dcc04 | note | METHODS OR REFERENCE - NZTA M/6
c00c0cfb-aa59-5190-8aea-9ff8b7c25efd | note | FREQUENCY - 1/500m3
07558025-0a6a-5c23-8cc4-a31d5d83c997 | note | ACCEPTANCE CRITERIA -
12935f30-9322-57ce-963f-325da05ce100 | note | Size (ald mm)
11782103-ef3a-5a8f-a289-2508532300dd | note | – G2 9.5-12.0
44e94c5e-3b44-5a61-82a0-eece3915e7e6 | note | – G3 7.5-10.0
1984cea0-5da7-55d6-bc7c-d8c86fcbaf72 | note | – G4 5.5-8.0
768d4c03-0d11-567e-b6e8-dd7fe9db02fb | note | – G5 Report
15e70cfb-aca9-5484-98ce-9eec0479b405 | note | Shape
f82cb0bc-d62f-5776-9daa-8438b46d5f8d | note | – AGD/ALD Ratio G2,3,4 = 2.25 max
60db0a4c-da63-588c-8928-ebf4b803f4cb | note | – G2,3,4 = min 98% with 2+ broken faces
8f78423a-f9a9-5514-b4e9-cc4ba38493a6 | note | HOLD / WITNESS POINT - Witness Point
98d6e4b3-0e9b-54b4-bf17-855a1dd511db | note | RECORDS - IANZ Lab Reports
7b023df4-94dc-57ff-a3f4-858833416993 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
ebf10891-fe7f-46c4-b36d-51c2afdc292d | checkpoint | Cleanliness (Grades 2-6)
7c65619b-65fd-546e-97d6-c64e48fa6574 | note | VERIFICATION ACTIVITY - Lab Test
03cb8793-2c69-59f8-aa27-01c7322eeb9f | note | METHODS OR REFERENCE - NZTA M/6
f0d46b0c-f384-51f7-a755-491981f4c5e5 | note | FREQUENCY - 1/500m3
f4b6fd92-59a5-54bc-8cff-289d4609caf1 | note | ACCEPTANCE CRITERIA -
ea51d4b4-42dc-51dc-8197-cee3300339cc | note | Cleanness value
b634aae2-db61-5847-a018-63f409d69af9 | note | ○ G2 = 89
85dfed76-b499-52ed-bfcb-845fb0cedd93 | note | ○ G3 = 87
528e97a9-bb34-55f8-ac68-fd90683a3b2a | note | ○ G4 = 85
657b1b6b-fced-5fc1-99dc-60f57a9027a4 | note | ○ G5 & G6 Report only
6006450c-969a-58d1-b3d3-d2cb8d3bf52f | note | HOLD / WITNESS POINT - Witness Point
a21ec498-cd5b-5f5a-a408-18c601a27747 | note | RECORDS - IANZ Lab Reports
90dca6c4-0511-576f-9d3d-288e1dd6d6d6 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
e73f616d-11c0-48f8-8920-2ea42b3d2115 | checkpoint | Compatibility (Multi Layered seals)
7e980c5b-8c39-5506-9747-9f03ad988d3e | note | VERIFICATION ACTIVITY - Comparison Of Chip ALD
d42a813a-c218-58bc-93e5-91181537e85f | note | METHODS OR REFERENCE - Chipsealing in New Zealand NZTA (NZTA 2005)
a2e97d79-8129-51ac-a0c4-5773358452b7 | note | FREQUENCY - 11.5, 7.2
dbecd8af-2e82-5b25-9b9a-a389539c430a | note | ACCEPTANCE CRITERIA - Two Coat Seal Aggregate Compatibility
162099d7-f4fa-565a-8138-ffce32955bfd | note | HOLD / WITNESS POINT - Witness Point
e9f39998-31a2-5895-b7e3-37b642a9c3c1 | note | RECORDS - IANZ Lab Reports
bcb04773-0f56-5c76-bca4-d4a320dfe836 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
7e8be982-f558-474e-9030-9dba08db4079 | checkpoint | Bitumen Distributor
b9c09588-6755-58f1-821e-b4be36e85557 | note | VERIFICATION ACTIVITY - IANZ Lab E/2 Results
f51d60af-7a34-5ba7-81a3-aa89a369a9bf | note | METHODS OR REFERENCE - Code of Compliance
734c7a04-c061-5da9-bcc0-2c3f8d1d34e3 | note | FREQUENCY - Annual
b24f8268-6ce7-5549-a12d-14448fb19c42 | note | ACCEPTANCE CRITERIA - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
5af5fa4d-a247-5238-a0a8-d90c5bf19cf9 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client - Engineer Witness
45751f62-b184-5307-b90d-bc2a76a0694e | note | RECORDS - RNZ E2 Certificate
ff0e155b-5666-5962-94ed-7b23928fc6be | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
970dd462-0f35-44ed-bf41-365807315c95 | signoff | AUTHORITY HOLDPOINT
462e4f08-9eda-47b0-aaf6-2262cd721c3a | checkpoint | Emulsion/PME Testing
6aeb0a91-de9a-57b2-bef9-2d079e0b0b7f | note | VERIFICATION ACTIVITY - Lab Testing
4fdffbba-77fd-5056-96d5-93ef86fa01e6 | note | METHODS OR REFERENCE - Manufacture Specification
7c8684ce-c6fb-5994-9b25-3ec764d8b3c8 | note | FREQUENCY - Per Emulsion/Bitumen Production Batch
8a87d516-97f8-5fa4-8e56-975f88db6e60 | note | ACCEPTANCE CRITERIA - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
680283bb-a734-5b34-bd05-1ee8ef0f5980 | note | HOLD / WITNESS POINT - Witness Point
577891d2-3c9e-5313-83df-b25405ed50f0 | note | RECORDS - IANZ Lab Reports
cd7eefc1-d5f1-51d4-9f87-81bc48bf496d | note | RESPONSIBLE PERSON - Road Science
17667d39-1862-4d4c-8671-01f35ef354b2 | section | Surface Inspection
7db94019-5321-40fe-8dfe-df4da62bfb80 | checkpoint | Surface Texture - Measurement
ea6a9301-f759-5538-bb9b-5a25c100807b | note | VERIFICATION ACTIVITY - Sandcircle Measurement
9710ae19-37b9-5d3b-83c4-1f94ead71953 | note | ○ ARRB Hawkeye or NZTA HSD
857bb0a6-e14f-5fee-a7d5-476eee1307da | note | METHODS OR REFERENCE - NZTA T/3
7852b2aa-23a4-5c29-afa5-faf365ece545 | note | FREQUENCY - At time of Seal Inspection
ff3fbaa6-5e79-5363-9a5a-9aab093639d8 | note | ACCEPTANCE CRITERIA - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
29fff669-1952-51ed-b07f-3002b9a0ea2e | note | HOLD / WITNESS POINT - Witness Point
234ca677-0ab6-5851-a175-42b913ed011a | note | RECORDS - Sandcircle Data
3fcebe63-1480-57fa-b0e0-fe2d549486ff | note | ○ Hawkeye Data
0b1587ce-5b5d-5457-b98b-0722f656240d | note | ○ High Speed Data
8ea2742e-7b0e-5026-b615-c14d80674efd | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
1819cda9-a9ca-477f-a96d-ccc856dd6b4c | checkpoint | Pre Seal Survey
fac6283d-08f6-5237-a0e3-c73938d3c026 | note | VERIFICATION ACTIVITY - Downer Survey or MS Forms Pre Reseal Inspection
56870af1-ed29-54d7-9dbc-b089e75c9043 | note | METHODS OR REFERENCE - Downer Survey or MS Forms Pre Reseal Inspection
d94ab634-9a6e-5abc-b5eb-c7d901b6f571 | note | FREQUENCY - At time of Seal Inspection
dd569752-feef-5d06-939a-cf9e519a9678 | note | ACCEPTANCE CRITERIA - Record & any noted issues / Client
78edf02d-ec62-53c3-bc49-88066950b248 | note | HOLD / WITNESS POINT - Witness Point
4fe26d9d-2452-5522-ad29-3bbe54fbc22e | note | RECORDS - Lucidity
2cc5fbd2-a42c-5335-95c5-aa005d992c78 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
4372a70b-8302-4050-a6f1-f734ac6161d8 | checkpoint | Construction Compliance testing
1eb04db5-34e4-5660-8519-a27246e365d6 | note | FREQUENCY - 24 hours in advance of seal construction commencement
00128c60-89a1-5ef7-98a8-ea71c05746b7 | note | ACCEPTANCE CRITERIA - Confirmation from renewals manager all testing has met requirements
cb9be670-7972-5074-aa8b-2b740c270d04 | note | HOLD / WITNESS POINT - Hold Point
4bd9901d-850f-583d-b411-582a00974f33 | note | RECORDS - Email Confirmation
39ba154c-acfd-57ba-b427-0399e387d28f | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
a64a768e-3aac-4358-bd06-d57cc1265c82 | signoff | AUTHORITY HOLDPOINT
54663e06-af7e-4621-802d-dc02121496a4 | section | Seal Construction
a16174cc-a798-4e72-8ad6-ee61a563ab5c | checkpoint | Go/No Go Survey
baa43280-b6bb-5490-85c3-5de56231da02 | note | VERIFICATION ACTIVITY - Visual, Zeus, Iris
82523af8-10de-561c-b149-ce1e2eccf94d | note | METHODS OR REFERENCE - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
56d7125e-7f44-51d5-bd96-3a088c2c6f12 | note | FREQUENCY - Prior to sealing on each site
e541738a-772c-5f14-872e-e0c231aa0705 | note | ACCEPTANCE CRITERIA - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
8c0acbc3-d424-5831-83e4-87a9390b3549 | note | HOLD / WITNESS POINT - Witness Point
16fd627a-f3d9-5575-bd0d-e97f7cb2ab5b | note | RECORDS - Lucidity
4bf36fe5-114d-58be-a02a-7f8c4d758797 | note | RESPONSIBLE PERSON - Supervisor / Foreperson / QA
b957b463-c3f9-41af-98fb-1b22935eaf2b | checkpoint | Pavement Markings/RRPMs
cbb7d398-86f0-5256-942f-c612f8f09515 | note | VERIFICATION ACTIVITY - Tagging of existing Pavement Markings, Removal of RRPMs
6b30baea-2447-5bf4-b915-e39265eff001 | note | METHODS OR REFERENCE - Pavement Marking Set Out Sheet, CBP
ba42138a-cd85-5c99-baf2-c534cd73b0bc | note | FREQUENCY - Prior to sealing on each site
fe740cdf-b21d-5165-8264-8a2fc52052b8 | note | ACCEPTANCE CRITERIA - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
351f7d9e-dc59-51ee-9060-19d2e6adc6e8 | note | HOLD / WITNESS POINT - Witness Point
11b33926-9666-51d5-b10b-34a8aef87bad | note | RECORDS - None
4cdbef59-ed90-5ad8-ac8f-fafa099e3672 | note | RESPONSIBLE PERSON - Foreperson / QA
3094e6d0-176c-4649-8114-1c3fb17f1f20 | checkpoint | Road Furniture & Sumps protected
5a4eccc8-cd0f-5a02-8f30-fb5a5e459358 | note | VERIFICATION ACTIVITY - Visual Inspection
42f1e396-c0d9-5a43-a2be-3b5681da6290 | note | METHODS OR REFERENCE - Crew Breifing Plan / Visual
f55a0dea-2d4a-55f5-8d4d-62868983ffe6 | note | FREQUENCY - Prior to sealing on each site
5a6f89ce-3c63-527f-8693-07bc20deeb55 | note | ACCEPTANCE CRITERIA - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
cb1d391b-896a-5f33-a6fb-f809c43b7646 | note | HOLD / WITNESS POINT - Witness Point
2d34c56c-94bc-57f2-b569-51f269f4e39c | note | RECORDS - None
da727d5d-e3f2-55fa-8dce-2bb068923fe6 | note | RESPONSIBLE PERSON - Foreperson
f897cef3-5616-464e-9856-ec315f28c12d | checkpoint | Surface Condition/Temp
60f26011-38d8-5390-9319-7b11e4ec5e68 | note | VERIFICATION ACTIVITY - Physical / Visual Inspection
39ee4605-b53a-5fda-a349-c1aa4ab55889 | note | METHODS OR REFERENCE - Visual / NZTA T/3
9eb6c39f-5839-5ed3-a8ce-17c8c8630567 | note | FREQUENCY - Prior to sealing on each site
5b88cb74-bd2d-5eb4-8aac-e410c548cacd | note | ACCEPTANCE CRITERIA - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
d33d06be-a844-528e-9ed2-f474fbda815e | note | HOLD / WITNESS POINT - Witness Point
7e13a1e0-da36-54e9-a169-c57461e797da | note | RECORDS - None
102c8bba-6366-5ca0-9120-14e74d93b64f | note | RESPONSIBLE PERSON - Foreperson / QA
cda8a75b-ddfb-491f-85c6-d3554869ca14 | checkpoint | Stockpiles
b529c606-7062-5642-977a-a8d91dbfbbd6 | note | VERIFICATION ACTIVITY - Visual Inspection
388ff826-4743-5308-baba-1581300c31e7 | note | METHODS OR REFERENCE - CBP
31554d94-64a8-58e4-82a8-1febc7b3c3ac | note | FREQUENCY - Each Stockpile
d9397fe2-ec8e-5784-bf1c-a7907b3ec982 | note | ACCEPTANCE CRITERIA - Correct Source, Grade and quantity. Uniquely Identified.
ca9591c0-b738-53e5-ac7b-5aba50e6c791 | note | HOLD / WITNESS POINT - Witness Point
f2eb0657-ee6b-5ad9-a7fd-91840a2f9ef9 | note | RECORDS - Sealing Data Docket
adf162fa-a504-5c56-8ad7-d89194018bc1 | note | RESPONSIBLE PERSON - Foreperson
89177b2d-3a56-4676-a19b-acc65dc30c14 | checkpoint | Spraying
56106492-10be-5ce8-bc53-6b987d8f3ba5 | note | VERIFICATION ACTIVITY - Paper Start and Finish all runs
1f8d9ef6-cc59-5265-b113-c5d942bcbbb7 | note | METHODS OR REFERENCE - Spray Runs
4939c459-3960-54bc-b5b3-b33dfbe1855f | note | FREQUENCY - All Runs
01216aaa-eb01-51d6-ad6d-3005082fe42a | note | ACCEPTANCE CRITERIA - Mark out start / Finish
b1c88459-58c3-5726-8fa8-ef7c8695271e | note | HOLD / WITNESS POINT - Witness Point
08f57fe8-0561-5f41-a290-d3a131d9c101 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
0ff66321-2bdd-4e6e-8f3e-418c851cdd78 | checkpoint | Sealing
18218745-f65a-53ba-a97b-bdb075a5af89 | note | VERIFICATION ACTIVITY - Longitudinal Joints out side of wheel tracks
1f42b9d7-d4aa-5565-b6fb-ad2b13404775 | note | METHODS OR REFERENCE - Spray Runs
1adfdd88-26c6-51cb-87b7-2fddadfc878c | note | FREQUENCY - All Runs
e598842b-7989-5a14-b255-0823df67cb9b | note | ACCEPTANCE CRITERIA - Mark out lane lines by construction team
e61df316-2f7a-5b8d-be66-bb7bd438d813 | note | HOLD / WITNESS POINT - Witness Point
371f534e-3cfe-5d18-8d6f-581789578ad8 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
920d94bb-8684-4007-9851-15b273195585 | checkpoint | Binder Application Rate
10dd4742-d07f-56b6-91b7-8339538910cd | note | VERIFICATION ACTIVITY - Tank Level dips prior to and after spray run
1dc07a81-5409-56fe-9571-531d2de1e2d1 | note | METHODS OR REFERENCE - Dipstick
48059586-5d48-538d-a517-d458937b210f | note | FREQUENCY - At Beginning of the day
049dc32a-90f0-502f-a33c-d53faf908311 | note | ○ After 1st spray run of site
9d1eb934-ca1c-52eb-bcee-3076161ba4bc | note | ○ After last spray run of site
4011c2a5-d693-508c-8607-e96c30700956 | note | ○ At end of tank prior to loading
7440e263-839b-55d1-8745-5251e4779785 | note | ACCEPTANCE CRITERIA - Quantities used to be within the desired tolerance of design Spray Rate
1eb285e7-9c90-574f-a02a-ace6bacba525 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT
50c91244-1a85-52a7-9f2f-7bd8bc3374ee | note | RECORDS - Spray Sheets
78502455-b481-59f0-a404-a015a3c07804 | note | RESPONSIBLE PERSON - QA
788d4a20-7658-4f10-bbb1-f91c1c8df471 | signoff | AUTHORITY HOLDPOINT
8e93cf7a-eb6e-46a2-bab3-46b3fcc2cc54 | checkpoint | Chip Spread Rate
f6a3da0d-9889-5b49-b149-aae2ecd3c087 | note | VERIFICATION ACTIVITY - Visual
958a4cd9-f1dd-52bb-9b45-debaffb1c1e4 | note | METHODS OR REFERENCE - Crew Briefing Plan/Visual
f5b55ba5-5c6e-5245-b8f1-e808e95dab1d | note | FREQUENCY - On going whilst seal being constructed
56ee706b-283c-541c-a3e7-6ab9faaab8c5 | note | ACCEPTANCE CRITERIA - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
53e439d7-7b5b-572b-b3bc-01526d2620b3 | note | HOLD / WITNESS POINT - Witness Point
ac2c9fec-3e01-588c-9626-3c1bdd4f6f6f | note | RECORDS - Data Docket
97bf4280-9ac6-5ce1-8801-ab3811cfcbf8 | note | RESPONSIBLE PERSON - QA/Foreperson
6e41cbfa-200c-492d-9550-fdf5f4252afc | checkpoint | Removal of Surplus Chip
1a09f4bd-0665-5431-829d-19f43b4d168d | note | VERIFICATION ACTIVITY - Physical / Visual
e1e375a4-d845-5326-b867-964ff8e9a5e8 | note | METHODS OR REFERENCE - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
3e8fbe8c-292c-5fa2-b642-c2e940e34e67 | note | FREQUENCY - At conclusion of positive traffication within 48 hours
3de16c8e-16bd-51c7-9606-14b21c24c644 | note | ACCEPTANCE CRITERIA - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
d43d4a0c-4b77-56c0-9d06-7a25a97007a7 | note | HOLD / WITNESS POINT - Witness Point
6b5af8f2-189e-5527-b869-a0e2c07b68e5 | note | RECORDS - Post Seal Inspection
52be7210-9bbf-57a0-ae5a-404a732bcee2 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
a11901b1-48ac-4811-88e4-22d764d0494f | section | Post Seal Construction
6077e2f0-884a-4171-97c2-d562cead7296 | checkpoint | Post Seal Traffic Management
bb2983c0-0360-5d1e-a3cc-4e050dac6722 | note | VERIFICATION ACTIVITY - Physical / Visual
01c83253-e5e7-5578-919e-6e488c6997b1 | note | METHODS OR REFERENCE - As per TMP
d1a0a5bd-9a7e-5878-98ac-a04367bb1896 | note | FREQUENCY - Full length and width of carriageway
bac4151b-4024-50c3-a393-958e8d74cae8 | note | ACCEPTANCE CRITERIA - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
0818d570-deb3-5dcc-aaed-a100a0238bba | note | HOLD / WITNESS POINT - Hold Point
bf34ccde-38b5-5c9f-affa-9d009371cd95 | note | RECORDS - Zeus or suitable recorded weather data
4664ad1d-8eac-5034-ab25-943130eb6747 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
236b056c-58d0-4362-9c6e-7d0e240ed7b0 | signoff | AUTHORITY HOLDPOINT
0c9a4237-0062-43a3-ae72-dfaf4261c886 | checkpoint | Post Seal Inspection
066c9566-5b0f-515e-a393-214cc6d42a3e | note | VERIFICATION ACTIVITY - On Site Visual
aed14217-3aa6-5cf5-b7fd-cd912a6aca77 | note | METHODS OR REFERENCE - Lucidity Post Seal Inpsection
595c5426-6a89-5938-9230-4cbb578f15e1 | note | FREQUENCY - After sealing is complete
825082a7-a947-553a-93aa-4dbf3aa7e3f6 | note | ACCEPTANCE CRITERIA - Engineers requirements. Any defects identified, repairs programmed and costs estimated
bd831730-f430-53af-9691-25380d7c4759 | note | HOLD / WITNESS POINT - Witness Point
f1f9e735-43ae-553f-b84b-4eb74c883340 | note | RECORDS - Post Seal Inpsection
092923c3-0cb1-5820-9a6e-a64424b342b4 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / Manager / QA
18fb86a2-a2f2-4346-a543-559b13a7d97a | checkpoint | Asbuilts and RAMM data
1861c79a-1a9c-58da-beca-415acba11db0 | note | VERIFICATION ACTIVITY - RAMM Update Sheet
5bee76e2-cfca-55f2-b786-d2789dcfb01d | note | METHODS OR REFERENCE - RAMM Database
1ec043cf-baa5-55be-a090-8bd8616db9e6 | note | FREQUENCY - After sealing is complete
b2776b25-f423-50bf-a1af-edbacb2291d2 | note | ACCEPTANCE CRITERIA - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
51aff0d1-38c1-540e-bcb9-895343e2e169 | note | HOLD / WITNESS POINT - Witness Point
a6387424-cf66-5156-97bb-e498e3f1e069 | note | RECORDS - As built information / RAMM Update Sheet
eec144d8-1215-5f78-a741-a1f9abb6e653 | note | RESPONSIBLE PERSON - Sealing Contract Manager/ QA/QE
ec5dda9d-0860-4ea5-b0ec-d715252426d4 | checklist | ITP - GRANULAR REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - GRANULAR REHAB INSPECTION TESTING PLAN
4a53e1ff-f0dc-47e7-9a1e-cbe79b2d4d1f | section | Subgrade
833a9c54-1516-47f3-a985-a2b77ba0cd24 | checkpoint | 1.01 - Field
217c5661-52f7-552b-a7ab-a5a90f6909ef | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
3a65fdda-d08c-50f0-af6b-8a8e1d6dd4c0 | note | Reference Documents - RITS Table 3-20
133e5ec1-a90b-5583-b99d-ddd18d80a640 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
7802ce43-eda7-5df5-a9ae-7ddfda0dfaf6 | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
46cc95f5-2963-5366-a384-28e51fa23d03 | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
2fdbc726-0ca9-51fc-a66d-28d8647cc7dd | note | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm
bff3ab40-b400-594e-886c-d7655d64c207 | note | Action Point Records Required - Test Record
9fd66279-5859-519f-9073-dd2a21c24c2e | note | Responsibility - QA / SE / PE
cee436d5-3e83-4280-8773-6d564c0c2a90 | checkpoint | 1.02 - Field
4da70fcc-7525-53db-9778-98dd519de912 | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
fa1197f3-3226-58c7-9810-84d0197c4154 | note | Reference Documents - RITS Table 3-21
d8f05b8b-cbeb-559d-a0e6-809fc70de94c | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
f9fba30a-986a-5511-b004-c3c484204bb8 | note | Material Test Frequency - In centre of undercut or trench, Minimum of 1 test per undercut location
99177218-9f58-5063-946f-15058d750d23 | note | Target Criteria - CIV ≥ 15 or CBR of 20
22ab9787-a494-5022-8aeb-ef5d8454c99b | note | Action Point Records Required - Test Record
a1280a49-e622-5738-a646-f92f08eea303 | note | Responsibility - QA / SE / PE
b192725d-7c62-4542-ab98-63fcafedef5d | checkpoint | 1.03 - Field
8076f805-8775-5018-9627-10381b293b95 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
59a028f6-cd8c-5b79-b701-63d760caa071 | note | Reference Documents - RITS Table 3.24
225e2ba0-e5be-5752-9b11-20c6d8b5fffd | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
5ba26114-b3de-5845-891e-f6e3b4fdf545 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
ba4d9ade-1f23-5319-9ce1-a8d58737781a | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
7f22a1e6-6d6a-56b5-afc3-cd3e03d032da | note | Target Criteria - +0mm/-30m from design or nominated level
bc5bf8b8-25c6-5e47-b943-d374e460e63c | note | ○ No more than 15mm deviation from a 3m straight edge
d0e8e422-eebc-5e6f-a5c2-5aa632ee39c0 | note | Action Point Records Required - Survey record
44e73bf1-4759-5d82-a8d4-9125f088699e | note | Responsibility - QA / SE / PE
d8354076-7ff9-42c6-ae5a-01ed10a41a62 | checkpoint | 1.04 - Field
4ba8327e-d6e3-53b9-8c07-e8569bddc636 | note | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
776e8d66-53a2-5ac0-b785-348fa908a026 | note | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
b1977f3b-775f-556a-9d1b-e9fb4ad0bb50 | note | Material Acceptance Criteria (Method) - Manufracture installation instructions
192439ae-aff8-5d75-ad84-858077eae986 | note | Material Test Frequency - 100% of Surface
74c5ab3f-aadd-533c-9791-25e1766c191a | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
ef61f35b-cc25-577e-a84f-6bb115d14cd5 | note | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
04eac2e0-38de-51b3-a298-e33d318cc6b1 | note | Action Point Records Required - Site Record
12eddcc3-4f6e-555a-a5c8-055a7872039f | note | Responsibility - QA / SE / PE
193100aa-64d0-4bb9-9a23-cf433515c84f | checkpoint | 1.05 - PQE
dfc1f7f7-7272-5839-8256-b2a6e2cfc245 | note | Material Test Method Requirement - Is the layer closed out?
af97ccbe-8dad-5e19-9367-e8665e611ae3 | note | Reference Documents - See PQE
475b2664-5e89-5a50-b7fa-b98e005952ef | note | Material Acceptance Criteria (Method) - See PQE
4027b42e-d650-5003-9c3a-07d71202b3cc | note | Material Test Frequency - 100% of Surface Prior to placement of material
02afbcf8-9035-5f8c-a837-ea8aed4da809 | note | Target Criteria - PQE Approval
f6d999d3-4262-599d-a764-5e78f437cf91 | note | ○ All testing record & reviewed as compliant.
6ef92a32-9ce2-5289-b63f-7e1a7296c25b | note | Available Documents:
0b1df901-e115-5587-86da-88da8de2d880 | note | ○ Test records
2fc702d2-3fe4-5804-bfae-27c4d1628b13 | note | ○ Survey records
177b54cf-79e5-51b3-9516-3e109b5b4ad9 | note | ○ Hold Point Records
bc7746a1-2c80-5328-9056-a9b6e020444a | note | Action Point Records Required - Hold Point
6ecb63a7-4788-5326-8b6d-67c0739d3a90 | note | Responsibility - SE / PE / PM / PQE
ea7637d9-d328-452a-99f4-47cb4daccad1 | signoff | AUTHORITY HOLDPOINT
09f00d49-f20e-400a-ac3c-554cabd17433 | section | Subbase
824f1692-c02a-4662-b0ca-40ca77f21aad | checkpoint | 2.01 - PQE
4e17b1ac-0e6c-5612-b1a2-c859db4c2c95 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
a1d01ca8-c4df-5e1d-9be7-59e5207a058f | note | Reference Documents - Insert Material Testing link
43a93335-8969-5841-b990-616de0075df6 | note | Material Acceptance Criteria (Method) - See PQE
8b55a06a-85db-5e89-a02f-bb5d54077ed2 | note | Material Test Frequency - Prior to construction commencing
49e30b3c-2d72-581f-a5fd-2e9651a12bda | note | Target Criteria - Material meets project requirements
9d8cd007-1f60-5f88-a075-83fc8c6173c7 | note | Action Point Records Required - Hold Point
3b7138fc-4818-5554-91d6-178db1867a85 | note | Responsibility - SE / PE / PM / PQE
1a7e6be5-6345-425c-9eb9-2b5340cc91a9 | signoff | AUTHORITY HOLDPOINT
81292115-f3ce-424f-a231-48c552055864 | checkpoint | 2.02 - Field
17612ea0-406c-5ca2-988a-f21a01188a08 | note | Material Test Method Requirement - Plateau Density Test
f5d4e46c-bac7-5c1a-bac6-b1231894b293 | note | Reference Documents - TNZ B/02: 2005
ec154a61-db3a-59a6-b7ec-35e2fb367ef5 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
3d9cf93a-d25e-50f3-90d5-99f746d59b7b | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
53980568-45dd-5dce-8101-32374a313787 | note | ○ Target to be approved by Engineer
de7a4797-91b2-5828-986c-a00ad3240a5d | note | Target Criteria - N/A
54641c7b-c6b0-5588-81ab-2f4f8413dd81 | note | Action Point Records Required - Hold Point, Test Record
55ac252f-cf45-5103-b919-dc907a2b1526 | note | Responsibility - SE / PE / PM / PQE
cdaec728-0f73-4816-a5c4-7d033b54ca3b | signoff | AUTHORITY HOLDPOINT
9255d1d7-e612-458d-8c11-9172faa9f5bc | checkpoint | 2.03 - Field
2f62eb67-6927-5981-85da-9fe62505948e | note | Material Test Method Requirement - Clegg Hammer
dafe8cf0-4f8e-5408-bc00-1e843ad44045 | note | Reference Documents - RITS Table 3-21
a57c0813-5009-5942-87c9-9f4fb2e61bce | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
0a8904c6-432a-598f-8e39-ff96fdcbd0d0 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
af16604e-49b8-54fc-ba4a-0e60b374ce28 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
50e45a78-d000-5e33-aa0e-6dbeeb7bfe2e | note | Target Criteria - CIV ≥ 25
aec72f6b-d942-524e-9307-c7bb75b97c7b | note | Action Point Records Required - Test Record
507c570b-c473-55cf-a6c4-180b1415fb15 | note | Responsibility - QA / SE / PE
9cfb2c8e-643b-480d-a6ed-63c08a76c1b7 | checkpoint | 2.04 - Field
55cd34b5-e8e0-5c76-ac21-099599e61940 | note | Material Test Method Requirement - Compaction NDM Back Scatter
24b1889e-1a8b-591e-97c2-fef5dab1dec2 | note | Reference Documents - RITS Table 3-22
5739aecb-0001-5010-b6ec-4aada27b1540 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
2416baa1-627d-5eda-b0a7-dede97b2abc3 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
77d54de2-a490-5510-9b3b-ccf7310aeea9 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
fad2497c-62e2-58d2-a7ef-8c8467d478d4 | note | Target Criteria - Mean ≥ 95 % MDD
4b87e9b4-7cdc-58fc-aad9-a3603b29fc5b | note | ○ Minimum ≥ 92% MDD
b94ba9ce-ca36-59f0-a291-63486a70fce3 | note | Action Point Records Required - Test Record
db71aa11-d97b-56f5-8dfa-d08c35810b21 | note | Responsibility - QA / SE / PE
419e3731-9916-4002-8700-16dd875bc1c0 | checkpoint | 2.05 - Field
2461d8a1-2853-5b8c-8025-0ef0e9a41931 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
f9d1bc7c-be01-50a3-8a0f-3b09a4ab3cf3 | note | Reference Documents - RITS Table 3.24
256104bc-683c-5056-a2a5-4a161c812f7f | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
e8c5af2d-7e98-565c-b021-ab2d023e0380 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
6a483674-1b54-575f-b57f-71fc44a7537b | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
7c720fb2-ad5d-5502-a862-f1e351d49f62 | note | Target Criteria - +5mm/-25m from design or nominated level
9cd91d47-5290-51ed-8be1-251389ebc3c8 | note | ○ No more than 15mm deviation from a 3m straight edge
ff69ed24-a19e-54cc-85fa-10f1cd61794d | note | Action Point Records Required - Survey record
727b94e9-cbdc-543e-9e04-aa4d4db88200 | note | Responsibility - QA / SE / PE
6a31d294-738b-4e88-9227-88e3a9bcac30 | checkpoint | 2.06 - PQE
51aba292-d103-54b2-b5f3-987f90cbb452 | note | Material Test Method Requirement - Is the layer closed out ?
867ecb5b-1b55-52d5-9468-7f792c168f2e | note | Reference Documents - See PQE
62da9652-cc87-532d-bcba-156aba5ca1c9 | note | Material Acceptance Criteria (Method) - See PQE
8a4e3b41-5cd6-5d46-877c-8f3b46a91ba4 | note | Material Test Frequency - 100% of Surface Prior to placement of material
c0ac5202-6a89-5bb6-ac2f-e27199f3644a | note | Target Criteria - PQE Approval
bd913970-ce2c-56c5-bc4f-6901d92e0c39 | note | ○ All testing record & reviewed as compliant.
418155dd-cfb2-5b43-93ef-29d1c2292807 | note | Available Documents:
7300ffca-a510-5db4-bec1-fdb715909978 | note | ○ Test records
e1d84957-ca31-528b-9ef8-dc7d0c47304d | note | ○ Survey records
3165f9ff-0825-53a0-a093-cc5ad70113c5 | note | ○ Hold Point Records
55c09936-04d6-596b-bc65-577081b612e2 | note | Action Point Records Required - Hold Point
cc9a8145-6597-5b88-8df7-17c52704c2f2 | note | Responsibility - SE / PE / PM / PQE
12c97a93-326a-4806-b1ce-4dccec36e011 | signoff | AUTHORITY HOLDPOINT
bbc4dca2-dca8-4195-82fd-63bea379a723 | section | Basecourse
fa58b4ef-564f-4019-b5a4-4f1f7906102c | checkpoint | 3.01 - PQE
d89b9fd0-390c-5a4f-9ebd-af6416da7b32 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
11591ee0-5257-5bb9-9d3d-09e420021ce4 | note | Reference Documents - See PQE
0e160e31-dce9-5bb3-acfd-c8cdd11dfdb7 | note | Material Acceptance Criteria (Method) - See PQE
473a5e87-8f04-556a-9443-418988173346 | note | Material Test Frequency - Prior to construction commencing
753f9814-1f41-51a8-9cfe-82c958ffc466 | note | Target Criteria - Material meets project requirements
e18366fd-8422-5c52-a973-01ed37acbba6 | note | Action Point Records Required - Hold Point
5ac12076-488d-5ea4-b876-0e08c923ff77 | note | Responsibility - SE / PE / PM / PQE
3f4a1013-4ee4-42d0-bf8c-8e8a192df1c5 | signoff | AUTHORITY HOLDPOINT
d4d3109a-2d17-4e34-9296-f14e993d8781 | checkpoint | 3.02 - Field
5dd3f8d4-04d8-58c6-90b7-307d35dd5fa7 | note | Material Test Method Requirement - Cement application Mat test
f1d05917-8a28-5b24-897c-316826012acb | note | Reference Documents - TNZ B/5:2008
5db59e49-c1b3-58d8-93fd-753a58179c7f | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
9c5d86fe-2806-58c7-9786-c294ab3fc986 | note | Material Test Frequency - 1 test per 400m² (minimum 1 per run)
e34469de-a6dc-5ae2-9708-c4db8acd1112 | note | Target Criteria - ±0.50kg/m² of specified rate
44944e70-a036-5651-9729-7bed04d17dee | note | Action Point Records Required - Stabilisation QA sheet
ce82c926-dc5d-52c7-ac4a-62a12ef6d108 | note | Responsibility - QA / SE / PE
6624ce3b-92e5-45cb-8c79-952fc0d973eb | checkpoint | 3.03 - Field
c60e5753-965f-5306-899a-ad6023cd49eb | note | Material Test Method Requirement - Stabilisation Depth
21b07c92-448f-5d58-a871-4f1b38af4b23 | note | Reference Documents - TNZ B/5:2008
34483f54-d26c-5e01-9d23-f409db9b4d88 | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
860c0023-58f7-5184-b7ef-d17b5f898d6c | note | Material Test Frequency - 2 test per 400m² (minimum 1 per run)
08c336c3-6572-5a19-8008-f97594ad2b9f | note | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
f31a62f0-dac9-5a5c-b634-4de1ba1d77a4 | note | Action Point Records Required - Stabilisation QA sheet
2aaa9f8a-8007-5530-85dc-d1aa7b4613fd | note | Responsibility - QA / SE / PE
e43e22df-4e18-4bd7-842e-22bfaac40124 | checkpoint | 3.04 - Field
e9d0b731-92ae-560c-9a3f-516254aa59a4 | note | Material Test Method Requirement - Plateau Density Test
dd87ffc1-b24c-5e5d-9d7e-b14196d72b64 | note | Reference Documents - TNZ B/02: 2005
6cd7dd11-43de-5417-b234-241a1b174b7d | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
65bc1887-c7e5-5d26-8d9a-dfb55a0c1ff6 | note | Material Test Frequency - 1 test per site
0a476c8c-6f92-598d-8509-9baec6159e4f | note | Target Criteria - N/A
fa2dc0b2-dea4-5478-a6c7-eb7fb1d4d5c4 | note | Action Point Records Required - Test Record
039e5309-b7fd-5152-9383-ba590f1ffe2f | note | Responsibility - SE / PE / PM / PQE
6d406241-86d7-4ffe-8ec2-9d678da10f00 | checkpoint | 3.05 - Field
c0e6d9e2-86b0-59c7-ae60-e1ca150c5f4a | note | Material Test Method Requirement - Clegg Hammer
c1af60b6-fb74-5f88-b6cc-c7e5b63f18ba | note | Reference Documents - RITS Table 3-21
5aa0d380-71e7-5445-a835-40ceeeb27cd7 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
87ac84c8-8380-5f45-881f-1faa6e947822 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
1fcc8f37-32d9-5fde-b41a-f3c101ad2528 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
f3b71b40-5464-547b-abbf-49d9c7cc99ee | note | Target Criteria - CIV ≥ 40
33f5ad8d-22d0-50d9-a290-3b7ca6efdd39 | note | Action Point Records Required - Test Record
23657f1e-dd33-512d-bd86-f5f498fec3a8 | note | Responsibility - QA / SE / PE
a0e7b3a4-e0b9-4874-a0f7-55d75e29eaec | checkpoint | 3.06 - Lab
b286bf9d-4a5f-5ea1-aa67-56dc816a2e66 | note | Material Test Method Requirement - Compaction NDM Back Scatter
8ab6dc35-0705-5963-9be8-4d3031f2b7a8 | note | Reference Documents - RITS Table 3-22
4fabbf8c-0259-5d78-b54c-3836b34b2c8a | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
4e260b44-d17e-56b6-91ee-c6f780f53d34 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
1d305402-96a2-587b-8cee-d7b5ba17adcc | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
08502657-3607-5633-a3bf-6cbaa26f59c5 | note | Target Criteria - Mean ≥ 98 % MDD
285bb911-afa3-54a7-8dd7-900bb45dab76 | note | ○ Minimum ≥ 95% MDD
993e302a-6e44-5ce7-880d-a2429ebbc4f6 | note | Action Point Records Required - Test Record
f38ced75-9069-566b-baa2-2b446c3fd186 | note | Responsibility - QA / SE / PE
5f96699c-1b9c-4c42-a382-eb79c32b9b0e | checkpoint | 3.07 - Lab
0b4f2dbc-ebc9-50cc-a818-57c057f0c779 | note | Material Test Method Requirement - Benkelmen Beam Deflection Testing
9e1136cf-ebec-59e4-9fcc-eb185f28bd16 | note | Reference Documents - RITS Table 3-23
e29ab170-055b-5b27-ab1e-5a84f3f44556 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.5, ASTM D5874-16
23f12a18-9134-5b34-8ec7-8d1dfcd049af | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
85bb246c-c73d-5453-a34d-51e1792ef34c | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
8360afee-f16c-5e91-81f5-ab7d4479c1eb | note | Target Criteria - Max deflection allowed: 1.83mm
d2bfde77-f9b7-5a77-abc7-bfca8a7245de | note | ○ From design report - due to non-RITs compliant Subgrade CBR
bf080c70-0a74-588b-8026-bc7a52e94d1e | note | Action Point Records Required - Test Record
c881c64f-8672-5269-854a-b91892516da2 | note | Responsibility - QA / SE / PE
5504906a-b934-41de-91ed-e0f91a03632b | checkpoint | 3.08 - Field
fbc4b6a1-2917-530e-b17f-ee6da4ff873e | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
2a8ceb4d-386a-5b65-8a05-012a9d25ba27 | note | Reference Documents - RITS Table 3.24
e58e894f-5e40-58e0-98ac-4506e9c66f27 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
6fafd489-d9d9-51e0-b23a-2ba8d7596d0d | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
1b8a4d8d-b30e-543c-8437-dd57675a2138 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
143ff4a3-6ff7-5e72-8032-ee038a11ca14 | note | Target Criteria - +10mm/-0mm from design or nominated level
9a1e64df-c4c0-51d4-94f2-99e3468fcd58 | note | ○ No more than 12mm deviation from a 3m straight edge
dcaccffa-ce94-57c8-94b8-abfb32138237 | note | Action Point Records Required - Survey record
786943df-1e2d-5040-9e6e-2e60d14b4d7a | note | Responsibility - QA / SE / PE
d5c7f0dc-8d70-47f5-90a8-a53ab4f672ef | checkpoint | 3.09 - Field
d7cb7000-8fc5-522f-88d3-4e89c6cd3fef | note | Material Test Method Requirement - Visual Inspection of Basecourse Surface
3fdbaa6f-5376-5874-b9e1-3338717a6b94 | note | Reference Documents - TNZ B/02: 2005 7.8
c723dd8e-4f67-5133-a078-d9f0202e5ef5 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
8bbc1d23-a12d-55eb-830c-5ac4a653b09e | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
18c01434-e1e2-5c51-8ac3-196d987b407e | note | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
44084d4b-0cee-5a5d-84ce-7cb6df73b5ba | note | Action Point Records Required - Hold Point
99de7704-b5ea-5aff-899f-7c1d521fcb27 | note | Responsibility - SE / PE / PM / PQE / ER
698878bd-a650-407e-8a95-a21eec1e7280 | signoff | AUTHORITY HOLDPOINT
0371f60c-3bba-41c7-af0a-814dd67a7670 | checkpoint | 3.10 - PQE
a5649b61-eb6c-5deb-a88c-22453df7b9ef | note | Material Test Method Requirement - Is the layer closed out ?
75a2432e-419e-5f6c-ab32-5da24dcff6ea | note | Reference Documents - See PQE
52e8b236-579b-5be8-866d-aa90a0671e49 | note | Material Acceptance Criteria (Method) - See PQE
da34bcfd-9d55-51c1-8883-e1e2d04ac1cb | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
598cef2d-cf75-58c4-9103-d268905865a7 | note | Target Criteria - Engineers Approval
4812bbfa-f9d6-5377-a8be-bc6a3fa44f4e | note | ○ All testing record & reviewed as comliant.
ac8e2aa8-5af0-5505-ab41-11ead8e2e9e5 | note | Available Documents:
7b2ef9f7-55f2-50cc-ac01-a38151082f83 | note | ○ Test records
5b4f9d0c-5945-598b-bf1d-6e9dacf74e04 | note | ○ Survey records
75eecdc4-1920-5d93-a2a4-e64bf986b29a | note | ○ Hold Point Records
36ee847e-9da0-5014-b92d-2f42bb967c6e | note | Action Point Records Required - Hold Point
ccecc880-dbea-5b9d-8524-92e138a545b0 | note | Responsibility - SE / PE / PM / PQE / ER
a2ce9bbf-7703-4468-94fa-16ef2984a8bd | signoff | AUTHORITY HOLDPOINT
c9f5d6ed-04ce-4589-95cd-20998e550750 | section | Membrane or First Coat Seal
c87c0384-79d7-4a11-866f-12e1a206ffe3 | checkpoint | 4.01 - PQE
41ce1379-6134-5e8d-aac9-e5ecace1c190 | note | Material Test Method Requirement - Seal Design
70ef40bd-e452-5103-b7e5-cc3f8b6cac6d | note | Reference Documents - INSERT SEAL DESIGN
f1e10dc2-d103-59d8-91d6-9174361d0366 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
94a02d35-418a-5739-8769-23050648fb49 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
12d56daf-82ca-57f8-8906-ff6e248d7a3e | note | Target Criteria - Meets project requirements
6a4118fa-cbac-52b5-b8c0-2c31e7c0a711 | note | Action Point Records Required - Hold Point
1fa47671-537a-5309-83bd-3e378bb583bb | note | Responsibility - SE / PE / PM / PQE / ER
e6beebda-227e-4010-86a5-74751e774afe | signoff | AUTHORITY HOLDPOINT
f52e49df-a1e1-4108-bf8e-30c0e78769bd | checkpoint | 4.02 - PQE
be365c2e-5fc7-5108-b195-7e4407502aa2 | note | Material Test Method Requirement - Bitumen Sprayer
3a4df9eb-52b5-5050-a816-40453de118eb | note | Reference Documents - TNZ P3
3ea963ec-43b9-59c9-aecc-b2f2a1492fb6 | note | Material Acceptance Criteria (Method) - Certification provided
a90d80ef-bd47-548b-a089-94341a9fc6c7 | note | Material Test Frequency - Prior to starting
176c992e-f692-55ba-b233-b446df7b4704 | note | Target Criteria - Current E/2 Certificate
6f5a5165-ac24-5302-88a1-fea9a01560ba | note | Action Point Records Required - Certificate Sheet
afd8424c-8ccf-5def-bb1e-a9ee14af8810 | note | Responsibility - SE / PE / PM / PQE / ER
7e3f6728-288d-4db1-bb9d-80ce8b85e4a8 | checkpoint | 4.03 - PQE
8875da92-7d31-5d67-aea1-7d6ad0ec427e | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
cd73aec3-88e2-5b30-bd70-0059cdbc503d | note | Reference Documents - Insert Material Testing
6101360e-4f2c-5e33-96de-48906f65d10a | note | Material Acceptance Criteria (Method) - See PQE
1994c5fe-ee3d-57f2-b99b-9afe29e11cc8 | note | Material Test Frequency - Prior to construction commencing
d2f9d746-bcf6-53f0-89f6-b044699d8e35 | note | Target Criteria - Material meets project requirements
2c5ffbd1-38aa-538d-bc92-3fd73c4ac65e | note | Action Point Records Required - Hold Point
98d1f77e-c544-5868-a3a9-15b9a3da7679 | note | Responsibility - SE / PE / PM / PQE
ff25151a-1cf4-4048-99b3-bc31a3201356 | signoff | AUTHORITY HOLDPOINT
52cb18a1-caf9-41ae-b1ab-20635c432ed1 | checkpoint | 4.04 - Field
9337bdc2-855d-5fb4-b9e9-904ad65b091a | note | Material Test Method Requirement - Preseal Inspection
392617a4-7b02-546b-8632-c6585bfa609f | note | Reference Documents - TNZ B/02: 2005
bf8a7d3f-059b-59dd-a468-c064eefc5950 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
c7b20a21-eb7f-586f-b2c8-d306fefbada4 | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
a16589c9-a040-5ab6-af40-d19436cbe45f | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
982ca5a1-1785-5acb-8006-22959e8d36c3 | note | Action Point Records Required - Test Record
909321db-6de9-55d5-9c06-ee741acfb48d | note | Responsibility - FM /QA / SE / PE
8d3ef751-8293-4431-a953-120f59ab9913 | checkpoint | 4.05 - Field
43395f88-cc7b-5268-ab63-0dd844797380 | note | Material Test Method Requirement - Degree of Saturaton
0b5cf5ec-8bc1-5f5e-8ba2-e4ebc277ae6c | note | Reference Documents - TNZ B/02: 2005
e47e1254-ebbb-53fb-bf15-de2521b56ee9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
eec30acc-984d-57b5-90a8-b1993647bed3 | note | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
4eeb90e8-b2cf-5171-9983-eb3990a95a04 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
294f2947-cdfc-5351-9e50-85e77eb58d71 | note | Action Point Records Required - Test Record
aeffbe2a-a7e6-5005-858e-7f7c2fcc1f93 | note | Responsibility - QA / SE / PE
ccd95ac4-5471-46af-8f75-934c6dabe64c | checkpoint | 4.06 - Field
f0055c25-3c12-5969-8e0f-e88baba3bd10 | note | Material Test Method Requirement - GO/NO GO Survey
487f1283-7984-5c48-b3e6-c05d8ed22938 | note | Reference Documents - Downers processes
b941304e-f89c-5ef5-8099-3282b5480953 | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
76180cf3-3f8d-529f-bff0-50b82c03c2fa | note | Material Test Frequency - Prior to sealing on each site
54fbb06e-8f7f-5275-9120-7ff77ce564cd | note | Target Criteria - Pass on GO/NO GO, Marginal & discussion with contract Manager or Written approval from Rehab manager
d9aa6425-cf7c-5cb5-85d0-a79a159ef17c | note | Action Point Records Required - Survey record
46514b4a-1fdb-503a-9b80-2c3f9d212c92 | note | Responsibility - QA / SE / PE
e2e83c43-1ca3-4637-803f-ab682fdfc820 | checkpoint | 4.07 - Field
7a135c46-629b-5820-a2ff-a3245a7b4202 | note | Material Test Method Requirement - Road temp
3ac80d12-ae6b-5f2c-93b1-7c5800b61b6e | note | Reference Documents - TNZ P3:1995.18
8fc698ec-76e7-5355-836d-2ed059f11158 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
2469b369-fbcf-5eb7-a020-fe489f5c350c | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
8fd3a21d-8554-5da7-acbd-4bc352dc9b02 | note | Target Criteria - Air temp >10°C
cc7d61dd-f81e-5642-bf3d-bbef158a4c64 | note | Action Point Records Required - Spray sheet
157fc9aa-492e-5ea4-8075-34d63e83a809 | note | Responsibility - QA / SE / PE
a83ea12b-9caa-4734-801f-4af57a119854 | checkpoint | 4.08 - Field
bdaa1955-9d8c-5bb8-9e7e-d1e8b7c77351 | note | Material Test Method Requirement - Application Rate
aa725496-7e7b-5e4b-be9a-a7bf865fcba1 | note | Reference Documents - TNZ P/3 : 1995.18
09448168-a52d-5079-ad59-ef395aa53814 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
f73cd632-85d9-57ef-8946-b1cd668a2d42 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
9881e53f-9dea-54b2-a2db-62655264074a | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
d167f5a6-cb56-5dbe-b762-92d78de90b65 | note | Action Point Records Required - Spray Sheet
d8759027-e115-5aae-9847-5e6ab5f51aaf | note | Responsibility - QA / SE / PE
27ad8de6-8d55-4b83-99bc-bad5ab18432b | checkpoint | 4.09 - Field
56978a08-56c2-5c9f-9bef-5bc646d8b076 | note | Material Test Method Requirement - Chip spread rate
02a5ab45-3923-5f4e-ba45-11c750b14a09 | note | Reference Documents - TNZ P3: 1995.21
ab0fbfa3-e25d-5bec-9c6f-9c1bec7754a0 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
442a4db2-e2be-5b12-9010-25efdca8b1f2 | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
be57aef9-a295-5e09-900f-1cd1a203a8f8 | note | Target Criteria - Visual checks meets seal design requirements
cb0ae1da-6619-5e41-971e-d7275a77e27a | note | Action Point Records Required - Witness Point/Spray sheet
1e69589f-2d8d-5754-9a2c-f7f92a1dcf7b | note | Responsibility - QA / SE / PE
0b1656b1-cdd0-4e62-b083-c8db27801250 | checkpoint | 4.10 - Field
d391db62-d282-527e-81fa-a2e03055fb75 | note | Material Test Method Requirement - Rolling Checks
8bc85263-68f0-5c8c-af1b-dcdfaef87fd9 | note | Reference Documents - TNZ P3: 1995.22
4b15e85e-1174-52dc-a966-e15f60b63e11 | note | Material Acceptance Criteria (Method) - Sealing Record
bfaed682-a215-5af1-aa5f-68f24aafd871 | note | Material Test Frequency - for each sealing site per day
00c39a84-270f-5159-ac47-dc857e7cf715 | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
fdc8b082-4046-5513-9278-660c66573a3c | note | Action Point Records Required - Witness Point/Spray sheet
170e2039-f457-5c9e-8fc8-abea08dd7481 | note | Responsibility - QA / SE / PE
b17bef5a-b03f-4efd-9ba6-c9421db8b76f | checkpoint | 4.11 - Field
5412f4b2-5e6f-5d6a-b338-8607f98b5824 | note | Material Test Method Requirement - Post Seal Inspection
72ce7dbf-8387-5a94-a649-8a173305fc82 | note | Reference Documents - TNZ P3: 1995
37d54f49-d378-5cad-a714-1c3bf78b3410 | note | Material Acceptance Criteria (Method) - Engineers Inspection
4d75cd0f-2093-574e-8a5c-a3aea63381d6 | note | Material Test Frequency - After sealing
9c103069-96c9-514a-8147-82fb279af508 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
7bc3005e-ec81-513b-84b3-76715deef1d9 | note | ○ Line marking has been reinstated
3540f5f6-f945-53bb-9653-aa9dc731826b | note | ○ All excess chip has been removed from site
d356802f-2926-57df-8bab-735a336e1eb5 | note | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
06f4260d-1527-5607-9a94-4abf9636934c | note | Action Point Records Required - Hold Point
6a513f12-6b0f-52be-a9c0-427897495ba5 | note | Responsibility - QA / SE / PE
9dbf2c11-6f60-43ba-97dc-50aa0a1dd61f | signoff | AUTHORITY HOLDPOINT
69364a53-2226-4365-b90a-95db596666c6 | section | Post Construction
99e1def4-ca59-43f1-a8cb-f5dec0f2fd0b | checkpoint | 5.01 - PQE
d0f35973-bf8f-52a1-a824-9d37004c6267 | note | Material Test Method Requirement - Asbuilt and RAMM Data
1090b273-c9f5-5d0f-9537-6042b57cac06 | note | Reference Documents - RAMM Update sheet
bc9bc198-ae79-5f9e-a679-a200de1ef063 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
f79655bf-f5a4-5bfd-a4b5-2dbd8d339ded | note | Material Test Frequency - After works complete
9829020b-afbc-52e1-b469-61122eb669dc | note | Target Criteria - RAMM sheet 100% complete and accurate .
56c7e62e-8a19-5778-b4f7-1c87146b3402 | note | Action Point Records Required - RAMM Asset Update sheet
24532aa0-0c2f-5110-ba9a-323b7027ef2f | note | Responsibility - site engineer / Project Engineer/PQE
b5bee41f-b361-484c-8c2c-dff0c3663947 | checkpoint | 5.02 - Lab
39960cf4-5076-52fc-be10-b1b0978d9f36 | note | Material Test Method Requirement - High speed Rutting - Road Roughness
7f72cada-6816-5ff5-aa49-4ef1b56a8828 | note | Reference Documents - CCA DOC
3d53d405-edb6-5445-b2b4-612a9ac36f42 | note | Material Acceptance Criteria (Method) - Laser Profilometer Survey
53bca1be-65bf-59ed-8845-bc36b8a6eaa5 | note | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
741c5def-2719-5cb4-9a2e-da25948d5b44 | note | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
5b3c3025-4dd0-556d-85e1-703875d056ae | note | Target Criteria - High Speed Rutting: > 5mm Report to Designer
52a6f1ad-442a-5719-b127-c8d20469361b | note | Action Point Records Required - Test Record
be4bfb58-7cec-55ef-8234-ab35003709ea | note | Responsibility - site engineer / Project Engineer/PQE
a432b6be-8ad8-4a22-b213-47c4e299bbd0 | checklist | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN
ed2f1c1c-0c72-43e7-869b-c962a807c4ec | section | Subgrade
9f9eb795-3e32-424c-9805-5e2f7e383d76 | checkpoint | 1.01 - Field
83dd20eb-d88d-5cca-9a26-1a35b7431106 | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
d7fec1b2-f63c-5e24-9998-ea9d6ae9de08 | note | Reference Documents - RITS Table 3-20
e5b0912b-5edc-5154-88df-2fa571823835 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
e380152b-ceac-52ee-ae96-d321f79e7ade | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
abf12906-d37d-509d-a431-21cce82c1c23 | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
68729cd6-be26-5338-88ef-5a04f650121c | note | Target Criteria - Confirm design assumptions - Scalar reaches minimum 7 blows/300mm
c86ddecf-f3b4-59de-8f8f-351c88d00dfd | note | Action Point Records Required - Test Record
d7640c3d-951b-57cd-9b88-61d72038490a | note | Responsibility - QA / SE / PE
2d06ac0e-1dad-487e-ae3f-6fa72309abb2 | checkpoint | 1.02 - Field
1e7ab05a-46d4-5e56-b438-b269b7bd0459 | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
ad2aaad3-fbbb-564f-91fd-de2629bd00ee | note | Reference Documents - RITS Table 3-21
ea6e231b-43a3-5a38-b5cf-4be7d15b2bd1 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
a4bbaed3-50c5-584a-a5d2-ee34e01189b7 | note | Material Test Frequency - In centre of undercut or trench Minimum of 1 test per undercut location
bb70b9eb-38c3-56df-a4ee-6bf5ce5976d1 | note | Target Criteria - CIV ≥ 15 or CBR of 20
437eaf52-9bda-5f41-a800-1ebd36ddeb0a | note | Action Point Records Required - Test Record
e89d3361-c686-5036-8991-900d78d9f0d3 | note | Responsibility - QA / SE / PE
4f06fc0a-7392-4c6e-b381-aa5a6086ceb5 | checkpoint | 1.03 - Field
fb7bf29d-3d8f-5073-b0ac-181540de1c68 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
9a72360e-2450-5c09-b14b-bf2ee2c19f66 | note | Reference Documents - RITS Table 3.24
a346496c-67ec-5614-9c7f-d370a061e9e7 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
f8ffc8e8-f876-5da1-86c8-d565f14c9f44 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
a8548cc7-00f5-56d5-a3c9-1f8025d4dedd | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
72a0244b-d623-5155-a787-914fd3e43318 | note | Target Criteria - +0mm/-30m from design or nominated level
db47f28f-5779-575a-a33b-bae4b67b3521 | note | ○ No more than 15mm deviation from a 3m straight edge
4a3524e2-3cb9-522c-a11c-32c5f8785e45 | note | Action Point Records Required - Survey record
610a7e85-942a-52c4-8bcc-2834b66f993c | note | Responsibility - QA / SE / PE
782def2c-3436-4036-9f34-57d16e80f2e5 | checkpoint | 1.04 - Field
6444c82e-1657-557b-88ab-66a6e1d6ffc1 | note | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
7978ee5c-6ee8-56ab-83f0-caf5a7d963a1 | note | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
fd9f1c38-95da-5f6d-98d2-12c75f68d1ce | note | Material Acceptance Criteria (Method) - Manufacturer installation instructions
d3e620fd-5d77-52c0-b69d-7bb2cdcee57f | note | Material Test Frequency - 100% of Surface
f01ad8fe-8dc1-5c8d-8deb-26de06319f86 | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
31ceeba8-10d4-5e46-8f7d-41dafd03f9b0 | note | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
b78c8054-5e6b-5d39-a602-389f4f282c92 | note | Action Point Records Required - Site Record
e925d51a-78b1-5df3-98ab-90f1955232cd | note | Responsibility - QA / SE / PE
7595520e-1d13-47b0-b2a4-ff628b0b6e07 | checkpoint | 1.05 - PQE
408513dd-2693-5790-a61d-dcf6509e556b | note | Material Test Method Requirement - Is the layer closed out?
f7336156-6d4a-5792-9e3b-129e604eac8f | note | Reference Documents - See PQE
0944a583-edc0-5cd6-abe1-9f1a84420820 | note | Material Acceptance Criteria (Method) - See PQE
b0a9b218-b9d7-5b6f-be3c-be7f8488b99c | note | Material Test Frequency - 100% of Surface Prior to placement of material
9124b237-6f47-503f-9eb1-dafba5559857 | note | Target Criteria - PQE Approval
52049364-bb1c-55a3-b523-149984b67a51 | note | ○ All testing record & reviewed as compliant.
f87bf984-58a5-5184-8106-a241a59d6a82 | note | Available Documents:
b92cb638-5127-5d06-8646-7a99c00176a8 | note | ○ Test records
db124d70-023c-5a2f-9ce7-6cc815bee769 | note | ○ Survey records
868007fc-6be4-5abb-a731-be1eaf06e4c4 | note | ○ Hold Point Records
a3d3c43b-578f-520e-ad2f-2936889bb82a | note | Action Point Records Required - Hold Point
4b208ca8-f3ba-5c31-aeab-3a1872cf2a1d | note | Responsibility - SE / PE / PM / PQE
e70dc611-cf89-4b5f-b245-50037ed809fa | signoff | AUTHORITY HOLDPOINT
425b2afd-789c-4183-93dd-83d43ab27697 | section | Subbase
5456715f-f02c-43e2-8d44-68b43100f5ab | checkpoint | 2.01 - PQE
f39b84ed-d56f-5475-a326-5e23ebc854d3 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
e702bd3c-a3a3-5a0b-a4dd-3e245aade11c | note | Reference Documents - Insert Material Testing link
78b0dfa0-085d-5569-935d-1aa8969be135 | note | Material Acceptance Criteria (Method) - See PQE
8dddd834-3b81-5445-a90c-148e96e09b56 | note | Material Test Frequency - Prior to construction commencing
17942e98-3028-5ecd-a4d0-38a609180a16 | note | Target Criteria - Material meets project requirements
0f735402-85b2-52c5-8280-d16bc2334a09 | note | Action Point Records Required - Hold Point
be997440-b8ce-5977-a737-94efe7da529e | note | Responsibility - SE / PE / PM / PQE
cea3c451-5eab-4029-ba9c-41bd4acab313 | signoff | AUTHORITY HOLDPOINT
0b935037-2c8b-48bc-a743-5b553cae0262 | checkpoint | 2.02 - Field
fe437cb5-0b5a-5a37-b7b7-9a267eb20d2c | note | Material Test Method Requirement - Plateau Density Test
3d9bff9f-9010-54d7-bec0-624af08eb4a2 | note | Reference Documents - TNZ B/02: 2005
3449acb9-02c4-5a7f-a146-53f9e00fef23 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
ce739100-9655-57a8-b730-d2b7f4531e90 | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
d6d44070-a443-5b0b-8aa6-e317b881501f | note | Target Criteria - N/A
95e47d95-37c4-5dc8-ba72-7616f35dcb7f | note | Action Point Records Required - Hold Point, Test Record
e47a4c89-8ab4-5479-9b07-bb03869cc768 | note | Responsibility - SE / PE / PM / PQE
44131022-14ae-4e95-b161-0cec3f9193de | signoff | AUTHORITY HOLDPOINT
da2f7e2c-05c5-4431-9990-cd8d01a36bb0 | checkpoint | 2.03 - Field
c4bba904-07bd-59a3-ac20-85c0d8278e40 | note | Material Test Method Requirement - Clegg Hammer
6da8dbcd-ed8e-5dde-b491-73be485d9ff4 | note | Reference Documents - RITS Table 3-21
ba3182e0-5157-5673-8706-cc632b9c02dd | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
7a1dfb6c-0e29-5423-a00d-08160a86abad | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
858ba4ec-090d-57da-be04-b66dd6e43476 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
0a49bce7-8f56-535d-850e-a5f7de783c1e | note | Target Criteria - CIV ≥ 25
5c4ef9b8-36dd-5150-826b-e204b9b9ea0d | note | Action Point Records Required - Test Record
530775b3-4e90-500c-9542-787bccfea5e5 | note | Responsibility - QA / SE / PE
c829c3b2-34ef-41cf-9584-f1d451e639b0 | checkpoint | 2.04 - Field
8ac03dbd-dd94-553b-923d-b85bf8c241e8 | note | Material Test Method Requirement - Compaction NDM Back Scatter
bec9dc1a-98ae-5530-a3c2-354391ae8015 | note | Reference Documents - RITS Table 3-22
1cd50b59-3351-56bc-8459-ac8528cce809 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
208c94ab-7af2-55f9-8534-f6b900d5cf7e | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
a5f04211-0bf8-5093-be97-9bcb5fab281d | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
ec4c4467-690d-51d7-9d46-425badbd717d | note | Target Criteria - Mean ≥ 95 % MDD
52e62f4d-d4bb-53ec-86d5-1a0e278e077f | note | ○ Minimum ≥ 92% MDD
ad0ed00f-e8cf-5f6b-93a0-133b395c4b2d | note | Action Point Records Required - Test Record
de6b53b2-6d82-5f8a-8f02-219a0a289723 | note | Responsibility - QA / SE / PE
d0819259-ea6c-47bd-87f0-587c87dd4df7 | checkpoint | 2.05 - Field
43ef66f2-04c7-5e07-8d51-aa30dff9ee04 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
42629ad7-f119-55b8-baef-4bb2dcf9a383 | note | Reference Documents - RITS Table 3.24
69ac5100-6b33-5127-90a9-436723342f43 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
eb3c0327-f1d9-5a04-b7be-aeef70c041d9 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
fc87979f-ca9b-54fe-9463-8c5e76009e2d | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
0a6bb718-2046-54c7-98c1-04114e2e2a33 | note | Target Criteria - +5mm/-25m from design or nominated level
2dcf72a5-da0c-5e00-b9fb-065d32019736 | note | ○ No more than 15mm deviation from a 3m straight edge
596d7d2b-a181-58f1-9868-4e6692fdd5a3 | note | Action Point Records Required - Survey record
7d8c89f6-f8ee-5ef8-a8a9-c6cd0c614b86 | note | Responsibility - QA / SE / PE
edac930a-3913-41c6-bfa4-ae7bc6eeb24b | checkpoint | 2.06 - PQE
6ff6404e-794d-5cb9-9894-6b15acf7a1f2 | note | Material Test Method Requirement - Is the layer closed out?
e6ed3098-2650-590e-aa69-3bb91f5b40f3 | note | Reference Documents - See PQE
cd0f387c-77c0-5652-8b38-c9bb4f84ce31 | note | Material Acceptance Criteria (Method) - See PQE
d91a534f-f662-5ce7-998c-13b769171479 | note | Material Test Frequency - 100% of Surface Prior to placement of material
a0aaad04-9ed2-5676-b639-67ec2e24d7f0 | note | Target Criteria - PQE Approval
a123d0cb-291c-5f8a-a417-1df986637bcb | note | ○ All testing record & reviewed as compliant.
fdf8007a-2095-5391-bb96-0d7095d96357 | note | Available Documents:
488f7cb5-e622-5db2-b3f2-07c60d3df7df | note | ○ Test records
6141ee7e-9b0d-517c-ad6c-36fd1a1f271d | note | ○ Survey records
0f3ddd01-c70e-5945-8bc3-e30c9c1cf5d0 | note | ○ Hold Point Records
7f82ec50-4ba2-5483-acbf-5b5b7853aa1d | note | Action Point Records Required - Hold Point
44fe665e-5f8e-5478-bd79-b6e95d087157 | note | Responsibility - SE / PE / PM / PQE
e2b9a67d-1f4f-4ac8-910f-2efe129b69bd | signoff | AUTHORITY HOLDPOINT
9ca32040-50ea-458d-b78f-2415f98424a4 | section | Membrane or First Coat Seal
eaaee871-5189-49b4-8e9b-2deaafdea006 | checkpoint | 3.01 - PQE.
829f6a4b-86db-5a27-af40-eea65ee117f1 | note | Material Test Method Requirement - Seal Design
9ed8ad2d-8ee5-5283-9cbe-8fc77093f601 | note | Reference Documents - INSERT SEAL DESIGN
8bf8800c-4299-5b62-9921-b64c8e89f21c | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
8b23908d-5926-5796-b7a5-067fb00ffd70 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
649eef1e-f6fb-5b93-941f-3df1ae9a650f | note | Target Criteria - Meets project requirements
cab5c74d-58b8-5b67-945d-21cb24635e00 | note | Action Point Records Required - Hold Point
64dd4c67-0377-5bf2-8217-131d9efc4d45 | note | Responsibility - SE / PE / PM / PQE / ER
4abb4d0b-7cb0-4b2a-a8fa-8e6f5ad1f929 | signoff | AUTHORITY HOLDPOINT
e432ad2a-0b38-4f24-9ebe-403e664fff16 | checkpoint | 3.02 - PQE
95447a1b-8147-5520-ab33-6b3ad5b6c951 | note | Material Test Method Requirement - Bitumen Sprayer
e46bba72-c4df-58ab-9c85-0331eb693e01 | note | Reference Documents - TNZ P3
65395671-aae0-51c2-8ad1-57fcd12fd05b | note | Material Acceptance Criteria (Method) - Certification provided
bdee1325-51f0-5635-ba61-b57c548443c8 | note | Material Test Frequency - Prior to starting
e82a07a3-3014-59e2-9e02-d3fb335dddf2 | note | Target Criteria - Current E/2 Certificate
1e6169a5-214b-5d80-8ec3-8816b028995f | note | Action Point Records Required - Certificate Sheet
e511e1b3-f838-5317-909a-d074c70c0e3a | note | Responsibility - SE / PE / PM / PQE / Era
2419210d-1321-47c6-a719-36d9ea30e0ea | checkpoint | 3.03 - PQE
a5242764-6ea7-5917-aa17-778da73cdbba | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
5fcdb352-3b2a-5d9d-838e-3b5f90cae371 | note | Reference Documents - Insert Material Testing
0727c617-b7c8-5651-a363-e5369c254735 | note | Material Acceptance Criteria (Method) - See PQE
7f50c619-1db5-55e4-945f-2122688cf992 | note | Material Test Frequency - Prior to construction commencing
b0a47dd6-2ef9-5ee6-abef-71a870ca7e4e | note | Target Criteria - Material meets project requirements
13b67c3f-ed21-5fce-a783-597a7422572e | note | Action Point Records Required - Hold Point
5525912a-a183-5ec3-95f8-807089426e43 | note | Responsibility - SE / PE / PM / PQE
a81bdc02-fc94-47c8-af24-0d6e352fc6b8 | signoff | AUTHORITY HOLDPOINT
c95407b9-e857-411b-9ff6-b3ba4e25c163 | checkpoint | 3.04 - Field
db05c041-a4f7-54bf-ad01-ae50dd18936c | note | Material Test Method Requirement - Preseal Inspection
9a25afdb-5e62-5f1d-aff0-5dc32fd9f138 | note | Reference Documents - TNZ B/02: 2005
40cffd30-bedb-5264-8c73-722f11b701ea | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
4f228b03-6f49-504b-ade2-115a971df52f | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
4c828742-0603-5646-a944-b9b69ea4b2aa | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
5b170bed-0e45-5808-97bb-eabcf5c5c8ba | note | Action Point Records Required - Test Record
c2846382-0350-5b53-8c74-da278ff34af4 | note | Responsibility - FM /QA / SE / PE
0f747620-5f62-416e-9e54-f99f4a969111 | checkpoint | 3.05 - Field
6816269e-f098-5d16-a80d-a8150c56c473 | note | Material Test Method Requirement - Degree of Saturaton
c42d3424-ff07-5d3f-90d8-68e505ba1c09 | note | Reference Documents - TNZ B/02: 2005
64501425-62ca-58aa-9048-18f2a6fbfe4b | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
eb1a163e-0f72-5c39-a13b-5282cd91f33b | note | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
a526c021-ea2f-5100-9100-5c46dd88a474 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
d5985ecc-6e4b-5e2f-bb3b-ad04cb4ad937 | note | Action Point Records Required - Test Record
8a91fec9-503f-5996-95c2-23ff192baab0 | note | Responsibility - QA / SE / PE
2af63280-a66d-4483-943f-3de0882ba2b5 | checkpoint | 3.06 - Field
0f770f35-41de-581c-bb24-1b492b4286ff | note | Material Test Method Requirement - GO/NO GO Survey
8776e696-d184-567c-9552-15320a949307 | note | Reference Documents - Downers processes
ea542827-4ff5-555b-ae1c-78b7ec2851c8 | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
bd290bb4-ce40-5406-abda-95283939a036 | note | Material Test Frequency - Prior to sealing on each site
1e5352f1-db09-56e4-beb9-3cf948f09ad5 | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
e3cf381e-642d-53d0-a9f8-2fbc2cbd8ab8 | note | Action Point Records Required - Survey record
17b85a33-a940-542a-84e2-4208971c822e | note | Responsibility - QA / SE / PE
800b3b3e-b349-4ad7-81a8-07b32aa014cc | checkpoint | 3.07 - Field
1c06b392-9215-5f99-abcb-916696b6fef7 | note | Material Test Method Requirement - Road temp
79e84a91-b784-5c97-bc36-72133bc9765d | note | Reference Documents - TNZ P3:1995.18
4c04e2b0-0e85-5386-b81d-713c4c8ca855 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
027bc837-2e19-5c08-8518-0ed31588a5d6 | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
eda8a95e-0855-50f0-92b8-9ea17bbf95b0 | note | Target Criteria - Air temp >10°C
e3cf7935-bf2e-5ae0-8aba-9525d02b8c58 | note | Action Point Records Required - Spray sheet
9ae2d44c-3f90-5e3f-89db-0fd80aa0b1b7 | note | Responsibility - QA / SE / PE
f411d882-e91a-4a92-847a-896e4d76dc17 | checkpoint | 3.08 - Field
11a6b816-5487-592a-9d9b-0baea9622b31 | note | Material Test Method Requirement - Application Rate
7c0fdbfe-2fd8-52e7-9f51-24de45b5519d | note | Reference Documents - TNZ P/3 : 1995.18
440598d8-88d3-5716-a5f2-d57a5414f1c6 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
565b240f-5598-5055-8bfe-1ff2b19adfcd | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
1ff48aa3-7c33-52e0-84c9-89b6559c0b6f | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
e75ddb50-2a70-5764-9bfa-baa6ac4ba899 | note | Action Point Records Required - Spray Sheet
33474055-c7b4-51d6-8701-ffef804d7c12 | note | Responsibility - QA / SE / PE
38869e7a-1c83-455e-8c7a-7391cdc12047 | checkpoint | 3.09 - Field
249422b6-5cd3-5e32-938b-98ba0d543ef0 | note | Material Test Method Requirement - Chip spread rate
298f15e2-166f-532b-844d-0688bf709a1f | note | Reference Documents - TNZ P3: 1995.21
a717ae2f-5262-5bf5-92d6-2bb46c28131c | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
d28a4e6d-6875-55cf-8308-51baa7182f4e | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
23149d55-6246-510b-96a6-102221922550 | note | Target Criteria - Visual checks meets seal design requirements
b1ae87d4-45ca-571a-8ebb-5e793dce4bd4 | note | Action Point Records Required - Witness Point/Spray sheet
8e3cb14f-4d34-5ac5-a4d7-e4ef11559226 | note | Responsibility - QA / SE / PE
a948f589-5c6f-402c-8f2b-73efca3b4b9d | checkpoint | 3.10 - Field
4655f788-ed72-5638-9f77-e90e93beb65e | note | Material Test Method Requirement - Rolling Checks
cb0672d2-c3fc-54e7-9986-f05a7cbf06c1 | note | Reference Documents - TNZ P3: 1995.22
32dc68b1-523c-5dce-859f-8504c490998f | note | Material Acceptance Criteria (Method) - Sealing Record
c76d2fd3-98d1-5eba-a074-30017d37ebba | note | Material Test Frequency - for each sealing site per day
926ac038-6b3e-5b5c-b834-bcbe44f2792d | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
103bdd56-de3d-5648-9d61-639fd3d535cd | note | Action Point Records Required - Witness Point/Spray sheet
4f4caccc-c454-5f1b-b6e6-6f063351cd11 | note | Responsibility - QA / SE / PE
a178d55d-98cd-493a-8f75-fd0a09cb7919 | checkpoint | 3.11 - Field
ef7525a4-0afb-5db2-a3dc-4941cdb85a0a | note | Material Test Method Requirement - Post Seal Inspection
d39e484a-05e4-5afd-92be-6ca2bf78a622 | note | Reference Documents - TNZ P3: 1995
aac293e9-f2a5-5e97-9bb5-cdaeea9322d0 | note | Material Acceptance Criteria (Method) - Engineers Inspection
67202766-d85d-5b63-a457-3bbde14a9872 | note | Material Test Frequency - After sealing
12054c9f-c12c-5bd1-b91b-11a31e462749 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
61b0f736-2bdc-55d6-b197-5d87fd465e59 | note | Action Point Records Required - Witness Point
5ad7eeb3-fd0c-50c6-84d6-bb0b0ca1ffed | note | Responsibility - QA / SE / PE
d8513920-839d-4b11-8331-944878bdb532 | section | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
cc4cd08d-90a2-45fc-9690-c4900b1330c9 | checkpoint | 4.01 - PQE
03ab5605-7885-554e-a201-e6d618c40a28 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
b617fda2-60d2-5061-8e58-0ba4a4f5327e | note | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
a5eab962-4425-54cd-93ee-5cbf4a66d1c2 | note | Material Acceptance Criteria (Method) - Approved Treatment Design
295f55cd-7474-564d-bf6f-f98e4da5e3c1 | note | Material Test Frequency - Prior to paving works commencing
d87a73da-759b-5418-a927-9089f4c08ace | note | Target Criteria - Treatment Design validation
5e2e04b3-3abc-5297-a5c3-a53af64495fe | note | Action Point Records Required - Hold Point
c2b11687-7b32-5c61-8e0b-2d1a3a9618c5 | note | Responsibility - SE / PE / PM / PQE
92d5b945-eb63-42d7-b67d-ac0ffb9aa9a4 | signoff | AUTHORITY HOLDPOINT
f2dc4bcf-6ae9-4824-9039-4ad569f18586 | checkpoint | 4.02 - Lab
db23a61d-2cd5-5a85-99bb-22580314fa24 | note | Material Test Method Requirement - In-situ mat density calibration cores
f5899597-053c-580d-a588-24fc320ab027 | note | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
4ec42ec8-3ad4-5df4-b102-4e14484b2973 | note | Material Acceptance Criteria (Method) - ASTM D5361
a9625ac0-4146-5a3d-a801-3e5250fd578d | note | Material Test Frequency - One test per 900 t of asphalt plant production
26a770ae-db1a-53b9-b70d-eac3359aa69d | note | Target Criteria - Characteristic value - mix design air void +3% -2%
63bfa68b-e5c5-58e9-8f0c-8050b3fb8454 | note | Action Point Records Required - Hold Point
3d3ce661-0272-5422-86ad-44c9da122e7e | note | Responsibility - SE / PE / PM / PQE
bc8ae5a4-cf0e-417f-921a-d6795049a475 | signoff | AUTHORITY HOLDPOINT
d722bca6-2ad7-46d0-866a-df7b4ee19016 | checkpoint | 4.03 - Lab
87b9a9d5-348b-5de8-986b-0656d2569407 | note | Material Test Method Requirement - Grading (Particle Size Distribution)
9df70da6-06ce-50db-bc0f-748b4bde2095 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
204fc621-f770-5fc6-9435-d918e3bcd6bb | note | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
a2140b49-2157-5faa-923f-690d38c46664 | note | Material Test Frequency - One test per 900 t of asphalt plant production
9c2ec068-edfb-5229-8ffd-b44227c12431 | note | Target Criteria - Tolerance from nominated JMF grading as per
62204bf0-886d-542d-909c-dfea9890bb0d | note | ○ NZTA M10 Table 5.3
e1e9d656-7e1b-5429-84e5-9652a70f4b8b | note | ○ NZTA M27 Table 5.3
6eff57b3-71d8-5fb4-9e9a-06af5d36cb5c | note | ○ TNZ P/11 Table 7.1
591587bc-6572-55d7-a872-22cfb2a6d890 | note | Action Point Records Required - Test record
c337748a-7293-526e-b681-cbf53673c81d | note | Responsibility - SE / PE / PM / PQE
201da1c4-2703-4b7f-9fb5-dbc046b78dcc | checkpoint | 4.04 - Lab
b0aec730-5203-5723-918e-8b643d1c7e8b | note | Material Test Method Requirement - Binder content
8765b322-50ee-5146-9418-c1184db1c76f | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
39e0d41c-78f5-5ad9-8089-4a27a9229593 | note | Material Acceptance Criteria (Method) - ASTM D2172
9280f8ce-d8c4-5665-9eaf-ef6c7a462c44 | note | Material Test Frequency - One test per 900 t of asphalt plant production
c02a3560-da84-5e57-8c93-ffb8dbe48598 | note | Target Criteria - Tolerance on JMF
07381507-3617-5c8f-8811-c61db14c5635 | note | ○ Individual ±0.5 (All)
6dc63d23-9c08-5f95-b77e-ea0136f9330f | note | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
cd7d297f-ee2b-5799-99e3-01488fe61b7c | note | ○ Rolling Average of 3 ±0.4% (PA)
931d136e-e743-58c9-b518-594a9227fc64 | note | Action Point Records Required - Test record
c2a57365-48a4-5fb2-bec2-0aac63ef1b12 | note | Responsibility - SE / PE / PM / PQE
b2e22d94-771c-4cfa-b719-191e2977bb1e | checkpoint | 4.05 - Lab
7188c1f2-0cf9-554b-ae02-772b8b4d98d5 | note | Material Test Method Requirement - Air Voids
326b7412-27b8-558b-9918-fe9b5f710ac1 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
6fe197c2-74d5-5f08-a971-3ccbcb9e6faf | note | Material Acceptance Criteria (Method) - ASTM D3203-22
35f8d412-e184-5d15-90da-a22197199620 | note | Material Test Frequency - One test per 900 t of asphalt plant production
b5b9c78d-ef46-5293-9924-83f0293b8785 | note | Target Criteria - As specified for each mix type
f74061a8-cfe2-5d26-a066-face8f9cc51a | note | Action Point Records Required - Test record
366c71ac-d0c6-5b53-87d1-384b965cb91f | note | Responsibility - SE / PE / PM / PQE
95c8e71f-98ee-49a8-b64f-013b7c0bc45c | checkpoint | 4.06 - Lab
6a0582ec-3f3f-57c8-92e5-529e84bb1650 | note | Material Test Method Requirement - Maximum Theoretical Specific Gravity
decbf91b-bf49-5061-ba65-a89aecbfa08e | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
1a2d1159-2be1-50cd-9ec0-cb45d6710f66 | note | Material Acceptance Criteria (Method) - ASTM D2041
48147a46-ab8c-513e-bb00-7a6b324cae32 | note | Material Test Frequency - One test per 900 t of asphalt plant production
694ec183-8c9d-5377-81bb-6919fc54d39c | note | Target Criteria - Report Value
cdbd5e73-ddda-52e3-87f4-1d65ebc51666 | note | Action Point Records Required - Test record
419a830c-da46-55b8-9c46-c224fc0b873a | note | Responsibility - SE / PE / PM / PQE
c20845c3-ccbd-4bd3-9d97-a96cceddedf7 | checkpoint | 4.07 - Field
88bee2ec-f686-54cb-8a21-a710eaea4f4d | note | Material Test Method Requirement - Load Locate
e83eba02-76ae-525e-8a42-4fe8593bb43b | note | Reference Documents - Downer Procedures
a7e5c555-c3e3-5656-97ab-e5211354f01a | note | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
c2b61529-84fe-5dd1-9489-f757f3fbbd52 | note | – Truck ID/Rego/Driver
3d12f4f6-6c51-500b-9e90-2b088e75b8e1 | note | – Depart Plant Time
f3a4200f-35a4-5681-843a-169e0c04c2ea | note | – Arrive Site Time
fa30dfe7-fe8b-5376-a222-ab03afb05b92 | note | – AC Temp on Arrival
3889a381-b014-5791-b01d-a3654851c667 | note | – Ground Temp on Arrival
f35f0789-dd6f-5b7f-aaba-c803240f27d9 | note | – Tonnage
6ff753f6-f608-5fef-981d-e7b58e895527 | note | – Run Width
e264a5a6-9e3e-51ee-8841-b4cef5c660d7 | note | – Estimated Run Length
76ef0a28-cf11-5c30-952b-3cc4a25996d3 | note | – Calculated Area
86e1ecfd-0888-5a58-8502-c15e5a9b62d6 | note | – Calculated Average Depth
957999f9-3a71-5c95-9845-12ea76885e71 | note | Material Test Frequency - Every Load
a1471619-d002-5875-b006-275c904c152f | note | Target Criteria - All data is collected
43c7f9b4-f67a-5128-b3a1-071fdfca0200 | note | Action Point Records Required - QA Sheet
205820a2-fcfb-52cd-a7f2-e154e377c5e6 | note | Responsibility - QA / SE / PE
25ec27a4-bf7e-498e-8e2b-597462d6a7d3 | checkpoint | 4.08 - Field
e8c1e572-1a70-5a7e-9436-0fe9fe0ef28d | note | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
9e12e809-737c-5b16-abde-69391e490242 | note | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
f537e9b1-a296-5a99-b389-b69f67601a59 | note | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
a75f5fac-3e0f-561a-96ad-731ae697b75b | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
6ac0d290-5410-5171-b58b-fe7f24d5a874 | note | ○ 1 test per 100m per layer length (min 3 / Construction lot)
13840120-5fbf-54e2-9ec1-b3262cc2fb46 | note | Target Criteria - Mat: Mean air voids JMF +3,-2
c10ad175-511d-5405-ba93-c7fb2826e663 | note | ○ Join: Mean air voids JMF +5,-2
9dbd1423-58b6-5e74-bfeb-6eba536ee02b | note | Action Point Records Required - Test record
ee87f9cb-9d28-5739-a3a9-74ab564d6f49 | note | Responsibility - QA / SE / PE
b09cb4f3-be47-4a9f-bcb9-fde89e0ca7ba | checkpoint | 4.09 - Field
4b79e4ff-d168-5290-a19f-a264ef9c3ea3 | note | Material Test Method Requirement - Surface Level- Stringline checks for validation
21f96f03-d5b4-5727-92ab-a473ffe927e1 | note | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2 Downer Procedures
494c2550-74a3-5fcd-99c1-070a451f219b | note | Material Acceptance Criteria (Method) - NZTA M/10
b9ba6700-f771-576e-a527-d1b03f1f2af5 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
ed803c8b-e6b2-5876-9a53-0fea451e1fd5 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
9852a97f-de06-5a8f-9630-1fe235326d55 | note | Target Criteria - +15mm/-5mm from design or nominated level
5596f386-d448-525c-80bc-6c9b3e75bd23 | note | ○ No more than 8mm deviaton from a 3m straight edge
d417b127-4357-51bb-856b-9dbaa11b94b5 | note | Action Point Records Required - Survey record
35e5a2b6-9096-5983-966a-30cf63cbdf13 | note | Responsibility - QA / SE / PE
ca405c39-9409-418c-b38a-d4a8b43c5e39 | checkpoint | 4.10 - Field
cafb8d5f-a482-5f82-bf97-dd530aeff262 | note | Material Test Method Requirement - Post Surfacing Inspection
181f69eb-413d-5164-bf56-126f9a93d99e | note | Reference Documents - CCA Procedures
b3f7922c-5628-5ece-8b2d-80b6dfdb9b6d | note | Material Acceptance Criteria (Method) - Contract Specifications
6b440ce3-7e2d-575d-8ce8-cef9907b6ad9 | note | Material Test Frequency - 100% of site After surfacing (within 5 days)
06b1c1cd-72de-513a-86df-bfad1b259621 | note | Target Criteria - Line marking has been reinstated
575702c4-97df-5b3e-bbb6-405d5b5d1607 | note | ○ All excess material has been removed from site
d7b9f9f6-2d4c-5511-991b-f4e1f580e09f | note | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
05fa6542-c271-58ff-acdc-126e992cc261 | note | Action Point Records Required - Hold Point
92106a43-6019-5f14-ac9a-668b98c858df | note | Responsibility - QA / SE / PE
90cd4623-96f7-49ac-b580-25c47c133a01 | signoff | AUTHORITY HOLDPOINT
1480edf6-8491-4f4b-810a-acc2c2e7a22b | section | Post Construction
ea79340e-bbeb-4705-90db-3922df072186 | checkpoint | 5.01 - PQE
200b8d7f-eb52-555e-81a6-14a8ef9c2ecd | note | Material Test Method Requirement - Asbuilt and RAMM Data
f72a5a35-5a9d-5fa3-ac08-785c2b3e34dd | note | Reference Documents - RAMM Update sheet
997e9c06-cb09-5010-8a31-762138fe1cdf | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
103e55de-c1be-56b9-b5c6-e26003c8fe64 | note | Material Test Frequency - After works complete
568fd26e-add3-5183-abc8-4a569e24df97 | note | Target Criteria - RAMM sheet 100% complete and accurate .
ad4ccd32-1e54-5272-816c-573b6b01e7de | note | Action Point Records Required - RAMM Asset Update sheet
80e4faf6-3e0e-5e5b-9ed1-4802167fa8c4 | note | Responsibility - site engineer / Project Engineer/PQE
60220e8c-2f9c-42db-8b9f-eb5ac4c1f963 | checkpoint | 5.02 - Lab
cf2bd284-6073-5252-b705-00215da3e177 | note | Material Test Method Requirement - High speed Rutting - Road Roughness
86568a45-4e7c-55aa-a3ab-d6c3536961d4 | note | Reference Documents - CCA DOC
8ff5ad7a-f279-571f-9157-60693a2714b1 | note | Material Acceptance Criteria (Method) - Laser Profilometer Survey
dd2c5e16-d01e-5d20-87c5-e837b0c2ddae | note | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
22c10ade-f858-5b6f-874f-bc9a2866cbe0 | note | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
5595abbd-9639-57c2-8ab0-86d03629d0f6 | note | Target Criteria - High Speed Rutting: > 5mm Report to Designer
c175a12d-8a11-57fd-a3b9-2d52c5a47819 | note | Action Point Records Required - Test Record
b1c3ecc6-3fc1-5cd3-8dbc-83f33c2eaa6b | note | Responsibility - site engineer / Project Engineer/PQE