## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - TAC Renewal | itp |  |  |  |  | ITP - TAC Renewal
section | Details
checkpoint | Office
label | Material Test Method Requirement - Weather
label | Material Acceptance Criteria (Method) - Consistent dry weather with no significant rainfall.
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Ground temperature 5˚C min for structural asphalt. 10˚C min for wearing course.
label | Action Point Records required - Hold Point
label | Responsibility - Downer Contract Engineer
holdpoint | AUTHORITY HOLDPOINT
section | 2.00 - Milling
checkpoint | 1.01 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24, NZTA M10:2020 10.1
label | Material Acceptance Criteria (Method) - String line or GPS rover
label | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
label | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
label | Target Criteria - +15mm/-5mm from design or nominated level
label | ○ No more than 8mm deviaton from a 3m straight edge
label | Action Point Records required - QA Sheet
label | Responsibility - Supervisor
checkpoint | 1.02 - Field
label | Material Test Method Requirement - Surface Inspection
label | Reference Documents - NZTA M10:2020 9.2
label | Material Acceptance Criteria (Method) - Visual Inspection
label | Material Test Frequency - 100% of Surface, Prior to paving
label | Target Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping.
label | Action Point Records required - Hold Point
label | Responsibility - Supervisor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Field
label | Material Test Method Requirement - Does the surface pre-treatment meet project requirments?
label | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
label | Material Acceptance Criteria (Method) - Design requirements
label | ○ Visual confirmation after milling
label | ○ NZTA SP-M-032: Step 4 Bond and Seal
label | Material Test Frequency - 100% of Surface, Prior to paving
label | Target Criteria - Is the suggested surface pre-treatment still suitable after inspectiing the milled surface?
label | Action Point Records required - Hold Point
label | Responsibility - Supervisor
holdpoint | AUTHORITY HOLDPOINT
section | 3.00 - Surface pre-treatment Membrane or Chipseal
checkpoint | 2.01 - PQE
label | Material Test Method Requirement - Seal Design
label | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
label | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
label | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
label | Target Criteria - Meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - CCA Project Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing
label | Material Acceptance Criteria (Method) - See PE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - CCA Project Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Field (1)
label | Material Test Method Requirement - Preseal Inspection
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 100% of Surface, Prior to sealing of surface
label | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
label | Action Point Records required - Test Record
label | Responsibility - Supervisor
checkpoint | 2.03 - Field (2)
label | Material Test Method Requirement - Road temp
label | Reference Documents - TNZ P3:1995.18
label | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
label | Material Test Frequency - Once per day of sealing prior to sealing commencing
label | Target Criteria - Air temp >10°C
label | Action Point Records required - Spray sheet
label | Responsibility - Supervisor
checkpoint | 2.03 - Field (3)
label | Material Test Method Requirement - Application Rate
label | Reference Documents - TNZ P/3 : 1995.18
label | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
label | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
label | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
label | Action Point Records required - Spray Sheet
label | Responsibility - Supervisor
checkpoint | 2.03 - Field (4)
label | Material Test Method Requirement - Chip spread rate
label | Reference Documents - TNZ P3: 1995.21
label | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3)
label | ○ Chipsealing in New Zealand (pg 435)
label | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
label | Target Criteria - Visual checks meets seal design requirements
label | Action Point Records required - Witness Point/Spray sheet
label | Responsibility - Supervisor
checkpoint | 2.04 - Field
label | Material Test Method Requirement - Post Seal Inspection
label | Reference Documents - TNZ P3: 1995
label | Material Acceptance Criteria (Method) - Engineers Inspection
label | Material Test Frequency - After sealing
label | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
label | Action Point Records required - Witness Point
label | Responsibility - Downer Contract Engineer
section | 4.00 - DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
checkpoint | 3.01 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Asphalt Design & Material Records
label | ○ NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
label | Material Acceptance Criteria (Method) - Approved Treatment Design
label | Material Test Frequency - Prior to paving works commencing
label | Target Criteria - Treatment Design validation
label | Action Point Records required - Hold Point
label | Responsibility - CCA Project Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02 - Lab
label | Material Test Method Requirement - In-situ mat density calibration cores
label | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
label | Material Acceptance Criteria (Method) - ASTM D5361
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Characteristic value - mix design air void +3% -2%
label | ○ Thickness as per specified nominal depth
label | Action Point Records required - Hold Point
label | Responsibility - Downer Contract Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Lab (1)
label | Material Test Method Requirement - Grading (Particle Size Distribution)
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Tolerance from nominated JMF grading as per NZTA M10 Table 5.3, NZTA M27 Table 5.3, TNZ P/11 Table 7.1
label | Action Point Records required - Test record
label | Responsibility - Downer Contract Engineer
checkpoint | 3.03 - Lab (2)
label | Material Test Method Requirement - Binder content
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D2172
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Tolerance on JMF
label | Action Point Records required - Test record
label | Responsibility - Downer Contract Engineer
checkpoint | 3.03 - Lab (3)
label | Material Test Method Requirement - Air Voids
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D3203-22
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - As specified for each mix type
label | Action Point Records required - Test record
label | Responsibility - Downer Contract Engineer
checkpoint | 3.03 - Lab (4)
label | Material Test Method Requirement - Maximum Theoratical Specific Gravity
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D2041
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Report Value
label | Action Point Records required - Test record
label | Responsibility - Downer Contract Engineer
checkpoint | 3.07 - Field
label | Material Test Method Requirement - Load Locate
label | Reference Documents - Downer Procedures
label | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
label | – Truck ID/Rego/Driver
label | – Depart Plant Time
label | – Arrive Site Time
label | – AC Temp on Arrival
label | – Ground Temp on Arrival
label | – Tonnage
label | – Run Width
label | – Estimated Run Length
label | – Calculated Area
label | – Calculated Average Depth
label | Material Test Frequency - Every Load
label | Target Criteria - All data is collected
label | Action Point Records required - QA Sheet
label | Responsibility - Supervisor
checkpoint | 3.08 -
label | Material Test Method Requirement - Plateau Density Test
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
label | ○ Target to be approved by Engineer
label | Target Criteria - N/A
label | Action Point Records required - Hold Point
label | Responsibility - Downer Contract Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.09 - Field
label | Material Test Method Requirement - NDM Density Testing On-Site, Mat and Joint
label | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
label | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
label | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
label | ○ 1 test per 100m per layer length (min 3 / Construction lot)
label | Target Criteria - Mat: Mean air voids JMF +3,-2
label | ○ Join: Mean air voids JMF +5,-2
label | Action Point Records required - Test Record
label | Responsibility - Supervisor
checkpoint | 3.10 - Field
label | Material Test Method Requirement - Straight Edge
label | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2, Downer Procedures
label | Material Acceptance Criteria (Method) - NZTA M/10
label | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
label | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
label | Target Criteria - No more than 5mm deviation from a 3m straight edge
label | Action Point Records required - Survey record
label | Responsibility - Downer Contract Engineer
checkpoint | 3.11 - Field
label | Material Test Method Requirement - Post Surfacing Inspection and Safety Audit
label | Reference Documents - CCA Procedures
label | Material Acceptance Criteria (Method) - Contract Specifications
label | Material Test Frequency - 100% of site, After surfacing (within 5 days)
label | Target Criteria - Line marking has been reinstated
label | ○ All excess material has been removed from site
label | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
label | Action Point Records required - Survey record
label | Responsibility - CCA Engineer / Downer Contract Engineer
section | 5.00 - Post Construction
checkpoint | 4.01 - PQE
label | Material Test Method Requirement - Asbuilt and RAMM Data
label | Reference Documents - RAMM Update sheet
label | Material Acceptance Criteria (Method) - Asset Management Information Plan
label | Material Test Frequency - After works complete
label | Target Criteria - RAMM sheet 100% complete and accurate .
label | Action Point Records required - RAMM Asset Update sheet
label | Responsibility - Downer Contract Engineer