## ITP-007
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-009
[11 empty] | Revision : 3 | Date : 27/04/2024
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Maribyrnong Rd Tram Track Renewal |  | Water Proofing of Concrete Bridge Decks |  | Name: | Leo Watson | Name: | Jack Wood |  | Name: | Rocky Sam
Contract No: |  | 8B4900 |  | Specifications: Vicroads Specification 691
|  |  |  | Structure / Component: Concrete Bridge Deck |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 27/06/2024 |  | Date : 27/06/2024 |  |  | Date : 27/06/2024
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Submission & Approval of waterproofing materials and procedures. |  | Prior to commencing any waterproofing activity. | Waterproofing systems shall not take place untill the Contractor's proposed materials and procedures and surface preparation in accordance with Section 691.08 and have been reviewed and accepted by the Superintendent. | DTP Section 691.05 | Verify | This ITP signed off | HP* | FH Engineer / Superintendent |  |  | N/A
2 | Construction Works
2.1 | Weather Monitoring |  | Prior to start | Waterproofing systems shall not be applied under any of the following conditions: (a) windy conditions where over spray and/or spatter may be generated. (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane. (c) when the ambient temperature exceeds 35°C or below 10°C, unless specified in writing by the manufacturer. (d) when the humidity exceeds 85% or where it may exceed 85% during the 12 hour curing period. (e) when rain spatter or run-off, including leakage through deck joints may contaminate the surface affecting the adhesion of the substrate. (f) when the substrate is wet or damp, unless the waterproofing system is required to be applied on damp concrete in accordance with clause 691.05 (g) the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C. | DTP Section 691.14 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent |  |  | N/A
2.2 | Trial Application |  |  | A trial application of the waterproofing membrane system shall be conducted on a test area of the actual substrate of not less than 10m2. The test area shall be prepared and membrane applied by the Contractor to satisfy the requirements of clause 691.08, 691.09, 691.14,691.17 and 691.18 | DTP Section 691.16 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent |  |  | N/A
2.3 | Surface Preperation |  | Prior to start | The surface preperation shall be done in accordance with manufacturer's recommendations for the waterproofing membrane system. Concrete surfaces shall be dry, clean, sound and free of dust or loose particles. Weak or loose surface layers shall be removed and repaired in accordance with DTP Section 689. Rough spots shall be removed with an angle grinder. Primer shall be applied in accordance with manufacturer's recommendations and installed by using a brush, mop, broom or spray. Only areas where the waterproofing membrane is to be applied on the same day is to be primed. | DTP Section 691.08 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent / DTP Representative |  |  | N/A
2.3 | Installation of Waterproofing Membrane |  | Where Required | •Waterproofing membrane shall be applied and prepared in accordance with manufacturer's recommendations. •The waterproofing membrane must form a seamless film with uniform thickness and complete coverage. •Coverage of the waterproofing membrane must be continuous over the entire deck area. •Sidelaps shall be 80mm and end laps shall be 120mm to ensure membrane is waterproof, as per manufacturers instructions. •Waterproofing membrane shall not be installed on wet concrete surfaces. •Surface shall be protected against contamination and rain or expected rain if water proofing is not undertaken within 24 hours. | DTP Section 691.09 & 691.10 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Drying and Curing |  | Where Required | •The curing shall adhere to the manufacturer's instructions regarding drying and curing, and overcoating time intervals, for the prevailing weather conditions. | DTP Section 691.13 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Testing |  | Each Lot | Testing shall be conducted in atleast 1m2 test area in accordance with Section 691.17. Testing after Application the bond strength to the substrate shall be tested using aluminium dollies with a minimum diameter of 50mm in accordance with AS1580.408.5. A circular hole cutter of diameter slightly larger than the diameter of the aluminium dolly shall be used, to cut through the preformed waterproofing membrane to the substrate around the dolly. The bond strength shall be greater than 0.75 MPa, seven days after the application and curing process. | DTP Section 691.17 & 691.18 | Test | This ITP signed off | IP | Fulton Hogan Engineer | N/A
2.6 | Post Pour Inspection |  | Each Lot | • Ensure finished surface of waterproofing membrane is of high standard, with a uniform and level surface in accordance with manufacturer specification • Ensure no defects are present in membrane. | DTP Section 691.17 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.