## ITP-007
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-007
[11 empty] | Revision : 3 | Date : 01/07/2024
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Maribyrnong Rd Tram Track Renewal |  | Bridge Concrete Patch Repair |  | Name: | Rocky Sam | Name: |  |  | Name: | Rocky Sam
Contract No: |  | 8B4900 |  | Specifications: Section 689 - Cementitious Patch Repair of Concrete
|  |  |  | Structure / Component: Concrete Bridge Deck |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 01/07/2024 |  | Date : 01/07/2024 |  |  | Date : 01/07/2024
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Submission & Approval of Patch Repair Material Prior to Commencement of Project |  | Prior to first concrete pour | Patch repair material submitted and approved at least 2 weeks prior to first pour. Mix shall be minimum 50MPa. Concrete shall be installed as per manufacturers specifications. | Section 689 | Verify | Email confirmation from Superintendent. | HP* | FH Engineer / Superintendent | N/A |  | N/A
2 | Construction Works
2.1 | Weather Monitoring |  | Prior to start | Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent | Section 689 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent
2.2 | Surface Preperation |  | Prior to start | For all types of patch repair, all defective an delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface. All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed. A 15mm flat face along the edge to be formed around the non-conforming areas by sawcutting/grinding. | Section 689 | Verify | This ITP signed off | IP | Fulton Hogan Engineer / Foreman | N/A |  | N/A
2.3 | Pre-Pour Inspection |  | Prior to start | Superintendent to review the depth of removal of concrete or defective concrete repair and the amount of exposure of steel reinforcement prior to commencement of application of repair materials | Section 689 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent
2.4 | Application of Reinforcing Protection and Substrate-Bonding Coat |  | Prior to pour | All exposed steel reinforcement shall be coated immediately following preparation and cleaning with a primer which forms part of the propreitary repair system to provide immediate protection against coroosion. The steel primer shall be adequately applied to the back of the steel reinforcement where it is fully exposed and where steel bars are tied together. A substrate-bonding coat which also forms part of the proprietary repair system shall be worked into the concrete substrate using a short bristle brush to enhance the bond at the repair interface. | Section 689 | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Pre-pour Inspection |  | Where Required | Reinstatement of prepared areas shall not commence untill: (i) a joint measurement of the repair area by the Superintendent and the Contractor has taken place; (II) evidence that the preparation of the repair area confirms to the requirments and specification (III) the Contractor's quality procedures has been sighted by the Superintendent. | Section 689 | Verify | This ITP signed off | HP | Fulton Hogan Engineer / YT Superintendent
2.1 | Placement of Repair Mortar |  | Each Lot | • Patch repair mortar shall be prepared as per the manufacturer's guidelines. •Patch repair mortar shall be placed within 20 minutes of mixing. -Patrchroc C only suitable for depths 25mm-200mm -Patrchroc GP only suitable for depths 25mm-200mm -Bluecem HE80AG | Section 689 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.11 | Testing |  | Each Lot | Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. The cubes shall be cured for 7 days under laboratory-controlled conditions. Two cubes shall be tested at 7 days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements as specified in Table 689.061. Test cubes shall be made and cured in accordance with AS 1012.8.3 and tested in accordance with AS 1012.9. | Section 689 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A
2.12 | Curing |  | Each pour | Immediately after placement and for seven days thereafter, the repair material shall be cured and protected from drying out and against the harmful effects of water movement and weather, including rain and rapid temperature changes. | Section 689 | Checklist | This ITP signed off, Vibration report, Concrete testing report | IP | Fulton Hogan Engineer | N/A |  | N/A
2.13 | Finishing and Surface Condition |  | Each pour | All surfaces shall match surrounding surface finish by use of steel forms or steel trowel finish. The surface of the concrete repair shall not have cracks of width greater than 0.10 mm measured at the concrete surface nor craze cracking covering a significant area of the repair at the completion of the curing period. | Section 689 | Visual Inspection | This ITP signed off |  |  | N/A |  | N/A
2.14 | Tolerances |  | Each concrete pour | All concrete shall finish true to the dimensions, the following tolerances apply: •Finished level of slab +3,-3mm | Section 689 | Checklist | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.