## Footpath & KC
ITP - Minor Projects
Enabling Works - Footpath, Kerb and Channel, Pram Crossing
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Kerb and Channel
2A | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Scalar | Subgrade CBR > 5 | In process Inspection | Scalar Sheet | Site Engineer
2B | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Clegg | Kerb & Channel to be laid using precast hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CVI > 12 | In process Inspection | Clegg Sheet Photos | Site Engineer
2C | Kerb Setout | QA FORM | TDM Technical Standards - KC0001 | Every site | Site Setout as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | K&C Pre-pour Checklist | Site Engineer / MSQA
2D | Channel Material | QA FORM | TDM Technical Standards - KC0001 | Every site | Concrete Strength 20MPa @28 Days | In process Inspection | Concrete Docket | Site Engineer
2E | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | Photos | Site Engineer
Footpath
3A | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer
3B | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Basecourse - 100mm min. thickness Clegg CIV > 12 | In process Inspection | Clegg Sheet Photos | Site Engineer
3C | Footpath Setout | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Site set out as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | Pre-pour Concrete Sheet Photos | Site Engineer / MSQA
3D | Footpath finishing | QA FORM | TDM Technical Standards - FP0001 | Every site | Concrete Strength 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) Standard Footpath - 100mm thick Heavy Duty - 150mm thick | In process Inspection | Concrete Docket Photos | Site Engineer
4 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | In process Inspection | Photos | Site Engineer
5 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Every site | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | In process Inspection | Nil | Site Engineer
6A | Tactiles /Pram crossing | Visual | TDM Technical Standards - FP006 TDM Technical Standards - FP0010 | Every site | Tactiles set out must be agreed with MSQA Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Warning TGSI tiles should have 100mm concrete slab underneath | Mandatory HOLD POINT - | Photos | Site Engineer / MSQA
6B | Tactile Material | Visual | NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Tactile to be yellow concrete paver slab type - 300x300mmx60mm | In process Inspection | Photos | Site Engineer
6C | Tactile | Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep. | In process Inspection | Photos | Site Engineer
As-builts
7 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As-Built drawings | In Process Inspection | As-built records | Supervisor and Engineer
8 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Daniel Tat | Initial |  |  | Date:
Approving Delegate |  | Daeyoung Jeong | Initial |  |  | Date:

## Traffic Islands
ITP - Generics
Traffic Island
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Every site | Kerb to be laid using precast hand-laid | In process Inspection | FH Concrete QA sheet Photos | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | In process Inspection | Survey Receipt. | Site Engineer
3A | In-Situ Concrete Island | QA FORM | TDM Technical Standards - IS0001 | Each Site | Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CVI > 12 | In process Inspection | Photos | Site Engineer
3B | Stick On Concrete Island | QA FORM | TDM Technical Standards - IS0002 | Each Site | Bonding Agent to be applied on existing surface Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix. Gaps between kerbs shall be no larger that 10mm | In process Inspection | Photos | Site Engineer
4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep Cross Fall of 2% or max rise in centre of 180mm | In process Inspection | FH Concrete QA sheet. Concrete Delivery Dockets | Site Engineer
As-builts
7 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | As-built records | Supervisor and Engineer
7 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  |  | Initial |  |  | Date:
Approving Delegate |  |  | Initial |  |  | Date:

## Standard VX
ITP - Minor Projects
Enabling Works - Vehicle Crossing
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Standard VX
2A | Residential VX | QA FORM | TDM Technical Standards - VX101 - 104 | Each VX | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer
2B | Residential VX | QA FORM | TDM Technical Standards - VX101 - 104 | 4 Cleggs per VX | VX to be laid using on compacted 100mm min GAP40. CVI > 12 | In process Inspection | Clegg Sheet Photos | Site Engineer
2C | Residential VX | QA FORM | TDM Technical Standards - VX101 - 104 | Every VX | Site set out as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | Concrete Pre-pour Checklist | Site Engineer / MSQA
| VX Material | QA FORM | TDM Technical Standards - VX101 - 104 | Every VX | 665 Mesh Required if 4 or more dwellings | In process Inspection | Photos | Site Engineer
2D | VX Material | QA FORM | TDM Technical Standards - VX101 - 104 | Every VX | Concrete Strength 20MPa @28 Days Thickness - 150mm 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) | In process Inspection | Concrete Docket | Site Engineer
2E | Residential VX | QA FORM | TDM Technical Standards - VX101 - 104 | Every VX | Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg | In process Inspection | Photos | Site Engineer
2D | Residential VX | QA FORM | TDM Technical Standards - VX101 - 104 | Every VX | Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg 1m reinstatement on carriageway | In process Inspection | Photos | Site Engineer
3 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | In process Inspection | Photos | Site Engineer
As-builts
4 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP | Every Site | As-Built drawings | In Process Inspection | As-built records | Supervisor and Engineer
5 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Daniel Tat | Initial |  |  | Date:
Approving Delegate |  | Daeyoung Jeong | Initial |  |  | Date:

## Stormwater Drainage
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: |  |  | FH Engineer
|  |  |  | Procedure: | Stormwater Drainage |  | FH Quality Manager
Inspection & Test Plan / Checklist
Job No:
Detailed Location:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols and GPR Report | B4u dig plans & GPR report attached | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per IFC Drawings and design AutoCAD file. | Survey Receipt. | Site Engineer
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards | Manufacturers Data Sheets, Delivery Dockets | Site Engineer
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services. | As-built Drawings. Doc. Review | Site Engineer
7 | Trenching & Excavation | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016) | Prestart RCP
|  | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer
|  | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer
|  | M | Trench Base | Every 10m | Scalar testing | Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2. | Test reports / Construction Photos | Site Engineer
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer
9 | Pipe Position Tolerance | M |  | At any point of pipe |  | Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design. | FH Drainage Line Record, Survey Data. | Site Engineer
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse. | Construction Photos | Site Engineer
Subsoil Construction
13 | Subsoil Material Compliance | H | Ensure Subsoil Drainage pipe complies with TDM RD010 | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | Delivery docket | Site Engineer
|  | H | Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate |  | Visual inspection | Ensure clean drainage aggregate - F2 Sand | Delivery docket | Site Engineer
14 | Trenching | H | Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet. | Photo / subsoil log | Site Engineer
|  | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / subsoil log | Site Engineer
15 | Bedding, pipe installation and Backfill. | W | Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / subsoil log | Site Engineer
|  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
|  | W | Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
| Catchpit Connection | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo | Site Engineer
16 |  | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
17 | As-Built Drawings | W | Red pen marked-up As-Builts of every 'Issued for Construction' | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep.
Comments:
[5 empty] | Signature: |  |  | Date:
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Ducting and Traffic Signals
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: |  |  | FH Engineer
|  |  |  | Procedure: | Traffic Signal Ducting and Pole Erection |  | FH Project Engineer
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | Potholing and traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Ducting
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and first gas permit obtained | This ITP signed | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifications | Survey Records | Site Engineer
|  | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifications | Photos / Engineers approval documentation | Site Engineer
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer
5 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
|  | H | Ensure all concrete used is 20MPa mix | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
6 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing) | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifications | Photos | Site Engineer
6.1 |  | H | Ensure trench is cut in a manner that will ensure ducts are laid at correct depths, grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dip sheet & Photos | Site Engineer
7 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifications | Photos | Site Engineer
7.1 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and Atop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifications | Photos | Site Engineer
7.2 |  | H | As-built Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifications | Survey Records | Site Engineer
8 | Bedding | H | Lay min. 150mm GAP<12 for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifications | Photos | Site Engineer
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifications | Photos | Site Engineer
10 | Traffic signal pole erection | H | Ensure Design engineer as inspected pole locations prior to proceeding | Per pole | Visual Inspection | Sign off by design engineer | Engineer sign off
10.1 |  | H | Ensure Pot hole is as per design with required depths and widths | Per pole | Measure | Consistency with Drawings and Specifications | Dip sheet & Photos
10.2 |  | H | Ensure Poles are plumb and within design tolerances | Per pole | Visual Inspection | Consistency with Drawings and Specifications | Photos
11 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project manager |  |  |  |  | Signature: |  |  | Date:
QA checked By Contract Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design/AT Engineer: |  |  |  |  | Signature: |  |  | Date: