## ITP-003
|  |  | Inspection and Test Plan - Concrete Construction | [7 empty] | Document # ITP-003
Revision : 1
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Spout Creek Bridge Replacement |  | Structural Concrete Construction (Bridge Abutment) |  | Name: | Jarrod Rodrigues | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: |  | DOT33479 |  | Specifications: VicRoads Standard Specification - Section 610, 611 and 614
|  |  |  | Structure / Component: Concrete Construction |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Great Ocean Road |  | Date : | 2024-07-25 | Date : | 2024-07-25 |  | Date : | 2024-08-05
Lot No: | 1 |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.3 | Materials |  | Prior to commencing any activity | The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. This shall include full details of the proposed methods of curing. Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing. Ensure that materials on-site are sufficient for the completion of works. | Design Drawings, VR Section 610 & 611 | Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP | Project Engineer/ Superintendent |  |  | N/A
1.4 | Submission of Preliminary Documentation |  | Prior to commencing any activity | The Contractor shall submit to the Superintendent for review the following: - Full details of the proposed hot or cold weather concreting procedure, not less than two weeks prior to placement of concrete. - Detailed WMS, ITPs, & Checklists for all concrete construction works not less than 4 weeks prior to the placement of concrete. - Full details of the proposed methods of curing, as part of the concrete mix design submission, not less than 4 weeks prior to placement of concrete. | VR Specificaiton 610.17, 610.18 & 610.23 | Document Review | ITP Signed, Submitted Documentation | HP | Project Engineer/ Superintendent |  |  | N/A
2 | Construction Works
2.1 | Survey & Set Out |  | Each Lot | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Design Drawings & Survey Date | Visual inspection | ITP Signed | HP* | Project Engineer |  |  | N/A
2.2 | Placement of Steel Reinforcement |  | Each Lot | Ensure steel reinforcement complies with the relevant specification and design drawings. Reinforcement placement shall be coordinated with formwork erection such that is can be placed to the correct size, location, diameter, number and spacing as shown on the drawings. If required, re-bending of steel reinforcement shall not commence until the procedure has been reviewed and approved by the Superintendent, and shall be witnessed by the Superintendent's representative. Splices in reinforcement shall be made only in the position shown on the drawings or as otherwise approved by the superintendent. Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commmence until the welding procedure has been qualified and reviewed by the Superintendent. Ensure reinforcement to be embedded shall be free of mortar, oil, dirt, rust, grease, paint, tar or any other contaminants. Ensure 70mm cover on all steel reinforcement unless noted otherwise on the design drawings. | VR Section 611 | Visual inspection | ITP Signed | HP | Project Engineer/ Superintendent | N/A |  | N/A
2.3 | Formwork |  | Each Lot | Formwork, including supporting systems, shall be constructed in a fashion that ensures the specified quality of concrete finish is achieved. Forms shall be clean and free of majore surface defects. Formwork shall be constructed and shall be sufficient stiffness to tolerate the rate of concrete placement and high frequency vibration, and shall be of uniform stiffness to avoid causing varying vibration aplitudes over the formwork surfaces during compaction of concrete. All corners shall have 20 x 20 mm fillets or chamfers unless noted otherwise. Formwork shall not be placed in locations where steel reinforcement and other fixtures cannot be inspected and/or will be left open until inspections have been completed. The application of any load shall not proceed until the signed Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewd and accepted by the the Superintendent. | VR Section 614 | Visual inspection | ITP Signed / Certificate of Compliance - Formwork Inspection | HP | Project Engineer |  |  | N/A
2.4 | Placement of Concrete |  | Each Lot | Ensure concrete being used for bored piles complies with the relevant specification and design drawings. Ensure that the forms, reinforcement, any stressing materials and embedments has been checked against the specifciation and design drawings by the Superintendent. Air and concrete temperatures shall be recorded. Concrete shall only be placed under the following conditions: - Air temperature 5 to 35 deg C. - Concrete temperature 10 to 30 deg C. Measured Air Temperature: Measured Concrete Temperature: Concrete shall be placed from a height not exceeding 2m. Concrete pumping shall be used where access is restricted. Prior to the commencement of placing concrete by pumping, the initial discharge of concrete shall be pumped to waste until a consistent workable mix is discharged. In continuous concrete pours the maximum time lag between truck loads on site shall not exceed 25 minutes. | VR Section 608.07 | Visual inspection | ITP Signed | HP | Project Engineer/ Superintendent |  |  | N/A
2.5 | Traceability of Concrete |  | Each Lot | All concrete batches (truckloads) used in the works shall be traceable from the batch plant to its general location in the structure by a unique lot number. | VR Section 610.14 | Visual inspection | ITP Signed, Concrete Delivery Dockets | HP* | Project Engineer | N/A |  | N/A
2.6 | Removal of Formwork |  | Each Lot | Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in VicRoads Table 610.251 have elapsed, after completion of the placing of concrete. | VR Section 610.25 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.7 | Curing |  | Each Lot | Ensure the method and period of curing is in accordance with specifications agreed with the client. The contractor shall ensure that records of temperature monitoring during the curing period are available for review by the Superintendent. Measured Curing Temperature: | VR Section 610.23 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.8 | Dimensional Tolerances |  | Each Lot | Dimensional tolerances shall be checked against the requirements in accordance with specications agreed with the client. The concrete shall be inspected for quality of finish and compliance with the surface class requirements. | VR Section 610.47 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
3 | Quality Control Testing
3.1 | Concrete Testing |  | Prior to commencing any activity | All concrete shall be sampled and tested in accordance with AS 1012. The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard. | VR Section 610.16 | Test Point | ITP Signed | HP* | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.