## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001- Type 2 Rock Beaching | itp |  |  |  |  | ITP-001- Type 2 Rock Beaching
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Prior to the commencement of work, the Contractor shall nominate the source of the proposed materials, supply specified test results and provide a representative sample for approval by the Superintendent.
label | ○ Rock for Type 2 beaching shall consist of field or quarry rock. The rocks shall be uniform in colour.
label | ○ All rocks shall have a mass of between 10kg and 40kg and at least 60% by number shall be over 25kg. Rocks shall be of such size that the layer of beaching is not less than 150mm thick.
label | REFERENCE DOCUMENTS: 713.03
label | INSPECTION/TEST METHOD: Test certificates, material data sheets and health and safety data sheets
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Submission of Safety Documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
label | REFERENCE DOCUMENTS: 713.05
label | INSPECTION/TEST METHOD: Job Safety Sheet, SWMS
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Preparation of Underlying Surface
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock
label | REFERENCE DOCUMENTS: 713.04
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/
date | Date Completed:
checkpoint | 2.2 - Placement of Type 2 Beaching
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Width of joints may vary between 10mm and 60mm, with an average not exceeding 40mm. Level difference between edges of adjacent rocks shall not exceed 40mm. The joint pattern shall be randon and the joints kept free from debris before grouting.
label | REFERENCE DOCUMENTS: 713.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/
date | Date Completed:
checkpoint | 2.3 - Grouting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Grouting with mortar shall be carried out when the air temperature is above 5 deg C and work shall be kept moist for three days after grouting.
label | ○ Joint mortar shall consist of one part portland cement and three parts sand by volume, and be thoroughly mixed with water to produce grout of suitable consistency. Propriety cementitious mortars with equivalent performance may be used if approved by the Superintendent.
label | ○ Grouted rock beaching (Type 2) shall be initially placed on a bed of mortar which infiltrates joints and final grouting shall ensure that mortar is firmly tamped into joints to fill the joints to 20 mm below the general top of beaching level.
label | ○ The joints shall be neatly finished by filling with mortar. The final level of the mortar shall not be within 10 mm of the finished rock surface. Care shall be taken to keep the exposed rock face clean. Brooming of mortar across the face of the rocks will not be permitted.
label | REFERENCE DOCUMENTS: 713.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/
date | Date Completed:
checkpoint | 2.4 - Perimeter and Toe Walls
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete perimeter walls shall be constructed around exposed edges of the beaching. Concrete used for this purpose shall be N20 strength grade complying with Section 703.
label | ○ Toe walls shall be 300 mm wide by 400 mm deep at the front face and reinforced with L8TM trench mesh top and bottom. The upper surface of the toe wall shall slope upwards at either the slope of the rock beaching or the adjacent verge as shown on the drawings. Side walls and other perimeter walls shall be 150 mm wide by 250 mm deep. The top of the walls shall be continuous with the beaching.
label | REFERENCE DOCUMENTS: 713.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-002 - Cast-in-Place Socketed Piles (With Permanent Casing) | itp |  |  |  |  | ITP-002 - Cast-in-Place Socketed Piles (With Permanent Casing)
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
label | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
label | ○ Ensure that materials on-site are sufficient for the completion of works.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Indentification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set Out of Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Data
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Protection of Adjacent Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa.
label | REFERENCE DOCUMENTS: VR Section 608.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Inspection of Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The rock sockets should be constructed in full-time presence of a Geotechnical Engineer who can confirm that the design sub-surface strength parameters are appropriate and provide advice if unexpected conditions are encountered.
label | ○ Following formation of the socket, the pile shall be de‑watered to enable inspection by the Superintendent (or the Contractor’s geotechnical representative in design and construct contracts) of the geology of the sides and base of the socket and to ensure that the base is free of debris.
label | ○ Reinforcement and/or concrete shall not be placed prior to this inspection.
label | REFERENCE DOCUMENTS: VR Section 608.04, Design Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Geotechnical Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Placement of Steel Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
label | ○ Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover.
label | ○ Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings. Ensure 75mm cover to CHS steel casing as denoted on the design drawings.
label | REFERENCE DOCUMENTS: VR Sections 608 & 611 / Design Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Placement of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
label | ○ During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole.
label | ○ Concreting shall be continued until sound concrete appears a minimum of 400mm above the required cut-off level. The pile concrete shall not be cut back to its required level until a mimimum of 24 hours after completion of placement of concrete.
label | ○ Concrete placed under water shall be self compacting concrete (SCC) in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c).
label | ○ The concrete shall be of such consistency, and shall be placed in such a manner, that pockets of air or water or ground materials are not entrapped in the concrete, and the space between the reinforcement and the side walls of the hole are completely filled with compacted concrete.
label | REFERENCE DOCUMENTS: VR Section 608.07 / Design Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Quality Control Testing
checkpoint | 3.1 - Concrete Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
label | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
label | REFERENCE DOCUMENTS: VR Section 610.16
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Pile Integrity Testing
label | FREQUENCY: First six piles followed by every third pile thereafter.
label | ACCEPTANCE CRITERIA: Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. All testing shall be undertaken by a prequalified consultant in accordance with the VR scheme for prequalificaiton and approval of the Superintendent. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing.
label | ○ Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile.
label | REFERENCE DOCUMENTS: VR Section 608.08
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-003 - Construction of Structural Concrete | itp |  |  |  |  | ITP-003 - Construction of Structural Concrete
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. This shall include full details of the proposed methods of curing.
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
label | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
label | ○ Ensure that materials on-site are sufficient for the completion of works.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Submission of Preliminary Documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review the following:
label | – Full details of the proposed hot or cold weather concreting procedure, not less than two weeks prior to placement of concrete.
label | – Detailed WMS, ITPs, & Checklists for all concrete construction works not less than 4 weeks prior to the placement of concrete.
label | – Full details of the proposed methods of curing, as part of the concrete mix design submission, not less than 4 weeks prior to placement of concrete.
label | REFERENCE DOCUMENTS: VR Specificaiton 610.17, 610.18 & 610.23
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Submitted Documentation
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Survey & Set Out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Date
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Placement of Steel Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
label | ○ Reinforcement placement shall be coordinated with formwork erection such that is can be placed to the correct size, location, diameter, number and spacing as shown on the drawings.
label | ○ If required, re-bending of steel reinforcement shall not commence until the procedure has been reviewed and approved by the Superintendent, and shall be witnessed by the Superintendent's representative.
label | ○ Splices in reinforcement shall be made only in the position shown on the drawings or as otherwise approved by the superintendent. Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commmence until the welding procedure has been qualified and reviewed by the Superintendent.
label | ○ Ensure reinforcement to be embedded shall be free of mortar, oil, dirt, rust, grease, paint, tar or any other contaminants.
label | ○ Ensure 70mm cover on all steel reinforcement unless noted otherwise on the design drawings.
label | REFERENCE DOCUMENTS: VR Section 611
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork, including supporting systems, shall be constructed in a fashion that ensures the specified quality of concrete finish is achieved. Forms shall be clean and free of majore surface defects.
label | ○ Formwork shall be constructed and shall be sufficient stiffness to tolerate the rate of concrete placement and high frequency vibration, and shall be of uniform stiffness to avoid causing varying vibration aplitudes over the formwork surfaces during compaction of concrete.
label | ○ All corners shall have 20 x 20 mm fillets or chamfers unless noted otherwise.
label | ○ Formwork shall not be placed in locations where steel reinforcement and other fixtures cannot be inspected and/or will be left open until inspections have been completed.
label | ○ The application of any load shall not proceed until the signed Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewd and accepted by the the Superintendent.
label | REFERENCE DOCUMENTS: VR Section 614
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Placement of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
label | ○ Ensure that the forms, reinforcement, any stressing materials and embedments has been checked against the specifciation and design drawings by the Superintendent.
label | ○ Air and concrete temperatures shall be recorded. Concrete shall only be placed under the following conditions:
label | – Air temperature 5 to 35 deg C.
label | – Concrete temperature 10 to 30 deg C.
textbox | Measured Air Temperature:
textbox | Measured Concrete Temperature:
label | ○ Concrete shall be placed from a height not exceeding 2m. Concrete pumping shall be used where access is restricted. Prior to the commencement of placing concrete by pumping, the initial discharge of concrete shall be pumped to waste until a consistent workable mix is discharged.
label | ○ In continuous concrete pours the maximum time lag between truck loads on site shall not exceed 25 minutes.
label | REFERENCE DOCUMENTS: VR Section 608.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Traceability of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete batches (truckloads) used in the works shall be traceable from the batch plant to its general location in the structure by a unique lot number.
label | REFERENCE DOCUMENTS: VR Section 610.14
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed, Concrete Delivery Dockets
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Removal of Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in VicRoads Table 610.251 have elapsed, after completion of the placing of concrete.
label | REFERENCE DOCUMENTS: VR Section 610.25
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.7 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure the method and period of curing is in accordance with specifications agreed with the client.
label | ○ The contractor shall ensure that records of temperature monitoring during the curing period are available for review by the Superintendent.
textbox | Measured Curing Temperature:
label | REFERENCE DOCUMENTS: VR Section 610.23
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.8 - Dimensional Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Dimensional tolerances shall be checked against the requirements in accordance with specications agreed with the client.
label | ○ The concrete shall be inspected for quality of finish and compliance with the surface class requirements.
label | REFERENCE DOCUMENTS: VR Section 610.47
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 3 - Quality Control Testing
checkpoint | 3.1 - Concrete Testing
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
label | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
label | REFERENCE DOCUMENTS: VR Section 610.16
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-005 - Off-Structure Bored Piles | itp |  |  |  |  | ITP-005 - Off-Structure Bored Piles
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
label | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
label | ○ Ensure that materials on-site are sufficient for the completion of works.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 611
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Indentification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Visual Inpsection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set Out of Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Superintendent shall review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Data
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Protection of Adjacent Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa.
label | REFERENCE DOCUMENTS: VR Section 608.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Inspection of Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforcement/concrete shall not be placed until the pile walls and base have been inspected by the Superintendent to confirm founding materails are of strength to satisfy design assumptions. Concrete to be cast within 24 hrs of acceptance of any pile sockets.
label | REFERENCE DOCUMENTS: VR Section 606.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer /Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Placement of Steel Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
label | ○ Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover.
label | ○ Rag bolts to be pre-assembled and secured at the correct distances and levels prior to placement of concrete.
label | ○ Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 611 & 606.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Placement of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure concrete being used for bored piles complies with the relevant specification and design drawings.
label | ○ Ensure piles are free from loose debris and contaminants prior to placement of concrete.
label | ○ During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole.
label | ○ Piles shall be concreted within 24hrs of completion of the pile excavation and shall be poured with a continuous supply of concrete.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 610 & 606.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer /Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Quality Control Testing
checkpoint | 3.1 - Concrete Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
label | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
label | REFERENCE DOCUMENTS: VR Section 610.16
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Pile Integrity Testing
label | FREQUENCY: First six piles followed by every third pile thereafter.
label | ACCEPTANCE CRITERIA: Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. All testing shall be undertaken by a prequalified consultant in accordance with the VR scheme for prequalificaiton and approval of the Superintendent. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing.
label | ○ Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile.
label | REFERENCE DOCUMENTS: VR Section 606.07
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-008 - Placement of Crushed Rock | itp |  |  |  |  | ITP-008 - Placement of Crushed Rock
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most up-to-date revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and Drawings Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: Cl.812.04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Mix Design Approval
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, ECP, ERA, QMP, SWMS.
label | REFERENCE DOCUMENTS: IFC Drawings EMP, ECP, ERA, QMP, SWMS.
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Layer Thickness
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150mm and the maximum thickness of any subbase layer shall not exceed 200mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: Proof roll each layer
label | ACCEPTANCE CRITERIA: No visible deformation or spinging in presence of Superintendent's representative.
label | ○ Proof rolling plant to comply with requirements of Cl. 173.03.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP/ WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161, VicRoads Spec. Cl.304.11, Cl.304.12
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | FREQUENCY: Every lot, every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial FrequencyTest No. ________- > 97.0%
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed, Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Material Grading - Post Compaction
label | FREQUENCY: Every lot, every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
label | – Class 4: N/A
label | – Class 3 - As per Table 304.101 VR Spec.
label | – Class 2 - As per Table 304.101 - VR Spec.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.11, Table 304.111
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed, Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Plasticity Index - Post Compaction
label | FREQUENCY: Every lot, every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
label | – Class 4: N/A
label | – Class 3: 0 to 10.
label | – Class 2 - 0 to 6.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.11, Table 304.113
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Survey Conformance
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Layer to be finished smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: No point deviation > 8mm from 3m straight edge in any direction.
label | ○ Surface level tolerance: Range x = +6, -10mm.
label | ○ Max S = 10mm
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.071, Table 304.072
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Test Records
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-009 - Cement Treated Crushed Rock Subbase | itp |  |  |  |  | ITP-009 - Cement Treated Crushed Rock Subbase
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for review
label | REFERENCE DOCUMENTS: Cl 812.04, Section 820.04 to 820.09, RC 500.02
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
label | HP
label | RESPONSIBILITY: Project Engineer /Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Materials
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
label | REFERENCE DOCUMENTS: Cl 306.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Moisture Content
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
label | REFERENCE DOCUMENTS: Cl 306.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Jointing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
label | (a) material shall be spread in such a manner as to minimise the number of joints;
label | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: Cl 306.08
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Test Rolling
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | REFERENCE DOCUMENTS: CL 306.09
label | INSPECTION/TEST METHOD:
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.2 - Compaction
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Testing and Acceptance of Compaction
label | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
label | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula:
label | REFERENCE DOCUMENTS: CL 306.09
label | INSPECTION/TEST METHOD: Compaction test and Visual
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.3 - Survey Conformance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
label | (a) Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | (b) Surface Level of Subgrade and Pavement: The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12.
label | ○ Surface level tolerances: Range x = +6, -12mm
label | REFERENCE DOCUMENTS: Cl 306
label | INSPECTION/TEST METHOD: String Sheets
label | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
label | SCP
label | RESPONSIBILITY: Engineer / Superintendent / foreman
date | Date Completed:
checkpoint | 3.4 - Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
label | ○ The surface of each compacted layer shall be kept moist for a period of seven days 1-3 days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | ○ The subbase shall be kept in good order and condition and free from contamination.
label | REFERENCE DOCUMENTS: Cl 306.11
label | INSPECTION/TEST METHOD: Compaction test and Visual
label | RECORD OF CONFORMITY: This ITP signed off;
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-010 - Hot Mix Asphalt | itp |  |  |  |  | ITP-010 - Hot Mix Asphalt
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.14, AS2150 10.1, AS2150 10.3, Completed ITP-008/009
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: VicRoads Spec. 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane.
label | ○ Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.17 (b) & (c), Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.16, Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.3 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: VicRoads Spec 407.20 (a) & (b), Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.6 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: VicRoads Spec. 407.23 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(iv), Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | For layers ≥50mm, if characteristic thickness is:
label | ○ 96.0% or greater Accept lot
label | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.232
label | INSPECTION/TEST METHOD: String Sheet
label | RECORD OF CONFORMITY: Survey Conformance
label | SCP
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-011 - Type B Guardfence Installation | itp |  |  |  |  | ITP-011 - Type B Guardfence Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Drawings Register
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All materials are to be used must be on VicRoads current accepted products list (RDN06-04) and confirm with the detailed design.
label | ○ The contractor shall submit to the Superintendent all test certificates related to the supply of steel for the works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VR Section 708.04 & 708.05
label | INSPECTION/TEST METHOD: HP
label | RECORD OF CONFORMITY: ITP Signed, Certificate of Materials
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Identification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any locations have been identified and marked on site. Ensure any approvals are in place with service providers prior to commencing install.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Witness Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Setout
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Contractor to confirm with the superintendent the required location and length of all guard fence alignments.
label | REFERENCE DOCUMENTS: Design Drawings, VR Section 708.08
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guard fence system to be installed in accordance with design drawings, manufacturer guidelines, and within tolerances set out in VicRoads Standard Section 708.07 (d).
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.5 - End Treatments
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed in accordance with design drawings, manufacturer guidelines, and specifications.
label | REFERENCE DOCUMENTS: Design Drawings, Manufacturer Guidelines, VR Section 708.07.
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.6 - Installation of Delineators
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to supply and fasten delineators on left hand side (red) and right-hand side (yellow).
label | REFERENCE DOCUMENTS: VR Section 708.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 3 - Testing and Quality Control
checkpoint | 3.1 - Submission of Certificate of Compliance (CoC)
label | FREQUENCY: Upon completion of install
label | ACCEPTANCE CRITERIA: Contractor to submit the CoC to the Superintended from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 3.2 - Submission of Material Test Certificate
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Contractor to submit test certificate to superintendent from guard fence supplier.
label | REFERENCE DOCUMENTS: VR Section 708
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-012 - Subsurface Drainage | itp |  |  |  |  | ITP-012 - Subsurface Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, ERA, SWMS
label | REFERENCE DOCUMENTS: QMP, EMP, ECP, ERA, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Placement of no fines concrete
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
label | ○ Geotextiles: Shall comply with Cl 702.06.
label | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: Constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: VicRoads Spec 702.04, 702.05, 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (c )
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.6 - Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: VicRoads Spec 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.8 - CCTV
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09(i)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-013 - Precast Stormwater Drainage | itp |  |  |  |  | ITP-013 - Precast Stormwater Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, TMP, SMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, EMP, ECP, TMP, SMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 19mm sieve.
label | ○ 5%-40% passing 0.075mm.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 37.5mm sieve.
label | ○ 5%-40% passing 0.075mm sieve.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15, Table 701.151
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.4 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding line, levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Place & compact backfill material over pipes
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures.
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: As required/requested
label | ACCEPTANCE CRITERIA: Backfill material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placment of the overlaying layer.
label | ○ Bedding material shall be compacted to refusal using hand held mechnical equipment.
label | ○ Backfill material which will have a nominal size after compaction of 40mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92%.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Inspection of Drainage Lines
label | FREQUENCY: As required/requested
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: 701.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-014 - Kerb and Channel | itp |  |  |  |  | ITP-014 - Kerb and Channel
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, ECP, ERA, QMP, SWMS
label | REFERENCE DOCUMENTS: EMP, ECP, ERA, QMP, SWMS
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
label | REFERENCE DOCUMENTS: AS 1379, 703.07, 703.05, 703.23
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Mix design approval
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY: If Required
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS: 703.18
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS: 703.21
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Reinforcement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Provide SL81 mesh cut to suit width centrally located.
label | REFERENCE DOCUMENTS: Design Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.5 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.6 - Concrete Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS: VicRoads Spec. 703.23
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Finish Surfaces
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Ensure 40mm chamfer as displayed on the design drawings.
label | ○ Concrete to have a neat appearance and uniform colour.
label | REFERENCE DOCUMENTS: Design Drawings, 703.25
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | REFERENCE DOCUMENTS: 703.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.9 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth.
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP