## ITP-005
|  |  | Inspection and Test Plan - Off Structure Bored Piles | [7 empty] | Document # ITP-005
Revision : 1
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Spout Creek Bridge Replacement |  | Construction of Off-Structure Bored Piles |  | Name: | Jarrod Rodrigues | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: |  | DOT33479 |  | Specifications: VicRoads Standard Sections 604, 606, 610 & 611
|  |  |  | Structure / Component: Off-Structure Bored Piles |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Great Ocean Road |  | Date : | 2024-07-31 | Date : | 2024-07-31 |  | Date : | 2024-08-05
Lot No: | 1 |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.3 | Materials |  | Prior to commencing any activity | The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing. Ensure that materials on-site are sufficient for the completion of works. | Design Drawings, VR Section 610 & 611 | Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP | Project Engineer/ Site Foreman |  |  | N/A
2 | Construction Works
2.1 | Indentification of Services |  | Prior to commencing any activity | Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works. | DBYD | Visual Inpsection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Set Out of Piles |  | Each Lot | The Superintendent shall review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Design Drawings & Survey Data | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.3 | Protection of Adjacent Piles |  | Each Lot | No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa. | VR Section 608.05 | Visual Inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.4 | Inspection of Piles |  | Each Lot | Reinforcement/concrete shall not be placed until the pile walls and base have been inspected by the Superintendent to confirm founding materails are of strength to satisfy design assumptions. Concrete to be cast within 24 hrs of acceptance of any pile sockets. | VR Section 606.05 | Visual inspection | ITP Signed | HP | Project Engineer /Superintendent |  |  | N/A
2.5 | Placement of Steel Reinforcement |  | Each Lot | Ensure steel reinforcement complies with the relevant specification and design drawings. Spacers and supports to be placed at intervals less than 2m along cages to ensure minimum cover. Rag bolts to be pre-assembled and secured at the correct distances and levels prior to placement of concrete. Ensure 75mm cover on all reinforcement unless noted otherwise on the design drawings. | Design Drawings, VR Section 611 & 606.06 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.6 | Placement of Concrete |  | Each Lot | Ensure concrete being used for bored piles complies with the relevant specification and design drawings. Ensure piles are free from loose debris and contaminants prior to placement of concrete. During concreting, the outlet of the tremie pipe or pump discharge hose shall be kept a minimum of 2m below the top surface of the concrete at all times. If water is in the socket, the socket shall be backfilled with concrete tremied from the base of the hole. Piles shall be concreted within 24hrs of completion of the pile excavation and shall be poured with a continuous supply of concrete. | Design Drawings, VR Section 610 & 606.06 | Visual inspection | ITP Signed | HP | Project Engineer /Superintendent | N/A |  | N/A
3 | Quality Control Testing
3.1 | Concrete Testing |  | Each Lot | All concrete shall be sampled and tested in accordance with AS 1012. The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard. | VR Section 610.16 | Test Point | ITP Signed | HP* | Project Engineer | N/A |  | N/A
3.2 | Pile Integrity Testing |  | First six piles followed by every third pile thereafter. | Integrity testing shall be carried out in accordance with test methods specifed in AS 2159. Integrity testing shall not be carried out until the concrete has achieved a compressive strength of 25MPa and not before 7 days after casting of the pile. | VR Section 606.07 | Test Point | ITP Signed | HP* | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.