## ITP-013
|  |  | Inspection and Test Plan - Drainage | [7 empty] | Document # ITP-013
Revision : 1 17/06/2022
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by: |  |  | Approved by :
Project: |  | Spout Creek Bridge Replacement |  | Construction of Precast Stormwater Drainage |  | Name: | Jarrod Rodrigues | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: |  | DOT33479 |  | Specifications: VicRoads Specification Section 701
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed: |  |  | Signed:
|  |  |  | Location: Great Ocean Road |  | Date : | 2024-07-31 | Date: | 2024-07-31 |  | Date: | 2024-08-05
Lot No: | 1 |  | Lot Details: | Inshore Drive |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, TMP, SMP, JSEA, SWMS & ITP | QMP, EMP, ECP, TMP, SMP, JSEA, SWMS, ITP | Visual Inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.3 | Precast Materials Inspection |  | Each Delivery | Precast materials have been inspected and fit for purpose and free of defects | 701.04b | Visual Inspection | This ITP signed Receival and Inspection Checklist | IP | Project Engineer | N/A |  | N/A
1.4 | Precast Pipe Compliance |  | Prior to Commencing | Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058 Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2. | VicRoads Spec. Cl.619 Cl. 701.04(a) Cl. 701.04(b)(i) Cl. 705.04(d) Cl. 705.11 AS4058 AS4680 | Document review & Site inspection | Receival & Inspection Checklist Manufacturer cetificate or accreditation | IP | Project Engineer | N/A |  | N/A
1.5 | Bedding material classification |  | Prior to start | Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 19mm sieve. 5%-40% passing 0.075mm. PI = 20 max. | 701.04e Table 701.041 Table 701.042 Table 701.231 | Verify | Test Reports from supplier | TP | Project Engineer | N/A |  | N/A
1.6 | Backfill material Classification |  | Prior to start | Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 37.5mm sieve. 5%-40% passing 0.075mm sieve. PI = 20 max. | 701.04e Table 701.041 Table 701.042 Table 701.231 | Verify | Test Reports from supplier | TP | Project Engineer | N/A |  | N/A
1.7 | Mortar material classification |  | Prior to start | Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa | 610.33 | Verify | Test Reports from supplier | TP | Project Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Set out drainage |  | Prior to excavation | The position of all drainage lines are to be confirmed with the superintendent | Drawings 701.10 | Visual Inspection | ITP Signed | HP | Engineer / Forman & Superintendent |  |  | N/A
2.3 | Excavation (pipes) |  | Each Trench | Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical Depth of trench: • > 100mm below underside of pipe (for pipe width < 1500 mm) • > 200mm below underside of pipe (for pipe width > 1500 mm) | 701.15 Table 701.151 | Visual Inspection | ITP Signed | IP | Site Foreman | N/A |  | N/A
2.4 | Compact base of trench |  | Each Trench | Compacted to refusal using mechanical plant. | 701.1 | Visual Inspection | ITP Signed | IP | Project Engineer | N/A |  | N/A
2.5 | Place bedding material & compact |  | Each Trench | Bedding material shall be compactied to no less than the below thickness: - 100mm under pipes. - 80mm (earth foundation) - 150mm (rock foundation) | 701.19 | Visual Inspection | ITP Signed | IP | Project Engineer | N/A |  | N/A
2.6 | Place pipes |  | Each Line/Pit | Pipes & pits placed as shown on the drawings. No laying to occur until bedding line, levels and compaction requirements have been satisfied | Drawings 701.17 | Visual Inspection | ITP Signed | IP | Project Engineer / Site Foreman | N/A |  | N/A
2.7 | Jointing pipe sections |  | Each Line | Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled | 701.18 | Visual Inspection | ITP Signed | IP | Project Engineer / Site Foreman | N/A |  | N/A
2.8 | Place & compact backfill material over pipes |  | Each lot | Backfill under paved area: - fill trench with selected back fill material to subgrade level Backfill under area not paved: - Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level Loose layer thickness <= 150mm. 1 lot = 150mm layer | 701.14 701.15 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.9 | Repairs to damaged pipes |  | Each damaged pipe | No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25 | 701.31 | Verify | ITP Signed | HP | Engineer / Forman & Superintendent |  |  | N/A
3 | Testing & Completion
3.1 | Compaction and moisture content of backfill & bedding material |  | As required/requested | Backfill material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placment of the overlaying layer. Bedding material shall be compacted to refusal using hand held mechnical equipment. Backfill material which will have a nominal size after compaction of 40mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92%. | 701.2 | Verify | Test Reports | TP | Project Engineer | N/A |  | N/A
3.2 | Inspection of Drainage Lines |  | As required/requested | All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. | 701.3 | Verify | Test Reports | TP | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent