## ITP-003
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-001
Revision : 0
Client: |  | Department of State Growth |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Davey To Macquarie Street Connection - Roadworks |  | Clearing and Grubbing |  | Name: | Mileva Savic | Name: |  |  | Name: | Sam Arnold
Specifications: Specifications Section 201, Contract Specific Clauses, EMP, TMS
Contract No: |  | 3741 |  | Structure / Component: Tree removal, clearing & grubbing |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Davey to Macquarie - CH9768 to CH10240 |  | Date : | 2024-08-05 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Independent QA Verifier | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings & all drawings are the latest revision - Signed onto work pack | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Limits of work |  | Prior to pre commencment inspections | Clearing extents to be marked out as per drawings and ATC's/ RFI's. - Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00. - Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09. - Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.) | Cl 201.03 | Visual inspection | This ITP signed | HP* | Surveyor / Site Engineer / Foreman / Clearing Contractor | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP | PMP, EMP, TMP, SWMS, Work Pack | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Implementation of environmental measures and controls |  | Prior to commencing any activity | Hold Point EMP meets the requirements of the specification and all controls have been implemented as per approved EMP | Project Spec Cl160.24 EMP | Verify | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.4 | Flora and Fauna |  | Prior | Hold Point Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits. | EMP Cl176.I1(c) | Verify | This ITP signed, Vegetation Removal and Clearing Permit | HP | Site Engineer / QAV | N/A
1.5 | Protection of Existing Vegetation |  | Prior to comencement of any work | Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected. If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor. | EMP Cl201.10,Cl160.24, 176.I1 | Visual inspection | Vegetation Removal and Clearing Permit, Tree Protection Plan | IP | Site Engineer / QAV | N/A
1.6 | Cultrual Heritage |  | Prior to removal of vegetation | Hold Point Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones | EMP Cl176.J1(e) | Verify | Vegetation Removal and Clearing Permit, Tree Protection Plan | HP | Site Engineer / QAV | N/A
1.7 | Authorisation for works |  | Prior to commencing works | Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area. Ensure work pack is reviewed & signed | Work Procedure, 160.08 | Verify | This ITP signed, Property Access Approval | HP* | Site Engineer | N/A |  | N/A
1.8 | Utilities |  | Prior to commencing works | DBYD - locate and mark all existing services and confirm clearance from proposed work | DBYD Records, Plan Mark-Ups, Excavation Permit | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
1.9 | Traffic Management |  | Prior to commencing works | Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent. | TMS, TGS, TMP, 160.07 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2 | Clear & Grub
2.1 | Clear and grub trees and vegetation |  | Each Lot | Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property. | Cl201.04 | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.3 | Clear and grub trees and vegetation |  | Each Lot | In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment) | Cl201.05 | Visual inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.4 | Clear and grub trees and vegetation (embankment areas) |  | Each Lot | In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment) In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade | Cl201.05 | Visual inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.5 | Clear and grub trees and vegetation at culvert sites |  | Each Lot | Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings) | Cl201.06 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.6 | Backfill holes |  | After clearing | Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort. | Work Procedure Cl201.05 | Verify | This ITP signed | TP | Site Engineer | N/A |  | N/A
2.7 | Dispose of Trees and vegetation |  | After clearing | All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately. | Cl201.07 | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.8 | Damage to Fencing |  | During Clearing | Immediately repair any damage to fences to a condition at least equal to that before damage |  | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.9 | Salvage of Vegetation |  | During Clearing | Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site. |  | Verify | This ITP signed | IP | Site Engineer | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| QAV | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent/ QAV |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.