## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-001- Clearing and Grubbing | itp |  |  |  |  | DTM-ITP-001- Clearing and Grubbing Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings & all drawings are the latest revision
label | – Signed onto work pack
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Limits of work
label | FREQUENCY: Prior to pre commencment inspections
label | ACCEPTANCE CRITERIA: Clearing extents to be marked out as per drawings and ATC's/ RFI's.
label | ○ Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00.
label | ○ Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09.
label | ○ Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.)
label | REFERENCE DOCUMENTS: Cl 201.03
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Surveyor / Site Engineer / Foreman / Clearing Contractor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, Work Pack
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of environmental measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
label | REFERENCE DOCUMENTS: Project Spec Cl160.24 EMP
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Flora and Fauna
label | FREQUENCY: Prior
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
label | REFERENCE DOCUMENTS: EMP Cl176.I1(c)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Vegetation Removal and Clearing Permit
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Protection of Existing Vegetation
label | FREQUENCY: Prior to comencement of any work
label | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
label | ○ If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
label | REFERENCE DOCUMENTS: EMP Cl201.10,Cl160.24, 176.I1
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
label | IP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
checkpoint | 1.6 - Cultrual Heritage
label | FREQUENCY: Prior to removal of vegetation
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
label | REFERENCE DOCUMENTS: EMP Cl176.J1(e)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Authorisation for works
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area.
label | ○ Ensure work pack is reviewed & signed
label | REFERENCE DOCUMENTS: Work Procedure, 160.08
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Property Access Approval
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.8 - Utilities
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
label | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups, Excavation Permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.9 - Traffic Management
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent.
label | REFERENCE DOCUMENTS: TMS, TGS, TMP, 160.07
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Clear & Grub
checkpoint | 2.1 - Clear and grub trees and vegetation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
label | REFERENCE DOCUMENTS: Cl201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Clear and grub trees and vegetation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
label | REFERENCE DOCUMENTS: Cl201.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Clear and grub trees and vegetation (embankment areas)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
label | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
label | REFERENCE DOCUMENTS: Cl201.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Clear and grub trees and vegetation at culvert sites
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
label | REFERENCE DOCUMENTS: Cl201.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
label | REFERENCE DOCUMENTS: Work Procedure Cl201.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately.
label | REFERENCE DOCUMENTS: Cl201.07
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Damage to Fencing
label | FREQUENCY: During Clearing
label | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.9 - Salvage of Vegetation
label | FREQUENCY: During Clearing
label | ACCEPTANCE CRITERIA: Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
holdpoint | Add Signature