## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | CHK-011-CIV-Material delivery inspection-Precast Pits and HDPE pipe Rev 0 | itp | CHK-011-CIV-Material delivery inspection-Precast Pits and HDPE pipe | af8584e3-9ec9-4fbd-a550-b52eff7a3031
| section | Details
| checkpoint | Referenced Documentation
f3423644-9f6f-574d-82e6-16ecaf29842d | note | Document Title: SBS-Civil-Material delivery inspection-Precast Pits and HDPE pipes
5d5b4f4a-2b4b-5a53-a601-5753b5ed27da | note | ITP Description: Material delivery inspection-Precast Pits and HDPE pipes
83f8bdc6-8b67-5922-a474-e8eb9f3399a3 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c2fe63f1-6128-59ab-894f-3786675da607 | note | Discipline (e.g. CIV/STR/RAIL): Civil
60fc8138-6307-5685-b522-46885e41db5e | note | Revision Number: 0
af6ac555-a15d-5f14-8ef6-63b33fdd8f8d | note | Revision Date: 6/02/2024
517803c3-f23f-5861-9b6f-1b76802b5c96 | note | ITP created by: Hiruni Wickramarathne
470691ed-40fa-593b-bcbc-dc697cc8dc9f | note | ITP approved for use by: Victor Mira
| checkpoint | 1. Delivery Details
a4bb43ea-e95f-5361-960d-5dc3f98768d4 | note | ACCEPTANCE CRITERIA:
8b87451f-1987-5274-9c52-61600581075e | textbox | Enter: Delivery Docket Number:
86b9082a-584c-5b7b-abf9-6e12e6cf92f8 | textbox | Enter: Delivery Date:
81dc5d50-6940-5e00-afb4-87f3664e587c | textbox | Enter: Element ID (s):
b419d3b4-3fc9-5d14-a42e-081ef63d310f | note | Attach: Delivery Docket and packaging Slip
dce49324-ae40-56c9-a096-3652311d78a2 | note | – – – – – – – – – – – – – – – – –
c8c64efe-07be-5f91-9e0a-6632756d6232 | note | METHOD: Document Review, Visual
d1824b32-12f6-5a32-8437-cd1e3d1730e0 | note | – – – – – – – – – – – – – – – – –
65f6f443-242a-53bd-82c8-6d895cb736ff | note | FREQUENCY: Each Delivery
86b6d7d2-b7e9-5c3e-a3f3-ce54240540e0 | note | – – – – – – – – – – – – – – – – –
1807fc1f-1e59-5df8-9611-2b2223637311 | note | CATEGORY: IP
dd8a077e-ac45-59cb-b179-063c55c71203 | note | – – – – – – – – – – – – – – – – –
d07e7776-17b4-5a7b-979c-6714e40f2296 | note | RESPONSIBILITY: PE/SE
e29001ae-9d5e-5076-8dc9-5958715e7bce | note | – – – – – – – – – – – – – – – – –
99dcb95a-dc00-5310-adc9-1481a6c81d37 | note | VERIFYING DOCUMENTS: This Checklist
e844f74c-0ccd-5199-834e-d8ee25111b0e | date | Date Completed:
| checkpoint | 2. Packaging Inspection-Quantity
bd41ca3e-8525-5174-889d-1ebf2304d980 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
57735865-9d3a-5dbf-a161-d616e60f1ec8 | note | – – – – – – – – – – – – – – – – –
3ca5a2cc-7594-5b49-b4e7-730b0ab2799e | note | METHOD: Visual
d24adb49-72cd-5dac-b8f5-5dcb2bb41148 | note | – – – – – – – – – – – – – – – – –
e87e5ecd-d8f5-5029-a905-d646c0b9af0e | note | FREQUENCY: Each Delivery
a076b8f2-bd2e-520e-be90-bacf58c12753 | note | – – – – – – – – – – – – – – – – –
11df2ec1-0890-5e02-8294-1c1f83682594 | note | CATEGORY: IP
e139600f-2741-595a-8cca-9a2c9a59b9bb | note | – – – – – – – – – – – – – – – – –
570fa390-cd6e-5d14-a799-1c1cc38c56f9 | note | RESPONSIBILITY: PE/SE
f9781b8a-3b7c-5e71-97ba-2b3531ee3123 | note | – – – – – – – – – – – – – – – – –
4e278929-b91f-5527-b8a1-81d0f127ddc1 | note | VERIFYING DOCUMENTS: This Checklist
b23b9f52-89fb-5276-8c8a-3e0ac36f52cf | date | Date Completed:
| checkpoint | 3. Packaging Inspection-Delivery Contents
d18f3413-56a7-5f35-bb5d-2c1792292088 | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
e5318dfa-e27f-5363-85f2-d5e528db3d70 | note | – – – – – – – – – – – – – – – – –
85c9aa3b-bf2f-5b2a-a1be-ccbc75543fdf | note | METHOD: Document Review, Visual
57e12a23-76ce-594d-a3a1-72ec8a214ec0 | note | – – – – – – – – – – – – – – – – –
9d3763d5-cc7d-57d8-99dd-211e88d2e6d0 | note | FREQUENCY: Each Delivery
e315e624-7f2c-59f1-afde-488e4795e1f1 | note | – – – – – – – – – – – – – – – – –
14293330-5a76-59ae-8305-a6741db3f332 | note | CATEGORY: IP
c57e86bd-db96-5493-b9fe-fe5fad2514bb | note | – – – – – – – – – – – – – – – – –
9217fd8b-702f-5b68-83e8-7bdb3c972778 | note | RESPONSIBILITY: PE/SE
7f59edbb-e9b0-5d96-a495-d7571ce7cb2c | note | – – – – – – – – – – – – – – – – –
7d6de392-f002-5c0e-bd69-1509d3ac14d6 | note | VERIFYING DOCUMENTS: This Checklist
1050a98b-8ea9-5c07-99a5-52a1e471c386 | date | Date Completed:
| checkpoint | 4. Packaging Inspection-Birth Certificate
705d64bc-8a2a-5c19-825f-5b238a17e7ee | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
463c923e-b01a-558e-9b00-29c8ad825f12 | note | ○ Precast components are to be marked on the birth certificate.
6ea1bb33-5afb-5513-b882-e562ae55ae3a | note | ○ Cast date and lot are to be marked on the birth certificate.
41e510b0-46c9-551e-8b6f-ab2bb4c6a7a8 | note | – – – – – – – – – – – – – – – – –
3459da4a-9b41-5364-ad58-b45b34265f64 | note | METHOD: Document Review
4ee071c0-e2af-5b5a-acf9-50c4ce514214 | note | – – – – – – – – – – – – – – – – –
822672ef-d73a-5e72-bbb6-71b4454d2298 | note | FREQUENCY: Each Delivery
f47f9eb6-5c4a-5d13-91eb-f856fbb2ab12 | note | – – – – – – – – – – – – – – – – –
d7c6659c-ac8d-5959-884a-d6ce8ccb5c2b | note | CATEGORY: IP
0c125d05-b82e-538a-9c49-6900b428bb01 | note | – – – – – – – – – – – – – – – – –
d2106352-718a-5737-b0bd-f28d8d002de9 | note | RESPONSIBILITY: PE/SE
f975fd62-b801-5deb-a170-1110bdf2b0fc | note | – – – – – – – – – – – – – – – – –
2eed8395-1a3f-5474-b2bb-2ef9248d3fb5 | note | VERIFYING DOCUMENTS: This Checklist
184e5cb8-f2ab-5553-b8e0-a699b860df71 | date | Date Completed:
| checkpoint | 5. Packaging Inspection-Transport
d2302e38-6544-526b-a013-e4c6e0292d52 | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
42fc1186-0691-59fa-b1d6-d80d3515fd27 | note | ○ Precast items are protected from damage during the transport
c5b47e72-95aa-5fc9-a7b8-56af505b5d64 | note | – – – – – – – – – – – – – – – – –
b3f11370-d279-528c-ac61-c59a10b74a2c | note | METHOD: Visual
b30d4c73-e228-51e5-9b56-1002806725f5 | note | – – – – – – – – – – – – – – – – –
428e8df7-be4f-5a7c-bd99-167652280f5c | note | FREQUENCY: Each Delivery
738f3b95-49a2-55d0-9f8f-8938f78429f7 | note | – – – – – – – – – – – – – – – – –
a9d571c7-cc5c-5381-a4bb-f62b1c2ce38d | note | CATEGORY: IP
a3d633c2-49b8-5c6a-8f87-90cf884823c5 | note | – – – – – – – – – – – – – – – – –
fb308de7-0289-5d55-999b-97519b1337ab | note | RESPONSIBILITY: PE/SE
dd342786-c509-52b2-9dcf-ec5eb69c0f4c | note | – – – – – – – – – – – – – – – – –
aab64e02-da9d-565c-825e-fbdbd9d6f348 | note | VERIFYING DOCUMENTS: This Checklist
25f42070-5c3e-5023-818c-bd2e91973dd7 | date | Date Completed:
| checkpoint | 6. Fault IDs:
c4235f2e-3c74-5d81-93eb-19a79087f02c | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
f51da19b-68eb-5ec7-a8e8-82ed557e1de5 | note | 1 - Identification markings match the Precast type
e985a98d-11b0-56b6-9540-733676275696 | note | 2 - Precast Pit fabricated as per drawings - inverts size.
d83c9ae6-6e6f-54f3-9497-f41406aa2467 | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
b13318fd-3772-5644-b285-5e4fae462ec9 | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
d762deea-1ea1-5f4d-a6b7-7f8d1445661f | note | 5 - Precast Pits- Inverts coliding.
d40fc15f-6931-5304-91d7-6c13a960f927 | note | 6 - Precast Pits a - Inspect for Cracks.
049cd494-2255-572a-9a95-50e4377d5b23 | note | 7 - Precast Pits - Inspect for Spalling/Damage to concrete surface
38cad2d9-c86e-56a4-8e2b-0da71012d3bc | note | 8 - Precast Pits - Inspect for Exposed Reinforcement.
c22c99c3-7c29-5b82-b82f-c40691700861 | note | 9 - Precast Pits - Inspect for correct Lifting mechanism.
3740203b-908d-5b0e-b3e4-b9ee3fb52ef6 | note | 10 - HDPE pipes-Inspect rubber rings
109d3cd8-924f-5b37-8778-ea3d6752c99b | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
c171ace1-0556-5249-9cf4-ec27def80bad | note | 12 - HDPE pipes - Inspect for any defaults/deformation in the pipe
e23a6b77-e0df-56b1-91a5-6344902bc2b0 | note | – – – – – – – – – – – – – – – – –
0d13640a-1dfa-5d2c-a194-1a68aa9473d6 | note | METHOD: Visual, Measure
a053e48a-de2c-5529-9710-2a06eec23094 | note | – – – – – – – – – – – – – – – – –
a55bfed2-7b5d-53df-9aa7-3d305a773e59 | note | FREQUENCY: Each Delivery
c87d991d-413d-5659-b754-fc2440e81e75 | note | – – – – – – – – – – – – – – – – –
2c5ae821-29fc-556c-b9e8-8e5ee52809a7 | note | CATEGORY: IP
95c5593e-db6c-56cf-a3fe-7802e629eb1a | note | – – – – – – – – – – – – – – – – –
18d238d8-0105-5811-893b-4c52a56b944e | note | RESPONSIBILITY: PE/SE
86cda14b-7321-56cb-b891-e30261eee54e | note | – – – – – – – – – – – – – – – – –
046e99ee-c99c-52e1-a64f-d6c8529b56cb | note | VERIFYING DOCUMENTS: This Checklist
9bd33929-a2fc-508f-8110-8f0ad8fa0005 | date | Date Completed:
| checkpoint | 7. Check for Faults - 1
76600261-3134-577c-842c-30cbbad512a1 | note | REFERENCE: Item 6 on this Checklist
3bae0ab5-e1f5-5524-8ebc-a3cfc7c44056 | note | – – – – – – – – – – – – – – – – –
b874b17c-eb99-5e40-84f7-8cc8c066a869 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
02b5923b-5c41-5955-a088-ec7e37962b38 | textbox | Enter: Pit Identification:
9d7f28c0-4978-5a1b-8225-f1ba991f4f43 | textbox | Enter: Quantity:
7f5fec29-e406-58f8-b8e3-07f66902247a | textbox | Enter: Fault ID if any:
0ad78038-96e9-5ffa-bd7d-5ef5917801c8 | note | – – – – – – – – – – – – – – – – –
07ffd7c0-a3c5-5539-b8bd-7f4b22b0fa8c | note | METHOD: Visual, Measure
03898245-ed4c-56cd-8cb9-e36330a214cd | note | – – – – – – – – – – – – – – – – –
d9e504d2-4852-5cb3-8b57-75862bb2b6e0 | note | FREQUENCY: Each precast type delivered
297f53ef-6c78-5a56-b43b-ca3efd6a3156 | note | – – – – – – – – – – – – – – – – –
da6f58f9-7d08-586e-9d2d-4915e8609fc1 | note | CATEGORY: IP
85d85f9b-fbdd-55a5-9d7c-612f6c8c9f94 | note | – – – – – – – – – – – – – – – – –
9bb8f437-5cde-5e32-9de1-5c50f017f93c | note | RESPONSIBILITY: PE/SE
1480504b-0b48-5ef1-a29d-e97a156b7a5a | note | – – – – – – – – – – – – – – – – –
30f98071-0816-533b-8b55-51d1c1d8fdea | note | VERIFYING DOCUMENTS: This Checklist
eb0f9639-c90b-507a-a1ca-b705ff1964d0 | date | Date Completed:
| checkpoint | 7. Check for Faults - 2
ee62fe60-d35d-514a-8b33-1bfecb1dbdbe | note | REFERENCE: Item 6 on this Checklist
ae45c303-41d2-5d63-8fe9-2454e00e130e | note | – – – – – – – – – – – – – – – – –
07304b29-fc1f-5280-b9ad-1a9b2101baab | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
8d5826ae-5045-52eb-8e86-272fa12686bb | textbox | Enter: Pit Identification:
47c8bdca-4999-5e1c-bb61-009b44e8863b | textbox | Enter: Quantity:
79c7f98e-d4de-5795-a007-a40bc513cd50 | textbox | Enter: Fault ID if any:
fa157429-0ba5-5a7b-b1f6-bf1dfde104e4 | note | – – – – – – – – – – – – – – – – –
2fa4c95b-23c9-58e7-9b4e-e19d1b12b573 | note | METHOD: Visual, Measure
59ca28b1-53c8-5d76-a1f3-07df3d535aba | note | – – – – – – – – – – – – – – – – –
49462a0d-afe8-5159-bd9b-1782a1f42fd5 | note | FREQUENCY: Each precast type delivered
374603f3-4a66-5297-95f9-6dfb28d2702e | note | – – – – – – – – – – – – – – – – –
fe44dca7-a0cc-5cb0-870f-71ad4ee98ec1 | note | CATEGORY: IP
12722d07-1117-5650-a276-a4465c9c0b14 | note | – – – – – – – – – – – – – – – – –
41440912-7389-5ae1-bbac-cdd34254c42c | note | RESPONSIBILITY: PE/SE
dcdc62ba-c501-57d7-9583-c4d473d665b2 | note | – – – – – – – – – – – – – – – – –
0fb2aaae-59b3-50a0-a9cb-17e65dc81855 | note | VERIFYING DOCUMENTS: This Checklist
46aa7d7f-ffe1-5fce-8444-9d15a5e78826 | date | Date Completed:
| checkpoint | 7. Check for Faults - 3
7a8a2a26-77b4-5076-9975-347009e3cbcc | note | REFERENCE: Item 6 on this Checklist
166f390c-4241-543c-9c9c-bb013a62c110 | note | – – – – – – – – – – – – – – – – –
620478a0-1e41-59b2-b7cb-efacd7ab0249 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
e721c376-a058-593d-94fe-d206460f4177 | textbox | Enter: Pit Identification:
39d66ac6-558f-5475-aed7-fbb590fabd25 | textbox | Enter: Quantity:
8df4393b-362c-56c8-bf23-873c92f1bb76 | textbox | Enter: Fault ID if any:
07706f36-b42f-5537-b638-0643b942cb81 | note | – – – – – – – – – – – – – – – – –
8678740b-4383-5e55-9e22-0d39c20bc9c1 | note | METHOD: Visual, Measure
4994ea99-475f-58a7-b566-93cf8a364e3b | note | – – – – – – – – – – – – – – – – –
8ca202c4-20d0-523d-b585-97755d22576a | note | FREQUENCY: Each precast type delivered
2a121cb0-7425-5332-9d53-3fcbbfe56300 | note | – – – – – – – – – – – – – – – – –
9ec33d5b-6736-53f1-88eb-142ee650411e | note | CATEGORY: IP
c79fcead-2f43-5b9b-b80e-fbd20e5e727f | note | – – – – – – – – – – – – – – – – –
a62f0ae1-a80d-53e3-8f4b-2fd0d9ca012f | note | RESPONSIBILITY: PE/SE
4556cea5-0fbd-5e33-8939-a44605fe6730 | note | – – – – – – – – – – – – – – – – –
2636d0af-88f4-5f6a-b2de-bf89f9df556b | note | VERIFYING DOCUMENTS: This Checklist
80bca0d8-7e42-51f0-a5db-c67179e1ed64 | date | Date Completed:
| checkpoint | 7. Check for Faults - 4
213d3c86-6a1b-5474-a7aa-c21b3d59db69 | note | REFERENCE: Item 6 on this Checklist
0d0d8123-e03f-52a6-9ef1-3744169b3350 | note | – – – – – – – – – – – – – – – – –
7f6c02fe-d847-59a1-bd74-dcff7a6727f4 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
f7beff20-23c2-53ff-8c40-1acac1912bd6 | textbox | Enter: Pit Identification:
7966bf0a-8149-5196-8f3a-72df6b96671d | textbox | Enter: Quantity:
6728a277-c9f3-5537-92c3-77ab9d921df6 | textbox | Enter: Fault ID if any:
a1c340d9-5665-5294-bed6-a467f5092ae3 | note | – – – – – – – – – – – – – – – – –
0edea162-430a-5d8a-b637-9a6ac98da5b6 | note | METHOD: Visual, Measure
05400f5b-ddf6-5268-85dd-e1c9ef79f424 | note | – – – – – – – – – – – – – – – – –
d6b33501-5cab-5d8f-bdaa-0f4d8d5247b8 | note | FREQUENCY: Each precast type delivered
ee6a320d-a631-53fc-869c-02fe2fc23f0b | note | – – – – – – – – – – – – – – – – –
4773c645-b17e-5ffb-adef-2b597eb905ac | note | CATEGORY: IP
a1696cc2-78f5-5727-90fa-85f69158b4ce | note | – – – – – – – – – – – – – – – – –
584fd335-d74e-502c-9c1e-17447915c4d7 | note | RESPONSIBILITY: PE/SE
a43710bc-3232-5049-b7ea-769df6382b2b | note | – – – – – – – – – – – – – – – – –
9f1c5844-feac-5926-8ac5-d76be023e6a2 | note | VERIFYING DOCUMENTS: This Checklist
cf43c7ca-a82e-56f4-807b-0218c3ea67f9 | date | Date Completed:
| checkpoint | Final Inspection
fc0d394f-b94f-5505-975d-3c070b424af1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
dfcba24b-0b6b-5aa8-a057-3f871c15cb91 | textbox | Name:
6d367d1a-6079-5d9e-9bd8-28c8f8924fc8 | textbox | Position:
9126cc5c-9de6-5018-b636-cee8bd0a7648 | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation Rev 0 | itp | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation | be43eaff-afb5-44dc-aa1f-9e226838b559
| section | Details
| checkpoint | Referenced Documentation
05bcb1af-b56b-5a71-974c-0e9a167df243 | note | Document Title: CHK-012-CIV-SSB-RSS Walls-Precast Panel installation
314c22f4-f135-5814-88ae-4c7900a4ef17 | note | ITP Description: SSB RSS Walls - Panel installation
5c2f25e1-bec6-5bc3-8ebf-976febb0364c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
b1bd4a56-30c2-50a1-9f2d-64a32c22a6ee | note | Discipline (e.g. CIV/STR/RAIL): CIV
c3f7bb2c-323b-5293-9934-184a5643a0ca | note | Revision Number: 0
504075f4-aad7-5718-a4c9-684c512078f4 | note | Revision Date: 18/3/2024
03830593-2163-5b7a-a93f-252a255e0e79 | note | ITP created by: Victor Mira
80b92985-8d18-5b39-8ccc-00f86f716053 | note | ITP approved for use by: Victor Mira
| checkpoint | 1. Panels-survey set out-Tolerance
35282311-353a-57e9-b5be-ee301c56cfcf | note | REFERENCE: IFC Drawings VR 682.20
f6492370-d092-5fdb-895e-385574f586de | note | – – – – – – – – – – – – – – – – –
e9a38788-f3a4-5565-bff5-2757dea2161d | note | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
47d0d8e6-ca49-5718-a31f-2f58a68477c7 | note | – – – – – – – – – – – – – – – – –
e08e6458-9baa-5054-a2d4-d4a33ed61656 | note | METHOD: Measure
ff8df87d-c057-59a9-9677-810172a3d834 | note | – – – – – – – – – – – – – – – – –
176add7d-1842-5f20-95b5-881f3063e2d3 | note | FREQUENCY: Base course panels
6b8221e2-d952-5d08-bee0-b1482f11da2e | note | – – – – – – – – – – – – – – – – –
2be475a5-d090-5c9a-b62a-064bf1cb8de8 | note | CATEGORY: IP
5a8af662-2a86-509a-9f52-a86956312ba2 | note | – – – – – – – – – – – – – – – – –
d9549b38-ac6d-520d-80ea-d7d37ce9f071 | note | RESPONSIBILITY: Surveyor/PE
e15bdf03-5aa1-5c72-b968-ea75a8f8e318 | note | – – – – – – – – – – – – – – – – –
3a5198eb-2991-5c13-bb01-1b5ec46797b4 | note | VERIFYING DOCUMENTS: This Checklist
ec636b6b-8700-5424-8209-1432b450dcf0 | date | Date Completed:
| checkpoint | 2. Mark-up panel for construction team
82967d01-8a36-52d0-872e-1abdc76f0e85 | note | REFERENCE: Construction Manual
05a6aa71-f7ff-5b22-bf11-1c490d10d9ca | note | – – – – – – – – – – – – – – – – –
64e506c0-89f5-5882-bd0c-ada50e46e842 | note | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
70d11210-dc50-5f75-8486-23407839b9d6 | note | ○ Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
1ff03c31-16b4-5532-8a5a-d47028bec71d | note | – – – – – – – – – – – – – – – – –
026a64de-dceb-5bbb-bebb-f838e67ee0aa | note | METHOD: Visual
f495f419-3f0a-51ff-b93f-708808de5cb0 | note | – – – – – – – – – – – – – – – – –
0644de4e-1f60-5170-ab96-f168d1868fa0 | note | FREQUENCY: Each panel
8ada8656-0ca2-5d19-b619-ce3fa3ae36a7 | note | – – – – – – – – – – – – – – – – –
6607fc1f-c4f5-54cd-ab22-ca0d8ea07ad3 | note | CATEGORY: IP
89a61a37-5af1-5f5c-a797-7b315d6c1574 | note | – – – – – – – – – – – – – – – – –
b3e0b1b9-29cf-57c1-95f2-db1ab46a7137 | note | RESPONSIBILITY: SE
ff598cea-0ee3-5be9-a666-386c0f1d821f | note | – – – – – – – – – – – – – – – – –
b650c1da-3680-564c-b87a-a510f5b2514d | note | VERIFYING DOCUMENTS: This Checklist
7f53c1e7-feae-542e-9603-c3e747f2ae84 | date | Date Completed:
| checkpoint | 3. Panel installation
6308eeac-2092-5856-be52-e724bd2e2d37 | note | REFERENCE: IFC Drawing:, Schedules:
2b485135-a82a-5c4e-bcbc-e075b4485aa3 | note | – – – – – – – – – – – – – – – – –
42e49546-13da-5e3a-8719-dbadeb8feb93 | note | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
223e699c-eaa6-5ad9-b472-e355a4729396 | note | – Check for correct architectural pattern
04c2d140-9dda-5036-ba0d-633ba13c8218 | note | – Check for Weephole Locations
03f7e517-9a6b-5475-838a-f259f5ea895e | note | – Check the 19mm nominal gap to be maintained
4189957a-ffbb-59cb-b122-dd4eed26245a | note | – Check the 1 in 40 slope is to be maintained
2923a843-2326-5be5-9ae4-9351f931a6b2 | note | – – – – – – – – – – – – – – – – –
553e63c9-fd9d-5102-ba4f-4c990745f2bb | note | METHOD: Visual, Measure
0aed1d61-1c72-55fe-9e0c-c10f26f25583 | note | – – – – – – – – – – – – – – – – –
21e44ef2-96b4-5606-9106-cc1cdaca1cd4 | note | FREQUENCY: Each panel
cd2f51d9-533f-56e1-bb46-dff722ba4104 | note | – – – – – – – – – – – – – – – – –
86ee691e-8df7-5f87-8c18-07ea8a43cdf5 | note | CATEGORY: WP
4eb0eb4a-92dd-5921-9d9a-e67343c0b37a | note | – – – – – – – – – – – – – – – – –
b4534345-0d56-5ab8-9b61-ff607a97dbe1 | note | RESPONSIBILITY: SE
e0042898-c33d-5ac8-81d6-a94154bd2169 | note | – – – – – – – – – – – – – – – – –
225eeffc-7aca-5d3a-b234-46cab6f97881 | note | VERIFYING DOCUMENTS: This Checklist
6296a8bc-6ae4-52a1-a2c0-9ffd087f17c0 | date | Date Completed:
| checkpoint | 4. Panel installation-Abutment interfaces
8a949ded-bb76-5203-bd4a-35883ecb7849 | note | REFERENCE: IFC Drawings
225f727b-d35a-528c-94a6-dc5518c4ef72 | note | – – – – – – – – – – – – – – – – –
c2a8bdfe-8cab-5c4e-bc2f-5f1cc4d80e82 | note | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be maintained
e8261631-bd22-5fee-b080-90ecf4adfab2 | note | ○ Where nominated 125mm wide x 6mm thk hot dipped Galvanized plates fixed to abutment wall OR 250x6 Galvanised Folded Plate as per IFC drawings.
cf3ddf46-191b-57f9-b4f7-765d02209c52 | note | ○ 600mm wide BITAC tape installed on the joint
0295b165-e60b-59ab-9e17-c75357dfd018 | note | ○ Galvanised Plate, installed with M16x75mm long Gr.4.6/S
2a9765b8-b55d-56c5-8ada-8ccf18b3f719 | note | ○ For the slip joint location, spcing between panels to be min 25mm.
efe70b07-09fe-5d41-8cce-d9a1db71e413 | note | – – – – – – – – – – – – – – – – –
b04cd623-728c-58bc-99f8-f97fc0d3ee89 | note | METHOD: Measure
c8300c24-f320-51cb-a123-25a2795984e7 | note | – – – – – – – – – – – – – – – – –
46c307f1-d065-506a-b8a6-65f3885bbf19 | note | FREQUENCY: Where applicable
af29307f-5093-52eb-8756-1d8790c383d4 | note | – – – – – – – – – – – – – – – – –
7580e6db-4904-5397-b690-d2cff3241727 | note | CATEGORY: IP
14678039-5602-5625-9591-800e06e8271e | note | – – – – – – – – – – – – – – – – –
511c0a07-210d-5ee9-a594-f3d9f575d31f | note | RESPONSIBILITY: SE/PE
bd8b5a13-d0d7-5b98-a7b6-4e8694b25218 | note | – – – – – – – – – – – – – – – – –
dff3f0a9-58ec-5dd5-8cd7-0e3185b3b378 | note | VERIFYING DOCUMENTS: This Checklist
51bdbf5a-a892-51fa-8de5-f19b26955197 | date | Date Completed:
| checkpoint | 5. Filter fabric -Installation
30662360-8209-5ec4-81cb-f9e5f36c7dc9 | note | REFERENCE: IFC Drawings
c0b2b1b9-19ec-5989-826c-d7b514168a1b | note | – – – – – – – – – – – – – – – – –
da6ee7de-4164-538e-87b0-f62982010ca6 | note | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
fba659fc-2c12-5e7d-865d-bde0c58da3e6 | note | – – – – – – – – – – – – – – – – –
780bc4fe-32b1-5f51-9847-783ea192ffdb | note | METHOD: Visual
e2fc4782-c4fd-5ce8-a949-03e3ac3cfa33 | note | – – – – – – – – – – – – – – – – –
22d7ebb2-119e-5899-8b32-9dbf8a13ac87 | note | FREQUENCY: Each course of panel installation
b3aa2df6-0a60-57cb-90b2-e8ed0409fcc7 | note | – – – – – – – – – – – – – – – – –
43a52030-61b5-51dd-b18f-3b67ede195c5 | note | CATEGORY: IP
a99a15b3-31b9-50bb-b0a8-35062e8ff4e2 | note | – – – – – – – – – – – – – – – – –
fabf06e5-211a-5fb9-b3fe-c66740c7c21a | note | RESPONSIBILITY: SE
0ce1f0c7-cd99-51c3-a394-6a5b2a544b8c | note | – – – – – – – – – – – – – – – – –
ef0797b1-9247-552e-8316-7cc8484d0221 | note | VERIFYING DOCUMENTS: This Checklist
13c4b006-2f77-59c1-b1fd-9471dd35ebca | date | Date Completed:
| checkpoint | 6. Drainage-Strip Drain
b427c354-075d-5abd-b105-b7e0ba91876b | note | REFERENCE: IFC Drawings
58f5bbbd-fd06-5f18-b0e9-d132411f1d6a | note | – – – – – – – – – – – – – – – – –
305a2908-9474-5065-b118-b1df5c726347 | note | ACCEPTANCE CRITERIA: Install 300mm wide vertical strip drain -at every vertical joint between panels in RSS wall.
b1a501fd-5309-55d8-a28d-70913255112d | note | ○ Ensure no gap is formed between strip drain and RSS panels.
d7f5e14f-a1fd-5c62-9a53-b5d6f56cd6fb | note | ○ Strip Drain to be encapsulated by non-woven geotextile with minimum width of 500mm in accordance with VR 682
b899bcd2-c8bd-5cff-a945-b9c377b0de7b | note | – – – – – – – – – – – – – – – – –
89f1483d-ca60-5f9a-b4b8-091de81b127b | note | METHOD: Visual
1ee32909-3623-507e-9845-ddabbce60750 | note | – – – – – – – – – – – – – – – – –
25ec28b1-ca83-521b-a726-e87341ff0932 | note | FREQUENCY: Each course of panel installation
a90566f5-bb76-5023-b23e-73f777256e3c | note | – – – – – – – – – – – – – – – – –
b5c9645b-ee64-5380-988d-ac39ce327143 | note | CATEGORY: IP
a9087e9c-da9c-5899-bded-c19d19f90f92 | note | – – – – – – – – – – – – – – – – –
21b6189f-9aaa-5bae-bcef-20f921ac0bbc | note | RESPONSIBILITY: SE
d0eaa692-76d7-5579-af99-47199724b3b0 | note | – – – – – – – – – – – – – – – – –
ef3f7b60-389b-5f83-86fc-a68910c85210 | note | VERIFYING DOCUMENTS: This Checklist
1b85873d-365c-5931-ba71-ffafa2456732 | date | Date Completed:
| checkpoint | 7. Panel installation-Survey reference points
499a73e5-93fd-53a5-9bf3-f0b905e4e820 | note | REFERENCE: VR 682.21
384e5d43-7dd6-58dc-bf79-1da75f81e984 | note | – – – – – – – – – – – – – – – – –
fca123bf-92d9-5968-ba10-2386311a5319 | note | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
8bc85f5d-c314-5468-96ae-3c987bcddd64 | note | – – – – – – – – – – – – – – – – –
15041c87-691b-5bd2-90c7-b67909137405 | note | METHOD: Visual
5430a93c-e1ef-5087-9b15-924ff6d42f4d | note | – – – – – – – – – – – – – – – – –
7447a8ab-dd3c-5d87-957c-8f9e46313df2 | note | FREQUENCY: Each course of panel installation
d6a327ff-6070-5c66-b9eb-5069eae65306 | note | – – – – – – – – – – – – – – – – –
de66e3d1-1d06-5af2-b821-88638b1d5ab8 | note | CATEGORY: IP
03c2743e-fb21-58b8-a746-7e8c0e861993 | note | – – – – – – – – – – – – – – – – –
adc8c9ed-3498-5a7f-9db3-505951fceee0 | note | RESPONSIBILITY: Surveyor/SE
2fc68bde-115a-5d97-8b7f-d183a1614606 | note | – – – – – – – – – – – – – – – – –
b4bf84f0-12a7-57fa-8891-85027205cfa9 | note | VERIFYING DOCUMENTS: This Checklist
736f350f-ab19-535b-99fd-164239d5a544 | date | Date Completed:
| checkpoint | 8. Traceability of precast units and records
6941c21b-0c69-5d10-823b-9fbcc79c2f55 | note | REFERENCE: VR 620.09
8187dd1d-bf2e-57f4-b410-9f169827cc52 | note | – – – – – – – – – – – – – – – – –
10c47335-e6de-5567-af77-f4010ae2ee63 | note | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
23774d0e-de82-57bb-8d24-e21130a22c33 | note | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
69e1fd82-72a8-5659-93cc-242c9f3e73e0 | note | – – – – – – – – – – – – – – – – –
1ac1d32b-0015-5cf6-8599-cc38a14fd0cb | note | METHOD: Visual
73c2bf58-9129-566d-96f5-233840a8d4a8 | note | – – – – – – – – – – – – – – – – –
3b9e4aad-6b94-5cf9-a4ca-f5dc0d802ba9 | note | FREQUENCY: Each panel
e4f14066-6a4f-5f52-9abd-d318b4f072bd | note | – – – – – – – – – – – – – – – – –
444f3911-f2ad-542d-8a85-85c88d2f76ac | note | CATEGORY: IP
bb07e712-55e3-5fdc-b417-4b8b5a8c92f5 | note | – – – – – – – – – – – – – – – – –
ecacb9ed-6431-581c-aa69-435be6fac318 | note | RESPONSIBILITY: SE/PE
27d90366-e1a6-554b-aa73-19d1c230790a | note | – – – – – – – – – – – – – – – – –
c6031028-01f3-5d1f-8d87-eb70106d1c52 | note | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
7c03c2c9-ac90-5c44-b7f6-cf0bd7720312 | date | Date Completed:
| checkpoint | 9. Panels installation-Conformance Survey
07b326e5-cbc5-5584-b294-1d4f55725be9 | note | REFERENCE: IFC Drawings VR 682.06, VR 682.17, VR 682.20
b3debc78-0a6a-5243-8ac8-fae0d5805ab5 | note | – – – – – – – – – – – – – – – – –
2c2e2f2c-43a8-513b-a5cd-988a4854ce5d | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
88a70efb-5b16-53af-9c93-9f4b544403b5 | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
b8dbe46a-c35a-5476-898e-278ade318d1a | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
412b1942-f533-548b-a0c8-3250480811eb | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
e6323a32-47e2-587f-b5cf-b60741f7cfb9 | note | – The wall level shall not deviate from the specified level by more than ±20mm
f1145391-4016-5cb4-9ed8-3326855f4dc2 | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
bad53cca-a92f-53ca-9032-400cad48261c | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
739a6de6-d9d5-5618-b662-f66b17c5c2bd | note | Attach: Survey Report
b5a5d1ea-7353-5d92-8b9c-1802796b8114 | note | – – – – – – – – – – – – – – – – –
ba45a3e1-7e7a-50c6-9569-21829fd03afc | note | METHOD: Survey, Measure
0bf2a5c6-8e3c-55c0-92a4-6d8405738d50 | note | – – – – – – – – – – – – – – – – –
3f399745-fb1a-5c01-84a6-fe6fd853ab8e | note | FREQUENCY: Each course of panel installation
e39d040f-970f-5891-a6d4-8ccd97da3d13 | note | – – – – – – – – – – – – – – – – –
3d83ab46-937a-5e83-b257-54783ae28ae0 | note | CATEGORY: HP*
3095caa4-5fc3-5154-99c5-5c77b9c29cb3 | note | – – – – – – – – – – – – – – – – –
73786f00-c168-5cdb-85cb-34558fc193d3 | note | RESPONSIBILITY: Surveyor/PE
486d5f38-96d2-5049-96e2-3bd515aa7ca0 | note | – – – – – – – – – – – – – – – – –
4a054169-3638-554f-ba8e-6a4422a48f2c | note | VERIFYING DOCUMENTS: Survey Report
bfee1f38-af2f-5c80-9c8a-0df388cac163 | date | Date Completed:
| checkpoint | Final Inspection
18c3c798-d013-556a-9b6f-1fbfbb5f3512 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
eace2a7d-3544-5833-bd67-cb34a461e93b | textbox | Name:
10b2739b-24fd-55e5-9806-e5b274b802e9 | textbox | Position:
48639596-4cb4-5bda-badc-97d66c05219a | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-013-CIV-SSB-RSS Walls-Fill Placement Rev 2 | itp | CHK-013-CIV-SSB-RSS Walls-Fill Placement | cda7bc59-5f3c-45bd-945d-15d1241d5fc0
| section | Details
| checkpoint | Referenced Documentation
8334ad17-b4fe-5a39-8933-6e2232e47c6f | note | Document Title: CHK-013-CIV-SSB-RSS Walls-Fill Placement
192ab00b-cfcc-51e2-a101-f1f3d4962e75 | note | ITP Description: SSB RSS Walls-Fill Placement
15bf60e5-f731-50e0-94a0-4204a54618a0 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d761d5da-7a1d-5858-95fb-ef8281bd6adb | note | Discipline (e.g. CIV/STR/RAIL): CIV
23ccd149-92c4-500d-b7a4-6ea6a84f0460 | note | Revision Number: 2
9776ccb6-7134-5562-88c3-73c40565baf1 | note | Revision Date: 18/3/2024
c0959d49-e4c7-5c75-845f-9b897816cb40 | note | ITP created by: Victor Mira
d3f4310c-a9b6-5ce4-a53c-b86d46191493 | note | ITP approved for use by: Victor Mira
| checkpoint | 1. Soil reinforcement-Straps
1971b550-2524-53c3-a8c3-205ecf6a1118 | note | REFERENCE: 682.08
1720aa8f-2986-5c24-94b2-70972467b300 | note | – – – – – – – – – – – – – – – – –
aae46a44-873e-5d09-91e0-1802bfc46827 | note | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
9c32d158-5a79-5f82-8d65-34e5885e346b | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
b395dcc8-852a-510b-b857-2791a32860af | note | – – – – – – – – – – – – – – – – –
1319f167-ea43-577f-9594-80d4e4badfed | note | METHOD: Visual
3c4e9bd6-a8c0-5303-82fc-c7591cb4adcd | note | – – – – – – – – – – – – – – – – –
01f6e0b4-d558-5cc6-8ae2-81a3a832fb31 | note | FREQUENCY: Each strap
3e678fd7-057f-59c7-bd95-c8dd16810592 | note | – – – – – – – – – – – – – – – – –
5332a9c1-829d-5f05-a18b-18477c7b7bd3 | note | CATEGORY: IP
3aae7819-e406-5d3d-90f7-5f38c8ac94c0 | note | – – – – – – – – – – – – – – – – –
e0743194-4b2b-5f6a-a9f6-746c0ea936c3 | note | RESPONSIBILITY: SE/PE
eadfc9f0-98d7-5694-a715-1e002f20dda1 | note | – – – – – – – – – – – – – – – – –
1c945a30-f6b3-5c14-9e58-e2a120aa94a8 | note | VERIFYING DOCUMENTS: This Checklist
13933cdc-8d3d-5e81-897e-c7cee194652b | date | Date Completed:
| checkpoint | 2. Soil reinforcement-Straps
09114d5f-052f-52f7-880c-9cce84df5bb3 | note | REFERENCE: Installation manual
36de66df-c4ca-55be-8d72-5e9fe1ad9c63 | note | – – – – – – – – – – – – – – – – –
6fafeadd-798a-5073-add6-6f02170758fd | note | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
ec68a1f1-ceb1-5857-8a43-b61ccf732fd7 | note | – – – – – – – – – – – – – – – – –
c40b65cd-9da7-5b63-8c47-15f11e572f67 | note | METHOD: Visual
2cd4cd8c-15ea-54e4-9e03-20760bf2ecbb | note | – – – – – – – – – – – – – – – – –
4f410dcd-8790-5a56-b251-f2b1b496fc97 | note | FREQUENCY: Each panel
86899828-a9b5-50ee-b315-1b6e942b9490 | note | – – – – – – – – – – – – – – – – –
d7e13b8e-197e-5191-98de-973bb4d15b5c | note | CATEGORY: IP
49f3f0cc-5fcf-519e-b5a7-0dd210176f98 | note | – – – – – – – – – – – – – – – – –
adc3cc69-19a6-5adc-9c01-cc838d34430e | note | RESPONSIBILITY: SE/PE
7f2a8fbd-5bf2-51a9-899a-ac742707a782 | note | – – – – – – – – – – – – – – – – –
085e1d42-6bf6-5edf-9836-ca74cda70925 | note | VERIFYING DOCUMENTS: This Checklist
b372d29a-a1bc-5491-b2df-5c8e6d7b88ed | date | Date Completed:
| checkpoint | 3. Soil reinforcements-Connections
345ea69a-6aad-520c-bcaa-c560a10c2c0a | note | REFERENCE: IFC Drawings, Schedule of lenghts
b1f1a86b-5ef2-58b4-919e-e0762eb9c124 | note | – – – – – – – – – – – – – – – – –
9d24d19e-6a25-5396-ba49-02ec6f53e2e3 | note | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
fc756f05-1d29-59bd-960c-76f4ef2e38ad | note | ○ Bolts are to be snug tight.
6043db55-2229-5c88-9502-925dd5f7cce2 | note | – – – – – – – – – – – – – – – – –
88d0e03c-ef39-5799-b844-17ff8ef95a6a | note | METHOD: Visual
f908145f-4e3e-543a-a376-693f58905eac | note | – – – – – – – – – – – – – – – – –
537cbc9b-8fed-513b-9e0f-e20f3d0c5bb3 | note | FREQUENCY: Each Fill Layer
f19c25d7-d6f5-5f5a-bf0f-0af5fabeda7b | note | – – – – – – – – – – – – – – – – –
e3ee187c-f162-56fb-880c-b439616d6df9 | note | CATEGORY: IP
66f5f8a0-a8fe-5c1a-be9f-b6f13b63f95e | note | – – – – – – – – – – – – – – – – –
332937f0-0030-5892-a127-5076a7d30f1e | note | RESPONSIBILITY: SE/PE
e4f2e383-cacf-54a6-a4f8-dc2919723bc2 | note | – – – – – – – – – – – – – – – – –
35e250f2-b9ec-5f27-bd44-5e7ea21310df | note | VERIFYING DOCUMENTS: This Checklist
5b13cb25-724f-5da7-8451-faaa17c21e58 | date | Date Completed:
| checkpoint | 4. Soil reinforcements-Plan arrangement
0475f369-266a-5525-a412-398859c4c8cd | note | REFERENCE: IFC Drawings Arrangements: VR682.06
6ff97acd-5cf7-5aa1-a513-7fdd934e1eda | note | – – – – – – – – – – – – – – – – –
7e64ca49-ac34-554b-a0d9-bc1727496a71 | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
068c875b-41a3-589d-ad56-e983cd4ae8aa | note | ○ Grid Strips shall not overlapped
b0792032-df35-52f1-99b6-82a1243c7d3e | note | – – – – – – – – – – – – – – – – –
cbea7ff1-d573-5c4c-a8e3-f863910b1ec4 | note | METHOD: Visual
b65a0374-fa3b-5db9-b40f-49fc03a2adc1 | note | – – – – – – – – – – – – – – – – –
fe7657b0-dc53-5971-a987-a39ffb0f2ed2 | note | FREQUENCY: Each fill layer
5ca42f04-e02e-5082-a733-74af66739e4d | note | – – – – – – – – – – – – – – – – –
2ebf0c5b-7426-56b9-aaa2-196ce37f434b | note | CATEGORY: IP
d48a02ac-76c5-538c-9caa-7d88cd7faf73 | note | – – – – – – – – – – – – – – – – –
1b0c7db8-92ac-5176-8b3f-48c104e8b2a5 | note | RESPONSIBILITY: SE/PE
ff8ff4a8-1fc4-50f8-bdda-ef5957330ffb | note | – – – – – – – – – – – – – – – – –
d8c315fd-ff90-53e5-ac76-c210dd6cc097 | note | VERIFYING DOCUMENTS: This Checklist
13548385-bf90-5c78-ba1a-5d6f24aa9d8e | date | Date Completed:
| checkpoint | 5. Soil reinforcements-Plan arrangement
f388bf7d-f388-5c97-ad42-130f75aa2370 | note | REFERENCE: IFC Drawings Arrangements: VR682.06
467ec53c-849a-5c39-a01f-1eb88a2d9c71 | note | – – – – – – – – – – – – – – – – –
f399f7c0-28af-56ba-ac0c-c89602095b60 | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
d9d482ae-2d1b-5d4b-bc7d-3b81ae78e321 | note | ○ RSS used in conjunction with a bridge abutment shall be independent of the bridge structure (i.e. Straps shall not cross pile cap boundary unless noted in IFC)
2b2973d4-d9e2-56c6-abb9-22d2a66ddbea | note | – – – – – – – – – – – – – – – – –
7d6e65ff-04fe-524f-a1d2-d66713140a6f | note | METHOD: Visual
7e9a4d66-886e-5192-960d-e5386ccc0fc6 | note | – – – – – – – – – – – – – – – – –
41898d6f-38f4-586c-9d14-f54112ffc8f7 | note | FREQUENCY: Where applicable
fc222203-8654-59ba-b830-ab795b0865ee | note | – – – – – – – – – – – – – – – – –
f7d90e39-5a4c-5d80-b62c-16bdcd237928 | note | CATEGORY: IP
2323e64d-ae9c-5184-8570-4fda9318ceb1 | note | – – – – – – – – – – – – – – – – –
29389113-36f3-535a-b162-6bb73f284654 | note | RESPONSIBILITY: SE/PE
03b0a87d-2530-5471-95a3-281eb8f1cf61 | note | – – – – – – – – – – – – – – – – –
0af6822b-3f00-5338-bebf-790fc4318ec5 | note | VERIFYING DOCUMENTS: This Checklist
2c27872b-2d59-53ad-b5ed-3c8d9b8cf11e | date | Date Completed:
| checkpoint | 6. Soil reinforcements-vertical deviation
c75cecab-fe77-50ce-ae13-f20bac2997cc | note | REFERENCE: IFC Drawings
ee09c3a9-2fa9-5a0e-86c6-1dd657cc6892 | note | – – – – – – – – – – – – – – – – –
bb4fac1c-932e-531c-a843-395b239d462f | note | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
cba87e6a-f4f8-52e2-bc0a-7552fb1f6092 | note | ○ Avoid clash with drainage as directed in IFC Drawings.
a73e4a4a-5563-5c5f-b97f-14b615805567 | note | – – – – – – – – – – – – – – – – –
73ec3bf6-274c-52b0-8671-92763662edfc | note | METHOD: Measure, Survey
6e730456-f58c-5539-a5c4-eef922f62ae8 | note | – – – – – – – – – – – – – – – – –
b8fa5c4f-d98a-58b0-b57d-5cb29e473711 | note | FREQUENCY: Each fill Layer
3bad7a8d-4f0e-513a-90f7-524362c61296 | note | – – – – – – – – – – – – – – – – –
11af4add-ffc5-5f2e-8e65-9f6c8d5d9a5f | note | CATEGORY: IP
981671b7-aec1-5955-ab3a-f4990a61cb47 | note | – – – – – – – – – – – – – – – – –
a7e6317a-856a-54b5-987f-a9db1a3c622a | note | RESPONSIBILITY: Surveyor/SE
12f0e907-3aff-5da0-b4a4-95d7375cfea2 | note | – – – – – – – – – – – – – – – – –
2c9f5679-a91d-504b-afb8-fa9e4d27a72b | note | VERIFYING DOCUMENTS: This Checklist
99caa4dd-45ce-523c-9ba3-f997f3af0d79 | date | Date Completed:
| checkpoint | 7. Fill placement-Protection of Straps
c04dc4ac-84b2-589f-b658-9cfb8757dc2f | note | REFERENCE: IFC Drawings
9e68b99f-6e61-5ec2-9bc6-f04d8b4a05b3 | note | – – – – – – – – – – – – – – – – –
3ec5546d-f43d-5eee-8832-bbf3be74f8a6 | note | ACCEPTANCE CRITERIA: A minimum of 200mm select fill required to protect reinforcement elements before tracked machines or vehicles are permitted access over soil reinforcement as per dtp specification 682 and ensure stability of the top layer of reinforcement.
2626ce50-c742-5a7b-a852-8b142cc7a7d8 | note | – – – – – – – – – – – – – – – – –
d422a546-bdde-59c7-b4a7-f1e73fbe9e28 | note | METHOD: Measure
238b197a-915f-5d19-9fd9-2ca5672def65 | note | – – – – – – – – – – – – – – – – –
1c54369c-f6dc-5380-8033-3cc5e93de575 | note | FREQUENCY: When applicable
b00dd57f-8be6-5209-b662-6fcedffddc15 | note | – – – – – – – – – – – – – – – – –
79a997fe-796c-5f82-8c81-435916761c6e | note | CATEGORY: IP
69d9a8bb-6b5a-5754-9183-0dd6d2c8f240 | note | – – – – – – – – – – – – – – – – –
f31a1e4f-1e86-54a4-aa22-8d0734476663 | note | RESPONSIBILITY: SE/PE
ce21fafb-02f8-5000-b43c-d65593459795 | note | – – – – – – – – – – – – – – – – –
c05644b9-c828-5173-965d-57ef54075d60 | note | VERIFYING DOCUMENTS: This Checklist
b9a02604-6ec7-5072-887f-d0fa5ece5cad | date | Date Completed:
| checkpoint | 8. Fill-Pacement
ed550cd7-0ccf-555b-87af-6147dc731d0f | note | REFERENCE: 204.10
a4e99d81-2a54-570c-9145-b75ed8ce9ae0 | note | – – – – – – – – – – – – – – – – –
a2cbfe6f-ac2f-5e36-a057-b343f55e77cc | note | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
2f1cab84-2977-5504-bc10-c2390476e304 | note | ○ All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
e1d43eee-ab4d-5abd-a410-d45e66940879 | note | – – – – – – – – – – – – – – – – –
ebe0e150-f199-522a-b1b8-083a9e69896f | note | METHOD: Measure, Visual
1f92fcf1-2a18-50fd-9ac6-dd4ebc786e31 | note | – – – – – – – – – – – – – – – – –
03117531-9c9e-5a76-9e42-2fd25a4d0794 | note | FREQUENCY: Each fill layer
1376e580-a4af-569a-8742-a851429bf309 | note | – – – – – – – – – – – – – – – – –
492d9a9f-1cd4-5007-a088-71ee47e59329 | note | CATEGORY: IP
dd4e710a-5805-5f95-bb6e-a2e7ee5a3727 | note | – – – – – – – – – – – – – – – – –
b5780d96-9707-5cb9-9a11-1a3d045c2394 | note | RESPONSIBILITY: PE/SE
d56d417b-4568-5aa4-8b7e-a51192b5ac7c | note | – – – – – – – – – – – – – – – – –
5f235724-9736-52c0-83eb-0107bb148d3e | note | VERIFYING DOCUMENTS: This Checklist
d8ca780c-0825-52e6-8d1a-802fb47b0764 | date | Date Completed:
| checkpoint | 9. Select backfill-moisture content
34132710-9e7b-5394-b2db-e7f8ab5c7aa2 | note | REFERENCE: IFC Drawings
0308d2b2-f716-5fa3-bf1a-d14b4f9ef2df | note | – – – – – – – – – – – – – – – – –
6d2ec039-45de-57fd-bac8-7abb049002a6 | note | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
fe0f3e4b-1005-54cb-bba2-0ca52da98cdb | note | – – – – – – – – – – – – – – – – –
ffebdb8f-62f6-5d53-8b4c-31fb022cc7c4 | note | METHOD: Measure
ce62cae5-acba-5f16-ad7f-b8e2c257895c | note | – – – – – – – – – – – – – – – – –
89b84252-7d27-58ee-b715-140588b0a024 | note | FREQUENCY: Each Fill Layer
0afec9a6-7e0f-5a04-a312-93d48f11d870 | note | – – – – – – – – – – – – – – – – –
0a18604c-7118-55bb-903f-039a8e71e477 | note | CATEGORY: IP
5ef67f78-4114-5ed5-97f2-a4757aeda1c3 | note | – – – – – – – – – – – – – – – – –
56790dab-bdb6-52c1-b853-dd65c1f6d5ac | note | RESPONSIBILITY: PE/SE
6a07e3d3-d21e-58d7-a5a5-bd16b359204d | note | – – – – – – – – – – – – – – – – –
1213574a-167a-56c8-83de-c6758af58ae2 | note | VERIFYING DOCUMENTS: Attached Test Results
38a2cbea-2da7-599a-8708-002a3a368a65 | date | Date Completed:
| checkpoint | 10. Select backfil - placement
60c9b8ac-7d6b-573d-b81d-02d6767d714b | note | REFERENCE: IFC Drawings
8519e808-1672-5207-9df5-de0ef7628259 | note | – – – – – – – – – – – – – – – – –
c101e411-70e7-56fd-922a-a41bf51a3916 | note | ACCEPTANCE CRITERIA: select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
267e5a9b-6d0a-5c16-9e87-e3a47a5573e5 | note | ○ Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
e2b7fedf-a74f-54e8-a754-bae0a927603b | note | – – – – – – – – – – – – – – – – –
42556010-77d1-5a75-88bb-0a49d71cf924 | note | METHOD: Measure
10d59bef-21a2-574d-9a64-72450f329065 | note | – – – – – – – – – – – – – – – – –
d895951f-ec4d-52dc-87c4-df9d5b6e66ba | note | FREQUENCY: Each Fill Layer
98647c6d-14b9-57f0-865d-4574d86f2446 | note | – – – – – – – – – – – – – – – – –
077dde33-4cd6-5e23-9f8a-56a5d50cbd1f | note | CATEGORY: HP*
7bf34389-c6bc-54fc-8c68-836effe111d5 | note | – – – – – – – – – – – – – – – – –
9ea9baed-3bda-55c9-b9e0-28966f221c4c | note | RESPONSIBILITY: PE/SE
b58ae4ad-62d2-5546-a877-30a14518ffb7 | note | – – – – – – – – – – – – – – – – –
9848d274-8261-5fb4-96c0-16dfcc37981f | note | VERIFYING DOCUMENTS: This Checklist
442c68ea-a2e3-5378-af63-b9013ed4a59e | date | Date Completed:
| checkpoint | 11. Select back fill-reduced frequency
f06467d6-3222-5c3a-9c41-8b2fba43af33 | note | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
81acc552-06a8-56cb-a093-bdff1446bfb9 | textbox | Three Consecutive Lots tested to satisfy this requirement.
5cdde263-04df-59fd-809c-27667f2cdd8d | note | – – – – – – – – – – – – – – – – –
0cef5afc-e833-556b-bb57-4c47bb0c3d6c | note | METHOD: Document review
d81f36ff-9705-5996-87c4-2533ba6e798c | note | – – – – – – – – – – – – – – – – –
5414ac65-f988-5112-860b-3d8802406628 | note | FREQUENCY: Each Fill Layer
25c9a63d-5377-59c1-821a-9952f7bd40e7 | note | – – – – – – – – – – – – – – – – –
54541b95-14b8-5eb0-961b-fea51b9ae51b | note | CATEGORY: IP
1b220a2b-54af-527b-b403-a8b2f2fef022 | note | – – – – – – – – – – – – – – – – –
091ec4d1-5842-56af-9538-02b43506f56e | note | RESPONSIBILITY: Nominated Authority/PE
a2fda2df-ccb8-5b91-a859-22f1048070c7 | note | – – – – – – – – – – – – – – – – –
aa105454-aa30-5a3e-b455-cd69dc220824 | note | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
fcaf36f4-ed8c-593d-812a-96c963ef3b5b | date | Date Completed:
| checkpoint | 12. Select Backfill-Testing frequency-acceptance
ba49a6ef-3a73-58ba-a6bc-13e8af6fe6cc | note | REFERENCE: IFC Drawings VR 204.14, VR 682.16
721c3690-ced7-559a-a54f-d650f16bc1e3 | note | – – – – – – – – – – – – – – – – –
974980ed-3889-589b-90fc-21b0db2dd7f3 | note | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
ce11f76f-5aa9-52b1-be44-d77632e95543 | note | ○ The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
3e9d37b2-4039-5928-a46a-fc99edc4e0d9 | note | Attach: Compaction test results
9af2c3b4-612e-582a-9a57-fa12a5359eb7 | note | – – – – – – – – – – – – – – – – –
cc53f70b-7bbd-523a-91b2-3c6838f2563e | note | METHOD: Measure
e054b0cc-dae6-5e60-976f-7113edb5f3aa | note | – – – – – – – – – – – – – – – – –
b4ff6d72-cc4c-57c2-ac04-e9ef6853a3e4 | note | FREQUENCY: Each Fill Layer or every second layer as agreed
205ef72a-2564-5d02-bbf0-4a7eb419835f | note | – – – – – – – – – – – – – – – – –
4402e821-21c0-5216-ad81-4e3cc100cd78 | note | CATEGORY: HP
001b0b10-4a2e-59f4-a408-f79df209a97e | note | – – – – – – – – – – – – – – – – –
57bcdcaa-e255-5e0a-a020-742f9b1df43b | note | RESPONSIBILITY: Nominated Authority
10105200-e48c-505c-9faf-5ede191ad4ef | note | – – – – – – – – – – – – – – – – –
9fa4c3b9-d993-567f-b222-d82bf324aaf7 | note | VERIFYING DOCUMENTS: Attached Test Results
d9adce36-86fd-587d-a6c6-27f1262029ae | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13. Select backfill - acceptance
79951b2c-477b-5b31-b956-1448f0c1eb1d | note | REFERENCE: VR 204.12
1f6a1623-62d2-5f0a-beab-eae18e3650ee | note | – – – – – – – – – – – – – – – – –
4d32da82-2dd0-546e-b393-d886fd523e7b | note | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
82c118ed-ba95-5f08-9826-94a78c4f171e | note | – – – – – – – – – – – – – – – – –
c8800936-04ac-509c-b899-04cfc6c441c0 | note | METHOD: Visual
abb91a2a-9ae9-56f5-9bc9-89ae177e0eb0 | note | – – – – – – – – – – – – – – – – –
43050042-1f0f-5623-ae91-67c02be27816 | note | FREQUENCY: Every Fill Layer
913c6ef8-34cf-5f2c-b735-27b13765a1e1 | note | – – – – – – – – – – – – – – – – –
324fdd87-83ec-5a14-8ed9-97f19790dcc0 | note | CATEGORY: HP
5e3e9063-f25b-58f7-930c-d5d4e5175c71 | note | – – – – – – – – – – – – – – – – –
cb21dde2-09c3-58bf-8b1a-db922b004e02 | note | RESPONSIBILITY: Nominated Authority
8d675e83-acb9-5c35-97c7-7b935007f4e2 | note | – – – – – – – – – – – – – – – – –
152dbcb4-0903-531f-bfed-a93fd76473f1 | note | VERIFYING DOCUMENTS: This Checklist
cfb245c5-6004-5d99-afd8-b5279d4678d8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
89d0475f-2e25-5602-9a04-d0c2cc159253 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8349daf8-32fe-538f-a62a-9ea90d1fa4ae | textbox | Name:
4417d222-abad-5f70-837d-102689fee9a3 | textbox | Position:
4ce82da6-0b9e-5c3f-b09e-078658f3322f | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-014-CIV-SSB-Precast Material Inspection Rev 1 | itp | CHK-014-CIV-SSB-Precast Material Inspection | ec7a57c5-8c28-4e1f-970b-69932a9645a9
| section | Details
| checkpoint | Referenced Documentation
92a805bb-368b-5734-ab7a-741b8b56c0c4 | note | Document Title: CHK-014-CIV-SSB-Precast Material Inspection
0ec0c184-43a2-5ab4-b5f7-27980645788e | note | ITP Description: SSB -Precast Material Inspection
d4b43c5d-b498-50dc-a547-2ad74406bef6 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c741d6a1-3b5e-590b-a10c-0343d702a64a | note | Discipline (e.g. CIV/STR/RAIL): 014-CIV
cb66a994-ae78-5ead-8524-364e7cceb38b | note | Revision Number: 1
31f24d4a-2547-5b1a-84ba-6de3ceae648f | note | Revision Date: 23/04/2024
c294256f-29e7-5a7a-8348-7cadcdede08a | note | ITP created by: Dan O'Brien
799a8b44-3db4-5d14-af97-aa508adcd0a6 | note | ITP approved for use by: Victor Mira
| checkpoint | 1. Delivery Details
a0982009-6d08-5a13-8d14-153751be74fb | note | ACCEPTANCE CRITERIA:
b164f3d6-5131-56d0-9ab8-c6c623af1d8f | textbox | Enter: Delivery Docket Number:
586bbf8b-cabe-5a46-a8bd-e41d4e936fab | textbox | Enter: Delivery Date:
d14e9af6-16e9-5093-a4a8-44d7242b26cb | textbox | Enter:Element ID (s):
61106c2f-a5cd-5ea8-b313-b67ec5fe920a | note | Attach: Delivery Docket and packaging Slip
6f33cd9a-e3f7-5815-97c3-3fd0a94bdd6f | note | – – – – – – – – – – – – – – – – –
72667d66-a31e-591e-bd7c-1dc85e0284a3 | note | METHOD: Document Review, Visual
98b91db8-e8fe-576d-891e-7b1a52d73c5f | note | – – – – – – – – – – – – – – – – –
f584f39b-56e7-52b6-b7e4-a725976e165a | note | FREQUENCY: Each Delivery
638fab0f-bf99-5c7b-b551-5522a930eb99 | note | – – – – – – – – – – – – – – – – –
d954e536-a88b-5fbb-a046-aa55d4d929b7 | note | CATEGORY: IP
2b005d39-f251-5f47-8267-a055d3c93279 | note | – – – – – – – – – – – – – – – – –
7ebd7dc5-385e-572c-ae4e-33ee17eb35c8 | note | RESPONSIBILITY: PE/SE
f25ef1a8-0ec9-5b60-bc9a-4ac8f223bcef | note | – – – – – – – – – – – – – – – – –
6b94cef5-c02f-5169-9d1c-c6ef7e672c32 | note | VERIFYING DOCUMENTS: This Checklist
c210fa47-212e-5cf2-a699-61565e039392 | date | Date Completed:
| checkpoint | 2. Packaging Inspection-Quantity
73e5843a-5d10-5f8d-beb7-a93d49f38818 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
cd2f29b5-497d-5ff3-87b8-352a0ce8a7e7 | note | – – – – – – – – – – – – – – – – –
c7026021-aa11-508e-b977-546be57d5b59 | note | METHOD: Visual
974d1bf8-3428-5945-8ef8-f54240bc186b | note | – – – – – – – – – – – – – – – – –
18544677-25cd-57b4-b8fa-4bc2d0f63767 | note | FREQUENCY: Each Delivery
e7f081bd-f9d9-52ea-b919-6bd467dd0691 | note | – – – – – – – – – – – – – – – – –
9afdc1bc-bf15-5ef9-907e-ea89642ac97e | note | CATEGORY: IP
52373539-89d0-5522-9eed-a9a59f580d3c | note | – – – – – – – – – – – – – – – – –
e3c5c16c-1764-5b79-875a-33c39bbe72f8 | note | RESPONSIBILITY: PE/SE
2541c0f6-42ef-57d6-b936-0ef76f51c153 | note | – – – – – – – – – – – – – – – – –
3e7b542c-fb75-5e53-bf11-a09c43faea62 | note | VERIFYING DOCUMENTS: This Checklist
7d476000-8cb4-5c51-b42f-4710443b532a | date | Date Completed:
| checkpoint | 3. Packaging Inspection-Delivery Contents
1c65cf4e-f97e-500f-98b6-ac019bf9c301 | note | ACCEPTANCE CRITERIA: Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
b064da43-3b9b-5842-b768-5af765fcb1ff | note | – – – – – – – – – – – – – – – – –
38cb9493-c494-50fc-b818-c2da7155144f | note | METHOD: Document Review, Visual
3d7eeb5e-0c81-5855-81ff-5f2e25f4e399 | note | – – – – – – – – – – – – – – – – –
a6467116-7865-5232-aacf-12deadc782bb | note | FREQUENCY: Each Delivery
3cce4219-eb12-50c6-a5cc-62c92a05280c | note | – – – – – – – – – – – – – – – – –
d291b333-1c8f-53e4-a1fe-8ebdbe0463f3 | note | CATEGORY: IP
27423cde-f42a-548c-bb2c-9e52d18c01b0 | note | – – – – – – – – – – – – – – – – –
1d9df1c5-f6a3-5d9d-97a2-c0722fcbc776 | note | RESPONSIBILITY: PE/SE
87842f4d-284c-5b1b-ba36-cedeb6890963 | note | – – – – – – – – – – – – – – – – –
ece48e5f-41a0-59ca-901a-7ad42fa4314d | note | VERIFYING DOCUMENTS: This Checklist
f03ffb02-bc10-5d1f-b834-ee37c9881a96 | date | Date Completed:
| checkpoint | 4. Packaging Inspection-Birth Certificate
c16d5e0c-4346-5019-b1f1-7b627845b0da | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
93e4b8e7-3702-5317-b763-2cf1a8f36425 | note | ○ Precast components are to be marked on the birth certificate.
604fcfcd-7896-58e8-a6db-71ae4fd23e2b | note | ○ Cast date and lot are to be marked on the birth certificate.
bd9c80f8-3ec0-5fc9-98da-18bd398dcdcd | note | – – – – – – – – – – – – – – – – –
0bae3046-f529-5f6f-94d6-c80928b2f541 | note | METHOD: Document Review
cf481477-bdeb-5e52-8608-a9a65659de15 | note | – – – – – – – – – – – – – – – – –
1c36c791-1982-5ec6-a63d-0e60334de40e | note | FREQUENCY: Each Precast item
49368e55-451a-5c0c-bc53-d80f6b7cfec4 | note | – – – – – – – – – – – – – – – – –
a6858150-286d-575b-b0e0-d3723124a518 | note | CATEGORY: IP
962a0105-ef10-5d0e-878f-5b5452307c39 | note | – – – – – – – – – – – – – – – – –
0fc923ed-daab-5a41-885b-090b2b96d97d | note | RESPONSIBILITY: PE/SE
c3241fc7-0ae6-5896-996f-464111b87dc9 | note | – – – – – – – – – – – – – – – – –
c2846f2f-1138-5716-8b86-30c4bfe55c12 | note | VERIFYING DOCUMENTS: This Checklist
eba88c58-6db4-56d9-b6c5-57b4c798967e | date | Date Completed:
| checkpoint | 5. Packaging Inspection-Transport
251531ed-38c7-5ed7-bd4a-07f8651ab4c3 | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
06acdaa7-5d84-5998-8df4-44cff122a9b4 | note | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
c36b1db8-643a-5393-9ff7-3141e5934216 | note | – – – – – – – – – – – – – – – – –
05375baf-07a8-56ec-82e4-dcd5a59680c5 | note | METHOD: Visual
154c49a9-36e1-5615-865b-ed645e6ff07c | note | – – – – – – – – – – – – – – – – –
4194a83e-7e32-5537-837b-b36f75d7849d | note | FREQUENCY: Each Precast item
b65e7bea-054f-527f-9e80-57e1ea5b2c3c | note | – – – – – – – – – – – – – – – – –
67ed73f0-6881-549f-9a6e-39110ca4e67f | note | CATEGORY: IP
e437f135-2d14-5fad-99a9-f3539499e293 | note | – – – – – – – – – – – – – – – – –
307167cc-48f3-5e51-aa9c-5a844a831487 | note | RESPONSIBILITY: PE/SE
c565a63b-7308-576f-915c-61650684728f | note | – – – – – – – – – – – – – – – – –
8c47d16f-fb3b-5785-bfb9-9dfdafe95f3d | note | VERIFYING DOCUMENTS: This Checklist
24e92d4b-debb-5d78-b55f-1fccf00b4185 | date | Date Completed:
| checkpoint | 6. Pre-Lift Inspection-Transport
0bcc6c9f-8152-54cc-8617-81d36ffef173 | note | ACCEPTANCE CRITERIA: Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
63c7577d-fb6b-5b45-868c-946ecea9539a | note | – – – – – – – – – – – – – – – – –
811eb581-4f3d-5911-9e53-a3b5906642e1 | note | METHOD: Visual
bf4ea95b-264e-5d74-a8bf-1b5308a98614 | note | – – – – – – – – – – – – – – – – –
13b487f5-8f71-5575-813a-f540c1a16e7b | note | FREQUENCY: Each Precast item
3ecc5b46-917a-5ad4-b62d-718cfcfa2e20 | note | – – – – – – – – – – – – – – – – –
f7acedff-9eb1-50ab-85e0-8e0df491777f | note | CATEGORY: IP
ea61a3d9-fff3-55af-b064-ca3fd0eca138 | note | – – – – – – – – – – – – – – – – –
877d3d8e-5e94-5cf2-9c9c-3682131ad067 | note | RESPONSIBILITY: PE/SE
2e6049f6-ef6c-5528-acc4-810862c5595d | note | – – – – – – – – – – – – – – – – –
9e2bb213-64ad-50f7-8f46-455de4b0f80e | note | VERIFYING DOCUMENTS: This Checklist
61575d96-3927-543b-8e2b-abdd996b5732 | date | Date Completed:
| checkpoint | 7. Fault IDs:
ba079847-8998-5e82-9ef5-543c1903fbfd | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
d53f67ba-d5b8-5390-87b9-7803309bb3b9 | note | 1 - Identification markings match the panel type
c81e3bb5-21e8-59a9-ab3a-154c16675836 | note | 2 - Panels fabricated as per drawings
4cc44dce-2f0e-5cd3-9e2d-05de32f8c03d | note | 3 - Cracks
3a236fcc-b3f3-51c1-9849-6c3676be1030 | note | 4 - Spalling/Damage to concrete surface
5b7f7ea9-d3e4-5abe-acfc-fd7508335074 | note | 5 - Exposed Reinforcement
c0a1c3ee-fb8c-5d12-b666-8ae957340592 | note | 6 - Damage to Anti-Graffiti coating
7422cfea-3e22-5662-9152-541790344940 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
da11e5cf-8cbb-541f-a9ed-8ceb9f701303 | note | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
ea1884f3-9636-5b60-9769-3eb5cb506874 | date | Date Completed:
| checkpoint | 8. Check for Faults - 1
d2397547-9e48-5646-a949-23e9d33712fa | note | REFERENCE: Item 7 on this Checklist
57bae06c-bc20-5d92-b061-e6868b6da06d | note | – – – – – – – – – – – – – – – – –
2cafbb79-a8ee-5376-a5b7-9b3e3644bb10 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
1f3a4068-6488-5c7e-a0dc-a26e71547c81 | textbox | Enter: Panel Identification:
30283c25-d82d-591f-8427-f7a76c7a0c5a | textbox | Enter: Quantity:
a977b8d4-5016-537d-9f14-bb99f62a4109 | textbox | Enter: Fault ID if any:
9a13a205-3325-5002-a7a2-f371c45f990d | note | – – – – – – – – – – – – – – – – –
4b781d2e-ea5c-5f79-9dfe-2d3338fd62c4 | note | METHOD: Visual, Measure
f2ed32cf-a815-5b78-a882-12c57e2df343 | note | – – – – – – – – – – – – – – – – –
e3fbd2b0-c3ea-5327-9304-4e09348a5e57 | note | FREQUENCY: Each precast type delivered
58e214da-5314-53b9-9ff8-0684c99cd77f | note | – – – – – – – – – – – – – – – – –
c7e3b3e1-2428-5f69-a2e5-515d2574d0c6 | note | CATEGORY: IP
ecfa34b8-e4fa-5754-8688-a08e557a55bc | note | – – – – – – – – – – – – – – – – –
da4844ab-7c1b-51d1-a80e-459ca4c0afb8 | note | RESPONSIBILITY: PE/SE
2e8e6bea-3a3a-5bf0-93a9-90deaaff2d07 | note | – – – – – – – – – – – – – – – – –
1de0f2cc-4fc8-5afe-8b53-a82350fc6920 | note | VERIFYING DOCUMENTS: This Checklist
6c5c9b75-fb7c-5ed2-9b9a-a9b708191ba8 | date | Date Completed:
| checkpoint | 8. Check for Faults - 2
282331ee-abc7-53ee-b000-89580a2d436a | note | REFERENCE: Item 7 on this Checklist
c357c0ef-c532-50de-829c-ef85a82fda1e | note | – – – – – – – – – – – – – – – – –
84086150-ebc0-5bb8-8e7a-d2a15529f515 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
3b1caca2-1cb6-5911-bc11-96df8bff205c | textbox | Enter: Identification:
5bacf16f-af4e-564a-89f1-02980fffec6b | textbox | Enter: Quantity:
cbe721b1-2ba4-5b7b-b8a5-a4e2f22fdcfa | textbox | Enter: Fault ID if any:
b7c57bf1-e488-53ba-9918-a2fc1a9be53d | note | – – – – – – – – – – – – – – – – –
b40085b5-34cb-5d37-955d-6141727e3adb | note | METHOD: Visual, Measure
4b27600f-e826-5cdc-b4d9-1e7647899b30 | note | – – – – – – – – – – – – – – – – –
a4f54e6c-ad88-5389-aaf6-f09770c5b64a | note | FREQUENCY: Each precast type delivered
e0a9c2fa-d385-5d55-84d4-4f787d2c434e | note | – – – – – – – – – – – – – – – – –
d115925b-d75f-5ac0-8f4a-44cba931b075 | note | CATEGORY: IP
bcb0e471-b040-57e0-a7b5-5347b6f15b44 | note | – – – – – – – – – – – – – – – – –
affdabe9-e2cd-5535-ad48-0d6ccb831a18 | note | RESPONSIBILITY: PE/SE
2275d6c0-ffdb-568b-9945-cff6b358c7a9 | note | – – – – – – – – – – – – – – – – –
15a6acb6-672a-5847-b362-7b69a7770321 | note | VERIFYING DOCUMENTS: This Checklist
19575ab6-ac46-5030-afd8-dacc611e5b44 | date | Date Completed:
| checkpoint | 8. Check for Faults - 3
48c1bc93-4f6a-51d4-a7f2-a1ebc19a8d60 | note | REFERENCE: Item 7 on this Checklist
855f7b60-1c4e-543b-bc70-89d52c926d06 | note | – – – – – – – – – – – – – – – – –
552163da-d5cc-53df-a1d4-373a4e8dfc33 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
3f02e9fb-28bd-5f3e-a9fc-8c5ea59bc5a7 | textbox | Enter: Identification:
7b098a5b-b295-5ddd-9be2-cd4355679add | textbox | Enter: Quantity:
d5a7ee5c-f4e6-54bc-988a-febe17f16f1a | textbox | Enter: Fault ID if any:
818d33e5-fc2b-575b-913a-01b265b2adb0 | note | – – – – – – – – – – – – – – – – –
9fa3b8e7-9939-5fb4-9dbb-6c0c2158f821 | note | METHOD: Visual, Measure
753663e7-b484-5a45-ab4e-82d1cd529070 | note | – – – – – – – – – – – – – – – – –
19b41c01-f719-5f32-9292-b224ba3ac48b | note | FREQUENCY: Each precast type delivered
42ddb35d-d282-5df3-a095-3def173d4858 | note | – – – – – – – – – – – – – – – – –
8fb719ed-7bd8-5b2a-9814-646f2df3b38e | note | CATEGORY: IP
7f8c65ef-ba3b-54e6-9eaf-b0474562be6e | note | – – – – – – – – – – – – – – – – –
b366b2f7-65fa-51f8-8dce-ff1489e5de54 | note | RESPONSIBILITY: PE/SE
ac03f430-ab00-5d7a-a296-fbd3ffae7e7a | note | – – – – – – – – – – – – – – – – –
0d3a8f5b-2b21-5a73-8ce3-0bb3845e5b34 | note | VERIFYING DOCUMENTS: This Checklist
a6a05642-2f68-5f38-8fe8-88b3005329e2 | date | Date Completed:
| checkpoint | 8. Check for Faults - 4
2e8e3baa-1740-539f-96f0-221055129bce | note | REFERENCE: Item 7 on this Checklist
362a1279-8c4b-561f-b4c8-4c76393ffda1 | note | – – – – – – – – – – – – – – – – –
221ea5be-3f88-5bfb-bbcd-2881fb9c1544 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
8b48bf88-bd64-5d77-ab94-c09d3237ae60 | textbox | Enter: Identification:
4556840a-95ff-5718-b2e4-3bc2d0a678ed | textbox | Enter: Quantity:
b55a7f7e-45e3-5c3f-bacf-4fc4a7fae502 | textbox | Enter: Fault ID if any:
65132cee-282e-5a47-ad37-9f03c1c8a2c1 | note | – – – – – – – – – – – – – – – – –
ee0a4063-f9ff-51e1-bab7-00c19923786c | note | METHOD: Visual, Measure
68963492-5a72-55d5-88b0-0b144f242e94 | note | – – – – – – – – – – – – – – – – –
07bc638c-13fe-55e9-a7a1-de34b0e4d4dc | note | FREQUENCY: Each precast type delivered
a29a75ed-c957-54a5-a133-80763fd1f98a | note | – – – – – – – – – – – – – – – – –
6016b514-48f2-5fbb-9176-e9b76f87474b | note | CATEGORY: IP
f690b14a-bfb0-54ba-a0d5-f25cf80b4fb4 | note | – – – – – – – – – – – – – – – – –
3e344112-2460-54cc-af45-817ca7a7f8a5 | note | RESPONSIBILITY: PE/SE
48b8bb2e-69a9-5e6c-80a1-6c5557c7250d | note | – – – – – – – – – – – – – – – – –
c3599c0f-4cf0-517c-b208-fe55fe897b22 | note | VERIFYING DOCUMENTS: This Checklist
4fe0c6ab-a6dc-54a9-9516-dd07670807f2 | date | Date Completed:
| checkpoint | 8. Check for Faults - 5
0622a3db-8770-5393-af77-cc1280aa7391 | note | REFERENCE: Item 7 on this Checklist
300215ea-c326-57b8-a3b8-02878f6bc929 | note | – – – – – – – – – – – – – – – – –
6f6bc281-cb81-54b4-ab0d-76b6e3d00ae0 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
8d9d5076-f53b-5bbd-ba16-b32f77a8b4a3 | textbox | Enter: Identification:
ee93b2fd-95bf-58c1-b0c1-3e2ca5444494 | textbox | Enter: Quantity:
9a415e8d-84b7-58d3-8076-5284dc684b32 | textbox | Enter: Fault ID if any:
ca6c6904-f5a5-5139-8801-5b51567b21f4 | note | – – – – – – – – – – – – – – – – –
09f48556-44c8-5f44-9c13-c0cff8b64d4a | note | METHOD: Visual, Measure
263d1286-abcd-5a69-a9cf-a8bbc8ec6d37 | note | – – – – – – – – – – – – – – – – –
81e59016-5c56-5869-887c-a16e8e47ba23 | note | FREQUENCY: Each precast type delivered
ee58e7a8-b433-5316-85ce-f478ab02b086 | note | – – – – – – – – – – – – – – – – –
3987bb14-8bfb-5f11-a98c-501f2bcd809e | note | CATEGORY: IP
4104254f-d22b-5b31-8027-07dd4669dfe4 | note | – – – – – – – – – – – – – – – – –
30846f39-df45-5d02-a9c6-59b731bf1163 | note | RESPONSIBILITY: PE/SE
f9b2494d-ba68-5cb4-a69a-27d017fa7891 | note | – – – – – – – – – – – – – – – – –
69285cff-9999-50db-9050-67395daf9e8f | note | VERIFYING DOCUMENTS: This Checklist
b49199d5-c08e-5e08-b6b0-fb02091a709e | date | Date Completed:
| checkpoint | 8. Check for Faults - 6
ceae903e-de4f-5c91-a626-8276764b0931 | note | REFERENCE: Item 7 on this Checklist
dcc9d65b-e255-5443-a0f3-0e19efd55746 | note | – – – – – – – – – – – – – – – – –
ac4ed648-c3b3-5724-8bb6-e9773b181747 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
c1e79155-d00c-54f7-b08a-c3f466803715 | textbox | Enter: Identification:
83e72d28-9ba8-5dec-a0ce-054fc364c19c | textbox | Enter: Quantity:
bae17b5d-bac3-5ed2-afad-71853e3ac6c3 | textbox | Enter: Fault ID if any:
44159820-b083-5e8b-aaac-80afbb265080 | note | – – – – – – – – – – – – – – – – –
c10854c2-86be-5589-98a6-7bc9235f91dd | note | METHOD: Visual, Measure
16927016-a11b-53de-a7e5-e4e65ddeb91f | note | – – – – – – – – – – – – – – – – –
fd0dfa1d-ffc5-5f2e-af12-5b67b66a709e | note | FREQUENCY: Each precast type delivered
c00ce30a-0a4e-5471-9aa1-6b4db3612861 | note | – – – – – – – – – – – – – – – – –
6b11217d-bc58-5991-ada3-acc5def2d3cc | note | CATEGORY: IP
ca9af56e-c6a7-5e8e-822c-8689ba3c1ef1 | note | – – – – – – – – – – – – – – – – –
a8bac74d-7b74-52e0-8e2b-3c7291b693eb | note | RESPONSIBILITY: PE/SE
e054950b-bdc9-5c36-9d69-90b9cb774fdb | note | – – – – – – – – – – – – – – – – –
23f7b486-c66c-57ae-b045-3425d408e11c | note | VERIFYING DOCUMENTS: This Checklist
2f93e750-48d9-55b5-935f-52710cc57f3a | date | Date Completed:
| checkpoint | Final Inspection
749348ee-5917-584d-950b-dd3478501043 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f9cc0039-4b1e-5002-915c-3a6243a33856 | textbox | Name:
22766b4a-2016-5fb1-a95e-ae2a03dcd4cd | textbox | Position:
f1c7190c-34b3-5cd0-bbaf-26470fdf1105 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-053-STR-SSB-Bored Piling Rev 0 |  | ITP-053-STR-SSB-Bored Piling | e03702b7-ddba-496a-9339-005e25b3359b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
3e779f93-32eb-5df1-b569-0f4831f664d5 | note | Document Title: ITP-053-STR-Bored Piling
926b15c6-16aa-5b9f-a782-48a7b5b905eb | note | ITP Description: Bored Piling
246c3cdd-bb27-51dd-9632-64a715de6bc3 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
62c3eb0e-6fa8-5458-970a-85bfd4e240ef | note | Discipline (e.g. CIV/STR/RAIL): 053-STR
b2dc183a-025e-5a17-a1e0-d00df2ecde5f | note | Revision Number: 0
df936f2f-e7dc-5a9c-960c-afa4089f4cef | note | Revision Date: 11/10/2022
e633e78a-1d17-559f-bc6d-2d62a86916bc | note | ITP approved for use by: Victor Mira
6e168bc7-9e17-560c-98b4-dd88846e4413 | note | 1.1 Non Dependent
34bbfe00-602f-55d9-af5d-35fbf67b2b2c | note | Reference: VicRoads Section 606 July 2017
f16c8176-5569-50e1-a510-ec23258c0fa1 | note | 1.2 Non Dependent
36c9023a-e270-533d-80c1-a7d5f1eebced | note | Reference: VicRoads Section 610 Feb 2020
41955c0a-9961-5acd-a606-c92c9cd23c4b | note | 1.3 Non Dependent
8d765d58-e0e9-5679-a32b-870ee1bfcea2 | note | Reference: VicRoads Section 611 November 2018
8d3a2ec4-c31b-5acd-a538-6299d33894b0 | note | 1.4 Non Dependent
7530dd1c-4b4e-5966-a9ef-12a7561e3b44 | note | Reference: AS2159-2009
c95fbb58-9376-5bce-9661-92b600315b00 | note | 1.5 Non Dependent
51a73135-0f58-546b-9b8c-3a688fe88950 | note | Reference: AS3810.1 2018
1ba23957-c205-5d23-b529-4c5cabd36ffb | note | 1.6 Non Dependent
a5934898-51d0-5304-b82e-c943773d48f8 | note | Reference: AS5100.3-2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
941a16cc-2c20-5675-9cd1-6c2b5ea0c3db | note | REFERENCE: 610.07 Table 610.071
eb6ebe6e-360f-528a-ab87-391658604bad | note | – – – – – – – – – – – – – – – – –
fe177f23-b430-5866-af71-091a459e816b | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
2b1675e8-9f6b-5529-aeca-172c298a1d62 | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
270b3928-c341-5a17-8fe6-280e6b59a19b | textbox | Enter: Teambinder Material Approval number
1540c9f4-056f-5a70-9803-cb23cfeddff0 | note | – – – – – – – – – – – – – – – – –
8a80406a-b036-5279-8a00-8c2c1de0c7f9 | note | METHOD: Document Review
fb963b6b-1f76-50db-8b50-45b8da7faefc | note | – – – – – – – – – – – – – – – – –
0cc9a842-e533-5e07-8332-34854cc086ee | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
6236d37b-62c2-5d2b-bb98-0bbb50691d94 | note | – – – – – – – – – – – – – – – – –
74900eda-3024-56ff-9785-9afcfc542cba | note | CATEGORY: HP
53273832-94bd-5ddc-9bb2-b254d5194dab | note | – – – – – – – – – – – – – – – – –
5abffe1a-306d-50f0-8caf-f66e6fb3e6fd | note | RESPONSIBILITY: Nominated Authority
7c6156c7-b0cf-5de6-98bc-692b081b2a51 | note | – – – – – – – – – – – – – – – – –
f1d52cf6-2e84-51dc-8c07-2e728058842d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ac45fbf5-53f5-5002-8ec4-e4c660fd91b4 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
2a0e4ed0-55f7-5ab1-972d-a4e2d82574c3 | note | REFERENCE: 611.05 (a)
c46fb620-dd8f-5fc4-a25f-811c5c7a143d | note | – – – – – – – – – – – – – – – – –
c346f5a2-391e-55a9-bd30-1d45278891ad | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
e6b0fa22-9de5-5920-b86e-d679017bc688 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
ec099a58-c8e8-5dac-a326-085c754fd691 | textbox | Enter: Teambinder Material Approval number
f8d90997-0f27-5b3e-b6ec-75963d24cebb | note | – – – – – – – – – – – – – – – – –
e3fc1327-8d16-51a5-8d85-cea7199c12b1 | note | METHOD: Document Review
69f11c12-bb4d-580b-af24-a884c5356680 | note | – – – – – – – – – – – – – – – – –
b98fc91c-cb9c-5e7b-b9c0-bc948d370f15 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
f0175d6c-050c-5abb-a8bd-7913c57fe6c7 | note | – – – – – – – – – – – – – – – – –
4dce3071-58dc-598f-a46f-5dc19df80a64 | note | CATEGORY: HP
3515bc0f-d6b2-542f-9845-e124609fdb20 | note | – – – – – – – – – – – – – – – – –
e5e42af5-19cb-5c06-895d-69bc3f0f0cba | note | RESPONSIBILITY: Nominated Authority
55f1ec4c-b392-53bd-b6ad-c55c133e3eab | note | – – – – – – – – – – – – – – – – –
10dd8e46-15b7-5b78-908c-20ed53abd465 | note | VERIFYING DOCUMENTS: This ITP
a5ce4ff8-bec6-5617-9b67-b39238395bb7 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
cecbdc14-156a-564e-a126-e241ce1abd4f | note | REFERENCE: 610.26 (a)
b6deab1b-51c3-5cde-8924-7d006a3dad18 | note | – – – – – – – – – – – – – – – – –
8afe296d-ef4c-5c15-b1e8-e8e097c9d419 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
653a0315-69e5-5ef5-a6e4-877150236b8d | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
85770361-1a80-5e82-aa56-b4fe1383107a | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
5a1bddc7-bfcb-5609-b7c6-19b357b20f63 | textbox | Enter: Teambinder Material Approval number
68047fbd-3706-50ad-b41d-ee570452626c | note | – – – – – – – – – – – – – – – – –
d218b103-1fe1-5f02-beb6-944685d9473d | note | METHOD: Document Review
1a4519e2-04ed-5aa7-9980-98f08fdd86c2 | note | – – – – – – – – – – – – – – – – –
25f51cd2-b2bb-59b7-8461-d88aee9c1fe8 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
79176b08-8de4-5572-b3e3-d4f7f3867dd6 | note | – – – – – – – – – – – – – – – – –
53ccb156-3b1a-57ed-ae90-ac316e7d076d | note | CATEGORY: HP
9ed3d253-f53c-5863-b83e-b42ddb0f03df | note | – – – – – – – – – – – – – – – – –
cc3c4db3-2c18-5301-b840-85984bc9e97d | note | RESPONSIBILITY: Nominated Authority
e6547f30-7265-55a8-8e55-33121e36d6d0 | note | – – – – – – – – – – – – – – – – –
986b7eb8-275f-5555-96aa-1be3b57b0e0b | note | VERIFYING DOCUMENTS: This ITP
cbcabe1e-c48f-5487-9fe7-10bddb067556 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Working Platform certification
872bdc04-7e18-5b26-9e86-75a27cfc23a0 | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
435f6fda-2095-5c98-935f-604e3ec66c7d | note | – – – – – – – – – – – – – – – – –
872a1ef1-e5d5-5a8f-92f7-f4c96e5ec457 | note | METHOD: Document Review
649c27ee-8b50-5220-b7ae-1a8baa4639c9 | note | – – – – – – – – – – – – – – – – –
42094b59-ea9b-5638-b522-5c64f2180aee | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
8a7bee26-0442-5512-9c4d-86c07aa5afa5 | note | – – – – – – – – – – – – – – – – –
d0ea6ac6-e3e0-5984-9b55-4e7808069c42 | note | CATEGORY: HP
2c38b223-e49d-5d38-96a7-97ad35424700 | note | – – – – – – – – – – – – – – – – –
f8b62633-fae8-5887-8b12-99574f148d64 | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
3a5ad411-682c-5939-abce-fbc63c85fa9a | note | – – – – – – – – – – – – – – – – –
2c32a45f-a95b-5a97-85ea-02ceacb783dc | note | VERIFYING DOCUMENTS: This ITP
2d6b02d9-0807-5d7e-a870-0538fc79e877 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Piling Operations Work Procedure
c22ecb84-e503-5c28-a513-7a327cae13d0 | note | REFERENCE: 606.03 (a)
0f3e6c41-60bf-596a-ad95-131c13c5b37b | note | – – – – – – – – – – – – – – – – –
8bb9b383-e8ca-5bcc-b919-cc60bfce44c2 | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
2760059d-2513-5c4a-b1a6-efdbcf7761f6 | textbox | Enter: Teambinder Approval number
2fed6c2c-5e85-5809-a49d-feda9cf50054 | note | – – – – – – – – – – – – – – – – –
4950638a-a6c4-5e8a-adae-f6233d696718 | note | METHOD: Document Review
b529d8aa-ab1c-509c-abe5-728b65424e4c | note | – – – – – – – – – – – – – – – – –
235ed496-6711-58d4-8776-b1e6a806bf28 | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
41d1e063-6dfc-50e4-9ef5-362cf70b7d24 | note | – – – – – – – – – – – – – – – – –
40b62bcd-918c-5a33-a513-faac791da619 | note | CATEGORY: HP
a0ff54a5-961b-5378-9465-ba7aeb6f01f6 | note | – – – – – – – – – – – – – – – – –
1c6a8d2d-7418-50af-bd1d-da5461450989 | note | RESPONSIBILITY: Nominated Authority
787485fa-edf1-5789-934a-3944f7d53bb3 | note | – – – – – – – – – – – – – – – – –
34656c9f-8bb7-5e40-9a8d-62902b0a397c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
231fa042-d1cc-5075-b450-a94c1f61f7be | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Temporary Steel Casings
2ff5c3fb-5189-590c-b5f8-5ed1b25adb70 | note | REFERENCE: 606.03 (b)
c4832d7e-d7ce-5d43-ac5b-ab4f207fbbf4 | note | – – – – – – – – – – – – – – – – –
2118a8f6-684e-5e74-bfb7-741e2dccb146 | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
b43144bd-d661-5f36-9848-6321d9621695 | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
3d234586-1f4f-5ee1-8436-876961b300aa | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
4ca75c62-1649-5f77-80cf-24be51a66d4c | textbox | Enter: Teambinder Approval number
0092f992-dc99-5ea7-9fdb-534a1531152d | note | – – – – – – – – – – – – – – – – –
76a53576-5611-5f1f-9152-16bbbed0ac3e | note | METHOD: Document Review
89c1455f-dbe6-5caf-b115-32536de61b48 | note | – – – – – – – – – – – – – – – – –
1ff73abd-0fa3-51d3-a52c-ff8afa719d32 | note | FREQUENCY: Where applicable, once, prior to use
99d30d8e-594d-59bb-8571-645f376774d8 | note | – – – – – – – – – – – – – – – – –
36a7d277-6630-5560-9d6d-a5c96eef8cc8 | note | CATEGORY: HP
3a86384e-aa95-5663-8b33-8f174b445293 | note | – – – – – – – – – – – – – – – – –
cac74c9f-74c2-5362-b71a-bc5153b82f76 | note | RESPONSIBILITY: Nominated Authority
e88d6fd0-4583-5a03-bbd6-ca666be43ac1 | note | – – – – – – – – – – – – – – – – –
1ebcbab7-6060-57c2-b911-e5549f72454e | note | VERIFYING DOCUMENTS: This ITP
7c779421-b18b-5574-bddf-1d5fae86b4dc | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Casting Under Water Procedure
3add7cec-31ef-5b4c-9ed9-ca56a7e64828 | note | REFERENCE: 606.06 (a)
5e44ed80-5997-51f4-9fb6-252d30dcc7c7 | note | – – – – – – – – – – – – – – – – –
e75bf48a-ade5-579a-b8aa-cc5a57f655ff | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
cfb1a414-1e8c-582e-98d9-b7e54273eddc | textbox | Enter: Teambinder Approval number
ec55a1ec-4d29-5e66-808f-e385b408532c | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
474aff2d-781b-5af3-bfa4-b3a73b827a49 | note | – – – – – – – – – – – – – – – – –
7f3884ee-ebde-5792-9675-6de1b4bb6fc0 | note | METHOD: Document Review
6921638d-083f-5dc5-9f75-633aea20aa46 | note | – – – – – – – – – – – – – – – – –
ad8ef4bf-650c-5c18-a557-166d005fe30b | note | FREQUENCY: Where applicable, once, prior to placement of concrete
f722ca60-262b-55e3-9834-19dcd2888941 | note | – – – – – – – – – – – – – – – – –
98e8e834-3aeb-5833-9db9-9e51159e8854 | note | CATEGORY: HP
0b06d24d-125a-5546-b853-15b0b7ad8885 | note | – – – – – – – – – – – – – – – – –
f2d13015-311c-5b2f-869f-a2b48407c730 | note | RESPONSIBILITY: Nominated Authority
8439a7fa-a23b-5d80-8bc1-eeef2cb94247 | note | – – – – – – – – – – – – – – – – –
28b73fef-624a-52c0-b20b-3f8063ace0b2 | note | VERIFYING DOCUMENTS: This ITP
104682bd-891e-5000-a7aa-4b833ab3710b | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
8d07e610-041f-575d-8990-56c974b7f07a | note | REFERENCE: 606.03 (c)
d94e036b-ff4f-595b-88b2-a561e69fcdd2 | note | – – – – – – – – – – – – – – – – –
2a842f17-519f-55ad-a810-93f31b58e407 | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
09f1670b-31ea-5933-89af-95e7a56bc201 | textbox | Enter: Teambinder Approval number
53df5c46-16de-5027-812f-b2d61e34d349 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
cecbd039-797d-5f4e-950f-24137eb21ebc | note | – – – – – – – – – – – – – – – – –
dec48c30-86c2-5eae-b9ed-3274ad98a855 | note | METHOD: Document Review
c6498d35-2cc7-5856-8dd2-a7eac9ca963d | note | – – – – – – – – – – – – – – – – –
4a9fd476-9417-5376-9428-8a2f3f0eb298 | note | FREQUENCY: Where applicable, once, prior to commencement of boring
8481ac1a-6061-5b45-846a-3058cd85777f | note | – – – – – – – – – – – – – – – – –
db3a796f-822c-500e-91ac-3963d71cf3a3 | note | CATEGORY: HP
6d4cae52-18a5-56fe-8a11-32dab24e598a | note | – – – – – – – – – – – – – – – – –
f66ecd06-33cb-58a4-811c-a99d80d579d4 | note | RESPONSIBILITY: Nominated Authority
c32dd49c-6f0a-52b3-8839-7c51be75053e | note | – – – – – – – – – – – – – – – – –
32e409c5-1af4-55a1-bca9-e0239345f3fe | note | VERIFYING DOCUMENTS: This ITP
4167edba-29e5-5de9-a4a0-4868fefdac08 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Dynamic Pile Testing Procedure
3bb4982c-602e-52ce-a88b-97a8d564aaef | note | REFERENCE: 606.07 (c)
123c5eed-fd7c-5336-8cbe-72922422653a | note | – – – – – – – – – – – – – – – – –
57881b7c-677b-5607-b308-ad5a6057ae7e | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
407fc805-c775-5191-8797-82601d9283d9 | textbox | Enter: Teambinder Approval number
899ebcb8-5cdf-5834-af40-45d69c9d764e | note | – – – – – – – – – – – – – – – – –
359a32c7-5e55-5fb7-9d0c-fc22409588a1 | note | METHOD: Document Review
e9700d91-47b1-52e7-8cbe-2842f92baec6 | note | – – – – – – – – – – – – – – – – –
34626023-76ab-5c9c-866d-e39395603733 | note | FREQUENCY: Once, prior to testing
8f552ce8-d801-5106-a624-d6b6ededb984 | note | – – – – – – – – – – – – – – – – –
42aa0cf7-ff09-5165-a0ed-eeedcd062e77 | note | CATEGORY: HP
084a2391-f420-53b5-b048-5912fe69cee4 | note | – – – – – – – – – – – – – – – – –
e67936dc-6163-5f4d-83bc-671b46aaec56 | note | RESPONSIBILITY: Nominated Authority
6b234cf5-d5a5-5fe6-acc7-8b0adad81d74 | note | – – – – – – – – – – – – – – – – –
7f5b9ab1-4a57-5ee4-9ae7-92e90361ab09 | note | VERIFYING DOCUMENTS: This ITP
d8cdc248-cabf-59fd-9f5f-590b65a0ceee | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Pre-qualified Pile Testing Consultant
6efc42f9-e241-5ef6-b14f-5d789e38d53b | note | REFERENCE: 606.07
1ed10013-8050-548f-a055-c26a45f01538 | note | – – – – – – – – – – – – – – – – –
aeede161-5ba7-57cf-b7ca-e5207f5d3e56 | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
4cb61ecc-ee89-5e5f-9cbf-a376b291eda4 | note | Details of the consultant to be submitted for review to the Nominated Authority.
87dc1559-080d-5a9e-ab15-c33ea14822f6 | textbox | Enter: Teambinder Approval number
25afd119-23ec-52ec-a89f-f91e37ab364d | note | – – – – – – – – – – – – – – – – –
b0facab6-d8d6-511d-a728-a8943aca7d73 | note | METHOD: Document Review
531ef812-0f39-5bd1-9030-f053cdd65b2b | note | – – – – – – – – – – – – – – – – –
ec8996d5-6d24-5253-a527-b9454c59a85d | note | FREQUENCY: Once, two weeks prior to testing
baf0c402-2316-519a-b337-f33621a94a41 | note | – – – – – – – – – – – – – – – – –
ec6d7407-8b92-5e02-b093-6ac7820e1846 | note | CATEGORY: HP
0ad84e3e-f78c-5a77-a479-6c6ff9289df3 | note | – – – – – – – – – – – – – – – – –
4c1a8182-f38d-5f3b-b081-5ca8efa6df34 | note | RESPONSIBILITY: Nominated Authority
d615a409-be1f-5695-8a85-9342fc99c8cd | note | – – – – – – – – – – – – – – – – –
2af67ebd-aa4e-5c4a-9e9b-63327fcd37ef | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
50f7b956-52ff-5a77-a93a-a374893dcb52 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
f86d384a-9893-549b-8847-ec66867c7a95 | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
7ceb68dd-1f8f-5843-9f1a-66fb243daf4e | note | – – – – – – – – – – – – – – – – –
65bffa2e-8ef7-5790-8b9d-71d913b283db | note | ACCEPTANCE CRITERIA: Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
217a172c-321c-5e79-82ce-fe2788519571 | textbox | Enter: Teambinder Approval number
808f6cdc-48c9-57c3-80ca-b0f275d1c943 | note | – – – – – – – – – – – – – – – – –
287f9101-b01a-569c-a0a7-4703b2e15526 | note | METHOD: Document Review
b8d40a8d-09d8-5123-8b94-552b180231c2 | note | – – – – – – – – – – – – – – – – –
7d296d59-0ecf-5b17-93dc-128d1d97d651 | note | FREQUENCY: Where applicable, once, prior to welding
d1445881-73ef-50c0-8ff8-76f6d9b52e0e | note | – – – – – – – – – – – – – – – – –
51691f4c-fc5e-5054-874e-20605ca4da30 | note | CATEGORY: HP
daa394fd-fddf-5a81-872c-817bd3fdaf1a | note | – – – – – – – – – – – – – – – – –
0745ddc9-2672-5948-9e8f-a81bae671354 | note | RESPONSIBILITY: Nominated Authority
5880147f-25e4-5f48-ad84-218797e22930 | note | – – – – – – – – – – – – – – – – –
60030d64-b85c-596b-be1f-3ee84bf41772 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
3a1b2054-aa52-563f-a95c-5a7e62a2e162 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
f8568de4-33dc-5acf-b4b3-3be955513578 | note | REFERENCE: MRPA Quality Management Plan
a757bcee-03d8-5aba-ac0e-c75ed79524fa | note | – – – – – – – – – – – – – – – – –
a35e22a4-f9c6-5b3d-9f60-97c33ca345fa | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
7ad5ec8c-4a18-594c-a607-1ea1c524fefc | note | – – – – – – – – – – – – – – – – –
43fb9970-1d9a-5163-9495-ea59bc2cb351 | note | METHOD: Document Review
8f298032-d17c-5fa7-a608-9e3579e815a1 | note | – – – – – – – – – – – – – – – – –
43f985ab-0e27-58ea-a433-b651ccb1fc77 | note | FREQUENCY: Prior to starting Works and at regular intervals
b01b922f-fed3-5da0-8140-ed05637f5178 | note | – – – – – – – – – – – – – – – – –
ae693699-e51c-5838-8898-a6aa04fd7ee2 | note | CATEGORY: HP*
99d3fc18-5419-5ad5-9cb1-204a10be0659 | note | – – – – – – – – – – – – – – – – –
8a5e2df6-f933-536c-8f78-37d867aa6ddb | note | RESPONSIBILITY: All
6327f7ed-24eb-52df-957f-39c58a2d400f | note | – – – – – – – – – – – – – – – – –
c56f7766-6c34-5c72-96d9-77b8f03ef125 | note | VERIFYING DOCUMENTS: This ITP
d0d1b552-7a62-5268-88a9-d2e1da9af9b3 | textbox | Date Completed:
| checkpoint | 4.2 Survey Set-out
c0050535-ec00-5b1a-aed5-ec72d873fbc4 | note | REFERENCE: IFC Drawings 606.08 (a - c)
98e7112a-ed83-5f01-8a4f-139118f71734 | note | – – – – – – – – – – – – – – – – –
a82dd41d-15a7-57db-a709-acbffbc7ca0f | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
92361831-ee7c-51ef-89f6-78a2b89fc5be | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
ac77cde7-fbcc-574a-be9d-600fdf1d07bc | note | – – – – – – – – – – – – – – – – –
7bc3350f-c562-51be-b215-a4742d6f88ac | note | METHOD: Measure, Visual
6d963c03-a853-5fb1-9a5e-4594d8bc0659 | note | – – – – – – – – – – – – – – – – –
a50bfb06-25ee-5f60-bc31-1201abe3c9bb | note | FREQUENCY: Each pile
ec91d7e7-22d1-5f12-bf1e-a358ee1434e8 | note | – – – – – – – – – – – – – – – – –
4b49669b-90ca-5d3f-ba64-d8e7b67fba40 | note | CATEGORY: IP
685d3381-389d-5f1d-b3b0-fd9e1f28e674 | note | – – – – – – – – – – – – – – – – –
2e6f8126-08ef-5d15-9c80-6fea6cc6632d | note | RESPONSIBILITY: Surveyor, SE
48a620fe-b633-5939-9038-4e6b01f49411 | note | – – – – – – – – – – – – – – – – –
d07f1bd7-c951-5bc2-b4f7-d3201dba3e6f | note | VERIFYING DOCUMENTS: This ITP
02791c64-ae11-54c0-8e7a-bcfe8fd02b75 | textbox | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
d268d5fb-5097-56c4-b908-f586c498005f | note | REFERENCE: 606.04
571e442f-3d6a-5aad-9575-0eae5b115d24 | note | – – – – – – – – – – – – – – – – –
4c8b2fd0-68b2-5323-a1ce-2722eca9a224 | note | ACCEPTANCE CRITERIA: Pile construction shall not:
7fc0db62-bc25-5343-8a63-c4196ff7f14e | note | i. result in damage to adjacent newly cast piles due to ground vibration.
4eeb74c7-b16f-550f-a03b-098cef8c1159 | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
98a09c19-0110-5ddc-91b0-59740ee11559 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
553b4560-a503-5c91-99a3-a8171cf23a5c | note | – – – – – – – – – – – – – – – – –
3d32afa8-5609-5e40-854f-08a023abaf99 | note | METHOD: Measure, Visual
7ce2e205-0153-52c6-b00c-2740ec6096b6 | note | – – – – – – – – – – – – – – – – –
7d64f9fe-2f17-5bc5-b9c8-ff5ab10b2933 | note | FREQUENCY: Each pile
f2ddce00-b4f3-5368-b17b-0b45606c6d7f | note | – – – – – – – – – – – – – – – – –
86900af8-18fd-5b92-adc6-5383a728e080 | note | CATEGORY: HP*
4748d0f8-36ec-5ad3-94d5-66445aa839ad | note | – – – – – – – – – – – – – – – – –
6706da26-824e-5eb5-891e-5079423a5068 | note | RESPONSIBILITY: SPE/PE
412f6dce-e0f7-5062-874d-84d398e1d5d9 | note | – – – – – – – – – – – – – – – – –
454c7326-e444-5ae5-8bad-008dc2b5e428 | note | VERIFYING DOCUMENTS: This ITP
3c8612d8-9b44-522c-bdb6-3f80f7e2de50 | textbox | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Boring Operations
ddfbdc17-e048-52a7-8ffd-d3a0c70b9b9d | note | REFERENCE: IFC Drawings 606.03 (a)
ad1c4225-4618-52de-86c4-3a826bf30b66 | note | – – – – – – – – – – – – – – – – –
b252f0a4-383e-5921-b883-f15c6265f7ba | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
e0142377-e723-5b22-b058-d79cd5796946 | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
3b06e9e2-29d5-558e-b955-097dbb41f202 | note | • Excavation clean and de-watered (where applicable) for inspection.
12884335-7fe4-5d76-8ed1-d47f7b888a3a | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
41399950-3bc7-5b24-86d2-4f7004ef6144 | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
8e563f03-27cd-5300-a279-095b1abec5bd | note | – – – – – – – – – – – – – – – – –
b8126d90-f1e2-59b1-b626-f825540d3b91 | note | METHOD: Measure, Visual
0531cd92-2d3a-59ef-9804-3655ee88db0b | note | – – – – – – – – – – – – – – – – –
546861cf-fbf7-56d8-8a2f-346612be24d5 | note | FREQUENCY: Each pile
df3d3f5e-0e48-58e1-803c-b18ceaa23a98 | note | – – – – – – – – – – – – – – – – –
47182788-35d7-5e6b-ac5b-18112a9c4b16 | note | CATEGORY: IP
60da6cb7-621c-514a-af1d-2a34fc09471c | note | – – – – – – – – – – – – – – – – –
6d719055-9a75-5265-9831-c554fc27761b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
095e60ad-40c7-53d3-92cd-307198adeecb | note | – – – – – – – – – – – – – – – – –
0a41ffdb-01e0-5c4d-9844-c1c14f841796 | note | VERIFYING DOCUMENTS: This ITP
b08b2cc7-c376-5d95-ad39-a9f4a114f53d | textbox | Date Completed:
| checkpoint | 5.2 Formwork Extension
cf657713-a524-544c-941e-cf911f50f08d | note | REFERENCE: IFC Drawings
66fca597-ea68-5b6a-8030-d8834b4b99de | note | – – – – – – – – – – – – – – – – –
0ce51d4e-bd03-51dd-bd51-50f15a8899f5 | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
b2d09a53-f373-5524-afde-98b49d550c2d | note | – – – – – – – – – – – – – – – – –
b6a97393-9c16-551d-8ad8-2188622d4f1e | note | METHOD: Measure, Visual
b52c29ef-0f70-5859-b011-b0f3941a95d2 | note | – – – – – – – – – – – – – – – – –
74879c65-1c33-5166-b547-df7d9d31c4c9 | note | FREQUENCY: Where applicable, each pile
84a86778-85cd-5671-b8d8-ef4eb57022a3 | note | – – – – – – – – – – – – – – – – –
a32adf1f-4e37-54c5-92ad-10e4330e8d87 | note | CATEGORY: IP
00eaf6f1-bfef-556d-9e37-c13611efa98b | note | – – – – – – – – – – – – – – – – –
11972a2e-dcbc-5981-a31c-6eae13ef1b7f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
0af9fdaa-c7a8-5dd6-8949-58e1813599c6 | note | – – – – – – – – – – – – – – – – –
e77a1b0e-c539-5152-bf95-8f8df6b34149 | note | VERIFYING DOCUMENTS: This ITP
20d840ce-c9f5-5e0e-8ee6-c9bce2a065dc | textbox | Date Completed:
| checkpoint | 5.3 Inspection of Pile Excavation
6dbee983-e29a-5188-bfb9-abd633b29ccf | note | REFERENCE: 606.05
67bfba29-62d1-531b-9535-da02c5a464c6 | note | – – – – – – – – – – – – – – – – –
750bf1ad-a350-5b15-992b-c0fe9beec670 | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
51971968-23c7-5fbb-8783-883551559693 | note | Attach: Geotechnical Field Sheet or Report
6345365a-8694-5b4a-bfd5-6e8c17f17a0d | note | – – – – – – – – – – – – – – – – –
05b2f277-c42e-51f5-8fcd-273893fe9381 | note | METHOD: Measure, Visual
f1f32f37-844a-5bd0-b395-7efd3b4bea37 | note | – – – – – – – – – – – – – – – – –
9ba9b66c-0ad9-529b-9c01-279fbf61593c | note | FREQUENCY: Each pile
3656e087-8bfa-59cb-8f8b-6feee3fcb66c | note | – – – – – – – – – – – – – – – – –
84ee6a5a-ab60-5e3f-b19d-a8dcb87a5faf | note | CATEGORY: HP
1b3786f1-402d-5dbc-8e98-f9b93ebcafc7 | note | – – – – – – – – – – – – – – – – –
2b2baabd-21be-5b34-bdeb-779b3a854c42 | note | RESPONSIBILITY: Geotechnical Engineer
0dce1279-ae5c-54d3-940a-7fd81d69f5ca | note | – – – – – – – – – – – – – – – – –
63a37005-e686-557b-b164-190fad11197a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
7bb331bc-292a-55e4-9cbc-f3d9aca501f2 | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Reinforcement - Placement
0ab0f5a8-aaee-5be3-ba12-560b0ddbd0e2 | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
dd9c59c3-50e5-5468-bdcd-66a722329938 | note | – – – – – – – – – – – – – – – – –
0e9a0b04-b067-5c8d-9f89-8f0adb5e562b | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
141197e7-8f37-51b0-be3c-381d818beccc | note | • Projecting reinforcement is the correct length and location.
7fc9d350-14fc-5d49-94d6-4be62d38cf8c | note | • Splice lengths achieve the minimum length and are in contact for this length.
99588dff-00b0-5a93-afd1-0f76e1871a7e | note | • The reinforcement surface condition is free from dirt, debris and damage.
3437824c-990b-5b1b-98c2-f4a7a3511d2b | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
3ead3e77-7b50-5769-8e95-42cabfa497e6 | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
28c5157a-052e-5316-bfc6-b9255bd1510b | note | – – – – – – – – – – – – – – – – –
bd28504f-0ab7-53e3-9711-859f37913666 | note | METHOD: Measure, Visual
8e5ee3ab-50da-5e3b-8608-aa2423ba43d0 | note | – – – – – – – – – – – – – – – – –
869c9bf7-b589-53c1-9b91-bb85200ab0d4 | note | FREQUENCY: Each pile
5c3e44e8-c5a9-5115-8091-c2518317cdfe | note | – – – – – – – – – – – – – – – – –
b0c1b315-3eeb-5935-ae3b-24acd7cff46f | note | CATEGORY: IP
cfe1fff1-6274-5fdf-892d-1e2aa1653267 | note | – – – – – – – – – – – – – – – – –
13e17386-5a99-5cc8-99ee-19c690c197d2 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
52411d72-955a-581f-b5f7-7f138979e7a9 | note | – – – – – – – – – – – – – – – – –
a749c53d-fc97-51f6-9494-0ec665766e3a | note | VERIFYING DOCUMENTS: This ITP
08d69192-bb1d-5915-b610-4364acf7a9d7 | textbox | Date Completed:
| checkpoint | 5.5 Reinforcement - Electrical Continuity
c5779768-0bfb-5af6-a14e-8d2d686004d7 | note | REFERENCE: IFC Drawings 610.29 (d) 610.43
d7951f6d-7482-5152-9592-f71676c01278 | note | – – – – – – – – – – – – – – – – –
d2f8bc86-0aba-57bb-8d31-a127f6017adc | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
0bb10d21-26e0-5a58-abba-8014734a6265 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
244cb006-bf98-500c-9fca-372415297748 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
cba62678-1573-5054-917d-f43be26d9f60 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
3df695e3-7d19-5959-99bf-2e2cbb190815 | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
523b4fec-2261-586e-a8c2-a65123a7c6a2 | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
18e9fb04-050e-5d8a-bba3-99a3c66e3cdb | note | – – – – – – – – – – – – – – – – –
2b0e1af0-8ca3-57cd-ad63-c045f45cfb7c | note | METHOD: Measure, Visual
5f017c6c-a12e-5146-ab2d-ab04e7c94428 | note | – – – – – – – – – – – – – – – – –
61da597f-a19a-50b6-8be2-5c1b21a05dcb | note | FREQUENCY: Where applicable, each pile
5fe55377-3845-5b67-b125-53c41c0abf8a | note | – – – – – – – – – – – – – – – – –
8b136fc9-97f8-57b3-b295-2b0df59cdf38 | note | CATEGORY: IP
7dc54f45-eb91-583e-8c4d-362e61bf0c4b | note | – – – – – – – – – – – – – – – – –
9633d664-0703-58fc-805d-c6b474e2e958 | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
86e9fd64-bc66-5f06-8aab-4ee29506f0bc | note | – – – – – – – – – – – – – – – – –
6f70eb62-3221-5250-8168-530cbb0cb14b | note | VERIFYING DOCUMENTS: This ITP
5e0eb8f0-c31b-50c6-b156-34a8c198336c | textbox | Date Completed:
| checkpoint | 5.6 Cast-in Items
fe32844f-4bed-55e0-87cf-e7cb17409e22 | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
4d2c3489-5331-558e-bdc6-1d2bf5e62bc2 | note | – – – – – – – – – – – – – – – – –
e032a61f-3f57-511f-bb29-a7929637f2c8 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
a4af778c-08cc-5f1b-83a3-38e4feb1c672 | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
8791efca-b106-5985-805b-2298ef735362 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
f8ddc543-0771-588b-b901-5ab9d855fc54 | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
ced37e0c-99c1-5a73-94e8-c6b75b6bee7c | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
6db3b2bb-f514-5542-9c96-0b9202448e63 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
afd4bd31-e7e2-5c7d-ab56-8275222948d6 | note | ii. Running dimensions of a group of the above = ±6mm
c2c1d39b-34b2-5513-9ae7-a4fa16b98a92 | note | iii. Ducts and conduit location = ±12mm
54a9490c-1b24-5454-905c-2a20e75706a5 | note | iv. Diameter of ducts and conduits = ±3mm
b05ae382-697f-5352-b3fb-b11a5b9c0bc6 | note | – – – – – – – – – – – – – – – – –
0c6f25b3-2cb2-540d-9d97-198707e3809f | note | METHOD: Measure, Visual
15668efe-f910-50fb-a36f-5d8c620f564b | note | – – – – – – – – – – – – – – – – –
e84711d0-10af-57e5-b9c5-cc7eb28e8034 | note | FREQUENCY: Where applicable, each pile
477c2d6f-1c9b-583d-9396-ed05174002d9 | note | – – – – – – – – – – – – – – – – –
02b2790d-a331-577b-bf95-2b27fe1b614f | note | CATEGORY: IP
a8b17f3a-8c64-5a9c-bfc5-9919dd1bb724 | note | – – – – – – – – – – – – – – – – –
6d7651e8-5b95-5a4e-8ab5-f3a40bce44aa | note | RESPONSIBILITY: Foreman, SE/PE/SPE
0e737688-2fc5-591f-a941-0c790646661f | note | – – – – – – – – – – – – – – – – –
379c9419-b6e3-5ff7-b569-ca53e90eff8f | note | VERIFYING DOCUMENTS: This ITP
239bb120-5ea8-570e-877f-cd2bfb59b6e4 | textbox | Date Completed:
| checkpoint | 5.7 Pre-pour Inspection
aec9448c-3f49-58c8-bffb-3a4219c400d4 | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
ed988ccf-811a-560c-be58-60f53ddb3184 | note | – – – – – – – – – – – – – – – – –
b5810a87-fc5c-557a-87b5-c47d7befa6b3 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
94986449-34b9-5484-8350-1a5883aac0a3 | note | • All foreign material has been completely removed from the excavation.
0e650d7d-f573-56c7-97cd-1b1dcf3fbbd0 | note | – – – – – – – – – – – – – – – – –
a3ac4ca8-db97-514a-a453-9f98481b48b4 | note | METHOD: Measure, Visual
b0df3c99-abaa-55e0-bf4c-ef61faf87b02 | note | – – – – – – – – – – – – – – – – –
21da78f0-9f39-5d3a-aaae-1d5c88466403 | note | FREQUENCY: Each pile
3c464046-7cc3-51ea-998e-e5f833c3b05d | note | – – – – – – – – – – – – – – – – –
6de6c2e9-0279-5f14-a158-305ee55b4073 | note | CATEGORY: HP
309529c8-e0e1-5bb5-9be1-f7f0499627b1 | note | – – – – – – – – – – – – – – – – –
352601b7-dbbd-59fd-8d1e-73fd317a72c7 | note | RESPONSIBILITY: Nominated Authority
f23c90b0-44da-5ad1-9672-6a1dfd515d10 | note | – – – – – – – – – – – – – – – – –
01c46415-9c3d-5cf3-8049-5f0298b5f95b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9c6c2fc3-4d35-5f59-8921-75dc4c0ffcef | textbox | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 Weather Conditions & Evaporation Limits
d51e64b2-ef2d-5730-a772-bfec68cffe09 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
319b32b5-1d58-5d7e-b37c-5384f8438cb6 | note | – – – – – – – – – – – – – – – – –
7c9dbdc0-4eba-5338-940f-bce9881b2b45 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
d5e7ee18-b6cc-56ab-9975-2ed604898c79 | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8fcb5a9b-cea2-57c0-bd7e-0d4e0c13d791 | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
5fff7795-c309-5d25-8e6b-cd3e33510455 | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
b0ad208f-d5a3-5ace-b5d3-8de30a760eb7 | note | Record: Required information on the Concrete Pour Record.
d6a37cc1-7b59-5abd-8566-b292ac639743 | note | – – – – – – – – – – – – – – – – –
8324f3d9-174b-5dd6-828c-8238e52aea1b | note | METHOD: Measure, Visual
c5f60aed-5ffc-500d-aad6-99c1b3982e28 | note | – – – – – – – – – – – – – – – – –
0832c559-a854-5126-971a-cc498240a507 | note | FREQUENCY: Each pile
bd66fdfd-68b4-5271-81df-01d38cdfe3b2 | note | – – – – – – – – – – – – – – – – –
c7650907-4e7b-59cc-9cbe-6795931a94b9 | note | CATEGORY: IP
69469389-66d9-5317-8ce9-9385f4c7ef1a | note | – – – – – – – – – – – – – – – – –
d9bd4ae7-f39b-53b3-8dae-4e91aee3bd54 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b16389f0-80a9-5f55-968e-52823da89b61 | note | – – – – – – – – – – – – – – – – –
6ae4b127-8c1e-54ae-afe6-1c73b1341962 | note | VERIFYING DOCUMENTS: This ITP
e37f9c59-f83c-58d6-ad3e-af5e32f04eb1 | textbox | Date Completed:
| checkpoint | 5.9 Concrete Testing - Sampling Frequency
0ef40f34-b5ed-5d5d-a23f-178817e3973f | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
3368c2d4-4171-51f9-b83c-b917c878e801 | note | – – – – – – – – – – – – – – – – –
581f63df-edcc-5e79-9824-269bb8b1abb9 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
9478d5f6-8a35-5977-9233-b9a10dc4b386 | note | 0m³ to 10m³ = 1 sample
a3058852-f2dd-5154-9bc7-aa46886b8f50 | note | 10m³ to 25m³ = 2 samples
b290fa30-ffbe-5c96-805e-fbf08c88768b | note | 25m³ to 50m³ = 3 samples
b83379f7-39d9-588d-825c-e3b511bd75d7 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
9c4a0b1d-77d4-50bb-8070-a25450b24bcb | note | • For each additional 50m³ and additional sample shall be taken.
657565dd-0505-5d12-88f9-eaa2af1d3708 | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
f5f0cb20-92a1-51c2-88d0-9ba4defb3643 | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
df01f0cc-2fb3-51ab-85df-628bc60caf88 | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
58e04722-0197-50e5-81c8-e0bd8af2ecab | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
93e87183-bd10-560d-a240-75405d6ecfe9 | note | Record: Required information on the Concrete Pour Record.
1a3153f5-2685-5673-bca4-c1b7b23c169b | note | – – – – – – – – – – – – – – – – –
b75ff32b-f7e5-5f3d-a700-91b68b8f12cc | note | METHOD: Test
2a46e046-7c2f-5d7c-acb3-53af6aca59b0 | note | – – – – – – – – – – – – – – – – –
09dcf212-2eea-54f8-8bce-867d8284310f | note | FREQUENCY: Each pile
a5d26ecb-3f95-5764-aca6-1d47880a490d | note | – – – – – – – – – – – – – – – – –
7fce780d-c539-5db5-bedb-d40f239c86f2 | note | CATEGORY: IP
a8155d83-b433-5765-bee0-9581329ec0f1 | note | – – – – – – – – – – – – – – – – –
467ee8d8-9706-5da7-9225-922fdd08796a | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
d741dd6f-78c0-5bd6-9be8-1766d93ff6e5 | note | – – – – – – – – – – – – – – – – –
39599ccb-2f02-5337-a845-5cdb88f89563 | note | VERIFYING DOCUMENTS: This ITP
c8b5c515-5071-59a2-953b-1bdfd14dee43 | textbox | Date Completed:
| checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
25bbde4a-27e8-5f06-8ffe-c666bdd11432 | note | REFERENCE: 610.13 (b)
3a867ef0-afd2-5109-8478-0307137bff8a | note | – – – – – – – – – – – – – – – – –
cf175af7-9264-558e-94d7-ece78e8eb7fc | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
e77f4ca5-fb45-51a5-910f-3a4a1f09385d | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
c88d8a8f-7267-5280-9d8b-e37fb1da6c35 | note | • Passability = ≤10mm (aggregate height differential)
f456b928-de8a-5cd7-b592-a220995b51ca | note | Record: Required information on the Concrete Pour Record.
495ca548-6d06-56d1-aad5-ee9a4ac423e6 | note | – – – – – – – – – – – – – – – – –
0a5d52e6-0afa-5c47-baf3-c908305e649d | note | METHOD: Test
8b2f5cdf-9280-5ea4-a0ab-3483165c99bb | note | – – – – – – – – – – – – – – – – –
a2b81406-8741-521e-9977-79cca9bab06d | note | FREQUENCY: Each sample of Self-compacting Concrete
06773d12-04c7-5177-ab9a-8de4a4badebe | note | – – – – – – – – – – – – – – – – –
af6cd45d-fc3a-5467-bf9d-3aea4a6a9522 | note | CATEGORY: IP
f520da25-40d7-5331-9196-7708c3e02245 | note | – – – – – – – – – – – – – – – – –
ed539f99-0f7f-5b89-b59c-661c25ea7605 | note | RESPONSIBILITY: Concrete Tester
07852a82-f4bb-554b-93af-757056703b57 | note | – – – – – – – – – – – – – – – – –
f86da9c0-d9c5-51aa-8743-2f32f4c56c83 | note | VERIFYING DOCUMENTS: This ITP
8cd8bec6-9b72-578f-881d-bed59d5985e1 | textbox | Date Completed:
| checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
ec3883bc-1524-5e8c-a068-9f50027d69e0 | note | REFERENCE: Site Sampling & Testing Procedure 610.16
8c5ca500-29b4-5572-b071-644d66f15c5e | note | – – – – – – – – – – – – – – – – –
b47b01eb-dc35-5f39-a706-521bf36df788 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
5732e763-0a7e-5994-ae6a-5efc979fc742 | note | Record: Required information on the Concrete Pour Record.
0511a59d-6f53-5dfb-b872-0c3344ed2a3d | note | – – – – – – – – – – – – – – – – –
b057c8cb-2d9d-581f-a4a3-02c3f47caa51 | note | METHOD: Test
7b69b9fc-136e-5634-9e4d-5d8d8dc239d9 | note | – – – – – – – – – – – – – – – – –
cc2b989e-5ffc-5dab-b723-21e802716874 | note | FREQUENCY: Each sample
6376fbf1-ce83-5bb4-9fe6-398e22384188 | note | – – – – – – – – – – – – – – – – –
41347a79-8f67-5761-ac04-5aba9ef0e146 | note | CATEGORY: IP
93681792-12c8-5d65-be91-b6b312805c36 | note | – – – – – – – – – – – – – – – – –
54ec6182-351e-5836-ad13-383542bb19ec | note | RESPONSIBILITY: Concrete Tester
2ff109be-33af-5319-a5ee-e21b085bb453 | note | – – – – – – – – – – – – – – – – –
37904152-5e0a-5334-b6f1-bd8c37538714 | note | VERIFYING DOCUMENTS: This ITP
ed174a8d-ff8b-55d7-81ac-66f53e977b0d | textbox | Date Completed:
| checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
fd6e180f-8007-53f0-bdcf-6a97d5e9d73a | note | REFERENCE: Piling Quality Procedure 610.18 (a) & (b) 610.18 (d) (i) 606.06 (a & b)
bbc87a57-c5fe-56e9-a85c-dbe1a23e34ab | note | – – – – – – – – – – – – – – – – –
771d951b-bcf8-5651-9061-4b9c7f6e719c | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
6f802b8a-f987-5cd9-b3b9-f52ce1e4bc58 | note | • All concrete batches are traceable.
b3d38e5a-954f-5b57-b98e-e7e87ef1a313 | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
05fbd8bd-c6d8-5496-adc8-9e2307037a12 | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
b72ebfab-a267-5400-8e0b-d69c9f6a538a | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
8e66b6f0-c8e1-5f04-8f04-4aac13054ceb | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
0e12994a-020c-5c1a-a3f9-dc855a78f7e7 | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
87424df1-f47c-5407-9cc8-842db2a10c50 | note | Record: Required information on the Concrete Pour Record.
3adc00fc-7bee-52d1-a2fa-9f484d106a01 | note | Attach: Concrete Pour Record
d678cdeb-b317-5dde-a439-babdf3565ef0 | note | Attach: Concrete Dockets
d1336547-d67d-5ed0-8c62-8f5debac8da5 | note | – – – – – – – – – – – – – – – – –
072d8bdb-377d-5b27-911b-b59b9310ff7f | note | METHOD: Visual
2420f2f0-487a-5f15-a208-f63f3355b4a1 | note | – – – – – – – – – – – – – – – – –
13fb2b26-c3b2-5978-8332-bff69aa56ffa | note | FREQUENCY: Each load
a3bcd20e-0bba-59ad-98a1-efef0725106d | note | – – – – – – – – – – – – – – – – –
c06c43bf-d9b3-55f5-a516-0f674b721ef0 | note | CATEGORY: SP
61b5f67e-e191-56c5-ac06-95e1b3d44a5d | note | – – – – – – – – – – – – – – – – –
b5ba36d7-f8fa-5d33-9086-dfda1d801eab | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7733b376-bb14-5234-8a9d-0c534d2d352b | textbox | Date Completed:
| checkpoint | 5.13 Surface Finishes
0d761eb8-99e8-537d-8ad4-0ef5e6de13f5 | note | REFERENCE: IFC Drawings 610.31 610.20
86f9a53c-f7e5-599f-9b10-80ed8c26f8bb | note | – – – – – – – – – – – – – – – – –
4eeca337-ac4b-57fe-87c8-caf8cd910704 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
26309abb-2110-589a-9a3e-c0a6a4f8b363 | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
76aab080-d2b1-5fb8-a282-683b26fc2d93 | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
d3a46d65-70de-52e2-a13e-a93ab8f06f66 | note | – – – – – – – – – – – – – – – – –
d750caee-e2a6-5b80-8c4f-5b38ad4a55b3 | note | METHOD: Visual
51b94231-81b6-5463-9099-ed7eb314bf19 | note | – – – – – – – – – – – – – – – – –
1588c1b5-5f7f-5ffc-960b-5d4a24bd61d4 | note | FREQUENCY: Each pile
1d70ea6b-af60-53ea-bd1f-10beb17c7803 | note | – – – – – – – – – – – – – – – – –
15b9284e-d5dc-58a0-a0bb-10b02103a68a | note | CATEGORY: IP
22017291-535f-5e32-ae9f-2066e07abefc | note | – – – – – – – – – – – – – – – – –
13168a56-48a5-5a4f-a149-ad11c0c36cda | note | RESPONSIBILITY: Foreman, SE/PE/SPE
27718c8f-0d48-5c27-a946-698c58dadf62 | note | – – – – – – – – – – – – – – – – –
93afa108-21d6-5e4f-80b7-580c29c64554 | note | VERIFYING DOCUMENTS: This ITP
f49d177e-84bb-5c1d-ac83-f1287885f725 | textbox | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Pile Trimming
a35a1395-5ba0-51c8-bd80-b3a6f555dc26 | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 606.06 (a & b)
06baa5f0-cb05-58b2-8e4a-cb9440e19e62 | note | – – – – – – – – – – – – – – – – –
497334a1-4237-589a-a972-8165d7bafa99 | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
e81c681e-a3fc-5f71-86c7-f3425b1c51c4 | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
2cdf6ad6-0df0-53b9-9c73-d1b91b13ab1b | note | • Any weak or damaged concrete shall be removed back to sound concrete.
d513c63d-65ef-5340-bed2-1ffa52547244 | note | – – – – – – – – – – – – – – – – –
a7531f63-444f-531f-806e-a81a928260d7 | note | METHOD: Measure, Visual
39f0b93e-8c5d-5b18-8e1e-59c79845a93a | note | – – – – – – – – – – – – – – – – –
5feef4a9-1091-5c67-94e9-5d010a457afb | note | FREQUENCY: Where applicable, each pile
ddd7e43d-2a0b-5ef5-84c8-a1a1e0fc8ec9 | note | – – – – – – – – – – – – – – – – –
ce078fa7-2f28-5199-8383-1d70ec2df69d | note | CATEGORY: IP
cd75d82e-f6b6-599c-ab4b-1c434e1c2edf | note | – – – – – – – – – – – – – – – – –
06554806-b026-5685-975c-23597c73dc6f | note | RESPONSIBILITY: SE/PE/SPE
3f47f00e-d1e5-5b4b-992b-13d6a5ca1a31 | note | – – – – – – – – – – – – – – – – –
0af724d2-a189-54e9-b86a-502aee1e18f0 | note | VERIFYING DOCUMENTS: This ITP
ae5c577a-8921-55a2-8779-78b8a2391b57 | textbox | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
cbed9ec4-f4ae-52a1-8106-f5675e36d5bc | note | REFERENCE: IFC Drawings Table 610.05.051 610.16 (g)
74d36346-f5f4-52df-a6e8-267398569422 | note | – – – – – – – – – – – – – – – – –
92b3a5fb-9e3c-5489-9ba8-ec26dda0e2c5 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
3d5ca9bc-a78d-516d-8e51-fc6496310dae | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
0786d6dc-f624-509d-b9fa-313d5ad01395 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
92710a56-c23b-5c8b-8445-ba43eae0db35 | note | Attach: Compressive Strength Test Results
877146d2-d4a8-5707-a08d-1781031ef103 | note | – – – – – – – – – – – – – – – – –
a230532e-e713-5813-9b21-26d22d717a3a | note | METHOD: Document Review
1ece919b-c936-5c15-ae74-e4b92ae0e677 | note | – – – – – – – – – – – – – – – – –
6eb7b19a-30ec-597b-8fc4-f3fc6eb4c2c6 | note | FREQUENCY: Each cylinder
dd8c695b-8228-59e4-9258-d570130e9781 | note | – – – – – – – – – – – – – – – – –
065d8868-3c0d-5d17-bd53-be2eb5d82658 | note | CATEGORY: IP
850e472e-f900-5d9b-9fbb-6575e05ba867 | note | – – – – – – – – – – – – – – – – –
7a921fc4-c414-5450-bd8f-1b3ea7fd4ef7 | note | RESPONSIBILITY: SE/PE/SPE
0e02434f-d120-5f0f-8304-420d50949645 | note | – – – – – – – – – – – – – – – – –
31acc580-13b8-5820-9214-101680427fcc | note | VERIFYING DOCUMENTS: This ITP
5c71fd28-65fe-509b-ac3b-f707ea5e7aa7 | textbox | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
34489083-0cf4-5377-97ab-0d15981aacaa | note | REFERENCE: 606.07 (a, d & e) AS2159 Clause 8.8
59def6eb-33aa-50b2-8e51-1463eec49314 | note | – – – – – – – – – – – – – – – – –
8db43e17-e389-5145-9ce2-c6f492b845c0 | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
54229314-3721-5d37-b80a-5a2aa0e10959 | note | • Cross-sectional area = ≥95%
50ae2fe2-74d5-55fe-8aa9-08a78e612210 | note | • If any test fails, all piles shall be tested.
99ec655a-b15c-58e8-8176-969310710dea | note | Attach: Pile Integrity Test Report
4adbd8d8-6e3a-56ea-9bae-6af78e57405f | note | – – – – – – – – – – – – – – – – –
51abb88c-445c-5751-a0bb-5cc4028dfe1d | note | METHOD: Document Review
b7cc1458-3376-5a3b-8a8f-5b8a41df340b | note | – – – – – – – – – – – – – – – – –
d0a0e821-2b79-526a-9c21-3782962857db | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
ee931a78-9eba-5e18-a25a-c072e186eb47 | note | – – – – – – – – – – – – – – – – –
09ad1d2e-13ad-57cf-9b9c-5bbd6d659b8b | note | CATEGORY: IP
51bdf18d-1686-55cf-b37d-22feb688436e | note | – – – – – – – – – – – – – – – – –
a3910dca-276b-5d77-a924-5f36adce41d2 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
9366cf7c-322b-5fdd-9231-ed9fa2cf273f | note | – – – – – – – – – – – – – – – – –
b66620c3-af5b-59e7-9d11-4937f54f6e9b | note | VERIFYING DOCUMENTS: This ITP
a15dcd91-c44e-54aa-8af0-42d0df8c67e8 | textbox | Date Completed:
| checkpoint | 6.4 Static Load Testing
8fa2952e-8b3e-59f4-b359-82d49947a468 | note | REFERENCE: IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
e9dc46dd-2d19-5ab5-9d22-aae75122cf27 | note | – – – – – – – – – – – – – – – – –
c2fd5d9a-fc19-56e9-8779-0f9a2def5daa | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
4f3f9445-9bfd-5a92-8c8a-eb40e8adb94c | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
c394a371-4136-5028-9344-98db2690a5f5 | note | ii. Creep rate = <2mm / log cycle of time at the test load
19f78f32-62e1-5468-895a-96279e815cb0 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
b7bb2580-b435-54a5-9898-af8885b8539c | note | Attach: Static Load Test Report
ea3dee8c-d330-540e-85f5-7b6d5f557b28 | note | – – – – – – – – – – – – – – – – –
0daf8d6a-cc14-5be6-a6ba-0905bbfc7031 | note | METHOD: Document Review
b0278f04-8320-5699-8a79-dcaa0370cde1 | note | – – – – – – – – – – – – – – – – –
2b652acb-90e4-5b7f-8e0c-a74f64c9013a | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
2d3c8ed2-c3a4-5aa9-9475-742de5364346 | note | – – – – – – – – – – – – – – – – –
a6fc1eb1-134b-5821-afb3-db8383cb5b4f | note | CATEGORY: IP
00f2776d-6123-5d4e-afe6-f5da4c8072c5 | note | – – – – – – – – – – – – – – – – –
56c915af-b3cb-52bf-a581-3d605671969d | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
4f50c1c3-4fc7-5546-8a3a-3f23c0639312 | note | – – – – – – – – – – – – – – – – –
2140f516-eafa-5763-8434-d48236e86a42 | note | VERIFYING DOCUMENTS: This ITP
ad2bff45-5e0c-53cd-aa59-fdc3ca05f92c | textbox | Date Completed:
| checkpoint | 6.5 Dynamic Pile Testing
e0fd7af3-817f-5270-b7d8-8c633360d1ad | note | REFERENCE: 606.07 (c, d & e) AS2159 Clause 8.7
9c879cfa-edfa-5ed2-aa08-f5f58d03ea97 | note | – – – – – – – – – – – – – – – – –
fdd57f8c-18cb-5766-97d4-c12615cc1b45 | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
27ac50c3-e764-5f31-8e4c-989092073278 | note | Measured Ultimate capacity = ≥ values on IFC drawings
d0b64a48-a830-5062-ac5d-eaaa82318678 | note | Attach: Dynamic Pile Test Report
b0d61f88-759c-54de-9d79-1cfd499fdfa4 | note | – – – – – – – – – – – – – – – – –
efe95a01-36b4-5bda-a01b-c81d41a6a453 | note | METHOD: Document Review
450f7055-9924-5519-aa1c-14a07c49d788 | note | – – – – – – – – – – – – – – – – –
c96ebc1f-99ff-5132-a1b6-0f5b190e2e9c | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
b1448f93-6028-59c9-b9b5-015a2c8c96f2 | note | – – – – – – – – – – – – – – – – –
3b642563-d674-546c-8271-5a4ecc08a50b | note | CATEGORY: IP
eeea3685-4d92-51da-9f97-d01af1d938cd | note | – – – – – – – – – – – – – – – – –
2d8dc730-bb04-5726-8fe4-23cdedab77f9 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
3e659148-5302-5418-a49e-239b159697fe | note | – – – – – – – – – – – – – – – – –
7dc30864-caf3-5530-9bc6-6e37bed712c3 | note | VERIFYING DOCUMENTS: This ITP
bc3543a7-8f57-52b4-8603-505a0f07e92c | textbox | Date Completed:
| checkpoint | 6.6 As-built Survey
2f4d8cdf-1906-5a27-9e25-0ed3d4ed5d69 | note | REFERENCE: IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
3f15c219-1392-5583-92f8-86205a15170c | note | – – – – – – – – – – – – – – – – –
00f6530a-f988-5c07-ac83-6f968004df49 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
77a5082d-a0a6-514d-ab94-4a4a210b0145 | note | i. Pile head plan location = ±75mm
f5028a51-e933-5fb7-9437-6af72aa60347 | note | ii. Variance from vertical or rake = 1:100
c45fa42f-4160-579f-9044-b7231f441978 | note | iii. Irregularities in straightness = 1:100
4d4212b0-c828-5ad0-be18-03c397270f50 | note | iv. RL = ±25mm
8990839e-1bfb-50e3-af96-a01d70faf6ab | note | Attach: Survey As-builts / Survey Report
41bfeafd-395e-5454-96af-a96f7624af3e | note | – – – – – – – – – – – – – – – – –
e5a33d2e-693d-51c4-bc44-da65dc3d326d | note | METHOD: Document Review
4b1500b9-2771-504f-b4f6-2f9e74d09783 | note | – – – – – – – – – – – – – – – – –
64c02500-df77-5cbf-bbfb-c0add0c7dc5e | note | FREQUENCY: Each pile
fc5a0f51-7c3f-5480-b5e4-30aea4e99ca0 | note | – – – – – – – – – – – – – – – – –
f9ef3e50-e7b4-53f7-84d2-3eece36860c9 | note | CATEGORY: IP
c3c40ace-4d7d-5968-aab9-c7b0ae847e8e | note | – – – – – – – – – – – – – – – – –
2114f26c-5cef-5159-bb49-5de60d42e9db | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
16154ae5-3aee-5865-9126-9d79c7be197c | note | – – – – – – – – – – – – – – – – –
608bc0fc-1634-58a6-a334-c8092b899aa6 | note | VERIFYING DOCUMENTS: This ITP
12204703-9300-5cce-ac1b-17cef2b718cd | textbox | Date Completed:
| checkpoint | 6.7 Non-conformance Report (NCR) Closure
cafe9266-53b6-5392-9679-b1a071be7b2c | note | REFERENCE: MRPA Quality Management Plan
88332635-95a9-5973-bf34-9d4bc34e76eb | note | – – – – – – – – – – – – – – – – –
3711deab-c05e-5df2-9f2c-d51836593294 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
00ef86c3-ef4f-5dcc-b629-ae514f6ee85e | note | – – – – – – – – – – – – – – – – –
8c9c699d-8f01-5ba8-9a33-e8e2a89b6e62 | note | METHOD: Document Review
502988e0-7ceb-588f-a899-216454e5346f | note | – – – – – – – – – – – – – – – – –
ad983036-4157-5f5a-baa1-496b1070e4ff | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
b8c11c63-386d-51bf-bad1-97ba8d92b27d | note | – – – – – – – – – – – – – – – – –
b1800cd7-0f2d-585d-b1b1-a816ddf80826 | note | CATEGORY: HP*
b18c3f9b-5d8a-5a1c-b034-1fcf5105fa9e | note | – – – – – – – – – – – – – – – – –
340dadef-d945-50c5-bd59-2768337d1174 | note | RESPONSIBILITY: SE/PE/SPE
b9788f93-bb61-5a88-826d-02f157a65662 | note | – – – – – – – – – – – – – – – – –
fd10df2a-a440-5349-be4c-50b125be4617 | note | VERIFYING DOCUMENTS: This ITP
9c689bc4-dd86-58f8-8914-d38923729003 | textbox | Date Completed:
| checkpoint | Final Inspection
600c0e73-1d0b-5d6d-8436-164f25379f77 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
34953e20-dec5-504c-9fde-76bc5ee207ad | textbox | Name:
3425c2e7-9c84-5a30-805b-afa9a69dd763 | textbox | Position:
beff82c2-e6aa-5ba5-91c5-15888ce25759 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-056-CIV-SSB-Subgrade Preparation - Road Rev 0 | itp | ITP-056-CIV-SSB-Subgrade Preparation - Road | c47369ae-e017-4a33-93e0-e81567b3736d
| section | Referenced Documentation
| checkpoint | Referenced Documentation
43f1a6b4-521c-559b-8716-f46c9ba08ad4 | note | Document Title: ITP-CIV-SSB-Subgrade Preparation - Road
fd3dd5b3-7d7b-5f48-b032-e8f438be3fe4 | note | ITP Description: SSB-Subgrade Preparation - Road
4d5aaeca-1881-5e6b-9463-7d44ffbbbfeb | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c21832a1-4fb4-5bf6-9b42-2247a076b161 | note | Discipline (e.g. CIV/STR/RAIL): CIV
273c51aa-23c8-54a0-9ca9-9d662907b064 | note | Revision Number: 0
c4f95be2-ffb3-5317-aec3-4311cd96b507 | note | Revision Date: 11/08/2023
df307c58-caf9-5e44-af0e-ab400354add8 | note | ITP approved for use by: Victor Mira
e3771424-2177-5951-8a50-765b9db83fd7 | note | 1.1 Non Dependent
050dfb9d-9974-5f4b-861b-7fdc3755b27b | note | Reference: VicRoads Section 204
54fec37a-c5ae-5cea-a2d2-d31c51433b9a | note | 1.2 Non Dependent
e5b25163-fbed-5585-82e1-8dfc3a7fd833 | note | Reference: VicRoads Section 173
| section | Preliminaries-Materials
| checkpoint | 2.1 Material Approval
72862695-1125-5a19-87e8-a3086266123e | note | REFERENCE: VR 204.04 (C)
f198a012-b50c-5b02-8bd2-0bcf5bdd43ac | note | – – – – – – – – – – – – – – – – –
969b55b7-eeff-51b8-baa2-39a6267e1ff2 | note | ACCEPTANCE CRITERIA: Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
74f5db17-7f5d-5510-ac53-0331d7c591db | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
21c18480-bf8f-5b5d-bae6-2a8a6985e210 | textbox | Enter: Teambinder Material Approval number
99073c38-e0bf-57db-97b7-2b7e28f304e7 | note | – – – – – – – – – – – – – – – – –
69170ad1-8c52-522f-939a-f1fb7b5f095c | note | METHOD: Document Review
360c2264-ad88-588c-89e9-b9d2d355a0d2 | note | – – – – – – – – – – – – – – – – –
c4fcfbe9-e148-5bda-935d-bd0ceae7255f | note | FREQUENCY: Once, for each mix material
2e261e98-2b0f-5492-a21a-946ab3d31782 | note | – – – – – – – – – – – – – – – – –
a2d10b82-a27f-5b76-bed1-7708277f048d | note | CATEGORY: HP
127a1708-9efe-579c-ba39-d9a8fd49a661 | note | – – – – – – – – – – – – – – – – –
e1e10970-820d-56ed-bf76-4bb02080ea11 | note | RESPONSIBILITY: Nominated Authority
66c931c3-bc1c-56fd-a92c-4fce157acae9 | note | – – – – – – – – – – – – – – – – –
b6ed2c20-9b1f-564f-9ccf-e5a47bd9986f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
03106aa2-ea45-5ac6-9289-2c505d5288c8 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Non Dependent
7fc23713-ec1c-56f5-b3d8-c82560876c5c | note | REFERENCE: N/A
a7807b01-e0d0-5390-9c01-76943f23be17 | note | – – – – – – – – – – – – – – – – –
24a28126-4db6-51e3-9608-d750166eaf62 | note | ACCEPTANCE CRITERIA: N/A
c40c586b-83af-5800-a7ee-b722a002f587 | note | – – – – – – – – – – – – – – – – –
7d42cecd-ac90-5ed0-a21c-20a9e9454e93 | note | METHOD: N/A
5222a907-62ee-5708-ab99-678b69d4f1e8 | note | – – – – – – – – – – – – – – – – –
36673688-a8fe-5f44-94b8-6ba7be9038bd | note | FREQUENCY: N/A
791b7f6d-1f45-582a-b587-e62a40c54d19 | note | – – – – – – – – – – – – – – – – –
90232f03-c94b-52f5-bc1c-103a5906271c | note | CATEGORY: N/A
5f2b51cf-18ab-57c0-841f-3afded2abab2 | note | – – – – – – – – – – – – – – – – –
a43175ae-62fe-505b-b60f-897cb6a773dc | note | RESPONSIBILITY: N/A
b3d4c8bc-2115-5b67-9fc8-2ba7e6143b38 | note | – – – – – – – – – – – – – – – – –
0a941dfb-53aa-5cf4-8a63-3d1d59f36021 | note | VERIFYING DOCUMENTS: N/A
3602c07d-7085-5791-a9bc-cff0a09980dc | note | Date Completed: N/A
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-Out
ca3cb0a6-e33a-5102-9f88-58439fec3ad2 | note | REFERENCE: IFC Drawings
9c124884-1468-5904-9a7a-f9ace9b8a736 | note | – – – – – – – – – – – – – – – – –
3d24f37b-6574-5264-955f-8eb067f02cd4 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
de6e43e0-395a-507a-9fea-f77fa852ce20 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
ec380872-4b3d-585f-9495-643285373ea8 | note | – – – – – – – – – – – – – – – – –
17b002d8-2d9d-56b7-bc94-9d35c15f543b | note | METHOD: Verify
d2f2867c-c725-512e-8ec0-4603d0373de9 | note | – – – – – – – – – – – – – – – – –
b7e924df-e3ee-569c-9daf-9828694098ad | note | FREQUENCY: Prior to commencement of excavation
4788bd36-9cc8-53c0-b954-5f61fcd2dd6e | note | – – – – – – – – – – – – – – – – –
65cca9f7-fea9-5b6d-98e5-d07d7d2b5457 | note | CATEGORY: IP
97cf5727-7833-556d-977d-2a0b6fda2265 | note | – – – – – – – – – – – – – – – – –
65fe314d-7685-5321-a54e-36fa8794a140 | note | RESPONSIBILITY: SE/Surveyor
976675df-2906-5be8-808d-2e0126fc27e7 | note | – – – – – – – – – – – – – – – – –
9814210e-82df-53c1-8973-b828b0d2710a | note | VERIFYING DOCUMENTS: This ITP
e5274ee4-d38e-5efa-80e8-c59632623e0a | textbox | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
9a7fb192-5f58-5baf-b993-32b2908b58a6 | note | REFERENCE: Section 204.06 (c), Section 204.06 (e) IFC Drawings
c4339e6c-ad67-573b-ac97-73935c402f87 | note | – – – – – – – – – – – – – – – – –
d12d64b4-4640-5eea-996b-893b7842669a | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
b51e5b02-6e5a-54c2-a776-912d81a88538 | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
2576035e-f803-5df4-816b-119461caa397 | note | ○ Assigned CBR ≥ 2.5%
b3918b64-014a-5b53-bb67-860de0577f60 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
77de24b1-24d7-556b-9618-e85388d35bd4 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
d428b87a-62f0-5abc-bff4-12c5c705d25f | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
9c3c3cdb-a2f1-5457-a2fd-878a49fbb6c4 | note | Attach: Laboratory testing Verification:
9f88e21c-fde8-5859-b780-7c7ae86a66c8 | textbox | Enter: Type A fill Lot Number:
b845a033-d7c2-59ab-9b0c-7ccba176f38f | note | – – – – – – – – – – – – – – – – –
4be2c54d-e431-5829-8075-3b1c4ed5a175 | note | METHOD: Verify-Document Review
b4bf38ba-dc97-534d-9258-356ea9020450 | note | – – – – – – – – – – – – – – – – –
a652ef41-06e5-5108-9f9c-1151d9f5f321 | note | FREQUENCY: Each lot
2fe936a8-30d6-5281-bec6-78d2b59738fe | note | – – – – – – – – – – – – – – – – –
4422d136-0e87-599e-8239-50f383c7e8fc | note | CATEGORY: HP
e3c54ca0-ce71-5c2a-bef6-7d18ef19ac38 | note | – – – – – – – – – – – – – – – – –
d444da0e-7d61-539e-8aad-f1af07b9a51c | note | RESPONSIBILITY: PE/Nominated Authority
429aa6b7-49ef-5f86-bb5e-3293de259e2d | note | – – – – – – – – – – – – – – – – –
be3fa3fd-dd88-5320-903c-48928607e25c | note | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
98ffe92d-3d8b-5e46-8188-183f4cb8d0ea | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 Material classified as silt
21c0c27d-724a-58b4-b0a2-580c089a1773 | note | REFERENCE: Section 204.04 b)
70dd408c-793b-5852-85d3-ac0fd2bce180 | note | – – – – – – – – – – – – – – – – –
7628b37d-15c6-5e93-9e44-5bfabdba07e5 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
9f1f25ca-c335-50f3-94af-421fae5cd320 | note | – – – – – – – – – – – – – – – – –
09f9440d-debe-52ea-9579-f171504e2225 | note | METHOD: Document Review
a69488af-9cd8-5659-a02b-a0690ef39056 | note | – – – – – – – – – – – – – – – – –
5dd1ba1b-e446-536b-8a3f-9b7926f2c0d1 | note | FREQUENCY: Prior to commencing
7b4fac0d-7135-5dec-9f76-9cbef350bcb7 | note | – – – – – – – – – – – – – – – – –
4ec2fd2d-1401-551c-bca2-37e1ca2bf1df | note | CATEGORY: HP
d0cf831e-fbc8-5001-be13-191c08cb6b02 | note | – – – – – – – – – – – – – – – – –
ba6af5a2-c58d-5f25-b500-4c4d2527fe00 | note | RESPONSIBILITY: SE/Nominated Authority
1e6676c4-65bb-5cbb-9b43-e40ba7fa2bed | note | – – – – – – – – – – – – – – – – –
a82bdc1d-5e8f-59cd-b799-017a7b915bf8 | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/ records
6cbadbab-282e-55be-99f3-e64b78d1b860 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
f1b4ab8d-656a-5380-88e0-78c061e55fec | note | REFERENCE: Section 204.06 f)
e5dee5ea-ff0f-5b79-989a-d6b63c2b2fc3 | note | – – – – – – – – – – – – – – – – –
e5643806-96a8-50af-b396-c5492e8113db | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
9374921d-471b-55b4-a848-f0a556704c88 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
fc95fd9a-6bb5-578f-b2cd-50824bb644e6 | note | – – – – – – – – – – – – – – – – –
3dee2f0f-b636-5d95-a0ce-dec007396cf4 | note | METHOD: Site Inspection/ Document Review
754765f0-3b95-5cb4-8f56-1c4ccd9592fd | note | – – – – – – – – – – – – – – – – –
d61c5edb-d893-57ef-8323-5490d18bbc3e | note | FREQUENCY: Prior construction of the regulating layer
d2c562d1-2460-50c0-8a6b-052f44089179 | note | – – – – – – – – – – – – – – – – –
fffc0ae2-ae73-5d30-b06b-16a5857b4a5e | note | CATEGORY: HP
4b0c2042-4483-5220-84b4-7d48d866db6e | note | – – – – – – – – – – – – – – – – –
9ba87b82-10d3-52eb-b8c4-f4906cfc23be | note | RESPONSIBILITY: SE/Nominated Authority
52d51c3a-cfa4-5eb9-a9aa-cfcf79997bec | note | – – – – – – – – – – – – – – – – –
475efa8e-0125-5129-8283-02fc54367e40 | note | VERIFYING DOCUMENTS: This ITP
a5304167-9904-5334-ad52-c0d7cfb22d30 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Unsuitable Material
263648d1-3b90-5917-b80a-6f991e3ddd59 | note | REFERENCE: Section 204.07 d)
0c81f2e8-f8c6-528e-bf33-0e5f92a35c28 | note | – – – – – – – – – – – – – – – – –
40385ad7-4258-5a78-9b7a-9a00acf0cf39 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
dfd4e832-54c2-56f7-8419-81374646c17e | note | – – – – – – – – – – – – – – – – –
b2c2ae2b-bad8-5a70-957f-6a77b6ba4489 | note | METHOD: Visual inspection
882ef4bc-11b5-5566-bf65-61b1e45ccdcb | note | – – – – – – – – – – – – – – – – –
906b7737-a966-50bf-bcd2-aa586a67c9e7 | note | FREQUENCY: Each lot
a4c86912-cbaa-5283-ae2f-2fbb65bc89ff | note | – – – – – – – – – – – – – – – – –
525545d4-e116-5a2b-b09d-290beb6936f8 | note | CATEGORY: HP
4b67f3b2-745c-5a2c-8fa3-2aed71d49c40 | note | – – – – – – – – – – – – – – – – –
19260519-9ba4-5c81-a6ea-b0b75742cf29 | note | RESPONSIBILITY: SE/Nominated Authority
d2e81e58-dd36-5fd6-818d-43296fc29bdc | note | – – – – – – – – – – – – – – – – –
b761b80f-92cf-59ce-a5af-29d10ad1f065 | note | VERIFYING DOCUMENTS: This ITP
ab19cf57-64d6-58d5-9e25-e2a0b9465a97 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 Groundwater
152e1013-f707-522a-8e78-3bca87fde8fc | note | REFERENCE: Section 204.06 h)
c0e3c65c-a7f0-520e-9dfb-122de4ccba16 | note | – – – – – – – – – – – – – – – – –
5115ecd2-7d5a-5d4e-9566-b7386c86bd03 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
b14fa0dc-c5b5-5dda-aada-d828d5beeb6b | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
30781549-88cc-5914-ab5c-7fce6afaaa64 | note | – – – – – – – – – – – – – – – – –
3f39096c-6973-54b8-a3e8-a52c21e26ef3 | note | METHOD: Visual inspection
fdc3d21b-6fe0-51e2-9516-994f405a9234 | note | – – – – – – – – – – – – – – – – –
f35ba411-65fc-55eb-9f42-40e4982043c1 | note | FREQUENCY: Each lot
9785ac06-6456-531a-9aab-0a0520fa9a51 | note | – – – – – – – – – – – – – – – – –
b6dc25d8-1ee3-532d-9d03-53f9259ed7e6 | note | CATEGORY: HP
baa9e1c5-baee-56d0-8e6a-47c4f062fbbd | note | – – – – – – – – – – – – – – – – –
70e757e7-16f3-5b59-92c3-8feec91d9bb4 | note | RESPONSIBILITY: SE/Nominated Authority
2f31140c-68be-592c-aa36-d667c6f2fc26 | note | – – – – – – – – – – – – – – – – –
bf5ae979-82d8-593f-82f3-cb4cace083b5 | note | VERIFYING DOCUMENTS: This ITP
def140bd-38db-596b-b360-d5ad09c3cdd4 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Cut to Fill Zones
ddcfb788-d94c-5697-8841-4b16c2f4e110 | note | REFERENCE: Section 204.06 g)
d41763af-bcfe-5419-b6d0-af1359b11072 | note | – – – – – – – – – – – – – – – – –
11e8e4d9-8fb9-506f-910b-777f5aa1a7fe | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
618026d6-1010-55e0-98e6-ca612b7f222b | note | – – – – – – – – – – – – – – – – –
919d220f-7780-54bf-a21f-91700f16d9d2 | note | METHOD: Site Inspection
c5583104-8770-5120-8367-0862de976328 | note | – – – – – – – – – – – – – – – – –
33b7f408-5ba3-55eb-8c48-edc7e1ad3283 | note | FREQUENCY: Each lot
bfc7900f-7e5f-5945-a6a2-50e88d3ef1de | note | – – – – – – – – – – – – – – – – –
143e6b06-f90f-55d9-8356-ed6308e3aa04 | note | CATEGORY: IP
ba9ba640-a25b-5233-974b-efe22267ade0 | note | – – – – – – – – – – – – – – – – –
bb198729-6790-515a-aa5a-9ed17feaac4d | note | RESPONSIBILITY: SE/Site Supervisor
8d6e5b43-6c6e-5a86-8719-2bd4ce1a69da | note | – – – – – – – – – – – – – – – – –
cb56ef4a-5908-501e-8634-13c3a7442a41 | note | VERIFYING DOCUMENTS: Sign ITP
d023d1c0-fc18-5b02-b1de-d87f9425b1d9 | textbox | Date Completed:
| checkpoint | 5.7 Proof Roll
3b50f972-5138-52bc-b19a-002be202d65d | note | REFERENCE: Section 173
a96d8080-d2e6-5c46-8d4d-26a6d2575db3 | note | – – – – – – – – – – – – – – – – –
1f6fe37a-7e89-5bb4-a631-e60a007e3e21 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
446745fb-0847-5585-a3d2-c30bff017d95 | note | – – – – – – – – – – – – – – – – –
a63518ff-0ae2-5e2c-ace4-257438c13126 | note | METHOD: Visual inspection
bcf1accc-0e7a-50e1-bd32-0ca79736d882 | note | – – – – – – – – – – – – – – – – –
8785a5d3-750d-539a-bcb9-8cad567a38d4 | note | FREQUENCY: Each lot
9d3546ac-2f88-5c6e-a588-601c9a41f6e7 | note | – – – – – – – – – – – – – – – – –
90dc1a5f-9ed3-57de-8a78-8373f7821cfd | note | CATEGORY: HP
ecf82675-f1c4-51d5-8608-fee86ea5a2da | note | – – – – – – – – – – – – – – – – –
787ba668-dfef-5b8a-82b4-abc9294bb95f | note | RESPONSIBILITY: SE/Nominated Authority
920f8aff-c366-5870-92f9-0ca2f5fec438 | note | – – – – – – – – – – – – – – – – –
72d3af76-fc09-50ee-8dfc-55eeb0191980 | note | VERIFYING DOCUMENTS: This ITP
fef5ca9d-5bc5-5d0f-8d19-dee01bcbfd8d | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 Compaction Testing
d261768c-41b4-5a41-a790-056ff1c9fd93 | note | REFERENCE: Table 204.131
98aeec87-3f3b-5025-9423-d41767d4618a | note | – – – – – – – – – – – – – – – – –
bb15fd21-45f7-5628-b3f2-355fa70e11aa | note | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
f4d00e56-a660-5218-857c-c709aa90b1b9 | note | ○ Ripped and re-compacted material below Cut Floor Level
b495fe56-ee36-5ab1-8b3b-4f66fa351187 | note | ○ Scale A: Characteristic Density Ratio 99%.
043dbcdc-ed9d-5643-9946-2a16b439d8aa | note | ○ Scale B: Characteristic Density Ratio 98%.
d01b9687-ceb4-5dc5-80b5-125220127a1f | note | ○ Scale C: Mean Value of Density Ratio: 100%
e48f4bb7-b774-5ddd-8eec-b2d836924a17 | note | Attach: Compaction Test Result:
c4602536-8e26-591b-bf8d-cf1a8693bb49 | note | – – – – – – – – – – – – – – – – –
218b1e14-8250-5d0e-987d-d3140bc04821 | note | METHOD: Document Review
d0550e8d-8474-575c-a1d9-ebb9763cd94c | note | – – – – – – – – – – – – – – – – –
7a1f6b90-cbd5-59ce-8e88-c92697e54a87 | note | FREQUENCY: Each lot
88ebffb2-6f51-5c01-8227-db0026f0d2d3 | note | – – – – – – – – – – – – – – – – –
9fbfcd89-40b7-5d87-837a-29dec83ee075 | note | CATEGORY: IP
5c40642a-91ec-554a-b3cb-95823373a4c0 | note | – – – – – – – – – – – – – – – – –
bb09f10f-88d5-5ccd-8c57-d6fc4a0ec15a | note | RESPONSIBILITY: PE/SE
ad57c6f2-d44d-5196-aef7-cf5cb4a1b5cd | note | – – – – – – – – – – – – – – – – –
4163a074-01dc-5407-b9ac-88620c8d2f9f | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
439a0e88-8eca-551d-8fb3-b59c57f5ecc1 | textbox | Date Completed:
| checkpoint | 5.9 Post Compaction Material Property Testing
ac99a703-9313-5218-9bbd-45ad5139e52d | note | REFERENCE: Section 204.04 (c), Section 204.14 (a) and Table 204.141 For Scal A Section 204.14 (b) for Scale B IFC Drawings
ba418250-5f19-5fba-80c7-93ab9deb293c | note | – – – – – – – – – – – – – – – – –
c119b231-a987-5fe2-9419-6cd1db143982 | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
6a1aafb4-6e09-5fe9-a4d6-362182d574c0 | note | Scale A:
b5389c87-068e-57ff-b21a-140c04da34ec | note | CBR and Swell as per IFC for design packge:
f3052f6a-97f5-5412-91c6-b96ee9c23fab | note | ○ MRP-DPK-087-00-CDR-0002-0
bb34619d-c722-5c44-b5ae-37650617d181 | note | ○ as per table VR 204.141
432a4400-ac83-5ca7-8b7f-4b4293f743ff | note | Scale B:
196ff042-b0cd-5744-846f-fe2a1bf261de | note | CBR and Swell as per IFC for design packge:
fd83fb0c-22fe-5fff-8987-93d82143141c | note | ○ MRP-DPK-087-00-CDR-0002-0
0a9e69ae-0987-5b67-a59c-a41c2254a4ca | note | ○ First Lot for Max Particle Dimension:
ba62fdf4-6fc3-57e0-9e1a-621c4be40955 | note | ○ After compaction Type B material shall have a maximum particle dimension of not more than:
ef4d0d6e-e46a-534d-b8dc-a217094dde62 | note | – 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
5d5ecdd7-d0d5-55f7-aac4-33cb17cd0d51 | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
84f66be1-7eda-58f5-b23f-d3c7b7c08195 | note | Attach: Post compaction test results:
45e3424b-4fce-5d69-901b-10180ec151da | note | – – – – – – – – – – – – – – – – –
539fafb4-685b-5f4d-8d2e-a7332447d0e3 | note | METHOD: Review Document
ee861b40-acfa-5d56-92ae-e668359e97bb | note | – – – – – – – – – – – – – – – – –
b2f834a2-d9e8-5441-8bf6-a540d1fb17c8 | note | FREQUENCY: Refer to Section 204
14d394ad-0fa4-5e45-8268-05cce7ef1c2d | note | – – – – – – – – – – – – – – – – –
e15d7c65-92c6-5df9-a5f3-7004293083f3 | note | CATEGORY: IP
57a9fa61-a0e6-5fd4-a3e2-e2a3c86d2d22 | note | – – – – – – – – – – – – – – – – –
e92f37d2-72f8-56ad-9c01-7670a63f6220 | note | RESPONSIBILITY: PE/SE
ccc79817-abe0-54a0-8357-d5c3ebfa678e | note | – – – – – – – – – – – – – – – – –
f71c1277-2d6e-58dc-adc4-846fc004ab88 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
44471867-362e-531c-b2a0-51f81fe2b6dc | textbox | Date Completed:
| section | Post Construction Activities
| checkpoint | 6.1 Survey Conformance
08321b5e-67c1-5368-80c8-592b2e102b26 | note | REFERENCE: VicRoads 204.03f,g and h
9bc124d4-d01a-5328-8f1b-1fda15bf1fcd | note | – – – – – – – – – – – – – – – – –
6b78f629-e7fd-55dd-b2e5-6a566f62d724 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
c272b85b-6b8f-50df-af67-981fee50fc7e | note | Level tolerances (Scale A):
ffd60f9c-54df-5f24-8224-09343a499d1f | note | ○ Range x = +5, -15mm
d649d53d-0c6e-5844-9335-bc99447f2884 | note | ○ Max S = 12 mm
66d9d045-8aed-52a1-973e-79a88210fa64 | note | ○ 80 measurements per lot
13836022-acde-534d-82b5-d00288961110 | note | Level tolerances (Scale B):
c96be512-c037-5db1-9816-65f2971d5509 | note | ○ Range x = +5, -25mm
b68d04c4-5b2d-54b1-89a7-7389bd1256c9 | note | ○ Max S = 15 mm
237c2e45-0de3-520e-94d1-3cd07e25331f | note | ○ 40 measurements per lot
f8f7ea42-f4ac-5946-956f-65272f3b7b77 | note | Level tolerances (Scale C):
b0205a51-7117-5688-b6f0-8abc8c07f63c | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
8a9ec1ac-ae9d-5e88-9d6d-1613af00f74e | note | – – – – – – – – – – – – – – – – –
f8fbeb2e-2d28-5bdd-8bfe-ceba3e509969 | note | METHOD: Review Document
ca3cbdbb-ef47-5329-916b-8892b6eab40c | note | – – – – – – – – – – – – – – – – –
df4eb765-a079-5692-8b0c-41c8f651b230 | note | FREQUENCY: Each lot
20f347f0-3b05-5764-a09b-25100f76d129 | note | – – – – – – – – – – – – – – – – –
97d41209-01db-5be6-82ec-8f53bbc8eab9 | note | CATEGORY: SCP
ed2b9122-9072-5c85-b7cf-b18fb3b4add8 | note | – – – – – – – – – – – – – – – – –
c59a9788-cb66-5a05-a73f-964b0b58ddf3 | note | RESPONSIBILITY: SE/Surveyor
82aa7d03-47e9-5542-8cae-1a746deb6b4c | note | – – – – – – – – – – – – – – – – –
c8bbeafd-7197-5c2f-a975-70a10f780ca8 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
742513f2-d118-510b-8b49-efe6b50d9b07 | textbox | Date Completed:
| checkpoint | Final Inspection
c05c783b-5b0f-519a-88f6-b1daaa6d8cca | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2f7954a7-3d9c-537a-a150-28fb0564b9d6 | textbox | Name:
278a50b3-e91e-5274-9bcd-7533476aae5f | textbox | Position:
b33132bd-0368-52c3-8914-c4c21fa16718 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing Rev 0 | itp | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing | 6c87b5eb-de3d-467a-a162-126d74a04804
| section | Referenced Documentation
| checkpoint | Referenced Documentation
ec9d73c8-ad39-520b-ae67-0fba6f606d6c | note | Document Title: ITP-CIV-SSB-Rail Delineation Temporary Fencing
332b2197-155a-5209-a978-753baacc2640 | note | ITP Description: Rail Delineation Temporary Fencing for Camms Road
e9b41770-43a8-598b-b852-e34148cb9f5f | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
b8f52ffa-a427-5227-92c4-adb0d6c3ff40 | note | Discipline (e.g. CIV/STR/RAIL): CIV
c77a6e1d-3785-559b-a88d-eb1c9bbb8e1b | note | Revision Number: 0
177694cb-fb29-553a-abae-153c51ca0e2b | note | Revision Date: 11/08/2023
c185b33b-1b7d-51fd-94a9-22b0239a8f74 | note | ITP created by: Isaac El Zayat
d9c7c88e-04bd-5392-9ba2-c3b401f16996 | note | ITP approved for use by: Aldrin Guinchoma
ce94261a-8749-5de5-b86a-5ad6e0f26349 | note | 1.1 Non Dependent
2e4290a9-27c0-5938-89c6-1aaf547955db | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
| section | Preliminaries-Materials
| checkpoint | 2.1 Concrete
4a78021c-33ea-5853-af05-31394837c17f | note | REFERENCE: IFC Drawings
a62c25db-85fd-5d30-8415-32b9d7e61eb8 | note | – – – – – – – – – – – – – – – – –
21e60ba6-dddb-51fd-8acb-469ea603df23 | note | ACCEPTANCE CRITERIA: 32MPa concrete to be used as per IFC drawings.
09c81732-154d-5489-b745-d121bf8ea13f | note | – – – – – – – – – – – – – – – – –
5bc24c93-ac54-57e0-b010-2acad315b789 | note | METHOD: Document Review
dd595eb5-5f7b-5640-b440-52335ab84a8c | note | – – – – – – – – – – – – – – – – –
c2daac0a-1ebd-548c-9881-58eb26a2f631 | note | FREQUENCY: Each Mix
07933187-3632-5217-9f5a-83b863d6a1e8 | note | – – – – – – – – – – – – – – – – –
2874d2cd-74f4-59b8-9717-7a78b49d2032 | note | CATEGORY: HP
f0d3cef4-5d03-5dd9-b7fd-8c6102e39f7c | note | – – – – – – – – – – – – – – – – –
d542df31-513c-50c1-b84f-e2796a7bc1bb | note | RESPONSIBILITY: SE/Site Supervisor
26b06228-a51c-58c9-baa8-839d816614b2 | note | – – – – – – – – – – – – – – – – –
c81bc904-0551-50db-915b-f4a72273219d | note | VERIFYING DOCUMENTS: Certificate of Compliance
4a44364c-e899-5036-b4e9-506466180010 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Steel components
b30eeef2-ffc4-5bde-b6f3-f677f0280087 | note | REFERENCE: IFC Drawings AS41000, AS1163
285fecec-9482-5e69-b491-d2745eb68497 | note | – – – – – – – – – – – – – – – – –
f4475997-e8b4-5632-9fed-41c83671f1ca | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
bd682eda-b412-5082-b1a5-97a96839c744 | note | ○ Steel section sizes must be checked on site.
f5ff98ce-241e-5bed-9957-084504462119 | note | ○ Steel posts to be CHS with a grade of C250
f9479c56-3e9a-53d5-a606-7aca77fd7919 | note | – – – – – – – – – – – – – – – – –
cc18b9df-8005-5c8c-aa54-f8f4fafc15a5 | note | METHOD: Document review, Visual and Measure
f0504c31-21c3-5d09-ab0c-4aeed7292947 | note | – – – – – – – – – – – – – – – – –
8e6ce503-9ea9-5336-985d-d0091fa79452 | note | FREQUENCY: All elements
55631e09-091d-5ee1-bb43-ed81790ae083 | note | – – – – – – – – – – – – – – – – –
6233ec51-54d9-5e81-9f93-38427557ae59 | note | CATEGORY: IP
a3200242-9e7b-5939-b566-d9ace19f6bf5 | note | – – – – – – – – – – – – – – – – –
dd60bcb9-5b44-5c75-a2d9-27e1b3d19e58 | note | RESPONSIBILITY: SE/Site Supervisor
ea0e1a05-0360-54ee-b72d-4b9fd7ed6665 | note | – – – – – – – – – – – – – – – – –
0cd153f9-7c3e-5709-8599-a28bd4e0382a | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
71660e72-f831-5b48-9803-316adc293132 | textbox | Date Completed:
| section | Preliminaries-Documentations
| checkpoint | 3.1 Excavation works
1ce32fc0-60cc-52d3-9e16-f6fbd5a2ee8b | note | REFERENCE: IFC Drawings L1-CHE-STD-005
551e9f4b-b6a6-5893-bd5e-e1b5ad307ff7 | note | – – – – – – – – – – – – – – – – –
9cfed8be-e4c3-56e4-a366-d6ceb5c5fbe5 | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine track and comply with PTDT requirements.
c66e598c-d606-5119-b4e9-217dd99b5b64 | note | ○ Follow asset owners guidelines for work around their service.
1c85925c-5e89-544d-836f-0e747618ede6 | note | ○ Excavation must use Non Distructive Digging in the rail corridor
f1c79e83-1753-542e-8977-4032d01e1169 | note | – – – – – – – – – – – – – – – – –
ebda8d61-c159-515b-bbfd-f057547b09ea | note | METHOD: Visual
862645ee-f440-56aa-9056-abcd1fde8457 | note | – – – – – – – – – – – – – – – – –
e6482c43-47bd-5f29-ae18-b4df4dab5759 | note | CATEGORY: IP
f16f4022-deb7-5b4f-809e-04afc50f4055 | note | – – – – – – – – – – – – – – – – –
711cbbbe-b1cf-59af-8207-1412e798439a | note | RESPONSIBILITY: SE/Site Supervisor
0a27d7ac-d712-5826-ab89-39ef05f97a47 | note | – – – – – – – – – – – – – – – – –
55d9347b-3565-596e-90b3-c41882558d96 | note | VERIFYING DOCUMENTS: This ITP
86daf07d-3f50-5c62-9824-635b7ae355f6 | textbox | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out
8631d05f-4b77-5cb5-9a2d-0fdca28fbccb | note | REFERENCE: IFC Drawings
0fb51cb3-0c09-5d3e-a144-d348f737ac63 | note | – – – – – – – – – – – – – – – – –
4831ba62-74d1-5b82-abf5-1fcde34f728b | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
a25fcc91-cf50-5466-ae17-8e90440aa4ad | note | ○ Offset checked against the running edge prior to installation of posts.
010a4776-141c-519c-a941-e781468cee78 | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
9d5e1af0-75ab-5ee7-b50d-3cf40000d2a2 | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
f9a472db-2fbc-5f7b-94b8-33f4b004db0c | note | – – – – – – – – – – – – – – – – –
f0f11594-9290-540c-821d-a636023e8417 | note | METHOD: Measure, Visual inspect
d54c7543-6046-5d85-b387-0f5bebe4c050 | note | – – – – – – – – – – – – – – – – –
67d7ab01-ceff-58dc-9bbf-a459edda10e2 | note | FREQUENCY: Each element
fd0ac6b1-b7e7-5c20-8deb-5181876a1a3b | note | – – – – – – – – – – – – – – – – –
de202cc5-3c9a-52ea-a7fc-6dcecd15d817 | note | CATEGORY: IP
7c4b3350-8bca-5cb2-947b-32bbefe6468d | note | – – – – – – – – – – – – – – – – –
b476da41-ec15-5af9-bcce-3afb998d1638 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
a969ae34-013e-5f74-ae1d-f2e8aa39614b | note | – – – – – – – – – – – – – – – – –
548d3a69-cde6-5187-b0ca-804a85d8c46a | note | VERIFYING DOCUMENTS: This ITP
26f9c3dc-51d4-5760-87ca-bbdef40ab0db | textbox | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Ground Conditions
726fb64b-4e44-5b85-aa4e-068072eba8fe | note | REFERENCE: IFC Drawings
d0f466e2-f62a-5fec-b27f-6d89e091e94c | note | – – – – – – – – – – – – – – – – –
72d01026-9c8f-5d36-938e-8dff910815a4 | note | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
2c866593-2b41-5404-a7bd-e393b36b50b9 | note | – – – – – – – – – – – – – – – – –
69d289fe-53d7-5050-846b-71cd1da71a36 | note | METHOD: Visual
a52c2c35-2bcb-5b69-87ec-77fa193e7e6b | note | – – – – – – – – – – – – – – – – –
c34a4ba0-48be-550e-9b5d-ae9fe023ba6a | note | FREQUENCY: Each post
64efbcb2-91e0-58cb-9480-480eb5eb5071 | note | – – – – – – – – – – – – – – – – –
a7752b9d-5386-55c7-b13a-aa8dded4f51b | note | CATEGORY: IP
6e80c0e3-be96-5699-a2bf-a2ad70864ff6 | note | – – – – – – – – – – – – – – – – –
a27aae94-0de2-596f-b0e4-8a282cbd07dc | note | RESPONSIBILITY: SE/Site Supervisor
ee3fbe81-e3d8-519b-a274-8632be3c0bc1 | note | – – – – – – – – – – – – – – – – –
f80cb3c5-5ecf-5343-b30e-fc7ecdaa892a | note | VERIFYING DOCUMENTS: This ITP
9d9c53a1-1522-5a00-92f1-3d26f5b6bd47 | textbox | Date Completed:
| checkpoint | 5.2 Post Foundation
3446ceea-4454-5f9c-8f53-5d0f274d8295 | note | REFERENCE: IFC Drawings
d33f6558-c39b-54ff-8a50-64bd78e181c1 | note | – – – – – – – – – – – – – – – – –
d4a82137-26ff-55ed-958c-9080ce3eb96f | note | ACCEPTANCE CRITERIA: Concrete
69763eff-b431-54a0-a7b3-2c0fa6fe2564 | note | – 300mm Dia
7a7a2493-13eb-58ad-a6cf-2352584efd44 | note | – 1000 mm Depth
1a16fcd6-b039-5d2f-b59f-9eb8ba821da0 | note | CHS Sleeve:
9da1f657-cfe0-5c42-854b-db649e58b2a1 | note | – Depth 1400
91c3dbf1-7e9c-5a81-b229-5d2455ee860b | note | – Other Dimensions as per IFC
a09fd334-165d-566b-80fb-246a3ee96860 | note | Direct Driven:
e94e8e57-150d-5d73-bd08-8d70b9cf06c4 | note | – 88.9x4 CHS
2b040436-a7b0-54db-8ac4-5d60a9d0f8c2 | note | – Depth: 1500
f9759267-9b29-55b0-8ecc-86d26cb774a8 | note | Spacings:
55dc6496-5687-5dbe-bdbf-33eb723097f0 | note | ○ Typical: 2700 max
9798de3c-e4f9-5669-8a67-89331b703fe9 | note | ○ Gates: 1350
ec307f70-e980-53b9-923f-4c4d45ba214a | note | ○ Refuge: 1200
bea79e93-a762-5651-a18c-a15f20929811 | note | – – – – – – – – – – – – – – – – –
a02bce53-cc42-5b2b-8678-f11f65d3b360 | note | METHOD: Measure
5347af57-0498-5b28-bfe2-dae14be60741 | note | – – – – – – – – – – – – – – – – –
7588c96b-c495-5be8-a991-420fd1a1af19 | note | FREQUENCY: Each footing
65e52681-7886-5181-9433-111e3176e3ef | note | – – – – – – – – – – – – – – – – –
e39cb3c0-0c0a-5514-918c-516a4ad99d24 | note | CATEGORY: IP
049ce94e-ecb4-5aba-b96c-fe761f795f00 | note | – – – – – – – – – – – – – – – – –
21405875-fa14-5d7b-86f8-18a1118e33a9 | note | RESPONSIBILITY: SE/Site Supervisor
fe16ac70-7456-5b60-8204-4db30b652b16 | note | – – – – – – – – – – – – – – – – –
8bfa800c-5b72-576d-91d6-8833b5361624 | note | VERIFYING DOCUMENTS: This ITP
453d66a5-56f2-5f07-96b8-fea87c00b7e2 | textbox | Date Completed:
| checkpoint | 5.3 Post Installation
082a1f3e-6519-5fd2-bbc7-301904cfc174 | note | REFERENCE: IFC Drawings L1-CHE-STD-005
b25962d9-92da-54fc-b369-67fe42bd4181 | note | – – – – – – – – – – – – – – – – –
94a329ec-3b7d-54b9-befe-8032f0ce7967 | note | ACCEPTANCE CRITERIA: Up track: Minimum offset 3000mm from centreline of track.
eda6477e-cda3-52de-96f1-72bebfb46cf8 | note | ○ Down track: Minimum offset 2200mm from centreline of track.
9d8f9fa4-6c24-55f1-9507-291b923586fd | note | ○ Maximum post spacing to be 3.1m
fe82249f-ff33-5e38-abe3-c0937cde5852 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
88de0b25-10af-5a39-9413-1637aa81dffc | note | ○ Max. post height 1800mm above ground level.
6a5e3c06-c080-5298-9b12-4b8538ff4378 | note | ○ Vertical Tolerance: ±20mm from the design line.
0d1149b6-cb4a-5e48-a81b-4b6e43354719 | note | – – – – – – – – – – – – – – – – –
2c436b2a-b0ea-54cf-b954-23175f6a7b5f | note | METHOD: Measure
07bbe768-204c-5c2a-9465-34713eb521d2 | note | – – – – – – – – – – – – – – – – –
18b27c06-1340-5aa1-9c2e-3d3e218a1f3c | note | FREQUENCY: Each post
80364c84-0f52-5381-a147-8b4492919e78 | note | – – – – – – – – – – – – – – – – –
25c88331-8888-5265-a381-1b5e7dddd042 | note | CATEGORY: IP
de2c5619-69ab-5243-852c-b2163eca0363 | note | – – – – – – – – – – – – – – – – –
f0163aa8-6941-5a02-b45c-0b5b59d2e24f | note | RESPONSIBILITY: SE/Site Supervisor
36bffe66-b5d5-5e00-b9f5-df0a2f0eff7a | note | – – – – – – – – – – – – – – – – –
5c14e2cd-1c86-52f2-a140-691a108a02cc | note | VERIFYING DOCUMENTS: This ITP
68904b44-93be-5e16-b69d-79e08f68b4bc | textbox | Date Completed:
| checkpoint | 5.4 Chain Wire Mesh Installation
25b27bcd-72fb-581c-8bc6-110af0351257 | note | REFERENCE: IFC Drawings
fae80f24-5c69-597e-b80f-2ab9e75f90ae | note | – – – – – – – – – – – – – – – – –
a9ce0599-a9a9-5770-ad24-05199a46193f | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
5c4b5526-308c-5dd4-9f44-6d22c98bb24e | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
540b7f55-8037-58a8-94d7-8b85ad33a235 | note | – – – – – – – – – – – – – – – – –
e807892d-1672-5464-8ec5-53fc2182dadb | note | METHOD: Visual
035c8f11-bf16-5fd9-ae50-d29e8af16028 | note | – – – – – – – – – – – – – – – – –
bdae91cf-a3b9-528b-a88a-7f2d7ebc5077 | note | FREQUENCY: Each element
c00ccefb-4779-5061-ad2b-894c76e39bc2 | note | – – – – – – – – – – – – – – – – –
fc67b590-b253-52ea-8af4-8c143dbddf67 | note | CATEGORY: IP
b25b21ec-6ec7-5873-bbb0-663d3c31426f | note | – – – – – – – – – – – – – – – – –
07fdacb9-2f00-552d-a8f0-93bafa433583 | note | RESPONSIBILITY: SE/Site Supervisor
449a7ba5-2215-581f-a5f5-a059cc39cc0f | note | – – – – – – – – – – – – – – – – –
07181ad3-457d-50ba-8b94-77959cf1197e | note | VERIFYING DOCUMENTS: This ITP
8b37dd69-644f-59aa-b5ef-f3e92a1be07b | textbox | Date Completed:
| checkpoint | 5.5 Bracing
71254aab-1833-5d22-ae64-4ac53333b449 | note | REFERENCE: IFC Drawings
8db5cbf3-e02e-5e78-98ff-0840bfaa2376 | note | – – – – – – – – – – – – – – – – –
0ffdd3f6-0526-56ab-a249-a901d8c01987 | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
1361af66-5e89-5acf-8fc8-dd17bd950b0d | note | ○ Bracing to be installed on both sides of the fence at the fence corners
ca9053e3-fa46-56aa-8dd2-094b638f2529 | note | – – – – – – – – – – – – – – – – –
d9833b19-b1a1-55b0-9847-cef5fa705727 | note | METHOD: Visual
e395b762-1873-5283-ace1-2e179d2c7d75 | note | – – – – – – – – – – – – – – – – –
25b40fb2-4287-5965-8f5c-6501eb4c3a74 | note | FREQUENCY: Each element
21608c98-c365-5fd3-b1cb-d1614602bef6 | note | – – – – – – – – – – – – – – – – –
5270e350-4b4d-536a-bbfa-f2dbdb52456f | note | CATEGORY: IP
a9d8903a-83fe-5c6e-a1cf-9a9c1186fbc9 | note | – – – – – – – – – – – – – – – – –
b9c9fd1e-5bb3-52a1-ab2b-776de3ade79a | note | RESPONSIBILITY: SE/Site Supervisor
1acdc240-a508-5f84-b79e-d2ebc25b6ae2 | note | – – – – – – – – – – – – – – – – –
246344ef-1aab-5dca-8ed8-a9968d355a91 | note | VERIFYING DOCUMENTS: This ITP
fa8dcdd2-e4a6-5f94-8074-717e1be4d324 | textbox | Date Completed:
| checkpoint | 5.6 Refuge Installation
4840f0dd-5f59-5971-a68e-f23d6b4e8e5d | note | REFERENCE: IFC Drawings
97cd7143-95d2-5c79-b2bb-67fcf3d7970b | note | – – – – – – – – – – – – – – – – –
e01de92e-1f3d-586c-acbb-6ef4c55345bc | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
9111e748-586f-57f1-a4f8-fb97a872a905 | note | ○ No chain wire mesh to be installed at refuge access.
45f24409-130c-5f5a-a9b2-3f600de23904 | note | ○ Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
61339afc-d051-5967-a711-e2ccdb16a49b | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
442265e2-156e-5eab-847b-5d4317d1bb48 | note | – – – – – – – – – – – – – – – – –
803f6c62-0e48-5575-8c9e-9152f79f4caa | note | METHOD: Visual
422a636f-2cfc-5326-8143-bea683196870 | note | – – – – – – – – – – – – – – – – –
fc27830e-e20e-563f-aaf7-16b46286d066 | note | FREQUENCY: Each element
34cf5c02-e8d1-571e-8e45-7d838cd95e41 | note | – – – – – – – – – – – – – – – – –
e08049ef-47d0-5b2b-8069-97c81c7a08bb | note | CATEGORY: IP
c24f8841-594e-5dbe-83df-7fa5d12b4f57 | note | – – – – – – – – – – – – – – – – –
9fc41de0-8891-51ed-a388-73f4e1cd922a | note | RESPONSIBILITY: SE/Site Supervisor
347699e2-111a-5a5c-8dbc-faed195487d5 | note | – – – – – – – – – – – – – – – – –
0d31a6fc-fc60-5371-8217-e0e85cd99215 | note | VERIFYING DOCUMENTS: This ITP
777b63df-8631-5936-a83d-efdc3439c140 | textbox | Date Completed:
| checkpoint | 5.7 Refuge Signage
3e53b2b0-9ba6-5081-9a2e-388ab3f85fae | note | REFERENCE: IFC Drawings
6ab36f94-3c39-59b4-b158-98d4fae7d423 | note | – – – – – – – – – – – – – – – – –
9c2bb6d7-0827-5281-9955-0ece193d0ecc | note | ACCEPTANCE CRITERIA: Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
1ba18b0f-f949-5822-b09a-f4d0d7c3a0c5 | note | – – – – – – – – – – – – – – – – –
5c5c0056-e5c9-58f2-8772-9bcfefb70014 | note | METHOD: Visual
485e5f83-95ec-5d8d-b9fa-1ec40e15bfee | note | – – – – – – – – – – – – – – – – –
eeb18d1f-4a57-5333-919f-08d3f31e7074 | note | FREQUENCY: Each element
21fa4787-049a-53db-8a93-8baa13235d95 | note | – – – – – – – – – – – – – – – – –
a00dfc65-6ac2-5005-9a7d-6baf9b9ccb9e | note | CATEGORY: IP
d78ce728-8a31-5b25-886b-315f8234c1cf | note | – – – – – – – – – – – – – – – – –
5c07eeb4-ad47-52fc-9d47-3d0e436d6b75 | note | RESPONSIBILITY: SE/Site Supervisor
70e8cdd7-cde7-54db-9566-87bd8ccec541 | note | – – – – – – – – – – – – – – – – –
1c0c96a6-1d9c-51e9-80c1-14bc3eaf20d0 | note | VERIFYING DOCUMENTS: This ITP
5dccd4a1-47fc-5f80-9951-f2acdef52245 | textbox | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Fence Height and Track Clearance
6a6506f1-2d58-57e1-a2fc-5c0e477363b0 | note | REFERENCE: IFC Drawings
a8e38ac5-1cc8-5694-9a53-e8b30f6cfc33 | note | – – – – – – – – – – – – – – – – –
7c740cca-0c63-5343-af82-46aa48537023 | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
e2530150-c500-5640-aa8b-29a6a51c6546 | note | – – – – – – – – – – – – – – – – –
8193ed29-aa06-5903-82fd-fcb330606f83 | note | METHOD: Measure
1e133529-02a1-5945-a91e-88617807a13a | note | – – – – – – – – – – – – – – – – –
b207691f-0b40-584d-b6de-d2de0570da84 | note | FREQUENCY: Each lot
82ab422c-c9ea-57f2-b6b6-3d37d13d55b0 | note | – – – – – – – – – – – – – – – – –
31dd574a-360e-5955-b22a-0a312cdf1c9f | note | CATEGORY: IP
0d5bae00-7c04-5e8c-8a82-f6dd5146dfb9 | note | – – – – – – – – – – – – – – – – –
371fb225-c4a6-5243-8443-8864e5b45cf7 | note | RESPONSIBILITY: SE/Site Supervisor
fbff6749-f858-54a7-b125-e81b8946985b | note | – – – – – – – – – – – – – – – – –
f2cd56e6-ed3d-5088-a7e5-18d87391f842 | note | VERIFYING DOCUMENTS: This ITP
1e6d8259-d4bc-540c-9af5-6d3036a9b1ba | textbox | Date Completed:
| checkpoint | Final Inspection
a7d23049-ba58-5a14-bbb6-13932c5e539f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
316b3e8f-8b54-5352-b4c8-6d45b1c48767 | textbox | Name:
ec28943a-8618-536a-aa52-cbab2b8edb92 | textbox | Position:
81aec31c-8625-532c-b7e0-471a8a120913 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-058-CIV-SSB-Clearing and Grubbing Rev 0 | itp | ITP-058-CIV-SSB-Clearing and Grubbing | 9d6a1460-07c1-43a8-8237-58c631a15a14
| section | Referenced Documentation
| checkpoint | Referenced Documentation
31c2a1d4-2c66-582f-ae55-6a049067cc65 | note | Document Title: ITP-CIV-SSB-Site Clearing and Grubbing
7afd9272-d2f5-5cd3-b29a-2e919e2d3c24 | note | ITP Description: SSB-Site Clearing and Grubbing
ff680ed1-e886-5745-87a9-123881da8364 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
441645c8-52f8-58bd-ba79-f6c9219e971d | note | Discipline (e.g. CIV/STR/RAIL): CIV
287d55c3-2784-5d46-ae64-f160c01ed66f | note | Revision Number: 0
3be47f7e-c6c1-56c5-80b0-661b26e99be0 | note | Revision Date: 9/08/2023
42a424bc-1537-56dc-9c9b-cc0cc66840ee | note | ITP created by: Jason Lee
0f388fee-3b6a-5f07-a2a8-cd9d186bdcf6 | note | ITP approved for use by: Jon De Castro
a22a7ca3-e2df-573f-a244-40c1a0d40826 | note | 1.1 Non Dependent
b69f5641-6789-568d-9839-d5a1eca2f7b0 | note | Reference: VicRoads Section 201 (Feb 2023)
381faa81-b369-585e-b4cf-250908514234 | note | 1.2 Non Dependent
8bc2ff87-dd5f-56b9-bc12-a4c030bb48e2 | note | Reference: VicRoads Section 204 (Dec 2015)
c174001d-f089-5c10-8ad6-d1ed5269eb43 | note | 1.3 Non Dependent
5d265fef-da7e-595e-8d0f-d77467c9297e | note | Reference: IFC Drawings
| section | Preliminaries - Materials
| section | Preliminaries - Documentations
| checkpoint | 3.1 Environmental Controls
9bcdcdac-d9f7-5655-ad44-2bad0007b2d6 | note | REFERENCE: MRPA Environmental Management Plan
96ce087d-4861-50c0-b098-49c68718613a | note | – – – – – – – – – – – – – – – – –
f05db4d9-491c-5350-b981-d67df7b2d0d6 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
f15b63c9-df07-5c12-8c42-07db6e747f5e | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
c98d9431-3a87-5758-85ec-513166153e79 | note | – – – – – – – – – – – – – – – – –
03f75504-815b-5edf-a1f8-f17dfa688cc4 | note | METHOD: Visual
020e66ae-8b77-5d03-a7e8-ae484351d3ec | note | – – – – – – – – – – – – – – – – –
e3f030dc-22ee-51fc-9c83-5509a2609d5e | note | FREQUENCY: Where applicable, prior to starting Works
9009c487-b2fd-568f-ad7d-b3f10b7c1be1 | note | – – – – – – – – – – – – – – – – –
d8b44800-a296-5212-ae2c-51c1083aea4a | note | CATEGORY: WP
8a1abdd1-37d0-5143-83fe-ee406696dc24 | note | – – – – – – – – – – – – – – – – –
ad4f93fc-4c7d-5ed5-8d87-85c0a357ae60 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
396ab0a4-5e74-51f3-9ded-44fd7301d23b | note | – – – – – – – – – – – – – – – – –
1d75e653-6aef-5922-b6aa-bcf9f55b9abc | note | VERIFYING DOCUMENTS: This ITP Signed-off
1de62e4f-a072-5516-b4cb-e15b68f2e17f | textbox | Date Completed:
| checkpoint | 3.2 Vegetation Removal Permit
5289ee3c-772a-51cb-8de1-7d40d276e461 | note | REFERENCE: MRPA Environmental Management Plan
ce5be544-4488-5e79-8b70-3128f1440099 | note | – – – – – – – – – – – – – – – – –
d9394939-87e0-5198-a546-423dd67c26a3 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
155df37b-2f6f-5ece-aad0-2798f8df1e9a | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
ea8fee6f-a9aa-5f15-92a6-db86eb2315a6 | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
072fa043-1509-5d34-929d-30813377eaa0 | note | ii. fence and sign all sites nominated as No-Go Zones.
0fcd399d-fe17-5a5d-862e-477d7acf3c9b | note | Attach: Vegetation Removal Permit
19e7c9e3-3f81-577b-85eb-c994d9f49f6e | note | Attach: Ecologist's Report
ee01f70a-4106-52c0-ba9f-0e629f7c8b30 | note | – – – – – – – – – – – – – – – – –
14edc8af-049e-56d7-a4e5-742586004bdd | note | METHOD: Document Review, Visual
163648ae-0f77-5eed-b6d7-854ad249a390 | note | – – – – – – – – – – – – – – – – –
7b7c2dda-d8d1-595c-8fe9-10e60929d976 | note | FREQUENCY: Where applicable, prior to starting Works
91341cf5-facb-5bb2-bd58-b97cb879ed5e | note | – – – – – – – – – – – – – – – – –
6d22d2db-8fa0-54ce-b5e2-ca4cb5635405 | note | CATEGORY: HP*
5dba7b3d-39b4-5078-8629-f5662f886c27 | note | – – – – – – – – – – – – – – – – –
0866cc46-7de1-55eb-a95c-70bbaee8b80c | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
6f25588a-829b-55e6-ac76-eb5450a88ec8 | note | – – – – – – – – – – – – – – – – –
ddf3a782-e3a5-5088-8ec6-b31dd2119dbd | note | VERIFYING DOCUMENTS: This ITP Signed-off
1e9bdff7-8428-51bd-ae3e-d9914b6e3576 | textbox | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set-out / Limits of Work
9df2ee72-5a6b-5988-b669-c2c9e4e3e58d | note | REFERENCE: IFC Drawings Section 201.03
c45bc1ce-bca6-582b-9ce0-9d9274291309 | note | – – – – – – – – – – – – – – – – –
ee22e862-16a8-5553-b967-89b2ba63aaec | note | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
b4c60fb8-38a8-52e7-92b2-23747a1895f9 | note | a. the limits defined on the IFC drawings
f54dd88b-bb1b-5c57-bf8c-094d29a2fc30 | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
31362beb-848f-5b21-854e-d85aa02dfbc3 | note | c. no more than the width required for completion of the Work under the Contract.
9d13a548-35f1-5c10-a075-8b3b7bcb029d | note | – – – – – – – – – – – – – – – – –
ecb2eda9-4c13-59e3-84f5-8742f9da22c3 | note | METHOD: Measure, Visual
77590177-7a2f-560a-8b1f-c63eed510c00 | note | – – – – – – – – – – – – – – – – –
ec3872f3-e713-5fb4-8ebc-dc0463d1dadf | note | FREQUENCY: Once, prior to starting Works
97692512-4508-5e10-bbe5-f90ea3687cfe | note | – – – – – – – – – – – – – – – – –
5a9e7979-6005-59cb-b81b-bd5ecc2b2bb4 | note | CATEGORY: IP
a693b7e4-21d2-5b2a-91d6-92918f0e31f7 | note | – – – – – – – – – – – – – – – – –
5d701ba1-8372-5e36-a5ed-c8444cd9c941 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
78a39e6c-7154-5ac3-a961-8ed372c0e881 | note | – – – – – – – – – – – – – – – – –
fe2e8694-3b12-556d-a856-13bbdf5ccea7 | note | VERIFYING DOCUMENTS: This ITP Signed-off
81c5b90f-f5f0-50b8-9d31-4db1bfed32d0 | textbox | Date Completed:
| checkpoint | 4.2 Cultural Heritage and Areas of Significance
1ac195cf-bb93-5941-8caa-279f7a3a61a8 | note | REFERENCE: MRPA Environmental Management Plan Section 201.10
68e635b5-65a1-5c8a-b743-78fa2356ac65 | note | – – – – – – – – – – – – – – – – –
f562a2c6-582f-51e9-a21d-8255e13fda6a | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
f80acabd-1a08-5488-89a4-cac6c78597d3 | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
509e98a8-7115-5237-b8e6-cede8122a219 | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
6b3bf29c-4875-508b-b72c-d9a268fe4531 | note | Attach: Cultural Heritage Report
11b2f4b7-ef57-5587-b836-8bc7d8157243 | note | – – – – – – – – – – – – – – – – –
8da9ad42-ec53-5c78-8673-bda8d6cc18cd | note | METHOD: Document Review, Visual
fe096d8c-5a8f-5423-9363-572bb3d92104 | note | – – – – – – – – – – – – – – – – –
456098f2-62bb-5d20-a3be-60ef54061606 | note | FREQUENCY: Where applicable, prior to starting Works
f195cb62-7959-560f-be0e-e680f3847468 | note | – – – – – – – – – – – – – – – – –
50a58e7f-a424-55f7-afcb-8c976079cc87 | note | CATEGORY: HP*
992c253e-f24c-5191-8520-d73f8075a170 | note | – – – – – – – – – – – – – – – – –
9d89ea46-4cd6-58fd-b4ab-91436d1a1ca7 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
a26cef06-257d-5534-b185-7d9d62111351 | note | – – – – – – – – – – – – – – – – –
558ee11d-0270-5dec-8e29-230c016adf86 | note | VERIFYING DOCUMENTS: This ITP Signed-off
fdbe8ba1-c445-5025-87a8-cc020b5fac0d | textbox | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Stripping of Topsoil
1c1a6efb-13af-598a-a0af-7c39c8ebb503 | note | REFERENCE: IFC Drawings Section 204.05
1948916a-35fb-5568-be16-b9c738d1127c | note | – – – – – – – – – – – – – – – – –
4af300ca-11e6-5bab-a9a6-b84fd2671467 | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
9901233d-3f90-5957-8ba2-136beee80e81 | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
ec840400-b930-56ac-8a06-d44cf5037a67 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
c8529ead-281b-590a-b412-a4db425cd018 | note | – – – – – – – – – – – – – – – – –
2d7918f4-ee1f-54ac-8e8d-534f7ffc4413 | note | METHOD: Visual
c34c9ecb-472e-5467-a6d9-6fd5c62dabc2 | note | – – – – – – – – – – – – – – – – –
323eac5b-fd4a-5893-9ce4-60018cc11c22 | note | FREQUENCY: Each Site
5012a42a-e3e0-5cd5-8239-4e42a335702d | note | – – – – – – – – – – – – – – – – –
96f70a72-b998-5f8b-9339-7c3ab67d5a90 | note | CATEGORY: IP
730b59f6-4e1a-504d-87a8-4b18217571fd | note | – – – – – – – – – – – – – – – – –
8540d81f-28ee-51b9-a7dd-39107571e6ee | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
d06cb9dd-91a6-5108-8c4c-65119cf2eb4c | note | – – – – – – – – – – – – – – – – –
3df6a9f6-363d-5e38-8066-3b8d3eb4104f | note | VERIFYING DOCUMENTS: This ITP Signed-off
96c6b0de-cc26-5434-ae3b-0eed931d719c | textbox | Date Completed:
| checkpoint | 5.2 Stockpiling
0a66492c-ce9a-5a54-a8e0-80bb0f921268 | note | REFERENCE: MRPA Environmental Management Plan Section 204.05
a49a971a-b417-5573-be91-d4d402323592 | note | – – – – – – – – – – – – – – – – –
f594bb8d-1375-5cb9-a7b1-0f772fdbb3fd | note | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
85573849-4670-5690-9cbe-0f1bccbfe38a | note | ○ If this clearance is not possible,additional protection shall be provided.
059eb324-8232-5837-9274-d5a7026509ba | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
7853fed8-d4c2-5657-ada9-74d8ffe0d2ef | note | ○ Topsoil shall be re-spread as soon as practicable.
e6b91db9-ca9e-5f17-9993-c6cb5564def8 | note | – – – – – – – – – – – – – – – – –
1f7c7739-259a-5b58-a977-f909690948f6 | note | METHOD: Visual
60f88afb-6cf9-542e-acb4-0114102cbfb7 | note | – – – – – – – – – – – – – – – – –
048c3af5-65f2-516a-a574-4ada34cdd056 | note | FREQUENCY: Where applicable, each Site
ce10b04e-52de-57e7-91e5-167affe06b91 | note | – – – – – – – – – – – – – – – – –
7b7c3496-697d-5a06-9dc7-417a7dbc4607 | note | CATEGORY: IP
50ad76d2-3ee0-5c5b-bffb-02612ae58a75 | note | – – – – – – – – – – – – – – – – –
3bb33179-93e2-5c06-9195-1b874b09a50b | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
a7554a6d-51a1-557d-a095-51f12bfc7f4b | note | – – – – – – – – – – – – – – – – –
1ddd2ccf-63c3-5a02-9ce4-98ef838d8a73 | note | VERIFYING DOCUMENTS: This ITP Signed-off
3ac5c1af-1df1-5ed7-ba9f-e82a32ef07a2 | textbox | Date Completed:
| checkpoint | 5.3 Abandoned Services
baa303bb-ffbf-5b1a-b2bb-20ee8cd28a82 | note | REFERENCE: IFC Drawings Excavation Permit Section 201.05
67812e51-02ac-58d9-ba45-f3428c492c9e | note | – – – – – – – – – – – – – – – – –
766f5f82-7f4b-51c1-8bf0-3fbe99ed774f | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
db462803-4a5e-5680-8a82-24f80acc3dd2 | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
6b416c3c-6e5c-5833-abad-ca2bd7f5cff2 | note | ○ Decommissioned services to be disposed of in a suitable manner.
9ba23c36-153c-5b98-8e73-917544e74edd | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
4cece54c-3d22-5497-bf60-d35b6a73517a | note | – – – – – – – – – – – – – – – – –
1c5c4354-7fc1-5642-9257-fa0f93f59873 | note | METHOD: Visual
1b01df17-792b-5ac5-8482-8114e8253fcb | note | – – – – – – – – – – – – – – – – –
998201b7-7031-5483-a3b3-0f998beab866 | note | FREQUENCY: Where applicable, each Site
cad2f0bd-237f-5f18-9b55-50bb7068d400 | note | – – – – – – – – – – – – – – – – –
926d113d-9141-5192-a717-260edbeeb5f4 | note | CATEGORY: IP
026baf7a-53a9-5b66-8457-0c75d0de6dd4 | note | – – – – – – – – – – – – – – – – –
1141177c-1beb-58e6-9126-6df75a14776a | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
452ba0c1-8c0c-5884-87b1-257579e57a86 | note | – – – – – – – – – – – – – – – – –
697b27bd-abfe-5775-a0db-504948ce8255 | note | VERIFYING DOCUMENTS: This ITP Signed-off
0c981773-099d-574d-b038-92f4507dd995 | textbox | Date Completed:
| checkpoint | 5.4 Clearing of Trees and Vegetation
b50fd0bb-3afa-5fd3-a7d0-80d14986617e | note | REFERENCE: IFC Drawings Section 201.04
edda8b12-cb3b-5aa7-8d88-5b85ffcd5bb0 | note | – – – – – – – – – – – – – – – – –
d99d2fe6-46d0-5cd4-958e-177f640cc09d | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
f29f8dd7-4ced-5da9-900e-eb55bad85780 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
55e947be-de95-5ec5-a067-3f6a4b512ad2 | note | – – – – – – – – – – – – – – – – –
f3b42f80-afa9-59b0-8d5c-14b4f8c5ae07 | note | METHOD: Visual
e6dc1a4d-ab53-599d-95d4-dff5c35fb58a | note | – – – – – – – – – – – – – – – – –
aae1f575-f75a-54a0-a936-5cff338ebfaf | note | FREQUENCY: Where applicable, each Site
cf9838ec-2798-5156-a21e-940e1c2ce460 | note | – – – – – – – – – – – – – – – – –
9030e0cf-86eb-58ad-8beb-551e35ae8f3d | note | CATEGORY: IP
8ccfd5fc-6231-5f0a-8e85-80c11a467004 | note | – – – – – – – – – – – – – – – – –
1b73d4ab-7d78-599a-8234-492e336d6054 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
70117845-893b-5ba7-8e55-69a4420333a6 | note | – – – – – – – – – – – – – – – – –
5a7707fc-1b78-527a-803f-2fde8c0a039a | note | VERIFYING DOCUMENTS: This ITP Signed-off
0e79bb0d-614e-527c-8bcb-0451fb10062b | textbox | Date Completed:
| checkpoint | 5.5 Grubbing of Vegetation
9b15bc7c-8e62-56bb-b7e9-5ff3e273b76f | note | REFERENCE: IFC Drawings Section 201.05, Section 201.06
aa3c7b8f-0412-526c-ac72-2a0fd34a1897 | note | – – – – – – – – – – – – – – – – –
399ccc37-66da-587d-bf0f-78c2a4974478 | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
d0e0f363-2d24-5c50-b007-faa4608f09b2 | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
b6a541ee-2e2f-5e02-8c3c-0ad05239c3c9 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
dc9dfed8-14ca-540d-8be5-6f7864cb7492 | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
4123beb9-9bce-5e1b-90c6-865c0b170115 | note | – – – – – – – – – – – – – – – – –
47693c78-de49-5131-b9fc-a12360dc84ff | note | METHOD: Visual
c10eb20d-0fd7-57d3-a6d7-0a1c8ed75bf0 | note | – – – – – – – – – – – – – – – – –
0777c875-a576-54b3-b361-402bb6fffcef | note | FREQUENCY: Where applicable, each Site
d411f435-4c07-537c-9dd8-df509560be3c | note | – – – – – – – – – – – – – – – – –
3433eda4-a006-55d8-85ef-8affeca7d325 | note | CATEGORY: IP
5be6c186-58ba-53a8-bc16-119b38777b65 | note | – – – – – – – – – – – – – – – – –
5542d11c-8f8e-57d6-b136-8d3d7d7eda02 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
c759cfea-f04a-59ae-a9fd-4424149f9e51 | note | – – – – – – – – – – – – – – – – –
380d1c7d-1e3b-584f-94bc-ed6ce8899b3e | note | VERIFYING DOCUMENTS: This ITP Signed-off
7e9baa61-03cc-5b17-afb8-2b5257e96f9b | textbox | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Disposal of Materials & Vegetation
29d9058b-8055-5719-89b3-7b2cb8d928de | note | REFERENCE: Section 201.07
98f5d6f7-11be-5c4d-b67b-ea979ee9f1d5 | note | – – – – – – – – – – – – – – – – –
76b09e1a-9c84-5b7d-b2dd-aa6b964d0c91 | note | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
1b4a2841-2d07-5567-8731-712a1b25002c | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
d69c8b99-dced-5977-8db8-d3445897ab9f | note | ○ Tree trunks and large branches shall be removed from the site.
173ef519-f359-5fae-b35e-c4a08603fd19 | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
6f8bae2d-773d-5585-ad75-82425eaa1482 | note | Attach: Delivery Dockets (for Items sent off Site)
ce04331f-2967-59bf-9eca-6d3173e14f1c | note | – – – – – – – – – – – – – – – – –
20f19455-b349-5872-8b0c-4296ba1183e4 | note | METHOD: Visual
a951c5e2-feb2-500f-a123-b4ba1fe3ffbd | note | – – – – – – – – – – – – – – – – –
ed35bcee-8c07-5103-b63a-cf1a86c15b6b | note | FREQUENCY: Where applicable, each Site
604da063-34a7-50c7-a360-1e8be23c7bb7 | note | – – – – – – – – – – – – – – – – –
5f082774-711b-5095-9db4-d535eae9fcda | note | CATEGORY: IP
b6a13b3e-1583-5b12-9f5b-85dd382024a5 | note | – – – – – – – – – – – – – – – – –
df7119ab-a9f2-5447-b355-b9ac261a9b87 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
86fe2415-2f65-5626-ad88-2bd379215a86 | note | – – – – – – – – – – – – – – – – –
3476491f-a775-58e6-8e48-c6d1bfac77d8 | note | VERIFYING DOCUMENTS: This ITP Signed-off
40ddc51b-6a19-5ece-93d9-2825c0443bde | textbox | Date Completed:
| checkpoint | Final Inspection
b519626d-2102-5e97-9124-5918766d9998 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
bdf29a0e-268a-5055-8331-e8ec00eb513b | textbox | Name:
b23c98d7-b87e-51e6-ae06-943b2c62f739 | textbox | Position:
ce378ea6-23fd-57f8-a591-49af20f143bb | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-088-STR-SSB-CFA Piling Rev 1 | itp | ITP-088-STR-SSB-CFA Piling | d3e61578-6c22-4a6f-87fd-2ba278163233
| section | Referenced Documentation
| checkpoint | Referenced Documentation
ce37ef73-4e8a-5b31-84a7-13ab05eaa17d | note | Document Title: ITP-088-STR-SSB-CFA Piling
f9f382c9-466a-5a6f-9409-97ff3ccc83bb | note | ITP Description: CFA Piling
0383d153-fa28-53aa-9e5f-91e59483d9d6 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
9fa81cf5-bb44-5721-a5a7-482a97868bb5 | note | Discipline (e.g. CIV/STR/RAIL): 088-STR-SSB
9931dbc4-0014-5a03-9a37-5fbb4a3b02b7 | note | Revision Number: 1
739096e2-4ddb-5a55-8aa0-77f07df7064f | note | Revision Date: 6/10/2023
5d7314c8-b206-5b95-8e75-3141ad10dd07 | note | ITP created by: Victor Mira
f0b87ae0-6173-5c9c-9a68-0414afc22e13 | note | ITP approved for use by: Victor Mira
e00f86c9-68dd-589b-9d54-6550d8f69b31 | note | 1.1 Non Dependent
deec25ad-cb5e-589d-83fd-7a5b873573f6 | note | Reference: VicRoads Section 607 March 2015
e01c462f-cfbd-5b14-9c9b-3e7749f4d91a | note | 1.2 Non Dependent
b53992ca-f875-5cea-92cd-e2abf3cb9aca | note | Reference: VicRoads Section 610 February 2020
38e74d20-fa1f-5879-93ac-78ffcb87392e | note | 1.3 Non Dependent
52103ce4-e79d-5546-a511-1c39558ba210 | note | Reference: VicRoads Section 611 November 2018
1fc603d5-7899-507b-b1d0-51f008ea79e0 | note | 1.4 Non Dependent
6ec2342c-d4ab-59b3-aa36-102d20ee1284 | note | Reference: AS2159-2009
f0425074-4384-529a-9f6f-344b7e0b59fc | note | 1.5 Non Dependent
4bf407fb-36e9-586e-9060-5104ce71bb47 | note | Reference: AS3810.1-2015
3ab0aeb3-be95-56fb-8fb6-d3bf680c7457 | note | 1.6 Non Dependent
8f54073a-225a-59e0-ba49-08a372349636 | note | Reference: AS5100.3-2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
78255ff4-0c25-58f1-a03f-0556f2ba7a83 | note | REFERENCE: 610.07 Table 610.071
79add433-0035-5554-aaef-cb2fcf9dbab5 | note | – – – – – – – – – – – – – – – – –
49608451-a0a0-5d86-ae15-e2e6bf9e43e1 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
83a3f782-c89d-59d7-b884-8cd20b8d97e2 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
ff5e37ca-f19a-5884-92ab-6aabdbc9e980 | textbox | Enter: Teambinder Material Approval number
9d700b82-0ebc-566c-aa9d-4ae207706787 | note | – – – – – – – – – – – – – – – – –
5b3ac936-2b6c-5207-9020-231462a052b9 | note | METHOD: Document Review
486c39a3-65c4-527d-acdb-a42ac38a8757 | note | – – – – – – – – – – – – – – – – –
eb3ef777-f8b3-51fe-bb88-c6b87bf06dff | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
8b484514-4c86-5fcf-b2b8-641df1d548b2 | note | – – – – – – – – – – – – – – – – –
7648f3e7-a414-5d58-81ba-616546d8f6eb | note | CATEGORY: HP
93502526-a0d0-58dc-9a3c-1d19a1410430 | note | – – – – – – – – – – – – – – – – –
ad0f964e-dd17-54a6-ba7c-15ee5b4734c2 | note | RESPONSIBILITY: Nominated Authority
9bfab37f-8f47-5792-a649-c4684d0205c4 | note | – – – – – – – – – – – – – – – – –
2beaecf4-7fae-53e9-93d4-7a25b9cee91c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
0ded282d-791d-558f-b40a-3e0f85f9a91d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
7bd65bad-5e0c-5e52-a595-469296e9342c | note | REFERENCE: 611.05 (a)
82b0ef7f-6589-5cb1-bc3a-0a55724cb63c | note | – – – – – – – – – – – – – – – – –
8abe62d7-91d7-5d40-986e-fd26aca0f862 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
ed127fc3-b5c9-5b5b-b9e5-1984ba60c947 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
c6b4da98-b01b-5815-a0a2-8cea3b45c243 | textbox | Enter: Teambinder Material Approval number
6285d169-9a52-5016-91aa-ad3ab385531a | note | – – – – – – – – – – – – – – – – –
af94afb6-508d-5346-9979-52c34f0340f4 | note | METHOD: Document Review
2808050f-ec43-597d-84fb-1e5a6c09a11f | note | – – – – – – – – – – – – – – – – –
50b81989-76cf-5ef8-a15e-e140989dad9b | note | FREQUENCY: Once for each supplier, 14 days of award of contract
d1f2c93e-5676-59ce-8544-88560a29aa84 | note | – – – – – – – – – – – – – – – – –
46447890-728a-5914-a0a4-22de4ff66040 | note | CATEGORY: HP
d12ad430-999d-5bd4-b6ce-6dca3472632e | note | – – – – – – – – – – – – – – – – –
34ec5b8b-2b05-5b68-a45e-400a62266726 | note | RESPONSIBILITY: Nominated Authority
e8cab6b5-b4cc-5c03-bada-cfb9b0ae25bd | note | – – – – – – – – – – – – – – – – –
bcfaf1f4-103b-58dc-86d0-dfd7e001a4e0 | note | VERIFYING DOCUMENTS: This ITP
96b31571-04ee-594f-856a-414c85f6d9da | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
2daf3003-daec-532d-9895-fcc702b5115d | note | REFERENCE: 610.26 (a)
bfcc2a23-4d6e-5e0d-9812-c91ddb47d474 | note | – – – – – – – – – – – – – – – – –
c16abb5e-9ee8-53e5-8cf0-4df0ab34f4f9 | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
8d89fcc0-3fd0-58a3-acb0-79cdcd75ba41 | textbox | Enter: Teambinder Material Approval number
0f90ab9f-052d-5552-8c52-4d557cbe99d3 | note | – – – – – – – – – – – – – – – – –
041625c5-b487-5e57-907a-e0efd71f7773 | note | METHOD: Document Review
10086686-6d63-50c8-bf5f-c51d0cd25793 | note | – – – – – – – – – – – – – – – – –
efed78c9-fbbc-590c-9f48-1178ac288cf8 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
9f37edd0-fef6-51ce-9ec8-6af861eaf651 | note | – – – – – – – – – – – – – – – – –
0258d279-2d27-54c6-b532-850b976908b1 | note | CATEGORY: HP
a1c57d98-c8fe-50ce-88d3-b8a8d5692df4 | note | – – – – – – – – – – – – – – – – –
2122adb4-e5bc-5aeb-88c6-a74855a7485f | note | RESPONSIBILITY: Nominated Authority
94f9d6d1-402f-5077-8447-87b88388732b | note | – – – – – – – – – – – – – – – – –
818f3d70-901c-52a3-9de2-15f951c4f9b5 | note | VERIFYING DOCUMENTS: This ITP
b04159f0-e229-5c9d-af9c-b09a1d08a58f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Working Platform certification
367852f8-e2d9-55fd-a572-878baebd9965 | note | REFERENCE: Piling platform design
b4a86204-665b-5df5-9661-a4cf5aada2ce | note | – – – – – – – – – – – – – – – – –
88774f8a-9d68-502d-9681-3120e6dd8f0b | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement.
385be268-61d9-5194-a3aa-e8af6e241eba | note | ATTACH: Piiling Platform Certificate
d6c82414-a00f-5335-a484-b3838ee9e33e | note | – – – – – – – – – – – – – – – – –
31662025-e223-5b00-8042-1afdc178d2ff | note | METHOD: Document Review
6cec18db-1edf-5ade-ae2f-86d272ccd71b | note | – – – – – – – – – – – – – – – – –
6b52529c-3d39-5ace-884f-f6bf8f97264a | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
a712c1d3-4732-5263-a232-6899e4c732e5 | note | – – – – – – – – – – – – – – – – –
ebf0fab2-a1a1-5b82-9555-a89c53b2152d | note | CATEGORY: HP
34b2d6b0-5d3c-5205-b06f-51c36ac131c9 | note | – – – – – – – – – – – – – – – – –
23356866-44ce-560a-b547-c47a7f231145 | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
a0af1c07-83f1-5e83-81d3-8f3e5aa2d464 | note | – – – – – – – – – – – – – – – – –
3026f215-2e42-549d-b1ca-58cdbc986d99 | note | VERIFYING DOCUMENTS: This ITP, Platform Certification
ba4c118c-057d-558e-939d-004883e32896 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete CFA Pile Design
6a1ae8bd-7739-585b-994f-a082666ae9a2 | note | REFERENCE: 607.01 IFC Drawings
ea2471da-3230-5f14-9432-d0b93fd5b606 | note | – – – – – – – – – – – – – – – – –
08499d74-8acf-5b3f-9da0-9b9d79887e39 | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
239f8a1e-1686-5eb9-9071-d7aaaa6d98f1 | textbox | Enter: Teambinder Approval number
6e07dc0b-9200-5f27-8e8e-a74ff9c17099 | note | – – – – – – – – – – – – – – – – –
6612fbe4-d193-5ee5-b9ac-fc330093212d | note | METHOD: Document Review
367fe31c-3497-5ead-a778-c3642a96d389 | note | – – – – – – – – – – – – – – – – –
9e3da163-8e60-537b-a17a-1d7e2c4095a4 | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
9c39b601-8a7a-5ad8-a1d7-931d7bb44dbe | note | – – – – – – – – – – – – – – – – –
bd91fbb7-2464-5b57-94db-82a838c986a3 | note | CATEGORY: HP
868d0a67-3ca2-51ee-8a6f-a98d9c7bfea8 | note | – – – – – – – – – – – – – – – – –
3b985391-e031-5e3d-b335-1cae722aef19 | note | RESPONSIBILITY: Nominated Authority
175ed209-27a3-5dd1-9400-0c9decd2418e | note | – – – – – – – – – – – – – – – – –
16d360a0-5cea-5da1-92d6-0831308077ac | note | VERIFYING DOCUMENTS: This ITP
1cbebf6f-807c-54c2-be0d-cc55b184f1d0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Piling Operations Work Procedure
4e9060c1-e956-570e-9341-57bdee8a820f | note | REFERENCE: 606.03 (a)
1815493b-8184-515d-8b4d-091d9eb42e18 | note | – – – – – – – – – – – – – – – – –
9a2bcfd5-25d9-56d7-8f61-2261fc82f8cf | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
e0380fd9-53c0-5272-b9c6-45611a4ec6b3 | textbox | Enter: Teambinder Approval number
67071498-e961-56a5-8179-35f0eb260b63 | note | – – – – – – – – – – – – – – – – –
a985af60-e19f-5c14-8a46-a01c4be2980c | note | METHOD: Document Review
0f5925b3-2ac5-5bf8-b41a-2b9ac0c7f322 | note | – – – – – – – – – – – – – – – – –
bd0c6efa-fbba-5824-a18d-a1927ca34628 | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
105bf3a1-a7f9-56bf-990b-eff503151a53 | note | – – – – – – – – – – – – – – – – –
044c55dd-30f6-59db-8078-2ff265910f2c | note | CATEGORY: HP
1d593e2f-6a06-5429-978a-cddd1ab4dd05 | note | – – – – – – – – – – – – – – – – –
110c4cd2-ab5f-5b15-935f-50d645e6122a | note | RESPONSIBILITY: Nominated Authority
1df8b480-9afb-55f4-a215-c1ea4e31cd31 | note | – – – – – – – – – – – – – – – – –
08a36ffa-bf42-5841-ad23-b66363dccb6f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
28200b30-098a-5e7a-b473-047836185049 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Casting Under Water Procedure
61c6daee-2dfd-542e-ba20-7a382a762019 | note | REFERENCE: 607.04
732075ee-d818-5b61-ba47-8a8cea223545 | note | – – – – – – – – – – – – – – – – –
7359427f-8b64-5ddf-9e73-8e1dc534b47e | note | ACCEPTANCE CRITERIA: Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
6d26025e-5fa1-545d-9576-2d13bb15b743 | textbox | Enter: Teambinder Approval number
5772f720-0d9d-5668-8563-234ae2f84ddb | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
75705bd9-1748-5735-ac89-fcc4c804b5bb | note | – – – – – – – – – – – – – – – – –
b13baa63-5db8-5511-b723-fb29b5e48bf7 | note | METHOD: Document Review
83fe223d-d974-5345-bf63-d8b3f5b0ea98 | note | – – – – – – – – – – – – – – – – –
9bd8a5b2-d9aa-5be7-86db-22fc6f76af59 | note | FREQUENCY: Where applicable, once, prior to placement of concrete
7d703e67-ce49-58b8-8560-377822191af0 | note | – – – – – – – – – – – – – – – – –
bc898154-95dc-553d-a8d0-b4c4093f1012 | note | CATEGORY: HP
9ba45203-95a2-5611-905f-4c299f602146 | note | – – – – – – – – – – – – – – – – –
c0ea5c15-3753-5a43-8627-3ea1463a86d2 | note | RESPONSIBILITY: Nominated Authority
527d26ad-6af4-5581-8531-909f49287ae2 | note | – – – – – – – – – – – – – – – – –
45994e4e-06e8-56d3-a3b2-9b6f50d5cfc5 | note | VERIFYING DOCUMENTS: This ITP
9ad12ddf-f9bb-5d61-a416-06a3fff46d58 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Dynamic Pile Testing Procedure
ffbc2438-a24c-5aaf-abe0-e96995acebd7 | note | REFERENCE: 607.07
cc626ac1-f783-513a-9326-3773161be8de | note | – – – – – – – – – – – – – – – – –
448c4288-106f-5a85-8ee5-d0e54ebcbfb8 | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
38200a75-af1c-5890-864a-92607af6a430 | textbox | Enter: Teambinder Approval number
6f4ca88f-c509-544b-9b7a-438c1486c034 | note | – – – – – – – – – – – – – – – – –
c8a080bd-74cd-5482-9ab4-881d20e394ce | note | METHOD: Document Review
2d0a399a-3075-50d8-a0f4-411134a6c229 | note | – – – – – – – – – – – – – – – – –
60a3ef58-eeda-59d4-a487-c3fed8551f89 | note | FREQUENCY: Once, prior to testing
d6639a63-232f-52ec-b829-19392a252f08 | note | – – – – – – – – – – – – – – – – –
9a1b1b8f-9d69-53f8-8276-4f77308e167a | note | CATEGORY: HP
e336f652-0b5a-57fd-be5f-f87fb6e7dad4 | note | – – – – – – – – – – – – – – – – –
f77fda92-1e5e-5c95-a910-014bcfe48dfa | note | RESPONSIBILITY: Nominated Authority
385b0d33-65a5-5617-b1bc-b77c1c24ef7f | note | – – – – – – – – – – – – – – – – –
a9471b2e-5392-5083-926f-209c5e9203f0 | note | VERIFYING DOCUMENTS: This ITP
799fd910-5af3-5dc7-8130-bdace764deb0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Pre-qualified Pile Testing Consultant
aea3b065-ecfa-509e-ad67-f58a74a05f9f | note | REFERENCE: 607.07
26e59fc1-c23e-50a3-993c-d4ee119fe105 | note | – – – – – – – – – – – – – – – – –
980c931e-9f8d-5083-88b5-d89e65375227 | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
af911ab6-56b2-5002-975b-230482aa69b0 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
7aafb37d-c3c7-5915-8b77-5a0614f3458d | textbox | Enter: Teambinder Approval number
433b83b8-7984-51c4-887e-e4273dc66512 | note | – – – – – – – – – – – – – – – – –
45d062f3-37b4-51f8-b65c-b242646abc8b | note | METHOD: Document Review
93686288-f15f-5d5b-8ae2-8166b339c4e9 | note | – – – – – – – – – – – – – – – – –
c20a8953-c93e-5977-8f1b-9293862272ed | note | FREQUENCY: Once, 2 weeks prior to testing
665d0c32-a94b-51a0-8312-b4a0f440d8b1 | note | – – – – – – – – – – – – – – – – –
f7329050-acd4-5f1a-aee4-5606858f7624 | note | CATEGORY: HP
9fc8f1f1-1f4b-532d-9d58-5d5b8a3caffb | note | – – – – – – – – – – – – – – – – –
6306dc3f-b31e-5f42-8ab7-7bad4ec4188c | note | RESPONSIBILITY: Nominated Authority
6f4abe53-3a91-5182-8797-d274f5d7c203 | note | – – – – – – – – – – – – – – – – –
9aabeca8-225c-5e5b-838b-19e598ffd57c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
fde87147-16e2-5fc0-8f13-958226288d4e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
f86c6f37-dc0b-5fee-8a67-89596071360a | note | REFERENCE: 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
fd321fdf-40db-573c-b5c1-150b903f00e0 | note | – – – – – – – – – – – – – – – – –
ffcb4a38-4167-5ff8-9a0f-490c169a4a41 | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
68649927-7992-5402-9726-70f78e634cfa | textbox | Enter: Teambinder Approval number
36a0d57e-a136-56b4-889d-56a7387b1629 | note | – – – – – – – – – – – – – – – – –
bac90f7b-8be7-53ea-8742-7a271e56b52f | note | METHOD: Document Review
16eb88e2-7cab-5c80-bfe6-1d73c7779d15 | note | – – – – – – – – – – – – – – – – –
0c1a48d6-d11a-5abb-8a72-c390c556b383 | note | FREQUENCY: Where applicable, once, prior to welding
573f0454-941a-5740-a880-cfb408872c05 | note | – – – – – – – – – – – – – – – – –
758d975e-ddee-516e-9f9a-6388557e7464 | note | CATEGORY: HP
9860dcbf-b240-5fef-9ec3-3cf4ecc6f49c | note | – – – – – – – – – – – – – – – – –
7e16a135-3f28-53ce-88b3-b191b19190e9 | note | RESPONSIBILITY: Nominated Authority
a79b98d0-a868-5d3b-ac15-ceb08002e833 | note | – – – – – – – – – – – – – – – – –
d8aadd38-de18-5ecb-aa34-dc7c230e5816 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
512142dc-8906-580a-9c32-f4f02f293d2b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
6cbe3aae-92d8-51f0-8845-604710e27cd8 | note | REFERENCE: MRPA Quality Management Plan
ebfb51e5-91ce-5dcf-811b-dc3d591ef3d1 | note | – – – – – – – – – – – – – – – – –
82e81376-0688-5064-be8b-acad138af265 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
9122d00a-1d11-5a21-b2e9-1d96c64cb806 | note | – – – – – – – – – – – – – – – – –
afbac224-561a-5c9e-862f-4d57a235a5e1 | note | METHOD: Document Review
0f4a4015-b958-581e-96d5-2a158842fa02 | note | – – – – – – – – – – – – – – – – –
59ba392d-cf90-542a-980a-3f03719d0550 | note | FREQUENCY: Prior to starting Works and at regular intervals
3e666726-00ec-50d5-83e5-88559b42792f | note | – – – – – – – – – – – – – – – – –
bf84d808-9eba-5e07-bdb4-d55505a08f3e | note | CATEGORY: HP*
4a1bbf32-16a7-5c76-8c76-5e7474ae63d3 | note | – – – – – – – – – – – – – – – – –
b3f7f45e-14d7-5d81-929f-66d6c8222b16 | note | RESPONSIBILITY: All
933cd9cf-8a78-5463-bbed-bf89a2b73705 | note | – – – – – – – – – – – – – – – – –
47a216ce-26d1-5d63-92f4-11683a576d8c | note | VERIFYING DOCUMENTS: This ITP
f19e295c-68e2-5c9e-8d88-28cd4148f625 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
085b8400-2040-5134-ba2f-a24f9966b1a9 | note | REFERENCE: IFC Drawings 607.06 (a)
f03974ef-0c9d-5c87-bc73-27e827fbbe5a | note | – – – – – – – – – – – – – – – – –
0476ec99-803e-5efe-9e42-b013665ffef4 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
7fe4dda2-415d-5f9f-9003-7fcfb20c42df | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
5aed1df6-3574-5002-8295-e51428599242 | note | – – – – – – – – – – – – – – – – –
89239d70-d462-52ae-9094-4f4cee8b8b0d | note | METHOD: Measure, Visual
55ff35a3-cee0-5225-8a7b-c61c8fdbd408 | note | – – – – – – – – – – – – – – – – –
a4216ab5-fa9f-5b09-b2ea-1e00e71d4123 | note | FREQUENCY: Each pile
df8d1009-271f-531c-93a3-45c95c6ba806 | note | – – – – – – – – – – – – – – – – –
24d23c7b-e3f6-5d92-ac90-3274164ecdd0 | note | CATEGORY: IP
1fd1cdd1-d51f-5028-867c-73eebaad3a21 | note | – – – – – – – – – – – – – – – – –
701cac65-b38e-55a4-aa4a-9e5e8cdaefb5 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
7dd9f119-3419-52b8-91e1-acb7587b87dc | note | – – – – – – – – – – – – – – – – –
0a68846e-15c2-53d2-b958-c77eb6c3951b | note | VERIFYING DOCUMENTS: This ITP
3f0ba86f-61f3-5019-9415-69503bc28317 | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
83a11a23-115a-584e-b542-ab42ff3c9dac | note | REFERENCE: 607.05
ee671884-afe6-50ed-a0e8-517e7b9dcc0c | note | – – – – – – – – – – – – – – – – –
a87901c2-2de8-5129-8953-b68a64f99518 | note | ACCEPTANCE CRITERIA: Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
9d4b6070-e384-566e-be52-5e9fefcf0c9f | note | ○ Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
befb2217-100d-58d0-abee-c9750e1856cd | note | – – – – – – – – – – – – – – – – –
40a3b7d7-c56f-5a78-ac7c-e199a855e79f | note | METHOD: Measure, Visual
6251b6e4-6aca-5eba-a549-823b9b838526 | note | – – – – – – – – – – – – – – – – –
1e91fba9-653f-50e1-8d58-42fc28f5f63b | note | FREQUENCY: Each pile
08cc4f44-7195-507c-b063-06e923565db9 | note | – – – – – – – – – – – – – – – – –
910d7c5d-1f09-5cff-8997-c7ec7a84e6b9 | note | CATEGORY: HP*
1952dc61-d804-5e02-a661-80751bf7eee8 | note | – – – – – – – – – – – – – – – – –
cd6da1fb-d060-5b9a-a9e9-c87c6d8e2496 | note | RESPONSIBILITY: SPE/PE
930e2a14-b424-56cd-86c9-62f4088530f9 | note | – – – – – – – – – – – – – – – – –
139ea829-398d-5aa3-b58d-e92c6260d418 | note | VERIFYING DOCUMENTS: This ITP
92d17f58-1c4c-56db-8aac-fbfc7ca8d5d1 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Reinforcement - Inspection
71cc85e3-7300-5cfb-8936-e20c7c67077d | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
e58173aa-50b6-5d06-bbb6-e15606408ab5 | note | – – – – – – – – – – – – – – – – –
5518a310-8609-5aa2-a835-c0d8cc5fb2e6 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
b88a9b05-ba65-5565-9227-5dcaa6b87907 | note | ○ Projecting reinforcement is the correct length and location.
dc9d9f1f-7f8b-5e8a-a5b7-8910bbf0dfbf | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
ce182849-d444-5f4e-8003-aaf3505784d8 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
d42bacb0-8798-58b4-b94d-1668cc2a844e | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
da3edd89-0d34-55aa-a760-ce9dce75edee | note | ○ The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
fc2857d5-e576-5df6-8d78-2585664e8820 | note | – – – – – – – – – – – – – – – – –
26dc6085-4b4e-520c-a1e0-6a21f864a0aa | note | METHOD: Measure, Visual
36247318-cebe-5a0d-8dd4-534f7067f1bb | note | – – – – – – – – – – – – – – – – –
c43ea7f4-8ca9-5b73-b68f-d9ee171a7770 | note | FREQUENCY: Each pile
ef69c6fa-944f-5da6-b657-27bd6ad43e0b | note | – – – – – – – – – – – – – – – – –
feb23be9-aa79-5350-899e-e98c85e01a19 | note | CATEGORY: IP
c78be086-dbda-52b6-be44-0e49bebdb27c | note | – – – – – – – – – – – – – – – – –
d2ecb7ac-4eca-56e1-86e8-62bc31f9ddae | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3eb1a448-5ff7-5e1c-9d91-d0d7aadaa20c | note | – – – – – – – – – – – – – – – – –
a58eb6c6-03c7-5a1d-878a-104ad0d6495e | note | VERIFYING DOCUMENTS: This ITP
724e3aaf-c0f8-5fb2-b28d-90f1a38858cc | date | Date Completed:
| checkpoint | 5.2 Reinforcement - Electrical Continuity
e493912b-5be9-504a-97b2-77b2802918b8 | note | REFERENCE: IFC Drawings 610.29 (d), 610.43
18212ef2-6e35-599a-99a5-e81ca9f2a683 | note | – – – – – – – – – – – – – – – – –
e63f36d4-104f-5b35-ba43-14fc199f93b6 | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
a81895c3-230b-5073-a92d-d614bd861764 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
59736c91-d7f5-56ad-8e18-818280ce819c | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
4d59e3a1-84ed-5489-b655-0b57330abb23 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
1886bacc-4579-5203-a636-2a6d764ea664 | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
928b2f18-5aa7-5f8a-90e4-f281ce4b7e75 | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
2a9b0ce5-04bb-5a76-acce-8721d97ab70a | note | – – – – – – – – – – – – – – – – –
37cfdd2f-50b9-57c3-bbe1-7ea3db67d7cd | note | METHOD: Measure, Visual
fcc56d71-c530-5b3c-a101-896e55fadc9a | note | – – – – – – – – – – – – – – – – –
b525e2eb-2ba7-5bf5-a972-507da7fce95c | note | FREQUENCY: Where applicable, each pile
a0767561-74ba-58ca-802c-f5d20b925127 | note | – – – – – – – – – – – – – – – – –
200684bf-df27-5f34-84dc-391a1c03d10e | note | CATEGORY: IP
3a00e492-fb52-5eaf-9a3c-bc3d6727e7dd | note | – – – – – – – – – – – – – – – – –
76ca7d32-99e3-5fd3-a6b4-45e7a94ef191 | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
98c53ee7-e27d-5173-86fe-3a06072c86b6 | note | – – – – – – – – – – – – – – – – –
3a63c3a0-51f2-571b-a125-38839cee3ee6 | note | VERIFYING DOCUMENTS: This ITP
240ef8bb-746c-5c39-99ef-cdbb5ed773bc | date | Date Completed:
| checkpoint | 5.3 Augering Operations
fcdbaca9-0c23-59c6-b09b-402638ebcc2a | note | REFERENCE: IFC Drawings 607.04
cf151e9e-e445-58c9-9153-d90ab2f777e1 | note | – – – – – – – – – – – – – – – – –
109cf183-117e-58b2-83df-f85682f856b2 | note | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
caeb467f-a0a4-5cb1-a8d2-d22914f82857 | note | ○ The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
09765511-eac2-5413-ac31-c7c77227e361 | note | ○ Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
28094a3f-7062-5b57-ac64-cbfd69413d53 | note | – – – – – – – – – – – – – – – – –
2e852797-d569-5375-a94c-afadac9b6d1c | note | METHOD: Measure, Visual
29639528-a711-59f5-9e6c-db4abf11fc21 | note | – – – – – – – – – – – – – – – – –
6dfbeb58-690a-52bf-a5f0-e2ea9b346b8d | note | FREQUENCY: Each pile
164c5f35-af5b-5edc-aa98-b45a4f8bd4a3 | note | – – – – – – – – – – – – – – – – –
4fbc5f7a-c8b7-5141-9801-b69ad10d557a | note | CATEGORY: IP
4532ee6b-0d83-55e6-bcd8-31238bfbe361 | note | – – – – – – – – – – – – – – – – –
be7c161f-5943-5735-9bec-790915c6c5de | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
dddea390-4f3b-50dc-b3a0-f8ffd4ca0ee5 | note | – – – – – – – – – – – – – – – – –
838d3a92-b172-5fa8-8a2b-6c7a57558294 | note | VERIFYING DOCUMENTS: This ITP
e935d3db-5a0d-5de5-a917-2c40cd25f302 | date | Date Completed:
| checkpoint | 5.4 Inspection of Excavated Material
71fc95cd-b548-53e2-9396-d70a9ce5e50a | note | REFERENCE: 607.04
d6d4b4d3-3874-5e17-b2f0-2fc87aaa52cd | note | – – – – – – – – – – – – – – – – –
b39e7e9b-0032-5a6e-b7ce-672a4b703fea | note | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
49693156-86da-5c5a-8b7f-25a8d873afbd | note | Attach: Geotechnical Field Sheet or Report
f2db6836-bea0-5541-8e0b-db43d020fd89 | note | – – – – – – – – – – – – – – – – –
b3cf4ed2-a78f-52d8-beb7-cbef2a13b07d | note | METHOD: Measure, Visual
76a1363d-1f72-5283-80b9-5478c2423490 | note | – – – – – – – – – – – – – – – – –
87f60046-488f-59d0-aea2-7b816f4b4c5e | note | FREQUENCY: Each pile
33bf5ec6-ef34-54ca-a98d-1cb37f021970 | note | – – – – – – – – – – – – – – – – –
36626423-dce4-5bbf-8c8e-d74931b30bb2 | note | CATEGORY: HP
51e603d8-78fd-5f09-a5db-9410414acfea | note | – – – – – – – – – – – – – – – – –
69493d29-491a-5be9-98ba-d413598738fb | note | RESPONSIBILITY: Geotechnical Engineer
c99bece1-b435-576b-a1b7-ac994c9a970d | note | – – – – – – – – – – – – – – – – –
05a0bd0f-9efe-5650-a3b3-65aeddfd2c5d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
239684ae-3c8b-57c9-89cc-8591b24d84da | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 Increase in Depth Beyond Design
f9124dcd-63e7-5c3e-9779-ccc927a48077 | note | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
49365e61-4848-5e66-951b-ca5e73d15d73 | note | – – – – – – – – – – – – – – – – –
f2915281-9ba8-538f-9837-cebb72d20b0d | note | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
63f98458-887a-5fbe-9860-cbab85de43f7 | note | ○ A full account of the changes shall be submitted for approval to the Nominated Authority:
0d1142f5-4490-596f-9823-24f22d5545cf | note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
4b42d1dd-27e7-5643-be42-a7d6554682ea | note | – – – – – – – – – – – – – – – – –
bccd2a1a-d64d-5579-9215-62e461e035e0 | note | METHOD: Measure, Document Review
4769f511-22d4-5cd0-8d47-0f37f2f6cc12 | note | – – – – – – – – – – – – – – – – –
1676d798-c39f-50a2-bd3e-92405436ab65 | note | FREQUENCY: Where applicable
c2c17470-925c-54f5-acdc-d1b5f7ae5256 | note | – – – – – – – – – – – – – – – – –
2b64afbe-4aa4-5cfe-88e5-838f4da72b43 | note | CATEGORY: HP
5ed44b24-af6f-5c4b-a437-ddc09662b651 | note | – – – – – – – – – – – – – – – – –
bc398501-5918-5a72-8693-07ea401d856b | note | RESPONSIBILITY: Geotechnical Engineer
8af1d52c-929f-53f3-872b-171abb89e0ba | note | – – – – – – – – – – – – – – – – –
1704fbfe-5448-5674-927a-5f792aec80d9 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f9664053-79b4-5daa-8273-e7385a13f601 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Weather Conditions & Evaporation Limits
6c4354bb-d852-52c0-8018-8944342ef096 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
5a1df9d5-edc6-5c55-a509-a5894a1ca898 | note | – – – – – – – – – – – – – – – – –
2bfbf3ac-1c99-52c4-8445-372dc54e38d3 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
3ea0d18b-60a5-5514-8e8f-ac6ba200ea6e | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ebdc9e67-5ffb-53aa-ac9a-fb22f6e21162 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
628a5fb2-e53c-555d-bd25-908615bb9017 | note | Record: Required information on the Concrete Pour Record.
0207048a-9d59-5e53-95c2-5b4b3a7a8aeb | note | – – – – – – – – – – – – – – – – –
579bdd69-d9e1-58fa-8803-43eb36e30b06 | note | METHOD: Measure, Visual
6b83db97-ad3d-5e29-b0c0-7119bda0bf93 | note | – – – – – – – – – – – – – – – – –
a5ae7fd0-cfe3-5061-9a9b-9e39b467e608 | note | FREQUENCY: Each pile
e25d8e69-2d97-50bf-81cd-4f27f0782d75 | note | – – – – – – – – – – – – – – – – –
3147301b-9326-5ea8-81ea-6d4430876e89 | note | CATEGORY: IP
4a2ac6ef-6741-53af-a100-b88bc4480934 | note | – – – – – – – – – – – – – – – – –
052e952e-0171-5b7d-8d30-476a74cd23cf | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fb436669-b701-5d6f-b8f9-3b723421700b | note | – – – – – – – – – – – – – – – – –
beb40417-efb0-5041-8030-9420435e2143 | note | VERIFYING DOCUMENTS: This ITP
10b82ba4-839f-5762-91f1-036142b6c433 | date | Date Completed:
| checkpoint | 5.7 Concrete Testing - Sampling Frequency
ac7d0bb7-39ad-55ba-8f77-67607991cf8f | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
1d85bd2c-cc53-5148-8ffd-f98dee8a74fc | note | – – – – – – – – – – – – – – – – –
7578848b-3589-5dfb-8d00-b4dcdb3c6803 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
6628801e-91d8-58e2-a0b6-719d28c7fef7 | note | 0m³ to 10m³ = 1 sample
9fbeb11c-1230-53c7-a0f7-b308753c661d | note | 10m³ to 25m³ = 2 samples
b70783f5-c31f-574a-8d5d-cb0a10ff5584 | note | 25m³ to 50m³ = 3 samples
024ffec2-ac2b-547d-9dbc-ef13bac034ce | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
3cbbbc94-49a5-5ff3-b5ff-8c25a3fa1671 | note | ○ For each additional 50m³ and additional sample shall be taken.
0ae47074-e043-52ec-9887-7f59ed77406c | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
db5197d1-6aa5-5641-91eb-781087e3629d | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
3bd648e9-23e9-52db-9aef-78c988e5d58f | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
a4f19947-3038-55f9-9e55-ffa5b75ce72e | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
457ddedb-2a49-512d-96a5-d7e476beef5d | note | Record: Required information on the Concrete Pour Record.
de9bb299-49f2-53f0-908b-8d56b1431b47 | note | – – – – – – – – – – – – – – – – –
b84a4e04-b62f-51c8-a4db-9e8786dce195 | note | METHOD: Test
51a1e4aa-1327-5602-8024-9e980ddef260 | note | – – – – – – – – – – – – – – – – –
23c9c9a3-d9b6-56c2-bfd3-18eb3eaa3d6d | note | FREQUENCY: Each pile
7b8d6229-4dca-5a60-b159-5809154295d4 | note | – – – – – – – – – – – – – – – – –
2575d3f3-3cba-5829-a767-f396132298af | note | CATEGORY: IP
993dcf6c-e699-5dae-a508-ad7d7a61d1ca | note | – – – – – – – – – – – – – – – – –
c213cdca-a3dc-5d87-a0e0-0d1641ced218 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
e4f8abde-6567-5383-97a2-a0a0ce9abf96 | note | – – – – – – – – – – – – – – – – –
db32c4f0-e06d-59c8-9921-bce02f9c181c | note | VERIFYING DOCUMENTS: This ITP
e67c3525-aa9e-5f30-ac14-379b30be2b72 | date | Date Completed:
| checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
5e2dc623-9b53-5eb8-bf78-96e775507633 | note | REFERENCE: 610.13 (b)
15c863ac-ddb1-574d-80e2-9732a509e952 | note | – – – – – – – – – – – – – – – – –
8f8d3f22-a83a-562e-9381-1438e1dc0160 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 800mm
593674fa-5430-5247-bc7c-9e088e404520 | note | ○ T500 = 1 seconds to 5 seconds (to reach a spread of 500mm)
d11a385b-dd49-52d9-8b5b-0229f24830fc | note | ○ Passability = ≤10mm (aggregate height differential)
10ac6740-46da-5c60-99ae-ad8854cfb615 | note | Record: Required information on the Concrete Pour Record.
99ab5fd4-ae66-55e1-a373-9d47039b29d0 | note | – – – – – – – – – – – – – – – – –
d171d348-0130-5000-9041-ffae8ac654bf | note | METHOD: Test
d6855e56-8457-5ac6-a0d9-1a6490046304 | note | – – – – – – – – – – – – – – – – –
13a47615-5744-5507-be00-be23d3d27046 | note | FREQUENCY: Each sample of Self-compacting Concrete
62946e57-a8bd-5589-bd6b-34223c6ac4fd | note | – – – – – – – – – – – – – – – – –
8ea9b865-7623-5eb4-8355-592f159f1463 | note | CATEGORY: IP
cbfec71b-d19f-58c6-9f40-32793a855397 | note | – – – – – – – – – – – – – – – – –
60d1bfc2-ca9c-5372-b823-a77fc5b31473 | note | RESPONSIBILITY: Concrete Tester
4ed410e5-f63a-5133-93ac-4778a23a2be5 | note | – – – – – – – – – – – – – – – – –
215c2bb6-63b9-53e9-9a97-049ef3220173 | note | VERIFYING DOCUMENTS: This ITP
545b0136-5480-56f0-9ef7-9e7eb392b03c | date | Date Completed:
| checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
f0c78711-6bd0-539e-9b2a-a4be8c971b7d | note | REFERENCE: Site Sampling & Testing Procedure 610.16
b00e08a6-63db-5373-a89c-2df8daca0a58 | note | – – – – – – – – – – – – – – – – –
b60dfe3e-5f6d-579c-9a86-dcb60433d71a | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
653d7941-1dcd-53bc-9a60-8017ecf8d9f9 | note | Record: Required information on the Concrete Pour Record.
d45f1c54-a644-5c80-ab55-5974a7d62f38 | note | – – – – – – – – – – – – – – – – –
fc711092-c709-597d-b116-1bab7c7084e6 | note | METHOD: Test
bf2fdc4e-a54d-5a61-b5a0-df9badb87d3e | note | – – – – – – – – – – – – – – – – –
99972190-acba-5c92-9c8d-16b38acc7faa | note | FREQUENCY: Each sample
5e3d3585-6b65-505a-8ed5-c7d8bd3d22f3 | note | – – – – – – – – – – – – – – – – –
ae043bf1-f888-5c23-801d-3bb2533fa8b2 | note | CATEGORY: IP
41a1d36c-1f20-5521-95db-7b5b6ec23946 | note | – – – – – – – – – – – – – – – – –
462db342-c01c-5e80-a0bf-81220451a24b | note | RESPONSIBILITY: Concrete Tester
536b87da-3a19-5812-97d7-62e347f2b879 | note | – – – – – – – – – – – – – – – – –
0d0e7f0e-d6c7-5208-a04c-0de8f0baefd4 | note | VERIFYING DOCUMENTS: This ITP
ee3e51c0-0365-5570-8877-530506af4145 | date | Date Completed:
| checkpoint | 5.10 Concrete Placement & Compaction
d9f51a49-e7c6-502f-8b17-43993afc5966 | note | REFERENCE: Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
e937d999-b1f3-52d5-bb9e-067a32c67af3 | note | – – – – – – – – – – – – – – – – –
4997cf07-aee7-54f8-968c-892665635212 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
898f8009-0403-565e-8ca6-8444d2fd0bb9 | note | ○ The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
eb25a466-1e4a-5c09-8296-dfca6fb34bb4 | note | ○ The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
85e8b27b-040e-56b6-8b4c-519c20ee1d7a | note | ○ Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
9e1d5c24-5cf8-54c4-8734-38426d72da6c | note | ○ Concrete shall not be dropped freely from a height exceeding two metres
670d0627-dcd1-5901-9d38-20f53c8ffe98 | note | Record: Required information on the Concrete Pour Record.
7744503c-a0b2-5291-a263-0358dd4d0452 | note | Attach: Concrete Pour Record
0e01ed58-de64-5079-b6c4-e669f4984f5a | note | Attach: Concrete Dockets
7abf77d8-ae91-591b-9d91-c9563353b184 | note | – – – – – – – – – – – – – – – – –
a8ddd601-10b4-5e03-8930-bc363af5f085 | note | METHOD: Visual
53c10c88-dd04-5097-8a81-f74955a76599 | note | – – – – – – – – – – – – – – – – –
09f5c2e3-eb34-5ccb-bbaf-2333e127c394 | note | FREQUENCY: Each load
4e3d870d-0b2f-5ed3-8b39-6dd9ba167ed2 | note | – – – – – – – – – – – – – – – – –
4342c1f0-02c0-5715-b503-4bfabb32d49f | note | CATEGORY: SP
7bdc4771-f26d-569b-90cc-b8165e24a9a4 | note | – – – – – – – – – – – – – – – – –
3592eed4-3302-58ac-bc33-06cc9b83c45c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
02946fac-f1d3-578d-9c79-d67446ec4d4a | date | Date Completed:
| checkpoint | 5.11 Reinforcement - Placement
ce0991c5-0a13-5d92-95ca-195a23c75154 | note | REFERENCE: IFC Drawings 607.04
00190cb7-0a0c-59a6-b53b-d097004f58b8 | note | – – – – – – – – – – – – – – – – –
ccc2c1e2-d28e-5939-a435-ec3ea83daf2d | note | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
18df4be8-bbc1-5f0d-9e38-f6ae8771192d | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
75d2d33e-da21-5de2-a0b6-fa19c8ec8368 | note | ○ If the cage cannot be positioned into its final level, the pile shall be rejected.
8f29b8c7-7f7e-56d6-9de5-80fa7912fc4d | note | – – – – – – – – – – – – – – – – –
c0befef7-6255-5147-b38d-cf35b1d29f6d | note | METHOD: Measure, Visual
91eab24d-cf54-517a-9f6f-6875e4df196e | note | – – – – – – – – – – – – – – – – –
9a5e0784-501b-58a9-8996-6b7c17295266 | note | FREQUENCY: Each pile
684ce3a6-dcc3-52c4-a735-b357586a4e03 | note | – – – – – – – – – – – – – – – – –
1047a014-24ec-520a-b124-1af0c6f34096 | note | CATEGORY: IP
f32ab5a1-d42a-59ae-b98f-3a105ff1a55f | note | – – – – – – – – – – – – – – – – –
437ee4ef-b999-56de-819b-0f6ea5baa849 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
e08b014a-0c31-5bef-9bae-2cd63c8c5dfe | note | – – – – – – – – – – – – – – – – –
a115dfc8-d804-5457-a76e-d0f2087daf03 | note | VERIFYING DOCUMENTS: This ITP
126dff5e-b0b4-523c-a0d6-9cfaf502da77 | date | Date Completed:
| checkpoint | 5.12 Cast-in Items
3c2c83f6-59c0-526b-958d-327a27e7ca5f | note | REFERENCE: IFC Drawings 610.46 (a) Table 610.462 (November 2018)
1fd6a4f7-5a4f-56be-8c74-ca4f5d5a5a9a | note | ○ 610.47 (a) Table 610.472 (March/June 2019)
c2ac5438-cf98-5fb4-bf12-099f42937442 | note | ○ AS3810.1 Table 3.3.6.2
cc9b041e-8bc7-5f41-bf7d-e0d51c37dc61 | note | – – – – – – – – – – – – – – – – –
8d88710e-467d-53d4-ac96-50487bbf7154 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
f0771329-3e57-57b7-95c8-f480267ea620 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
44c4a07b-63e1-5c9e-b23d-26ba54ba16b1 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
3cf8b8bf-bdee-598c-bd4a-cf963b0941d2 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
436738de-4698-565c-9fd9-3dbff70dcea7 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
f5c8d27e-e6a9-57e6-bb39-84112e3b5ac0 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
bf197ad8-db8c-5859-8db0-c44599022e4d | note | ii. Running dimensions of a group of the above = ±6mm
79572661-e04f-561f-9f43-432238085da3 | note | iii. Ducts and conduit location = ±12mm
51718b28-3504-5559-946a-a9690c8e4050 | note | iv. Diameter of ducts and conduits = ±3mm
d6be6812-4bc6-54a0-a12a-85358fc349e1 | note | – – – – – – – – – – – – – – – – –
540f38bf-0cff-52b2-836a-bfc3302671b7 | note | METHOD: Measure, Visual
6b7eaf0b-711f-5e4b-a255-bd6072e46aed | note | – – – – – – – – – – – – – – – – –
683dd1be-521a-5cda-be3f-7171bf7e8e78 | note | FREQUENCY: Where applicable, each pile
dea35585-b472-5680-aeb3-ecbbfcd8074e | note | – – – – – – – – – – – – – – – – –
5aa0bdb0-398d-5677-b045-f75639d5ae22 | note | CATEGORY: IP
435c6e37-cee7-58cd-8947-fe6c7049a62a | note | – – – – – – – – – – – – – – – – –
da010cf0-96ea-5f56-a499-f09bf4ce8de4 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9a2d4287-4483-503d-82c0-05c05fde6027 | note | – – – – – – – – – – – – – – – – –
6cd847fc-5829-5e44-bdd1-62e49a37deed | note | VERIFYING DOCUMENTS: This ITP
e64249c7-058f-5017-9cf3-40962fc29968 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Pile Trimming
7bef164d-ae2c-52a8-a450-1975892f6034 | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 607.04
f02a7fa5-809d-5e61-a112-06e0852936b4 | note | – – – – – – – – – – – – – – – – –
f9205aae-9e43-5266-815a-112b2ed5ae01 | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
5b30e2da-9ebb-5bb7-bade-4296dae3596d | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
817fe356-09fb-57b8-906b-3aa32c63f1bf | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
01c2a79b-2e7b-5b47-8948-3dfe9e789ffd | note | – – – – – – – – – – – – – – – – –
3db81e58-01a0-5d24-b189-0bd81669f348 | note | METHOD: Measure, Visual
605d81ed-2cea-575f-8bca-0f5912f3de0c | note | – – – – – – – – – – – – – – – – –
5cff535d-afa9-5d85-bdfb-0eeb79c1ee2c | note | FREQUENCY: Where applicable, each pile
cb317560-1340-5e7f-befd-be021f1c42f8 | note | – – – – – – – – – – – – – – – – –
1f6a7455-dfb8-5216-8a92-a2e8209c1f75 | note | CATEGORY: IP
0359b341-c601-5b14-8fcb-bda69fbffd5d | note | – – – – – – – – – – – – – – – – –
fbbfed90-f65e-565b-bf17-3612acc9b6c8 | note | RESPONSIBILITY: SE/PE/SPE
26bf46fb-07f5-58b4-9a9f-c085ab1f9e21 | note | – – – – – – – – – – – – – – – – –
8075161e-b72e-54af-8af7-105380acd7e5 | note | VERIFYING DOCUMENTS: This ITP
a7af3056-0950-516c-a842-8e1c38e37cc8 | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
9d39fd02-4ce9-5030-b1e3-37d86a0062b1 | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
f84c1f03-2de4-5b40-a2be-395cb5adcc73 | note | – – – – – – – – – – – – – – – – –
c005c0f0-2a0e-5690-b970-072be1196d57 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
562d5435-97d8-55de-aff1-04b3f0aaffcf | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
d2e5098f-66e8-5ce8-8f69-a54e053537d4 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
75d2af20-8ad1-5831-918a-decbffd2db8b | note | Attach: Compressive Strength Test Results
04e96597-eaf3-5d6c-9894-3e62b417553d | note | – – – – – – – – – – – – – – – – –
f9bca2ad-3692-5231-b577-7b504c1d0b1e | note | METHOD: Document Review
fcaa88e1-2538-552c-9df7-4e1a213795c5 | note | – – – – – – – – – – – – – – – – –
809383ad-a030-56a1-af48-3bb593563136 | note | FREQUENCY: Each cylinder
9c891015-39a0-5ad5-be4f-b1f8610bbee0 | note | – – – – – – – – – – – – – – – – –
2a60605a-484b-5f41-b935-03213d203ee5 | note | CATEGORY: IP
2a5253aa-311e-58d9-bced-5f6b0092aae1 | note | – – – – – – – – – – – – – – – – –
536e328d-d62b-5618-9d28-697c107c0074 | note | RESPONSIBILITY: SE/PE/SPE
674ce256-2596-5a15-9f2d-66bc22a4fb94 | note | – – – – – – – – – – – – – – – – –
15f64e95-e718-5866-9570-39856bdefbed | note | VERIFYING DOCUMENTS: This ITP
702beb48-3fa1-5036-b8a7-694ba4e5aa9a | date | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
00864ccf-c2e7-549a-9070-7d3ec5d62cc0 | note | REFERENCE: 607.07 AS2159 Clause 8.8
2a6d7b7e-f0fa-5503-a58d-b02db6b1840e | note | – – – – – – – – – – – – – – – – –
450bc72a-1aa1-5afd-a47d-0cccbd4aeb61 | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
adcb6431-ded1-5d5c-bafd-8a0ddf9b9db5 | note | ○ Cross-sectional area = ≥90%
7ec9b674-f4ab-5a05-a5b8-70936e1cf458 | note | Attach: Pile Integrity Test Report
b4d80fdc-990c-5d90-a291-86657f9cb086 | note | – – – – – – – – – – – – – – – – –
2e2d9e09-ac8c-57c5-a67f-de3dadc516d7 | note | METHOD: Document Review
81f187cb-fac3-5a26-b2d9-ae45fcde2ec6 | note | – – – – – – – – – – – – – – – – –
92adc1e3-4234-5db4-88c5-696bb3c03e52 | note | FREQUENCY: Each pile
a1bb3602-fd55-52a8-9e06-e802936d31f8 | note | – – – – – – – – – – – – – – – – –
85743e41-d18c-5136-a007-415402d3c804 | note | CATEGORY: IP
153eeceb-31a2-5174-a085-9497fa59fa04 | note | – – – – – – – – – – – – – – – – –
ae9f86f8-2d9b-5738-a234-c094a7397a26 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
4ab01659-9478-561d-9ff0-d50e2c1fd4fa | note | – – – – – – – – – – – – – – – – –
94ca1e02-3e64-5d78-b672-423957c5390a | note | VERIFYING DOCUMENTS: This ITP
133c7689-a2ea-5b50-9f71-ef45888ed198 | date | Date Completed:
| checkpoint | 6.4 Dynamic Pile Testing
d3164511-61e9-5ec3-b8ba-b0c361e47b5c | note | REFERENCE: 607.07 (b) AS2159 Clause 8.7
3f0a954b-937c-5c3a-b70d-e1f1dd54b7d0 | note | – – – – – – – – – – – – – – – – –
f14a479a-f0cb-524c-b9dc-18f9e04595f0 | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
ffd457e9-b484-557a-b0fb-ec4a976d801c | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
2be4bac9-b885-5a19-a0d3-4dde2aef5fbd | note | Attach: Dynamic Pile Test Report
2f30e772-6a75-5017-9c29-ecfe64d7a57d | note | – – – – – – – – – – – – – – – – –
54aeccb8-890a-5c24-ad56-df4671745119 | note | METHOD: Document Review
658f8039-ce16-5b03-9b70-39ff428082d6 | note | – – – – – – – – – – – – – – – – –
87120cf2-08b3-5a19-b82e-2c72da7acec0 | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
caa3c493-22ff-504d-894e-510c444eb0c9 | note | – – – – – – – – – – – – – – – – –
871fdcc6-fe67-5a45-9ba2-9d579c91ab88 | note | CATEGORY: IP
0a706749-7b70-5906-a0d3-1bbfb0cb1819 | note | – – – – – – – – – – – – – – – – –
e14dabb8-89c8-5e13-9576-6ce6c491c892 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
0c6f4e71-2bce-51e6-b4e4-c591e5accaf3 | note | – – – – – – – – – – – – – – – – –
f38b6867-345f-52fc-8653-47ffb6b6c568 | note | VERIFYING DOCUMENTS: This ITP
3b2beda6-c96a-5c42-9a8d-e2cac5a28756 | date | Date Completed:
| checkpoint | 6.5 As-built Survey
c281510d-156a-51ca-8472-2fa6f48bdcdf | note | REFERENCE: IFC Drawings 607.06 (a & b) AS 2159 Clause 7.2.1 and 7.2.2
3bd64545-9446-5526-8816-dca9bb04e8fb | note | – – – – – – – – – – – – – – – – –
2fd3fdd2-4271-584a-bda6-051c9408c122 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
1dab2f0a-1665-5ce4-8473-88abd27a7be5 | note | i. Centre of pile head plan location = ±75mm
da5d8ec4-9376-5cc3-9407-bc34928aa3c6 | note | ii. Variance from vertical or rake = 1:50
521ebe53-c830-5157-9929-2319a93e56c8 | note | iii. Irregularities in straightness = 1:100
6f60fece-aaf0-5d31-8027-074d482e3130 | note | iv. RL = ±25mm
5787ac3d-cbe8-5322-999f-2f813aa50804 | note | Attach: Survey As-builts / Survey Report
83c76d28-3b69-5a72-a849-a63f4abc9ae2 | note | – – – – – – – – – – – – – – – – –
fa5dd911-cfa3-583d-a396-6cc61d7fb344 | note | METHOD: Document Review
4ee4401f-6495-583e-b437-0422317cdb92 | note | – – – – – – – – – – – – – – – – –
b1e72821-4a70-5e7e-9107-4813674a239d | note | FREQUENCY: Each pile
7479e714-053c-53d5-aec5-4a5c397c4c72 | note | – – – – – – – – – – – – – – – – –
423180c8-be90-576d-a392-75f63db5a613 | note | CATEGORY: IP
c24047d4-86af-5723-a73d-16611789e6d4 | note | – – – – – – – – – – – – – – – – –
f69743a7-f5e8-52cc-87af-6564201dc56b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
4c752cba-4c6b-51c9-a757-6cc3624be485 | note | – – – – – – – – – – – – – – – – –
da537542-7966-5e7e-b41f-cc9073ca8ec9 | note | VERIFYING DOCUMENTS: This ITP
3a13f2cf-e496-59c5-823c-a00fea1e2153 | date | Date Completed:
| checkpoint | 6.6 Non-conformance Report (NCR) Closure
285d42de-6e77-5ef4-bade-ffd58e6f0853 | note | REFERENCE: MRPA Quality Management Plan
8da411c2-cd18-596a-8e4e-cc0a1ab80b07 | note | – – – – – – – – – – – – – – – – –
ec613088-7a1e-505a-8ecc-fa70bfe0bdc4 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1813bfaf-cd76-5917-a6dc-ba56e0ff075b | note | – – – – – – – – – – – – – – – – –
35ba151b-82b1-5a88-ac5b-26601cf3e8ef | note | METHOD: Document Review
18220dbb-0d0e-59df-9e52-6f99c30882f6 | note | – – – – – – – – – – – – – – – – –
89a38244-6f50-57f0-ab49-79080c4cfc1b | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
f8b4a8c5-2110-5357-8f7d-6b43669fcff4 | note | – – – – – – – – – – – – – – – – –
f87fc22e-aa4b-5582-a3b2-c9a4733300a1 | note | CATEGORY: HP*
bbb8baf0-c02c-5b1b-835f-36c3c989d792 | note | – – – – – – – – – – – – – – – – –
ca721224-81c7-5244-8c0e-2704fd3b053d | note | RESPONSIBILITY: SE/PE/SPE
4aa76577-c2bf-5d24-af70-311964defd83 | note | – – – – – – – – – – – – – – – – –
8fdb0309-bc25-565a-af81-8d7bec21f06c | note | VERIFYING DOCUMENTS: This ITP
ea549437-e0d5-5974-a552-041cf88789be | date | Date Completed:
| checkpoint | Final Inspection
ade42c8e-cc3e-52cc-9d3b-e95f1725a8fb | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b71565bd-6a4d-522d-ae58-f0a2c6755796 | textbox | Name:
38993dc6-6259-5e1b-bd29-18691443d425 | textbox | Position:
38459256-5491-5501-b890-cb0b4417df56 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-089-STR-SSB-Precast Driven Pile Installation Rev 0 | itp | ITP-089-STR-SSB-Precast Driven Pile Installation | 682b3e93-b886-4b68-9da0-d8c2de32b70b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0c2b3e02-7cbe-5b14-a108-a38aa5c867a3 | note | Document Title: ITP-065-CIV-Camms-Landscaping-Ground Preparation
d3251015-c2a1-5698-8d12-a52a5b4b3c49 | note | ITP Description: Landscaping - Ground Preparation (Subcontractor)
932b4185-c915-5271-ace3-6a6abfd3d7f0 | note | Discipline (e.g. CIV/STR/RAIL): CIV
b3a0db35-c807-5343-b5db-95e33830c97e | note | Revision Number: 0
07440d0b-92d1-5fda-9c48-94cdf361010b | note | ITP created by: Victor Mira
7738fa20-f9c6-5ff7-b387-a27471ab8477 | note | ITP approved for use by: Victor Mira
3c4715ae-7ff0-5b7d-99aa-475be42ad983 | note | 1.1 Non Dependent
6f13767b-3842-5bd2-a666-d9ef70b22dc3 | note | Reference: AS 2159-2019
28cdc70b-8658-5ac2-9599-df8db7be83e2 | note | 1.2 Non Dependent
3167bcbe-e39c-563f-96fd-3cea2449e6b5 | note | Reference: Vicroads Section 605 June 2018
a1a3c698-4d55-5452-810f-c3b62049cfdb | note | 1.3 Non Dependent
70403535-9983-5c43-8434-7054ac0cf7a7 | note | Reference: VicRoads BTN 023
| section | Preliminaries - Materials
| checkpoint | 2.1 Precast element
09ab5e77-afab-506b-aab1-398908605461 | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019)
505fcc85-abe3-520d-a5bf-15aaf0f16e93 | note | – – – – – – – – – – – – – – – – –
890e68a6-8cdc-5105-9d54-6cc69f55c82b | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the Quality Assurance documentation for each element, typically this consists of:
4f10705a-88ea-5efb-b14d-fd21e5041435 | note | i. Certificate of Compliance / Birth Certificate
8cf1524e-000e-51bf-b3a7-15ce93643097 | note | ii. Compressive strength test results
c019d744-283f-5b93-b4c0-605877f3084a | note | iii. Precast Lifting Design
0361dfe1-a9cd-5eeb-910b-5edd0f321bd0 | note | iv. Pre-pour check sheet / ITP
f9ef298a-2612-50d3-8244-d4919e2ab36b | note | v. Post-pour check sheet / ITP
d5e6543e-8f09-5f1f-9c90-ee289d3d8e45 | note | vi. Covermeter check record
265fb25e-70c9-5e5d-8942-8742f9af3c43 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast as per VR 610
84534942-49ed-58d2-8c8e-a04555116ff7 | note | Minimum age before driving:
9424bb9f-b7b3-5a3b-a25b-eb7ed47f7daa | note | ○ Steam cured 7 days after the date of casting
6406287a-97aa-54cc-9a0b-e6458c7764d4 | note | ○ Moist cured 14 days after the date of casting
0d155a25-f92a-57d7-b607-8145be5cf439 | note | ○ provided that in all cases the specified concrete strength has been achieved.
67ea357e-1034-52e2-a073-e0cfd8eef7d2 | note | ATTACH BIRTH CERTIFICATE
bc948092-dbf7-5f32-ba10-30c8e46caf29 | note | – – – – – – – – – – – – – – – – –
0e568f6b-cca5-5955-bbdf-b2e8b0983702 | note | METHOD: Document Review
9549056e-a489-50ca-acb6-ddecbfaed3b9 | note | – – – – – – – – – – – – – – – – –
a3df08c0-77b1-577d-b2db-2bb6001d8eec | note | FREQUENCY: Each element
b91a5765-bff3-5d63-b9e7-d143c10f9667 | note | – – – – – – – – – – – – – – – – –
4a980461-3db2-56fe-a544-e2a761444d8d | note | CATEGORY: HP
9a7d472d-88cd-586f-98ce-4d7e8647be08 | note | – – – – – – – – – – – – – – – – –
f15cf415-dac7-5ed8-b51d-d23f7687a30d | note | RESPONSIBILITY: PE/Nominated Authority
01661989-3576-5e6d-b678-1c61f75ddf66 | note | – – – – – – – – – – – – – – – – –
46cc7c72-0bab-5dde-96fc-6b31f787af78 | note | VERIFYING DOCUMENTS: This ITP, Birth Certificate
20cf5673-d654-5f05-86cf-604c6cf5257f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Precast piles
9d6d8f2c-6f14-583e-a9a0-6887bd2381a3 | note | REFERENCE: VR 605.01
2057ca60-ebc0-50f4-ae77-2fb0f7008bf0 | note | – – – – – – – – – – – – – – – – –
d3aa1072-a3f6-5a78-bd0a-c2ef24caff4f | note | ACCEPTANCE CRITERIA: Care must be taken to ensure that piles are not damaged during transport, handling and driving.
215f0a9f-5755-52b6-b91a-60f7982dba81 | note | ○ Piles shall be inspected for their length and cross section prior installtion.
d1039ea5-2e2d-5d55-8894-a92d9fb44abd | note | ○ Piles shall be inspected for any defects.
51368c07-52c5-5e7d-8cf5-a8e33e090eaf | note | – – – – – – – – – – – – – – – – –
9551e091-050d-524f-a584-87d22c4bb5af | note | METHOD: Visual
84590600-8e1c-54ec-93f6-3fe3493cc7e6 | note | – – – – – – – – – – – – – – – – –
91f05441-3f3f-50f3-a73d-51eaad41b9df | note | FREQUENCY: Each pile
9c61030a-34c1-5c94-a3ad-0570af6bcc87 | note | – – – – – – – – – – – – – – – – –
af428225-771d-5682-a90d-67b9fccb7b2b | note | CATEGORY: HP*
e91ad308-6478-5b1d-b1fe-62ceab3dcd6b | note | – – – – – – – – – – – – – – – – –
1c85a97f-c8a4-5e75-9f2f-3ddbe807884a | note | RESPONSIBILITY: SE/PE
8e958899-5442-5cf4-862d-93fe4ba485e6 | note | – – – – – – – – – – – – – – – – –
126dbb1d-1045-53bf-b942-a77e8dbfa959 | note | VERIFYING DOCUMENTS: This ITP
46f1212e-6cf9-5a36-a9ac-b3b0776e7740 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Driving System
5206ee4e-7fd6-540e-b3f4-c713a1cd219b | note | REFERENCE: VR 605.02
37cc1932-3b0d-5bfa-a736-a0534ba1a437 | note | – – – – – – – – – – – – – – – – –
b806e463-1d20-5b68-820d-7f583f190702 | note | ACCEPTANCE CRITERIA: If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
3014f124-821c-55e0-9e96-04d157850703 | note | ○ The Contractor shall provide details of the driving system including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap-block and cushion materials.
5e4c9f0a-49a2-53b2-a2fb-95f961b4ac8d | note | ○ These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, shall be submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving.
ca1d5497-6ce9-542b-8da4-ee3777423503 | note | ○ If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
d1de81d8-24cf-5d53-92a7-b0f5fcca5845 | textbox | Enter: Teambinder Approval number
10b9d996-d6cf-502c-8d1e-9bcf4fef912e | note | – – – – – – – – – – – – – – – – –
fe914f00-05a2-51d6-94aa-66755244ef1c | note | METHOD: Document review
61c4b6cc-570c-559e-a030-194d0e2a578b | note | – – – – – – – – – – – – – – – – –
532d8344-e2c6-57e1-a181-3fa6b87c1e2d | note | FREQUENCY: Prior driving
656b7631-e58f-5659-bd05-3ac1f68ea623 | note | – – – – – – – – – – – – – – – – –
c6aa5f21-c574-5335-8c42-51e1515a5323 | note | CATEGORY: HP
1a4d97f0-1512-57a8-93e5-b16bc13df2d8 | note | – – – – – – – – – – – – – – – – –
765cdb6e-d1f3-5bf2-a01a-03979f9e9527 | note | RESPONSIBILITY: PE/Nominated Authority
c6a0b5e5-20c4-50da-9229-93944eaac8d8 | note | – – – – – – – – – – – – – – – – –
232cac7a-e3f1-5fe6-a1cc-5c95a82769d9 | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
da21c924-4203-5dfd-bca8-4b9a55252567 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Monitoring
c9b1889f-718e-5b54-82b1-97f9420afba5 | note | REFERENCE: 605.04
ba8decb3-821a-5116-b7ef-25dec41a4ddb | note | – – – – – – – – – – – – – – – – –
f68db9b8-13a8-5ce9-82b1-4367bb6f27fb | note | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile. Where set measurements cannot be undertaken due to OH&S issues, the Contractor shall provide alternative methods to the Superintendent for review at least 7 days prior to pile driving.
d69cada0-3f51-5405-b649-2ddc7969405d | textbox | Enter: Teambinder Approval number: [free text box]
c00fc7cb-8f4b-5e8e-a646-ec3f6611a906 | note | – – – – – – – – – – – – – – – – –
ee127315-de8a-524a-8b01-2ee00a04609b | note | METHOD: Document review
1eb68c12-d17d-5c6d-a1c8-1c9478df7df5 | note | – – – – – – – – – – – – – – – – –
435cff8c-7059-5eda-acb9-ca34d6cc3b7c | note | CATEGORY: HP
05ad8426-5994-57a3-b562-ec1cee113e75 | note | – – – – – – – – – – – – – – – – –
f140d849-66ba-5d0d-8b27-213cabc2f4b1 | note | RESPONSIBILITY: PE/Nominated Authority
f6c6eb91-e49f-5bd3-92c3-a7207b29cc41 | note | – – – – – – – – – – – – – – – – –
97e20d71-5c5f-5272-8cd6-d3303af333b5 | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
1c5d04fd-5ab6-5700-ae01-1c12902147b8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Pile testing-Prequalified consultant
c453e7d4-cb91-5da4-a5f7-03ec6e4e698b | note | REFERENCE: 605.07 (b)
f91e85ab-66b7-59a1-a79a-5c89153ae478 | note | – – – – – – – – – – – – – – – – –
f79cbaee-7b40-507d-855b-7e3dec48fb75 | note | ACCEPTANCE CRITERIA: All high strain dynamic testing shall be undertaken by a prequalified consultant and approved by the Superintendent. The consultant shall be independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing.
4ccf53d6-6fd1-5c4c-a4c8-8003489522b9 | note | ○ The test procedure and test reports shall conform to the requirements of AS 2159.
78c677fb-841a-5629-b4f8-79472604c754 | textbox | Enter: Teambinder Approval number: [free text box]
6fdfab24-c857-5977-9de3-9b68a20fac48 | note | – – – – – – – – – – – – – – – – –
32a632d9-380f-51ac-bec8-84482924be23 | note | METHOD: Document review
f96e6e15-8deb-5627-bee3-d84468bde504 | note | – – – – – – – – – – – – – – – – –
f0f41752-c09a-55b7-b027-a90e8e1372b3 | note | FREQUENCY: Each test
b3dec4c0-1ab6-56c8-a47d-c8a87ea7916a | note | – – – – – – – – – – – – – – – – –
ca41fea6-e272-5e87-948b-14bc47d46a82 | note | CATEGORY: HP
d735164a-ba41-567c-bec3-925be280e382 | note | – – – – – – – – – – – – – – – – –
50fd5404-6b3e-5f83-821f-1efc0f38e4d1 | note | RESPONSIBILITY: PE/Nominated Authority
e80b1635-cae9-5a7f-a5f0-2078b57e1872 | note | – – – – – – – – – – – – – – – – –
f0322555-3efa-5625-863a-1a9e34295f99 | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
3484f509-64db-586d-baa7-988566899c09 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Pile-Approval for using HILEY Formula
5812bb45-569e-50a6-8b5d-15993c22b155 | note | REFERENCE: 605.04, 605.05 (a) BTN 023
8952e1f1-413e-5b36-97c4-169b1cb3279a | note | – – – – – – – – – – – – – – – – –
a6158753-2950-5ef7-b7a2-1d22d996e595 | note | ACCEPTANCE CRITERIA: Pile testing using the Hiley Formula may only be used for bridges of low significance and where high strain dynamic pile testing is not practical. Advice should be sought from Technical Consulting Geotechnical Services if pile testing using the Hiley Formula is to be adopted.
08c6505b-40ea-5f44-b124-74a1f5041a77 | note | ○ The dispensation conditions for Pile Driving Analyser (PDA) for predominantly laterally loaded piles may be applied to embedded retaining walls or other structures, subject to compliance with the criteria listed in Table 1 of BTN 023. Where any of the conditions cannot be fulfilled, relevant structural and geotechnical reports must be provided to the DTP Chief Engineer – Roads for review and approval.
b1d4bb53-f250-5442-8722-2fe7f4d174c8 | textbox | Enter: Teambinder Approval number: [free text box]
c27cf50b-7397-51ac-a49c-f7974354b195 | note | – – – – – – – – – – – – – – – – –
f1f8e3b4-aa02-5b41-9664-ce5779c37cf1 | note | METHOD: Document review
c031e6bd-0a03-5ac9-8be0-c69e909304ce | note | – – – – – – – – – – – – – – – – –
4c5f2b3f-d8b5-5b97-8272-9facc43936ae | note | FREQUENCY: When Applicable
10458fd3-a1a4-535f-92b2-8e75a1203c63 | note | – – – – – – – – – – – – – – – – –
1b0575a8-a0f5-54bc-8c80-050baae506a4 | note | CATEGORY: HP
9cbad073-1f28-56dd-b8d7-3b8333de65f0 | note | – – – – – – – – – – – – – – – – –
5ece008f-58c9-53f8-8d99-3580f3e6deba | note | RESPONSIBILITY: PE/Nominated Authority
3409a7fa-241a-599b-878f-70e86fb0b79b | note | – – – – – – – – – – – – – – – – –
54de208c-1231-53c5-b7d4-679b722153d9 | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
7200c0a2-5ee7-5c55-9375-9909d3154554 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
3c6d90ea-0f7e-5950-b5bb-bacd9dc23c4b | note | REFERENCE: MRPA Quality Management Plan
8d59f9c9-f77c-5baf-a4c2-9fca3c7cf07e | note | – – – – – – – – – – – – – – – – –
833b52a8-5d35-5fb8-a077-f42932aa08c6 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
4c983e5b-ad46-5cf2-be08-986f239cb8e8 | note | – – – – – – – – – – – – – – – – –
7eb613e0-a02e-57be-a0cb-48bf830d497e | note | METHOD: Document Review
be1b2329-2699-5bb9-bf28-daa334552778 | note | – – – – – – – – – – – – – – – – –
a54751e4-3978-5122-97f8-854776ab812f | note | FREQUENCY: Prior to starting Works and at regular intervals
08c08988-ea12-50c9-8e66-6ebcb28e3bd3 | note | – – – – – – – – – – – – – – – – –
d53fcd58-a022-5e9e-9b7b-f6a05273829e | note | CATEGORY: HP*
c1403943-422f-56fc-a935-fd45b39928cd | note | – – – – – – – – – – – – – – – – –
1d47f1a8-881f-57cc-91fa-134063be2518 | note | RESPONSIBILITY: SE/PE
e50a504c-7df4-554a-85aa-51cc64eb6849 | note | – – – – – – – – – – – – – – – – –
12183888-60b9-5f12-95d4-efa41e1e46ab | note | VERIFYING DOCUMENTS: This ITP
1ba4f86a-c0c2-5952-abd9-f11b136abce8 | date | Date Completed:
| checkpoint | 4.2 Pile-Ultimate Capacity- Wave Equation-First pile in the group
18ca8b1d-9efd-5bff-b97b-2f1564065e8d | note | REFERENCE: 605.05 (b)
8df7941d-63fb-5031-981b-9a48a7fe66fc | note | – – – – – – – – – – – – – – – – –
67900ff3-a583-5cb6-b309-4b14f0cbc687 | note | ACCEPTANCE CRITERIA: The initial pile in each pile group shall be monitored with Dynamic Testing Equipment DURING DRIVING.
39b63eed-9ada-5ab2-a142-8f75c62369d1 | note | ○ The records shall be subjected to closed form dynamic solution and wave equation analysis.
b41f149c-2246-587e-868c-cdcd3602ce18 | note | ○ Pile stresses during driving shall not exceed 0.8x fc) compression and 1.1x SQR(fc) tension for concrete piles, where fc is the concrete strength.
a07df8d4-1793-5207-900e-5d3e86ac8217 | note | ○ The measured stresses in the pile induced during pile driving and ultimate pile capacity calculations shall be submitted to the Superintendent for eview prior to driving further piles.
674c6934-eab8-539f-a1ba-5dfac4e33aa7 | textbox | Initial pile in the group:
ef2d63c3-3c3b-5058-b5b5-e74303fc9b5c | note | – – – – – – – – – – – – – – – – –
5090cced-fac1-59a8-bcb9-86594509c844 | note | METHOD: Document Review
e1844051-844c-5dc6-83aa-95304517e832 | note | – – – – – – – – – – – – – – – – –
3a385656-fe0f-57cb-873b-2eee0246e028 | note | FREQUENCY: One for Each Pile Group (First pile in each group)
6769badc-9713-5e40-80a7-03bcdbade0cc | note | – – – – – – – – – – – – – – – – –
315f747f-e5c8-5bd5-a378-76987c740432 | note | CATEGORY: HP
31d4042e-0493-5ef7-8491-598dc5e99b43 | note | – – – – – – – – – – – – – – – – –
eb4ce9e5-371a-5f2f-b3e4-366ab007386c | note | RESPONSIBILITY: PE/Nominated Authority
009ab34a-ddf8-5b7f-9bf3-6a05f2914ef4 | note | – – – – – – – – – – – – – – – – –
aab002a7-8c3c-5a75-942d-415fb536474b | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
a87ccc67-e7d0-5949-87c1-1c03c4201851 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 Survey Set out
340650ee-aeb0-5b61-9c9b-c530bcedfbc5 | note | REFERENCE: VR 605.04 (c)
63ec29e5-c672-5bf8-adb4-d29565fe2edb | note | – – – – – – – – – – – – – – – – –
e0c37af4-3eea-5bf8-b261-da96355aaa50 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements within the tolerances:
660319cf-259d-56e7-8003-6843e9b26c70 | note | ○ pile head centre, ± 50 mm of the specified position.
e0a673fe-6e62-50eb-b30e-2fb24b7cdafb | note | – – – – – – – – – – – – – – – – –
e03567fb-7f22-57b2-80fe-be917bc74bcd | note | METHOD: Survey
90a02cd0-fcd5-5817-87a9-d74afa41741f | note | – – – – – – – – – – – – – – – – –
d4346beb-68d0-59dd-86ca-f55200714816 | note | FREQUENCY: Each pile prior driving
095dd307-2932-5724-9dfc-4e4ebbf8d956 | note | – – – – – – – – – – – – – – – – –
ef665d67-7e1d-56f6-835a-8d548090ae13 | note | CATEGORY: IP
8015ed48-bd30-5360-8b2b-12728f779082 | note | – – – – – – – – – – – – – – – – –
8d961cb4-82c7-5b2e-bcc5-3d3b4d060269 | note | RESPONSIBILITY: SE/Surveyor
f0be51d0-e6da-5613-94f5-e288b2add67d | note | – – – – – – – – – – – – – – – – –
ff98e03b-1cf6-53f4-a07c-252c8e627709 | note | VERIFYING DOCUMENTS: This ITP
f5905de7-52f7-5407-91ee-1406de820462 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Driving-Pile protection
ec2a0a03-f058-5b81-bf46-196e730f0dcb | note | REFERENCE: 605.04
cbfa00f6-021f-5aba-8b3c-6356a182644a | note | – – – – – – – – – – – – – – – – –
818f8b22-f341-5b8c-b690-69786d3b9266 | note | ACCEPTANCE CRITERIA: During driving, the tops of the piles shall be held and guided by a suitable helmet and protected by a cushioning material, to avoid damage to the pile.
506a1440-d964-5508-86cc-41aa2d88c000 | note | ○ Piles shall be guided into the specified position and shall not be bent or sprung into place during or after driving.
34dd9cf6-b0bc-5567-ba76-2f2146852464 | note | – – – – – – – – – – – – – – – – –
a5a706ec-4d8e-5577-95ab-8e4773b29808 | note | METHOD: Visual
79b21d80-4f41-5a27-a8ea-a18a02f47961 | note | – – – – – – – – – – – – – – – – –
d4916286-22ed-5ae5-82c5-28e8dd92ed35 | note | FREQUENCY: Each element
61f891de-7030-57e3-8688-6fda7cadb025 | note | – – – – – – – – – – – – – – – – –
6185e5bd-7e33-5617-8bca-662594f56e86 | note | CATEGORY: IP
9784b812-4e3c-5043-8bc2-a3ee6e86df16 | note | – – – – – – – – – – – – – – – – –
ee81bd6e-6e5f-5255-808e-d9c4d0f73ac5 | note | RESPONSIBILITY: SE
6585705c-9080-5a1d-9f91-b8612039ed0a | note | – – – – – – – – – – – – – – – – –
b6d9aea9-d5f7-5eb0-ac51-00b844c3983b | note | VERIFYING DOCUMENTS: This ITP
96b1dcd5-0e01-5561-a554-217466028609 | date | Date Completed:
| checkpoint | 5.2 Pile alignment and Straightness
f62f6a3a-064d-5953-997b-27596797f0cd | note | REFERENCE: 605.04
a5944d4e-df04-5f4c-90c4-4345a653fe2b | note | – – – – – – – – – – – – – – – – –
d393395c-9daf-5540-9997-a1f6824bbaba | note | ACCEPTANCE CRITERIA: The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving:
0eef5acd-be1f-5396-b3f0-24ff2970a14a | note | ○ pile alignment: deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile
0890b579-0c87-5c11-b287-18bca821ea21 | note | ○ pile straightness: deviation from vertical shall not exceed 5 mm per metre length of pile
8e9b0e33-0c5f-5365-85a1-608cfbc73208 | note | – – – – – – – – – – – – – – – – –
f89fcf3e-1a78-5b6d-a2e7-fc7a4d0e56d3 | note | METHOD: Visual, Measure
1e5a660b-fbae-5d31-a206-7ce0bb34dbe7 | note | – – – – – – – – – – – – – – – – –
2bf87edf-b023-5dc3-b78d-9fa8ee556ba6 | note | FREQUENCY: Each element
da8c138c-c0e6-560e-9ada-ae54c9c4491e | note | – – – – – – – – – – – – – – – – –
273c8f84-cad2-5dd4-b10e-3eced69bbd62 | note | CATEGORY: IP
419e268c-c2ed-5440-b600-587c31a8ae06 | note | – – – – – – – – – – – – – – – – –
fa924227-755a-52c1-84fa-7d45acb07850 | note | RESPONSIBILITY: SE
53c0e7cf-8ed5-5a45-b5fb-d827099d8f88 | note | – – – – – – – – – – – – – – – – –
997534cf-52d5-58e9-94d0-d610ddd22535 | note | VERIFYING DOCUMENTS: This ITP
65c44005-cd59-5aac-a84e-15c501d16597 | date | Date Completed:
| checkpoint | 5.3 Pile driving-Monitoring
99a78319-a4df-59fb-976a-404f205aa740 | note | REFERENCE: 605.04
5733b7b1-01be-5a93-9ffc-089dd2fc9951 | note | – – – – – – – – – – – – – – – – –
94ca554d-1289-5f86-a7ec-62e474c11f03 | note | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile.
6b9b0266-9932-52f5-99ad-36d3f1e67050 | note | – – – – – – – – – – – – – – – – –
2d456c58-daaa-52de-b604-1adbb0bcb0d2 | note | METHOD: Visual
edc958d0-ccd3-5e47-8654-68846bdc637e | note | – – – – – – – – – – – – – – – – –
0c326300-1dea-5a40-85e5-a9645a1601c4 | note | FREQUENCY: Each element
e1d25a8a-0af1-5c02-b96d-72d52f97f1c4 | note | – – – – – – – – – – – – – – – – –
2f0fd7a8-2469-5ee9-ab59-54b021a2e1ff | note | CATEGORY: IP
0b0cc8e4-c42d-598d-aaa8-cd42ac39eb3b | note | – – – – – – – – – – – – – – – – –
40a99e89-9705-50e1-9d72-f28c239b2acf | note | RESPONSIBILITY: SE
ee8d41aa-15ce-5f55-9883-2a212315ff9a | note | – – – – – – – – – – – – – – – – –
b612c1fc-380b-5832-b502-02a5517b72e8 | note | VERIFYING DOCUMENTS: This ITP
1515e8c4-20b9-5c26-a81c-1b1769301e58 | date | Date Completed:
| checkpoint | 5.4 Pile Driving operation
701557cd-64cd-54a4-aa94-0a3c8ddc1104 | note | REFERENCE: 605.04
03930afb-cb43-56e3-a5dc-cddcdb174d90 | note | – – – – – – – – – – – – – – – – –
51e6c808-79ba-51ed-886c-a7e32b187034 | note | ACCEPTANCE CRITERIA: Each pile shall be driven in a continuous operation and not left partly driven.
0aaac1a3-7bd1-54e8-848d-aa68cf441f60 | note | – – – – – – – – – – – – – – – – –
78f13e20-6b9b-59d1-807e-8a1aa1e07676 | note | METHOD: Visual
48bf8014-dcd6-53c9-8f86-30004bed6f77 | note | – – – – – – – – – – – – – – – – –
5d0d3c0f-25d2-5bf7-8b18-782978d523ff | note | FREQUENCY: Each element
f8786ee1-5fa2-51c0-a843-ff6bef38d5c8 | note | – – – – – – – – – – – – – – – – –
74dae29e-cfe7-5696-932c-94913bb2b401 | note | CATEGORY: IP
5702b6a6-fa18-5fea-b289-1b5e4a73cb40 | note | – – – – – – – – – – – – – – – – –
aa156107-3722-5e0b-80f1-c1c11d42c0ae | note | RESPONSIBILITY: SE
8dc1f5c7-1a8b-56d7-a5d3-91a16a8c83f2 | note | – – – – – – – – – – – – – – – – –
4b99bbe9-e668-5a74-a490-8de090132ea8 | note | VERIFYING DOCUMENTS: This ITP
56df590f-ed30-5984-8823-2b7b26af2791 | date | Date Completed:
| checkpoint | 5.5 Pile Extension
6bcdf356-a2cd-5346-ad30-4d1f762d0533 | note | REFERENCE: 605.10 (c) BTN 023 - 3.2.7 605.04
62870004-971c-5940-8d7e-37403dd55344 | note | – – – – – – – – – – – – – – – – –
764f93b4-6715-5525-a20b-761db3e124d2 | note | ACCEPTANCE CRITERIA: precast extensions may be used provided that
e5bcb404-d17b-52e1-ab7c-317298857fa5 | note | ○ the mechanical joints must comply with the requirements of AS 5100.3 clause 6.4 and BTN 023
48f3c347-4fdd-53c4-b8d6-c28a52fad5f5 | note | ○ design of mechanical joints must comply with the durability requirements of AS 5100.3 Section 4
e3e0239a-9476-58bd-bfa1-f886166a58f0 | note | ○ the precast extension must have a minimum length of 5 metres
8259d19b-1465-5ddc-93c6-79088ad4d49d | note | ○ the joint location is determined by the structural design engineer.
56a13d6e-2245-5202-950c-6a81d03c0ddf | note | ○ Mechanical joints must not be located within 5 m of the underside of a pile-cap or in aggressive groundwater
b7cf47e2-8903-54d9-bdbc-b7bb39316bff | note | Driving shall re‑commence as soon as the splice is completed.
8d2ce9a7-6668-54e9-b5fd-db898a80906d | note | – – – – – – – – – – – – – – – – –
29bedf3c-bc37-5205-bed7-1152f4e1442c | note | METHOD: Visual, Measure
682f203e-870a-58d4-a349-177e325be88f | note | – – – – – – – – – – – – – – – – –
bc3e6f80-aca6-5aa3-b8bc-e48805c1109a | note | FREQUENCY: When Applicable
718e45ee-c114-55ea-995b-1b48504af066 | note | – – – – – – – – – – – – – – – – –
c42a1981-bf4e-568f-8cab-c1a74a903529 | note | CATEGORY: IP
18a1f2a1-1308-5ade-8b3e-b638ec57412c | note | – – – – – – – – – – – – – – – – –
da7b1239-aaa0-59e9-b4c2-ee0b1fda0711 | note | RESPONSIBILITY: SE
b0d129af-04d2-5417-9056-363c42232775 | note | – – – – – – – – – – – – – – – – –
029b866e-bb11-5cd0-817e-82181c491b31 | note | VERIFYING DOCUMENTS: This ITP
8c713a69-564a-560e-90ec-77732b77daee | date | Date Completed:
| checkpoint | 5.6 Pile-Ultimate Capacity- HILEY Formula
cc5296fd-1b82-58f4-9f71-4f920ff8fede | note | REFERENCE: 605.05 (a)
9fed1744-5ad3-5dd4-9b24-a7a545bf5daa | note | – – – – – – – – – – – – – – – – –
56800022-0a36-553a-a8a3-99023145eccc | note | ACCEPTANCE CRITERIA: Piles shall achieve the specified ultimate load capacity.
77e4887c-cfb7-5816-afd4-6c68772dadbe | note | If using Hiley Formula is permitted:
469d011e-01ad-53f8-8f73-f5a04d1f7ad4 | note | ○ The values of the coefficients EF, E and C1, which are dependent upon the type of equipment used and the rake of the piles, shall be nominated by the Contractor and reviewed by the Superintendent.
d5064d3a-42de-5922-ade7-34ae2705bb76 | note | If using Hiley Formula is permitted:
33521173-f005-5b6f-9636-01cd06db2d3a | note | ○ Coefficients C2 and C3 shall be measured by the Contractor for each pile during driving simultaneously with the measurement of set per blow.
bda8052c-3905-5cd9-a057-1df728174f78 | note | Contractor ITP to be attached:
ca302d23-4bf3-5b77-a816-cf9901bef2db | note | – – – – – – – – – – – – – – – – –
1c359097-585d-5665-88f2-4252fcd0a5d1 | note | METHOD: Document review
51467be7-d0a6-5085-84ac-d5251b07fdc2 | note | – – – – – – – – – – – – – – – – –
2fec8a7c-e3b3-548b-9bcd-d94c39390b1c | note | FREQUENCY: Each pile when permitted
51fdf74e-35a6-5874-af85-c6a765537d82 | note | – – – – – – – – – – – – – – – – –
798fbbeb-7a73-5741-b4e5-06e10642cfb5 | note | CATEGORY: IP
8476bcb2-aad7-5e6d-b592-05786e9d4caf | note | – – – – – – – – – – – – – – – – –
e612b249-b66b-5b83-a83b-ed699f2a1d9e | note | RESPONSIBILITY: Nominated Authority
dd22cb5e-7600-50b3-bdda-59c142d79c8b | note | – – – – – – – – – – – – – – – – –
1801183f-2f9e-5aa8-8abb-6484322eb4c0 | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
60f64f72-728d-510f-99d1-29bbd45226e2 | date | Date Completed:
| checkpoint | 5.7 Pile-Ultimate Capacity- Wave Equation-Other than the first pile
8700e292-c1c6-57c2-b8a3-08c9b3070ee1 | note | REFERENCE: 605.05 (b) I, 605.07 (b) ii
e19013d9-00d1-5f88-84fe-b8d4044c63b4 | note | – – – – – – – – – – – – – – – – –
4c1ba188-af6b-57ef-83a2-94b20eaf3796 | note | ACCEPTANCE CRITERIA: The driving criteria for each pile group shall be determined by testing the first pile driven in each group in accordance with clause 605.07(b)(i).
b7d94dfc-266d-57f1-b614-0eac6d31f714 | note | ○ All piles within that group shall be driven to a set not exceeding the driving set as determined by the PDA test on the basis of wave equation analysis.
2b11bad4-63fd-502e-8139-582b36f96e59 | note | ○ Refer to Pile driving record
015e0409-e657-5305-a835-4bb26811ff8d | note | – – – – – – – – – – – – – – – – –
efc5819d-6ac5-5d2e-b7b4-6ba11586e74f | note | METHOD: Document review
fcaeebd0-6a31-5489-98a2-a0e2c8fe0105 | note | – – – – – – – – – – – – – – – – –
8dab6648-f631-5021-bd70-58d61446d277 | note | FREQUENCY: Each Pile
f0687879-97c4-56fd-9833-a1a3fc5a7a1f | note | – – – – – – – – – – – – – – – – –
67b494d4-4dae-58d2-9fc5-a3f5738f31bb | note | CATEGORY: IP
c37dade3-c883-58ba-8d67-9dec5a40f37a | note | – – – – – – – – – – – – – – – – –
424ed586-3448-52ce-a164-e01cbd6dad82 | note | RESPONSIBILITY: Nominated Authority
fe9d46af-3658-55f2-8367-aa728e8d7c53 | note | – – – – – – – – – – – – – – – – –
45286c4e-981b-58fd-82f4-6587ff6b05e9 | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
bdb6ea60-1c01-5797-893d-e7f78c9e28cc | date | Date Completed:
| checkpoint | 5.8 Pile driving records
4721155c-738d-5b18-95ae-05047a699b25 | note | REFERENCE: 605.06 AS 2159 Clause 7.7
84b5b30d-d3da-5f25-83c0-8b48682e23d9 | note | – – – – – – – – – – – – – – – – –
155c1206-536e-5dd7-851f-2ee41d23cc5d | note | ACCEPTANCE CRITERIA: Pile driving records shall be in accordance with Section 7.7 – AS 2159. The following records must be retained for each pile driven:
e49e9de1-fb24-5126-985d-7532af7118b8 | note | ○ Sequence of driving in th pile group
2ddb30f8-5e63-57d9-93d6-22c0f780484d | note | ○ length of each segment prior to driving
b7218dc9-ad13-5299-8be2-0df66a473c6e | note | ○ date of driving
cd22c86b-a3e6-565b-99f6-2587024a3d3a | note | ○ Final toe level
8a7587b2-cd8c-5869-856c-c3af5a8e0f24 | note | ○ set measurements for the last 10 blows and temporary compression for one of the blows
f989dc77-2368-51a3-abd3-b2ee82a242cf | note | ○ calculated ultimate pile capacity
c68e7e67-3173-5300-86ff-70ccd48adec4 | note | ○ measured stresses in the pile.
11d4a591-4d4f-549a-a045-c34ba9c75100 | note | Attach: pile driving record
d7496b7c-9a36-5f8a-8c20-eba19cfae6aa | note | – – – – – – – – – – – – – – – – –
f23f8234-e867-58fd-ac61-393feb6a1a4f | note | METHOD: Document review
61460c92-72e7-5894-bb81-b3dc45cc1bb5 | note | – – – – – – – – – – – – – – – – –
14c439b8-6cae-5def-acf1-9e2ebac92d0e | note | FREQUENCY: Each Pile
251b0fc1-624c-5004-9161-42edd0f710f1 | note | – – – – – – – – – – – – – – – – –
c14e2805-ab34-5a07-93e3-3456f5be790d | note | CATEGORY: IP
eecb09bb-811e-5171-94ad-0e24cd073440 | note | – – – – – – – – – – – – – – – – –
da0d1b62-4a65-5ff1-8e10-bd92b0fbb440 | note | RESPONSIBILITY: Nominated Authority
cc45e053-7672-5385-9c65-b9116cbeaaee | note | – – – – – – – – – – – – – – – – –
7b323c10-e6f9-56b7-b12f-fc3c2c34b97b | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
1d7dc09f-07d4-5556-842e-bbfa9e29f8ea | date | Date Completed:
| checkpoint | 5.9 Re-Strike test
906ca8be-c1e9-5e6d-893c-e9d10a5d67c3 | note | REFERENCE: 605.04, 605.08
a204395a-a11d-5bd2-a5ca-0b8b0b711926 | note | – – – – – – – – – – – – – – – – –
f125c49d-ee81-5262-9a63-c613671e9723 | note | ACCEPTANCE CRITERIA: If the ultimate load capacity is not achieved at the specified level, the pile shall have a restrike test undertaken in accordance with clause 605.08 – Restrike Test. If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved.
0bf9af59-dddd-5962-ab17-37f56e8882b9 | note | ○ Restrike testing shall be conducted not less than 24 hours after initial driving.
fb9de572-8b86-5019-8404-f83a3fcba741 | note | Attach: Re-Strike record
9b4b474f-209e-5321-9469-1d188417504f | note | – – – – – – – – – – – – – – – – –
aaf970ca-05d6-53d7-a4dd-87e954e8a0fa | note | METHOD: Document review
59ae437e-10ac-5a0d-99a5-7f6a2b3ada3f | note | – – – – – – – – – – – – – – – – –
b54cb0ad-fa44-502d-9a49-c7e62ebf6656 | note | FREQUENCY: When Applicable
c48663e3-fa56-518a-bae7-18178ff0195e | note | – – – – – – – – – – – – – – – – –
ce97b5b9-cb71-5899-8f3d-7dd896034bad | note | CATEGORY: IP
5aafecdc-9455-5c2d-9cba-bf40840d38e8 | note | – – – – – – – – – – – – – – – – –
6117468d-b086-54a7-b036-a340946c9d39 | note | RESPONSIBILITY: Nominated Authority
e66a4fe1-3061-5d08-9170-4e489dcf24e4 | note | – – – – – – – – – – – – – – – – –
75d407c3-6b57-5347-abee-b3c6e71c8460 | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
d773dfad-7894-5044-866c-2d52abd1fef4 | date | Date Completed:
| section | Construction Activities
| checkpoint | 6.1 Pile testing-High Strain DynamicTesting
92472aed-194c-57db-b021-20d9b03eb3f9 | note | REFERENCE: 605.07 (b) I AS 2159 Appendix B
37e22a99-46de-53e5-91ae-12e0375bb750 | note | – – – – – – – – – – – – – – – – –
5e789bd8-3750-5599-890f-df9cd025b5ec | note | ACCEPTANCE CRITERIA: High-strain dynamic pile testing shall be performed to confirm that the design pile capacity and integrity has been achieved.
a61c2db9-b9ea-50c6-b2d2-42e4b1398c70 | note | ○ The pile driving system shall have adequate energy to mobilise a test pile by a single hammer blow.
2590526a-d21c-5261-9d74-6d19770a6e96 | note | ○ Testing shall be carried out by use of a PDA or approved equivalent and data obtained from each test shall be analysed using CAPWAP or TNOWAVE or approved equivalent.
a7d155a3-776a-520b-bdeb-cab8ab4ef227 | note | ○ The driving resistance and corresponding set per blow of the test pile shall be measured during PDA testing to extrapolate the results of the test pile to the piles in the pile group.
72a1782e-a036-5b56-857e-237e88563c57 | note | ○ The test results are required to demonstrate meeting the acceptance criteria shown on the drawings.
892c9e70-be3c-5767-8bc9-810a865e82d6 | note | ○ The measured ultimate capacity of the test pile shall be equal to or greater than the pile test load shown on the drawings.
a8b13f6e-cbe1-5d6c-b865-204f756ae793 | note | ○ Pile testing shall be carried out in the presence of the Superintendent.
6fded778-b13f-585d-8273-cf5b9e735509 | note | Attach: High Strain dynamic pile test results
443b60b5-6e7a-5fb1-b760-d1ca850554f7 | note | – – – – – – – – – – – – – – – – –
ff79a819-2983-57e6-8c13-427961acb766 | note | METHOD: Test, Document Review
33db5d92-0aa3-5c68-8b56-9fe1f960df85 | note | – – – – – – – – – – – – – – – – –
6b71ef6c-9e86-53b1-b390-37a9a97775ab | note | FREQUENCY: When applicable two test per group (First pile and other nominated pile)
a4966aa1-0ea8-5065-9b8f-e9b375b076b7 | note | – – – – – – – – – – – – – – – – –
e3ace820-0893-5046-a6fb-e686d532f65c | note | CATEGORY: HP
72af29d8-04d5-5f36-8509-94e784004804 | note | – – – – – – – – – – – – – – – – –
ec961011-ea9f-50e5-acea-b47851e08173 | note | RESPONSIBILITY: Nominated Authority
37325c10-2784-55a7-9bf9-88b1350ed1d3 | note | – – – – – – – – – – – – – – – – –
fde88c36-9473-5f88-a281-e45558d9f6b1 | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
27d5d7c6-e6a8-5ae1-a3cb-2404ba17a022 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 Pile -Driving
d9ec253f-c910-57fd-bbae-ab1f89d6bf25 | note | REFERENCE: 605.04
53201375-22a7-5eb8-9bc6-5081785c1a18 | note | – – – – – – – – – – – – – – – – –
f48ffabb-e82d-5d7d-b8ee-fe6760553f3f | note | ACCEPTANCE CRITERIA: Piles forced up by the driving of adjacent piles shall be re driven to the specified toe level.
eb1a56fe-7647-5f4a-a220-ca1962945b75 | note | – – – – – – – – – – – – – – – – –
46551260-c528-56d1-95b8-8b40d5fa8fe2 | note | METHOD: Measure
281b057c-bf06-5d21-903b-aa08af5b574d | note | – – – – – – – – – – – – – – – – –
4b49d649-59ad-515c-a108-e86d029aa652 | note | FREQUENCY: When Applicable
97857bdf-ab5d-586a-8766-420c27f92691 | note | – – – – – – – – – – – – – – – – –
836ff675-2307-5e2c-bb08-513ce19796f7 | note | CATEGORY: IP
92cb50ca-94f1-5bca-8972-dcdbc10ad6f9 | note | – – – – – – – – – – – – – – – – –
582982c2-ee88-5675-977a-0fe79b4196c2 | note | RESPONSIBILITY: SE/PE
f035f7d3-9404-560e-8913-ff865472eda9 | note | – – – – – – – – – – – – – – – – –
1282ee90-8500-569e-96ae-4228bf7e7a38 | note | VERIFYING DOCUMENTS: This ITP
ae3d093f-3f4a-59f5-81f7-22437c73fd1a | date | Date Completed:
| checkpoint | 6.3 As-built Survey
6235fbc0-8ddb-5d8d-996f-d5f9a4e61731 | note | REFERENCE: VR 605.04 (c)
e4d3bae2-b459-53d0-9bbf-1dfcf7f6d84a | note | – – – – – – – – – – – – – – – – –
01bc05ef-eccb-5460-9c80-73639487aeb7 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
4e772518-eed9-5e37-8e69-8e59e0886d62 | note | i. Centre of pile head plan location = ±50mm
8b1661b5-50bc-5285-8362-a58189a955e8 | note | Attach: Survey As-builts / Survey Report
0dab335c-ea59-5069-bda0-116ffbe8129a | note | – – – – – – – – – – – – – – – – –
59030b0c-719b-5b29-98bf-5e81a7611a5a | note | METHOD: Document Review
9df3fa37-d006-56e0-ab5a-f0125ee75cc9 | note | – – – – – – – – – – – – – – – – –
735d030d-3188-52c1-92ce-5e4cd8ec1104 | note | FREQUENCY: Each pile
ceab0815-ad48-58dd-8944-5e1aa494ede5 | note | – – – – – – – – – – – – – – – – –
288dd536-6c63-5f38-8dd3-d6ecbf2816f9 | note | CATEGORY: IP
2b74ecf5-ef3e-5395-9034-d09dbb95d61f | note | – – – – – – – – – – – – – – – – –
9fe2de1e-91cb-5dc4-bb4f-3663aa6eb071 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
90f6931f-bcf1-5076-acf4-b3b4da048f5e | note | – – – – – – – – – – – – – – – – –
e2e6a248-79c8-50ce-b2a6-9d4478d63db5 | note | VERIFYING DOCUMENTS: This ITP
da347da8-8656-5576-b96e-1bdf37c852a9 | date | Date Completed:
| checkpoint | Final Inspection
dd55c564-6f3c-5187-9c6a-790c7cbdeefa | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
da1bb674-22f7-5684-b8f9-d47bb73d93b7 | textbox | Name:
26e32928-52aa-526a-8b82-d7ef117e8a77 | textbox | Position:
d47bee62-79bd-59e9-8629-7778119c8619 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-106-RAIL-SSB-OHLE Wire Regrading Rev 0 | itp | ITP-106-RAIL-SSB-OHLE Wire Regrading | 6e7846ae-e24d-4d39-8a81-a9f6134d8075
| section | Referenced Documentation
| checkpoint | Referenced Documentation
8de54cd4-256e-5be9-bf65-908760af92d6 | note | Document Title: ITP-106-Rail-SSB-OHLE Wire Regrading
0173dcda-9f4a-5484-8372-7e9f756d9b86 | note | ITP Description: OHLE
f82d15e1-4cda-5e70-82c2-f1e783aca1ba | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
125f75bc-088f-5c1d-9f6f-8a625716b9f7 | note | Discipline (e.g. CIV/STR/RAIL): OHLE
fe67e6af-66b9-5db5-a15a-d1552f189d51 | note | Revision Number: 0
ee515a32-9e01-58cc-97fe-7ad23c1f6104 | note | Revision Date: 26/06/2023
bbac6e7a-dc5a-5a47-bd6c-6a86c8d47562 | note | ITP created by: Nikhil Siram
2c265608-5309-55b2-814c-fda78193ef46 | note | 1.1 Overhead Line Electrification
2f8cc59a-1656-5e4b-942f-e4bb9e4ffb98 | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
3a2c2a1a-30cc-5bae-a740-70c789a05698 | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
518b4d20-978e-5575-934e-397640590d9d | note | Reference: VRIOGS 001 AS 4100
24b42bfa-9112-5254-90ad-14fb011468eb | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
ad145d9c-69da-5b28-b1fd-4d09880793e1 | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1)
| section | Preliminaries - Materials
| checkpoint | 2.1 Procurement Materials delivered/collected to stores/Site.
32c7e9d7-eef2-513f-ab30-697b0cc8bcf6 | note | REFERENCE: Contractor - Site Material Control procedure. Cat5 Material received -Camms and Camms Tracking sheet
7979c0ff-c668-5901-9c62-e3498f3b848e | note | – – – – – – – – – – – – – – – – –
114a9586-69b7-55c2-8109-0c2f2a4968cd | note | ACCEPTANCE CRITERIA: Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA
6c251d2d-82b3-5928-93ad-3ca43be7195a | note | – – – – – – – – – – – – – – – – –
89022edd-a91f-589f-88a5-be988d0b65fb | note | METHOD: Document Review
65090fa0-0130-5fa8-af10-9d005a9c6240 | note | – – – – – – – – – – – – – – – – –
d0e35f51-8a59-5174-bc34-524611f272db | note | FREQUENCY: Once for each supplier, prior to works start
9fc43839-2aa3-55db-ac8b-e64a7f08a622 | note | – – – – – – – – – – – – – – – – –
b4d3bd8c-1383-5c56-9562-055e82d86276 | note | CATEGORY: IP
0e707311-bbb1-5314-8860-bb63353848a7 | note | – – – – – – – – – – – – – – – – –
ee967925-bd7b-50cd-9a39-1f94313e3768 | note | RESPONSIBILITY: MRPA Issue CAT5 Receive
d494ff61-1c43-55cf-98e2-1990d89f5ddb | note | – – – – – – – – – – – – – – – – –
8fac4128-e649-5102-827b-713dbed5fc60 | note | RESPONSIBLE PERSON: MRPA
6040122e-70d8-534d-a1db-86af4d361e74 | note | – – – – – – – – – – – – – – – – –
1df21b99-980c-59cf-90ef-8d4304749753 | note | VERIFYING DOCUMENTS: This ITP Signed Off
f176856d-420b-5744-b63b-da6a8ba0eacd | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Produce Work Package Plan
1fcdb60b-77d4-5b37-a4bf-5dd3302840ff | note | REFERENCE: Work Package Plan WAP_BR_184
5637db4b-72c4-5f20-a58a-389f79f45d19 | note | – – – – – – – – – – – – – – – – –
26a914c2-72e0-5dbd-9916-1b39e166bd5d | note | ACCEPTANCE CRITERIA: Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
45ba5fac-ad2a-52d4-83d5-624af939f715 | note | – – – – – – – – – – – – – – – – –
107b1085-28aa-50f4-99c9-e4a611910be8 | note | METHOD: Document Review
85f7bdae-147b-5f12-92c1-e71ad6910ba1 | note | – – – – – – – – – – – – – – – – –
73e1ca89-4f69-5852-9f13-1a124b3ff193 | note | FREQUENCY: Prior to Works Start, TBC in accordance with MTM Standards
95330590-c241-583a-8178-ae647d55cfb9 | note | – – – – – – – – – – – – – – – – –
d996192c-f66b-5c80-ae22-93a1281c6df4 | note | CATEGORY: HP
c695fb30-5351-56dc-8251-caaa4f801de1 | note | – – – – – – – – – – – – – – – – –
83a8dd56-9094-504d-99e8-cbc868956ad2 | note | RESPONSIBILITY: MRPA/CAT5
e83d086c-5886-548f-8bd6-f8294d5cf238 | note | – – – – – – – – – – – – – – – – –
cc1495af-3b6f-554f-a3e3-a7bc60a3c107 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
068eab42-87c1-5c6f-b5a1-8ecbd8de1a99 | note | – – – – – – – – – – – – – – – – –
288330c6-7a1e-5150-8c7b-a7698679abe0 | note | VERIFYING DOCUMENTS: This ITP Signed Off
dd5f1f44-faa8-578d-b068-1667b4b929f3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 Approval of IFC drawings
553c38a1-98a5-5f97-873a-db178efd365f | note | REFERENCE: Contractor Design Management procedure. MRP-DPK-089-00-ETN
d21d21fb-e0de-58de-b6dd-d223c74f3bcd | note | – – – – – – – – – – – – – – – – –
6c9f6581-c6e9-5b8c-8ef9-1d5f2bbd369d | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
0e68750c-ad34-55e3-993b-551f37b3bbeb | note | – – – – – – – – – – – – – – – – –
068ac861-7289-5264-8971-0f0f7c460bf0 | note | METHOD: Document/Drawings Review
843a8784-e260-52ca-9554-950e75f7535b | note | – – – – – – – – – – – – – – – – –
c1df354e-03ee-5050-9f23-3df0e0270dad | note | FREQUENCY: Prior to Works and at regular intervals. TBC in accordance with MTM Standards
d8ce4062-1f55-5f56-b00c-e3bbb183daba | note | – – – – – – – – – – – – – – – – –
177049d9-310c-5eb8-a618-3ccd4013ff5d | note | CATEGORY: HP
e8b5a6ad-ab2f-5723-b5cb-ead8d1fe3a30 | note | – – – – – – – – – – – – – – – – –
61c0d0f3-220a-563a-8315-1b3c3eeddec5 | note | RESPONSIBILITY: MRPA/CAT5
a78200c7-7882-5ab0-bb78-03d1fb6b4f83 | note | – – – – – – – – – – – – – – – – –
0c9b721f-46b4-5ae6-9bf0-a8b6d9b5581d | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
3abaf707-4826-5aef-95bd-8e306eeffc9f | note | – – – – – – – – – – – – – – – – –
9464ce7e-b759-538c-9fe6-045788e04f9a | note | VERIFYING DOCUMENTS: This ITP Signed Off
0cf1c1e1-eb5b-5491-9d8f-28b38e74313c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 Task Specific Permits
ae27d8d4-3507-59dd-9fed-1061d3744b8f | note | REFERENCE: Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
c221506d-b619-5996-8cfa-df750721c906 | note | – – – – – – – – – – – – – – – – –
e502e688-1544-53eb-a9fd-9491d0a1f21a | note | ACCEPTANCE CRITERIA: Ensure all task and activities have relevant permits issued and received.
b20c7aa0-914b-540c-a2cf-bab0636f0576 | note | ○ Task Permits to be generated and signed off by appointed person.
899c0f35-5368-5910-bf2c-389fa8078357 | note | ○ Task specific documents - MTM to issue permit to enter/Isolation permits etc.
44f25b51-3b24-5cca-9f61-1c39b0fd4cf5 | note | – – – – – – – – – – – – – – – – –
4c43779b-3fe1-5071-bc2a-a5e6a7e0fa54 | note | METHOD: Visual, Document Review
6dfc9e8f-9a93-5cfd-b298-8fe226577404 | note | – – – – – – – – – – – – – – – – –
43452a32-5ccf-5919-9a29-e92b73946346 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
6ee19b3a-548d-50d8-907e-e0744fdc2571 | note | – – – – – – – – – – – – – – – – –
3412af54-87da-5793-8773-51e60194b48b | note | CATEGORY: IP
05b2dc91-32c5-5212-9f9d-9b5be3f29896 | note | – – – – – – – – – – – – – – – – –
1d32d0b8-ecc8-5e16-8fe0-0293ab9ee556 | note | RESPONSIBILITY: CAT5/MRPA
c0358cfa-911c-5cb8-be81-863a3c2d87a1 | note | – – – – – – – – – – – – – – – – –
88c2e217-b225-54b3-8486-924c0dcc4971 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
0581c454-2fb8-5773-bcd2-ceec6066b462 | note | – – – – – – – – – – – – – – – – –
9725c8bc-3ccc-5755-95c8-b1cb00e4b515 | note | VERIFYING DOCUMENTS: This ITP Signed Off
13f7910a-8d55-57e6-847e-6fe9a6d4e5af | date | Date Completed:
| checkpoint | 4.3 Cantilever assembled.
e4ed99bb-fdc2-51fe-bf4e-9f7975ad00c7 | note | REFERENCE: Cantilever assembled as per IFC design.
3323c665-e782-58a3-9d26-677b7431f049 | note | – – – – – – – – – – – – – – – – –
ddaaced1-766f-5864-9e00-42051247bd56 | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
2303c2c9-16f6-5717-a706-251f4f4f9eb1 | note | – – – – – – – – – – – – – – – – –
533f681f-a287-56da-a411-964b90b365a3 | note | METHOD: Visual, Document Review
767013c8-0348-51e6-aa31-94586a892c43 | note | – – – – – – – – – – – – – – – – –
dce2d28e-fefa-54d2-beff-77afaecb3e18 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
2c6a60d7-6601-525e-b551-454ea839d747 | note | – – – – – – – – – – – – – – – – –
2f320419-687f-5b5e-8e19-1328e0c76663 | note | CATEGORY: IP
b2ec7724-e884-52ec-8d84-e5bd5202b2e8 | note | – – – – – – – – – – – – – – – – –
e53cf6f1-9e40-5885-87c5-7cd9bfd89ab3 | note | RESPONSIBILITY: CAT5/MRPA
67f52306-b995-5bf3-b4c7-e20c076d03cb | note | – – – – – – – – – – – – – – – – –
6dd885a9-98f3-5837-b487-d47fd3e07119 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
32cbf425-d65e-5634-bf4a-48921d1c7ab0 | note | – – – – – – – – – – – – – – – – –
7b014b0c-7b0c-5c61-b21b-73129141d952 | note | VERIFYING DOCUMENTS: This ITP Signed Off
1e28cdfe-7df8-54f5-b857-92ab69b478f8 | date | Date Completed:
| checkpoint | 4.4 Pre-Installation check
7be86ea6-2510-5d27-aac6-5f17425c823f | note | REFERENCE: IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
4aa4cd36-c961-53c6-9afb-67e13a95acc7 | note | – – – – – – – – – – – – – – – – –
294713f9-6cb5-5d4c-87c3-4bab1ad574a1 | note | ACCEPTANCE CRITERIA: Ensure that locations matches most relevant IFC drawings
bdfe59a5-21f7-5888-b7df-32c764f14133 | note | – – – – – – – – – – – – – – – – –
22ef5149-e66d-5d36-9d34-c42ced376a9b | note | METHOD: Visual, Document Review
d2dff423-2012-545c-8e88-8f49aaeeac4b | note | – – – – – – – – – – – – – – – – –
79c92b22-b3dc-5f92-b08a-3c0a99676783 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
2009504e-f06f-54d1-b291-1cf099bba634 | note | – – – – – – – – – – – – – – – – –
7b4d8bbb-240f-5297-968f-76d8c4c380a8 | note | CATEGORY: IP
78dd1877-ceae-524c-89b1-285f27f494fe | note | – – – – – – – – – – – – – – – – –
1db834f3-efa9-5d7a-972c-e38a5b9ab614 | note | RESPONSIBILITY: CAT5/MRPA
5d151510-1ece-5123-bcb3-53347e42ecea | note | – – – – – – – – – – – – – – – – –
43820e00-4971-5827-9dc4-b478bcd10151 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9125e1a4-a2cc-5013-b49c-c48fe1355092 | note | – – – – – – – – – – – – – – – – –
e5855140-622a-5ccf-aa30-b42b9798312e | note | VERIFYING DOCUMENTS: This ITP Signed Off
feddfa15-c3b0-5efd-a18c-05ec373b9c63 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Cantilever installed.
0977ba1c-bd4a-5ff1-898e-af6365a57368 | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
35e7173f-9fb3-56f2-b376-fbcd33ebd602 | note | – – – – – – – – – – – – – – – – –
c7920609-f574-5fb6-ac27-0a521c525007 | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
f08acc08-5f2b-5994-88a5-85c522fc1ae6 | note | – – – – – – – – – – – – – – – – –
043671a3-f2d8-5daa-a044-c23f41fadea0 | note | METHOD: Measure, Visual
a68914bb-239b-5a35-a9ee-5b5ee9672fcc | note | – – – – – – – – – – – – – – – – –
e58bb989-c05b-588a-8467-3add1a3e4aa1 | note | FREQUENCY: Each OHLE Structure
0fdf4cf9-e8dc-5997-a4b9-8c58f8352bc4 | note | – – – – – – – – – – – – – – – – –
bed921fb-b0e6-5c1e-acf6-4677a5570aec | note | CATEGORY: IP
5c95b3e2-83c1-5e73-91dc-fc035a17aec1 | note | – – – – – – – – – – – – – – – – –
d2866877-cc29-5fea-960d-43cb654a68d8 | note | RESPONSIBILITY: CAT5/MRPA
1e8136a5-7ba7-5877-8a18-f3cf89220a17 | note | – – – – – – – – – – – – – – – – –
5ba04593-b48f-5900-9407-303a0f2d94df | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
553fad17-5b11-5638-b3d4-fe9ea57a2195 | note | – – – – – – – – – – – – – – – – –
c52f2c90-8ed2-5b75-8a2a-3705436da32e | note | VERIFYING DOCUMENTS: This ITP Signed Off
84e33ea2-0477-53a4-b0f3-6c255f4c8c7c | date | Date Completed:
| checkpoint | 5.2 Install SPS to correct height / position relative to track
680192af-6c94-5168-b841-82639eefe045 | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
43fa809c-dbbe-5200-99f4-783a40187beb | note | – – – – – – – – – – – – – – – – –
9aec2775-b28b-5650-983e-fd60d6597867 | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
00f15125-6a05-5f5b-b943-ecd75a3b46f5 | note | – – – – – – – – – – – – – – – – –
53809025-0e6c-5de1-b538-3515b90507af | note | METHOD: Measure, Visual
badbe591-0096-516b-8ca7-0818cfa9e72c | note | – – – – – – – – – – – – – – – – –
dd108c07-805c-5c43-a0b2-2a9ad7c9b95f | note | FREQUENCY: Each OHLE Structure
09c4ad43-577e-5fad-aa17-55562dfb34b5 | note | – – – – – – – – – – – – – – – – –
eba10c0a-5f06-502c-aacb-147ccff2824c | note | CATEGORY: IP
c3ffa07b-06b1-5f90-924b-718347eedb9a | note | – – – – – – – – – – – – – – – – –
e37ca71b-bbaf-54b7-bc86-e2df990539f5 | note | RESPONSIBILITY: CAT5/MRPA
0a872d52-5590-58ed-b388-c7bafb7cd917 | note | – – – – – – – – – – – – – – – – –
c4fdfa2b-7a97-59c5-9032-a14be5b120c6 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
b67d9055-10ad-535a-92f5-0c90db208e44 | note | – – – – – – – – – – – – – – – – –
f1ae3bed-496a-56fb-a23b-f9982b0976d9 | note | VERIFYING DOCUMENTS: This ITP Signed Off
c29b6f6c-fa02-5990-bfe3-ddf845ff219f | date | Date Completed:
| checkpoint | 5.3 Cantilever checked once installed.
ebfcbd2b-cf60-5031-ab76-c0586b973ed1 | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
b9e70a90-c6ca-548d-8058-a787ec4428e5 | note | – – – – – – – – – – – – – – – – –
ff576ec2-7553-5b5a-9e0e-77fdf8b4d7c5 | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
9aed3750-eab9-5e48-8256-a1255668c07b | note | – – – – – – – – – – – – – – – – –
24cc0f59-a634-583c-b902-3638ab10f6f2 | note | METHOD: Measure, Visual
a4252b0a-47df-5471-962a-11e00ee0670a | note | – – – – – – – – – – – – – – – – –
1ebc1b3c-d70d-52b3-b0c5-cbc8a809b4a7 | note | FREQUENCY: Each OHLE Structure
35072d99-9a86-50db-a20b-b88c3682a620 | note | – – – – – – – – – – – – – – – – –
421cada0-e034-5b4b-b1f9-066d224aea16 | note | CATEGORY: IP
8a345251-64ea-5e52-9e79-2483270509f4 | note | – – – – – – – – – – – – – – – – –
054f01c8-3f9f-500c-ad8f-a5bd7cbaac85 | note | RESPONSIBILITY: CAT5/MRPA
318af586-a314-5ac0-9cd3-16b53b800c51 | note | – – – – – – – – – – – – – – – – –
0776c0c1-bf21-5452-8b5b-f2af07312be4 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
a5afab66-7d88-5b99-ba74-aacb93bf5365 | note | – – – – – – – – – – – – – – – – –
82370b4a-45c1-5b42-aa63-4e6812f448d2 | note | VERIFYING DOCUMENTS: This ITP Signed Off
f6be6c12-673d-5c02-a693-40ca78c20079 | date | Date Completed:
| checkpoint | 5.4 Installation of wire supports at the correct height and stagger.
6ecb80ae-7eb1-5f73-8e07-ff8ede5d36d8 | note | REFERENCE: Install as per design drawings.
fe123e1b-74b7-5b17-a6ff-e7af6287fa41 | note | – – – – – – – – – – – – – – – – –
322a3dea-d32c-5252-862e-5075514366d1 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
3ab2580c-61f0-530d-86c4-dd6b69e60fe5 | note | – – – – – – – – – – – – – – – – –
716e87d3-7144-55db-90ce-8c42f1c4ad9f | note | METHOD: Visual
e35442d3-df82-5cfa-9862-a45b04f80736 | note | – – – – – – – – – – – – – – – – –
3edf960e-8d79-5d51-9319-25648ff149c1 | note | FREQUENCY: Each OHLE BWA structure
c79a7e90-36e3-5e34-a6d3-0ee73ba02bcc | note | – – – – – – – – – – – – – – – – –
9a3f639a-693a-5cb7-a79a-72e8387d4c04 | note | CATEGORY: IP
ec8cf4e8-675a-53e9-84e0-9aa250b8877c | note | – – – – – – – – – – – – – – – – –
303a6443-59d9-5c17-a12f-c79db2f6a0e1 | note | RESPONSIBILITY: CAT5/MRPA
1c959f16-8150-54d3-8b17-2d12635a2c4d | note | – – – – – – – – – – – – – – – – –
a0e3f832-1fbe-5f61-82dc-be037c0c3186 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9b7f0be7-ea90-5469-a8e2-7cf325175640 | note | – – – – – – – – – – – – – – – – –
ffee7b0f-856e-50da-ae59-2c8309116ee7 | note | VERIFYING DOCUMENTS: This ITP Signed Off
fe121d03-29e1-51ed-a21f-39aa40526832 | date | Date Completed:
| checkpoint | 5.5 Installation of small parts
75ac6e90-cccd-579b-b87a-b3c0f5058697 | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
9034acdc-fe77-549e-a22f-a1f822c68af9 | note | – – – – – – – – – – – – – – – – –
37dabfe6-79ca-568b-bf8e-59836efa353d | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
f97be056-c43c-50ea-957b-b4b2b15ba24d | note | – – – – – – – – – – – – – – – – –
74a62932-fa5e-539e-9342-c4aa453ee8da | note | METHOD: Measure, Visual
e0d13fdd-c6e8-54b7-bfcd-52394ee5b042 | note | – – – – – – – – – – – – – – – – –
a039bc2e-34ee-59cd-83f5-be9676d11ce4 | note | FREQUENCY: Prior termination
11efae9d-84a4-59ad-9b81-3c2ae36b2150 | note | – – – – – – – – – – – – – – – – –
00fb76c9-d31c-5c53-8a8a-1ece75133153 | note | CATEGORY: IP
2ea0546e-4f44-5603-bb17-53a0c5625855 | note | – – – – – – – – – – – – – – – – –
7edc3398-d9d4-5d20-bfa4-6da9e7f2b858 | note | RESPONSIBILITY: CAT5/MRPA
5c0768d7-3874-5682-950e-bf1ab7444bf8 | note | – – – – – – – – – – – – – – – – –
cb03a1b2-4a19-5ba9-989e-b279bd49f87a | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
4214bc4d-ea95-5353-be25-aa59a5c4cc9a | note | – – – – – – – – – – – – – – – – –
b950d760-c0b1-5b07-abe0-9ff3cf7d46b3 | note | VERIFYING DOCUMENTS: This ITP Signed Off
808ae318-e5fe-5e11-840d-102e0b61679b | date | Date Completed:
| checkpoint | 5.6 Complete Clearance Checks
aaf8e40b-7380-5aec-b41d-d9233a8b74dd | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
ef994ccd-1304-5ae3-ba78-88742f1eaa6c | note | – – – – – – – – – – – – – – – – –
1a2f2d08-0324-59f1-b9e6-2e92fe0c1c3c | note | ACCEPTANCE CRITERIA: Visual inspection for clearance and wire staging from Hirail EWP
8e5ad01c-29a6-50ad-93e7-4a50fbd121db | note | – – – – – – – – – – – – – – – – –
362aca34-d3c1-5d6e-bab5-bc7449b27ef4 | note | METHOD: Measure, Visual
223756cb-2c60-592e-8385-2d1832519767 | note | – – – – – – – – – – – – – – – – –
5b59f61a-06fc-5c7c-a5b7-881c7d5b1a7d | note | FREQUENCY: Prior termination
1ee6bf9e-ceb1-5911-a58c-92f850eb908b | note | – – – – – – – – – – – – – – – – –
2c79ed84-5b41-57ce-b72a-c183cae1d99e | note | CATEGORY: IP
b150012f-ce1f-55e5-9a50-c2f539536956 | note | – – – – – – – – – – – – – – – – –
ffb920ca-3d5f-5e6e-89e7-6cd951d3b660 | note | RESPONSIBILITY: CAT5/MRPA
a1aa9c1a-7b9f-5350-ab34-dad47f6ef5cc | note | – – – – – – – – – – – – – – – – –
f3adc9cd-68fb-573f-af0c-f3e83ff475f5 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
6c9d9092-bff3-54ab-8f58-e5a34135e05e | note | – – – – – – – – – – – – – – – – –
b0fb4232-c40e-5e72-b0ac-9985b693adf9 | note | VERIFYING DOCUMENTS: This ITP Signed Off
abe7122a-88d3-5d12-b9ff-abcd9e166387 | date | Date Completed:
| checkpoint | 5.7 Comnplete Pan Run Test
c90bbf56-12fa-5b08-acc8-ce47a16f3e9d | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
ca6ed2b2-3d8a-5502-8654-0e163899291d | note | – – – – – – – – – – – – – – – – –
49f0f55f-5eee-597e-aad4-3cfd1b931dfc | note | ACCEPTANCE CRITERIA: Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
bf991b64-19f2-5d5d-8f62-9ce6a4367fed | note | – – – – – – – – – – – – – – – – –
75fdf6ab-80db-5746-b6ec-1ea28402e97b | note | METHOD: Measure, Visual
34c931e0-13fa-5f92-8751-67f9182d0f9d | note | – – – – – – – – – – – – – – – – –
79d8a5f1-316f-5097-8941-d13a73f5b10f | note | FREQUENCY: Prior termination
ac37f645-ae95-54d5-82ee-64fb46ca1aa3 | note | – – – – – – – – – – – – – – – – –
d48a166e-16da-52d7-9570-8b4b62547d26 | note | CATEGORY: IP
6f54ab35-b6d7-5171-a6e0-c97a85a3c5c2 | note | – – – – – – – – – – – – – – – – –
c9d58b3b-3729-5680-8e41-ff3375e2f8a7 | note | RESPONSIBILITY: CAT5/MRPA
6ecfe790-589c-5edd-a849-d5401de36a2a | note | – – – – – – – – – – – – – – – – –
d73499a7-9413-5bca-b1df-f66eb6297b5b | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
474248f5-7631-59f2-b71d-f082b3b6703f | note | – – – – – – – – – – – – – – – – –
7d45b0fd-a82e-5df6-93cf-87b5c72c0dcb | note | VERIFYING DOCUMENTS: This ITP Signed Off
27af6476-ee76-5f73-8c78-865fc37081a7 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Defects/Temporary Works
60f32d68-bb50-59e5-8ecc-d1cbceb54790 | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
9ef517f9-ea66-58b4-bf29-f52425a52252 | note | – – – – – – – – – – – – – – – – –
53af6d5f-8b6e-5b3d-8e27-2609babfa44c | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
10c49235-1c19-553d-9fae-314f7272c367 | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
de2cc0e2-0504-528b-b71f-83ea692ff521 | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
aba03e6e-a7fa-5b89-944b-5e431657ca24 | note | – – – – – – – – – – – – – – – – –
3c6fa44e-6ab0-5f4c-a6b6-ad1798fc8ae8 | note | METHOD: Document Review, Visual
377b46c5-7272-5bc8-b3b9-bf26665fff91 | note | – – – – – – – – – – – – – – – – –
0c8555ba-c95c-5759-8f70-8a2bfda8f521 | note | FREQUENCY: Each OHLE Structure
09035ba6-c9ca-5ecd-a3d4-d90e696bef1e | note | – – – – – – – – – – – – – – – – –
4f4c1c50-cbff-5c8a-9fc5-e7717d4c3516 | note | CATEGORY: IP
1d51441c-88c5-54fa-89ad-2d2a9138c577 | note | – – – – – – – – – – – – – – – – –
5dc962cf-872c-5d84-b3a3-712a5e58c2b6 | note | RESPONSIBILITY: CAT5/MRPA
95b6197e-589a-5684-9f31-ae3dd6cf7805 | note | – – – – – – – – – – – – – – – – –
8f80780a-8b7d-56f9-bbdf-f4fd45d1c926 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
5c07d9a8-7809-5752-8a2e-2e000b5a924b | note | – – – – – – – – – – – – – – – – –
3ff0be60-ba58-54ff-992a-80e6542ea7bd | note | VERIFYING DOCUMENTS: This ITP Signed Off
b0d7b6e3-f71f-5014-ba19-95193fbfccbd | date | Date Completed:
| checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
c9fb323a-8579-5ae8-95b2-535a0b391467 | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
ed3536f4-dd4c-59cd-ae30-e4fb7dbc783d | note | – – – – – – – – – – – – – – – – –
fde08d7e-952d-5840-823d-8144a6307329 | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
d5a70258-abe5-5e29-ad19-6221c4afdc2b | note | – – – – – – – – – – – – – – – – –
8489ffab-7437-5a31-a85e-8c04a9f9421c | note | METHOD: Document Review, Visual
25a8fb9c-1dbd-52f1-9bc2-e328965a9fc7 | note | – – – – – – – – – – – – – – – – –
6e8cbbd0-248e-5792-8308-a29a2c46dec3 | note | FREQUENCY: Each OHLE Structure
b347afe7-892e-5ba2-8ed2-0f737f5eb7ea | note | – – – – – – – – – – – – – – – – –
ff6ded0a-509d-502a-a25a-75a6cb73bd93 | note | CATEGORY: IP
c2868694-2498-52bb-b7be-10f486999484 | note | – – – – – – – – – – – – – – – – –
66f99049-1cb1-5c52-89a3-70a9e07798b3 | note | RESPONSIBILITY: CAT5/MRPA
0c6594c7-6b61-52a1-bfbe-910197798316 | note | – – – – – – – – – – – – – – – – –
125bd639-befa-5888-b5ca-adf0dfc786f6 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
e156902c-babb-5310-8535-024c8dacfb35 | note | – – – – – – – – – – – – – – – – –
e41236ad-e8ae-5915-9d60-6504a96e2d39 | note | VERIFYING DOCUMENTS: This ITP Signed Off
e02c92ef-6094-5386-85b2-4aa33eea0035 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
63f8b3e0-4dc5-575b-8467-b4eb20f8e5a4 | note | REFERENCE: MTM Quality Management Plan
ecbbc35b-f273-5ac0-bfa1-36a00e9b9d61 | note | – – – – – – – – – – – – – – – – –
10d75c11-0393-5a34-a675-aa5fdc2acab1 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
00ffc811-6368-55ec-b24a-c873467f9ada | note | – – – – – – – – – – – – – – – – –
c0599f81-f10e-5903-80d8-06d24b674bcc | note | METHOD: Document Review
7d5f31ad-21be-504f-ad8a-adda40a9343a | note | – – – – – – – – – – – – – – – – –
9bd6e7c5-2150-54c1-8c5b-0eda4f4f5106 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
096eba4e-ba95-51c4-a2fa-a101c607b4e9 | note | – – – – – – – – – – – – – – – – –
697eb82a-857b-5a68-9cf3-a4bf8a406b80 | note | CATEGORY: HP
d93e89cd-3184-5973-a14f-080879603bb3 | note | – – – – – – – – – – – – – – – – –
fe5e2659-08cb-583b-9cb8-de8041ebd8a3 | note | RESPONSIBILITY: CAT5/MRPA
942c71b1-7beb-582a-98c0-04c5d27b089e | note | – – – – – – – – – – – – – – – – –
c14d8b72-3ce6-5b19-8756-ced89cff6d02 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9e15c119-c995-59a3-99af-4354d3414dd2 | note | – – – – – – – – – – – – – – – – –
de667435-563c-51b5-a3a2-e59f2add4801 | note | VERIFYING DOCUMENTS: This ITP Signed Off
e6d6c50b-a341-581b-8388-e00ec243398e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
d7da4bf3-81dd-59a6-b208-b80678e74b9e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d9c77843-bb8b-59fd-871c-590705eee9db | textbox | Name:
2e7992c4-29a9-5050-a52b-88c0fb754fcc | textbox | Position:
16cdf6b0-3cf4-5ecb-a978-ae5c978a032d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-107-RAIL-SSB-OHLE Installation Rev 0 | itp | ITP-107-RAIL-SSB-OHLE Installation | 0f719e80-7a79-4546-8381-66f9242bab1a
| section | Referenced Documentation
| checkpoint | Referenced Documentation
f5c48fde-3c25-50e8-b1bf-59cc052e5712 | note | Document Title: ITP-107-RAIL-SSB-OHLE Installation
8a6e91ce-bed3-5ec5-8eee-2485ffbd8da6 | note | ITP Description: OHLE Installation
08914925-1468-5ecf-9514-489f6f9bc90a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
2fda529e-521d-5d89-907b-b5ac4fdfbfd4 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
4815e592-e6f9-5052-ace9-5fc5db0fda3c | note | Revision Number: 0
113b297d-106a-53a2-a7f2-68e12a1ca366 | note | Revision Date: 26/06/2023
80ff0387-a9fa-5aac-a5c2-673cc0d97262 | note | ITP created by: Nikhil Siram
39233005-88ea-5c29-ac4a-75b5cbec119f | note | 1.1 Overhead Line Electrification
176dd747-ed18-5a73-9470-61f2cfc9fddf | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
3381191d-8d69-5a0d-a6aa-553c96923249 | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
01d92440-c86a-5f12-bf55-7947c702eed2 | note | Reference: VRIOGS 001 AS 4100
071e02ad-c894-567c-9441-7082e39664ce | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
10b98818-a889-5dff-bcbb-8c8137d756ed | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
71f3ba6a-df9a-5aec-a9a8-22eef501a124 | note | 1.4 Fabrication of Steelwork
8ce225b9-ad39-5101-a05b-ac39074a5106 | note | Reference: VicRoads Section 630 January 2023
f87025be-1cc4-5839-80d4-da3a67d40f65 | note | 1.5 Electrical Networks Standard Electrical Networks Principles and Performance
09338ec5-c832-5a93-84c9-6aff002a086d | note | Reference: Structural Steel Work - Fabrication and Erection
| section | Preliminaries - Materials
| checkpoint | 2.1 Structural Steel Components and Fasteners
7f48b0e5-a05c-5e69-bbd8-7fb54e76d029 | note | REFERENCE: IFC Drawings
00933c54-31bc-5952-982d-e7c48bd68d5d | note | – – – – – – – – – – – – – – – – –
56d18367-3d59-5932-b91b-bd7426e435d7 | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
d3796ec1-7fe9-58fa-b856-04b7afdaa620 | note | ○ Typically this consists of but not limited to:
b4022e53-fca6-5658-a83b-0b252120c4f8 | note | i. Completed fabrication ITP
1ce6e042-a72e-5b3d-a5e6-1922ce316e68 | note | ii. Weld Procedure Specifications
6fdec736-7b88-5750-aef7-d8e9ab5d8ba3 | note | iii. Weld Procedure Qualifications
d242421e-deb3-50a7-8383-c1ac535ae9ea | note | iv. Welder Qualifications
7b4ff8cd-4ba0-5964-bfa3-0d58350cbd3b | note | v. Material Certificates
bdcf8ba9-56c1-53c1-b756-6728462d2f0b | note | vi. Coating certificate(s)
d24cd7dd-235d-5070-80c8-149249417d3c | note | vii. Non-destructive Testing (NDT) Reports (if any)
61925f5d-bcc6-5155-a106-c0eab1814d32 | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
0079e540-8b83-5ba3-bd63-4105bf53fd59 | note | ○ Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
78287339-16fa-5a29-9fc3-0ca4aae85c4a | note | ○ Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
71d132c1-0e6d-5f8d-b6f7-90da3817d9e4 | note | ○ All bolts nuts and washers are hot-dipped galvanized.
1c6d773d-eacb-57ec-9708-c94336a351df | note | Collate: Structural Steel Quality Assurance Documentation.
97ad8655-139d-584d-9483-8bc806287015 | note | Attach: Collated QA documents in ConQA
22db6e69-ecb5-5f21-b61b-cf59eaccc384 | note | – – – – – – – – – – – – – – – – –
d6862f54-7f02-5a05-bb7e-c36094dc549d | note | METHOD: Document review
5d98d8f7-a452-597f-a8d2-14627b1f7aa0 | note | – – – – – – – – – – – – – – – – –
87acce17-c919-5fa7-885c-76630bbe905a | note | FREQUENCY: Where applicable/ Each element
4547958a-38a7-53d3-8cf5-df14b3afa004 | note | – – – – – – – – – – – – – – – – –
91c02744-1e3f-54cf-aa31-3eddc35ac389 | note | CATEGORY: HP
8ada2bff-a197-5d82-93e2-2be7d406a0e0 | note | – – – – – – – – – – – – – – – – –
2e790551-8b94-58d4-9e5d-233a389a2501 | note | RESPONSIBILITY: PE
08b32966-6e9e-5f79-a5d3-c694cf3e181d | note | – – – – – – – – – – – – – – – – –
172603bb-f0a9-5a52-a5dc-f89f45dbd3dd | note | RESPONSIBLE PERSON:
25803825-3f79-5c41-bb0f-fc8eb531e7f0 | note | – – – – – – – – – – – – – – – – –
947e00e2-2a18-5dbc-80a2-ad1e237bafd7 | note | VERIFYING DOCUMENTS: This ITP Signed Off
c6f46720-490f-5b81-a774-a5a26f83e34c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bolted Connections Using Direct Tension Indicators (DTIs)
4db1b464-aa00-5075-b7f6-f00be9ccb1db | note | REFERENCE: AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
52669e31-a66e-5b21-8099-b6ca16b92cd5 | note | – – – – – – – – – – – – – – – – –
f845548c-2311-5d45-81ab-5fcbb1048745 | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
6681e48c-3121-5b5f-a75d-5fdd0ae1e729 | note | i. technical data sheet or information on the product
c40d2749-e791-54b8-8e85-8f9712d6a7c5 | note | – – – – – – – – – – – – – – – – –
9b97709c-b4ba-5651-8c3c-2912c261c9d7 | note | METHOD: Document Review
f6d2733e-da09-53ce-94bd-7ff867a0a2ea | note | – – – – – – – – – – – – – – – – –
8ba368e0-803b-55f2-8d54-e18552b14ae3 | note | FREQUENCY: Where applicable/ Each element
20282071-3896-567c-9c5a-ed7894a1a286 | note | – – – – – – – – – – – – – – – – –
b99a4a83-4b40-5c57-bcaa-de4dd5d18a72 | note | CATEGORY: HP
e4dffe7d-5012-51f4-8915-d8d49a51a87e | note | – – – – – – – – – – – – – – – – –
3cea4ccc-44e2-5f31-b532-6d8ee80a4d91 | note | RESPONSIBILITY: PE
3f481267-29f5-5b20-b202-3c5119f9ff11 | note | – – – – – – – – – – – – – – – – –
b040a363-089a-52f8-ab58-08caf5364ff4 | note | RESPONSIBLE PERSON: MRPA Engineer
07e41947-f445-55e7-ae0f-be5d912ba697 | note | – – – – – – – – – – – – – – – – –
28bfff6a-19d1-525c-bbc0-22a1b800edc0 | note | VERIFYING DOCUMENTS: This ITP Signed Off
b2b18a3c-2dc6-5b02-840b-7f8cd0de85f8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Overhead Wiring Small Parts Steel and conductor wires
7ec7c784-0d5f-55e9-b0dc-d990b9413187 | note | REFERENCE: Relevant MTM Standard Drawings
af0f832a-494d-5b7a-80e3-cc10fee4d509 | note | – – – – – – – – – – – – – – – – –
f62663fe-5197-51dc-a8b5-4149ef131d3d | note | ACCEPTANCE CRITERIA: Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
5add9b89-e1d5-56fe-9dbc-e1ac13a53cfe | note | ○ Deliveries are to be inspected to match the purchase order
f4a781d2-e239-5ee4-9592-bc20bc84f8f7 | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
f03739a6-0fb9-5e06-a89e-54f16f877097 | note | – – – – – – – – – – – – – – – – –
5d7d804e-f7a6-59c7-bc3d-160c6d540482 | note | METHOD: Visual Inspection and measurement
94f9e43d-d45d-55bc-a735-7dbd08c8206b | note | – – – – – – – – – – – – – – – – –
880de731-27e0-5cef-b95b-cafae84bf766 | note | FREQUENCY: Upon delivery
b71bd415-b1b4-5906-afbd-cb1a7a190422 | note | – – – – – – – – – – – – – – – – –
ee7086c4-7c92-51d9-b9c6-4c0716e7bc33 | note | CATEGORY: IP
3ffa9fab-83e6-5176-87ab-7f4a34c31bab | note | – – – – – – – – – – – – – – – – –
9c05a891-78df-59f0-b291-4505d0677208 | note | RESPONSIBILITY: PE
8e52345c-e6f7-5b5b-815b-78ab79e4db4b | note | – – – – – – – – – – – – – – – – –
e763123f-3b3f-5479-9ba2-0546c71a6824 | note | RESPONSIBLE PERSON: MRPA
c87d283d-4a06-55b1-a169-286a774a41f4 | note | – – – – – – – – – – – – – – – – –
789c61d5-dfab-548a-8fca-d905d1f624b5 | note | VERIFYING DOCUMENTS: This ITP Signed Off
a2bcd3ef-c709-53df-8094-372c67252d14 | date | Date Completed:
| checkpoint | 2.4 Grout
8cbec756-ffcb-5e1e-bc37-72cee335bbeb | note | REFERENCE: IFC drawings
b6e0237c-2b3d-5921-af23-5e85ee179411 | note | – – – – – – – – – – – – – – – – –
2592bc8f-30f5-5b26-b178-73dd19272c8f | note | ACCEPTANCE CRITERIA: All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
59918e31-9962-51eb-9303-6bbbf5823426 | textbox | Enter: Teambinder Material Approval number
0eb4fd4d-968f-5b55-b094-639ceb753554 | note | – – – – – – – – – – – – – – – – –
bce2337f-7fca-5c30-bb68-a00b474940ba | note | METHOD: Document Review
ec7e4b40-7807-5cd6-925a-3a1003159608 | note | – – – – – – – – – – – – – – – – –
bdd22932-43e9-56c1-a3fe-ed2720bc22f6 | note | FREQUENCY: Where applicable/ Each element
3a89f8b9-db13-511d-9a1a-5a1904c8ce5c | note | – – – – – – – – – – – – – – – – –
a0feacb8-3c68-5b7b-a35a-e3f2c7c1621b | note | CATEGORY: HP
e834f7e8-7cec-5fd2-b7ce-4cc670890ec9 | note | – – – – – – – – – – – – – – – – –
dccf37e8-c7da-54b7-8ef8-72425965afff | note | RESPONSIBILITY: PE
29f77572-f0cd-5d85-a995-e8d381e63064 | note | – – – – – – – – – – – – – – – – –
0c33f82c-a0cf-5368-b97a-813e37ccc2c0 | note | RESPONSIBLE PERSON: MRPA
b64ae4f0-8309-5ac6-beae-84527b3baba2 | note | – – – – – – – – – – – – – – – – –
646a91c3-e6ca-5fa7-867c-4612eb20527c | note | VERIFYING DOCUMENTS: This ITP/ Material Approval
607fd64a-fd95-5552-bc20-f101e27fcdd8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Installation Methodology & Works Method Statement
06b87b39-b938-596e-9321-8e403cf57f97 | note | REFERENCE: AS5131 Clause 11.2.3
48f20d59-fd7a-5d42-8b5d-02fb6d200c07 | note | – – – – – – – – – – – – – – – – –
37ff175d-2934-514f-a960-15769eacc79a | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
40ad14c5-3ef3-5c3d-8d94-12c56986d644 | note | – Transported to site;
5c163383-84b3-515d-9912-2e4901dd64c7 | note | – Handled on site;
1dfbef54-4b81-5147-830b-4015ca392aa5 | note | – Installation Procedure (subcontracor ITP's);
08abbfa4-c3c4-54b4-9c0f-9de2833eb84a | note | ○ Submission of Work Package Plan and MRPA approval and acceptance.
cd35c9d6-b307-58a9-a2c1-d8c88ef6b6cd | textbox | Enter: WAP number
e544f331-3e6c-5ddc-a627-2d9be45c75a5 | note | – – – – – – – – – – – – – – – – –
4e12ea3f-6e11-5515-8890-e067e9314b03 | note | METHOD: Document Review
b3b2deb4-5f13-5207-bd52-b41177191892 | note | – – – – – – – – – – – – – – – – –
bea95289-5fe9-5e1a-976e-6e22e87d6502 | note | FREQUENCY: Prior to Works Start
d36b72c5-a9ca-5810-b78d-f7a428c728a8 | note | – – – – – – – – – – – – – – – – –
c966f8e6-2634-5da6-9bd0-0b3b368eb0f6 | note | CATEGORY: HP
aae3543e-3a4a-5514-bbdb-5680d264a22e | note | – – – – – – – – – – – – – – – – –
df3ce3e0-f979-5e2e-a959-3dba3c7c6b79 | note | RESPONSIBILITY: MRPA/CAT5
cdfdafd3-96b9-5765-b057-9dee4a8365c2 | note | – – – – – – – – – – – – – – – – –
03a40938-10d7-527d-8b40-4be2c68694bf | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
27fa005f-f52e-5efb-bc16-911556e8d138 | note | – – – – – – – – – – – – – – – – –
b4ca5da0-8f0e-5e8a-ae4f-cecefac9a6fa | note | VERIFYING DOCUMENTS: This ITP Signed Off
8f1de70a-1110-55bb-bc02-1b9c6cce1a0c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 Approval of IFC drawings
03726548-a028-59b2-bcda-9129ad3a0256 | note | REFERENCE: Contractor Design Management procedure.
80f6003a-756e-5ad0-8b2a-98289d1b0b95 | note | – – – – – – – – – – – – – – – – –
48dbc9e2-692e-5f94-b2e8-f043e8a731b0 | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
5e567a32-445b-53f7-bf70-57f7c7b2534f | note | – – – – – – – – – – – – – – – – –
0e1f38c5-61c5-5709-b3d8-bbfaaea13d8f | note | METHOD: Document/Drawings Review
cffcb202-799a-53ba-9cfc-d1232efc2fea | note | – – – – – – – – – – – – – – – – –
acedcaa6-86be-5398-839f-cdc90bd6960a | note | FREQUENCY: Prior to Works and at regular intervals.
7db8c5b3-0682-5ab5-9ded-0240dbd52567 | note | – – – – – – – – – – – – – – – – –
2d9ccd84-c15d-5a80-9836-dfab72db52dd | note | CATEGORY: HP
213a3a08-5961-5bd9-9256-ae3d4c507e34 | note | – – – – – – – – – – – – – – – – –
23e993d6-81f4-59b9-aafe-45ce7cf6e160 | note | RESPONSIBILITY: MRPA/CAT5
ee6936d4-378f-5607-a399-b2c1eeaa99be | note | – – – – – – – – – – – – – – – – –
743d1855-a3e2-5b1b-b885-b88fa60f4450 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
06e730f3-19f5-5366-a52a-cf743b1e7ebe | note | – – – – – – – – – – – – – – – – –
029c51df-c5f7-5d86-90ae-4e85f30dc737 | note | VERIFYING DOCUMENTS: This ITP Signed Off
cc0e6ffc-3da0-5255-8203-464d873dee77 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 Cantilever assembled.
daeb9e86-0c20-5572-ad60-b9a07c463071 | note | REFERENCE: Cantilever assembled as per IFC design.
1888c66c-e1e9-511c-8004-523fee4912e2 | note | – – – – – – – – – – – – – – – – –
c668f5c3-7120-5354-a07a-bc361cf78088 | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
ae6c7d48-d5bf-565f-a12a-c8ed5fa415ac | note | – – – – – – – – – – – – – – – – –
80012fcd-ffb9-5f9f-934b-115dd36f6587 | note | METHOD: Visual, Document Review
bd6f4b22-7ee8-5653-848c-3d48be06f3a5 | note | – – – – – – – – – – – – – – – – –
470ddab8-b23c-5fca-8e5b-00fbd3790630 | note | FREQUENCY: Each Task prior to works start.
2507c14a-c766-53a7-84b1-be065cd92b61 | note | – – – – – – – – – – – – – – – – –
d197c8b2-0d31-50fb-af67-be3e1bbba8a9 | note | CATEGORY: IP
eb5c3db2-f4df-571b-9cd1-35e64bac6d1b | note | – – – – – – – – – – – – – – – – –
b6e246cd-2103-562d-b224-4582a1174862 | note | RESPONSIBILITY: CAT5/MRPA
5d3de08b-51c0-5a0f-bd74-dae92dd024c3 | note | – – – – – – – – – – – – – – – – –
6301e623-44a5-598e-baf5-44ec96908fe3 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
dfe398d2-bb3c-5b0f-8ec1-e96e92e21eef | note | – – – – – – – – – – – – – – – – –
20ea961f-a2e2-5337-bd91-c47b37f12a21 | note | VERIFYING DOCUMENTS: This ITP Signed Off
56f082f9-1dc3-5866-9677-0989d3bfa7c7 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Mast Installation
f836838d-5917-5ad3-9ee2-90240535423c | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
68c217af-d910-5478-9efa-19bfc35836dc | note | – – – – – – – – – – – – – – – – –
f9678e6a-2f79-51d7-bd8a-03bf55e62cdc | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
037314b6-5081-520d-b99f-21faf8c83299 | note | – – – – – – – – – – – – – – – – –
3e0815a3-04b5-5400-abdd-289767b6dc79 | note | METHOD: Measure, Visual
f4e25d06-666b-5281-9236-abf99b71f042 | note | – – – – – – – – – – – – – – – – –
4980fdcb-d940-5c5a-8ec9-138410f4f7d8 | note | FREQUENCY: Each OHLE Structure
507d6d56-c89d-55de-adb7-f8b8ef37974d | note | – – – – – – – – – – – – – – – – –
7e02f24e-93b7-5cb5-9d76-ab073d43984a | note | CATEGORY: IP
54ec0c94-6f99-5d10-8480-78367384473a | note | – – – – – – – – – – – – – – – – –
cef86f02-446d-554b-9013-1eefb4bb2dfe | note | RESPONSIBILITY: CAT5/MRPA
2b3feba3-cb56-5882-834e-3a5bccc09705 | note | – – – – – – – – – – – – – – – – –
aaa02d86-fb6f-5f7b-8b96-7612ecd4b7b2 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
704023ca-530b-5995-921b-c2777a64404a | note | – – – – – – – – – – – – – – – – –
62802c72-180c-5c29-a35c-291303fedc1c | note | VERIFYING DOCUMENTS: This ITP Signed Off
ed1dee77-fbc9-5f86-8f70-bce51fe42fcb | date | Date Completed:
| checkpoint | 5.2 Cantilever installed.
63d96ecf-1fbb-59d5-8961-81573cd45d63 | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
ba36bfb7-1225-5af7-8a8f-68cc12af69ad | note | – – – – – – – – – – – – – – – – –
bd6ea88d-50ca-5b65-a5f9-9e611a153754 | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
b8c1f307-9831-55a2-bee5-79e4e0e6a71e | note | – – – – – – – – – – – – – – – – –
b6409d62-2499-53ca-af92-3f9dab2ea4e7 | note | METHOD: Measure, Visual
8adbfca9-da64-5043-bc16-7722def07645 | note | – – – – – – – – – – – – – – – – –
fd71d78b-82a5-5b24-b33f-a362b37effbb | note | FREQUENCY: Each OHLE Structure
098db34e-7b9e-5093-bb69-2b79727519dc | note | – – – – – – – – – – – – – – – – –
6aa2bda7-cc38-5bad-bbca-1ebbea093180 | note | CATEGORY: IP
4cb4b7d7-87bd-5158-a5e2-44e49af7d4e1 | note | – – – – – – – – – – – – – – – – –
824f6fc9-1337-5ab6-962b-f62214d32b35 | note | RESPONSIBILITY: CAT5/MRPA
14d4c480-973a-588b-a232-e4d248a51cc1 | note | – – – – – – – – – – – – – – – – –
9230be26-a0c6-5611-bb52-710bbd53826b | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
cffc2974-a7d6-51ff-8265-3b008ca5e886 | note | – – – – – – – – – – – – – – – – –
63cc700a-bc8e-53e3-8483-d679f2787207 | note | VERIFYING DOCUMENTS: This ITP Signed Off
a582ff00-aa80-58b8-a13a-49bd30f52774 | date | Date Completed:
| checkpoint | 5.3 Bearing type Joints TB Friction type joints TF
6db97c23-c0fa-5fb1-be9c-70968f6cbe4d | note | REFERENCE: IFC Drawings
d2aebb1b-5445-5b62-b8db-e2f7746e15a2 | note | – – – – – – – – – – – – – – – – –
a99ab9c1-b1fa-5766-a4c0-8c5d5a6473bb | note | ACCEPTANCE CRITERIA: BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
fc48ca2e-57d4-5cff-a4ef-e90bb19b30f8 | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
bbb1dd51-6e75-52f6-9b9e-ea8b0860391b | note | – DTI squirts are to be visible for inspection
9ad37ab9-3e69-5320-8b85-1ce7155597de | note | – – – – – – – – – – – – – – – – –
97ed00a7-e45e-5b7f-a415-2407f14520ad | note | METHOD: Visual
2f94ea13-5f1b-5b16-b3a3-9cd6a0b20513 | note | – – – – – – – – – – – – – – – – –
e574ca61-f92a-5dbc-8067-fb7673ddc1e2 | note | FREQUENCY: Where applicable/ Each element
8e4f2c72-e42c-5b30-91a2-6270bbd989ae | note | – – – – – – – – – – – – – – – – –
ff7e206b-380f-58b3-925f-91183260d963 | note | CATEGORY: IP
95464445-1f82-5f32-8ddf-cd5c306c32f7 | note | – – – – – – – – – – – – – – – – –
9d1ec060-98ea-5f52-b58a-87dad30ad5bf | note | RESPONSIBILITY: PE
8f3a639a-3e9c-5133-bdd9-6e35bf2942fe | note | – – – – – – – – – – – – – – – – –
6d1a3669-e41b-5fc5-b4cc-d7a31bb276b2 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
09fc2020-7d73-5db0-a24c-380464188db8 | note | – – – – – – – – – – – – – – – – –
f6014d24-465f-5d18-8510-6a382b46a667 | note | VERIFYING DOCUMENTS: This ITP Signed Off
d9b97650-44c8-53b7-8e9d-d6d88d90c790 | date | Date Completed:
| checkpoint | 5.4 Install SPS to correct height / position relative to track
1aa57f7e-da97-5849-9950-95863f415a77 | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
746ec6b0-b0c9-5821-82d7-39d4f4ea371d | note | – – – – – – – – – – – – – – – – –
24d36fd1-927a-5922-830c-6b2fab3b7b21 | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
2273c080-059d-5b4b-b950-0e9834558eb0 | note | – – – – – – – – – – – – – – – – –
3e946535-ced9-5d18-8f04-767201e12455 | note | METHOD: Measure, Visual
63f7aa02-4d16-5f7c-8990-cd03d7c1975f | note | – – – – – – – – – – – – – – – – –
60002949-78cb-5169-bab2-5ef97543c714 | note | FREQUENCY: Each OHLE Structure
d7c91213-0dfb-5197-be3d-ee5b864bbe91 | note | – – – – – – – – – – – – – – – – –
48c4eb36-f553-56cf-8815-81a3e2fbbf0c | note | CATEGORY: IP
6f61e8df-9787-59cc-a65f-d9d85f86c271 | note | – – – – – – – – – – – – – – – – –
9e6c836c-06e6-52a6-b10c-e45f85450158 | note | RESPONSIBILITY: CAT5/MRPA
29c48d56-e44b-5f29-a66d-8a74f3506a8f | note | – – – – – – – – – – – – – – – – –
f5b08423-6c6c-5c91-b104-a09e63a80a34 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9f2723cb-97cd-56f5-9908-d1fc06d47362 | note | – – – – – – – – – – – – – – – – –
aa92441f-e490-58a2-a0a5-969bc3bbee51 | note | VERIFYING DOCUMENTS: This ITP Signed Off
f5182cb1-f181-5513-9d3d-441600c2c660 | date | Date Completed:
| checkpoint | 5.5 Cantilever checked once installed.
40c753a0-58ab-5b44-808f-dddcb5e7e4e8 | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
da60ed6f-c936-5bcc-a57f-9b4678482921 | note | – – – – – – – – – – – – – – – – –
a8eb0c5a-3caf-5aac-8d3a-66d8852fcc35 | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
7fdd5fe8-768c-5619-997c-c71bbc5de732 | note | – – – – – – – – – – – – – – – – –
83973b5d-f32d-52ce-bf3b-e888ef4d37ac | note | METHOD: Measure, Visual
e364e8ec-52a9-5899-b31e-d3e6b1450e58 | note | – – – – – – – – – – – – – – – – –
1c47c9af-6eb8-5e5e-a111-c235fa38654e | note | FREQUENCY: Each OHLE Structure
314b524d-9443-576e-8c02-70bc26f951e2 | note | – – – – – – – – – – – – – – – – –
a381d6fd-6e75-5ff7-8d8b-4308a9f89154 | note | CATEGORY: IP
28589d8b-8b15-5633-a26b-b30d86da68c3 | note | – – – – – – – – – – – – – – – – –
a9bba10a-93fb-56ef-a3aa-d1a54a4ccbe7 | note | RESPONSIBILITY: CAT5/MRPA
d1ddbac9-a08e-5ec1-a6a2-165325626726 | note | – – – – – – – – – – – – – – – – –
ea37a33a-2397-5ca6-8a43-e29c5d83565a | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
42abe06a-f106-5ee8-a54c-b0b4454cdc05 | note | – – – – – – – – – – – – – – – – –
ab4afdc7-79f3-5948-8dd7-877f8cc91cb3 | note | VERIFYING DOCUMENTS: This ITP Signed Off
7be22012-1704-5bc2-8afd-e167b8680a59 | date | Date Completed:
| checkpoint | 5.6 Base Plate Grout
472f013c-4a6b-5a85-be79-2404a48328fd | note | REFERENCE: IFC Drawings
26622f3f-3cf4-5b4f-bc6f-97d06b70d8c7 | note | – – – – – – – – – – – – – – – – –
9a50a172-1b43-583c-93d5-05ada46d320d | note | ACCEPTANCE CRITERIA: Grout to be mixed as per manufacturer TDS.
2994292e-ee6f-5db6-8e15-94832a57b902 | note | ○ Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
e97e2710-d7a5-5163-a6ae-ce8e0b3fc093 | note | – – – – – – – – – – – – – – – – –
2656c8c8-57ee-5718-9449-0806de149355 | note | METHOD: Visual
507c3fdb-f67c-5bf1-a3e8-5980839eec4a | note | – – – – – – – – – – – – – – – – –
7dc93e0d-4fbc-58f2-b55a-9e3492fab876 | note | FREQUENCY: Where applicable/ Each element
52858881-4be0-5782-aa3d-3da75ccb6e0e | note | – – – – – – – – – – – – – – – – –
970487a6-9901-59af-b0dc-916480ca581a | note | CATEGORY: IP
d702fe00-4911-5d06-9208-4f382d322edb | note | – – – – – – – – – – – – – – – – –
f5597ac9-ce74-5cc1-9db0-a993d667a75a | note | RESPONSIBILITY: PE
0324028f-6096-5299-904d-33535fb67fba | note | – – – – – – – – – – – – – – – – –
f7d779ba-797f-5c7c-ad40-339c51808db4 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
599c726e-cf27-557d-bc32-9c46fb003506 | note | – – – – – – – – – – – – – – – – –
b5014127-7ee4-54e4-94e6-fc4455b14681 | note | VERIFYING DOCUMENTS: This ITP Signed Off
cd80f9fc-2443-5d68-864d-c9830f0bac1f | date | Date Completed:
| checkpoint | 5.7 Installation of wire supports at the correct height and stagger
fcc96006-b7d9-5045-9c6a-bff44f0e8475 | note | REFERENCE: Install as per design
280a2a25-f8e9-5df3-b7a5-98e751d24fd6 | note | – – – – – – – – – – – – – – – – –
4a69bea1-4ceb-550c-80a6-a754f6269740 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
7828dbf0-83cc-5fda-a221-0cbe8a96dc6c | note | – – – – – – – – – – – – – – – – –
2d7e927e-9eb7-5dcd-b79e-143c5caa97af | note | METHOD: Visual
46e231e1-2f7a-5fdd-89b0-1a5f494773f3 | note | – – – – – – – – – – – – – – – – –
a12c7f09-1e0a-5ffe-b878-fc9fd1a5ea08 | note | FREQUENCY: Each OHLE BWA Structure
9e2ca214-4204-58f7-9b2f-c7bd8467f5c0 | note | – – – – – – – – – – – – – – – – –
1452ba88-12e4-5ed7-8212-891b7a379d29 | note | CATEGORY: IP
5fc422d0-e59a-581c-aec0-647c1ebe39af | note | – – – – – – – – – – – – – – – – –
a3dc6e6e-d59b-5498-bf0d-7897a5aeeb43 | note | RESPONSIBILITY: CAT5/MRPA
f129c705-a3f6-5445-be75-3d39bd50eeca | note | – – – – – – – – – – – – – – – – –
f22bcfc8-7f72-52ae-8e9c-7a8127b93758 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
441bdb42-d37c-5f43-b9b8-b5c7af05983e | note | – – – – – – – – – – – – – – – – –
62286e36-3d2f-5e5b-bad2-aa533677321b | note | VERIFYING DOCUMENTS: This ITP Signed Off
5f80cca7-6405-570a-a7b9-260670117718 | date | Date Completed:
| checkpoint | 5.8 Install to correct tension
4abace70-0f8e-5acd-bc8f-55a4e7fb68f6 | note | REFERENCE: Install as per design
e54dbcee-131d-5800-8db2-dbff56ba7e62 | note | – – – – – – – – – – – – – – – – –
23aa9df0-9f15-501f-9b90-d8fd20150036 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
4f6b6484-4507-5ae1-92fe-998447d3f299 | note | – – – – – – – – – – – – – – – – –
8c9f5641-8693-5460-b218-5409bdfb95fc | note | METHOD: Visual
bd8714e4-62b2-5e33-b69f-402515d09f22 | note | – – – – – – – – – – – – – – – – –
e1b74f73-e958-5e50-8312-2359030d10c1 | note | FREQUENCY: Prior termination
08ab6b8e-c616-5561-8fb1-02f455c366cf | note | – – – – – – – – – – – – – – – – –
3d22de95-1796-5a89-b20e-2eb3b553c309 | note | CATEGORY: IP
cc42afe4-d31b-513c-9082-ec464cf53a9e | note | – – – – – – – – – – – – – – – – –
e7e154a3-ecdc-5d10-aaa5-95b26004aeee | note | RESPONSIBILITY: CAT5/MRPA
886784fe-6e30-5603-8a38-159aa7bd6778 | note | – – – – – – – – – – – – – – – – –
aa28529a-6d96-5f42-8175-17544065b37e | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
26388024-0aa3-5153-aed0-6dcce5b74fb3 | note | – – – – – – – – – – – – – – – – –
9a717416-0a02-5029-84b1-2f955d03b8c0 | note | VERIFYING DOCUMENTS: This ITP Signed Off
073ee182-b453-551e-aefb-0cc230428632 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Defects/Temporary Works
8e5b20f0-aedd-50e0-8837-4cfda6888ff9 | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
aad3ad53-f78a-527d-adca-8165b43469e7 | note | – – – – – – – – – – – – – – – – –
81985eee-e375-5967-be50-c81a1e62f180 | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
e48dc262-11c3-5c99-9c97-0d216689ff91 | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
5977aa75-3312-56c1-9e8e-5924f6be181a | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
76220dc5-f144-5a51-bd04-3a784d59af62 | note | – – – – – – – – – – – – – – – – –
5481a2c3-3c24-5d8b-98c5-c862f8431513 | note | METHOD: Document Review, Visual
521da5ab-6de0-5266-9cc1-a78c2cae07b3 | note | – – – – – – – – – – – – – – – – –
778add88-1405-5cef-bcca-10f2c4e36c96 | note | FREQUENCY: Each OHLE Structure
532b9e49-a50b-5724-aa64-903f33276c7b | note | – – – – – – – – – – – – – – – – –
1f9914fa-6f8e-50cf-8a61-8d3c02373bf8 | note | CATEGORY: IP
90b4d32f-bfae-59d8-a589-b6b32fc559b2 | note | – – – – – – – – – – – – – – – – –
e4f0aefb-32cf-544d-9375-84f3aed21a98 | note | RESPONSIBILITY: CAT5/MRPA
cf49f667-b651-5b46-95fe-a85df82be67b | note | – – – – – – – – – – – – – – – – –
f217e66a-1eb5-551c-9e7c-73249d974583 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
324d62a5-257d-5c04-afd2-97e7d48ce97d | note | – – – – – – – – – – – – – – – – –
8e1a2245-0360-5a7f-b8c3-162450aa96c9 | note | VERIFYING DOCUMENTS: This ITP Signed Off
c5bd15a4-3b3d-510b-bdc3-3cab8e683e9b | date | Date Completed:
| checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
5dcd57a0-6070-5d1f-a40d-2e8287bbeefc | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
6bf6fc30-c69a-539c-9977-691915cd71f0 | note | – – – – – – – – – – – – – – – – –
66f07e6c-8a1a-556a-8a60-4594e4b6ca7f | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
af95d27b-b40c-5708-bf58-5a79d926b22d | note | – – – – – – – – – – – – – – – – –
73bd7905-e7fd-5468-acd7-610163b1f206 | note | METHOD: Document Review, Visual
606ab702-d632-54a7-ba38-87bb95c74aa8 | note | – – – – – – – – – – – – – – – – –
3acabf6d-d016-5cf0-abbb-fc5e2376d428 | note | FREQUENCY: Each OHLE Structure
659b7a70-476a-5377-81ba-24dca963c751 | note | – – – – – – – – – – – – – – – – –
b0755c96-53de-56a6-9e35-e4ced03522de | note | CATEGORY: IP
9198c3c8-6f66-5089-ad81-82e29ff048d7 | note | – – – – – – – – – – – – – – – – –
7c01eef9-c55b-5073-9513-04da0545460d | note | RESPONSIBILITY: CAT5/MRPA
a87b5892-a74c-58ad-8554-38ee502e4c51 | note | – – – – – – – – – – – – – – – – –
ff182eaf-28a9-5501-b252-a12e7a88e9f0 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
362d1d17-b1dc-54fb-84ce-01367bc2a177 | note | – – – – – – – – – – – – – – – – –
1b5e274e-d16e-523e-ade3-a5495354be6b | note | VERIFYING DOCUMENTS: This ITP Signed Off
faf34a72-f863-5153-9589-feae71cf3c71 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
8a14dcbe-13dd-5762-b42e-25623c030c34 | note | REFERENCE: MTM Quality Management Plan
fc3d709a-0024-51a0-a488-6f35e7c200da | note | – – – – – – – – – – – – – – – – –
b2c3584c-44fa-5af6-b2ca-411c815a4a96 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
bea11cc4-ac13-586a-b23b-7329051824d9 | note | – – – – – – – – – – – – – – – – –
d99adc94-5f27-569c-91f1-ce9adeff5f65 | note | METHOD: Document Review
c5a4b39b-6769-5b01-bd79-90983f5042e6 | note | – – – – – – – – – – – – – – – – –
6b1bd36a-19a8-5c12-8fc8-354eb196ee61 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
d89b08ad-7e65-5677-aee8-4cce4a857b8b | note | – – – – – – – – – – – – – – – – –
9654a071-8b23-59bd-b53f-e73e99005098 | note | CATEGORY: HP
c76cde6e-a315-5a6c-9327-6e31d8472957 | note | – – – – – – – – – – – – – – – – –
d715b7ee-c420-58b8-a7ee-614bc43702b4 | note | RESPONSIBILITY: CAT5/MRPA
93e256e9-51ff-54f5-a119-ba3760940847 | note | – – – – – – – – – – – – – – – – –
a3ecd573-b018-5142-b35e-b69e64ef6e4a | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
801195e6-7702-52c8-bcb7-63f41c80acfd | note | – – – – – – – – – – – – – – – – –
4a321a0c-270a-5f45-b033-cbb5966179b5 | note | VERIFYING DOCUMENTS: This ITP Signed Off
63eefb72-6924-57f0-a28a-3782188b04b0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
d384d2f2-544a-5d4a-ba72-f04de1f3313c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8fbbd0bd-8390-59a5-a60d-2f60d26ffa81 | textbox | Name:
34994f68-105f-560d-a385-9882e1ec343f | textbox | Position:
98aa1362-5e33-54cf-8864-cdad148ed63d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-108-STR-SSB-PILE CAP CONSTRUCTION REV 0 | itp | ITP-108-CIV-SSB-Pile cap construction | f914bbe2-ca9a-489c-8d3f-3a96a23a3107
| section | Referenced Documentation
| checkpoint | Referenced Documentation
75ad334e-f5c3-5ad1-b32b-f0f302a757e4 | note | Document Title: ITP-108-CIV-SSB-Pile cap construction
a1eac5be-aff0-58f1-9281-835d0cc99aab | note | ITP Description: SSB-Pile cap construction
9d2e0ed2-e245-58f7-aff3-b1580222a1a8 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
00aff2f5-1113-5292-85ac-aa14ff967b6d | note | Discipline (e.g. CIV/STR/RAIL): 108-CIV
1c8ff8d5-ea80-5c40-9149-d096cbfc89b8 | note | Revision Number: 0
9a30eff1-213d-5dff-91ca-e9451a2ded1e | note | Revision Date: 22/11/2023
9216fa02-b12c-5cff-9463-c3b1d37b3332 | note | ITP created by: Iyasu Enoro
196569bb-798a-5e29-b6a0-de08145ff6ef | note | ITP approved for use by: Victor Mira
57087e35-7009-5d0f-870c-f8d19158b348 | note | 1.1 Non Dependent
ce2b26eb-eb19-51dc-a655-08cc1e69b1dd | note | Reference: VicRoads Section 602 October 2007
dc213dbb-1b32-5e71-b1eb-79ef7f204477 | note | 1.2 Non Dependent
b628ffd8-1578-5914-9226-76ab775e48e5 | note | Reference: VicRoads Section 610 February 2020
0f88d43e-8140-5f13-80ad-5819c1f5ee97 | note | 1.3 Non Dependent
866312a1-af54-5b5d-ad84-91744cbd4311 | note | Reference: VicRoads Section 611 November 2018
2ebfdc2e-174b-59f1-a8b1-5d42e831c6a9 | note | 1.4 Non Dependent
774d0111-a0ea-56f2-9238-100730d47b06 | note | Reference: VicRoads Section 614 June 2017
e03e1a39-cf37-59c9-8541-1f0b62ff9a45 | note | 1.5 Non Dependent
67c98bcc-dbf8-560f-aaa2-7bfb7fe23ae1 | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
eb13fda3-99f5-5119-8b41-cf565cc20114 | note | REFERENCE: 610.07 Table 610.071 IFC Drawings
964aaaab-cab1-582b-8ccb-72a57df1e78a | note | – – – – – – – – – – – – – – – – –
bed43440-48ff-59f0-a0c0-1c627a2c4486 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
9fa546e5-9118-5d58-98ec-e7eb317e6c4f | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
5a93a7f1-66ab-588d-9db1-035d9628a9c8 | textbox | Enter: Teambinder Material Approval number
9986f40d-2eb5-590b-bdc9-f2c868cc9c54 | note | – – – – – – – – – – – – – – – – –
c700d991-b989-56de-be58-4aa70808ee0e | note | METHOD: Document Review
c80eaef6-3362-5a66-bba5-39ed98380a6c | note | – – – – – – – – – – – – – – – – –
6ae2976e-6ae9-5780-aa2d-a48ea37ed7f9 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
0e9ade17-cf8f-5eb7-b42d-5c50e0e28900 | note | – – – – – – – – – – – – – – – – –
c205df14-335a-5f8e-9415-b8ebf53e35fb | note | CATEGORY: HP
8ddf48e5-bec2-5cfe-88d9-7ca413b23e85 | note | – – – – – – – – – – – – – – – – –
897b8c64-bbd8-5f11-be70-8868347dbbfd | note | RESPONSIBILITY: Nominated Authority
1dc6c592-1a52-58cf-bd88-d6870eb9cca2 | note | – – – – – – – – – – – – – – – – –
dbc4c161-6487-59ed-a6cd-f623633e1faf | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
82e75caf-44ee-575d-9265-8e177ab4430f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
a25203ed-bfa4-5833-9200-023b21f3baf4 | note | REFERENCE: 611.05 (a)
99aca7ac-f54f-571e-b22c-ed6431a98da2 | note | – – – – – – – – – – – – – – – – –
84eea4c7-c8f0-52ea-8c82-554e10efe740 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
12c50047-eac9-5598-bab8-56539fc79cc8 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
9e5b6d94-93be-55bf-8334-5492b19959d8 | textbox | Enter: Teambinder Hold Point Ref Number
3144bef0-71a5-56c0-9122-27562e8e0357 | note | – – – – – – – – – – – – – – – – –
3a4f7328-46e9-5b54-8b81-cc89199f6333 | note | METHOD: Document Review
d5f86f8f-12e3-5a0a-87a0-18fc1da0c583 | note | – – – – – – – – – – – – – – – – –
9eb5531f-4a51-5231-9523-974079f38b22 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
155dcc4f-f445-5004-9bb4-d15df36e2281 | note | – – – – – – – – – – – – – – – – –
3352c9b5-0386-5f25-8257-3284ba19d283 | note | CATEGORY: HP
a5725e78-efc6-581c-872a-559cae352595 | note | – – – – – – – – – – – – – – – – –
49f5d99b-9adc-5853-a4be-dd208bdcb75f | note | RESPONSIBILITY: Nominated Authority
cba70abf-a64b-52fc-8d7d-852ad6c6fe2e | note | – – – – – – – – – – – – – – – – –
c45c82af-0a1a-538a-b179-ff04a0d52a1d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5d38627a-8688-5610-84f5-38f15483354a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
6e3ce1d0-81c0-5f16-b4e3-03b737419a3f | note | REFERENCE: 610.26 (a)
e88a8d0e-a1bd-5b99-aa24-9d31cce29044 | note | – – – – – – – – – – – – – – – – –
de68321c-a2f4-57f3-a72c-e4c543be4e74 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
4eb45076-e07f-5325-9b4a-b4d791179296 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
997a73e2-d048-5eb2-abbe-3855fc5a26dd | note | ○ Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used.
00d4e383-283c-5fd4-a938-0a0854cd40d6 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
33358328-f834-56c4-96ea-594d5dbbd08b | textbox | Enter: Teambinder Hold Point Ref Number
70c5ebe7-2ad4-57de-8270-8afcc575b9ec | note | – – – – – – – – – – – – – – – – –
260debe8-4e30-5127-8908-4533e35c02a8 | note | METHOD: Document Review
5a06cef4-03b2-54ed-94e9-b8c7f4e64ed8 | note | – – – – – – – – – – – – – – – – –
1a5c9547-3c77-55e9-92c0-44d7c2a0287c | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
e39d93ab-8000-5ee4-abc7-36524ba5f89e | note | – – – – – – – – – – – – – – – – –
eac58f6b-88bb-5423-9d79-0dd47d357ffe | note | CATEGORY: HP
8cde9566-e707-585b-987d-88c86c18193f | note | – – – – – – – – – – – – – – – – –
dc93c961-1d39-5622-90bf-772c02adc55f | note | RESPONSIBILITY: Nominated Authority
65fe747d-f01f-52df-a807-4452b4e2be59 | note | – – – – – – – – – – – – – – – – –
0e796ffc-091a-5027-a4c9-e95ac2325c50 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
1b0199d2-e5d6-5171-8071-8133ae221ec7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
5b0f2d95-270d-5f91-ad94-1b834f5dca4e | note | REFERENCE: 610.17 (f)
bbb339dc-498a-50f8-b9f8-37f829c242aa | note | – – – – – – – – – – – – – – – – –
c9cd3752-b65c-562c-b818-eeb9dd2fafb6 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
10819e99-a1ff-5e1f-8347-6720a1fc21d6 | textbox | Enter: Teambinder Hold Point Ref Number
9a404f9c-3de8-58c4-87ad-42495af812d3 | note | – – – – – – – – – – – – – – – – –
0eaabbf7-3c33-51ad-9e4a-27e3e15db7b6 | note | METHOD: Document Review
40fd6056-789c-5cdb-8e8d-9aeaa1e1eee6 | note | – – – – – – – – – – – – – – – – –
c7a312df-41d0-554f-b4cf-bf35eef3c743 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
d9b56557-891a-5861-bc36-f47b641ac1b9 | note | – – – – – – – – – – – – – – – – –
28ba91a0-f68d-5130-a1f3-27a12420224d | note | CATEGORY: HP
60a57c11-7377-543b-8a25-2a892d4467d4 | note | – – – – – – – – – – – – – – – – –
11e99c19-44ef-5436-ac14-8ac7f0a3c22d | note | RESPONSIBILITY: Nominated Authority
3501cc85-5e11-5e11-9464-baa7d57adccf | note | – – – – – – – – – – – – – – – – –
327d0001-d21b-5dbe-8189-f09823506f48 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
31bcef47-1bc1-540f-9325-2471ec9a77eb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
dd443fb9-51e8-5ad5-839a-c5d0b9c7f12b | note | REFERENCE: 610.23 (d)
054e1b58-60bc-557f-8b2e-495e0be6c9eb | note | – – – – – – – – – – – – – – – – –
ef1f9f1e-4b34-5e34-9779-8682d10cce4f | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
a69ae6cb-e467-5ba4-9244-c17a0d88145a | textbox | Enter: Teambinder Hold Point Ref Number
50d7dd80-b485-58ef-8a6b-2b59853501c4 | note | – – – – – – – – – – – – – – – – –
edd9f899-9ea3-5e42-ae54-ef6753b3a879 | note | METHOD: Document Review
b5053cfa-5d3e-50c4-a881-7a2b1ee69f6e | note | – – – – – – – – – – – – – – – – –
85b1c2d4-1ddb-531b-b9f6-822710ec93e5 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
ee93496c-6067-5591-b83a-48a186ff4955 | note | – – – – – – – – – – – – – – – – –
9a967ea1-5b6c-54b8-a1c7-962a256a3839 | note | CATEGORY: HP
ed617d64-f34e-5d5f-9cc1-7f254f49b0c7 | note | – – – – – – – – – – – – – – – – –
d378f76c-83ce-5f5d-b2f2-8ee2abcb0443 | note | RESPONSIBILITY: Nominated Authority
7192da8c-e9a0-534b-a183-012ae759de55 | note | – – – – – – – – – – – – – – – – –
932d0359-184a-5888-b658-2470fbe74618 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c725cf19-f8b8-546d-af47-085c495582a2 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
3bb16a2e-3283-54da-a55e-b1af4f69b136 | note | REFERENCE: 610.18 (a) (i)
7aa79323-b9c9-58b2-bfb9-9d9938eacfb3 | note | – – – – – – – – – – – – – – – – –
9b761ed8-1ead-5513-9240-d668371734be | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
6ed5a249-8c35-5aa2-8cdc-b647e59e0c24 | textbox | Enter: Teambinder Hold Point Ref Number
4f3ed4f8-b389-5d1c-a6d3-79d94feb46d1 | note | – – – – – – – – – – – – – – – – –
e6c8f141-d297-51d5-b157-929bb66d0c7e | note | METHOD: Document Review
64b3edbe-7ea7-537d-9f70-69d050357fb9 | note | – – – – – – – – – – – – – – – – –
9d83b6fc-20ea-5435-8b30-98d0254e722b | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
83cd0803-200f-5809-8364-ff91c754b0dd | note | – – – – – – – – – – – – – – – – –
3ff17ddd-915f-5919-b9d7-9af5688d20c1 | note | CATEGORY: HP
37d78bd9-4907-500c-8d2f-e361a15b28b7 | note | – – – – – – – – – – – – – – – – –
47d50a06-8ccd-5d29-8100-f461c8bf1631 | note | RESPONSIBILITY: Nominated Authority
e056df59-a916-5b12-be6b-2b904be166a2 | note | – – – – – – – – – – – – – – – – –
80194c35-5ca8-54e5-b756-fbb456f934f3 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
fc1f682e-cf3b-5202-9bf8-a4b0c3792010 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
865c5113-1727-5a61-983b-328345115740 | note | REFERENCE: 610.18 (a) (v)
8a3a6a12-8b48-5f44-adc2-5d2c66a6f151 | note | – – – – – – – – – – – – – – – – –
07c6d53e-86f3-5518-bc1c-3a650172c22e | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
af93aaaa-d95e-5831-8459-278134198310 | textbox | Enter: Teambinder Hold Point Ref Number
39484936-53a6-58b6-a2e2-454a17a83c49 | note | – – – – – – – – – – – – – – – – –
cddd39a5-aa25-5e9b-84c7-738da78b147a | note | METHOD: Document Review
ce572a31-0014-5476-ac9e-f48d2624829e | note | – – – – – – – – – – – – – – – – –
952c1ebe-0d17-5807-b0f4-4be86c7f8ab8 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
772d097e-3580-5d9d-a173-75c4a10a4b52 | note | – – – – – – – – – – – – – – – – –
dfba63ae-ce43-55ee-a71f-cea528607646 | note | CATEGORY: HP
2fae6b30-e1df-535a-a48b-68a99e338da7 | note | – – – – – – – – – – – – – – – – –
6dd2da4b-a598-53df-a9dd-9a5470a4156d | note | RESPONSIBILITY: Nominated Authority
87d9e8f1-a467-5253-8b62-ef2704bd9fbf | note | – – – – – – – – – – – – – – – – –
590330cf-cc82-57c2-a96f-4be873a76659 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
8f96fe99-fc6b-52df-895c-3dffd3b5b47a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
8dde537b-ef57-5efa-bc80-8a439a284af1 | note | REFERENCE: 610.18 (a) (iv)
e39dc8eb-3300-5158-a9fc-007f2babf77f | note | – – – – – – – – – – – – – – – – –
976486a0-3a4d-5717-b931-3b7301231807 | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
55c96f04-853c-56bb-aa4e-9eaa8dc7027f | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
8e4397f6-8095-57cf-b6ec-843f6c7d1c9b | textbox | Enter: Teambinder Hold Point Ref Number
2cc0dd5f-c239-5d6b-be5f-1a6ef063cb2f | note | – – – – – – – – – – – – – – – – –
608c38ba-f90f-5e72-af0d-a23948c2fa07 | note | METHOD: Document Review
a029c3f5-7d4b-52b7-a006-ee5c3b5d4485 | note | – – – – – – – – – – – – – – – – –
3b3f445f-3c13-506e-8a98-3717eaa14f24 | note | FREQUENCY: Once, 1 week prior to placement of concrete
87099105-0059-53dd-a11d-a02b404057a8 | note | – – – – – – – – – – – – – – – – –
7f6b05f2-cef5-5973-b8e2-35344420a50c | note | CATEGORY: HP
12aee24d-9bac-502c-9231-42d860777943 | note | – – – – – – – – – – – – – – – – –
01f43475-4aee-56b8-8d10-0762228ff401 | note | RESPONSIBILITY: Nominated Authority
2dbccacb-f0bd-537c-ac9c-b5b956ba9014 | note | – – – – – – – – – – – – – – – – –
cbe71a3e-5d7d-5e81-a099-e9cdb9a39611 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
58c3fca5-a207-5c5b-9b79-5cb51066c3bc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
537adb6c-a6ec-5395-8a06-e905c592f41a | note | REFERENCE: 610.17 (a)
17af61b4-8c37-5089-a0f3-0b0bae6e66bf | note | – – – – – – – – – – – – – – – – –
cf863cfb-f35d-5d09-bcf6-5922135a47f0 | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
5e48d6af-1505-5eda-85a0-b1e9c8aaaedf | textbox | Enter: Teambinder Hold Point Ref Number
9e2d4572-d55c-542c-a4cc-31e01d194fdb | note | – – – – – – – – – – – – – – – – –
19439da4-7a55-519a-88bf-cefe0bd7f82e | note | METHOD: Document Review
f3c2ec95-93e7-565f-b659-100da54f062e | note | – – – – – – – – – – – – – – – – –
93baec44-4e61-5144-b52c-7f8ad78793da | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
e33d1fa1-d161-53c8-bfe9-4af03ecae850 | note | – – – – – – – – – – – – – – – – –
c3b9a27e-f22c-5a9a-ac99-3f708f347599 | note | CATEGORY: HP
d85c0eed-0ed1-5580-82e0-6487b32c67b9 | note | – – – – – – – – – – – – – – – – –
135ce26d-8920-5f74-bbf5-1120788cf82d | note | RESPONSIBILITY: Nominated Authority
b1a29fce-ad91-5ad0-b067-fb93732dfb7a | note | – – – – – – – – – – – – – – – – –
4941cf49-9321-57c6-9eda-9749170e80e0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
cc75e4c6-753f-5038-8f06-f085fff979e1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
0059ee76-bd72-51a7-924b-9f449a3dbfc3 | note | REFERENCE: 610.23 (a)
db780c17-ae88-5bcb-a82f-8794d1736d0f | note | – – – – – – – – – – – – – – – – –
4be02d95-1e9b-52b9-a1ad-9329237cb503 | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
7590bc5f-625d-5327-9577-3cff46c85bc6 | textbox | Enter: Teambinder Hold Point Ref Number
734a2722-b346-5eb1-8d30-9bf3ee2f3a69 | note | – – – – – – – – – – – – – – – – –
8557e966-c2d4-5c78-91da-0b0178d1ba0e | note | METHOD: Document Review
a48893c7-b6e1-51e8-8d58-3791c221650a | note | – – – – – – – – – – – – – – – – –
921d376c-26ce-514f-a99b-916e3ebca288 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
5f5e91cf-2a6a-5b6e-b505-7e28bbafef63 | note | – – – – – – – – – – – – – – – – –
fab206d5-2be7-5c0b-a67c-8e4673eb20f1 | note | CATEGORY: HP
32738457-53ab-5656-9be4-9d534d197725 | note | – – – – – – – – – – – – – – – – –
0eef0e54-37af-5e05-a69e-27c40ed58b61 | note | RESPONSIBILITY: Nominated Authority
ec4f8989-9c49-511f-800d-78144aab0d1f | note | – – – – – – – – – – – – – – – – –
d597bf4a-f610-58e5-9a8f-c5e8b38c66c3 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
b5c0daa2-6456-5744-9abb-553b87d15ced | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Concrete Drilling Procedure
4453b6b2-c52d-5f48-8fc3-794c796c8431 | note | REFERENCE: 610.46
8d11747f-9d06-5f0b-93bd-c1305fb91273 | note | – – – – – – – – – – – – – – – – –
aa29123c-fea5-5ed5-98b0-792aa29a1e40 | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
ef620911-cea5-5121-9a82-dcaaaf1a6cb0 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
295f1dfe-12d6-556e-b98e-52b3cb21f483 | textbox | Enter: Teambinder Hold Point Ref Number
58083a15-a415-5086-9c2a-df66269725ef | note | – – – – – – – – – – – – – – – – –
3414c841-25c3-5fa3-b4c1-dda0b38acc84 | note | METHOD: Document Review
12db835c-5e2d-592f-9be6-e426daba0342 | note | – – – – – – – – – – – – – – – – –
99ac93ee-9668-5f50-89a0-89ed281a7e92 | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
169c1787-3b49-57cd-ab45-ee369fa621d7 | note | – – – – – – – – – – – – – – – – –
3e3ce1ba-fcd8-5d9c-8a25-a0e0e8f4039a | note | CATEGORY: HP
6bc96472-74de-5c41-a382-23e52d51f5c3 | note | – – – – – – – – – – – – – – – – –
e4e113eb-57ec-56ff-afe2-be61a7614d47 | note | RESPONSIBILITY: Nominated Authority
5badbbb2-d7fb-5ebe-b343-f255766b11fa | note | – – – – – – – – – – – – – – – – –
cd9a2c53-68bc-5048-b4c3-28308145b160 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f770757d-04da-5ee8-b843-c04f3fea85a8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Temprature difference measuring-Calibration
fa36e064-e342-5941-9825-b9293bf391cd | note | REFERENCE: MRPA Quality Management Plan
fb44124d-e62c-515e-8668-f375b25cc3ee | note | – – – – – – – – – – – – – – – – –
972a5cfa-b12c-515d-91f5-5948325f5416 | note | ACCEPTANCE CRITERIA: Calibration records for Themocouples are valid and up to date.
68845afe-7e60-51e5-a87a-19e025aa7fe7 | note | Attach: Calibration certificate
5c42b84b-85bc-5d31-a965-16c0739d7d85 | note | – – – – – – – – – – – – – – – – –
1f3e4bbc-3da3-5bf3-a5b9-6d071bfee8ea | note | METHOD: Document review
d534e0cd-fc77-52be-88f2-4ee449536ac9 | note | – – – – – – – – – – – – – – – – –
44ee315b-c39d-5ebd-8349-6aa781242240 | note | FREQUENCY: Where applicable
5053a5cb-eb42-5835-8df9-5ee975f508c8 | note | – – – – – – – – – – – – – – – – –
2433afce-8613-55c5-a58e-c600d3ea82dc | note | CATEGORY: HP*
e360394b-85f3-59fe-a343-f84f99e3b7c8 | note | – – – – – – – – – – – – – – – – –
0b262405-a4fe-5e90-b5cc-050ffb736906 | note | RESPONSIBILITY: PE
71b07c55-b4a6-55e2-a844-7ee68cdb6c19 | note | – – – – – – – – – – – – – – – – –
001624e3-d9cd-595c-a428-e1a8dde588ec | note | VERIFYING DOCUMENTS: This ITP Signed Off
58c963fb-2861-57c8-b55b-bc6d4e95545a | date | Date Completed:
| checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
3e74be04-2cf9-5983-957e-527296f077c0 | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
ae06e9b1-43ad-5609-9a51-f86d1eaa5ce9 | note | – – – – – – – – – – – – – – – – –
c216e302-b1cb-5d55-a241-84a435a312cd | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
e213a39b-da34-54df-bb01-24fe0abec9b6 | note | – – – – – – – – – – – – – – – – –
e6a3b632-6f9b-5125-a042-a23612d9646e | note | METHOD: Document Review
c54451e7-1874-5f83-9d05-6e52213db480 | note | – – – – – – – – – – – – – – – – –
357e33a9-73a6-594d-b63d-c9a377d0544c | note | FREQUENCY: Where applicable, once, prior to welding
2b309e67-7427-5434-983a-cbcfbfbf7d8e | note | – – – – – – – – – – – – – – – – –
9f90c1c6-a5d3-5fd6-a45d-efce358f2ded | note | CATEGORY: HP
958eb80c-68b4-567d-adfc-7d2a554754d5 | note | – – – – – – – – – – – – – – – – –
bd65da05-16cd-54f6-b21b-e05305f5e077 | note | RESPONSIBILITY: Nominated Authority
a4e5586f-2702-5414-b56f-44905599ae50 | note | – – – – – – – – – – – – – – – – –
44705d6a-1488-5b87-a50f-9eb5ce7e47c4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5c66912f-2104-5f13-8159-ec0d05271425 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
01c651bb-7a4f-5df0-9291-67dc5a934917 | note | REFERENCE: MRPA Quality Management Plan
d512fa7a-a63c-519a-af43-4548403e616f | note | – – – – – – – – – – – – – – – – –
691e7aef-ec07-5cb9-8529-47a0f22c51c9 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
37bfb56b-baad-5de2-8f6c-d223d381aaa3 | note | – – – – – – – – – – – – – – – – –
6067c163-75dd-5df4-884a-53c0c5a09147 | note | METHOD: Document Review
6f39bdf1-4588-5243-828f-569be76b425c | note | – – – – – – – – – – – – – – – – –
f40ee8c3-86e2-5878-b594-9e4eb922aae9 | note | FREQUENCY: Prior to starting Works and at regular intervals
f76b11c3-4b2c-534c-8add-fd4af6178e7c | note | – – – – – – – – – – – – – – – – –
1468a1de-44e2-5baf-8361-e6f5a12854f5 | note | CATEGORY: HP*
b3b9eb62-06e6-5c97-bc97-be43c0f05ab6 | note | – – – – – – – – – – – – – – – – –
b4f482c2-dca8-5c4f-919a-a3da83ffb65e | note | RESPONSIBILITY: All
5a5222c5-d058-5914-bde9-0950c36ff469 | note | – – – – – – – – – – – – – – – – –
fa1e8e43-eb75-5c78-aca6-99c85aba898b | note | VERIFYING DOCUMENTS: This ITP Signed Off
32fcae49-d134-5450-a13a-8a5e57592250 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
e9aa9197-1a50-5210-be0d-fe25935e81fe | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472
7011ef0a-0ced-51f3-b6cd-f0f6146d783b | note | – – – – – – – – – – – – – – – – –
ac94741c-da42-5c70-af2d-07b163ff2b4f | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
44d3be9a-19d3-5a97-aecd-45827864041e | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
f6f93a28-6684-5d74-a8bb-2cc38ceec0b3 | note | – – – – – – – – – – – – – – – – –
a4d1a88d-e45b-54fb-9172-83d5813b752b | note | METHOD: Measure, Visual
fcea2ecb-0642-5997-9955-8a108d25ac23 | note | – – – – – – – – – – – – – – – – –
12751e15-ee2e-58a8-ac9f-703ff9dae24c | note | FREQUENCY: Each element
e8b79840-6e78-526b-9384-1388104c4d98 | note | – – – – – – – – – – – – – – – – –
cf082f96-0022-53a6-a0bc-f09eac262712 | note | CATEGORY: IP
d088766f-7503-5ef0-817c-e65fa19bf4bb | note | – – – – – – – – – – – – – – – – –
e752a94a-dbcc-5cb1-b9ca-e3723686e2fb | note | RESPONSIBILITY: Surveyor, SE/PE
f6742a8e-5475-524c-b08e-851527c6fff5 | note | – – – – – – – – – – – – – – – – –
1d422bc3-9a7b-5ae3-94e8-a2f4b340976f | note | VERIFYING DOCUMENTS: This ITP Signed Off
61502484-0b0e-5f57-a49f-84a2bc018b14 | date | Date Completed:
| checkpoint | 4.3 Piles - Completed Prior to Construction of Pile Caps
5cff02df-3057-5e4c-9eae-e7882c637383 | note | REFERENCE: IFC Drawing
e0049fce-b933-5784-90de-88bd1c353347 | note | – – – – – – – – – – – – – – – – –
3f403321-0f30-56d1-ba0e-228560d4367c | note | ACCEPTANCE CRITERIA: Related piling Lots are closed.
61154a99-00b2-5457-9b32-ef0ecf08a4a0 | note | – Pile design strength is achieved
37f4226c-ec38-567c-952a-174f68455921 | note | – Integrity and Dynamic tests performed and interpreted (if applicable)
4a0cb65d-c3b4-5f37-a6a6-f26168e55512 | note | – Pile is broken back to the design level
8ade11ab-00cc-55b3-90c9-f01becac527d | note | – As-Built Survey performed
8cd6780f-6744-5fb9-8087-c37334fa140c | note | – Related piling NCMs are closed
90dedd97-4e1d-5d1c-ac0d-ee4c7cdcddbd | textbox | Enter: Relevant Piling Lot Numbers:
87717015-e93e-5a40-bbbb-0ef4c5ce78df | note | – – – – – – – – – – – – – – – – –
956964aa-cdcd-55f2-b991-4f56691068e0 | note | METHOD: Document Check
27abf0ee-487b-5449-9859-50beeb477bcf | note | – – – – – – – – – – – – – – – – –
feabe1fb-c47d-59ca-bac9-1eeac1426319 | note | FREQUENCY: Each Element
4874a157-70bd-5f42-9101-1f19893e208f | note | – – – – – – – – – – – – – – – – –
39914738-48a6-5624-9d95-f90dde0b4bdf | note | CATEGORY: HP*
63521a8b-70dd-5d19-8a6c-e3073df765c2 | note | – – – – – – – – – – – – – – – – –
99060254-d75d-5dc2-b4af-c0d381a43f4b | note | RESPONSIBILITY: PE
c4069790-616c-5d92-844a-ad9af7a1c045 | note | – – – – – – – – – – – – – – – – –
674bf0b0-4264-5d4a-89c7-4220e00edf27 | note | VERIFYING DOCUMENTS: This ITP Signed Off, Piling Lots Closed-Out
969bb123-bce2-5a4f-b442-c7eee801dd29 | date | Date Completed:
| checkpoint | 4.4 Excavation support
bdd92dcf-8def-54e2-9f04-1fbeb578d4e8 | note | REFERENCE: 602.02
cb08bb6c-f43b-5962-a2ea-0154dd28d56d | note | – – – – – – – – – – – – – – – – –
0b34f6a2-7566-5f5b-ac28-ca6fc9cb1e62 | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal. Where applicable, a PTDT approved for use.
586da738-472f-5a86-9b3b-b11c3ba5733b | textbox | Enter: PTDT Ref No.
8ef5cc89-90a9-5fd2-a9a4-a0994c6780d0 | note | – – – – – – – – – – – – – – – – –
03f56ffd-2f26-5e22-adde-d89e89a06075 | note | METHOD: Document Review
ce9d9696-0299-5ca1-bd00-e75a4aabacf3 | note | – – – – – – – – – – – – – – – – –
d3b21cce-0cf8-5953-bf35-e2ac1087f78e | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
732f533a-17e6-5b62-973d-949a66e9e76c | note | – – – – – – – – – – – – – – – – –
19bad036-6825-599e-9034-03d3613a3a90 | note | CATEGORY: WP
98b72a25-5782-5dbb-a63b-d4afc7df4b26 | note | – – – – – – – – – – – – – – – – –
edf81731-7d5a-5726-9739-edb459a1c2d2 | note | RESPONSIBILITY: SE/PE/SPE
fcd6f22f-3a73-5c93-a21b-81ea25c521d5 | note | – – – – – – – – – – – – – – – – –
703a12cd-1f5e-5791-b882-5391ea9d34aa | note | VERIFYING DOCUMENTS: This ITP Signed Off
394972e5-c783-5b17-b963-71e2998460c2 | date | Date Completed:
| checkpoint | 4.5 Excavation Inspection
709527a8-3e92-5425-a790-a0719c74cb99 | note | REFERENCE: 602.03
92589bcf-81d7-5630-955c-e26cf7dfd5e8 | note | – – – – – – – – – – – – – – – – –
88425b6b-20ba-5d6b-8a6e-be1c2d018377 | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
bbe5b5d5-6160-5708-bc3e-ac847d97f255 | note | – – – – – – – – – – – – – – – – –
6494bbb0-f6c0-533e-aae3-50219f417793 | note | METHOD: Visual
99d80111-0a82-5676-8768-ce197b5cc335 | note | – – – – – – – – – – – – – – – – –
31bd2386-02ce-503a-8f11-6fec6be6612d | note | FREQUENCY: Where applicable, prior to placing blinding concrete
f5cf7f0c-ab5f-520e-ac7a-dfd7ce674a25 | note | – – – – – – – – – – – – – – – – –
d9c4da3c-6691-5cb9-8aed-7fc11a29e1d8 | note | CATEGORY: HP
51947593-96fb-5511-bac5-275e18b8b57c | note | – – – – – – – – – – – – – – – – –
a343a525-889f-5905-9298-05a9e5307033 | note | RESPONSIBILITY: Nominated Authority
bc53246f-eeb4-517f-98fe-09f511db3e84 | note | – – – – – – – – – – – – – – – – –
8d022393-53b6-57e4-bc5d-e3fef6dff509 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
8675b58f-d5e5-5345-abb4-d983031f8c12 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
4b0c3059-3e2b-59ea-93cc-5a1aab6ffd7e | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
b4282e1f-0312-5a76-85bd-06ec2ba51e11 | note | – – – – – – – – – – – – – – – – –
dd4a3b57-f0b1-59a4-a48c-a814ee4c7060 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
e942c15d-71cc-5671-a76c-9e2504f7b782 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
2b26b8dc-e473-559d-acd0-88a38ba83b6d | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
5f9782b1-99d6-50ec-beaf-c05166d06c5c | note | – – – – – – – – – – – – – – – – –
b527e63d-e6c6-54c3-8dfa-2919ba835290 | note | METHOD: Document Review, Visual, Measure
ae76910d-9818-56aa-a52c-da4e8bfb53ff | note | – – – – – – – – – – – – – – – – –
710c142d-1f89-5f32-b28c-63ba0ccccc4a | note | FREQUENCY: Each type of element
45fcc732-cc27-53f4-82d1-8d512963d34c | note | – – – – – – – – – – – – – – – – –
607d5c23-eb97-5431-a3ae-05beca1a90ae | note | CATEGORY: IP
051cffb6-66b4-580c-aba0-ccb04970aa52 | note | – – – – – – – – – – – – – – – – –
1a766206-c166-5cf1-8287-f39bf297eee7 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
be91c0e9-36f6-5a17-89c3-550f8216513f | note | – – – – – – – – – – – – – – – – –
8f7f487f-0f0b-5e03-b9e6-092fca2eeaaf | note | VERIFYING DOCUMENTS: This ITP Signed Off
540250b8-4169-5c7f-bdc4-8fe6b61083a0 | date | Date Completed:
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
15d673eb-c71c-5de5-9530-f2ffe2321e1c | note | REFERENCE: 614.08
25295e0b-5aa3-5321-908c-9ff9e92b9f17 | note | – – – – – – – – – – – – – – – – –
f22fc474-65f3-5539-b2b8-ab1a9f393e76 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
da3a45d5-410f-52c5-ade4-05068997d5de | note | ○ Pile caps with heights greater than 2.0 metres
7423e30a-f039-5056-bc1c-f65159ff837f | note | ○ Any member for which self-compacting concrete is proposed.
e6224a45-4cd8-5a82-ad44-b037c11d3296 | note | Attach: Attachment A
a337c332-fa4d-5a11-ad3d-2db97026de0e | note | Attach: Attachment B
147d0441-c604-5b07-b2cc-31b0197a52a9 | note | – – – – – – – – – – – – – – – – –
b8aeaa42-4fbf-5558-910f-10e7726897cb | note | METHOD: Document Review, Visual, Measure
86eb0fda-4195-5a28-82d1-7fed7235eca2 | note | – – – – – – – – – – – – – – – – –
a9da7a77-85d6-52d0-b4d0-d5b42bf6b2a6 | note | FREQUENCY: Each element (where greater than 2m)
a74d7a3f-0c18-5ea7-a849-92e4b4a95737 | note | – – – – – – – – – – – – – – – – –
a58c27a6-76b8-5625-b0dd-671541074f8d | note | CATEGORY: HP
9642a304-485d-595e-990b-429c2658bbf1 | note | – – – – – – – – – – – – – – – – –
7f88f279-ee7d-5160-91cf-2cf4e4e6bdf9 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
29dd9c67-fb84-5c0d-a88a-529d5897b535 | note | – – – – – – – – – – – – – – – – –
6d1f6888-7df4-5f5b-890e-c6623986b2ec | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
2e9da57b-8a7c-5605-b03e-6225c7a7564e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
bc3b7a42-8f16-5a89-b080-f988c4ee8cfa | note | REFERENCE: 614.08
f0909d00-de42-50c2-90d6-bb424526e4de | note | – – – – – – – – – – – – – – – – –
2031dcb9-3272-5d90-b6d9-f965e33c86c2 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
c924bf7c-8b77-5cae-bfca-074567470bfc | note | ○ Pile caps,with heights less than 2.0 metres
29c79e9e-5d46-5e0f-bcf9-518b817c06d4 | note | Attach: Attachment C
904afa4f-0a07-59e4-976d-bd92dfaedf0f | note | – – – – – – – – – – – – – – – – –
c544a07d-0789-585f-89bd-d021365d8675 | note | METHOD: Document Review, Visual, Measure
3512b01c-7ae9-563e-b136-ffa382a00d26 | note | – – – – – – – – – – – – – – – – –
766d1fec-73a0-539c-a3fb-41aeb035d565 | note | FREQUENCY: Each element (where 2m or less)
ca0f643f-056a-5bb4-bb88-47d1f5d009a6 | note | – – – – – – – – – – – – – – – – –
58f72beb-2989-560b-938e-954fc43a2e36 | note | CATEGORY: HP
046e5053-758b-52dd-b6ba-27ab387e2fe4 | note | – – – – – – – – – – – – – – – – –
08ae2bec-d976-568b-86d2-8912a3e03919 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
51449e44-6417-57b0-9b7d-9fdeef388d07 | note | – – – – – – – – – – – – – – – – –
d515e061-1a75-5b23-a54a-086d3901a56c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
27c34810-88ba-57ed-a971-20c5a4dc2651 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
a1c9e217-fcdf-5f3e-96af-0d04e076777d | note | REFERENCE: 610.47 (a) Table 610.472
01d19e9a-f8f1-57cb-af0c-98152eefdab3 | note | – – – – – – – – – – – – – – – – –
79e76956-1a5f-586d-952d-3f1bf89d5486 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
65dcaea6-71fa-5b7a-a323-8c0109489a84 | note | – – – – – – – – – – – – – – – – –
13f0fcb8-04b7-5127-b937-f1df89ff7c94 | note | METHOD: Measure, Visual
3b65670f-d2e7-573f-ae36-dbc6db6d9ecd | note | – – – – – – – – – – – – – – – – –
b492de2d-783a-5c37-974f-a039e96074bc | note | FREQUENCY: Each element
e5743eef-9405-583c-bb53-c81bf69b53f7 | note | – – – – – – – – – – – – – – – – –
a53c95e2-cf16-510a-afc0-361661b0980d | note | CATEGORY: HP*
299b2931-84c5-5420-adfd-90c178918a20 | note | – – – – – – – – – – – – – – – – –
12237a6e-8537-52d0-99b9-10d88e57dc9b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
654ad862-ff2c-5c01-8606-7e12c95be8b9 | note | – – – – – – – – – – – – – – – – –
afd8e860-9686-5563-9bd3-7574f8bbe77c | note | VERIFYING DOCUMENTS: This ITP Signed Off
5c9d1497-71be-5a6c-bde7-4e16505e5c83 | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement
169fb114-13ad-5bcb-ae68-0834c7ecccfd | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
e88e116a-c435-555e-ba8e-909ed165c166 | note | – – – – – – – – – – – – – – – – –
0fe3ee6d-6fe6-57c4-9c1c-5be2260ac9aa | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
97e3dc98-bb0e-585e-bfbd-d1aca42b2801 | note | ○ Projecting reinforcement is the correct length and location.
de39ccba-f4d4-5f6b-8b18-8764f492deab | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
468ae188-91f9-5735-88f4-7b188f185379 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
c0117e44-0dfe-5763-a8b3-70de3614904d | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
8aa8b212-7d84-5dc5-9aed-a6a0063d8ae5 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
fd2ddf52-0b0c-5c1c-85de-536f34a74c47 | note | – – – – – – – – – – – – – – – – –
413c1ab8-46e8-52e5-83e7-fb851a33252f | note | METHOD: Measure, Visual
7fda199e-08d4-56f6-bf22-5454bc764d01 | note | – – – – – – – – – – – – – – – – –
7484138c-b161-582c-843a-e43c0db6b8f6 | note | FREQUENCY: Each element
cdf2fe43-b86f-572a-9c62-108a6a36ba3a | note | – – – – – – – – – – – – – – – – –
ca26b1ab-2bce-5cf1-8c1c-906c517d2557 | note | CATEGORY: IP
f556660e-9116-5910-b717-593c96eb3c99 | note | – – – – – – – – – – – – – – – – –
8875fca1-bec4-54a1-8380-23ca52f20ecf | note | RESPONSIBILITY: Foreman, SE/PE/SPE
83898f7e-88db-5f7c-883a-8ec8ce243c65 | note | – – – – – – – – – – – – – – – – –
e6fc4aa6-b8e5-5e77-80ff-432e0260ea6d | note | VERIFYING DOCUMENTS: This ITP Signed Off
4e4b75a5-138d-5854-b44c-c5a255d829f7 | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
38ce53fa-d016-5295-9316-03d13b7c05bd | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
11847715-3429-51b9-a0eb-58bb3238392f | note | – – – – – – – – – – – – – – – – –
e387c32c-807c-5d01-846a-ba4b507b52e3 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
34feb54c-5a97-5333-83ad-e6a1e4983f38 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
3b60fa78-5d39-5198-b1de-c2a4218634b5 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
9aa24af1-1e36-544c-b9af-027bb3484130 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
e354e949-f117-59ee-b4b0-597bac763004 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
99df53b0-b4e1-5e65-8789-83b6ed03147b | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
6b652b88-9025-53f1-8bcd-79e60e3e5b09 | note | ii. Running dimensions of a group of the above = ±6mm
8773037c-4795-533a-a7d6-8dde12466f26 | note | iii. Ducts and conduit location = ±12mm
e9dd2fd4-1333-5a32-b691-40b0907aee6d | note | iv. Diameter of ducts and conduits = ±3mm
529e2556-6d13-5600-a15c-1197e7b5d4ea | note | – – – – – – – – – – – – – – – – –
2b780473-3798-5a8b-940f-66f47a87adbb | note | METHOD: Measure, Visual
de75a17b-00b6-5e4c-bfa7-c9530b37c9de | note | – – – – – – – – – – – – – – – – –
2296dfb6-08ca-546e-8cf8-076ac9200b97 | note | FREQUENCY: Where applicable, each element
303a149c-e7db-548a-8302-0055faad6aad | note | – – – – – – – – – – – – – – – – –
53b66f2c-b8f4-5009-bb42-ed343261fc2f | note | CATEGORY: IP
88020e01-1594-5e95-afa7-cca79881a4b1 | note | – – – – – – – – – – – – – – – – –
97094c75-3f55-59ce-a02f-99fe0321dfdb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
bfd28305-3ca2-59d3-8017-15efccac04dc | note | – – – – – – – – – – – – – – – – –
21780c99-9361-514d-ad0f-01922991080e | note | VERIFYING DOCUMENTS: This ITP Signed Off
27fe1c14-2b45-575e-986b-817263572836 | date | Date Completed:
| checkpoint | 5.7 Thermal Differential Monitoring
295e9482-be82-577b-8a79-f0b12f7a6966 | note | REFERENCE: 610.22
ba8a2640-c1f1-5374-a8ab-6172995e9657 | note | – – – – – – – – – – – – – – – – –
c0a2708a-7f0d-5858-8c23-54d0fecdcce7 | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
b4f6544a-6bd8-5bff-bdb5-e8943fac60f3 | note | Only applicable if the element has:
ad5ca6b1-c671-50f6-8ac7-a7871a07dc8a | note | i. the smallest sectional dimension exceeding 500mm
2479051c-c75d-5b45-bb18-ab279e383c0e | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
8bb50839-9d4a-59a8-942f-288b98bf787e | note | – – – – – – – – – – – – – – – – –
3e5f2325-e4ab-51e7-8b8a-be0ccfcf0722 | note | METHOD: Measure
a51c64ad-521e-5088-8996-2af3e47749d7 | note | – – – – – – – – – – – – – – – – –
08ab76e1-6d9b-5b96-9304-8f11fba28bf1 | note | FREQUENCY: Where applicable, each element
350548e9-5a92-5d30-a1c5-ce44606902f1 | note | – – – – – – – – – – – – – – – – –
536cb6a3-2ec2-5a2c-9c22-28a2a49c323e | note | CATEGORY: IP
0dcf4dbf-565a-59f3-bed7-d00f97595b48 | note | – – – – – – – – – – – – – – – – –
14cfad9d-ff00-5a8a-9b87-5641a2ab0b10 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5cab74ff-bd86-583e-aecf-a2b993176795 | note | – – – – – – – – – – – – – – – – –
0d364ff7-c4e9-5aed-98b6-62e93021097f | note | VERIFYING DOCUMENTS: This ITP Signed Off
d1ce9eca-ee09-5f1b-8c58-9f09082c76a3 | date | Date Completed:
| checkpoint | 5.8 Pre-pour Inspection
490c2fc4-5d76-58b7-b165-002865ecb29a | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
bcf16635-3cdc-5e01-8f7a-af0bca7a7dc8 | note | – – – – – – – – – – – – – – – – –
da4e69da-5735-5b50-8b5a-7397095a40b4 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
798d9bca-195e-5868-95d6-448ff694ad99 | note | ○ All foreign material has been completely removed from the forms.
2b445b25-c667-5b1e-b3b3-8d884391e123 | note | – – – – – – – – – – – – – – – – –
ce73a211-b8e2-5d54-8305-a9a7fa45597c | note | METHOD: Measure, Visual
7019365b-ed2f-53bc-bca4-ffbc4af1e24c | note | – – – – – – – – – – – – – – – – –
27f8e618-7842-5e1e-a910-cdf75bd49073 | note | FREQUENCY: Each element
c4d6394a-720c-5221-b838-7df34121bcd9 | note | – – – – – – – – – – – – – – – – –
2521b607-5337-55b8-8ed2-190611a17335 | note | CATEGORY: HP
4f6c39eb-f276-5548-91ee-abf32780a79a | note | – – – – – – – – – – – – – – – – –
9513cf9a-3184-5b3d-bd3d-6ac94000836f | note | RESPONSIBILITY: Nominated Authority
b2671d5a-7265-5486-98f8-6fda664649c4 | note | – – – – – – – – – – – – – – – – –
cbce3166-15f8-5302-92ff-53aa0df46dd4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c36c8511-3b19-5ff7-a794-9ff46be37d36 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
8d891a01-650a-53ed-bafd-a4dfac85d544 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
53b0ad40-21b3-575b-aa3e-255c1ebc2f0c | note | – – – – – – – – – – – – – – – – –
755a9b6e-9fa9-5cfd-bb50-939f609381a3 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
493e0dd1-94ab-5bf1-9de0-1fd3aa8f2bf4 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8591c6cd-b3e4-5017-9eb3-cd80e999043d | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
133e241d-92c2-5fe1-ab9c-fd130f693edd | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
bc639595-7260-559e-8843-e8f1d4c032af | note | Record: Required information on the Concrete Pour Record.
3d481ab8-6017-54e7-9930-7f4eb4fd435f | note | – – – – – – – – – – – – – – – – –
6acb1fdc-5d48-5d6a-8719-05a6f2277363 | note | METHOD: Measure, Visual
99f5970b-9a63-51de-ab76-ea8fb8836ade | note | – – – – – – – – – – – – – – – – –
b1a08e07-34f8-5d85-8bb0-a8de3326a7d6 | note | FREQUENCY: Each element
ce7a9ae2-d1f9-54bb-aac9-64cb778f200c | note | – – – – – – – – – – – – – – – – –
36f710e3-4ca7-5dc2-9d1d-f641cc8904dd | note | CATEGORY: IP
291f43d4-6601-5e2a-8b44-54047c2f1734 | note | – – – – – – – – – – – – – – – – –
11d26f07-0e3a-5b31-a47a-4afe4cf50557 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
73ecb994-1225-588b-b1a1-0a5740920af7 | note | – – – – – – – – – – – – – – – – –
8bfdbe64-8ce0-535e-9e62-0ba889074d3b | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
51219050-18bb-5ea3-9e12-0a5fb58cd41e | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
e47a285c-4d4b-5342-a3c3-b9fb83322695 | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
8fec8d57-b327-5767-bbd3-c241775ee222 | note | – – – – – – – – – – – – – – – – –
673daaad-f361-540d-a7d4-6d16624e616c | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
b8be0292-fe73-5518-9627-0b648ae0239a | note | 0m³ to 10m³ = 1 sample
245b8276-e1c0-5131-ab3f-27abc3737c29 | note | 10m³ to 25m³ = 2 samples
e71a7c76-f380-5433-965f-bcc404e17e6e | note | 25m³ to 50m³ = 3 samples
89fcb291-9ef6-5a9a-b41e-db4f6f11a7dc | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
3957b494-8a8a-5554-8f6d-8dadcfcf6872 | note | ○ For each additional 50m³ and additional sample shall be taken.
b0f227a0-4e80-546f-974d-574023eab261 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
6fbb32d6-eb10-5042-b2a9-7867094851dd | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
e8df9fda-fdee-5c29-9f93-6d1170faf9a5 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
5d53382a-5f96-5b50-92f4-2b48e7e00a85 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
1f593956-73f1-552c-b6fe-7e2b0b31b002 | note | Record: Required information on the Concrete Pour Record.
8f2117b7-8730-5baa-badc-e12aea994010 | note | – – – – – – – – – – – – – – – – –
1f95fefa-ce1e-589b-94a6-7919596665b6 | note | METHOD: Test
3eb92c4c-b358-580b-ba5f-899c0b7b6edb | note | – – – – – – – – – – – – – – – – –
0cca850f-001a-5d73-8203-f642d2087a5f | note | FREQUENCY: Each element
cb4aad9a-3ded-5f07-b8f1-08a18b19b3b7 | note | – – – – – – – – – – – – – – – – –
b8621594-6a08-530d-ac68-160226f1b992 | note | CATEGORY: IP
6392e9ac-7674-5ad9-bd43-f6215bccd3fa | note | – – – – – – – – – – – – – – – – –
e04dedd4-e368-5f39-91ec-e8ae8f36f794 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
ac2a10d2-8b5d-5dec-b342-2755113513da | note | – – – – – – – – – – – – – – – – –
d9cfe656-c092-5e1a-8e68-6c37bfeb9b1b | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
9340b217-5d17-55f5-996e-14d4bbad33f3 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Slump
95f7e703-c0a1-515e-94a3-d8aec9bcf888 | note | REFERENCE: 610.16 (c)
939c21dc-10a1-5ea7-b816-41865a7adc4e | note | – – – – – – – – – – – – – – – – –
2ea8807b-77ca-5860-9578-2c1168c117ec | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
9113e36a-1caf-5e16-9520-15dbec0e9bbf | note | <60mm = ±10mm
057e2e59-8a02-5127-8ae5-30256ea937ea | note | ≥60mm to ≤80mm = ±15mm
4ef62e6c-e57f-5c20-8ac2-1fcba00164ef | note | >80mm to ≤110mm = ±20mm
463245dd-39d8-53dc-ba2e-ee79373bf385 | note | >110mm to ≤150mm = ±30mm
5517c4bf-c628-5243-9cec-76568fd6b415 | note | >150mm = ±40mm
a9350005-c4fc-5d6f-a129-a23619c4d475 | note | Record: Required information on the Concrete Pour Record.
424036ec-91b6-5e5a-97a4-ae720d576b90 | note | – – – – – – – – – – – – – – – – –
d3c6f689-5304-50b4-b39c-90a9f2e1385a | note | METHOD: Test
fcca32ca-d338-5fc8-8aa4-a9bb8ca08637 | note | – – – – – – – – – – – – – – – – –
4d320755-8e01-5562-9fb5-3237d9379ca7 | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
f9a75554-4093-51f6-a692-cb53dc0e8d47 | note | – – – – – – – – – – – – – – – – –
5a3f3dd5-99b6-57ff-996a-dc4ac69a8f73 | note | CATEGORY: IP
11adf8e2-1cbd-5801-847d-eab9ed8cf151 | note | – – – – – – – – – – – – – – – – –
678a01f4-b8e0-5033-bf51-cf1515020ed5 | note | RESPONSIBILITY: Concrete Tester
9a76ca9e-9657-59bc-93a0-d01cc7b21b1f | note | – – – – – – – – – – – – – – – – –
49242aba-0ecf-5800-a094-b1bd5e962d83 | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
3d17259b-de22-5dc9-b12b-708b8f5bd3a0 | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
2bc6852b-96b2-5efe-9cf0-3d808b34657a | note | REFERENCE: 610.13 (b)
4ec471b2-b4a0-5242-8530-2f631c6a6a7f | note | – – – – – – – – – – – – – – – – –
78a7d2dd-0522-5204-99cd-c8f6a13117bd | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
696a5ffe-fbf1-5929-a2fd-b2f4d81e1dff | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
a6fd2e28-edd6-56c1-87eb-2e5fb81be7ae | note | ○ Passability = ≤10mm (aggregate height differential)
f611ece4-431f-581d-b902-b5a24ffe3190 | note | Record: Required information on the Concrete Pour Record.
6eec8e5e-2177-5b59-a7ea-c8678c33d986 | note | – – – – – – – – – – – – – – – – –
0bae0e43-0a19-59ae-86c3-366fb43183c6 | note | METHOD: Test
c3ad13a8-fc2e-52bd-8560-934f8bdad40a | note | – – – – – – – – – – – – – – – – –
00800c62-92e3-59ee-acca-a0e3f19481fe | note | FREQUENCY: Each sample of Self-compacting Concrete
394369e1-8d2d-504d-851f-e00a41ec7523 | note | – – – – – – – – – – – – – – – – –
9549e3f3-6bd0-5377-affe-84316eca9afc | note | CATEGORY: IP
ba08f6d7-e40f-577a-b0a1-56f12da31faf | note | – – – – – – – – – – – – – – – – –
14a1c3ff-19eb-5a46-9b9e-75314ad668e6 | note | RESPONSIBILITY: Concrete Tester
23c80ff1-e056-5515-a01e-9e7ac005fd42 | note | – – – – – – – – – – – – – – – – –
df258501-3653-52e4-a02b-131d4308d7bc | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
920db69b-6a1a-50bb-bc71-ee069b6ed87a | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
fcb36d3f-0809-5dd0-a138-2cd4eeb4b77e | note | REFERENCE: Site Sampling & Testing Procedure
90e43887-87cf-56a8-830a-f037db3a1f59 | note | – – – – – – – – – – – – – – – – –
d63e0724-e06a-5085-ba75-3800a60e3dda | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
594745a7-399e-5120-8a3c-b0a6ebfbdd2b | note | Record: Required information on the Concrete Pour Record.
5c28a684-f84c-5196-b352-580727ba9f1c | note | – – – – – – – – – – – – – – – – –
820fda40-b7a8-5bf4-9e08-c9553bca913a | note | METHOD: Test
7385d12e-54af-5240-ba2f-a424724c6198 | note | – – – – – – – – – – – – – – – – –
6aa07a05-8cb5-5b1a-9512-fbc4bd272982 | note | FREQUENCY: Each sample
174f43d3-bbe8-5058-93dc-8ee2f07f223a | note | – – – – – – – – – – – – – – – – –
77cdb8c7-6481-5374-bc9a-164d430c3176 | note | CATEGORY: IP
b9243425-cc7a-5cf9-a4b6-8b889f4a1ccc | note | – – – – – – – – – – – – – – – – –
6b5e4ba6-81a8-546d-b837-4f8fdaedcfea | note | RESPONSIBILITY: Concrete Tester
d1a5d4f7-fcf7-5004-93f1-1e69870967a5 | note | – – – – – – – – – – – – – – – – –
688fb8a0-242e-5100-8be9-70e35e38f121 | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
6f5dc458-4953-5ea4-b23c-cfeccf1780f9 | date | Date Completed:
| checkpoint | 5.14 Supply & Discharge Rates
0ae15405-76ae-569e-aaaa-26dc757eb9d4 | note | REFERENCE: 610.13 (a) & (f)
77141fd7-fa61-575a-9ee0-b5e75f35be2c | note | – – – – – – – – – – – – – – – – –
611c5833-7e0b-5ee2-bae6-63f8b935a344 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
5fd8e20a-67e0-5537-acb5-1ecddd767563 | note | ○ No water is to be added once discharge commences.
22bf9342-6a42-5223-a54a-ad44c04478af | note | ○ Maximum time between batching trucks is 25 minutes.
49eba8d8-12a5-5f7f-af4e-b7499c009178 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
bb93a7b4-a4a8-54b7-861e-e01573756b85 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
80c3ad78-72b5-5f9f-9c24-d94e1b54277d | note | Record: Required information on the Concrete Pour Record.
51d75ad5-e7b9-5d57-ba67-56a7f07fee43 | note | – – – – – – – – – – – – – – – – –
312628cb-3f69-572e-a602-6a43098ba5f3 | note | METHOD: Measure, Visual
0dce991d-0aaf-521c-9379-9c10b8d0e50d | note | – – – – – – – – – – – – – – – – –
6c2116f9-05e8-58b2-a900-1a458d35d31a | note | FREQUENCY: Each load
5c2a574f-50cc-56f7-9e72-b834bff7573a | note | – – – – – – – – – – – – – – – – –
72ae9ae8-17c2-546c-b200-1a5bf0f654ac | note | CATEGORY: IP
cfe39ef6-0535-5fcf-932e-b08c8c287c4d | note | – – – – – – – – – – – – – – – – –
69f3820f-a79e-5148-90a1-3d32644913c6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b324308b-3210-57ca-907b-8563ee0f2995 | note | – – – – – – – – – – – – – – – – –
542e6b55-b030-5933-9900-91ee944cc465 | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
509a4c13-60d6-5a7e-ad7f-2a341c796c4c | date | Date Completed:
| checkpoint | 5.15 Placement & Compaction
9af40069-8407-5b72-966e-c011973c1f34 | note | REFERENCE: Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
ba1ef2ab-1a7f-5475-9325-77e4e5e468b3 | note | – – – – – – – – – – – – – – – – –
60c3bd9d-0365-50ab-b0f8-da2b600acd8b | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
885534e6-8ba5-5a9a-a0cb-dbc76b156651 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
59fb8e0b-cc8e-5ba0-8c58-e0449cc9feb1 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
af289af5-1c12-5af6-a170-bb908e3967a4 | note | ○ Concrete is not moved horizontally by use of vibrators.
1d8984cb-29d5-5628-8c5a-e753c378cb5a | note | ○ Adequate compaction is ensured
c7a3154e-1130-59a1-b7a6-8ad6f0058dde | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
8aeca3e1-9a4f-50c1-9650-0aa3659d3140 | note | ○ Concrete layers are not more than 350mm
21e803e6-079b-5b15-8858-39cc59926420 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
a4f63cd8-2bb0-50d7-8ac6-d375d9aad529 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
7aaa5a02-f128-57f1-9496-d1fac33f1908 | note | Record: Required information on the Concrete Pour Record.
5346b63c-4345-5db1-9d97-38bbe8b22221 | note | Attach: Concrete Pour Record
660dab67-3202-541e-9d66-b3f79e1cd8b1 | note | Attach: Concrete Dockets
25ba33f6-bda3-561f-8b48-af7bc78f5c1e | note | – – – – – – – – – – – – – – – – –
619cfceb-8afb-56f3-9ae3-0943c232a215 | note | METHOD: Visual
f8518f5e-4bec-5cc7-ac2f-68be706a76bf | note | – – – – – – – – – – – – – – – – –
04e320e5-d72b-5ed4-8d92-805ac45f2733 | note | FREQUENCY: Each load
acc3908d-504e-5be9-9932-20c63a415fad | note | – – – – – – – – – – – – – – – – –
c1a6c9e7-c2f1-510b-b40a-049060695812 | note | CATEGORY: SP
e4c73b7a-2297-5bda-879b-a6ef5817cb23 | note | – – – – – – – – – – – – – – – – –
63deefc5-d771-5892-aa47-3dc31bea077d | note | RESPONSIBILITY: Foreman, SE/PE/SPE
938e45d8-2572-5472-b7f0-c04db6666b2d | note | – – – – – – – – – – – – – – – – –
8e7e304b-2746-534a-9890-452c40d4290f | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
0a6a436d-c7b7-5722-8b60-567ab4134a60 | date | Date Completed:
| checkpoint | 5.16 Surface Finishes
20546c31-6aec-5fdc-96b4-a9b913a7cca1 | note | REFERENCE: IFC Drawings 610.31, 610.20
f471be65-7abb-51e4-90e4-7a92170b05aa | note | – – – – – – – – – – – – – – – – –
f38ba466-d487-5bf0-a423-c05bded050a7 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
0d14777b-f8ba-5c35-9a1e-72790269890e | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
d18bf5a0-898c-51a8-80e5-de6f31f0d8a2 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
9c63c4f9-48bc-56e1-9232-2a11b2035b7b | note | – – – – – – – – – – – – – – – – –
7cea8ae9-7d2e-59ae-8a54-b6bd0481bb61 | note | METHOD: Visual
8ba6c378-03f3-52d9-baea-1f1c00a79b38 | note | – – – – – – – – – – – – – – – – –
7140403d-508d-5cd1-9e6f-535ccda5a6fd | note | FREQUENCY: Each element
e9d02230-6ae3-5711-9562-d822d6a47d5d | note | – – – – – – – – – – – – – – – – –
e0cf4962-c45c-5d24-974e-9765ef196621 | note | CATEGORY: IP
890a6699-6bf0-582e-a1ff-677072abf58b | note | – – – – – – – – – – – – – – – – –
856c4d5d-eab0-56d9-9736-26933aadd8a0 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
70b3b7d0-0111-52a7-a8aa-8bee704426b7 | note | – – – – – – – – – – – – – – – – –
8d610d2e-074c-5c73-a362-2a44a47cebc7 | note | VERIFYING DOCUMENTS: This ITP Signed Off
b6e175fb-e5fd-5cab-8418-99a04495a000 | date | Date Completed:
| checkpoint | 5.17 Curing-Top Surface
b7aaa924-896d-5160-a873-7972fb585b63 | note | REFERENCE: IFC Drawings
8b1dfcef-668c-5630-b39a-82500427f7f9 | note | – – – – – – – – – – – – – – – – –
acaa58fa-e1ae-53c6-8bc7-dff6eae9b01b | note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
d9098656-005c-5173-b798-1aef16461bf3 | note | – – – – – – – – – – – – – – – – –
fc01384d-0348-530d-a3f7-506bab97e625 | note | METHOD: Visual
79a7c41a-4ebf-5b1e-a0c2-6a2c094a790d | note | – – – – – – – – – – – – – – – – –
b34640d8-c2fd-5b83-99e0-4ba0ef224fcc | note | FREQUENCY: Each element
c06f85b6-3f21-5ee4-80ee-8d2d12e173a0 | note | – – – – – – – – – – – – – – – – –
afc3754d-0159-5a5d-845d-1c65453646c3 | note | CATEGORY: IP
994aced1-93f1-5fc0-b79e-78ecd934885f | note | – – – – – – – – – – – – – – – – –
3f843df2-55e5-5f1e-bfad-473b9100b659 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9acbc8d9-b3a0-5a94-bb73-b0dd7911bf4a | note | – – – – – – – – – – – – – – – – –
1dbcb2f0-bb77-5c9c-9bb0-85d185b6af47 | note | VERIFYING DOCUMENTS: This ITP Signed Off
69cdcae8-9d91-5fc2-9133-2432218a4a50 | date | Date Completed:
| checkpoint | 5.18 Curing after formwork removal
9abea23f-b0b8-59a6-84bf-235149c59955 | note | REFERENCE: IFC Drawings
8d2e421b-841c-5bc9-9540-ef6756e668aa | note | – – – – – – – – – – – – – – – – –
f005b622-f39b-5501-bc3f-6f51afbb9779 | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
89a29cfa-70d7-5961-993f-aad041fb8b88 | note | – – – – – – – – – – – – – – – – –
77d0eada-b1af-578d-9377-326bf6031def | note | METHOD: Visual
9753428f-2660-58b2-ab9f-182239541a3a | note | – – – – – – – – – – – – – – – – –
1adb7283-e28d-5110-8f08-00e09703ccdb | note | FREQUENCY: Each element
ab2aad19-3f07-57db-91ef-9e85dcd2bdee | note | – – – – – – – – – – – – – – – – –
b7dd3568-bd91-520a-b61c-cfc5d5d379c3 | note | CATEGORY: IP
c139a828-dde3-5756-87f3-1eb386c65e85 | note | – – – – – – – – – – – – – – – – –
fcc4ed7f-ec0b-5200-b19e-047a92e28b1f | note | RESPONSIBILITY: SE
93ab68bd-ea1b-506e-a23e-afd9b6fabf6a | note | – – – – – – – – – – – – – – – – –
d947dfd8-f9e8-5369-a768-101b15d4a1c4 | note | VERIFYING DOCUMENTS: This ITP Signed Off
1de77906-7a15-53ff-8f6a-62f4621cff94 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
df951459-210b-5114-b0bb-e6287156b14f | note | REFERENCE: 610.22
363b99f8-bb9d-5a54-bb56-7e41a20fa245 | note | – – – – – – – – – – – – – – – – –
afb0e797-8218-5af9-bb43-98e0fca93c2f | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
976f957c-1246-5634-a613-87ef1cd481cd | note | Only applicable if the element has:
9417a764-b314-50e4-8962-062619445c06 | note | i. the smallest sectional dimension exceeding 500mm
a7693dee-e6a8-5ea6-a12b-349c7a0ab4a9 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
170e1ea3-e648-5b82-bd25-4da6b8225641 | note | Attach: Thermal Monitoring Report
089d72f0-f3b7-5314-b5dc-4efd984547a7 | note | – – – – – – – – – – – – – – – – –
bb87a86c-0c4c-5d4c-9456-14e1105b7408 | note | METHOD: Document Review
0adefe46-e8e5-5b20-8b38-471c8ae6b6eb | note | – – – – – – – – – – – – – – – – –
245aaaa7-01f2-513c-a66d-5f157accc9d7 | note | FREQUENCY: Where applicable, each element
d90ee354-db3f-59b5-9522-4f9ecca53edc | note | – – – – – – – – – – – – – – – – –
0410da2e-fe96-5223-a846-798beae23842 | note | CATEGORY: IP
4082d6ca-7cee-5bfb-8121-1100016d9985 | note | – – – – – – – – – – – – – – – – –
f2e23410-be41-5143-9d99-4e5a5a583451 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
ee318345-f1ce-5dcb-a115-4b9b377013cf | note | – – – – – – – – – – – – – – – – –
c0252605-0c09-58ad-a2f2-cef5f8546efc | note | VERIFYING DOCUMENTS: This ITP Signed Off
d43782f7-0775-58d2-9cda-dd35f17392c7 | date | Date Completed:
| checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
5805f5e6-06b2-54e9-a32c-41b45cf2c50d | note | REFERENCE: IFC Drawings
e5ef1535-b14d-5c64-b378-8e4f4a144572 | note | – – – – – – – – – – – – – – – – –
0f0a90ea-907b-5600-b174-2ec8ddcd9cf8 | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
f8880ad7-9699-59d8-ab15-2df03bcd6b18 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
4e782f81-267f-5c34-ab26-c1bb6a2f3524 | note | – – – – – – – – – – – – – – – – –
16c29ea9-dd18-554e-b866-3c41c1029139 | note | METHOD: Document Review
b93210d2-02b8-5798-b817-3f46c4aa520d | note | – – – – – – – – – – – – – – – – –
791d4fb8-5eeb-5d08-ad0d-1ce7fb54cf60 | note | FREQUENCY: Where applicable, each element
ecd3c28d-0f35-5cf7-a768-3db13a8f5401 | note | – – – – – – – – – – – – – – – – –
90079d0b-fdc5-5342-bb36-5028efff23ce | note | CATEGORY: IP
3aec0bdf-6672-5b03-bedc-f8775aaa6546 | note | – – – – – – – – – – – – – – – – –
87d8c41c-dbb7-5df2-8703-22535209efbb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
ea522cb7-5227-5ae4-a8e8-e1931e91d44c | note | – – – – – – – – – – – – – – – – –
edaf6c99-6e7e-5868-8945-256b2688c41c | note | VERIFYING DOCUMENTS: This ITP Signed Off
2cadc7ee-73e4-50b8-945f-b4975e845251 | date | Date Completed:
| checkpoint | 6.3 Surface Inspection - Cracks
22e64788-71da-5167-ad8e-137fcb9353fc | note | REFERENCE: 610.24
ac1dc02b-f0ac-515c-84fc-5e08855fb724 | note | – – – – – – – – – – – – – – – – –
59293335-9d1b-5b11-a255-e9c41644511c | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1). If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
596181b3-1e2d-5a57-8469-4eecb19ee0c0 | note | – – – – – – – – – – – – – – – – –
643ea348-1100-5734-869e-2421720e1f26 | note | METHOD: Visual, Measure
1c900044-f1d9-5be0-babc-cc60da84c1ea | note | – – – – – – – – – – – – – – – – –
fdae024e-869b-5366-89d2-016a15ccf117 | note | FREQUENCY: Each element
0a5b7fc5-dbf3-51cd-8348-14240b0b40d0 | note | – – – – – – – – – – – – – – – – –
e1ca5cf0-7508-578e-af86-afc9dbac1fde | note | CATEGORY: IP
058c6d4b-ce0d-5ca2-b4f6-94652ccc9b0f | note | – – – – – – – – – – – – – – – – –
76806fce-c3a7-5551-952b-4cc2e04dcff0 | note | RESPONSIBILITY: SE/PE/SPE
cfe9a5a2-1cad-5640-903d-b6c2fd9d0c40 | note | – – – – – – – – – – – – – – – – –
7320dbca-26b3-527e-8ee5-9356e851cfbe | note | VERIFYING DOCUMENTS: This ITP Signed Off
0e22ac14-99f2-5ce8-9b85-9e2c67be9bfb | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Surface Finish
9a64021c-2666-574a-859c-1e0d47e6b231 | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
718cded4-e028-5856-88c7-c7ad3f3551db | note | – – – – – – – – – – – – – – – – –
fc4f527b-8508-5712-9a64-829357de8dbf | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
ce785974-e512-5f0e-92fd-8b08d5bf076c | note | – – – – – – – – – – – – – – – – –
02bcd21a-937a-5d3e-a872-8a1ce5e9c56d | note | METHOD: Visual
af41fc44-e02c-530c-8312-24cba703066b | note | – – – – – – – – – – – – – – – – –
46af4362-0087-5c59-aa18-a31f8d9650b5 | note | FREQUENCY: Each element
f0efe838-5cd1-58f2-b768-f7ac07899441 | note | – – – – – – – – – – – – – – – – –
38c44a43-4848-5171-a0e4-525afde4cfbb | note | CATEGORY: IP
8c210766-8e44-53a9-8146-f3b8974cc4ea | note | – – – – – – – – – – – – – – – – –
fdb996c7-73e1-5662-af9c-71572028b35a | note | RESPONSIBILITY: SE/PE/SPE
8065ad4f-a7f1-5db1-bacf-dcc772631b41 | note | – – – – – – – – – – – – – – – – –
40a5334a-6711-5c25-9e1e-42be4fa96f10 | note | VERIFYING DOCUMENTS: This ITP Signed Off
4838401b-7afb-5fba-b63c-c93f86570e1b | date | Date Completed:
| checkpoint | 6.5 Measurement of Concrete Cover
f1912451-a285-52e1-ba61-b8a616feb133 | note | REFERENCE: 610.34
11b43a97-fecc-5522-b6b1-2775d9ce3007 | note | – – – – – – – – – – – – – – – – –
260ad736-08d3-5456-b86c-50cd499359ee | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
954b855b-8c28-5478-98e7-6846d6294b2e | note | ○ Minimum 10 no. measurements recorded in each area.
0a7aae5c-601e-59ec-a828-7f18385e2a8b | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
c410cf41-0cde-502d-b9bc-faddbdced9d3 | note | Attach: Covermeter Check Record
cbc487a2-e517-5e89-95c5-cfd4480082e9 | note | – – – – – – – – – – – – – – – – –
2493ccb0-cf95-51cb-bed0-389bb0c8212a | note | METHOD: Measure
a654085d-d41f-555e-8b43-5da7e857f67e | note | – – – – – – – – – – – – – – – – –
3649b612-e1de-5ccc-9d04-52cd0126ca42 | note | FREQUENCY: Each element
2021626d-8bdf-52cf-af0d-b9419f90d2c4 | note | – – – – – – – – – – – – – – – – –
3056604c-50fa-57a4-9205-6462196637cd | note | CATEGORY: IP
7bef27d9-f1ba-5e05-88ab-9fdb5563c570 | note | – – – – – – – – – – – – – – – – –
d6ec20af-872f-59e9-b6fa-6e9654508c85 | note | RESPONSIBILITY: SE/PE/SPE
b311e8b9-7381-5ea7-8ea9-35328d161e84 | note | – – – – – – – – – – – – – – – – –
1845b2fd-4f6a-513b-b1c4-90e9680695f2 | note | VERIFYING DOCUMENTS: This ITP Signed Off
d16ce1f3-90a1-5daf-989f-7131d20a5958 | date | Date Completed:
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
84713a49-5f7d-5da2-a125-683653f7bedb | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
1a691f44-1539-5689-9567-00be224050a2 | note | – – – – – – – – – – – – – – – – –
424d66e5-4702-54d8-8dc6-a564dc65f751 | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
f3243b66-27d4-5fe7-919a-dac9abe7ba12 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
d8cf0ba9-3074-5e11-afd4-31839ec4ae26 | note | Attach: Concrete Test Results or Maturity Test Results
47ac9658-e1d0-54d2-94b0-d47bbcf53362 | note | – – – – – – – – – – – – – – – – –
7bbcaec6-7aa9-53a0-bca5-cfd3aa474547 | note | METHOD: Document Review
c8791c55-eb9d-5212-9c8a-8de1112e883f | note | – – – – – – – – – – – – – – – – –
ea799b1d-010c-59e0-aae7-de486cd93f9c | note | FREQUENCY: Where applicable, each substructure element
3a11ac0b-8dd6-5bc8-ba32-1a593b2e6f2e | note | – – – – – – – – – – – – – – – – –
57516961-a5a5-5ea7-b30b-58b9af781f37 | note | CATEGORY: SP
ae00a234-8b99-54fd-be6b-8a623c043b95 | note | – – – – – – – – – – – – – – – – –
6d5fc2da-a242-5914-bd77-c0a624397894 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
834551b2-5ecb-5a78-bc7e-13b16c58c2b1 | note | – – – – – – – – – – – – – – – – –
7de058de-5ddc-5e7c-a29e-37f1c7cfd371 | note | VERIFYING DOCUMENTS: This ITP Signed Off
9bd73a25-fc18-5c04-98da-c05c08c69729 | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
f3f6d7c1-7bd5-5dea-ad18-779cdca21242 | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
82ca1944-b066-5ec7-bd69-f189f5673ad8 | note | – – – – – – – – – – – – – – – – –
e8ec5a7b-8150-592c-a2d2-14ee69d2d253 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
c2cfa570-4796-57a4-92ca-9adcf5e96321 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
b63ed3e6-dbc2-5e57-82ce-07254754d060 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
60c7e6e4-74b7-59c9-b6bf-81522501d5be | note | Attach: Compressive Strength Test Results
6c1bc01d-9c95-51e4-bc79-f7a645c70162 | note | – – – – – – – – – – – – – – – – –
0bd5333c-bfaa-5e53-8fbe-c064b3c8339e | note | METHOD: Document Review
4ab8158f-98ce-5dd5-9bad-62cd22e16d5b | note | – – – – – – – – – – – – – – – – –
f6ad73fd-dfcf-56f2-8343-c5a3cad70d97 | note | FREQUENCY: Each cylinder
41ab39f9-7543-5f9e-aa61-17d086c88af4 | note | – – – – – – – – – – – – – – – – –
4744a4b0-71be-56fe-b960-c9e2e1958994 | note | CATEGORY: IP
2e0045e3-8fb7-55bc-93c2-abb7cd2f9a69 | note | – – – – – – – – – – – – – – – – –
0a70df19-7b50-5c3a-bc2b-f49ca6cb8c92 | note | RESPONSIBILITY: SE/PE/SPE
2995cdc5-0dbe-5e25-b737-460696bbcfe9 | note | – – – – – – – – – – – – – – – – –
94eac283-2537-5eaf-a854-6abe07cd74fc | note | VERIFYING DOCUMENTS: This ITP Signed Off
b33b1515-a26a-54b7-bd45-4344a1731b9e | date | Date Completed:
| checkpoint | 6.8 As-built Survey
4e2f0ff9-b1ce-5e55-9f1b-6943d66cc567 | note | REFERENCE: IFC Drawings 610.47, Table 610.472
c883ff68-048d-52c0-812b-a135ec89df70 | note | – – – – – – – – – – – – – – – – –
747e6fde-2d46-54c3-926e-5c185da6b20f | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
b681ac31-4eb6-5877-9c6a-6ac69b997f8b | note | Attach: Survey As-builts / Survey Report
b64d4650-e20f-5087-8b8a-6cb8cf2f8d91 | note | – – – – – – – – – – – – – – – – –
f3fd0252-eff2-51ea-86d8-d405472a9269 | note | METHOD: Document Review
f64c9ecb-7f5b-5b30-8582-17db68b1db3f | note | – – – – – – – – – – – – – – – – –
931c7b0e-c31e-5683-8095-1bf149132445 | note | FREQUENCY: Each element
85093da8-0d4d-5e3f-b39e-f60841b922a8 | note | – – – – – – – – – – – – – – – – –
63a97d44-18a5-539d-9787-58ed330be2f2 | note | CATEGORY: IP
2ec859ff-2be8-5786-b94f-1fa92657f0ca | note | – – – – – – – – – – – – – – – – –
171b1206-728c-58e4-a041-015a6f59724f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
4b0b89ee-913a-5b3f-93a2-cb5d9a8efd70 | note | – – – – – – – – – – – – – – – – –
9140098b-408f-52d8-a4dc-0d3891d4fe46 | note | VERIFYING DOCUMENTS: This ITP Signed Off
ff24c6db-df11-5511-87d0-e681d662d276 | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
e19c800a-d3b4-557d-b2cc-894a8d981390 | note | REFERENCE: MRPA Quality Management Plan
174c21e0-7586-50eb-a323-ed871830d154 | note | – – – – – – – – – – – – – – – – –
75868e33-abdc-59b0-a0b7-1e2c0c8f6059 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
78a2df68-7af8-5ceb-9d00-3996c3f7fd79 | note | – – – – – – – – – – – – – – – – –
beb0dbd0-f9f7-583d-b091-59d79c186c92 | note | METHOD: Document Review
2a85e407-ed37-518c-8c35-6b708babed31 | note | – – – – – – – – – – – – – – – – –
0fcd3d77-72fd-5c4a-abd6-b9b0626fe647 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
bed4ba33-8ca4-5007-856f-5d3f1e63b659 | note | – – – – – – – – – – – – – – – – –
f29ae1a9-7ef2-5b4a-84c6-e8ee571aad4c | note | CATEGORY: HP*
280bc707-eb76-51c8-8d53-20aae27e4795 | note | – – – – – – – – – – – – – – – – –
7a988826-bdca-5213-83e5-6ac20364eac6 | note | RESPONSIBILITY: SE/PE/SPE
9385e4ce-b913-563a-910c-fca2f67d635e | note | – – – – – – – – – – – – – – – – –
43b46741-b3e7-5379-93be-e5f6ab6cf5e6 | note | VERIFYING DOCUMENTS: This ITP Signed Off
28c9448c-8fd1-50a0-a83f-554d050febca | date | Date Completed:
| checkpoint | Final Inspection
059e18aa-ec6f-5378-9fd7-8f6a5c7aeb8f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5e4d66f1-07a0-557f-bf9e-a2152fcdfc76 | textbox | Name:
665dc205-1b45-51f2-84c9-8a27fbdd2b91 | textbox | Position:
f26b4ea8-2ba3-59c3-a122-03da4b972f5e | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) Rev 0 | itp | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) | 98988600-f109-4162-9d46-623772bc71ac
| section | Referenced Documentation
| checkpoint | Referenced Documentation
1afd8c2b-b2fc-5b27-90e6-6832699469d3 | note | Document Title: ITP-110-CIV-SSB-Ground Improvement (Structural Fill)
53683786-8133-5c98-a723-1221521b30d7 | note | ITP Description: SSB-Ground Improvement (Structural Fill)
f0ac5ab0-88ae-58c9-9817-6f02c4a479b7 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
b1e4a114-e4c4-595b-9249-c676fbec1daa | note | Discipline (e.g. CIV/STR/RAIL): 110-CIV
ca0c9f87-b3ec-50d1-9bab-2c3580f80113 | note | Revision Number: 0
8f09148c-3abd-57a4-9cd5-95d714cb6b2a | note | Revision Date: 27/11/2023
433cd1d2-249d-5580-8270-9c1bec88ad08 | note | ITP created by: Hiruni Wickramarathne
861423c7-08c7-5955-bd2d-723970a7aa27 | note | ITP approved for use by: Victor Mira
9a4739ce-3918-586c-a9c7-dc97c8f8d90b | note | 1.1 Non Dependent
7455affe-0e39-5be8-a5a2-80a073c222cf | note | Reference: VicRoads Section 204 (Dec 2015)
a406d50d-8d3f-5d91-84e1-726ae9c1db94 | note | 1.2
13925f9a-2948-5064-a7cd-ad191428e97a | note | Reference: IFC Report and Drawings
| section | Preliminaries
| checkpoint | 2.1 Material Approval
a510e2e7-1d22-558d-89d9-72eb50c491c3 | note | REFERENCE: Section 204.04 Table 204.041 IFC drawings
bdd63e20-b456-5f00-b3cf-448868df87e5 | note | – – – – – – – – – – – – – – – – –
73609ffd-1283-58ef-a223-2d4c0b998b16 | note | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
2fdf20c5-ff36-55d9-a3c2-8658f52ae0b8 | note | Scale C:
9ee370e9-303f-5fd2-86cb-0e33bdc97ca7 | note | ○ CBR ≥ 6%
69989c43-55e6-5d6f-b195-d514a73a8906 | note | ○ Swell ≤ 1.5%
2944fc49-ce55-572b-8a1d-410a1bb17a83 | note | ○ Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided)
ea8ee84d-324c-52f7-810e-28065639f93f | note | ○ PI (LL) = 6 - 25
b8f99c52-779c-576d-be4a-9b67bf794564 | note | ○ Effective Friction Angle = 32*
ee9027d8-7064-5c99-9151-c1e3ce152cc5 | note | ○ Effective Cohesion = 0-5kPa
d216e45d-00af-5297-8067-4489ad6433cd | note | ○ Unit weight ≥19kN/m3
ebab351b-ae6e-5990-9b3d-8df465f96bb0 | note | Grading:
c77dd560-5dcc-55b9-b9ff-0e6fc65a3dd8 | note | ○ % passing 75.0mm sieve = 100
bcd6644f-1e49-535c-bfb6-fe4cd615d7c8 | note | ○ % passing 4.75mm sieve = 40 - 80
247ebdc8-c7b7-56dc-9164-e89ee1aa05bd | note | ○ % passing 0.075mm = 10 - 40
c8b50c2c-5d3f-5066-97d6-28bd3fce0679 | textbox | Enter: Teambinder Material Approval number
dff70a35-4f71-5979-8764-328eb96bb5c6 | note | – – – – – – – – – – – – – – – – –
14eb9469-a93d-5e3e-a446-f88217aef1ff | note | METHOD: Review and Verify
44de2753-fa07-56fa-978f-cd79d848de5b | note | – – – – – – – – – – – – – – – – –
79db2307-3391-5c42-a6ab-0dbe064c3d35 | note | FREQUENCY: Once per material type prior to commence of works
9661e9d1-3059-598b-a4a8-383f61b8adb7 | note | – – – – – – – – – – – – – – – – –
d6d210a2-3f85-53b4-b9ce-bebe6970e4e8 | note | CATEGORY: HP
06ae8c8a-753a-5a21-a8e5-8f8dc1cbb955 | note | – – – – – – – – – – – – – – – – –
96c012cb-ebe3-5015-87fe-9ba76e561d28 | note | RESPONSIBILITY: Nominated Authority
951eb720-e9fd-5df8-a4d0-87767cd71789 | note | – – – – – – – – – – – – – – – – –
4ecb23de-d31b-5dad-a7b9-ff54bda6fcd8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9540651b-9946-57ac-aac1-fccc334bcf7e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Survey Set-out
1e021484-2172-51e7-a7df-d5e8025d3c90 | note | REFERENCE: Section 204.03 IFC drawings
d0b96f91-ca32-572f-a7ef-c5053b316193 | note | – – – – – – – – – – – – – – – – –
5ceeb57d-2455-546c-87da-a20ca7ad052f | note | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
a830c4df-4929-56cd-b206-ed10cf0e34d6 | note | – – – – – – – – – – – – – – – – –
a5b0a3a9-20d3-5e85-bcff-1f4f31dbdeb5 | note | METHOD: Measure, Visual
ff200919-3451-5dd2-9009-2da4b44404a7 | note | – – – – – – – – – – – – – – – – –
e9d33901-c549-58e2-bd1c-6227b894a5f5 | note | FREQUENCY: Each element
4970237e-7e25-54f2-95da-618a67ade4f1 | note | – – – – – – – – – – – – – – – – –
f4cc4ec6-1b93-5d5d-bf61-e093966d0f52 | note | CATEGORY: IP
7eb42b09-08ac-5e01-962a-d9aa2af3d9a3 | note | – – – – – – – – – – – – – – – – –
7f58558d-d228-538c-b283-bd5e575d3c0b | note | RESPONSIBILITY: SE/Site Supervisor
2b307a5a-78c8-5bf0-b251-aa234e72adf8 | note | – – – – – – – – – – – – – – – – –
e976dd7e-15b2-5dc2-9708-dd0c5d5bcd30 | note | VERIFYING DOCUMENTS: Sign ITP
c15e0622-c768-5baf-a363-09e47f06e391 | date | Date Completed:
| section | Cut Activities
| checkpoint | 4.1 Subgrade Level
d73c7ae8-88c3-5c26-ad46-3235b20019c3 | note | REFERENCE: Section 204.03 (g), Section 204.03 (h) IFC drawings
d574146e-a297-5b65-9f56-41c9f10c4cb1 | note | – – – – – – – – – – – – – – – – –
b8d8040c-c53d-5cd2-9c33-f8d793eaf910 | note | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant Ground Improvement drawings within the following limits:
9521b8cb-15da-5f1f-b128-e0530ac7b714 | note | ○ For Scale C: No point of subgrade surface shall be more than 10mm above or 30mm below the specified level.
e8b65c28-e7c7-5103-b2af-18097c7a6dd2 | note | – – – – – – – – – – – – – – – – –
25e7e71f-a283-57ca-8898-7bc9ab60e502 | note | METHOD: Measure
d9980e02-8fdd-5aab-90a9-ea08cefcebf1 | note | – – – – – – – – – – – – – – – – –
6ab586ac-5c59-5795-a343-a508afd6378b | note | FREQUENCY: Each lot
77aef399-e8e3-5be3-8d06-8b16f9ce39d6 | note | – – – – – – – – – – – – – – – – –
3e5ba9bd-6551-5c1f-81b9-d13d290aa477 | note | CATEGORY: IP
1e22f16a-de74-5339-9472-ad9fd02ec21f | note | – – – – – – – – – – – – – – – – –
e9617374-a47f-5c29-865e-c21b7e6d4c20 | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
1c78ceff-e33c-501f-bcea-8d3a5f0b9e51 | note | – – – – – – – – – – – – – – – – –
50cd297d-9f5a-51a1-a413-2d064b4a299d | note | VERIFYING DOCUMENTS: Sign ITP, Survey Pick Up Report
1dbddeb9-9b54-5374-88ce-21947cfb3d50 | date | Date Completed:
| checkpoint | 4.2 Founding Material testing
acd72940-9d9e-5252-b66c-66791f82d5d6 | note | REFERENCE: IFC Report and Drawings
2be319f1-95fd-536c-9786-a35dceca0b56 | note | – – – – – – – – – – – – – – – – –
fce75a44-fb4d-5b98-bffa-32c79522b127 | note | ACCEPTANCE CRITERIA: DCP test to be carried out on the excavated surface to confirm the strength of the existing material is in accordance with Deisgn values for relevant chainages as below.
87e6638c-6651-502c-aee2-cac4ba0cdc1d | note | ○ Min DCP required /100mm
7900b1dc-bcc2-5e06-acf5-94c0e01da8eb | note | ○ 10000-10030 : 5 ( South)
f73e6fab-1682-5d86-9617-f0633abaf7da | note | ○ 10300-10320 : 7 (North)
0d89a1ea-9e46-5165-a3ff-93f5a2ccb5cd | note | ○ 10320-10360 : 6 (North)
b1dc253d-c3de-5fb3-8482-8743b283f13f | note | ○ 10360-10400 : 5 (North)
7bf7d979-56d5-5788-9b23-2e9362559f99 | note | ○ 10400-10410 : 3 (North)
4bc4f8d7-12e1-5765-a130-addbaa21c9d3 | note | – – – – – – – – – – – – – – – – –
363c00c4-7108-5dba-a708-37b81c05b82c | note | METHOD: Document Review
264b7a8f-4e25-5f2d-9be4-852669423b2c | note | – – – – – – – – – – – – – – – – –
a2341b73-b5a8-56aa-b565-78f5eead40d8 | note | FREQUENCY: Each lot
ebd126cc-2aa8-5e72-8b10-581aab350f85 | note | – – – – – – – – – – – – – – – – –
8129ee78-3bed-52e3-971a-0a66f012c129 | note | CATEGORY: HP
db1ddd17-4c93-538e-a6f9-5dc947a1d41c | note | – – – – – – – – – – – – – – – – –
8ed05b04-2150-54f6-8425-c88ea414fbe5 | note | RESPONSIBILITY: Third party Geotech Engineer /SE/Site Supervisor
43199ddf-10ad-5e45-b105-621b46e99865 | note | – – – – – – – – – – – – – – – – –
aa95297c-e434-5a68-b32c-dcbd26f4b737 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Test Report
4ad1e089-51cd-555a-a2b8-303ff88f1eb1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 Proof Roll
be2b0d6d-369f-5ee0-a6d2-fb05384adca0 | note | REFERENCE: Section 204.10 (b), Section 204.12 IFC drawings
e932ccb9-4af8-5e24-8c0d-23c8998b16da | note | – – – – – – – – – – – – – – – – –
25d93995-8104-5320-85f6-45b7744e26b7 | note | ACCEPTANCE CRITERIA: Excavated subgrade to be compacted and proof rolled before any construction.
c3c357e2-9d36-5282-a68a-1861661fcf58 | note | ○ Withstands Test rolling without visible deformation or springing.
38011b9e-693e-532a-8c8d-150b87f29c9f | note | ○ No fill to be placed until the area has been reviewed and approved.
89131125-e049-57fe-8dd4-5eaf23e46a7b | note | ○ If Proof Roll fail go to section 4.4
f50b1daa-b73c-548b-a33a-2d62a920b306 | note | – – – – – – – – – – – – – – – – –
3a064b22-d917-538e-94bf-de3ed9e3381c | note | METHOD: Visual
76536e14-339c-5133-a926-b5979c95ef1f | note | – – – – – – – – – – – – – – – – –
29a44105-d081-5fa5-b30e-549c5d4ed6d9 | note | FREQUENCY: Each lot
0baacbb9-d547-5402-b9d5-3ae47c8e4df1 | note | – – – – – – – – – – – – – – – – –
8b57d3d1-9f00-5c75-b1f5-0bc830517893 | note | CATEGORY: HP
df97a84a-c9d9-52ad-810a-c562da063770 | note | – – – – – – – – – – – – – – – – –
18582f35-9017-5399-bebc-f7cd62b2fe4a | note | RESPONSIBILITY: Nominated Authority
be8dfcd7-0591-5f46-a8b9-4249281ccab4 | note | – – – – – – – – – – – – – – – – –
31a02151-9420-5b12-a4e1-51355f8df45f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
92e68391-aed7-5d82-bca6-0633f25d508a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 Founding Material Inspection
ff88d49f-3a3d-532b-8dc6-f1a57b161f7a | note | REFERENCE: IFC Report and Drawings
2b19344b-7d61-522a-999f-bb4fdfa70929 | note | – – – – – – – – – – – – – – – – –
ed0a4f47-7658-5807-b79a-71b1bedaa3aa | note | ACCEPTANCE CRITERIA: Geotechnical Engineer shall inspect founding material.
1e2816f0-58e2-5129-b345-a636bbdce704 | note | ○ Any areas in Ground Improvement footprint where proof roll test or bearing capacity are inadequate crushed rock shall be placed and compacted into the excavated surface under direction from geotech engineer
917ba2d4-8685-5b83-b0c8-5235d3cbcf10 | note | Attach: Geotechnical Field Sheet or Report
a1c07dfd-286a-59b7-a7b5-88a8639d2788 | note | – – – – – – – – – – – – – – – – –
1be3e270-3d55-513b-9078-fae9c6793441 | note | METHOD: Verify, Document
0b12a377-6a4a-5d93-9304-2046772b2989 | note | – – – – – – – – – – – – – – – – –
aa0168ba-b447-5e53-ae1a-fb1d39c00bf9 | note | FREQUENCY: Each lot
7ce7c7aa-bc68-5780-9352-cbe1077f8480 | note | – – – – – – – – – – – – – – – – –
3f294ed0-64ab-5128-a1a9-cb23da4aaeb9 | note | CATEGORY: HP
0d2d926d-4301-5ec2-ba7b-c951f6099e04 | note | – – – – – – – – – – – – – – – – –
38b06337-cc09-5d24-aff5-bc05cf032ab5 | note | RESPONSIBILITY: Geotech Engineer /SE/Site Supervisor
0fbfbb69-799a-55b3-a737-e4f8db96dd1a | note | – – – – – – – – – – – – – – – – –
96001f41-6af1-5819-818e-ad07777b8f9b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Geotech Report
e0006976-9616-5a43-9913-dfad1435a513 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Fill Activities
| checkpoint | 5.1 Structural Fill Placement
47b724af-af6a-5e94-bebb-c315a7a3b204 | note | REFERENCE: Section 204.10 (d) (ii) IFC Report and Drawings
bebf5eef-07f9-5de6-bedd-fcfc3c9e73bf | note | – – – – – – – – – – – – – – – – –
c5c5b68c-a30d-555a-a9ac-d2d142aaab93 | note | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Extent of fill placement to be as per IFC Report and Drawings
d34e4349-7ac3-5bd3-b8cf-6c98887ee3c3 | note | – – – – – – – – – – – – – – – – –
20fe646d-c7fb-5f72-aeea-924392351adc | note | METHOD: Visual
00b3f737-68aa-5d67-84dd-c1b14e1089c5 | note | – – – – – – – – – – – – – – – – –
2df46527-3f35-5eaa-8bf3-139569423611 | note | FREQUENCY: Each lot
43128893-aa86-5590-a136-fae5e2354d0c | note | – – – – – – – – – – – – – – – – –
3520e48b-5953-5311-850d-7fc88e55ffee | note | CATEGORY: IP
584ae2f6-4e1f-56c2-97d1-53dc9e1ce916 | note | – – – – – – – – – – – – – – – – –
680f9e89-f221-52b0-9295-de4b64606fb6 | note | RESPONSIBILITY: SE/Site Supervisor
e9cd5f7b-e260-5937-91c3-f68a69fabce1 | note | – – – – – – – – – – – – – – – – –
4724ae6a-a642-56ed-92c2-b1dec31eec4e | note | VERIFYING DOCUMENTS: Sign ITP
e561bb69-3603-5fb4-8087-448d6984272c | date | Date Completed:
| checkpoint | 5.2 Keying of Layers
90b823e2-81a6-5e36-89a0-a394af15203c | note | REFERENCE: Section 204.10(d)(i)
2af87710-8e47-5be3-be62-583f1ed1d74b | note | – – – – – – – – – – – – – – – – –
0cab024f-6831-57ab-9272-3dc703017d00 | note | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
dcbf9679-0572-57a2-875b-50ece5234e0b | note | – – – – – – – – – – – – – – – – –
4f9db37e-1d03-5b68-aef2-600cfff82d00 | note | METHOD: Visual
bd227242-66b8-5cac-862e-152da96affd7 | note | – – – – – – – – – – – – – – – – –
0323d662-7488-5d6d-9090-118145ef15ea | note | FREQUENCY: Each lot
83fc03e9-1eca-57a5-81eb-c8f6ff243186 | note | – – – – – – – – – – – – – – – – –
b94e5e0a-f2fa-540b-93fc-42d65bb215c0 | note | CATEGORY: IP
85a68a15-a3ff-5c38-bef6-3f6e8acce801 | note | – – – – – – – – – – – – – – – – –
c6521853-d1e4-5001-8952-3afa9fe52200 | note | RESPONSIBILITY: SE/Site Supervisor
1601e548-8e74-549f-a629-9332651111f7 | note | – – – – – – – – – – – – – – – – –
a81c18ed-ac54-538e-8a09-999b10aa869e | note | VERIFYING DOCUMENTS: Sign ITP
761cc61f-cc84-5817-9eff-946db0b260b6 | date | Date Completed:
| checkpoint | 5.3 Proof Roll
582d882d-6d70-53e6-9333-5bc3768d7081 | note | REFERENCE: Section 204.13 (b) (i) Section 204.12
1f45786e-78d7-5581-83a7-65e5d2229300 | note | – – – – – – – – – – – – – – – – –
698d111b-a84e-5833-bc73-42c552f55dd0 | note | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing. No fill to be placed until the area has been reviewed and approved.
273f6889-f33b-5c49-8d57-b38f1cbfb4f7 | note | – – – – – – – – – – – – – – – – –
b260d8c1-9db6-5304-b475-88576186ea13 | note | METHOD: Visual
5e301e87-2d7e-5a82-aef4-7a255cfd2f3d | note | – – – – – – – – – – – – – – – – –
40bed61a-d2d5-5075-9ff4-cb705ebe1c8a | note | FREQUENCY: Each lot
e1a2f962-7fd3-5787-99a6-7211c81521b7 | note | – – – – – – – – – – – – – – – – –
c03c6c8c-37f1-57d8-83b7-ad574edc5551 | note | CATEGORY: HP
8d0f61d1-5e84-50f1-996d-5af8014b0792 | note | – – – – – – – – – – – – – – – – –
f9a18f2a-2d21-508e-bc9f-5ac577b4dde8 | note | RESPONSIBILITY: Nominated Authority
9b294082-94e4-50b8-8c9c-819f71985dd6 | note | – – – – – – – – – – – – – – – – –
cb5ef388-78d3-5e97-a69e-f1bfb62bbb9b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d12a86cb-c8df-584c-8d53-e5250250e2fd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Compaction Testing
f49ae573-addc-5ce0-9e23-11615e2efae3 | note | REFERENCE: Table 204.131 Section 204.13, 204.14
b77684dc-33d2-5798-802f-bb6259ed6aff | note | – – – – – – – – – – – – – – – – –
cf0b3fd2-f7bd-563b-ad19-b20fc9036cc2 | note | ACCEPTANCE CRITERIA: Each Lot to be tested for compaction as Scale C requirements (3 tests per lot)
bfb72d84-c7de-5de4-9ef6-86d9bf36310d | note | ○ Lot = One day's production or 5,000m2, whichever is the lesser
db52f007-4065-50a2-bd61-eedd40436ca1 | note | ○ Characteristic Density Ratio = 100% minimum
c667cf27-83fb-5013-a057-b02a815b2068 | note | – – – – – – – – – – – – – – – – –
e3a56e4a-52c6-556d-9fef-3c0078973ab0 | note | METHOD: Document Review
0b15da88-2d72-551c-99e2-50d274a73f9f | note | – – – – – – – – – – – – – – – – –
9275ac65-05fc-5f9d-b0a3-09f69eac3efa | note | FREQUENCY: Each Lot unless otherwise directed by Nominated Authority
af52ac44-e047-51ee-9f56-c5d12e3f8349 | note | – – – – – – – – – – – – – – – – –
0acfa5f6-0ec4-5fd6-95f1-211b940fb58a | note | CATEGORY: HP
3104936e-8c0c-5abc-9fd8-1c00d0d62e3c | note | – – – – – – – – – – – – – – – – –
e40a5845-ceec-585b-b857-957035041034 | note | RESPONSIBILITY: SE
b80a5ce4-2fdd-5081-8210-a252e74e59dc | note | – – – – – – – – – – – – – – – – –
2247f424-8f3e-5f4b-96db-f6d42f87a589 | note | VERIFYING DOCUMENTS: Sign ITP, Compaction Test Report
25485214-6e55-502a-9ecf-726077e38413 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Preparation of final surface
0fb068d8-0b48-5d7c-8b0e-b9d9f076d5f1 | note | REFERENCE: Section 204.15
be074ba7-673a-5cb7-88c1-a21601d64e5d | note | – – – – – – – – – – – – – – – – –
29b186fb-604b-5e4f-9032-0d66f2a983a2 | note | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
8e73a86e-3ea5-590c-838e-01a7d110981b | note | – – – – – – – – – – – – – – – – –
c6d0d504-9ee7-5448-8b1d-d2f589a63c96 | note | METHOD: Visual
cf7d18fd-7de3-512b-b280-f756d90c8348 | note | – – – – – – – – – – – – – – – – –
9ecd34ec-1b3d-5cf9-8f26-4df44326b64c | note | FREQUENCY: Top layer
0ec42131-47a7-55fb-9bdd-9870c6965d50 | note | – – – – – – – – – – – – – – – – –
62dc43a5-5f27-541e-8f71-64e28d22fd12 | note | CATEGORY: IP
a615cffa-76b9-5290-9473-7623cf21ef25 | note | – – – – – – – – – – – – – – – – –
fe17f4b8-a994-5c02-8c06-6fc0190706d2 | note | RESPONSIBILITY: SE/Site Supervisor
b63ac9d4-ff61-5208-b841-765d05cc3151 | note | – – – – – – – – – – – – – – – – –
9b6b9bf2-42c3-5846-9102-7cb779d5fb20 | note | VERIFYING DOCUMENTS: Sign ITP
6e7fa9b1-bd60-57bb-a761-46bb3167f5e3 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
33a1c0ea-a1a5-5ee1-af07-d4a403644b7a | note | REFERENCE: Section 204.03 (g), 204.16
35a82db5-0fea-540e-b91e-3e8fbd218ce0 | note | – – – – – – – – – – – – – – – – –
0640b48d-6a32-53fa-8202-d8058a76dbbf | note | ACCEPTANCE CRITERIA: Scale C: Tolerance: No point surface shall be more than 10mm above or 30mm below the specified level
5b60b06c-5e31-558d-9f70-b1c536e0371f | note | – – – – – – – – – – – – – – – – –
8a3a9264-e302-5461-83ef-65e94feed7a2 | note | METHOD: Document Review
1a7e16ec-053e-5abe-8ce7-f1b48a960611 | note | – – – – – – – – – – – – – – – – –
7f39f077-50eb-5495-9844-9ce28201d061 | note | FREQUENCY: Each lot
3b155158-ecb7-5938-a1ea-9af2109e57d5 | note | – – – – – – – – – – – – – – – – –
468bbba1-b5c0-56e7-ab61-ad895ba881ca | note | CATEGORY: IP
dcf3dc1a-5ecd-5d2c-8756-7fda93960a5b | note | – – – – – – – – – – – – – – – – –
1183ae2a-8574-5a6e-b460-309b174f6c5b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
62e3b709-9103-5561-8489-309376b96a7d | note | – – – – – – – – – – – – – – – – –
d592a512-e97c-582b-b5a1-9763b7cd0841 | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
59f2ecc7-6cd7-5653-a824-f7f60072dac5 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
bd86881e-ab65-5f78-8e54-469da215f14e | note | REFERENCE: MRPA Quality Management Plan
4d303343-9c7e-547f-9204-67f2c6ebf82f | note | – – – – – – – – – – – – – – – – –
59475e00-246b-5504-97f4-ba9cc23bcb7c | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6e92d102-48d0-5477-9340-9ebdc629c1a8 | note | – – – – – – – – – – – – – – – – –
3f094878-e993-5a40-bdfc-127c804e0f67 | note | METHOD: Document Review
b9c231c8-74e0-596f-9233-20a541fddaed | note | – – – – – – – – – – – – – – – – –
61dd0102-90cc-504e-bbff-2258129c6eb7 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
d800afa2-5e98-5098-b25e-1659e6055684 | note | – – – – – – – – – – – – – – – – –
b3e33fe9-ae3b-50f7-ad26-d22e81c5b079 | note | CATEGORY: HP*
c08453ee-2a21-55aa-8245-5de7fc98532b | note | – – – – – – – – – – – – – – – – –
fb076b9e-f723-5888-a076-d93f92508a61 | note | RESPONSIBILITY: SE/PE/SPE
f4c1f7bb-4338-531f-b415-4e8bda8c6c0e | note | – – – – – – – – – – – – – – – – –
b096796a-7fc4-5f86-a5c1-609cc24896ef | note | VERIFYING DOCUMENTS: This ITP
081299b4-7023-507c-a76f-b31089c3c15b | date | Date Completed:
| checkpoint | Final Inspection
79d44fbd-896c-5776-800a-8bc155655d10 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
241d28f2-92d9-572e-baab-545ef3ee2f1b | textbox | Name:
d96ac934-92b8-5521-8da0-32863e4c1646 | textbox | Position:
91bd161f-e4e2-5896-8e3b-40a67cc1a480 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-111-CIV-SSB-Type A Fill-Road Rev 0 | itp | ITP-111-CIV-SSB-Type A Fill-Road | 7710b727-a508-445a-a3cf-8ec8891cb8d7
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7b0ed01d-9e0b-597b-afe9-a2d538472855 | note | Document Title: ITP-111-CIV-SSB-Type A Fill - Road
6fe550ff-54ba-5d42-b23f-df913b180904 | note | ITP Description: SSB-Type A Fill - Road
5422bfce-4876-56f3-b3c3-1d18c601e2b5 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
a98a1fa1-b9c0-5f71-8e74-fb43b938dada | note | Discipline (e.g. CIV/STR/RAIL): 111-CIV
7c288a76-7a42-59ad-a854-2982329dfcee | note | Revision Number: 0
7214c815-d3fd-5df7-9cbb-3b089280e258 | note | Revision Date: 24/11/2023
a2b2170c-4a14-5bb6-b995-b38f41794ad9 | note | ITP created by: Hiruni Wickramarathne
7438f737-42ec-50b3-83e7-d21fc2d0d8a5 | note | ITP approved for use by: Victor Mira
f04380e6-eea5-5900-aa28-8fe12b139f70 | note | 1.1 Non Dependent
b304ae4f-f74b-591d-aa72-af80b6d87b3f | note | Reference: IFC Drawings VicRoads Standard Section 176 (Sept 2008), VicRoads Section 204 (Dec 2015) Code of Practice RC500.20, Code of Practice RC500.5
| section | Preliminaries-Materials
| checkpoint | 2.1 Material Conformance
6acbc758-3ac4-58c5-8d91-6d8ec4425cdc | note | REFERENCE: Section 204.04 b) Table 204.041
20b259fd-04bd-5cfa-beeb-c6400f6c1b0c | note | – – – – – – – – – – – – – – – – –
0ab54a7f-d13e-52fc-9626-831e2bee91c6 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
8814ed27-cb56-5c47-b8df-1f796d7b44c5 | note | ○ Assigned CBR≥ 6%
c618994f-d815-5619-ad3e-9a59a56a2e78 | note | ○ Swell ≤ 1.5%
694f3ddf-68e9-54a3-83dc-4479451a0e81 | note | ○ Permeability ≤ 5X10-9 m/s
69006073-20fb-5fcc-a3df-1dd9f8ce972e | note | Grading:
74bce88b-c0af-5212-9be7-465a0d7e3c24 | note | ○ 75.0mm 100%
78b3a598-0963-57d1-918b-ba7ff61f0e0e | note | ○ 4.75mm 40-80%
4f903566-f292-5f96-bf58-5b891e2ba92c | note | ○ 0.075mm 10-40%
2963c0cf-ee05-58a8-b763-155017182ead | note | Reference: Material approval in Teambinder:
3b66f8b4-f673-51cb-a246-f7d152767690 | note | – – – – – – – – – – – – – – – – –
736640ed-1f3b-5f7f-a696-519dff88f0f6 | note | METHOD: Document Review
baa79aea-e7f4-5a81-997a-62185a24c3fe | note | – – – – – – – – – – – – – – – – –
5b07538f-43e2-5702-a1d7-58e685dfc7a4 | note | FREQUENCY: Once, for each material type
7273d381-0e52-52fd-9d72-7c3735bfb239 | note | – – – – – – – – – – – – – – – – –
619a3365-2507-5146-8966-f72f7806eb51 | note | CATEGORY: HP
c3c02877-a7b1-5cb0-82e0-5eae89dff17f | note | – – – – – – – – – – – – – – – – –
1983c06f-c615-5d61-b7dc-5bf901de9029 | note | RESPONSIBILITY: SE/Nominated Authority
ad568569-8f14-550f-a411-5d225eb74987 | note | – – – – – – – – – – – – – – – – –
e1fad065-288b-508f-8d13-516c56dfa2d3 | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
b3af119e-c18c-5984-85d5-f99fe9ec98fc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Pre-Commencement of Fill Works
4a08799e-7c61-593f-9d0c-5ee8d6e9cffb | note | REFERENCE: Section 204.10 (b)
b3f33c00-1d58-505c-b28e-880c5bc42226 | note | – – – – – – – – – – – – – – – – –
3fe2711f-3dc3-5b55-bc56-7e1862865da4 | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
bac81c96-bc7a-5ce1-bf65-8f8eb7b93209 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
a779dc1c-c10b-5fd4-9b1a-e15cae73b8e8 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
08724628-a985-5364-8842-a39f09b268b8 | note | Reference: Subgrade Preparation Lot Number:
e67b390f-237f-518a-af4f-40afc039af30 | note | – – – – – – – – – – – – – – – – –
50664ae8-9536-5293-91e0-c9a455a8f831 | note | METHOD: Visual Inspection
7d3ea42b-02de-5cbf-9146-0b6945bd0257 | note | – – – – – – – – – – – – – – – – –
6e3eab20-2014-567d-badc-f8f5d3d9ce1d | note | FREQUENCY: Prior to commencement of fill works
108d055f-61cd-57ec-9167-e04e1100f0f0 | note | – – – – – – – – – – – – – – – – –
68d97ba9-f134-5278-ab2e-6fa2b854273f | note | CATEGORY: HP
64c2ede0-5d98-5e4e-b854-b799a4232c28 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set Out
fed94f2f-3a7f-50c1-bc9a-a3827c566d82 | note | REFERENCE: Design Drawings
c9137c68-7d3e-5b85-b4d5-047c01d397f0 | note | – – – – – – – – – – – – – – – – –
779f660a-e905-5840-9141-4c42ffe5fd3e | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
650150fd-074c-5dbd-878f-1c92c1328e02 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
e77a37e2-84ca-5053-a62f-a3f6cbe2ff94 | note | – – – – – – – – – – – – – – – – –
74f2e95e-0046-585a-b4dc-f6e7ee3d5a3e | note | METHOD: Visual Inspection
719bad39-89ca-5a05-b1b5-9cb111b2abcd | note | – – – – – – – – – – – – – – – – –
470d44b0-9cf7-5649-b6e4-27c87efaac82 | note | FREQUENCY: Each lot prior to commencement
c551f42d-cb62-5511-b91f-6d61640db3c7 | note | – – – – – – – – – – – – – – – – –
e0358141-1b7d-5c8f-9e2c-d953682f3ff7 | note | CATEGORY: HP*
49809648-97c5-5d43-8e09-ed90024ecd4c | note | – – – – – – – – – – – – – – – – –
2bee308f-f3b1-55f7-8746-ec9b49ffface | note | RESPONSIBILITY: PE
fa242a4d-fcc9-53a6-a185-87c46b4c76a3 | note | – – – – – – – – – – – – – – – – –
5fa6a548-9979-5791-89e6-b5582839f85a | note | VERIFYING DOCUMENTS: Signed ITP, Lot Map
67553c64-6303-5111-8772-943dd997657c | date | Date Completed:
| section | Type A Fill/Verge Activities
| checkpoint | 5.1 Placing of Fill
60492459-c74d-51e3-b789-2b25ab1be999 | note | REFERENCE: Section 204.10
ea2fd678-a0f6-58bb-8331-53415d6768b4 | note | – – – – – – – – – – – – – – – – –
7173c115-5896-5419-801e-1b935abf5038 | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
2f486c07-30b2-5e82-9a57-5dc655d62562 | note | – – – – – – – – – – – – – – – – –
13503d29-6960-5b2a-b6bb-18ac62c2d570 | note | METHOD: Visual
e1c80533-1e2e-5d99-80ed-197a8257ba19 | note | – – – – – – – – – – – – – – – – –
d322a590-a1a6-5172-be0f-da69208948b0 | note | FREQUENCY: Each Lot
01550c45-da43-5399-834d-a6c96a110d43 | note | – – – – – – – – – – – – – – – – –
a283b000-c03e-5d4e-8890-128fcadb5418 | note | CATEGORY: WP
0a335f52-eadf-5e79-a2bb-c34d3ea3dfa5 | note | – – – – – – – – – – – – – – – – –
b3ae8c3a-0f85-5058-9d5b-6432b25409d9 | note | RESPONSIBILITY: SE/Site Supervisor
871041d5-6484-5904-8699-2dcde80cabdf | note | – – – – – – – – – – – – – – – – –
16f86063-14b3-5d45-b939-0edf0dc45b1e | note | VERIFYING DOCUMENTS: Sign ITP
fc6ddce3-abca-56de-bd25-7eee676748d7 | date | Date Completed:
| checkpoint | 5.2 Test Roll
8840c685-d301-5cfa-8d01-0b01e70d6f46 | note | REFERENCE: Section 173.03, Section 204.12
0c1b5e23-8c4b-5df8-915f-dd001de84c08 | note | – – – – – – – – – – – – – – – – –
64fe781b-ab5c-5022-a0cc-cd592c91f1dc | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
46219b2a-72f5-540f-96d3-b345a06c7e94 | note | – – – – – – – – – – – – – – – – –
0d9af085-ddf2-58c1-be3e-eccdac2665ed | note | METHOD: Test Roll as per 173.03
ba8d83e6-5976-5b68-9a39-d2ab6627d309 | note | – – – – – – – – – – – – – – – – –
cf2b24ef-6f02-5913-aa5a-1b386f12b413 | note | FREQUENCY: Each Lot/Layer
5d58a843-7843-5b28-bab4-d79be91a175d | note | – – – – – – – – – – – – – – – – –
6a88659c-6568-5248-a1e1-7b0f83cd726b | note | CATEGORY: HP
eed56307-6388-5c39-a412-32e2549f6e27 | note | – – – – – – – – – – – – – – – – –
0995a9da-db55-5dc3-9bcf-465365aa3346 | note | RESPONSIBILITY: SE/Nominated Authority
c0895674-ff20-5a66-b0dd-b73868dfaa0b | note | – – – – – – – – – – – – – – – – –
a9b83bbb-1926-5407-9e72-e9db5b0f974a | note | VERIFYING DOCUMENTS: Sign ITP
72da1e38-9bb1-5362-a1ec-bc9e7b0df082 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Compaction Testing
f451855a-855d-5d07-9e6b-0ef6c8b0c9be | note | REFERENCE: Table 204.131, Section 204.14 c) Table 204.142
3a496e3f-dbdd-500e-be23-dbf86fe5dc97 | note | – – – – – – – – – – – – – – – – –
a2225958-b491-501b-a058-ccfe27744a7a | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
218292b8-3d16-58a0-ad73-70be755fd97d | note | ○ Standard Compactive Effort
038b2eb8-3b1f-5b3e-9d2f-36814476c34e | note | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
b4706ebb-6546-5ea9-8f30-8ca8d2550000 | note | Compaction and Moisture content
5a3a0ec1-16df-51b4-9f1b-ec4bd4f0056f | note | Scale A: Characteristic Density Ratio 99%.
99f1c526-eefe-572f-85e7-a8ff58b51c1c | note | Scale B: Characteristic Density Ratio 98%.
ff0b6cdb-8f0c-5d7e-afd2-5aa2d62e2c71 | note | Scale C: Mean Value of Density Ratio: 100%
e21a7543-ef78-599f-b4f6-2a9203d8990e | note | Lot size - the lesser of one day's production or 5,000sqm
59615c60-9771-592e-acb4-40cca4aad1bd | note | ATTACH: COMPACTION TEST RESULTS
80955259-9b2e-5c4f-a76a-cb95cfd7d059 | note | – – – – – – – – – – – – – – – – –
5a24eabb-1115-5dca-bebd-ae809e75bafe | note | METHOD: Review Document
faac6a7a-2cb0-5a71-abfd-978ca4f226da | note | – – – – – – – – – – – – – – – – –
4939a9c6-09ac-5687-aa23-4ef6b1df9a1c | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
2b322580-a443-5b13-bbe3-66487754c7de | note | – – – – – – – – – – – – – – – – –
aa614b63-c0d0-59a4-a0ff-c5950a813f11 | note | CATEGORY: IP
c0916bba-1737-5a6e-a14a-c44f4f2f4dae | note | – – – – – – – – – – – – – – – – –
4c0d724a-3c0e-5984-88bb-3b3d409ac88e | note | RESPONSIBILITY: SE/Site Supervisor
22ba17a5-0883-5ea2-b51f-00e606a8a5e5 | note | – – – – – – – – – – – – – – – – –
c2a4570f-9e23-5f9f-a932-88e0bf614e66 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
c012431a-0700-55ba-ad65-a9b491e48c74 | date | Date Completed:
| checkpoint | 5.4 Preparation of final surface
e9353454-f7fd-5450-be8c-352c21a21e64 | note | REFERENCE: Section 204.15, 204.03 (g)
44fee8d8-838f-53b4-b555-56ac10af2953 | note | – – – – – – – – – – – – – – – – –
43cf727f-3709-5eaf-8370-189abdb74580 | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
87c8fc5f-d69a-559e-b29b-6a1a3e5b7a5f | note | – – – – – – – – – – – – – – – – –
4aebfe75-02eb-59d8-ab9e-e729682b451c | note | METHOD: Measure
b733d541-0c66-50bb-a3d1-66bff4d4721d | note | – – – – – – – – – – – – – – – – –
7e85bae6-9d56-5246-bf1e-c2faaabee780 | note | FREQUENCY: Top layer
b391a4d4-e1d3-5594-998e-11f2f4cf1ff6 | note | – – – – – – – – – – – – – – – – –
483edbbb-df70-54f6-910c-21bd01a1bab5 | note | CATEGORY: IP
e54b36d9-47da-5c42-8b91-6028680475a7 | note | – – – – – – – – – – – – – – – – –
e6fb281e-5c96-5013-a938-500c42dc1d85 | note | VERIFYING DOCUMENTS: Signed ITP
0d80a005-ab7c-504d-9023-14a577259da1 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.2 Survey Conformance
9c097bef-69ad-5139-8848-04f1fef504d4 | note | REFERENCE: VicRoads 204.03f,g and h
45b9427e-0fa7-5633-83a9-e0bb8709ee6e | note | – – – – – – – – – – – – – – – – –
995d00e9-931f-5531-9042-240c317d9276 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
741f145c-eb18-599f-b9b3-88c314dc5907 | note | Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
3df30cdd-810a-589f-b5fd-fd0b6466a6b6 | note | – – – – – – – – – – – – – – – – –
89ca628a-1c89-54e6-9a77-e61bf9e58691 | note | METHOD: Document Review
74c5f0d6-65c9-5cff-aa88-dd698bff4286 | note | – – – – – – – – – – – – – – – – –
3a5ae890-0dc2-58e3-9ef0-667481f0b5f3 | note | FREQUENCY: Top of Type A/Verge
4e42c783-bbbc-5e9b-8bc6-197c2d727e50 | note | – – – – – – – – – – – – – – – – –
0298cd73-dd40-5b0c-8e39-7ffa095b04c3 | note | CATEGORY: IP
85fe74a4-e5c8-50b5-a0d4-1d072c42e666 | note | – – – – – – – – – – – – – – – – –
1091be68-223f-5b20-915d-59820a05bea1 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
97b60292-6e5d-55f8-8127-16a49c96735d | note | – – – – – – – – – – – – – – – – –
ae4b5b3f-43fc-5298-ade3-316d961caeeb | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
09648b85-dbdd-58f0-8c5c-095b0ba71843 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
f97f234b-687c-5f43-a574-a46115951f20 | note | REFERENCE: MRPA Quality Management Plan
4a8b89ba-9c0f-537c-bd86-2d1c711b1280 | note | – – – – – – – – – – – – – – – – –
97c60bad-e515-5611-abf5-9f1684c25fbe | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
1d350e50-a689-5ddb-93cf-b211d729a2e9 | note | – – – – – – – – – – – – – – – – –
9201dcc2-2cd3-59bd-b552-c9d7b0b4fdb5 | note | METHOD: Document Review
e4e1c6f5-10d2-5d0e-bbb3-f8c90ce722f6 | note | – – – – – – – – – – – – – – – – –
d3637be9-0153-503a-8588-6d8b550d8c0e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
6301a7d0-0800-52f0-a115-aec07c437b0e | note | – – – – – – – – – – – – – – – – –
b313e75b-b42f-5e8b-88b9-896c5d576daa | note | CATEGORY: HP*
f82d6b40-706b-51bf-9d5e-08016ac8e899 | note | – – – – – – – – – – – – – – – – –
97a3de9d-ce43-5e8a-8650-6dfc126a1744 | note | RESPONSIBILITY: SE/PE/SPE
7f13bf6d-f681-50a7-87d5-b191293c12b2 | note | – – – – – – – – – – – – – – – – –
ff6ee77d-a0f6-59b3-a707-a7c4b29d7eda | note | VERIFYING DOCUMENTS: This ITP
6b4f6877-b1c9-566a-b869-1890ae6b5d1c | date | Date Completed:
| checkpoint | Final Inspection
689d0967-d554-5b51-9756-696bd1dc47ee | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2ace93ea-daca-5f74-ae4e-3657a2ae19da | textbox | Name:
a46217eb-0ba3-5b9e-880d-73e786916a2b | textbox | Position:
19089550-f35f-5e85-9eaa-fb62f588ace5 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-133-STR-SSB-Structural concrete Rev 1 | itp | ITP-133-STR-SSB-Structural concrete | 53a7eae4-2a8c-4e47-bca6-04c89f1b7c4d
| section | Referenced Documentation
| checkpoint | Referenced Documentation
3617ce0a-f7b3-548e-8268-b2c8b7a12626 | note | Document Title: ITP-133-STR-CAMMS-Structural Concrete
3a9e34e3-8dbb-53a2-9325-ddfe7e19db5a | note | ITP Description: Structural Concrete
e57a94a5-387f-5323-8c06-9075e089671c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
21305406-3d32-5171-bb75-5ecf55dfb77c | note | Discipline (e.g. CIV/STR/RAIL): 133-STR-CAMMS
da9b291f-1e57-5bce-97ec-440adb54db81 | note | Revision Number: 0
6541a096-20d6-55c8-bf2e-c937ed307ac9 | note | Revision Date: 8/02/2024
f3e46dab-1dad-5348-8dda-6bbb20c36c3f | note | ITP created by: Iyasu Enoro
34ae75b3-5b99-5162-ada1-b011f8b323b8 | note | ITP approved for use by: Victor Mira
cbbf10d1-294e-5d02-ae18-566f17f883cb | note | 1.1 Non Dependent
caa04885-52ff-57b8-8198-115309927cd2 | note | Reference: VicRoads Section 602 October 2007
c404ecaf-fea3-5156-97fc-d569fa45f539 | note | 1.2 Non Dependent
aaea576b-3ccf-577a-9a0c-ee5e9b8d3404 | note | Reference: VicRoads Section 610 February 2020
f9afbce4-e9ff-5544-8862-141fb4371ca4 | note | 1.3 Non Dependent
6c643811-3dbe-59bd-8281-4fd0d7b6fc93 | note | Reference: VicRoads Section 611 November 2018
22e7d66c-f7f1-5514-b510-22b577e8bb12 | note | 1.4 Non Dependent
f68009ad-c4d7-551c-aa00-c869d96ecd34 | note | Reference: VicRoads Section 614 June 2017
6475064a-77f8-52ca-83bc-657794622eee | note | 1.5 Non Dependent
ba9694f2-e8f2-592f-8322-0fef609da647 | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
18a6b5d4-f202-59a7-9b93-bd2401e979ec | note | REFERENCE: 610.07, Table 610.071, IFC Drawings
62bfa5d0-b4fb-57ab-af0f-ace58a311b0e | note | – – – – – – – – – – – – – – – – –
18cd4c66-cba9-5c3c-ba3c-9e9cf11fc54b | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
4fff605f-632c-55d9-89b2-98745acf1298 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
e84e266e-085d-5555-8e74-6148e8a69a63 | textbox | Enter: Teambinder Material Approval number
33249643-ba3d-5e7e-95c4-5ce1ab247bca | note | – – – – – – – – – – – – – – – – –
36f47d36-83a7-55e3-a119-14a2da4f0245 | note | METHOD: Document Review
18c44e6d-8d06-5ebb-a81d-4ab717fce144 | note | – – – – – – – – – – – – – – – – –
f837704f-4b6a-5265-ae0f-01717f7d93c3 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
b7dc8daa-d314-56b1-940a-bab3133efb73 | note | – – – – – – – – – – – – – – – – –
d317990c-8347-5a4d-ae35-2f0b7cefc721 | note | CATEGORY: HP
26423c1c-0c22-56fe-a0ad-54738d15822c | note | – – – – – – – – – – – – – – – – –
670fac2f-197f-5f0f-8640-3308c00616b0 | note | RESPONSIBILITY: Nominated Authority
83e9b1c5-7f7e-56ec-a2dd-50796beb342b | note | – – – – – – – – – – – – – – – – –
c2fc748c-794a-50c0-bb30-c551fc7db14a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4f70eee1-a005-5422-b6b3-d37e3aaef5ea | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
56434563-8375-5880-be11-626ca2b66a65 | note | REFERENCE: 611.05 (a)
fe664fd3-ffaa-54fd-9737-6a660a40d242 | note | – – – – – – – – – – – – – – – – –
bae02d4f-d4cc-5d86-a538-46896ba32da3 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
4b2160f7-7602-542f-ba21-bf17bb9b1aa9 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
25409886-af99-5923-83b4-57cd03ceee67 | textbox | Enter: Teambinder Material Approval number
03515f44-0008-5818-95bc-b2ad2147aa16 | note | – – – – – – – – – – – – – – – – –
b6de3505-d03d-5f80-88f4-6807489df3c8 | note | METHOD: Document Review
1d17dc86-07a3-5fdb-9de1-f880ff05cba9 | note | – – – – – – – – – – – – – – – – –
ee942b53-3b2f-5573-aba3-4ea50efe7b8f | note | FREQUENCY: Once for each supplier, 14 days of award of contract
b2174777-2fd7-5257-aca0-fcb41b52b2c5 | note | – – – – – – – – – – – – – – – – –
6c28f9fa-f000-5acf-979f-898b83134d78 | note | CATEGORY: HP
27063d47-bae6-57d7-ac60-afc7468c50b6 | note | – – – – – – – – – – – – – – – – –
e3e8c2a6-6362-5028-96ae-c2c9803c1967 | note | RESPONSIBILITY: Nominated Authority
ce6ada9f-e64f-5135-800b-8bd0094a3d5f | note | – – – – – – – – – – – – – – – – –
f870dd2e-5a7d-5226-ac3b-b0a61f2d837f | note | VERIFYING DOCUMENTS: This ITP
6b5dcaeb-a04c-587e-a3f1-5945d9334614 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
4a26950b-7f51-55ee-9ac0-fbc967c4c3d4 | note | REFERENCE: 610.26 (a)
80848350-222b-5c87-a84e-d4be3e3a5214 | note | – – – – – – – – – – – – – – – – –
c14bf559-38b4-558a-b267-28037fb84306 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
249d0f72-5cef-5e21-8b98-109c2af9c6c9 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
cca9a073-11c4-5cea-bf21-4ce8478a32b2 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
aec07bb9-9c4a-5205-ad1e-24031b788d13 | textbox | Enter: Teambinder Material Approval number
c9a25040-a198-5bc4-a9dd-24cdc8a44d47 | note | – – – – – – – – – – – – – – – – –
9f05de0a-e943-5d5a-866f-98afc8c4d3b8 | note | METHOD: Document Review
388d8abf-594c-597d-9659-0f7328a21eb8 | note | – – – – – – – – – – – – – – – – –
4a9652a1-e4ba-56a7-977f-28a1ea9855b5 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
597c113e-6d72-5e6e-88fe-94a789a28681 | note | – – – – – – – – – – – – – – – – –
a23ef16f-88bd-5b57-be57-cdd94807d374 | note | CATEGORY: HP
9611cb89-6c71-5d26-bd16-17a06663f6be | note | – – – – – – – – – – – – – – – – –
ac7ef350-50bf-50ab-b279-2f222b53b660 | note | RESPONSIBILITY: Nominated Authority
689c2d60-c790-5e10-8690-1f625ca96b66 | note | – – – – – – – – – – – – – – – – –
a48d0209-c754-5b2f-b13f-7b03cd892d09 | note | VERIFYING DOCUMENTS: This ITP
d9b7fd26-b7f6-5af5-882b-834a46912137 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
7dd7d90a-9b17-5b1f-a3ba-ac0d276c72f1 | note | REFERENCE: 610.17 (f)
da3a5733-827b-5872-9df6-2dc994dc7807 | note | – – – – – – – – – – – – – – – – –
f075f242-bbae-5703-a86b-f6db6e33c0e0 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
efeeabae-51cc-5aa9-bdf0-ca46d6ee1144 | textbox | Enter: Teambinder Material Approval number
206abcd7-addf-545f-bdd4-5cb7e9446539 | note | – – – – – – – – – – – – – – – – –
bb292ffa-0aaa-5aea-b104-a34401df9c3b | note | METHOD: Document Review
8567f9c3-143a-5fc5-9515-9a2d8e02de2b | note | – – – – – – – – – – – – – – – – –
c42c865d-d24f-5139-bedc-dc7c3a930c7d | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
70893350-a83e-552d-872a-62b92cd72e32 | note | – – – – – – – – – – – – – – – – –
b71ba94b-dee2-50f1-b3f9-f3cab86a0f83 | note | CATEGORY: HP
a05703a8-93c5-5eaf-8f29-6007303cd65a | note | – – – – – – – – – – – – – – – – –
2b9d23ed-aee7-52ab-92fd-f1ccadc5ee3d | note | RESPONSIBILITY: Nominated Authority
8a2151de-1c2d-5579-aaf6-cd474deed4fb | note | – – – – – – – – – – – – – – – – –
c4282269-8134-5bf8-9406-ef83ef2d322e | note | VERIFYING DOCUMENTS: This ITP
5638e6b5-011f-5a6d-b342-8b0de656b6d7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
7ebbd610-2ba9-54e4-ad2b-6031fd81d732 | note | REFERENCE: 610.23 (d)
7fdeb5d2-ed98-5b0c-892f-5db27798ac55 | note | – – – – – – – – – – – – – – – – –
e8b8c564-3c9f-5aea-a635-74eb464975ad | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
2f61cc7c-3c40-5401-aca2-c086bf3f636e | textbox | Enter: Teambinder Material Approval number
cc42a900-2dc1-52d6-8568-0b5d6530f1b4 | note | – – – – – – – – – – – – – – – – –
f53851ed-87c9-5e0c-a2c0-f726b0a0d199 | note | METHOD: Document Review
19b35606-363e-56a1-a20d-2fe788bc8560 | note | – – – – – – – – – – – – – – – – –
988cdcb7-d376-53ce-8d4a-6c8fcb303778 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
f1c64ebd-8762-542a-8b12-ff6df004e791 | note | – – – – – – – – – – – – – – – – –
12ed6048-86fc-5f90-a229-1c89f8c9f791 | note | CATEGORY: HP
20d77c8e-7dbc-5f49-93fd-c5d7534c4e76 | note | – – – – – – – – – – – – – – – – –
cc321b92-84d1-5e79-b481-6e764203b93f | note | RESPONSIBILITY: Nominated Authority
f80a3973-c594-53ad-969f-73681e2a667a | note | – – – – – – – – – – – – – – – – –
0d0269c1-4b0e-5765-b64c-5bee0868497c | note | VERIFYING DOCUMENTS: This ITP
53b18ec2-3293-504b-90db-50f4df50d3c5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
632b1ea6-4b6d-5bd9-9001-8cc59655c607 | note | REFERENCE: 610.18 (a) (i)
581d4b87-2223-51d8-a301-c50316e01e4f | note | – – – – – – – – – – – – – – – – –
00658e84-b8ff-53d2-a458-21441a35bc26 | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
e483756b-2e29-525a-be7f-7b2bd3f1dec3 | textbox | Enter: Teambinder Approval number
577b0e00-075a-51e2-a45e-200ff94bf559 | note | – – – – – – – – – – – – – – – – –
f03601c0-975b-5f4c-8c96-38c04074b90b | note | METHOD: Document Review
5b5513ea-fa52-5823-8696-443d381fbc41 | note | – – – – – – – – – – – – – – – – –
6e7ff9a9-37aa-53e2-af37-595e61bc2a53 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
98fadfc4-5ff7-5816-88dd-880f0f087da7 | note | – – – – – – – – – – – – – – – – –
d8155cb9-46c9-5e36-a287-8b0d4900d330 | note | CATEGORY: HP
56adf78f-f85b-53d9-9f09-a1ec83c4116a | note | – – – – – – – – – – – – – – – – –
e3ae0ff3-0bf7-58c8-ba7a-cf4e3361e59d | note | RESPONSIBILITY: Nominated Authority
5a906e92-0cf2-5ac9-8f6f-9308517d5b02 | note | – – – – – – – – – – – – – – – – –
350a82d0-9a5e-5872-8b00-ce3085f24611 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5c533eb8-1bc7-5284-b9e1-3013d87006d4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
e0e8c368-1dfd-5501-b7eb-365fb406538a | note | REFERENCE: 610.18 (a) (v)
99cb1c07-458b-5e3e-8980-417f243947f4 | note | – – – – – – – – – – – – – – – – –
6305c4f4-a305-58c6-a851-087fc1635775 | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
3066dad7-8ee5-587b-b5e2-f249525fc2fd | textbox | Enter: Teambinder Approval number
53b8d1f4-7119-56cb-9419-068dca622ae0 | note | – – – – – – – – – – – – – – – – –
7f9a64fa-1f8c-5c30-be03-f3ceca059b00 | note | METHOD: Document Review
a7abd993-fca5-57a7-8a62-1f3ebddda095 | note | – – – – – – – – – – – – – – – – –
7318a5ff-6de5-52e4-9f1b-6c147d92a27a | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
079d03a2-7d5a-582e-9292-12d716da7ade | note | – – – – – – – – – – – – – – – – –
625926a9-2a95-5bfa-ac11-6d425064ba79 | note | CATEGORY: HP
299058bc-c255-5892-99e0-18da4ff3fe84 | note | – – – – – – – – – – – – – – – – –
b6683516-9e7a-5a23-ae3b-96e2eee7df33 | note | RESPONSIBILITY: Nominated Authority
64332483-3c49-58ea-a00f-47b6cdbb294d | note | – – – – – – – – – – – – – – – – –
f3958f59-9f1a-5eb6-823d-d7f4e292cd33 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ceaf9442-a3e5-58e6-a73a-4e1e6cce028b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
9287d04c-3352-5613-ac58-52fdd4a40442 | note | REFERENCE: 610.18 (a) (iv)
4f52013d-746b-57f9-bab9-9b02b709f381 | note | – – – – – – – – – – – – – – – – –
4451dae8-501c-501e-bec7-67ee3ac9c6b7 | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
b38a0729-6931-5318-a471-c01addcc15a1 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
c4662b56-d5a2-5b64-b811-6bae353fb69f | textbox | Enter: Teambinder Approval number
4267c090-ff78-560a-8a30-7e24e87808f1 | note | – – – – – – – – – – – – – – – – –
e4c116d6-54a3-5251-8281-c34c53d56567 | note | METHOD: Document Review
2866f510-ee4b-57d1-927f-58c6f17d853b | note | – – – – – – – – – – – – – – – – –
77cd39b7-4e6b-50c0-b3ce-ea6af8c03f89 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
d1754fea-abf6-5d4f-b079-f88eb0d353d7 | note | – – – – – – – – – – – – – – – – –
fb6ea59b-38c1-5c21-afc7-83d0075a429a | note | CATEGORY: HP
1adbd660-d30a-5973-9d66-bf1275bcc90a | note | – – – – – – – – – – – – – – – – –
9c2e07d1-7f63-5e0c-9b91-bceaae02df6d | note | RESPONSIBILITY: Nominated Authority
949fb72c-920f-510e-b655-0579dfa39ac5 | note | – – – – – – – – – – – – – – – – –
dd75bc65-5595-5f95-b570-661416eadaeb | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c5e57bdb-3dc4-5196-9c73-135f39e4d61f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
10b5da00-4e8e-575c-8a6c-23f41dd956b5 | note | REFERENCE: 610.17 (a)
6d0db8c0-cfd5-5caa-bb15-0a3972ad7887 | note | – – – – – – – – – – – – – – – – –
1f9aeeef-e1f7-573e-a312-ccf118a64760 | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
4cda3a38-9881-568c-be08-107ff7dd15a3 | textbox | Enter: Teambinder Approval number
de8e08ce-dd34-502b-8bfc-81fb7f514aac | note | – – – – – – – – – – – – – – – – –
b896b046-77d4-5d0b-8a15-9c905d70965a | note | METHOD: Document Review
aa3ac717-6307-5e15-8924-ef09983233b4 | note | – – – – – – – – – – – – – – – – –
af1fb91a-3800-55b3-9729-a5974a9a4d6c | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
481b81cf-375c-517f-8008-ea056952cc0e | note | – – – – – – – – – – – – – – – – –
02d26eb7-0261-5efa-a2af-3b33dc413fc6 | note | CATEGORY: HP
b36c6baa-fe48-56cf-a3d8-6ed5583d6e08 | note | – – – – – – – – – – – – – – – – –
bf4ba29d-8325-5ebb-aaaa-a8a297a3a92b | note | RESPONSIBILITY: Nominated Authority
47d84d77-716a-5f7b-968a-c5c325ef9ed1 | note | – – – – – – – – – – – – – – – – –
1650d610-b4ca-5fe8-a312-2e1754ea565a | note | VERIFYING DOCUMENTS: This ITP
dda03089-e720-5f52-98c7-e87bf23cda3f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
546e9e59-02fa-55cd-91cd-477824926d2e | note | REFERENCE: 610.23 (a)
198f6ed1-da4b-5957-bf8d-03e3b95d7f4c | note | – – – – – – – – – – – – – – – – –
0596029f-a124-5219-8a2d-4f6074edd3ef | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
3dc8f208-44ac-5595-92c9-f0829e904593 | textbox | Enter: Teambinder Approval number
534664d8-d75d-5437-98f3-a3f4085e1a90 | note | – – – – – – – – – – – – – – – – –
df0b402f-18e7-508c-be9a-4e18c662b2c7 | note | METHOD: Document Review
4b147056-bd05-5b46-bcbd-7bf2d22fac04 | note | – – – – – – – – – – – – – – – – –
678b2c66-d2c0-513c-9d11-83858364cab1 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
52697f01-cd25-5358-bb43-d5ecd93ba1b5 | note | – – – – – – – – – – – – – – – – –
2b35d2ea-0181-5fc7-a2f9-1f1848139520 | note | CATEGORY: HP
8a05c230-bc12-562a-a403-1ea50c55603c | note | – – – – – – – – – – – – – – – – –
867d90ff-4f6d-5a19-9aa9-c1eaee726d60 | note | RESPONSIBILITY: Nominated Authority
898d6818-8988-5f36-95c9-1bc5782f9348 | note | – – – – – – – – – – – – – – – – –
92511afa-ac67-505f-8a33-28b4be0b5e8e | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
af807591-5069-5d67-9608-ec293a4e5377 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Concrete Drilling Procedure
67386919-07a2-5f15-9ebf-92ca0dcc1b33 | note | REFERENCE: 610.46
72488c75-927e-520f-a3b5-c2b3f1024547 | note | – – – – – – – – – – – – – – – – –
305632b4-2c1f-52d2-876b-25e3b87ecc04 | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
853b364c-6e51-544b-8a11-ab618d9af539 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
7df266b1-6a66-555e-9f19-365237208a20 | textbox | Enter: Teambinder Approval number
6c833848-5240-5000-813b-49bd528915c1 | note | – – – – – – – – – – – – – – – – –
75694289-ab85-5d9b-a3f6-b4b7080dcbc3 | note | METHOD: Document Review
96cf7811-86e0-5fed-a5f8-7bf23f159b33 | note | – – – – – – – – – – – – – – – – –
edc1d3a4-8bde-554e-95ca-e7c3777c04a6 | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
9b4271b0-3ef1-50a8-83f8-fa2f169527ae | note | – – – – – – – – – – – – – – – – –
d2d3beca-c920-5e90-acdc-e7f0a24f0faa | note | CATEGORY: HP
3c9d4a76-4150-502c-bfd4-f0f13300917d | note | – – – – – – – – – – – – – – – – –
42e5390e-b9c4-5da7-ac06-accf59d2d5d3 | note | RESPONSIBILITY: Nominated Authority
54a2f26e-93e3-504d-ba17-acfb6b18caf0 | note | – – – – – – – – – – – – – – – – –
9739e546-1709-5279-8241-097dd370c257 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5761771b-21ff-5160-bc33-15e0156c8a8a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Temprature difference measuring-Calibration
9b297b0b-c582-5415-82e3-e10c9813bee8 | note | REFERENCE: MRPA Quality Management Plan
f025bd66-4874-5c50-8e2f-0e6f24ff840e | note | – – – – – – – – – – – – – – – – –
fe6a24f5-2641-5b85-a335-38c63455b658 | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
7c143489-250f-5197-bfde-498c7331e32d | note | Attach: Calibration certificate
cfc83ea9-7c39-5ef4-ac53-996e21de05f8 | note | – – – – – – – – – – – – – – – – –
10f3e4b7-820f-5a47-995c-3e30d117b736 | note | METHOD: Document review
63ed4198-c191-572d-950f-a8165b9a7b1d | note | – – – – – – – – – – – – – – – – –
6b08356c-852d-53ef-bf8b-adb48d1e9730 | note | FREQUENCY: Where applicable
3c62b04f-6c34-52f8-87c3-39d934c76e32 | note | – – – – – – – – – – – – – – – – –
a084602f-cd23-5425-b603-b32359c93b8a | note | CATEGORY: HP*
8ded140a-4f6d-5b6d-8d6a-27d995243cc6 | note | – – – – – – – – – – – – – – – – –
7d6a61ab-36b9-5313-8eff-51caa8dc7c3d | note | RESPONSIBILITY: PE
f523ce56-ec9e-56f4-b853-d1fc417e2b1b | note | – – – – – – – – – – – – – – – – –
1669e1a3-963e-53de-bcc7-8c69b758469f | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
fc74f4e5-eab2-5dc6-8045-a8e4ef4f663c | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
228571e7-4d30-5326-a5ed-991bec3aac95 | note | REFERENCE: MRPA Quality Management Plan
c881977d-4c16-5ef0-b570-14e957a0d2a4 | note | – – – – – – – – – – – – – – – – –
a506ed15-cd97-513e-807a-8fcf0749ca2f | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
60d8c406-1961-54b2-9b1a-c22934e3dc0a | note | – – – – – – – – – – – – – – – – –
d100728d-b7ed-51f5-bbfc-fffcaa54d75b | note | METHOD: Document Review
d19f064e-9774-5c54-8bf7-74fe92b5be99 | note | – – – – – – – – – – – – – – – – –
4fc953d4-749a-5623-9e2f-c518d550a7bd | note | FREQUENCY: Prior to starting Works and at regular intervals
38f9e019-f5c2-5e25-8ad6-cd4e4759e189 | note | – – – – – – – – – – – – – – – – –
fd694c3a-b938-51f0-8d39-8b2d0e5936b7 | note | CATEGORY: HP*
ff98d5d5-fa20-58ac-b98e-da042b6a90ef | note | – – – – – – – – – – – – – – – – –
89357b38-31db-5bbe-af46-00c11425ba3a | note | RESPONSIBILITY: All
d6a8b424-a7cd-5694-b81e-a87ff7439035 | note | – – – – – – – – – – – – – – – – –
8300f86b-b554-5545-8c4c-d2bf6b828f6f | note | VERIFYING DOCUMENTS: This ITP
304e09c0-2066-5345-a1b7-7e8fc3e5715d | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
cf018bb8-4ba3-5631-9f34-9f73c92fb28a | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
81b8a8ba-f731-5c6b-b67b-608d991e3f6a | note | – – – – – – – – – – – – – – – – –
830b30f4-caf5-5dca-af75-7b2dfeb9439e | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
0e8d2852-69e7-532b-8d63-b7f5bf3785f8 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
c1751ce6-4359-574f-bf4a-6e8305a51877 | note | – – – – – – – – – – – – – – – – –
ca58b5d1-2373-5eae-9d83-55838382be22 | note | METHOD: Measure, Visual
0f159bd1-3054-5b1a-92b1-7072fc49251b | note | – – – – – – – – – – – – – – – – –
76666acf-2f23-5e0c-882a-473eea96efc3 | note | FREQUENCY: Each element
a3c96e9e-a98c-51a2-830e-4fe8c66dca2a | note | – – – – – – – – – – – – – – – – –
8b173766-4e2c-56e6-8721-4fa7b66e32b8 | note | CATEGORY: IP
4175ea55-b8e1-5f59-8116-956042bca06e | note | – – – – – – – – – – – – – – – – –
cfad84e4-60d1-5ed4-9a71-f1111b8ef336 | note | RESPONSIBILITY: Surveyor, SE/PE
59ba58cf-e7b5-54bc-89c5-329c1e9a7afb | note | – – – – – – – – – – – – – – – – –
d16a0ffa-657a-543c-8e21-32b1c861905f | note | VERIFYING DOCUMENTS: This ITP
43c6b838-cf1b-5bb2-8838-5e94ebaa9440 | date | Date Completed:
| checkpoint | 4.3 Excavation support
689f3bfc-8a53-571c-b12e-d9221b15ae02 | note | REFERENCE: 602.02
8e09e336-74e3-594a-a1f0-14f7c5126baf | note | – – – – – – – – – – – – – – – – –
61fcfc2c-1123-5978-854d-ba428a711df6 | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
c2909fb8-5aed-5de6-bdaa-e681c04bebda | textbox | Enter: Teambinder Approval number
39b049e9-ce37-50a4-a1b2-570f9d1b9b51 | note | – – – – – – – – – – – – – – – – –
a0f8e2ae-a721-5343-8443-14102c217c6e | note | METHOD: Document Review
0739cb79-e528-5418-8d8e-f376dafb719d | note | – – – – – – – – – – – – – – – – –
061d0535-60f5-5060-90a4-10637fe498a5 | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
9c9d61fd-6f22-5d4f-9f6a-bc56b8494cb4 | note | – – – – – – – – – – – – – – – – –
e8c43c1d-a8e9-5b72-8fc2-30fac6e31d80 | note | CATEGORY: WP
44457bfa-8143-5ced-b370-67f490550242 | note | – – – – – – – – – – – – – – – – –
0a563983-b321-564e-9e62-51438c6ab8ad | note | RESPONSIBILITY: SE/PE/SPE
ba7591c4-dc57-5b2e-a65f-faf97fdb32cd | note | – – – – – – – – – – – – – – – – –
b8f3e8d2-c254-51fc-a578-4e00f53be441 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
44d38e9b-4fc0-599a-8c5f-197c86fb9102 | date | Date Completed:
| checkpoint | 4.4 Excavation Inspection
1ed51713-eb62-5ba5-a536-7cc321f51df7 | note | REFERENCE: 602.03
1eb899c6-6183-555c-98b6-44156f1fdd2f | note | – – – – – – – – – – – – – – – – –
b7c38f01-c8dd-56d5-98e9-018e7a4ff1bf | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
b957ff58-d5a0-53c0-bc85-41e246023971 | note | – – – – – – – – – – – – – – – – –
bac2468b-8345-56f4-a5ee-63ba2ff42440 | note | METHOD: Visual
94074fb5-3931-5467-a349-a4ac29b8e4f3 | note | – – – – – – – – – – – – – – – – –
5ead8f14-4e80-54c2-afa9-de56c42a5a0a | note | FREQUENCY: Where applicable, prior to placing blinding concrete
f5fa7215-872e-57f3-9a8b-a94fbfe25e8f | note | – – – – – – – – – – – – – – – – –
4f2e9b2d-cfe1-57ad-9cc2-ae47669fcc5f | note | CATEGORY: HP
706cdd4d-ed54-5162-8d8f-8d8939a867d0 | note | – – – – – – – – – – – – – – – – –
a8dc1f60-c3dd-585f-9870-98aa98cacddc | note | RESPONSIBILITY: Nominated Authority
910688e0-3d09-550f-ad64-93f6a0020257 | note | – – – – – – – – – – – – – – – – –
ff54eb6c-c4a7-538a-a498-c5c5bd241aee | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
afda0287-0c09-5a8c-adce-246f9e75d6aa | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
a57b2d38-5ae2-5464-8e25-dbcd378fad65 | note | REFERENCE: IFC Drawings
c5ee9cab-5e54-5057-a6b1-ab3c6bac2b81 | note | ○ 614.04
96fb0d0d-b588-539a-b9d9-67eac97fcce8 | note | ○ 614.05
1610eb5a-46ba-54d0-a98d-157c14eb78bb | note | ○ 614.06
d33f2b89-4745-59d4-b791-9222a801a025 | note | – – – – – – – – – – – – – – – – –
27b2d3cb-d8ef-5b8f-8371-74a3f2905898 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
8eda1a80-6005-5759-813a-095eb073ee2a | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
0347a7d2-b205-5835-b1e7-6ae2b1eecce5 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
fdf6a2b1-19bf-59e5-a3b6-efdc8b71faea | note | – – – – – – – – – – – – – – – – –
cd366b12-1f3a-515a-9cc1-9a1bc069549e | note | METHOD: Document Review, Visual, Measure
e4ee535e-acd7-5d10-b145-442e088c663c | note | – – – – – – – – – – – – – – – – –
89e72805-238f-5f48-8638-8edc188e085f | note | FREQUENCY: Each type of element
e56303c6-8da9-5029-bf4c-edb9fad2fa5b | note | – – – – – – – – – – – – – – – – –
1d46ec74-521d-5640-af62-0364bd6f18f7 | note | CATEGORY: IP
92736f37-2658-5178-9dd1-8252e1a8174a | note | – – – – – – – – – – – – – – – – –
d30061ac-ea7a-5381-88f3-ae58ef1429a3 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
db7a3c6b-e44b-549e-8d69-903c1899cb01 | note | – – – – – – – – – – – – – – – – –
0c526e70-ff26-5ef3-b4fc-b9f4bc467e19 | note | VERIFYING DOCUMENTS: This ITP
bf4e96d5-0fe2-54ed-b6d1-c3ad55318c7a | date | Date Completed:
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
215c9e07-a296-5dca-ad71-767b52d8841e | note | REFERENCE: 614.08
d0132289-3916-583a-a73b-8f9f73a30795 | note | – – – – – – – – – – – – – – – – –
68991295-a3ff-5cd8-a5c9-b35a3c6bfce4 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
0d238679-32da-5218-b12d-82d24731a0d5 | note | ○ Walls with heights greater than 2.0 metres
0c779dab-969a-5538-8ef6-553968107703 | note | ○ Any member for which self-compacting concrete is proposed.
37211f32-f44f-530e-9edb-81320976fb2a | note | Attach: Attachment A
73b0a59a-fb1b-5a39-8c66-180a91567f85 | note | Attach: Attachment B
5c17a99c-7513-5d2e-b27c-9281969ae017 | note | – – – – – – – – – – – – – – – – –
4f02a41c-05c9-563e-8780-708071101a20 | note | METHOD: Document Review, Visual, Measure
95ea7c81-49a3-521f-8bf1-1fa5cf357e02 | note | – – – – – – – – – – – – – – – – –
b26da431-7431-5aff-9f39-0db0c3db5540 | note | FREQUENCY: Each element (where greater than 2m)
40c7990c-0f99-5a91-8887-993693cb58f1 | note | – – – – – – – – – – – – – – – – –
6ef8346d-e65c-54c2-9879-059a4f267269 | note | CATEGORY: HP
0bfe2fa1-6df5-5bbe-b3c9-12199c0864d6 | note | – – – – – – – – – – – – – – – – –
273dc534-1602-5e56-9671-37fb50ecde3e | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
8d89316e-bbbe-5cfe-bed8-5a6fab6502e4 | note | – – – – – – – – – – – – – – – – –
504fddf0-474b-5b99-83ac-51d04db21377 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9cc4df0c-3b75-569b-add6-28aec85bbd0b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
9c759842-9472-5b95-a144-fd6e1bfbeee9 | note | REFERENCE: 614.08
e36b068c-51db-587e-813d-a9085c2d1ff7 | note | – – – – – – – – – – – – – – – – –
03ffd202-bf2f-595d-8316-dafb9e4bdfd7 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
0ef118df-a768-55ff-b745-ce9414c3cd98 | note | ○ Walls with heights less than 2.0 metres
b9c33267-4134-537c-b8c3-da161349e655 | note | Attach: Attachment C
4579743e-d3f2-5a58-a232-258a640f2623 | note | – – – – – – – – – – – – – – – – –
9083da68-567f-556e-b494-0187c5ecc1f4 | note | METHOD: Document Review, Visual, Measure
696788ea-2a1a-51b5-acbf-d1ab10841d5d | note | – – – – – – – – – – – – – – – – –
2d4c3d61-a5d4-5160-afbe-32bd9ae0a216 | note | FREQUENCY: Each element (where 2m or less)
9eacd631-780f-5e72-939a-89a60024ccb4 | note | – – – – – – – – – – – – – – – – –
fbb247d3-e798-5074-9b3c-06e7054ca745 | note | CATEGORY: HP
98122fff-c85d-5f7a-a3ec-ad22926f000e | note | – – – – – – – – – – – – – – – – –
0abbb8dd-3b51-50d7-87d9-0706d8920e7e | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
cc90f28e-782d-5809-82ef-dda5a7d3d658 | note | – – – – – – – – – – – – – – – – –
cf166c61-505e-56ab-999b-76c4af6c1604 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
fbfd1fbe-9f46-5dc4-9dc0-b896d5e5cf03 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
e87b4ea7-0b65-57cb-aca5-5e7c3551bfdb | note | REFERENCE: 610.47 (a), Table 610.472
a83465a6-eb88-5869-b566-1ffbae4ffd32 | note | – – – – – – – – – – – – – – – – –
dede3c59-ad57-505c-946b-abea844a99bf | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
7fda2bbb-2b2d-572e-987d-e14256e3f045 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
8533e936-046f-5ad1-81ac-4037ed072072 | note | – – – – – – – – – – – – – – – – –
cd5022a1-e205-5e0f-b52e-226cd798a079 | note | METHOD: Measure, Visual
86823f8a-c2ba-5795-9097-da0675e11ada | note | – – – – – – – – – – – – – – – – –
f8900018-bbab-5228-aaf4-97ef4663d4a7 | note | FREQUENCY: Each element
72ad85fc-6f73-572b-8045-760f29221254 | note | – – – – – – – – – – – – – – – – –
0e9d13eb-fc32-5fc0-9cb6-da9033ae2a0b | note | CATEGORY: HP*
0ea95999-5849-5efa-ad25-47d43a96d429 | note | – – – – – – – – – – – – – – – – –
1dd0482d-b79b-5b6a-9a93-a5f08dff073a | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
dc227623-914c-57fa-a142-c3a4575efb78 | note | – – – – – – – – – – – – – – – – –
dab56508-d392-52dd-8911-88c6d51666a1 | note | VERIFYING DOCUMENTS: This ITP
6dda4d50-7908-575a-a6c9-b0690e78365e | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement
a09b1cc3-64cb-54b8-b73f-a39af69ecd8d | note | REFERENCE: IFC Drawings
8cea1052-44c6-594e-9203-85045db837a2 | note | ○ 611.06
c2c464e3-10cd-595b-897a-aa223bb3f295 | note | ○ 611.09
9108de18-0600-5033-867c-7b96f77e5ab7 | note | ○ 611.10
7fc6681e-278e-547a-ab0d-f0f562536cf0 | note | ○ 611.11
f6922d07-bb6d-5bb7-948f-1031f7567732 | note | ○ 611.12
813bfc61-b1d5-5a81-9f2c-ebff0d8efc1e | note | – – – – – – – – – – – – – – – – –
392bbff2-7179-5a28-9de5-16e6aca2cc0c | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
9145bd8b-11d1-5c7d-86c3-b802e75fa627 | note | ○ Projecting reinforcement is the correct length and location.
99920efe-34fe-5a70-9f80-7e6f275eac24 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
93c2bfe1-fb41-5941-88d4-e4a287975a90 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
a8d2a962-da30-5734-89b8-235500c9dcd8 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
313db5c7-a176-5a93-8e6f-f60d1bd055a4 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
3b9894af-802c-5d31-8b7e-592b5373b8bd | note | – – – – – – – – – – – – – – – – –
b00c6c99-6c1c-5d1f-a012-fbbf9f4b6708 | note | METHOD: Measure, Visual
0b4066b7-83d2-526f-a38a-e1fce6ed07ea | note | – – – – – – – – – – – – – – – – –
914ba1c7-ef3b-5504-aa5e-3609752661fd | note | FREQUENCY: Each element
6c77a0c3-2413-5450-9113-7ea9a2b88a6b | note | – – – – – – – – – – – – – – – – –
c49bece4-26cc-5b5c-985c-9f0b58f57f46 | note | CATEGORY: IP
e62fc1a9-e681-58d8-acf6-4942c6b76a4c | note | – – – – – – – – – – – – – – – – –
748529c1-0096-5583-919b-36e853ec69f7 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
369e28c7-6034-5ef6-935e-3b90b0da5765 | note | – – – – – – – – – – – – – – – – –
ea3889ae-69a3-58ef-8ce8-7d2ac7efa73e | note | VERIFYING DOCUMENTS: This ITP
c6ce92c1-e291-599b-b829-108886d2cafd | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
8df2b242-8fc3-570b-b1a4-e38e867acad0 | note | REFERENCE: IFC Drawings
03cd870e-2b7b-5612-b077-d28158ea9137 | note | ○ 610.47 (a), Table 610.472
0b84fbe5-b4d1-5930-9893-d15ab9a0e072 | note | ○ AS3810.1 Table 3.3.6.2
90533280-b6b3-506a-9820-69fc9fd56f4a | note | – – – – – – – – – – – – – – – – –
b7692507-6f21-5f9c-8a9e-8266474edf88 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
06d2a469-f9a0-592c-95e1-f237a70aad65 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
347bc44f-20c6-5731-9510-df086284df2a | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
772d724f-3697-5b08-bb28-88a6b4c69a3f | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
72eec155-1f05-58df-a473-f27cadb322be | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
746259a7-a29c-57ac-acb6-b8504f97797a | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
598f33db-74dd-508e-93d4-014ae4715351 | note | ii. Running dimensions of a group of the above = ±6mm
91d6c0ce-0db4-5b95-bae2-7723ead97342 | note | iii. Ducts and conduit location = ±12mm
91816efc-f114-524e-9313-94c095139e02 | note | iv. Diameter of ducts and conduits = ±3mm
1d73c8ec-a285-5fb8-9c70-57643da1c866 | note | – – – – – – – – – – – – – – – – –
6279254a-e09b-5aca-99bb-b5db04df5d68 | note | METHOD: Measure, Visual
8d722559-f0e2-544d-9686-904a8f7d6519 | note | – – – – – – – – – – – – – – – – –
8139bc4f-6fcb-56c2-a7d2-f72365eb6c3e | note | FREQUENCY: Where applicable, each element
5238d028-3107-57b1-b3d7-fa23225cf2ef | note | – – – – – – – – – – – – – – – – –
830275db-1764-52a1-88c2-a5a40c4df49e | note | CATEGORY: IP
584063ec-8f0c-527d-b956-ab4dfcfe7f04 | note | – – – – – – – – – – – – – – – – –
f9f4e426-3f21-5533-96d2-88a241cb9dc9 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
28e7de03-3543-5445-abf0-7dd6b93e763a | note | – – – – – – – – – – – – – – – – –
b08d61ed-3c80-5b42-a57d-67c08f7ecb9c | note | VERIFYING DOCUMENTS: This ITP
4f05e13a-b77d-5d9b-ad08-b58ffcc265a6 | date | Date Completed:
| checkpoint | 5.7 Thermal Differential Monitoring
bc980bab-bb34-5d7c-9fa2-2e55ebe5cf61 | note | REFERENCE: 610.22
d799b5eb-7876-5e06-9eb1-15fd79afa661 | note | – – – – – – – – – – – – – – – – –
1fab0fca-0d31-5c9d-aadf-ed765303786a | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
fba7680a-e562-5ea8-b98f-5fcc07b258a1 | note | Only applicable if the element has:
a4b22af4-edb5-5231-81fd-77193d2a557f | note | i. the smallest sectional dimension exceeding 500mm
05d6a62e-4c1b-5030-a4cb-df471b0cdc2e | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
79d369df-892a-5a60-aa93-eb20351d08ad | note | – – – – – – – – – – – – – – – – –
e585f825-3112-5d08-a3b9-ef1f2582823e | note | METHOD: Measure
ee83ad63-86e5-5633-a4bf-d61e6cb28bef | note | – – – – – – – – – – – – – – – – –
1bd549e1-fc34-5650-bc5a-017f027f63d9 | note | FREQUENCY: Where applicable, each element
1c78aae9-0075-556b-a264-1c1691cacfc6 | note | – – – – – – – – – – – – – – – – –
6527ba10-bf54-5aff-8851-9bf600273ab3 | note | CATEGORY: IP
02675efc-3776-5972-9c88-6e457a96fd43 | note | – – – – – – – – – – – – – – – – –
6114411c-e461-5e9b-9e56-a1018d95aee5 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9af98789-9a92-5729-8877-264426a9e6e7 | note | – – – – – – – – – – – – – – – – –
58c6ac30-59da-5b45-b42e-26cdc29e0e6e | note | VERIFYING DOCUMENTS: This ITP
5003147e-96bf-5824-951c-b76b660452c0 | date | Date Completed:
| checkpoint | 5.8 Pre-pour Inspection
bde86661-946b-520e-bec8-b0678ee7e2fe | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
4ac5b7d4-a30e-5ced-81a7-26d31bb852ed | note | – – – – – – – – – – – – – – – – –
214f435b-593b-559f-8527-56e853dc13b9 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
2bff291d-36ae-5b15-8169-9f52a63646f8 | note | ○ All foreign material has been completely removed from the forms.
0aeaca2e-b933-50fb-b741-5a938e78657e | note | ATTACH: Pre-Pour Checklist
db7389bf-050a-5abf-a70b-a312cff93fa8 | note | – – – – – – – – – – – – – – – – –
2a2f9164-b89a-5f15-85f9-78387024456b | note | METHOD: Measure, Visual
8ba75a98-bb99-5795-adaa-9476ba672582 | note | – – – – – – – – – – – – – – – – –
06372b2a-f161-5732-89c5-f49ac07a93bd | note | FREQUENCY: Each element
f6f2f1ea-91be-5f3c-bc68-1587db2ca501 | note | – – – – – – – – – – – – – – – – –
fecd5b27-5aa1-52b3-a281-3d887ca6ad86 | note | CATEGORY: HP
ba91e922-1f52-5a72-8fc3-a5fbde41d346 | note | – – – – – – – – – – – – – – – – –
c4980ec2-2572-5b93-8541-6af651dbf161 | note | RESPONSIBILITY: Nominated Authority
3f785c8f-6e45-5c1e-aa92-5a6699801338 | note | – – – – – – – – – – – – – – – – –
336dddb1-0a5e-5df9-ae96-47c92fc3da90 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
e35c991f-9f14-532c-aa7a-858846439de0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
7920f989-2d7b-5294-be4d-a06bb258ec65 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
49c76626-d41c-5e4c-8a9c-193ef80cc5fd | note | ○ 610.17
f2a9acb1-8fea-5587-a2c1-5d22a300205e | note | ○ 610.17 (a) & (e), Table 610.171
80975b1a-4fef-5ef0-b3c7-d21c65e1dac2 | note | – – – – – – – – – – – – – – – – –
b3d30f41-b292-512b-8132-0ce9d9ecf9ab | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
29a1648a-67eb-5844-ac36-b93e95216297 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
3c45bba4-d041-5a4f-903f-6ecb5e8761d7 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
a5234362-0315-5568-9b48-bf6adbcb1295 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
50230019-d8c5-5730-be4e-929d11b0ab52 | note | Record: Required information on the Concrete Pour Record.
603522b8-c1f0-506f-b601-90a462d9264f | note | – – – – – – – – – – – – – – – – –
0c9329d0-253f-538a-b521-0bf612ce1449 | note | METHOD: Measure, Visual
4ca38b86-66fe-50ab-be91-fcb264120d79 | note | – – – – – – – – – – – – – – – – –
99a0f9eb-1411-53b2-8a84-d6ed72b252fe | note | FREQUENCY: Each element
7f9ee751-c075-59c3-b86a-ee6658dd52af | note | – – – – – – – – – – – – – – – – –
3d7cb455-558d-52ce-a2e4-f5e98fa7adde | note | CATEGORY: IP
e26e0eb4-2849-5fba-8c89-9c2652463fed | note | – – – – – – – – – – – – – – – – –
9a641759-e523-521a-a814-17477ebc5b41 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
633ade92-d8ff-59ea-966a-0634cf4b41c4 | note | – – – – – – – – – – – – – – – – –
4d5d1d7c-a2ff-523f-9610-dc9f74962e7f | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
20d19040-77c3-5bf9-ae22-972b353423ed | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
9a064030-3731-5fee-b8c9-fa3d6077d795 | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
5eb887ba-80eb-523d-8186-580b48b14cc0 | note | – – – – – – – – – – – – – – – – –
3bb69ff5-2ddd-564f-8bc2-3a5ac471012e | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
8b7680dd-8fee-5139-b17f-1dce74e56008 | note | 0m³ to 10m³ = 1 sample
e95bf7f7-f977-51ef-9d16-205cc507d4f9 | note | 10m³ to 25m³ = 2 samples
e4b886f9-e964-5f14-82cd-8606894305ee | note | 25m³ to 50m³ = 3 samples
963e1a42-51fe-58a4-81f7-a5b624024e58 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
6a8a3b97-a9a5-5cdb-9bfe-8769e02cffb4 | note | ○ For each additional 50m³ and additional sample shall be taken.
918095b6-65c6-5a4a-bcbc-acefc3c6e815 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
a7387b7d-01e6-5147-892b-5a4dc6499f5b | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
ea579f29-7904-5db6-beb8-5063633a587c | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
0ffa58bf-2b61-58e8-bdd2-5d70c8d2bff7 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
51054f46-295e-560e-9043-a56bf1a4962f | note | Record: Required information on the Concrete Pour Record.
3b0e091c-cdd3-5c15-a936-89564486a1cf | note | – – – – – – – – – – – – – – – – –
dc810b55-079e-5982-8ca0-75ce12b6b415 | note | METHOD: Test
f25ab48a-f75d-5836-bd13-1b6c9874ccc2 | note | – – – – – – – – – – – – – – – – –
80973312-08a1-574a-bfec-353c15970f24 | note | FREQUENCY: Each element
32a2c2e8-dab0-5dfe-8939-4543f5654d5a | note | – – – – – – – – – – – – – – – – –
8ed8d1a1-bfb8-52c3-930b-92bc8e64a0e6 | note | CATEGORY: IP
dbc86553-45a4-5ac8-9d4f-c8c81ae7c74b | note | – – – – – – – – – – – – – – – – –
086ba968-2264-53cd-abcc-c5e7927c9d5a | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
126b94af-d740-5b2c-8852-2e78ff2ee50d | note | – – – – – – – – – – – – – – – – –
2d00f970-6b44-5817-85ef-01194eb5ab2e | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
597b6036-63c9-52fe-8576-399e3b179f64 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Slump
4bcfc3cc-fbb1-5cfd-b1d4-7a8836a6781b | note | REFERENCE: 610.16 (c)
b3c2af49-690f-57c0-ad3f-33dbd757410d | note | – – – – – – – – – – – – – – – – –
de36be57-7a74-5451-8c8f-9f0873db63b4 | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
24e959b8-057f-500f-87b8-8e3a60b03ac3 | note | <60mm = ±10mm
3856595a-4a92-53a0-b41d-6c419d0b6de4 | note | ≥60mm to ≤80mm = ±15mm
e18b45d3-86c8-5d82-bfcd-c01eae75b84c | note | >80mm to ≤110mm = ±20mm
c1bec4a2-0f0b-5fb3-883f-8000dbef7067 | note | >110mm to ≤150mm = ±30mm
2e6cbfe1-5f08-58ed-b9fb-e087ce3e57e3 | note | >150mm = ±40mm
15ca0e1a-a943-5367-9959-4fa464520e8f | note | Record: Required information on the Concrete Pour Record.
39ceed1e-7b46-5f9e-b101-f2919d072489 | note | – – – – – – – – – – – – – – – – –
49cdf2ec-df38-5d0b-9932-afb41db1ffd2 | note | METHOD: Test
5c9e4f04-e608-5d82-9e97-258ccff61267 | note | – – – – – – – – – – – – – – – – –
6c7a3357-acbe-5498-b6f8-d1dd2da2db8e | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
45cafdb9-3324-58e3-a817-a2cabdfc3d44 | note | – – – – – – – – – – – – – – – – –
39680b01-1f57-5129-8a8a-74b376f586e9 | note | CATEGORY: IP
33da3bb4-d74e-5a00-8e5e-2aa85174a604 | note | – – – – – – – – – – – – – – – – –
a4fa7531-5efb-5dac-b166-15f8d77b3b2b | note | RESPONSIBILITY: Concrete Tester
1e17d127-1005-5e2b-924f-1dcb3e3eb666 | note | – – – – – – – – – – – – – – – – –
c0afbaf7-fe9d-5206-a113-44f41fa55429 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
c0e6ea34-fc58-5ecf-8f02-aaefe645c192 | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
2f2fe718-39a7-5291-8241-5dc0d6110c94 | note | REFERENCE: 610.13 (b)
49de7e84-e82e-5a79-9746-e4870db782ff | note | – – – – – – – – – – – – – – – – –
d222781b-7254-587e-92c9-cba63ac57664 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
e809f61f-e532-5256-b310-ec1f8f28c15d | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
1f92e563-b520-590d-bb3d-8ab958b2f1de | note | ○ Passability = ≤10mm (aggregate height differential)
d31b5d0f-7781-5314-96ca-532db4644898 | note | Record: Required information on the Concrete Pour Record.
8d6a044a-82be-5f45-9e39-5428235e93b4 | note | – – – – – – – – – – – – – – – – –
cbb72424-06ab-5fd4-8b85-be8aa40619c6 | note | METHOD: Test
6743909d-2918-5a4e-b9bd-24b196e47038 | note | – – – – – – – – – – – – – – – – –
ab5e6826-59ac-56a1-997b-de5e5d766415 | note | FREQUENCY: Each sample of Self-compacting Concrete
537c0584-620f-5961-ad34-c9842f1b8107 | note | – – – – – – – – – – – – – – – – –
c5dcf787-b2cb-5552-8686-d475cf3da287 | note | CATEGORY: IP
7b41219f-ba41-5a3e-8550-61c6882f9733 | note | – – – – – – – – – – – – – – – – –
22634bcd-1373-5249-9339-654526d0ca28 | note | RESPONSIBILITY: Concrete Tester
caad3818-c17d-51f7-a24d-122896f5e6e2 | note | – – – – – – – – – – – – – – – – –
71667c95-7389-59ce-9a30-dce8ba78ff9f | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
4772a52c-4d54-58de-ac5d-2f52c006a28c | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
d4b9bc5e-0bde-5480-ab2e-9be3c53c4223 | note | REFERENCE: Site Sampling & Testing Procedure
98d942fc-20f0-5ce7-b69d-7603c739c791 | note | – – – – – – – – – – – – – – – – –
ebab7169-f431-57d6-b53d-0fb8857bb77c | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
ae703c67-b831-5401-b865-dcc7ac8b0bd4 | note | Record: Required information on the Concrete Pour Record.
22c8067c-e4a5-5abf-bbc4-865825c91acd | note | – – – – – – – – – – – – – – – – –
c2ce0cdf-92a8-5e8a-8721-3a2b6cc25db4 | note | METHOD: Test
e59a7651-e9ab-5c91-95c4-30b655391a7b | note | – – – – – – – – – – – – – – – – –
dade0410-b1cb-5145-ac87-bc5a4ffb4e8c | note | FREQUENCY: Each sample
fb44e19f-08e5-581b-8064-d31878b56955 | note | – – – – – – – – – – – – – – – – –
ae9826b3-3361-5138-91d6-52d4eec43394 | note | CATEGORY: IP
4fcacd16-b92b-50c3-a2b6-b86cff6e08c0 | note | – – – – – – – – – – – – – – – – –
90257ba4-f367-5ced-bf93-98286186cb29 | note | RESPONSIBILITY: Concrete Tester
4c352764-d170-54db-ba64-7548a26e111a | note | – – – – – – – – – – – – – – – – –
067104b7-0ebe-5801-8727-1ff71581a087 | note | VERIFYING DOCUMENTS: This ITP
29cb598b-d72c-5ef0-b173-b5f176fd031d | date | Date Completed:
| checkpoint | 5.14 Supply & Discharge Rates
da4b4c10-a375-5847-9538-ecb4dc3c22ad | note | REFERENCE: 610.13 (a) & (f)
cd563335-88a8-5fab-866e-b477a06061d2 | note | – – – – – – – – – – – – – – – – –
d2913d7d-56a3-5ca8-b0a6-9ba590da0c95 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
5026b67a-176c-5b40-8f42-3ac7ace02a28 | note | ○ No water is to be added once discharge commences.
42a7c318-c779-5af3-a73e-b798d2e89b20 | note | ○ Maximum time between batching trucks is 25 minutes.
2a1866d7-5d36-5300-8e06-e89914427f89 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
39306197-737d-5931-9d0c-8137463b80d0 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
9f8b72fd-b24f-52d5-9b0b-6f02e313efd8 | note | Record: Required information on the Concrete Pour Record.
23819e85-121a-50a3-b41f-e860c5b240c3 | note | – – – – – – – – – – – – – – – – –
d107245a-27f9-571a-95c2-690da89c9e5e | note | METHOD: Measure, Visual
4454edce-8b8d-58b8-b850-187b98caa507 | note | – – – – – – – – – – – – – – – – –
a4ea42ab-1211-5824-9d78-647b3787b882 | note | FREQUENCY: Each load
ac27f5d0-d750-5c78-a9c0-39f861e21eb3 | note | – – – – – – – – – – – – – – – – –
72925e05-f645-5a56-b8b4-9fbb763c9fcb | note | CATEGORY: IP
dff42072-64df-59b7-8f60-83666816f291 | note | – – – – – – – – – – – – – – – – –
3e3a461a-1298-5e2f-bbdd-0dad16101d71 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
76dd45c8-5493-5117-938d-6cdfce7e80a0 | note | – – – – – – – – – – – – – – – – –
ecd17b52-b51e-55ff-b330-480179fc402d | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
382e3765-6f70-5324-a882-8ce4c666af34 | date | Date Completed:
| checkpoint | 5.15 Placement & Compaction
1fb6c7fb-c7e7-560b-9796-07f81d22afef | note | REFERENCE: Placement & Compaction Work Procedure
8540691b-dfa6-567c-a915-08a0964ea8f1 | note | ○ 610.18 (a) & (b)
9f034357-2a54-56d9-af55-ecf6fca45659 | note | ○ 610.18 (d) (i)
4e8094c4-1048-5aef-9ca5-365f54e36c7a | note | – – – – – – – – – – – – – – – – –
4a8b5426-22f2-53ef-985b-530c092f8d92 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
8e215548-380b-54cf-a83b-eccc368b2b8a | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
83df6988-1669-5861-9183-35543535187b | note | ○ Concrete is not dropped freely from a height exceeding 2m.
e9390c75-30d4-5b18-87d1-ef013063de33 | note | ○ Concrete is not moved horizontally by use of vibrators.
7ecbd09b-e8f5-5c3e-bb45-7e614cb4aa3b | note | ○ Adequate compaction is ensured
16e7284f-3e8b-51b3-b906-876ef4325c99 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
63b8361b-4bc7-5a67-9bfb-3ec1b8fcb989 | note | ○ Concrete layers are not more than 350mm
cb6d9eff-b23e-51bf-87bd-0f88a8795c1e | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
37927f53-769a-56aa-bbc3-fc85a5a4f98c | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
a4e24a02-a8d8-5811-9eff-588ec7d4b8c8 | note | Record: Required information on the Concrete Pour Record.
35467c78-3a0a-5c17-ade7-2739a391f4b4 | note | Attach: Concrete Pour Record
be8f91e6-2e9e-556f-abcc-219283149371 | note | Attach: Concrete Dockets
cc8619fe-3e35-5287-8d95-58c9a7e87468 | note | – – – – – – – – – – – – – – – – –
1a1522fe-722f-5fcb-9ab2-d527e470c5c0 | note | METHOD: Visual
98cda946-673e-522f-b4a7-56f0a3de8949 | note | – – – – – – – – – – – – – – – – –
0b85d246-c438-5108-9057-073af405d9cc | note | FREQUENCY: Each load
85122871-436b-5f03-a254-1132609a2607 | note | – – – – – – – – – – – – – – – – –
d01d47b6-bdbe-5d89-a454-5361bb862a77 | note | CATEGORY: SP
66a855a3-6e50-56fb-8501-d8c0684d5276 | note | – – – – – – – – – – – – – – – – –
8fabdeb5-6e57-5ce3-9700-bb1fb9c306cb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
42fd6c48-be2c-593f-83b0-986b9b54b51a | note | – – – – – – – – – – – – – – – – –
6b3a98ce-b5e0-5488-941a-53a80fa9aea3 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
64878c7c-3db1-54bc-9d6e-715ec9446c4f | date | Date Completed:
| checkpoint | 5.16 Surface Finishes
bed066cb-2f35-5289-9820-e74a858252b0 | note | REFERENCE: IFC Drawings 610.31, 610.20
4f91c1f1-28b0-5f62-a264-6f6f88b8cef4 | note | – – – – – – – – – – – – – – – – –
160d3633-13a2-5107-a175-e10fac458f64 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
fcac7b32-0b44-5fdf-9637-85effb285096 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
a811ad9e-3e46-5e9b-8d76-ebbb7e1a6f6b | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
e999c9dc-66b2-52a6-a5ef-b3d4e935f235 | note | – – – – – – – – – – – – – – – – –
40b4ef40-2eab-57c1-898d-15c6a5865bc7 | note | METHOD: Visual
7cb1c30e-d73d-5179-8ad8-a7054baa8b40 | note | – – – – – – – – – – – – – – – – –
040b84fa-aac7-5f57-a5cf-54dfc7d70926 | note | FREQUENCY: Each element
c565ca54-ca08-5717-926e-8db2e95057ae | note | – – – – – – – – – – – – – – – – –
8ecee906-950b-52d3-8dc3-dd1a02de67cc | note | CATEGORY: IP
d8abaef7-a8bf-5cd4-80c2-5f70603f46e6 | note | – – – – – – – – – – – – – – – – –
eea45dbe-16ee-5822-88bb-a5c26251a3ba | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5f1f8ee9-5e64-59a3-a50d-e4bc1fa911c0 | note | – – – – – – – – – – – – – – – – –
4ba62632-dc0b-5ac5-aacd-803aa5655845 | note | VERIFYING DOCUMENTS: This ITP
6645dbaa-1e2a-5b35-bd8b-a972b2f707ce | date | Date Completed:
| checkpoint | 5.17 Curing
fdd31c9e-1e72-5ae3-bd75-4c479ee3d78a | note | REFERENCE: IFC Drawings 610.23 (f)
315c65be-7c15-5c2e-b623-740835ed3f87 | note | – – – – – – – – – – – – – – – – –
6f78163c-8d47-53a0-a425-9fcf9af372ef | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location.
c01c50a4-2e67-5d22-855b-12b53c7e2c9f | note | ○ Where formwork is removed prior to the completion of the curing period, curing shall recommence within half an hour.
11567f60-82f4-5059-9ba7-5659750f0155 | note | – – – – – – – – – – – – – – – – –
8ca66b26-8ac3-50b1-a0bf-80e49124bfae | note | METHOD: Visual
fc4fbc01-2bbf-5c2f-88cc-71755bfdef7c | note | – – – – – – – – – – – – – – – – –
663f7fa1-b259-5e7f-b10d-f28a90b03be5 | note | FREQUENCY: Each element
bf691c43-3cbc-5179-bfd1-8ef3ab8f4dc2 | note | – – – – – – – – – – – – – – – – –
8f119521-9756-52f4-9bd5-71cab59e3eff | note | CATEGORY: IP
a7c8716a-69bd-5aa9-8326-9e43c3a239eb | note | – – – – – – – – – – – – – – – – –
c40b39bf-806a-5e86-90c4-0fccaedb92db | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c3cfb61c-90b6-5e9b-a04e-293876b87d4b | note | – – – – – – – – – – – – – – – – –
34ea78b5-129d-5cce-bca5-d7c03c3d842c | note | VERIFYING DOCUMENTS: This ITP
7d63b1bd-8058-571d-b8d6-222a31ed301b | date | Date Completed:
| checkpoint | 5.18 Curing after formwork removal
7cbedca8-1bb6-5b3b-929c-1fd6f1ddcc01 | note | REFERENCE: IFC Drawings
20ea7db7-7c75-554d-a9d5-5aba57ac0a54 | note | – – – – – – – – – – – – – – – – –
b2afd64d-034c-51ed-b252-be447a4875de | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
0bd70ae5-0d47-5599-b2d2-8e5476e12681 | note | – – – – – – – – – – – – – – – – –
9e6571f8-da9e-592a-b838-58c45e237a9d | note | METHOD: Visual
d2557abe-9384-5fb6-bc88-9a617abceae5 | note | – – – – – – – – – – – – – – – – –
788e94b6-87f2-5ded-9ab6-7740fcf1a4cc | note | FREQUENCY: Each element
b236041b-3dc6-5986-8941-61aa1d0d29dc | note | – – – – – – – – – – – – – – – – –
43526095-5a75-5d48-8564-d708ca69e97a | note | CATEGORY: IP
155a3ce6-54b3-5b59-8940-b81a4a2dce74 | note | – – – – – – – – – – – – – – – – –
56cdf59b-7fa8-50df-98c0-ccbc36ceceac | note | RESPONSIBILITY: SE
4dac2884-82b9-531f-b6de-0c3e07501a4c | note | – – – – – – – – – – – – – – – – –
d082127a-fc89-5595-849d-0540adc833e7 | note | VERIFYING DOCUMENTS: Thip ITP
0554b793-00a8-5b12-bdec-6183c74cfeb7 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
579366d6-4414-5b5a-82a0-d2c5dfebdb78 | note | REFERENCE: 610.22
c2e911a3-2253-517c-a1ca-6827390290b7 | note | – – – – – – – – – – – – – – – – –
65ea8926-df1e-5032-9c36-593abf68b703 | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
42fc1e94-16c5-5df1-8dda-a682ab88f819 | note | Only applicable if the element has:
c8376195-47af-56f7-9f8f-5de7d36e2f9c | note | i. the smallest sectional dimension exceeding 500mm
fda78224-8dbf-5464-a1e6-83dcf2fe962d | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
1b87d277-1538-53c6-8261-1c107e2e5c6b | note | Attach: Thermal Monitoring Report
7d5283f7-e590-557d-8d2b-0e0c3e679b8f | note | – – – – – – – – – – – – – – – – –
608bec93-1c31-50ff-ab81-a918c484fd6a | note | METHOD: Document Review
2ba01d93-7910-5c74-8aad-61241642dcbd | note | – – – – – – – – – – – – – – – – –
6ac67a55-0703-5f0f-9eb3-ae66f3d4bfb3 | note | FREQUENCY: Where applicable, each element
66483603-5122-5612-b810-0aaff2f92e60 | note | – – – – – – – – – – – – – – – – –
5765b621-90fa-5f9e-9428-d54bfbeb12ce | note | CATEGORY: IP
114b8bfc-8a0d-588a-9711-2e8b95222e2f | note | – – – – – – – – – – – – – – – – –
fd5a3a7d-765f-510d-a9cc-466872ccfcd2 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
198ab2a9-dfbe-5c97-92bb-eca7725d9b52 | note | – – – – – – – – – – – – – – – – –
81201e9b-69a6-51d8-aed6-27b02019438d | note | VERIFYING DOCUMENTS: This ITP
61a21e79-5347-529e-8f86-d03b7be08570 | date | Date Completed:
| checkpoint | 6.2 Removal of Formwork
1b5d9373-d2b6-5001-9109-4cfe1935339d | note | REFERENCE: 610.25
f0e892f9-0a02-5e02-9465-618f4caf91d8 | note | – – – – – – – – – – – – – – – – –
573676b6-19ec-5e1b-b7cf-4f7576a3f201 | note | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in Table 610.251 have elapsed, after completion of the placing of concrete.
a2e8e413-c3d7-5f9b-9d88-cd21c9ec973b | note | – – – – – – – – – – – – – – – – –
94f35d4a-dca9-5e3e-bb46-3b8fd9743cb1 | note | METHOD: Document Review
4e48f9ea-dda0-5cd0-81aa-61a29ab3e680 | note | – – – – – – – – – – – – – – – – –
e7ee6cf5-0fe3-51a3-9f8f-602b0a1ea705 | note | FREQUENCY: Where applicable, each element
42612da0-dcf5-5822-9177-f90a9e6f1638 | note | – – – – – – – – – – – – – – – – –
57d5f02f-699e-5da9-9764-ca13b2c2c410 | note | CATEGORY: IP
813f9e45-0b8d-5e9e-bb34-91761ec22976 | note | – – – – – – – – – – – – – – – – –
180cba94-41ae-5bfc-a782-2209108a3018 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
45a1dbcd-a8f1-59e6-9216-2fbe25b5a9d5 | note | – – – – – – – – – – – – – – – – –
58bd2e0f-8166-533b-95ea-cd7fc8975917 | note | VERIFYING DOCUMENTS: This ITP
33892ad7-4e1a-52b4-adf1-16cf4e524d79 | date | Date Completed:
| checkpoint | 6.3 Surface Inspection - Cracks
aca7bf82-2bf0-55fe-9fd3-268d6b45d7da | note | REFERENCE: 610.24
e0bd379c-da1c-526f-ab27-33c122b8c395 | note | – – – – – – – – – – – – – – – – –
67a4ca32-f4cf-56ac-b8f9-955134de30c1 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
6f130200-222a-5f80-9e7f-11567ae00759 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
c90bfdf1-798d-5b43-b6d2-186c6e46a36a | note | – – – – – – – – – – – – – – – – –
41491c7b-3e19-559a-8e1e-73b692cb5e6a | note | METHOD: Visual, Measure
26fa7b65-6071-5b19-b724-d88a1ab2ef27 | note | – – – – – – – – – – – – – – – – –
69dc9c09-0436-5eda-8e38-798153f4ce1e | note | FREQUENCY: Each element
62064e0b-ee87-5162-adbe-707becca640f | note | – – – – – – – – – – – – – – – – –
8d663a75-a7bd-5808-843f-5fed0cae9462 | note | CATEGORY: IP
f29a126e-6f71-5274-a38c-7fc2fb355789 | note | – – – – – – – – – – – – – – – – –
acbda6f2-8fd1-5e7c-bc33-4461aea712cb | note | RESPONSIBILITY: SE/PE/SPE
40842fd7-5ce2-5f34-9a10-762abc1d4624 | note | – – – – – – – – – – – – – – – – –
f5bb5547-d3f4-5a92-a052-73cca61d0250 | note | VERIFYING DOCUMENTS: This ITP
92c45535-6197-57ba-b39c-28a1091edc05 | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Surface Finish
d1f1ad70-4fab-58c8-aaa3-e2498c2b56e7 | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
add94181-8354-5386-ad0c-874c8f3563ab | note | – – – – – – – – – – – – – – – – –
49442c57-e408-5818-805d-46e98b1e172d | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
dc15321a-4d3d-5b5d-88e0-8ada2b70223a | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
e858c277-9d19-5bf1-8c5f-270730c46a99 | note | – – – – – – – – – – – – – – – – –
526a3c7d-1ec5-50f8-bb07-9ad590968634 | note | METHOD: Visual
cdd5304b-a7aa-5a0e-91f3-5e1ed118a816 | note | – – – – – – – – – – – – – – – – –
540df31a-1ea1-508f-be4e-c8946a4711ce | note | FREQUENCY: Each element
53110a7b-fac0-5e62-a330-64b694a77a9a | note | – – – – – – – – – – – – – – – – –
56ffbb2c-f631-5cd1-a1af-1fec9469a516 | note | CATEGORY: IP
ce6ade44-4b23-52dd-84c2-74baa1bc39b8 | note | – – – – – – – – – – – – – – – – –
a7981130-5748-5cc7-8cf5-179e857de15c | note | RESPONSIBILITY: SE/PE/SPE
3c9d4772-764a-5ef3-9676-4d48f88c29f8 | note | – – – – – – – – – – – – – – – – –
a5c35094-af8e-56e9-85a8-e680412d6e49 | note | VERIFYING DOCUMENTS: This ITP
926bdd38-c625-5829-be3a-31aea83249d7 | date | Date Completed:
| checkpoint | 6.5 Measurement of Concrete Cover
18b98800-7ef9-5bed-a870-9c4060d5a746 | note | REFERENCE: 610.34
89c9b5c1-77fb-52ce-80d6-7d14dc2c7f76 | note | – – – – – – – – – – – – – – – – –
fd1737b6-02ad-51d7-a726-9f419d16d1ec | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
06b67d18-02ec-5030-aa14-7c26a13eef60 | note | ○ Minimum 10 no. measurements recorded in each area.
29f2f737-0523-5fa7-b221-b631d14377b4 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
41430883-1608-5d61-ac0a-9aed432951a4 | note | Attach: Covermeter Check Record
68e1326c-fb74-5ee5-8150-586ea9c3175d | note | – – – – – – – – – – – – – – – – –
6d05061a-b5d0-5238-b230-617a0bbe67c2 | note | METHOD: Measure
cc1088da-7321-5bfb-884e-e22b7f7a4297 | note | – – – – – – – – – – – – – – – – –
0dfe733c-73b3-524b-9382-35aaf6a35103 | note | FREQUENCY: Each element
02dc3136-7e58-535f-9428-fc8a640ad3eb | note | – – – – – – – – – – – – – – – – –
1f4e7747-ec97-5915-acba-aa3c4f1fcfaf | note | CATEGORY: IP
413732a1-863f-5d4b-8ca7-2a17ff510e1b | note | – – – – – – – – – – – – – – – – –
ceb591b0-1664-5549-838f-23bdb90cfaca | note | RESPONSIBILITY: SE/PE/SPE
ece82cab-b644-51e4-b688-1a040cd588d8 | note | – – – – – – – – – – – – – – – – –
290a9a40-5795-556e-8b14-749a94931825 | note | VERIFYING DOCUMENTS: This ITP
27bbe8bc-99be-5e3d-8e3e-dead541862e6 | date | Date Completed:
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
f288463a-50c4-57f0-a106-c27f73e623f1 | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
dc0de755-424e-5054-9b62-92ff69b1cd62 | note | – – – – – – – – – – – – – – – – –
89ea1698-b524-5e33-bedf-4d97dd1c3338 | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
2d31ab0d-4cd8-59e3-ba70-460ce189661d | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
5ef7c433-3efa-561d-9c03-9335d1f403df | note | Attach: Concrete Test Results or Maturity Test Results
d6ff6b92-beed-54d6-9b9e-db127c582f1e | note | – – – – – – – – – – – – – – – – –
74edb0b9-1426-5bc2-afe1-a2212ea68e20 | note | METHOD: Document Review
ccf34cc3-fe99-5c59-8748-04e240a14d31 | note | – – – – – – – – – – – – – – – – –
951113bc-7a8c-5aa8-86b3-840e45517ea0 | note | FREQUENCY: Where applicable, each substructure element
24cfe2d6-2612-5d8a-9fb4-64f64bd20a75 | note | – – – – – – – – – – – – – – – – –
d20a2470-1397-5703-b511-f8b8dea747c5 | note | CATEGORY: SP
8dd9954c-8496-53e5-b053-f514f2fc62ea | note | – – – – – – – – – – – – – – – – –
140c24ed-0759-59b7-950a-99104160e434 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5ce03f86-086f-553a-a683-661fee1ac1f5 | note | – – – – – – – – – – – – – – – – –
36dde0e8-bd37-5702-a08e-2bf08e780db6 | note | VERIFYING DOCUMENTS: This ITP
ed785a37-1a61-582c-ae57-499e9d919527 | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
3c66a637-ca6f-543a-a453-24b42b936dab | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
cfdd8ec1-9e78-5934-bd01-b7fc523deedc | note | – – – – – – – – – – – – – – – – –
6b05e89f-3128-5510-9253-ba9549c42dd9 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
2b6e3228-f8f0-5655-aa94-7dcf5eed2ee2 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
b669fc09-2c20-5ac4-939d-5c9567a0313a | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
b841d884-b01e-582a-8f3a-9b00fb932f4f | note | Attach: Compressive Strength Test Results
2b656301-89ad-588c-bd83-73d84a470bab | note | – – – – – – – – – – – – – – – – –
77a0df4e-db05-516e-9377-552a8f27edc3 | note | METHOD: Document Review
04d36855-d182-50a2-8a6b-f001d1572aaf | note | – – – – – – – – – – – – – – – – –
2cee84a3-111c-5b87-af20-ba49b55ac74f | note | FREQUENCY: Each cylinder
a6c00103-0b69-58ff-bc83-0f58dcd16c81 | note | – – – – – – – – – – – – – – – – –
cb1b40cf-91d6-5ccf-86af-29e5e10a5467 | note | CATEGORY: IP
7a997df6-d7b2-5bbc-a589-186f34beecce | note | – – – – – – – – – – – – – – – – –
4d0ed923-be47-597c-b6e9-6e68d03b931f | note | RESPONSIBILITY: SE/PE/SPE
d4ed377a-3062-5543-8c3c-84ba4a8b8da9 | note | – – – – – – – – – – – – – – – – –
812c2898-e0be-59c9-99fb-92a36a29b137 | note | VERIFYING DOCUMENTS: This ITP
2415e92a-3d29-5d1c-b810-43baa6eb09a5 | date | Date Completed:
| checkpoint | 6.8 As-built Survey
a9d01638-da74-516a-bfab-6a9053f78b7b | note | REFERENCE: IFC Drawings 610.47, Table 610.472
51c56989-d65c-5519-a79d-9722766ed9e0 | note | – – – – – – – – – – – – – – – – –
0b28a700-5c7e-5034-a7af-9e15ad8eec62 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
6311e58c-0068-57b2-a4c5-64646f90d3df | note | Attach: Survey As-builts / Survey Report
812e1e18-74b0-56a4-9ef0-165b329b0256 | note | – – – – – – – – – – – – – – – – –
f8cd379f-cec7-56c6-9343-96a6ef7629c1 | note | METHOD: Document Review
82cbd0e6-2920-5997-908d-99e6d7d15d08 | note | – – – – – – – – – – – – – – – – –
933f0525-cd73-530a-9e7c-c6aa4c9c440f | note | FREQUENCY: Each element
41d9f47b-8a46-56ce-b8ad-532797720a86 | note | – – – – – – – – – – – – – – – – –
a5673ee7-7c55-5b04-8b92-e2c77b7b9d18 | note | CATEGORY: IP
caf3f08b-d3ee-55a5-8ba6-e1fc40168c7b | note | – – – – – – – – – – – – – – – – –
378c2d07-994d-5fa1-9b0c-cb709734f58e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
e970f705-c0ab-510d-bea0-0b7226c9298c | note | – – – – – – – – – – – – – – – – –
85269567-1539-5656-880c-09fd1453f10b | note | VERIFYING DOCUMENTS: This ITP
a5cd4ab5-c59f-5bb7-bdb3-b74f222024a6 | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
35a9acee-e673-56d2-8df7-d493524fa737 | note | REFERENCE: MRPA Quality Management Plan
12968ef5-2816-5e03-bd7b-1e07b8504f92 | note | – – – – – – – – – – – – – – – – –
718c1863-8a68-5190-bb1f-3a89c78ebbde | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f1cc183c-81bd-5643-a475-16263aa8c73a | note | – – – – – – – – – – – – – – – – –
3e8b4abf-aafd-5519-ade8-f5f6131dffdc | note | METHOD: Document Review
6d17ed25-0025-5fa3-b25d-4f48258f60ec | note | – – – – – – – – – – – – – – – – –
7b7dcb5a-8b3f-5fa9-9b8e-e75c97271ee4 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
0b795d04-e987-5f91-9eb5-d7f3af4a4620 | note | – – – – – – – – – – – – – – – – –
cc8f2fe3-05b1-5b3f-99a8-dfb4ed5853a6 | note | CATEGORY: HP*
e6545563-4107-5c98-be0a-90e76be47800 | note | – – – – – – – – – – – – – – – – –
415d0751-6218-58ef-821c-557889d6a088 | note | RESPONSIBILITY: SE/PE/SPE
2beab900-e426-5aee-9e0c-d4b8fad9b798 | note | – – – – – – – – – – – – – – – – –
3ffd7575-aaa5-5779-a800-348675b5d246 | note | VERIFYING DOCUMENTS: This ITP
99f38a1e-54c3-58b2-8138-fc46479a907c | date | Date Completed:
| checkpoint | Final Inspection
6e236b4e-1376-5d8a-9690-826ed856261e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a98216f1-1908-53f8-a5f7-da87f4cdf822 | textbox | Name:
6c446545-d914-5a4f-9d09-a0269d911ef7 | textbox | Position:
6622ee09-73fa-5930-9007-53767782cdd0 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-134-CIV-Stormwater drainage materials and CCTV Rev 0 | itp | ITP-134-CIV-Stormwater drainage materials and CCTV | eacfb1db-cb28-4a15-8ce0-317027c98af8
| section | Referenced Documentation
| checkpoint | Referenced Documentation
b6df2066-a908-5df3-b475-a2f174ba945a | note | Document Title: ITP-134-CIV-SSB-Stormwater drainage materials and CCTV
693f6f69-8b01-50cc-8411-21f0399154ed | note | ITP Description: SSB-Stormwater drainage materials and CCTV
3f705841-b60b-5562-aea0-ea99960949c1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ae6cd36a-f46b-529c-b5c7-57a3917087fe | note | Discipline (e.g. CIV/STR/RAIL): 134-CIV
ef784316-36f8-5884-b014-915e6d7da16f | note | Revision Number: 0
ea37f743-facb-5be7-b74a-f8cd575736bc | note | Revision Date: 30/01/2023
ee319ba6-8dac-5158-bef7-82a232516a89 | note | ITP created by: Hiruni Wickramarathne
204e181c-9791-5f9b-aba2-e251a101ba16 | note | ITP approved for use by: Victor Mira
be926cc4-e8c1-5813-8783-f9bc218e72cd | note | 1.1 Non Dependent
073d3d4a-5212-58b5-b5a0-d681b6d27a71 | note | Reference: VicRoads Section 701 (May 2020)
fcc1fa88-86ed-5271-a3c6-49c6c31dae91 | note | 1.2 Non Dependent
de119a66-7e73-5615-8444-2d22bf630f09 | note | Reference: VicRoads Section 705 (June 2021)
1d9b205e-f8ab-5dbc-a391-f338aa59524b | note | 1.3 Non Dependent
b0c258d7-bd93-577d-9cd2-cbfd83d2cd3b | note | Reference: IFC Drawings
| section | Preliminaries-Materials
| checkpoint | 2.2 Drainage Flexible Pipes
1560bf2d-896a-5752-94ad-fcd2696d367d | note | REFERENCE: Section 701.08
f0d5cb77-b35b-519c-9a4a-4e5b0f730bb8 | note | – – – – – – – – – – – – – – – – –
c5bf580c-6edd-5cc3-b8d3-f44a8720f4cb | note | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
6b4dadd6-15fc-5b5e-b045-d677d06e7c7f | textbox | Enter: Teambinder Material Approval number
353b896c-c45f-552d-8d95-6cc282b23a74 | note | – – – – – – – – – – – – – – – – –
bff0030a-0859-5053-a94d-cfbbf367c87d | note | METHOD: Document Review
eec6e970-88b9-5eb3-8725-056a2375ea77 | note | – – – – – – – – – – – – – – – – –
46fbfb08-eec8-5421-8f1f-fb7278020e4b | note | FREQUENCY: Each lot
912c8b30-8ac2-5d6c-9278-70ac96828aa7 | note | – – – – – – – – – – – – – – – – –
31f0afe7-ae58-5bea-9a32-004f2a4530e4 | note | CATEGORY: HP
4de0794d-a82c-50d9-a527-363daf1d1bf2 | note | – – – – – – – – – – – – – – – – –
6a9cf61c-a218-59a4-8314-4f452ae3b19f | note | RESPONSIBILITY: Nominated Authority
6eb83c92-55a1-5204-b3e3-ad6c034b9433 | note | – – – – – – – – – – – – – – – – –
a083acdb-002c-5095-bb66-6826f3826609 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
2dc99c3b-0d71-5464-82ce-cc553412097b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Precast Drainage Pit
99d482dd-5422-5019-839b-9559784d3ff8 | note | REFERENCE: Section 705.07, Section 705.04, Section 705.09
16c01170-9231-52ec-a9c4-e9c2488406e9 | note | – – – – – – – – – – – – – – – – –
bfd20872-04e8-5932-91b4-5a3b6da9696e | note | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
fcd66195-d803-52a4-8825-0004a99247c3 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
882147a3-bf3c-54e2-b532-cbdc1992e7d0 | textbox | Enter: Teambinder Material Approval number
db53b2cf-f4d6-5963-a098-d2ba09d6e5b4 | note | – – – – – – – – – – – – – – – – –
655347ac-4312-5f4a-ae58-c82cade83363 | note | METHOD: Document Review
540fc1e0-b882-5a69-80bc-204cd2fba020 | note | – – – – – – – – – – – – – – – – –
5c9f802a-43a5-542b-b4fc-14ea5e536df1 | note | FREQUENCY: Each lot
4e3f1473-3542-50a5-9bf1-8c334bcd800a | note | – – – – – – – – – – – – – – – – –
a1a9d853-8651-568f-8298-e4c1bca299cd | note | CATEGORY: HP
7f07fcfb-1523-59a7-a884-974d397ea8c6 | note | – – – – – – – – – – – – – – – – –
878566e0-558e-507f-b0ef-e76727806da4 | note | RESPONSIBILITY: Nominated Authority
71cd9045-2d68-5fdb-a9ea-3589e0bd8f0c | note | – – – – – – – – – – – – – – – – –
c0d0c430-783f-56b0-85a4-d634c8bf3d29 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
81c29c8c-894c-55d1-b6de-051377a230fa | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Cast in Place Drainage Pit
211fe53b-9865-582f-8f29-5bb0e8ff5514 | note | REFERENCE: Section 705.06 IFC Drawings
86577d97-27f4-5fc4-8913-ccea2fb521c0 | note | – – – – – – – – – – – – – – – – –
d3e9d8ff-7dce-5d7a-855a-406aded55f6a | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
e928b4dc-8181-5627-bc2b-2f3360296938 | note | – – – – – – – – – – – – – – – – –
6553d6a1-be04-5326-bf4d-2adc3910a6b2 | note | METHOD: Document Review
6110e432-1a97-5b11-bd74-e3023546c579 | note | – – – – – – – – – – – – – – – – –
df05c318-70fe-57c3-9122-c26bd6ff2cd7 | note | FREQUENCY: Each lot
28960e55-a7c4-5cf3-83bc-6d13ad603f6a | note | – – – – – – – – – – – – – – – – –
055321bf-1dd6-5ed5-853f-1e6f2f3bd8a4 | note | CATEGORY: HP
0e99e633-afc1-582e-9a57-3ba7f00120ec | note | – – – – – – – – – – – – – – – – –
c43722a7-eced-5808-9b0f-f1da7af2ac2c | note | RESPONSIBILITY: Nominated Authority
3139d56c-2c87-593e-9bce-65637f84d15d | note | – – – – – – – – – – – – – – – – –
2439740d-cb56-5cab-82f0-bfef82adf662 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
2d507439-d758-56cd-907b-2223798a97a8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Drainage Pit - Step Irons
906387b2-a3b0-5120-bb16-5265217a61af | note | REFERENCE: Section 705.04, Section 705.12
034935a3-7e68-5210-8eaa-5ce8c29d03bf | note | – – – – – – – – – – – – – – – – –
b69e7290-b9c0-5dfc-b345-2da5667c6cfc | note | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
81ac4805-4820-5b70-9932-4bcd687ff1de | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
8fb918b5-211c-5fba-a92a-0b0b6149fbe7 | textbox | Enter: Teambinder Material Approval number
36136f23-4fea-51c6-ae95-3a7d24fa645c | note | – – – – – – – – – – – – – – – – –
b57bc471-213b-5610-b3ec-bec9cb269e50 | note | METHOD: Document Review
e99aaede-b236-5748-82c0-4061f92be5dc | note | – – – – – – – – – – – – – – – – –
b403e655-7a2a-5a4d-8abc-22fd89dc854f | note | FREQUENCY: Each lot
7b3a3c8c-95fc-541c-80b4-9f1755110c83 | note | – – – – – – – – – – – – – – – – –
e1407ee4-0c8e-5aee-86e3-0c17eb301c00 | note | CATEGORY: HP
012d3a78-204b-5054-aff9-d9d03792ecce | note | – – – – – – – – – – – – – – – – –
946c17f1-7458-59ac-a890-234cd4d936c5 | note | RESPONSIBILITY: Nominated Authority
06c25003-c063-5a36-b9e9-a478a88ea46d | note | – – – – – – – – – – – – – – – – –
665b7242-648d-5dcc-b522-a4ce5006ff37 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
4b0b38ee-54d8-52c4-8b48-34be576a433a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 Drainage Bedding Material
0a235c29-2911-5e84-9c76-a110a0b46f5c | note | REFERENCE: Section 701.09
991f8991-2e80-58cb-94d9-548731a57c0d | note | – – – – – – – – – – – – – – – – –
cb86d183-37f3-5760-8237-e8aedf866c44 | note | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
a24192ad-6261-57a1-8efe-656646965bae | textbox | Enter: Teambinder Material Approval number
aa173625-007d-57ef-a58c-a3c85e0e991d | note | – – – – – – – – – – – – – – – – –
599ccef6-dd21-5eff-8c72-7192ff8de980 | note | METHOD: Document Review
b0b90333-9e98-5fb4-a5f8-3bcc93f544a9 | note | – – – – – – – – – – – – – – – – –
b27498d0-69b5-5e32-b26b-5643f0e5acc9 | note | FREQUENCY: Each lot
51141b22-1d3a-5145-baa6-646481403beb | note | – – – – – – – – – – – – – – – – –
f8dc3c9d-ffe8-5b50-b7b8-49e0a1a257db | note | CATEGORY: HP
eaa62a6c-e912-54d7-9866-05dcbf64ca32 | note | – – – – – – – – – – – – – – – – –
21dbc6f8-a636-5d9a-9366-d54ad051e517 | note | RESPONSIBILITY: Nominated Authority
8eb3f777-983e-535c-a8fb-90ad4e64aabd | note | – – – – – – – – – – – – – – – – –
4e5f5bb3-7e89-5305-997f-90668bdfa9e8 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
efd8a22e-1681-5ea5-aba4-52f1d886de50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 Drainage Backfill Material
a594a59f-ccba-57ea-87e9-80155dc6506f | note | REFERENCE: Section 701.09, Section 701.19
dfc36ac7-b92e-5d31-8025-6077ac56ecb3 | note | – – – – – – – – – – – – – – – – –
b9969b5e-a80a-5cfe-9e78-932f915315a3 | note | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
2efabe59-bd24-5c63-a4b4-8bd1d4403f36 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
ae207015-41ce-51c4-bd0e-b109a9c092f4 | textbox | Enter: Teambinder Material Approval number
d3293c7f-cf9a-5e88-b7e7-d54b6a73cbc0 | note | – – – – – – – – – – – – – – – – –
5f6abd62-7d2a-5798-88c9-f1dedc07e72d | note | METHOD: Document Review
8cd5beb8-0e35-57b7-82c9-bf1ea244e028 | note | – – – – – – – – – – – – – – – – –
0e94615d-883c-59cf-b4eb-ae151184bdba | note | FREQUENCY: Each lot
58299da3-a96d-5fd0-8c28-b44f332f81b3 | note | – – – – – – – – – – – – – – – – –
35cc81da-c841-5a7f-baa4-a0f2f1f99c30 | note | CATEGORY: HP
b1412ab3-c7ec-5cae-8855-bc098fa33701 | note | – – – – – – – – – – – – – – – – –
9c64ecba-d94a-563c-889b-61c2549796de | note | RESPONSIBILITY: Nominated Authority
b037f207-7231-572b-b0bb-f3c242c10039 | note | – – – – – – – – – – – – – – – – –
afe21135-fbcc-5743-8f43-e3195f1e7226 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
9b121048-8e18-569c-90b2-adb650cdad60 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Construction / Installation Activities
| checkpoint | 5.1 Pits - installation
fbf26493-2be0-52ae-9094-baf75b455f17 | note | REFERENCE: IFC Drawings VR 701, VR 705
be082da4-ddb2-55da-8393-bec9e9ef8446 | note | – – – – – – – – – – – – – – – – –
1c3226ef-6269-5908-86d0-687f1bcc0204 | note | ACCEPTANCE CRITERIA: All the pits for this separable package are installed and respecting Lots are closed
e9fd10e3-3d09-5966-abf2-13d7732c7b64 | note | – – – – – – – – – – – – – – – – –
a5d63093-149f-5859-806d-de93856a0c6c | note | METHOD: Document review
09dd1c74-5474-5195-9dd7-4a8ada764d78 | note | – – – – – – – – – – – – – – – – –
6ddeccf6-3f7c-5c52-ba57-aabf03916d28 | note | FREQUENCY: Each drainage separable package
7c968c95-e0b1-5331-8434-27077154cdd9 | note | – – – – – – – – – – – – – – – – –
4615c388-ee90-5ee4-ae1c-e92805739863 | note | CATEGORY: IP
8e40b438-4520-5b8c-a83e-62684e8dd09f | note | – – – – – – – – – – – – – – – – –
b6ffadfe-b3c3-524b-8563-e9a0b9c5a966 | note | RESPONSIBILITY: PE
aab03cd7-b46c-57ff-acfe-aedd5446401f | note | – – – – – – – – – – – – – – – – –
f423e3e2-5c0d-5dd2-9e86-31962b38f06a | note | VERIFYING DOCUMENTS: This separable package Pit installation Lots
4d401518-bac6-595a-8cb9-8b2075a0a0e1 | date | Date Completed:
| checkpoint | 5.1 Pipes - installation
f89147d9-659e-5ce7-936c-464e3364b246 | note | REFERENCE: IFC Drawings VR 701, VR 705
8b4d53cd-d524-52ea-8a6c-e3481c5c9a95 | note | – – – – – – – – – – – – – – – – –
f0eb49cb-056b-5a11-9ac8-1b6c44223d30 | note | ACCEPTANCE CRITERIA: All the pipe runs for this separable package are installed and respecting Lots are closed
a93f3dc9-023a-5a50-8aad-4ba635bf86e4 | note | – – – – – – – – – – – – – – – – –
66f20e8b-6620-52fe-9b3a-0ee2f7d1dc26 | note | METHOD: Document review
246b30d4-6242-5690-a05d-39ef7fac2d05 | note | – – – – – – – – – – – – – – – – –
2edf073d-9dd4-5035-a4b6-f3b09bc4306a | note | FREQUENCY: Each drainage separable package
648f5186-d1f5-5fcf-87b9-f755bc55eb4c | note | – – – – – – – – – – – – – – – – –
853c587b-0e5f-501d-bd12-c36625cf1ea7 | note | CATEGORY: IP
641f36e7-8700-50da-b7f4-cd27decb8558 | note | – – – – – – – – – – – – – – – – –
19fa22ea-70c4-5835-8b87-00de22a0fb2d | note | RESPONSIBILITY: PE
8e9d7b94-42c8-544a-bc98-22fa43b76ef1 | note | – – – – – – – – – – – – – – – – –
c2e42f49-0418-58ec-8c5f-79389923bc1b | note | VERIFYING DOCUMENTS: This separable package Pipe installation Lots
1a00d89b-9068-5e8f-b0d6-934cf041a6e2 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Flushing & CCTV
1b6ad945-a41a-5b48-ada9-8ad377ce88df | note | REFERENCE: Section 701.28, Section 701.30
318b0ad6-cb2b-5fdb-a7e3-93ecdb2fc257 | note | – – – – – – – – – – – – – – – – –
3a491b3a-7c10-58cd-9f1a-601398ba2450 | note | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
cd8f5565-dd59-579d-bc44-15af2c3479b0 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
6c8e4b71-2b1a-514e-ae98-1513ffa9d57d | note | – – – – – – – – – – – – – – – – –
270bed7b-9f46-5ede-a066-7ec75ec2ac1e | note | METHOD: Record Review
928e703a-5c66-56de-8fc9-a93f75a6b40b | note | – – – – – – – – – – – – – – – – –
25b07617-9361-5278-a036-7c0422a1c13e | note | FREQUENCY: Each lot
ba8b2bf9-7c86-5f7a-9df2-cc0771c0e532 | note | – – – – – – – – – – – – – – – – –
7e8e6595-b031-5f41-9ae0-23d43b3dfb12 | note | CATEGORY: HP
a58b2f62-8857-5003-a41a-746154efe5ed | note | – – – – – – – – – – – – – – – – –
1476c701-f18e-5ef5-a013-9a7cf4551b9c | note | RESPONSIBILITY: Nominated Authority
7a4b29b0-893d-553e-8817-7429c8eaad62 | note | – – – – – – – – – – – – – – – – –
2efa0526-7b40-544c-84e5-2f352086e533 | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
b12a26b6-a181-5c44-8f95-c09665e93f71 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 As Built Survey
bd213bef-fc55-5b92-ade4-1f67d16a3a7f | note | REFERENCE: Section 701.10
cd6082bd-f164-50b8-94ce-9f70ecc9ce2e | note | – – – – – – – – – – – – – – – – –
b62150c6-3f68-5827-b19e-37ef7281c1ec | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
aa98b22a-8b51-5454-9174-8f1f48d12260 | note | – – – – – – – – – – – – – – – – –
de6e57a5-82fc-5c1b-a690-e5229fafc98a | note | METHOD: Document Review
05085290-30ab-5d1a-9525-c3f849aa23bf | note | – – – – – – – – – – – – – – – – –
1f91f13f-cd77-5510-831c-d256e1f907ba | note | FREQUENCY: Each lot
e8821cf2-2f50-51e4-9d47-07a8d61b341b | note | – – – – – – – – – – – – – – – – –
462cf1ab-7750-5e00-8c2e-fd390b459ded | note | CATEGORY: IP
3dde512c-3579-5237-ba16-03817597cb34 | note | – – – – – – – – – – – – – – – – –
c9f8933c-466c-531a-ab80-0ca2f63e3f0a | note | RESPONSIBILITY: SE
30b430f1-7f61-5b39-80ab-64cb3acc9762 | note | – – – – – – – – – – – – – – – – –
329f3b49-a3d8-5fd1-a3ab-070bb537bb9d | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
545daaa6-39f1-5f85-ac02-9f3afb19f8c8 | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
f6e3e40e-399c-5a93-b266-b81e8d0fe6fd | note | REFERENCE: MRPA Quality Management Plan
15d318c3-3651-5424-872c-c003ff90eeaf | note | – – – – – – – – – – – – – – – – –
46a0955c-8cb5-5a29-8a28-90e064efc042 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
29fe7c1e-9b7c-5fdc-9449-edb0df709ebf | note | – – – – – – – – – – – – – – – – –
ce9fac5b-e223-5bd2-9c6a-32d8caf3c7c4 | note | METHOD: Document Review
c2f8073c-dbef-5ee9-a92a-701e1ccb4760 | note | – – – – – – – – – – – – – – – – –
3abcd0ec-bfb9-5a7f-906f-d8c790e2420e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
cd59348f-85a9-53a7-896e-5466d716fb97 | note | – – – – – – – – – – – – – – – – –
cabfd1e2-1fe4-5e71-8955-3eadf4cd1a74 | note | CATEGORY: HP*
8d253613-f7d0-51ac-9cec-5b44abd65571 | note | – – – – – – – – – – – – – – – – –
fe6c529a-5f94-5261-8b99-9e03beffacda | note | RESPONSIBILITY: PE
e226c724-6c3b-5a2f-bb0e-a05aa513241a | note | – – – – – – – – – – – – – – – – –
0359a043-c611-5ac8-8da8-0b35d565f8d0 | note | VERIFYING DOCUMENTS: This ITP
01749e93-6fe2-5c53-88e4-1789a453f466 | date | Date Completed:
| checkpoint | 6.3 Repairs to Damaged Pipes
89cf432a-036a-5b68-935e-e2d5badb5d26 | note | REFERENCE: Section 701.31
5b996d2c-e8a5-5605-bbeb-110e7a066bd9 | note | – – – – – – – – – – – – – – – – –
f40bd7bc-e39b-586a-b2ac-d87a0283ac0f | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
2aa06115-82d7-56a2-b343-4a90349096c2 | note | ○ cracks wider than 0.5 mm
986cd197-e8f6-5a1a-8bf0-fcca6db92d4f | note | ○ spalling of concrete
3dd8cac0-368b-590a-94e9-3e8def388852 | note | ○ exposed reinforcement
dd1014d9-7e32-50d2-81c7-85689c60ef5d | note | ○ joints that are not fully engaged.
880ff1f2-3b37-5ea3-b0c9-bfee9767e0ef | note | Any pipes with defects greater than the following limits shall be removed and replaced:
04bb313f-1075-57c6-bb08-50c9c6e50403 | note | ○ longitudinal cracks greater than 2 mm
8221aea6-876e-5adf-8d3a-52c8b7e57a14 | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
cab96df1-a09e-53dd-a352-c1c0170a5dc6 | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
e5e3ac21-5b46-568a-b3e0-75ecb3dc32bc | note | ○ penetrations with area greater than 400 mm2
30a6c14c-2134-54f8-ba95-1cada10f6fc9 | note | ○ pipe joints that are separated.
727ae7b0-3b45-54cc-abe7-42cf73f4f7c6 | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
2028f1e8-22e6-55d6-8643-263514e87144 | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
c82ed60d-4417-5225-ba40-35844157e9d8 | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
782d8c0f-c326-54e0-af09-9ae206b4f0e7 | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
cfd31a4f-aec2-51b4-9913-f09673fb79ea | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
e781f43f-dc88-5fc2-a274-155a32c4f720 | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
4ba8a41c-c5c0-54c5-9b68-1deb708b4c0d | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
24ae10eb-a5f9-58cd-b7c4-b90666bf9368 | note | – – – – – – – – – – – – – – – – –
c8a68447-cecd-5c87-bbca-afa416a06647 | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
22771e1b-b1c0-5270-884d-604e07c9fd4f | note | – – – – – – – – – – – – – – – – –
cce2e277-fe64-5c87-9abd-b84e42270cab | note | FREQUENCY: Each lot
2ad05663-ee80-58fb-a4b8-cdd72dd9d3b7 | note | – – – – – – – – – – – – – – – – –
7ad42deb-f3fb-5e8f-ab29-70d7b25787c1 | note | CATEGORY: HP
7a55fe5b-42bc-59a5-bb25-bbcbe7fcb61e | note | – – – – – – – – – – – – – – – – –
1a3c1bbd-29f9-5734-964b-b5b5a6ef0806 | note | RESPONSIBILITY: Nominated Authority
e250f340-c7c0-5ee6-857b-3c0823281ec3 | note | – – – – – – – – – – – – – – – – –
f5ba17e1-54d9-575e-bb2a-27e2a13edb20 | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
9c22fa31-6549-529b-87f3-369941c5d75c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
e319ba46-cf6c-5bd3-b09f-69050c010dd6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
72e643a2-d40e-5df9-a562-7ddaa7cb4403 | textbox | Name:
bad3487d-a8f4-5566-927e-839e739bb50b | textbox | Position:
3214e678-a7f2-59ff-bd7d-22082e257665 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-135-CIV-Stormwater Pits and Pipes Installation Rev 0 | itp | ITP-135-CIV-Stormwater Pits and Pipes Installation | 6d97ff78-6114-43f5-8f64-9ad28419ca27
| section | Referenced Documentation
| checkpoint | Referenced Documentation
04391565-ddfd-5b82-89b5-bb09c68eac13 | note | Document Title: ITP-135-CIV-SSB-Stormwater Pits and Pipe Installation
a29bc45f-cd00-5623-ab9b-7e197a4fcf05 | note | ITP Description: SSB-Stormwater Pits and Pipe Installation
1c5663e7-7418-51e2-a0cb-3b7a667e2986 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
e1c5ce1f-36b3-5d1f-a164-0585099559c4 | note | Discipline (e.g. CIV/STR/RAIL): 135-CIV
dbe53d57-1794-5d9b-886e-664a75d31955 | note | Revision Number: 0
a886a32c-0648-5438-a2ec-9a04233ea81e | note | Revision Date: 30/01/2023
159d90f8-ab07-54df-a56b-3b4e3d9ebcc8 | note | ITP created by: Hiruni Wickramarathne
4e750cca-2183-529f-924b-89df6e11432e | note | ITP approved for use by: Victor Mira
5780151d-c157-5b44-aa29-ab86a8a107f3 | note | 1.1 Non Dependent
5d6e6f9b-0bc4-552c-8512-a5b49529ea0b | note | Reference: VicRoads Section 701 (May 2020)
c1e73bf9-74b9-5fc2-922b-cabb8088cb2f | note | 1.2 Non Dependent
82174e2f-3ce6-5ad7-95d2-4b7c4ae5b25a | note | Reference: VicRoads Section 705 (June 2021)
babd2626-561e-5333-90c8-5197045d916a | note | 1.3 Non Dependent
7074a2e0-9ea7-5694-89e1-e800cbadb861 | note | Reference: IFC Drawings
| section | Preliminaries-Materials
| checkpoint | 2.1 Materials
40551439-2dce-53ac-a8b7-36b844ba543f | note | REFERENCE: Respective separable package Materials and CCTV ITP
19b9881d-f2e2-5329-9604-e32f348cb43b | note | – – – – – – – – – – – – – – – – –
c5b5f5b2-072f-5ad6-a9e0-84ce1af469f0 | note | ACCEPTANCE CRITERIA: Materials are as approved in the main ITP
e6b7ad4e-d799-5438-9b1c-05aaaa7a1ed2 | textbox | Enter: Separable package Lot number:
45428f51-20e2-5750-8e01-69d90334217a | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set Out - Pits & Pipes
7b878672-94e7-5fdc-bc51-542aa87f0586 | note | REFERENCE: IFC Drawings Section 701.10
0e5bb542-fde1-5f68-bec8-c6f624036461 | note | – – – – – – – – – – – – – – – – –
b1af9fd1-7547-5d4c-aed9-5ccb0c1cad56 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
de502132-3162-50bc-9485-aeb13cf01171 | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
ff0e1dcb-e2d2-5e7b-aaf6-7045bbed7971 | note | – – – – – – – – – – – – – – – – –
97529a07-5475-5287-afce-8f1f35ca498a | note | METHOD: Survey
f6f4a246-9711-5122-98a9-40651d6355b6 | note | – – – – – – – – – – – – – – – – –
aa373280-c807-59af-b5fa-091a41b64297 | note | FREQUENCY: Each Lot
640a9e65-a0f5-5f40-b83e-8a9d7e8ececb | note | – – – – – – – – – – – – – – – – –
79143b4b-8867-5a97-9cc2-c8e57c099646 | note | CATEGORY: HP*
8c0ba418-0849-5c3e-96a3-cac0979eeeae | note | – – – – – – – – – – – – – – – – –
eca945b2-5f35-5066-9608-988ae6b1b5b5 | note | RESPONSIBILITY: PE
11e6e400-c390-5586-b6f3-2eb7d2a61d65 | note | – – – – – – – – – – – – – – – – –
14787b91-506b-52c3-ac9d-903b0045ddfa | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
49ad363c-3f36-5804-b8ba-bca714f3f914 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Pits - Excavation
2d810f6e-55d5-5509-9f19-865246ffb0aa | note | REFERENCE: IFC Drawings Section 705.05
70fb46c8-19ff-5756-8674-fb87336fd600 | note | – – – – – – – – – – – – – – – – –
2e3fb576-6d90-55dc-bb92-925d1955f8b8 | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
edfd5833-0d1b-54f2-b609-9f2c8e4dbdad | note | – – – – – – – – – – – – – – – – –
e1692ce4-197b-5f62-aa28-f60fa09e93ad | note | METHOD: Visual inspection, Measure
718f690b-f98b-5b95-8d00-3cc976240515 | note | – – – – – – – – – – – – – – – – –
612a337d-1410-5231-a9ab-88fdd8c3b64b | note | FREQUENCY: Each Lot
615790b2-d2fd-50e9-9d20-db86f46bb3be | note | – – – – – – – – – – – – – – – – –
5cc56e29-7575-5600-bb61-701f230a261c | note | CATEGORY: IP
415e9976-0e1b-5a76-9a23-6b82d00d6552 | note | – – – – – – – – – – – – – – – – –
2cdfa91f-3006-5074-a6ef-c7d113de6d75 | note | RESPONSIBILITY: SE
50d8f4fb-e91b-5d2c-a16f-b0ec965e1fdc | note | – – – – – – – – – – – – – – – – –
3ad52cc8-fd6f-54a6-87bf-706a84bf4540 | note | VERIFYING DOCUMENTS: This ITP
0436414d-8b83-51c9-901b-87a1b2c102b4 | date | Date Completed:
| checkpoint | 5.2 Pits - Placement of Bedding Material
64af1d77-0b7d-56bd-87d5-2aaa5f5e86d5 | note | REFERENCE: IFC Drawings Section 705.05
5da49dad-c1f1-5f59-95ca-9f63f140e1ee | note | – – – – – – – – – – – – – – – – –
1266dac8-acf9-51b0-a380-4e1b6a9f19f0 | note | ACCEPTANCE CRITERIA: Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
0a15d195-3abb-5f7e-be38-b4b4b5cec7fa | note | > 80mm for clay foundations
38b7964c-940a-5268-b18f-6c33601d047c | note | > 150mm for rock foundations
43020139-085e-55cd-b4ea-33f0e8ee926a | note | – – – – – – – – – – – – – – – – –
997c49d7-a930-51a2-9cb4-42106682928e | note | METHOD: Visual inspection, Measure
0e9ff813-7b52-5df7-beb4-54aed1040e7c | note | – – – – – – – – – – – – – – – – –
9f9d2fc9-63e2-5d33-90be-cc2aa98772aa | note | FREQUENCY: Each Lot
f4bfcacc-8245-5137-988e-b939e07945d0 | note | – – – – – – – – – – – – – – – – –
124ebaf6-5445-59d9-95c1-58bafb29c0c1 | note | CATEGORY: IP
62117805-e8c2-523c-856f-ee73cbc78212 | note | – – – – – – – – – – – – – – – – –
b54502a2-0b81-5043-81c1-18ae88806e7a | note | RESPONSIBILITY: SE
8fe1969b-7ce3-5f38-b0bf-7d2ec0de08d1 | note | – – – – – – – – – – – – – – – – –
2386f4ab-336f-5a10-90e0-064f26779367 | note | VERIFYING DOCUMENTS: This ITP
0d9875b8-b2ed-5ee1-82ca-de8044b66ae8 | date | Date Completed:
| checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
458bc05b-ff69-537c-ada8-493f83f33168 | note | REFERENCE: IFC Drawings Section 701.10
e896b6b0-f6e2-54de-a56d-f0d156f0b873 | note | – – – – – – – – – – – – – – – – –
ce331d73-f80d-5ad9-9a86-f13d0b82ff86 | note | ACCEPTANCE CRITERIA: Survey pick-up to verify:
d6171753-04da-5b87-b2f9-39bbcad8bfbb | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
b2c3186c-f271-5a14-aa84-7a7afd05fd17 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
d7068f62-f420-50b8-bf08-684bdbce3d7b | note | – – – – – – – – – – – – – – – – –
e0b0a2d7-3c29-5242-bc37-8c10ee08894c | note | METHOD: Visual inspection, Measure
8504748c-b769-5f0a-bef5-befac6cf1724 | note | – – – – – – – – – – – – – – – – –
f515c9ad-bef5-54d2-b2ee-7d9ab612423c | note | FREQUENCY: Each Lot
f6ea2bf8-8ece-5d44-80fc-688bcfaf26e3 | note | – – – – – – – – – – – – – – – – –
1d585d52-e33f-55a0-904a-ca9bd5d600e5 | note | CATEGORY: IP
96aae33d-30f8-5be2-aace-f82a1be302ee | note | – – – – – – – – – – – – – – – – –
a7949f3b-571a-5384-8478-62a93071151c | note | RESPONSIBILITY: SE
35c5212c-b86c-54b0-86f2-bc3de4d9015a | note | – – – – – – – – – – – – – – – – –
3365d77d-e779-52ed-b8e2-964726fde686 | note | VERIFYING DOCUMENTS: This ITP
b4260dde-be17-54c9-b247-8def34a6ba7e | date | Date Completed:
| checkpoint | 5.5 Pits - Cast in Place Drainage Pit
609e6698-6318-55c3-90f9-6350d3c4dbfa | note | REFERENCE: IFC Drawings Section 705.06, Section 610, Section 611
df480bbc-141c-552e-a698-a5a406dcf573 | note | – – – – – – – – – – – – – – – – –
69a7b3a0-c135-5407-ae84-222c2c80887c | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
ad1e1f63-0a63-593b-8c67-e383f5457f5c | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
e36d40d3-2b11-5924-93d4-e9df3af5ad9f | note | – – – – – – – – – – – – – – – – –
8fd86456-3651-5116-9c35-29f949ee3266 | note | METHOD: Survey, Measure
6e3447ee-cb17-55b5-9eb1-7a0f4e06e997 | note | – – – – – – – – – – – – – – – – –
b35b1d54-04b4-5413-8bfa-440113cd9080 | note | FREQUENCY: Each Lot
bb5e8bf5-6461-5e01-9f0e-acc881610268 | note | – – – – – – – – – – – – – – – – –
e4f1d45d-4d40-597e-852d-79eaf02f28d0 | note | CATEGORY: IP
82291ad5-0d06-5eca-a2ea-7b7de234d0ef | note | – – – – – – – – – – – – – – – – –
3006fcca-e6c8-57ef-9f01-a069a825c596 | note | RESPONSIBILITY: SE
759288ff-fdae-5d35-890b-f42f7c48d3f8 | note | – – – – – – – – – – – – – – – – –
20da4cec-f9ba-52fe-b056-cd933ff2a708 | note | VERIFYING DOCUMENTS: This ITP
56f2a906-4b3e-5585-8f23-4bac2a8f27d9 | date | Date Completed:
| checkpoint | 5.6 Pits - Jointing & Drainage Connections
0d64d62c-f8d0-5f15-9ce4-eca303654dc8 | note | REFERENCE: Section 705.11
77e43547-a14d-54e5-8a5a-58fcb16ad733 | note | – – – – – – – – – – – – – – – – –
27566d09-5a9f-54a2-bc1a-0763197cfafd | note | ACCEPTANCE CRITERIA: All connections to drainage pits shall be neatly made in accordance with Section 705.11.
261c9ed4-f8c8-5fc7-ba54-bcd5f481c749 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
feb3d6a1-b78c-5a78-b808-970d936fee75 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
6260fa4a-6c81-5458-89fa-2e980990d847 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
1f93aa24-bafa-55bf-bc79-a4d3ddb4153e | note | – – – – – – – – – – – – – – – – –
3c73f5b6-5cf1-5c8c-bf99-585e9aeb0597 | note | METHOD: Visual inspection, Measure
eeef3e09-4b13-524c-a998-7397551cd093 | note | – – – – – – – – – – – – – – – – –
d0e84b29-ce2e-5a49-b7c9-0c2b9b72c290 | note | FREQUENCY: Each Lot
2c48f7d3-7626-565e-a08b-ef302001ddb5 | note | – – – – – – – – – – – – – – – – –
f434d0d4-36aa-572b-b495-d5906ffe7d5e | note | CATEGORY: IP
d5461670-60ea-5d94-aca2-5f00377de2a4 | note | – – – – – – – – – – – – – – – – –
2b4cbe56-59f1-5d88-88a3-1b34f532fe6d | note | RESPONSIBILITY: SE
bdb7afff-7aac-5774-abc6-3f098e349184 | note | – – – – – – – – – – – – – – – – –
04df2716-989d-5249-967f-0515f3c8d6b8 | note | VERIFYING DOCUMENTS: This ITP
497fb7dc-0535-5b4b-9bb7-93c74fb579b6 | date | Date Completed:
| checkpoint | 5.7 Pits - Shaping of Floor
bc7bddb5-fbf3-5d02-95e3-7d81b60255ed | note | REFERENCE: Section 705.13
3a74d8aa-a833-58c4-ab55-30a7e8a61e72 | note | – – – – – – – – – – – – – – – – –
a03b88e8-13ad-53a3-a318-03627df242da | note | ACCEPTANCE CRITERIA: Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
2d2d6cfa-64fc-5764-a73e-c82ec7e21a81 | note | – – – – – – – – – – – – – – – – –
af024222-65f4-52fc-a451-4de179bfa5a1 | note | METHOD: Visual inspection, Measure
11d7eaae-1bdc-5497-a77a-4e3f1d799fbd | note | – – – – – – – – – – – – – – – – –
332ffd7b-f366-53d7-87b1-17dd3eae8044 | note | FREQUENCY: Each Lot
04145651-f3fd-50e2-bfac-d9fa5e863699 | note | – – – – – – – – – – – – – – – – –
fe2f15c3-9d3e-5544-a45a-f4f061424a89 | note | CATEGORY: IP
2f53112c-b277-51e7-bbea-37ae31b88ebf | note | – – – – – – – – – – – – – – – – –
59823087-6bc1-51e3-b517-0398495cd63c | note | RESPONSIBILITY: SE
e9ba0f59-87cf-56df-89aa-ec71944b1ef6 | note | – – – – – – – – – – – – – – – – –
7d144958-0a45-5b94-95a4-35d3d973f857 | note | VERIFYING DOCUMENTS: This ITP
75b726e1-948f-533e-b9d4-ea321011e74b | date | Date Completed:
| checkpoint | 5.8 Pits - Step Irons
5dd02c15-72c5-5a59-81df-eeff467ae177 | note | REFERENCE: IFC Drawings Section 705.12
448f41b6-f666-51c3-a962-83e1855323ae | note | – – – – – – – – – – – – – – – – –
9c87880b-fe88-52b4-a1b2-0f6b47f906c8 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
781ee137-d1fb-5778-b7da-4b8d1b606fd8 | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
01d9aea7-6d72-51cc-8fa3-ecda6227b23e | note | – – – – – – – – – – – – – – – – –
60ea98f3-3617-5147-8ef3-2f2e84e9ff9c | note | METHOD: Visual inspection, Measure
a5148cc5-9602-57fa-81d8-780aad3a2a37 | note | – – – – – – – – – – – – – – – – –
105e23c4-ff01-555a-83a8-d788fa97c6c0 | note | FREQUENCY: Each Lot
a14fba4c-4cf1-56d7-b279-ae817eb19309 | note | – – – – – – – – – – – – – – – – –
ed2726db-f490-5073-986f-487fb1d7e79c | note | CATEGORY: IP
226e2509-fa99-5b17-8899-3a31dd5fb32e | note | – – – – – – – – – – – – – – – – –
83e8489c-3c14-5d53-ad38-c6581634dd1d | note | RESPONSIBILITY: SE
b127bda3-6f73-5c3e-9ec0-c5e2e21e4d5c | note | – – – – – – – – – – – – – – – – –
5bc906e4-cc10-52ab-9a30-41b64ae2a084 | note | VERIFYING DOCUMENTS: This ITP
742f6b20-9472-54e9-b3f3-b2fb2f3413fa | date | Date Completed:
| checkpoint | 5.9 Pits - Fitting of Covers
edc0f83b-6b2b-52c0-816e-4ec5b707b958 | note | REFERENCE: IFC Drawings Section 705.17
fa91a51c-7681-5451-9f2e-169cb4c2cd58 | note | – – – – – – – – – – – – – – – – –
798c698b-b40a-57ca-b416-bd7e3b98cb2e | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
af428cff-3c6f-5923-abfe-a78e17140e39 | note | ○ Height shall be within 10mm of the design level.
98625480-ecf8-5f48-bf78-9bfb2961ebfc | note | – – – – – – – – – – – – – – – – –
04778c0d-11d1-5bdb-bb37-9d9ab0490014 | note | METHOD: Visual inspection, Measure
f888998f-db01-5448-a301-4bcc74003a73 | note | – – – – – – – – – – – – – – – – –
d76b92b8-e81c-5296-ac0d-4fa138f55c3d | note | FREQUENCY: Each Lot
e87e8498-9c50-51c4-adf2-31780cc3b3c5 | note | – – – – – – – – – – – – – – – – –
ab9610af-a42c-5efe-9629-3c5fc95ceb06 | note | CATEGORY: IP
0a1fc520-97e5-567a-bc5b-0d52dc7530f6 | note | – – – – – – – – – – – – – – – – –
0486bc07-c117-5cef-ae2f-c73105f502d1 | note | RESPONSIBILITY: SE
b0626317-139f-5e83-b79b-58d31b27c5db | note | – – – – – – – – – – – – – – – – –
7d5ce0a6-26ca-55aa-b411-116ac9827e65 | note | VERIFYING DOCUMENTS: This ITP
74996fca-3785-509c-a39b-3e856b2dc7b8 | date | Date Completed:
| checkpoint | 5.10 Pits - Pit Lids
50aadc2b-916b-5fc3-bae7-295d2212acd9 | note | REFERENCE: IFC Drawings
501ef372-e25c-5035-8a01-832376335468 | note | – – – – – – – – – – – – – – – – –
192a0c8c-001d-55e0-bfdc-481598f424ae | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
e8d8a7a5-111c-5cb7-a616-7ec47fe8d96a | note | – – – – – – – – – – – – – – – – –
4cdb6932-f84b-5938-8efb-be66e9b0a2aa | note | METHOD: Visual inspection
a5ff5dab-7b49-5307-b0cb-937335f7b31e | note | – – – – – – – – – – – – – – – – –
69d565e8-5aaa-57ae-b339-e837eb7ccfaf | note | FREQUENCY: Each Lot
40654cc2-9ea0-5db9-a70a-f86a0db207ba | note | – – – – – – – – – – – – – – – – –
cc327ba1-b123-5563-bcae-54afef8572c1 | note | CATEGORY: IP
8331a104-f7e7-5fa6-a6d2-547a7fdc98ef | note | – – – – – – – – – – – – – – – – –
50b148ce-7272-5c0f-9a3e-c1db3a9cacc6 | note | RESPONSIBILITY: SE
9c0b9f5b-356e-52f6-912c-fc08778de89b | note | – – – – – – – – – – – – – – – – –
7385f7ff-b8eb-559c-ba7b-a05263e5390c | note | VERIFYING DOCUMENTS: This ITP
a74c7e0e-564d-58d4-8891-4e187fe34b0e | date | Date Completed:
| checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
8bdaa3aa-29f9-5d5c-ae61-c709d13d8ffa | note | REFERENCE: Section 705.18
74fcdf24-3240-5cca-9995-ee6a9871b189 | note | – – – – – – – – – – – – – – – – –
77aee714-2611-54ca-b653-b3099b2b43a9 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
9fbb6f72-a621-5960-a46f-1e2a3e5a6b06 | note | – – – – – – – – – – – – – – – – –
177f6e43-8aa2-5965-a6ab-6505d28cf0cf | note | METHOD: Visual inspection, Measure
63932334-db7b-5bd0-b6b8-3438048083c9 | note | – – – – – – – – – – – – – – – – –
de762caa-8398-5364-b16c-2128b058d6d9 | note | FREQUENCY: Each Lot
e23c8a2d-92bb-58a6-a00c-d3c41490f7a8 | note | – – – – – – – – – – – – – – – – –
dd2b3275-414b-5acd-a6ef-5d548191f728 | note | CATEGORY: IP
645490d1-0b4f-5cc0-86f2-5ecbd440b39f | note | – – – – – – – – – – – – – – – – –
932495fd-b823-5d3a-8e5d-300f17108cbf | note | RESPONSIBILITY: SE
38323c65-cafe-57b8-ba7d-6b47a9d064f1 | note | – – – – – – – – – – – – – – – – –
e130590c-d1cd-55ec-afe1-42e033f408ab | note | VERIFYING DOCUMENTS: This ITP
c2d42cda-786c-51cf-8f4d-84845a999ecc | date | Date Completed:
| checkpoint | 5.12 Pipes - Trench Excavation
a1463092-5606-5496-b176-651530309ec5 | note | REFERENCE: IFC Drawings Section 701.15
f0d641a3-f0bd-53a1-9a5f-dcbb2777d0aa | note | – – – – – – – – – – – – – – – – –
26fa592e-010e-58b6-ba1c-70ed07d252bb | note | ACCEPTANCE CRITERIA: Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
297a2a4b-f372-5a4f-bd89-5b767c4ec2d7 | note | > 300mm, < 600mm for RCP
4ebbd5ce-815e-59cc-8c9b-91ff751b505f | note | > 150mm for Flexible Pipe
aa6cb807-e3e8-54b0-b444-7d2e94ba03c7 | note | ○ The base of the trench shall be compacted to refusal using mechanical plant.
66f76f46-21c8-57fd-bdc6-ead0401cac02 | note | – – – – – – – – – – – – – – – – –
33cfb1e7-53d7-5dab-bc32-b57e2d1855bf | note | METHOD: Visual inspection, Measure
42430b2f-b050-5a01-ac6d-9f67b33e348d | note | – – – – – – – – – – – – – – – – –
2ad2fbfd-45f3-564a-b7c6-c75b88153ed1 | note | FREQUENCY: Each Lot
05551ec1-83b5-5dd1-9a5b-323b999bc4e9 | note | – – – – – – – – – – – – – – – – –
2d39d301-36e3-58b9-ac51-857d83873d39 | note | CATEGORY: IP
05e121ad-9fac-5cde-bf8e-a16f9c0e8879 | note | – – – – – – – – – – – – – – – – –
bc3d3b8b-bf3d-5918-979a-31db01cafa0c | note | RESPONSIBILITY: SE
a2307047-e7f9-5f02-9629-9e78084b7ad2 | note | – – – – – – – – – – – – – – – – –
62c27364-2321-5fcf-a00d-b9ebedf6bec7 | note | VERIFYING DOCUMENTS: This ITP
65d3aaa7-52e1-58b8-9a8d-04112b6926c8 | date | Date Completed:
| checkpoint | 5.13 Pipes - Bedding Placement
ac3d6f44-6c21-5004-a6bc-84492a3ef895 | note | REFERENCE: IFC Drawings Section 701.16
6799b2c5-dd59-5092-a4c1-8b994591aae8 | note | – – – – – – – – – – – – – – – – –
5860d7ce-d804-5e76-b01e-97b29e6bc237 | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed in the full width of the trench to the below minimum:
1c5cae2f-5af6-53e7-a2db-f52df51f9a4a | note | > 100mm where D<1500mm
dfdaf92c-f7f5-51c7-9f0b-ec432124fbc6 | note | > 200mmwhwere D≥1500mm
2dad76fb-3ac1-5a9e-a78e-a8f2488feee9 | note | ○ Bedding material shall be placed and compacted in layers <150mm loose thickness
5e20a4e3-7a82-5a3f-ab7b-cdc9ff507d23 | note | – – – – – – – – – – – – – – – – –
4cb251dc-0c1e-5ca2-85aa-458f47b1fe1f | note | METHOD: Visual inspection, Measure
7fab2cd9-5192-57b3-9d66-ceb993c3bfd3 | note | – – – – – – – – – – – – – – – – –
75fa4392-b9b6-5c67-a057-889e4d017411 | note | FREQUENCY: Each Lot
fc593a07-7a66-5701-ad28-9d8a08b6a884 | note | – – – – – – – – – – – – – – – – –
2ba3133e-f5ca-52c1-905d-54c976bdf442 | note | CATEGORY: IP
b0577772-2466-5531-b1d1-826b34d14710 | note | – – – – – – – – – – – – – – – – –
8d5e134e-1825-560d-bdc2-8b859a02406d | note | RESPONSIBILITY: SE
d111d644-9c67-596e-8c1d-1bd0d17c5c99 | note | – – – – – – – – – – – – – – – – –
7acd55ea-b7cc-5549-abe2-173ee6fd232b | note | VERIFYING DOCUMENTS: This ITP
7908cd69-b9e2-51a7-9cd3-8a6067ab13f9 | date | Date Completed:
| checkpoint | 5.14 Pipes - Bedding Testting
357ef94f-93d9-53f9-8942-2370391ddfe1 | note | REFERENCE: IFC Drawings Section 701.20
de978ca2-ee71-5ae4-aec0-04ca9208041e | note | – – – – – – – – – – – – – – – – –
94b2e6bf-1a0e-52a7-b32e-c58504bfdd1e | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill). The number of tests per lot shall be three
d26be425-3de5-57f3-8709-d56600a89c7e | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
a87f6a72-6411-5078-9942-257eb00b495f | note | – – – – – – – – – – – – – – – – –
28e87581-6126-5b6e-9f15-a7480cbfdaf0 | note | METHOD: Compaction Test
df6f56d3-ca6b-508f-82e7-192b2bed6b5f | note | – – – – – – – – – – – – – – – – –
b7993350-6503-5247-ba7b-eba98056e5ef | note | FREQUENCY: Each Lot
0cd184fc-5ce3-5eba-b14e-611c9b21d436 | note | – – – – – – – – – – – – – – – – –
0a573f6e-17b3-561b-9cca-bbfd461c2a2e | note | CATEGORY: IP
1ffcb4ac-537d-59c5-a794-b60d48ceb221 | note | – – – – – – – – – – – – – – – – –
14564162-7810-56d1-9ee2-fd0e2fac0889 | note | RESPONSIBILITY: SE
c592267b-c6af-5ba7-a52f-84c095544999 | note | – – – – – – – – – – – – – – – – –
f04e8044-4e42-5918-afa3-5477cf00f527 | note | VERIFYING DOCUMENTS: This ITP
5e46c042-b1c8-52a9-a5a1-4eb855afc638 | date | Date Completed:
| checkpoint | 5.15 Pipes-Placement of Pipe - Flexible Pipe
861afdc8-bc33-59c3-81b9-ae1bcf4fe86f | note | REFERENCE: IFC Drawings Section 701.17, Section 701.22
edd19266-2aa3-5b65-a23f-1a26fa0e155c | note | – – – – – – – – – – – – – – – – –
e19a2ef3-cb66-5dc7-9fff-d21d6878bfca | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
ec07afc8-ab64-5b3c-96b3-51dd388e92cc | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
44910d46-81fd-5fca-8a91-177ee1defebd | note | – – – – – – – – – – – – – – – – –
16286394-5e06-55c6-93a3-01b830726294 | note | METHOD: Visual inspection
eaa23ad4-ebac-5f7f-b596-1282a7daeba4 | note | – – – – – – – – – – – – – – – – –
b5e6febb-7fd5-524a-b633-970fc9aa942c | note | FREQUENCY: Each Lot
e5ce1914-6afc-511a-8141-37911fb26059 | note | – – – – – – – – – – – – – – – – –
6eff7d26-3e87-5b60-8c7a-d88e3c54b274 | note | CATEGORY: IP
7464998c-0ea9-5412-8e7e-62b19289d4e6 | note | – – – – – – – – – – – – – – – – –
05516062-1f12-5953-bae4-270d6880a197 | note | RESPONSIBILITY: SE
8829ebcd-9dac-522c-9c8d-fd52e208b0a7 | note | – – – – – – – – – – – – – – – – –
a68ced0d-2bad-5c60-84d7-0d3a8ab4b1cc | note | VERIFYING DOCUMENTS: This ITP
287a57f0-8617-55bf-8be4-3a4618e0fb29 | date | Date Completed:
| checkpoint | 5.16 Pipes - Lifting Holes
7d592c8b-eb5c-546e-8de3-9398804b56d7 | note | REFERENCE: Section 701.18
703cd847-5def-5868-b123-f79145bf292f | note | – – – – – – – – – – – – – – – – –
1141b5a5-00d6-567e-9002-7a647940bb8c | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
07595bf6-38d6-5591-8d98-018d956aa6b2 | note | – – – – – – – – – – – – – – – – –
a120d573-1a4b-55e8-ba95-37e39bedaabf | note | METHOD: Visual inspection
9a871ad1-289e-59d7-bbbf-cfa6020fa048 | note | – – – – – – – – – – – – – – – – –
071964d8-cfca-515e-b99b-f418252b9ff4 | note | FREQUENCY: Each Lot
cce80615-47f1-5e8a-a212-e9761170d0d8 | note | – – – – – – – – – – – – – – – – –
a52041a3-c76f-5a2e-a9cd-cf5957ff70f3 | note | CATEGORY: IP
f1932905-c9c3-5cac-8318-a5a928630b76 | note | – – – – – – – – – – – – – – – – –
95ec6fc8-ff84-5f15-b09d-baec895dcbed | note | RESPONSIBILITY: SE
8af52a63-1b96-5d77-ad9b-62253f9108de | note | – – – – – – – – – – – – – – – – –
b13d0800-5fcf-55b5-a50a-9f174b0bad1c | note | VERIFYING DOCUMENTS: This ITP
12284204-4fbd-5f34-ba8f-2c6e692a48da | date | Date Completed:
| checkpoint | 5.17 Pipes - As-built survey pick-up
3b8be892-f21b-5d58-97c1-c65e45a3a212 | note | REFERENCE: IFC Drawings Section 710.10
0d3bcdde-d63a-5d01-a70d-c68406f2aef0 | note | – – – – – – – – – – – – – – – – –
d83eba63-105c-5a27-96f9-8060212bc7a1 | note | ACCEPTANCE CRITERIA: Each run of underground drainage shall be Survey verified prior to backfilling.
892ad12f-529f-57a4-8acc-659fb507fb17 | note | – Offset pits to kerb +/- 20mm
bf2e742d-b948-5722-9d5c-e3a5fc7f9529 | note | – Plan location pits not adjacent to kerb +/- 100mm
d16fde89-66ce-5620-869b-6378d1028ea4 | note | – Invert level of pipes at pits +/- 50mm
f502bbcc-ab87-5cf0-a297-77631d3dc63a | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
6c3eda35-e23f-57e6-80d4-aea5c1929148 | note | – – – – – – – – – – – – – – – – –
230d2595-808f-59c2-b3c8-17ddebf90e28 | note | METHOD: Survey
f137af92-4eff-5f2d-ab63-59786d907bc4 | note | – – – – – – – – – – – – – – – – –
b7616ea3-a8f3-5886-b498-abe8634c35aa | note | FREQUENCY: Each Lot
31b92d13-fccd-502d-a130-d89297c18b45 | note | – – – – – – – – – – – – – – – – –
0e1632ae-e251-5cbb-b7ad-a2e704a55650 | note | CATEGORY: IP
4994d53b-dd57-5a75-b8e7-339976719e34 | note | – – – – – – – – – – – – – – – – –
e7364b02-5362-5234-ae13-33326c100cc9 | note | RESPONSIBILITY: SE
1e691812-b602-5f82-8185-583a18993683 | note | – – – – – – – – – – – – – – – – –
f6383bc5-f1fe-558d-b481-1bcd7364cdd8 | note | VERIFYING DOCUMENTS: This ITP
bbb8884e-eaa3-5b92-9794-da7891bcf53c | date | Date Completed:
| checkpoint | 5.18 Pipes - Backfill Placement
377188da-4956-5ad2-94d9-de472b701cf3 | note | REFERENCE: IFC Drawings Section 701.16
fbf84ebd-efce-5b6e-839c-6d5ef49d6a6b | note | – – – – – – – – – – – – – – – – –
665909ef-1a05-5b65-8bf8-687ab108dcb7 | note | ACCEPTANCE CRITERIA: Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
cf07057d-8aab-513f-afb5-1cbe745c8eab | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
d0b7667f-f705-5928-92ad-dfd613b4c412 | note | – – – – – – – – – – – – – – – – –
6be27db9-0dd3-5493-b420-1f81aa543317 | note | METHOD: Visual inspection, Measure
b71c8e4b-f354-5817-990f-0fda4a79dc82 | note | – – – – – – – – – – – – – – – – –
7d676f50-22ef-51fb-8b0a-f908b7fa2187 | note | FREQUENCY: Each Lot
c4e239bb-171a-54b7-9eb4-0f646b3d31e2 | note | – – – – – – – – – – – – – – – – –
3919dfe0-75c5-5f47-9e31-fe4c29ff8546 | note | CATEGORY: IP
6a1c15f4-7ea3-5b13-a308-a3eddf8b2d78 | note | – – – – – – – – – – – – – – – – –
63af109a-b6f9-5bf1-a6af-e3ef13510c05 | note | RESPONSIBILITY: SE
ff3ab324-383e-5842-8a2d-406d21979164 | note | – – – – – – – – – – – – – – – – –
13d2eea5-85a9-53e4-a64d-d41d36636788 | note | VERIFYING DOCUMENTS: This ITP
776ba891-6555-5eb7-9c03-c829d95609b7 | date | Date Completed:
| checkpoint | 5.19 Pipes - Backfill Testing
ecff3aa9-25c9-51dc-85e3-912c0caebe93 | note | REFERENCE: IFC Drawings Section 701.20, Section 701.29
80dfd554-7aa8-5211-8ed3-70c33ec15de7 | note | – – – – – – – – – – – – – – – – –
0e1abed8-a51e-51e7-863d-43bed9209fff | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
15655407-923f-5050-bb23-1b853ee8932e | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
78a136ac-d489-51ba-bf16-ddb7fd2260fd | note | – – – – – – – – – – – – – – – – –
0cd7e1d9-301f-54eb-b127-33fe054dd6be | note | METHOD: Visual inspection
f7d471a1-6b07-5b60-a8aa-ce59eac59c52 | note | – – – – – – – – – – – – – – – – –
a99e0168-54a8-5a9b-affe-edc77d09605c | note | FREQUENCY: Each Lot
3b414779-eaf9-52b7-93b4-27d179c76caf | note | – – – – – – – – – – – – – – – – –
68b0465a-f4b2-57bc-8c51-365b0063ad08 | note | CATEGORY: HP*
25786544-96fd-5243-a293-fedd3717175f | note | – – – – – – – – – – – – – – – – –
3639baaa-b831-51cb-b394-88b7688bef0a | note | RESPONSIBILITY: PE
2c8bf7c3-a24e-5b1c-9085-a6acc4817efa | note | – – – – – – – – – – – – – – – – –
169a8a2c-2c94-5063-8cd9-64b06b0f9dc2 | note | VERIFYING DOCUMENTS: This ITP
454803be-d5b9-58ec-a6cb-6294c5b986b3 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Flushing & CCTV
4e959b29-8ec2-59e7-9214-c1b594c5f70f | note | REFERENCE: Section 701.28, Section 701.30
aa4c8b68-91e5-5cf5-8cd6-fdea51891fca | note | – – – – – – – – – – – – – – – – –
616a7114-b409-5c42-a4a4-f4d846526651 | note | ACCEPTANCE CRITERIA: Refer to Respective CCTV and Material approval Lot
c8563f6d-d0bf-57bd-aaa5-76da25956ac1 | textbox | Enter CCTV and Material approval Lot number: [Text Box]
04a7445b-767a-5c34-ac4d-393ba8e521f8 | note | – – – – – – – – – – – – – – – – –
bb93bb93-32c0-5a56-b067-ece9d1f5c43c | note | METHOD: Record Review
1db6afec-9d12-5eeb-88f2-ce8403e090c0 | note | – – – – – – – – – – – – – – – – –
2a952972-ae55-54dd-a18b-8f0d3415d3bc | note | FREQUENCY: Each lot
4fd9cfd0-a931-5fd9-9325-189b26137b9d | note | – – – – – – – – – – – – – – – – –
5283c573-ae8b-5382-8bbe-9c2b4a311b78 | note | CATEGORY: HP
e9acc9c1-d45a-5d98-82d1-4703b010ab88 | note | – – – – – – – – – – – – – – – – –
7820f300-6964-5eab-bac0-b8973a6679b2 | note | RESPONSIBILITY: Nominated Authority
83639742-907b-5788-9d25-7fbf2e6deebf | note | – – – – – – – – – – – – – – – – –
83f141c2-4bf5-5757-9b0a-f8e54e6fd564 | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
a7e446c9-17b5-50db-b628-37529836ae4d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 As Built Survey
ac4bf227-e29d-5ca4-b4c5-d5128d802c5c | note | REFERENCE: Section 701.10
8f4203d1-68f5-5b60-b1cd-3749142c122a | note | – – – – – – – – – – – – – – – – –
8585ed51-db2e-5cda-95fd-b7ebaf50c5a9 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
305a0baa-6542-5126-b5a8-d66e5342e435 | note | Attach: Survey conformance Report
c0c27a5c-12de-55fd-9991-009d014002d2 | note | – – – – – – – – – – – – – – – – –
cfa9c418-44b4-5171-8468-8fffe3ba4e06 | note | METHOD: Document Review
6e8fadd7-afc5-52e4-a4dd-50181f441d0e | note | – – – – – – – – – – – – – – – – –
f548025d-bc90-553d-b07a-c99525e5d5aa | note | FREQUENCY: Each lot
e5b6fade-9b6a-5b71-8eaa-66af34ff61b9 | note | – – – – – – – – – – – – – – – – –
8d62d037-f20b-5dea-a036-8bf380522f93 | note | CATEGORY: IP
25c46a9b-d0a0-535f-b646-e7ffed017b7a | note | – – – – – – – – – – – – – – – – –
fd8c95ca-bf16-5dd1-b755-c8918acdea2f | note | RESPONSIBILITY: SE
7d287b7b-4d13-5999-bac5-be69edb0e15a | note | – – – – – – – – – – – – – – – – –
96e0f7ea-d1c3-562c-8a64-8594762250a4 | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
cb10bad2-9bd4-5aba-9e2e-9988c2227bbb | date | Date Completed:
| checkpoint | 6.3 Repairs to Damaged Pipes
0ac072ff-c7a2-5be7-af55-c5a34e2ada1d | note | REFERENCE: Section 701.31
683bff01-5bf1-5b3f-bc29-651237a0932e | note | – – – – – – – – – – – – – – – – –
5b67f1b4-3063-5dc8-97b4-35cda1e5d7fc | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
78b7aa52-6cd6-5a7b-a610-650def9f1cd4 | note | ○ cracks wider than 0.5 mm
15e592aa-f895-51e9-a6aa-dccbc5ab8656 | note | ○ spalling of concrete
9154b395-f705-5e47-939c-9b30f4d357f2 | note | ○ exposed reinforcement
b1420640-b359-5147-9b0b-d0dfed62e269 | note | ○ joints that are not fully engaged.
2cbf9bd6-4e4e-5154-aea5-14fd7a81d457 | note | Any pipes with defects greater than the following limits shall be removed and replaced:
14924b46-54fb-563e-974c-63ff508ceb65 | note | ○ longitudinal cracks greater than 2 mm
2267ee54-6234-5992-9c66-48d262628423 | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
78734db6-c593-5a69-bf3d-7b0a84a97896 | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
4b686584-f1af-5659-8173-ad62aefd0c67 | note | ○ penetrations with area greater than 400 mm2
5febb688-00d2-5bac-85c6-d40ad9b4231d | note | ○ pipe joints that are separated.
cc3d03e7-88eb-57a3-8b70-bdbbdf45007d | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
2dd8defe-30de-5bfa-acb5-49ef08a2bd19 | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
5887dd39-64bc-52c8-8dd5-337d6dd77808 | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
1cf38c8e-c4bb-568a-8a8a-08427b1e6244 | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
ff9788fa-b3dc-5a42-ba6d-754b626a58c6 | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
b2813dfd-29a2-5552-87e8-ba502f3e1d17 | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
e68d66ec-30e2-545f-a38a-e240b982abfa | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
dabf3ff7-37d1-52bd-b38d-656b71e4f25c | note | – – – – – – – – – – – – – – – – –
36533370-6300-5273-b7c8-ee50b21e4082 | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
df70032a-fb2e-57a2-b68c-8e1429e9d69e | note | – – – – – – – – – – – – – – – – –
8754990d-a75d-5f5d-961f-84b8b9c59b42 | note | FREQUENCY: Where applicable
8cdbb2fc-a769-5fbd-b2c9-c172e810d9d8 | note | – – – – – – – – – – – – – – – – –
f4355d79-07b9-51b9-91d2-182cfa2b4fe7 | note | CATEGORY: HP
18398917-6145-5776-9a5f-340063985ad8 | note | – – – – – – – – – – – – – – – – –
6338928d-e074-54cb-9f3c-11a80325a141 | note | RESPONSIBILITY: Nominated Authority
44f34830-8dd0-51f9-9b33-69a85c75f1af | note | – – – – – – – – – – – – – – – – –
44f45f1c-ae05-5342-8b6c-1be6ac9e11ac | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
0df6f47e-f85e-5b7f-b9dc-77667b3d9a2b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
681fb432-530e-58ac-af25-eaf1917953d9 | note | REFERENCE: MRPA Quality Management Plan
15e89e84-e83a-54a6-afe0-a35491cad461 | note | – – – – – – – – – – – – – – – – –
732dd6e1-745b-57d7-a24b-ee916e569d01 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
680b97b4-c3ed-5d59-acaa-8c53d0730abe | note | – – – – – – – – – – – – – – – – –
6d876135-66b4-5549-955d-1539ae7c6928 | note | METHOD: Document Review
7e902bcb-ac38-561f-9841-1e99c909ea5a | note | – – – – – – – – – – – – – – – – –
e64f47ab-b14f-53f5-aae0-fe8177f45b02 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
08bb4ab2-0702-58fb-916d-87ca8947838a | note | – – – – – – – – – – – – – – – – –
e1f5500a-9673-5539-828c-a9e48382f795 | note | CATEGORY: HP*
69f21e10-6cd6-5a17-a703-dc066c0d46b6 | note | – – – – – – – – – – – – – – – – –
d98eb0fe-ddbf-5b13-b237-989ab46c02ec | note | RESPONSIBILITY: PE
cf743bf5-17b1-5fbe-a231-8ffcccbf817b | note | – – – – – – – – – – – – – – – – –
a1927ae5-d1e8-5578-9607-ba85632ba99a | note | VERIFYING DOCUMENTS: This ITP
6ee37e75-2a38-58dd-84eb-5f739d35c300 | date | Date Completed:
| checkpoint | Final Inspection
01835ab7-f82a-5ace-82a0-f426d326f9ae | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c5352df0-bb0a-52dd-a345-c8be499cf59d | textbox | Name:
4df9ed7c-f7db-5634-8501-fa6b20f42c80 | textbox | Position:
a8acc463-2cff-5655-a5c3-576d7ef680e2 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-144-CIV-SSB-RSS Wall Construction Rev 0 | itp | ITP-144-CIV-SSB-RSS Wall Construction | fc449c12-f15e-468a-8a2e-3cb6f859bec4
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7ad3c78b-2f0b-513d-8c6f-da6190184698 | note | Document Title: ITP-144-CIV-SSB-RSS Wall Construction
d880b081-dade-5850-b050-de4600aa1b05 | note | ITP Description: SSB-RSS Wall Construction
a9a0bcdb-a8a7-5f93-9c09-9402dfb91255 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
88e74bca-e038-590c-88f1-20e96e7fa230 | note | Discipline (e.g. CIV/STR/RAIL): 144-CIV
afc06562-808d-5465-9916-83b2c7633a51 | note | Revision Number: 0
903f386e-73a4-51be-85bf-84af5e900434 | note | Revision Date: 18/3/2024
cbebac8e-17f4-5121-a7b1-8c6407ff04f7 | note | ITP created by: Victor Mira
cddbb23b-899b-509a-a200-df903ce7564f | note | ITP approved for use by: Victor Mira
ccd2882a-0873-5f42-b217-0b353c7e2dc9 | note | 1.1 Non Dependent
4b46dea2-ef3e-5672-86f8-86df3d031cc9 | note | Reference: VicRoads Section 682 November 2018
89989d33-1342-51fe-9733-7a454f9a72a4 | note | 1.2 Non Dependent
ce0b7fd0-fa2a-539a-bace-ca4c9177c8bf | note | Reference: VicRoads Section 204 December 2015
dbdd145e-0b3f-5b84-8e50-600928bf60dd | note | 1.3 Non Dependent
acce2aee-1fdc-5a25-b126-5e5bcfabb53f | note | Reference: IFC drawings
| section | Preliminaries-Materials
| checkpoint | 2.1 Concrete-Leveling Pad
12841b11-31cb-59c2-a511-54310882c823 | note | REFERENCE: IFC drawings
3e6f675f-680b-543a-b3e4-b30a92334305 | note | – – – – – – – – – – – – – – – – –
0d8cd981-3262-5320-932b-7fa1e6e80bc4 | note | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
7b9389ab-22b9-5941-86e3-f5d19b738fc3 | textbox | Reference: Teambinder MA number:
65eb4491-4549-5708-b90c-baa40fa5886a | note | – – – – – – – – – – – – – – – – –
69e86604-782e-5b81-8026-1359a7960350 | note | METHOD: Document Review
8893c1d3-5a3e-5a34-92da-43fe8b713d88 | note | – – – – – – – – – – – – – – – – –
6ef02bae-8f12-582c-afde-2adb97a07544 | note | FREQUENCY: Each element
c8884770-39be-555b-9141-89a559738aef | note | – – – – – – – – – – – – – – – – –
4a3ba61a-7e29-5d23-8431-32acb60834ed | note | CATEGORY: HP*
935018c7-aaa8-5851-ba95-e5f701728ef0 | note | – – – – – – – – – – – – – – – – –
4d2335d1-4704-519e-a0d9-51700c5a360e | note | RESPONSIBILITY: PE/Nominated Authority
f75e9f06-f1f6-5fed-a681-2bdcdf8c6b2d | note | – – – – – – – – – – – – – – – – –
e0358049-d6d1-5d85-8fa2-85c7978dbf7a | note | VERIFYING DOCUMENTS: Material approval
36abb0e3-2987-55c6-b8f3-ce6d7b37032b | date | Date Completed:
| checkpoint | 2.2 Select fill
5538da05-feaa-5df2-94b6-8eb7434ba3ec | note | REFERENCE: IFC Drawings
cd9c5b4b-30a3-5136-9ecd-8cb4d2c851e2 | note | – – – – – – – – – – – – – – – – –
e1f2b542-6c18-5282-86d9-f5fca95f73a7 | note | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
16d9e723-6f50-52fa-81fe-07330e507a9c | note | ○ UNIT WEIGHT: 22 ± 2 kN/m³
98c581e7-e513-528e-b93a-9436682e6bdf | note | ○ INTERNAL FRICTION ANGLE ≥ 34.5°
4aae1d1f-b387-5314-b75c-c92ff531085f | note | Gradation:
409235d4-dd76-5a80-901d-261e26d168d3 | note | ○ 150mm : 100% PASSING
cde48e1b-8c0e-5443-a66a-6e23407ddb4a | note | ○ 37.5mm : 60 TO 100% PASSING
047f778c-56fc-5320-8448-cd0d0782be95 | note | ○ 9.5mm : 25 TO 100% PASSING
c3769af8-8fa0-56a6-bfdf-4c8ffe1f8740 | note | ○ 2.36mm : 15 TO 100% PASSING
77eb1c01-c387-5ae0-906f-0ebe7c8de976 | note | ○ 0.6mm : 10 TO 100% PASSING
26d6702a-8a8c-5fe3-b761-cab58d85c7a0 | note | ○ 0.075mm : 0 TO 15% PASSING
1a7fce39-0557-5249-898d-edaf0c0e28fd | note | Electrochemical Properties:
fcf14360-15d9-5928-afd3-329ebfb6d946 | note | ○ RESISTIVITY >1000 Ω-cm
c3685c0f-88f1-5e4b-b87d-8a627ad7a2b8 | note | ○ CHLORIDES <200 mg/kg
3d826144-95b9-5d14-a59b-bc5f874206fa | note | ○ SULPHATES <200 mg/kg
f931cc97-7724-5fca-8ebd-41dce801ca52 | note | ○ ORGANIC CONTENT 0%
5332a1eb-3b36-50e1-9787-5b67abd3cd2e | note | Structural Properties:
49fe130d-491f-53bb-a217-35467b982d8c | note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
f30e1e07-cdae-5e2d-8c22-9b9b0e3e771a | note | ○ LIQUID LIMIT ≤ 30%
05a797f5-601f-591c-bb02-660ed051439b | note | ○ PLASTICITY INDEX ≤ 12
abfe3017-4c42-523b-b463-7fd939f1777e | note | – The select backfill must meet the minimum requirements of Vicroads Type A filling
b62174d2-f934-5310-966b-95a9e5584219 | textbox | Reference: Material approval in Teambinder
a1726c78-5a9e-5a43-8610-05b1cfd71514 | note | – – – – – – – – – – – – – – – – –
4278ada4-0aee-52f5-9d06-2864e2a4a665 | note | METHOD: Document Review
20164af5-b0ae-57da-a26d-c1c9735ab14f | note | – – – – – – – – – – – – – – – – –
e950c5f9-1b81-5b04-b1fc-11b967a4ef66 | note | FREQUENCY: Each material specification
2238bd13-cc08-50f8-baa1-1c38a1f7858f | note | – – – – – – – – – – – – – – – – –
2219de46-0ad1-5a63-8905-8b6f14830894 | note | CATEGORY: HP
5ec9cb57-0111-5d60-b1b2-3d6daa32321a | note | – – – – – – – – – – – – – – – – –
73d6dcdf-e915-5f99-8a83-40ea9c6a4df3 | note | RESPONSIBILITY: Nominated Authority
4f96df17-2030-5b3e-a9a4-ddb52bcae5ee | note | – – – – – – – – – – – – – – – – –
31e39188-ef3a-5588-b378-f6d6483a8b4d | note | VERIFYING DOCUMENTS: Material approval
f5e59fd2-8dfe-5122-9c74-cbe1447e16d1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Perforated Pipe-material
a9ead059-b8b3-5175-ba46-e2a4ad941b2e | note | REFERENCE: IFC Drawings
6a910136-450a-5bd8-a1bf-c5c6c35b165a | note | – – – – – – – – – – – – – – – – –
cc06d5d2-7525-5a4a-aa05-e9adc4c8af4a | note | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
5a3b6409-1321-5775-8753-bdb3af193482 | textbox | Reference: Teambinder MA number:
8001ef0e-7023-542a-aa87-bc2e87307988 | note | – – – – – – – – – – – – – – – – –
a1c29cfe-5a57-52c3-b14c-cbae3039e15c | note | METHOD: Document review, Measure
fa8b5889-3013-5b6b-942f-867c06877d97 | note | – – – – – – – – – – – – – – – – –
123f1c54-3481-5d14-9b77-18eb62ef760f | note | FREQUENCY: Each wall
77a2285c-f12b-5b20-a6f9-c553ec69f8c7 | note | – – – – – – – – – – – – – – – – –
d9957710-3f72-5ac3-9b61-761e76413309 | note | CATEGORY: HP
01cf6161-989b-5d03-9df7-9e410c61c95e | note | – – – – – – – – – – – – – – – – –
ddeb2f02-2a00-594c-aa61-09ce4dff610b | note | RESPONSIBILITY: Nominated Authority
627f4dad-b2b8-5546-afda-40a76ab5cad0 | note | – – – – – – – – – – – – – – – – –
189f15cd-f97c-535c-9608-cb7af52418a8 | note | VERIFYING DOCUMENTS: Material approval
3533b6bb-7a00-5e3a-bf0a-cb7255599af9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Documents
| checkpoint | 3.1 RSS Panels
79090a72-c573-512e-acf8-ec970a324621 | note | REFERENCE: IFC drawings
c10c9a27-577a-52b4-aa26-44f650c43b22 | note | – – – – – – – – – – – – – – – – –
e7ef0130-b096-5b10-9fb6-4a4252d4aba7 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
d6c9a64f-07f6-5bcd-b288-1792e9ce54d8 | note | i. Certificate of Compliance / Birth Certificate
19a50b73-4b6a-5835-9099-d2b59466f32b | note | ○ 1. Concrete strength;
001a0a5e-443d-54c9-9da1-014f198c5f29 | note | ○ 2.Date of manufacture;
d5c64f41-0532-5ce6-a45b-7aad66cd3069 | note | ○ 3.Unique Identification number;
ae20fc96-8122-5e3c-9c34-1534935c609c | note | ○ 4.Mass;
43200c0f-b98c-5c18-b138-da3972291f87 | note | ○ 5.Confirmation of number, type and capacity of lifting inserts;
23b7c9c5-217a-52b8-98fb-77e2abb9cc65 | note | ○ 6.Quality assurance sign-off.
717b00a8-882f-5b2d-adfa-b0d1aa737e1f | note | ii. Compressive strength test results
053e846d-8a19-5a9e-aeab-e6a8cff9a15f | note | iii. Precast Lifting Design
b7a4adc2-5875-5bfb-833d-f4101f54d551 | note | iv. Pre-pour check sheet / ITP
e6720480-6bc6-58c2-900c-c6a4f14ba79e | note | v. Post-pour check sheet / ITP
36cd4d9b-2573-53e5-850c-cecf22b4e59f | note | vi. Covermeter check record
b4c8b84f-46da-5ac3-8134-9b43a7b104e4 | note | vii. Record of dimensional measurements
dac40754-5737-5351-b276-9a595e320fd0 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
ec34e2b0-8d76-5719-a87d-e32a3b46e342 | textbox | Reference: Precast panels MDR Lot in TeamBinder:
3d306289-e4f8-5a62-b6ea-2647c2a61649 | note | – – – – – – – – – – – – – – – – –
c1ed81aa-9be8-5366-afdf-bfb6c21a4e5e | note | METHOD: Document Review
4967a8f1-5b9c-5b3a-a32c-3326f2bfa482 | note | – – – – – – – – – – – – – – – – –
32d6a93e-9882-5351-a841-fe8cb1a91b0d | note | FREQUENCY: Once for each type of panels
02cb1273-a16e-5b6c-b66a-0074d4469ebc | note | – – – – – – – – – – – – – – – – –
d4fb2498-432c-5a7b-a46c-a1d894512acf | note | CATEGORY: IP
176c8f73-e46a-5867-8660-ade4f9102fb5 | note | – – – – – – – – – – – – – – – – –
e7687614-7455-504f-84ae-00888180af33 | note | RESPONSIBILITY: PE
def9e81f-5601-55bd-8e8f-28c8f1eca2ac | note | – – – – – – – – – – – – – – – – –
ef6eb6bd-d2fe-5837-bbd7-a84885c46d97 | note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
e3395073-b7dd-5a06-aa7d-85efb2e3eda8 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Foundation
1cd0bf17-fb3b-5968-9a63-3280672f256c | note | REFERENCE: IFC Drawings
fca44326-3fbd-5fc1-bb4b-768c05bc6e43 | note | – – – – – – – – – – – – – – – – –
c85e7209-11ad-50c1-ba1f-74191e8e275a | note | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
9710936f-c34c-5cec-a8f2-e78d7cf6d67f | note | ○ Effective friction angle: 28°
72e8b1c7-0812-5b9c-891a-0c4909ad2669 | note | ○ Effective Cohession: 5 kPa
03bdf0c0-2949-5f99-8c43-723d9538f9f9 | note | AN ARCADIS GEOTECHNICAL ENGINEER SHALL ASSESS FOUNDATION SOILS DURING CONSTRUCTION.
819f6e5f-18b9-57d6-9f7a-960c616de0db | note | Attach: Geotechnical report/Certification
b984bbac-f241-572c-ad1e-d75ffd42b773 | note | – – – – – – – – – – – – – – – – –
3cd0a9b3-9774-5bbe-a604-c94e4eb9996e | note | METHOD: Test, Document Review, Visual
2358ce99-0e53-5494-8077-24f18d094851 | note | – – – – – – – – – – – – – – – – –
42200a5e-ff5a-546a-87a0-f3155fcd33e7 | note | FREQUENCY: Each retaining Wall
ed0e892e-9244-5900-b16d-6ec475e1675a | note | – – – – – – – – – – – – – – – – –
22937a1d-aa00-543e-a7ad-45c6b77cd0e1 | note | CATEGORY: HP*
58067fed-8bdb-56e1-a45e-43cae380ebfb | note | – – – – – – – – – – – – – – – – –
fd49ae0c-3168-55de-99dc-333c4f63869c | note | RESPONSIBILITY: PE/Geotechnical Engineer
4e5e8017-c7ba-59b0-ac5a-ba2bebb997a4 | note | – – – – – – – – – – – – – – – – –
d1551015-bd06-571c-a302-bacbd82e7ccc | note | VERIFYING DOCUMENTS: This ITP, Geotechnical report
e1e62571-f1c2-576e-a333-64f58a0c73c8 | date | Date Completed:
| checkpoint | 4.2 Foundation
cab71637-022a-5978-9f35-8bbaf7ce546a | note | REFERENCE: IFC Drawings
02c78c07-64dc-5770-80fb-c97e8d0197b7 | note | – – – – – – – – – – – – – – – – –
803fe055-880b-526e-a9af-3b05f6795969 | note | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
57bfc6c2-917f-5e66-981e-b8f2bc126b47 | note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
d919ab1e-22e3-5558-8dc8-4fbb1edebd58 | note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
6e9787e1-9826-54cf-beca-25e577c14662 | note | – – – – – – – – – – – – – – – – –
46ead4dc-2e84-5f69-838f-95d658245b3a | note | METHOD: Visual
d94a1569-52bf-5519-b86d-c077f3c83b21 | note | – – – – – – – – – – – – – – – – –
9881fc5f-44e2-5748-89b1-ca4949885961 | note | FREQUENCY: Each retaining wall
e0b35445-1085-5b4e-a8dd-7101c67d4611 | note | – – – – – – – – – – – – – – – – –
f198d7d1-600c-50f1-b09f-3e0c14e80e83 | note | CATEGORY: IP
b1429708-190d-5bc4-a79e-3639ebd1767e | note | – – – – – – – – – – – – – – – – –
efb97b4a-c9bd-52d1-9281-2e23b4efc43f | note | RESPONSIBILITY: PE/Geotechnical Engineer
1fc17ef4-8e95-5603-9259-2c346495fcef | note | – – – – – – – – – – – – – – – – –
cc666beb-def9-5a93-8abb-4d550378ecb6 | note | VERIFYING DOCUMENTS: This ITP
634c9e9c-5cdd-5bf0-896c-a723fa3a0244 | date | Date Completed:
| checkpoint | 4.3 Foundation
cf5ca20e-362b-59de-8d5b-062c043c537a | note | REFERENCE: VR 204.12, VR 204.11
d865eeac-f3cb-5411-8af1-cefa68fa453d | note | – – – – – – – – – – – – – – – – –
df20ee42-3919-5e75-8740-c840aa5293cc | note | ACCEPTANCE CRITERIA: areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
b255fe5f-0b37-5e41-bd62-429c1ae782d8 | note | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
eed22e75-a5a0-5519-aa69-eb2a6a51ea17 | note | – – – – – – – – – – – – – – – – –
7147e00f-ac8f-54d6-9aa6-ff5756571eef | note | METHOD: Visual
2db224e9-f70e-5185-b77f-3921c3f5ac8c | note | – – – – – – – – – – – – – – – – –
c3d9d64e-3225-59b0-ab91-0929dae8613f | note | FREQUENCY: Each retaining Wall
833c4cbb-f4eb-5ff5-9bcf-e8543416144d | note | – – – – – – – – – – – – – – – – –
6a147e13-7724-5efe-985b-4b20cf500f0d | note | CATEGORY: HP
284c9003-363f-5349-a77b-d3b011197bf2 | note | – – – – – – – – – – – – – – – – –
51e048fb-1257-5cda-940f-ef778b4cefbb | note | RESPONSIBILITY: PE/Nominated Authority
c1bdbb93-f6e4-5a4a-943c-1b979ba418b5 | note | – – – – – – – – – – – – – – – – –
27983d05-6f91-59d0-984d-31baa131db27 | note | VERIFYING DOCUMENTS: This ITP
ceaa93fa-4660-5a3a-bf1b-366d0c5f21f5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 Levelling Pad-Survey Set out
b3ff7f4b-c8ce-5158-b0d3-8803af3db069 | note | REFERENCE: IFC Drawings VR 682.20
358fffa8-d00f-558c-a407-656ee782eb79 | note | – – – – – – – – – – – – – – – – –
1901854a-2862-553f-865e-b767b27e0f11 | note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
52782192-82c7-5d74-a227-3e6249b3e17c | note | – – – – – – – – – – – – – – – – –
14c39524-58ec-56b6-ab68-a5a9e525d2a2 | note | METHOD: Measure, Visual
22370400-034c-5874-90e6-7821ee538ba0 | note | – – – – – – – – – – – – – – – – –
5f18d70c-b60c-5044-82f7-e70611e051c3 | note | FREQUENCY: Each retaining Wall
38e10fa7-9618-57a4-b2f8-de49f761e9d5 | note | – – – – – – – – – – – – – – – – –
d06b5e84-2b0d-553c-b1ee-f1d3e649db51 | note | CATEGORY: IP
364de2d2-da30-57a3-ba31-5d7a118933da | note | – – – – – – – – – – – – – – – – –
8b7cdc3a-f0c6-5a0f-be52-a37a2cdce27d | note | RESPONSIBILITY: Surveyor, SE/PE
7ffbc1d0-cd34-5e48-b958-9d2a77b6d830 | note | – – – – – – – – – – – – – – – – –
57cd80be-ec5b-55ca-8b16-b3fdb417d07d | note | VERIFYING DOCUMENTS: This ITP
d98c2d0a-db24-5bf4-b899-e299e68db2af | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | Shape Arrays installation
09aed333-d01b-5361-aac4-c5790d399aed | note | REFERENCE: IFC Drawings MRP-087-C-ACD-DRG-10-BFD-CSF-3404
f7f0eead-5568-5c34-a281-2f645a235c83 | note | – – – – – – – – – – – – – – – – –
7c7d214b-c460-5519-b816-eb20931a0e99 | note | ACCEPTANCE CRITERIA: Shape arraye are to be installed and mainatained as specified in Design package 10 notes:
02f7e053-5c23-574a-828a-20d8005268ec | note | ○ Shape arrays shall be installed horizontally across the full width of the embarkment prior to placement of the embankment and reinforced soil structure walls, in accordance with the manufacturer's instructions. Shape arrays shall be installed nominally 5m, 25m and 50m from both the north and south abutment face.
68520ae1-249f-5060-a62a-f0e83e7c8016 | note | ○ Upload Shape array installation records.
aa392a7f-ed5b-5cd0-bf3c-6b6145fbea24 | note | – – – – – – – – – – – – – – – – –
0789003b-b5ae-587c-8c29-04803c2933e2 | note | METHOD: Visual
7f8c3861-03e8-5952-84cd-b4091220b75f | note | – – – – – – – – – – – – – – – – –
3aaf4b24-6499-5f85-8d1e-3089abb04792 | note | FREQUENCY: Each RSS Block
b7ae658b-1cd6-5b11-964c-7b0d2c3ede36 | note | – – – – – – – – – – – – – – – – –
0fd03f09-488c-539a-aea3-2ca1d802d79a | note | CATEGORY: IP
f01c55ed-9408-5d14-bb0d-adfb03f7240f | note | – – – – – – – – – – – – – – – – –
eda51fbc-2413-505d-9ba9-3d232b329616 | note | RESPONSIBILITY: SE
2b7c9de5-0341-59a1-9f87-c8a17c47b18d | note | – – – – – – – – – – – – – – – – –
3a3d31cf-a0fe-5b32-8334-36830af3d4ca | note | VERIFYING DOCUMENTS: Installation Documents
258fe6d3-73b5-5c65-ba27-b20b2eb60303 | date | Date Completed:
| checkpoint | 5.1 Form Levelling pad
e9cd0f2b-d95f-597b-bda6-c382f6961645 | note | REFERENCE: IFC Drawings
d4d4cd6a-8591-5927-ae2f-d1e9c076259b | note | – – – – – – – – – – – – – – – – –
c8cbb7a7-9ba7-5d09-a0e6-def4c8edd565 | note | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
c0d67f61-be66-5084-9e17-28fe1b68ac1a | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
04bd62ee-f76f-5fd7-adb4-0558070a2bdb | note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
0e737d70-113a-5644-af6d-cdf5fd8d2660 | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
49e167ec-89a9-55b3-8b74-5dba87e8cf4a | note | – – – – – – – – – – – – – – – – –
bc8a1bb0-d3bb-5fda-81a7-ec71d07bbe39 | note | METHOD: Measure, Visual
b960ac2f-9b1d-535e-b10a-4f8b069a637a | note | – – – – – – – – – – – – – – – – –
6271dea0-352a-59f9-a8da-e5a4165328dd | note | FREQUENCY: Each Lot
cfec660e-660e-5585-8e54-39b6a73686f4 | note | – – – – – – – – – – – – – – – – –
ffb03464-c6bc-5918-849b-4ec4ee0d884a | note | CATEGORY: IP
e9a86b8d-e110-5be1-9855-dc267715c741 | note | – – – – – – – – – – – – – – – – –
0bd4f8d6-30bd-5b3f-bfdb-12b487ea1574 | note | RESPONSIBILITY: SE/Site Supervisor
ad973360-9c63-520d-8b85-4e650f5d57e7 | note | – – – – – – – – – – – – – – – – –
4bf17680-74bc-59ed-b26d-44c513c791e3 | note | VERIFYING DOCUMENTS: This ITP
2e9570bf-fe08-57ed-964d-36ad10e6dd83 | date | Date Completed:
| checkpoint | 5.2 Leveling Pad Concrete Pour
aa727c9a-f2b7-51a4-9d79-08e75f9bf5b5 | note | REFERENCE: IFC Drawings
dd714741-6928-5197-b711-a7bd35ae95f2 | note | – – – – – – – – – – – – – – – – –
fba66a65-9c96-5b8d-9de6-850854d6a7f5 | note | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
68c70c17-9f5d-597d-81e9-eec0b929e9d2 | note | Attach: Concrete Delivery Docket
0b4471ce-25ab-5e5f-90fa-cd7ad685ad97 | note | – – – – – – – – – – – – – – – – –
37066468-de5c-5be1-85f4-e6c3a104d416 | note | METHOD: Visual
facf59e7-d364-5023-84c7-8a3766844e99 | note | – – – – – – – – – – – – – – – – –
af56a489-666d-5863-9d85-35a687aa276a | note | FREQUENCY: Each Lot
49999b10-5a40-5fc2-b020-ca0428e8c023 | note | – – – – – – – – – – – – – – – – –
4435172e-7306-5460-8cdf-b6a3938588c0 | note | CATEGORY: IP
fc5a2320-63a8-5d01-a460-89799dead79b | note | – – – – – – – – – – – – – – – – –
45414a59-ed0a-586e-809e-19c4ffa926a9 | note | RESPONSIBILITY: SE/Site Supervisor
f26f41b2-ca16-5778-ab13-36d7a4390847 | note | – – – – – – – – – – – – – – – – –
8945ab04-2ae8-507b-bae0-316d235d3655 | note | VERIFYING DOCUMENTS: Concrete Pour record
343bfad7-aa6e-502c-85ef-d8387bef0389 | date | Date Completed:
| checkpoint | 5.3 Leveling Pad Concrete Testing
594c6d8f-3da0-5870-bc9b-73ec4d35f907 | note | REFERENCE: IFC Drawings
c9ce1adc-e686-52a7-a7ef-9c25a0a2460f | note | – – – – – – – – – – – – – – – – –
3e35fbbe-5663-5ddc-a984-75d390923b34 | note | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
30d955b1-cbb6-5da6-a257-868069aac3b6 | note | Attach: Concrete test report
8a7c63b0-1195-52f6-8f88-af2fdf07b4f9 | note | – – – – – – – – – – – – – – – – –
807d0ada-8bcd-59c3-ae06-6e795d7edfd4 | note | METHOD: Document Review
554d5f7b-da28-5009-a668-c6c9d2429cce | note | – – – – – – – – – – – – – – – – –
7db57bbf-3b19-5a19-8719-ec8de02297cd | note | FREQUENCY: Each Lot
1892be49-1fbe-5bc8-9812-22663bce13ea | note | – – – – – – – – – – – – – – – – –
b1d3b9bd-a708-5926-a1ac-d2cc36e3b1ec | note | CATEGORY: IP
0fafa312-79f1-580c-925a-7a5af80c30d5 | note | – – – – – – – – – – – – – – – – –
c1dee926-404d-5a8c-a50d-08ba79627051 | note | RESPONSIBILITY: PE
abf80ebe-3b83-5157-9db5-7f64857b4a81 | note | – – – – – – – – – – – – – – – – –
2bb5c4a3-b70b-58bc-8637-89dd2a99b2ce | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
86eec4b8-7de5-5505-942d-5651d12e50a4 | date | Date Completed:
| checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
490ee8f7-4a9e-54a1-89c4-472a8f5a40ae | note | REFERENCE: IFC Drawings
52659107-caa2-5f90-b95b-f3f4a9a388b1 | note | – – – – – – – – – – – – – – – – –
8ee36dcd-536e-5d69-949d-3c7e56de3765 | note | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
76d56fd0-5895-57b4-aab4-b01530cebdfa | note | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
efa32bf9-e027-5dbb-bb4c-f9806df78e61 | note | – – – – – – – – – – – – – – – – –
0f08dff7-9707-54ac-a86b-1c5315b0bc46 | note | METHOD: Measure, Visual
3e05026d-9ac3-50f5-8978-c4b7b11c5a65 | note | – – – – – – – – – – – – – – – – –
4b1c397a-2d5f-5546-b9f8-e4586befaa6b | note | FREQUENCY: Each retaining Wall
57a66164-7580-5b5e-bbd6-c5445437490c | note | – – – – – – – – – – – – – – – – –
a64bfb34-0064-5ded-8ffd-0d66d572499f | note | CATEGORY: IP
4b647753-29dc-5dc9-bcef-212ab2ceff34 | note | – – – – – – – – – – – – – – – – –
835cc6d4-b903-5a6b-9487-3b5b08798e72 | note | RESPONSIBILITY: PE/Surveyor
665823c6-afee-52ed-a751-2612175d57d4 | note | – – – – – – – – – – – – – – – – –
52c05d7c-e0f2-5887-ba8f-cd7f0cc8cc69 | note | VERIFYING DOCUMENTS: Attach Survey Report
acb41b4b-8e58-5f90-b0ec-93b9bf1e8ee8 | date | Date Completed:
| checkpoint | 5.5 Wall Panels Installation
e365f60e-32ce-5471-9e13-345809a17a9b | note | REFERENCE: 682.17
7f477fb4-ae85-53aa-9b1b-87aa7026eb89 | note | – – – – – – – – – – – – – – – – –
69a26c47-d2a7-5ca1-b85e-60a5feef9c66 | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
1b098574-2980-5f81-bc77-fb02ed6a8ac3 | note | ○ Refer to checklist for each course of panels
6605377f-4861-582e-b8a8-694332c18ffa | note | Attach: Lot map
be072aba-27e1-56a8-b5b6-49145b645787 | note | – – – – – – – – – – – – – – – – –
e7ab7946-21dc-56c2-9832-a62864ec554f | note | METHOD: Visual Measure
53634b96-50fd-5833-a4c7-4a553db5dc61 | note | – – – – – – – – – – – – – – – – –
45459ef7-f294-5957-ae1f-248235b6b4cd | note | FREQUENCY: Each course of facing panel
76c9e556-15bf-515c-b1c4-99d69e74b281 | note | – – – – – – – – – – – – – – – – –
e13504ea-ecb0-5f9c-85c1-1212f0b443a7 | note | CATEGORY: HP*
aaecb0dc-580d-5232-858e-893f0a065a26 | note | – – – – – – – – – – – – – – – – –
e89ec47e-f6b0-5956-8dc7-fce730b342df | note | RESPONSIBILITY: PE/SE
8f074b5a-7d2b-55cd-aa32-a2634a33c158 | note | – – – – – – – – – – – – – – – – –
d17e41ee-68db-5a20-a0e2-b546d8a554a1 | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
209ad745-7ca3-5b44-9001-89cca910d271 | date | Date Completed:
| checkpoint | 5.6 Drainage-base of the Wall
da807f56-c4d4-54f0-8f70-141510e51b24 | note | REFERENCE: IFC Drawings VR 702 MRP-087-C-ACD-DRG-10-BFD-CSW-3520
d6548a8c-3f3a-54ab-8a9b-49c0d7eb4e6f | note | – – – – – – – – – – – – – – – – –
1b415726-0c45-5599-a32b-effde5260171 | note | ACCEPTANCE CRITERIA: 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps. Strop Drain to be encapsulated by Non-Woven Geotextile in accordance with DTP Section 682
92b3b951-7018-5e9d-9738-ff8df186663b | note | ○ 100mm dia. perforated subsurface longitudinal drainage (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material.
06311d75-e0cf-50c4-a6c5-b03cb64272ef | note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
2bd9f354-c94d-58fe-8719-9244a0e750b4 | note | Attach: Lot Maps
7831e8de-5992-5b64-a518-5b72c1f51c2b | note | – – – – – – – – – – – – – – – – –
7bb01222-27d0-5f04-948c-bd6f61cdc77a | note | METHOD: Visual
c82b7b84-9c15-5b2c-a401-bda893a1ae04 | note | – – – – – – – – – – – – – – – – –
b5e9931b-0d58-5c98-b484-f98c144264bc | note | FREQUENCY: Each wall
e80e5788-0d45-5eb9-b89f-720c0f565683 | note | – – – – – – – – – – – – – – – – –
c315c6a8-3a6e-5a5a-9552-6a7bf9ddefd4 | note | CATEGORY: IP
881c529d-1d5e-570d-a80f-6c5e0b1c6204 | note | – – – – – – – – – – – – – – – – –
99975a0c-ea48-535b-ad4b-d95e44fb07ef | note | RESPONSIBILITY: SE/PE
35864f5f-3dc6-5116-925a-c7f2c843e3f5 | note | – – – – – – – – – – – – – – – – –
d94c8266-1a29-5546-a86f-fdef80de015e | note | VERIFYING DOCUMENTS: This Checklist
094648ae-79b8-5e4c-a559-c6b28e95da70 | date | Date Completed:
| checkpoint | 5.7 Fill
402dfbad-a88b-5a1a-9817-117a95467f23 | note | REFERENCE: 682.16
6dc30382-2731-5314-ad92-961005dcfbe8 | note | – – – – – – – – – – – – – – – – –
46612f81-9bfd-5920-9266-a7bcc8485b35 | note | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
b11fa154-f86f-5af9-850c-968d46de8988 | note | ○ Refer to checklist for each fill layer
4946ec95-ddc9-5922-8d70-78234f05ca7c | note | Attach: Lot map
983975b1-ef46-5acf-9ce6-f51b3db6e05e | note | – – – – – – – – – – – – – – – – –
861fed06-d640-56af-aca4-98fcc408fe9b | note | METHOD: Visual, Test, Measure
85f5266e-2400-501f-9f3a-3b265aefe2e8 | note | – – – – – – – – – – – – – – – – –
d3d779dc-125e-5686-841b-114ba2103d62 | note | FREQUENCY: Each layer of fill
97415daf-8538-5a7c-99a7-be41d33888e4 | note | – – – – – – – – – – – – – – – – –
af461c11-7523-5cd8-b742-8873c4bd3010 | note | CATEGORY: HP*
82dcc5b4-f1e7-5600-ab4e-d65d067a08d6 | note | – – – – – – – – – – – – – – – – –
91502871-82e5-58a9-8fa0-6560b93eb46f | note | RESPONSIBILITY: PE/SE
22065aa6-95d1-5881-9237-ec53bfd484ee | note | – – – – – – – – – – – – – – – – –
8bb02fe7-9911-5aeb-aaf4-556bff11c760 | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
dc894ae6-bb98-55c6-a525-9946a2ec7755 | date | Date Completed:
| checkpoint | 5.8 Panel installation-Settlement monitoring
13d862c2-dfda-5aa7-80a4-980411e24608 | note | REFERENCE: IFC Drawing MRP-087-C-ACD-DRG-10-BFD-CSF-3404
3fd2a39e-4354-5699-8b39-f3a368fa6af3 | note | – – – – – – – – – – – – – – – – –
a22fde84-6cad-563f-8f3b-338c5ffd79c6 | note | ACCEPTANCE CRITERIA: III. DURING FILL PLACEMENT - ONCE PER FORTNIGHT (OTHER PANELS).
2f633cd4-c418-559b-a840-57351a7b3cf2 | note | II. DURING FILL PLACEMENT - TWICE PER WEEK (SHAPE ARRAYS AND BOTTOM ROW OF PANELS ONLY).
e66953cd-d47c-5c58-9425-9a5048c224db | note | I. AT LEAST 2 WEEKLY BASELINE READINGS PRIOR TO PLACEMENT OF FILL MATERIAL.
c9ba1343-5ba6-5f7c-ac04-6608719d3dc3 | note | ○ FREQUENCY SHOWN BELOW.
f498f227-8b5f-5994-9f44-8fd9b77b7632 | note | ○ SHAPE
0893058b-0448-558a-bcff-2e21f44c7c37 | note | – – – – – – – – – – – – – – – – –
1c887cb0-2446-58b5-b0c8-3ff129ab4c00 | note | METHOD: Survey, Measure
89a99581-1e45-59d9-a42c-7ec6fa3fbb58 | note | – – – – – – – – – – – – – – – – –
0cd05a96-cf7a-5d3d-859b-4e647a4bb943 | note | FREQUENCY: When applicable as instructed in IFC
871dcfcd-59b0-5004-af5d-08043e256f39 | note | – – – – – – – – – – – – – – – – –
eeedeb29-1cdd-59bc-a541-3f7c5118aa55 | note | CATEGORY: IP
157f5d5f-da06-55d4-a5b9-f34b42ec557c | note | – – – – – – – – – – – – – – – – –
f1185485-385e-5d28-8725-d3d884185e8e | note | RESPONSIBILITY: SE/Surveyor
5d39216d-e229-5c14-a758-b1987599d8d7 | note | – – – – – – – – – – – – – – – – –
78618526-2741-5fb0-9058-69101d74905b | note | VERIFYING DOCUMENTS: Survey Report
1509ed59-c235-57a9-802e-9e48ba00ba00 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
1b7343c8-d3fe-5f83-be6a-eae86faa2f55 | note | REFERENCE: MRPA Quality Management Plan
b582cd5b-9c9c-5092-a177-11dddb08623e | note | – – – – – – – – – – – – – – – – –
a0ce6e71-c349-5e71-bb39-b3bdf8f89e88 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
fc69a99e-4509-546a-b08d-9570471095ec | note | Attach: Survey As-built / Survey Report
723a5a1b-5c33-5846-815d-24b006465bfe | note | – – – – – – – – – – – – – – – – –
3a39c053-15ce-59b7-9fe7-2f91f8072518 | note | METHOD: Document Review
0d716859-9484-5944-af6d-1ac313ee3eca | note | – – – – – – – – – – – – – – – – –
d2073bf5-d809-5406-904c-b8aa258bb516 | note | FREQUENCY: Each element
6c741aa5-4f9b-50e4-9556-02a4bb5fa29e | note | – – – – – – – – – – – – – – – – –
1026c7bc-75f8-5650-84f3-b74945eab628 | note | CATEGORY: IP
b699f13b-e383-5643-9897-28a593aaacca | note | – – – – – – – – – – – – – – – – –
7c3c5b9e-106d-5597-a80b-0e0d3e80c67d | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
0e424186-ce79-5026-90fc-490e90971ea6 | note | – – – – – – – – – – – – – – – – –
2584b47e-6a00-5744-9663-94108da9c14e | note | VERIFYING DOCUMENTS: Survey Report
68dd6227-4f82-5034-99b6-2402c3b46ed5 | date | Date Completed:
| checkpoint | 6.2 Wall Post construction monitoring
3536d517-c783-5677-b6ac-98ea091ce583 | note | REFERENCE: VR 682.20, VR 682.21
fb2c938f-62e8-5d76-8df8-213a48ba43a0 | note | – – – – – – – – – – – – – – – – –
27392549-5838-5640-ac79-2245f841c381 | note | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
4ad081a8-bf38-5df5-b13d-ab112b69e82e | note | (a) plan position shown on the drawings, at base of wall shall not exceed 15 mm;
2192c37a-c71d-538a-a8f8-fac91c3d055b | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
466dc2ac-5997-5946-83a9-61106801562c | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
70f1e23e-c762-51e9-9139-ade2be79d1ca | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
d6debe93-0df5-55fa-8ef7-40967553d12a | note | (e) the wall level shall not deviate from the specified level by more than 20 mm;
c92cd860-583e-5578-9f25-ead5ba3a0a96 | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
5e14e213-25d0-5a9b-bce2-941092ac83f7 | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
bbd08ef9-1316-59eb-b21b-43dae8d18e1c | note | – – – – – – – – – – – – – – – – –
dfa5f473-e844-5ca6-8284-50e1ae14f268 | note | METHOD: Measure, Survey
01eb73d4-2187-5019-b2d0-84bc484dbc7f | note | – – – – – – – – – – – – – – – – –
c526a22c-5d46-5b8f-ab94-78d51e97610d | note | FREQUENCY: Each wall
bc26f7b0-38ca-5bcd-9394-7509ac7e7520 | note | – – – – – – – – – – – – – – – – –
ec634186-5755-5093-9445-e10a250c5315 | note | CATEGORY: IP
e3621675-9968-5137-8b36-ff250a8cbb94 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
bc722485-819b-5422-b3b2-d27192eab99b | note | REFERENCE: MRPA Quality Management Plan
ce0d35f5-1c27-5dd9-9766-1d9ae5972112 | note | – – – – – – – – – – – – – – – – –
b377903d-99e6-52c7-8795-6dc1e81437f6 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
65811e7c-490d-5ed0-91f5-0d80b4ce340b | note | – – – – – – – – – – – – – – – – –
a6041e01-5dce-5251-a38a-4ac4a41e7042 | note | METHOD: Document Review
7a943581-7cd9-5908-ad2c-c2af260faef1 | note | – – – – – – – – – – – – – – – – –
9047362f-1b95-5fda-83e3-9cde3f59c1d0 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8a294523-456c-5a4f-b7f0-81718f6d24c8 | note | – – – – – – – – – – – – – – – – –
5be8992b-6fad-58ec-96a9-5af062eb95df | note | CATEGORY: HP*
9ab04aee-bc67-5cb2-9562-142a2feb65ab | note | – – – – – – – – – – – – – – – – –
ccce0e01-3422-5e09-b0cf-3c3cf2a9d4c6 | note | RESPONSIBILITY: SE/PE/SPE
3d74cb57-dfa0-54df-a9f3-134224718247 | note | – – – – – – – – – – – – – – – – –
79f793a3-6feb-5b31-a21a-f53c71aa35f7 | note | VERIFYING DOCUMENTS: This ITP
e6242e43-2144-5f79-82c4-f7c9608e4982 | date | Date Completed:
| checkpoint | Final Inspection
fee15d72-c0f6-5c20-a437-0ec69f8d879a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
741ce72d-ab13-551e-8db5-7033c74375ba | textbox | Name:
2585d9bf-1a5b-524a-a151-381beaa64b0a | textbox | Position:
29a8074c-d337-5d5e-a0a5-2971cf9f59e4 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-151-STR-SSB-Shotcrete Rev 0 | itp | ITP-151-STR-SSB-Shotcrete | 0f0cb2af-52dd-46db-8956-16f038533a20
| section | Referenced Documentation
| checkpoint | Referenced Documentation
b58a43fa-499a-5f50-a996-541b6216375f | note | Document Title: ITP-151-STR-Shotcrete-SSB
5b760dbd-361e-5e00-a0eb-505445322b45 | note | ITP Description: Shotcrete-SSB
3decbe3a-d9d4-5ea5-aee8-0c7d628c2255 | note | Discipline (e.g. CIV/STR/RAIL): 151-STR
1b364ea3-68d7-5eb2-9342-b683d0cd7be6 | note | Revision Number: 0
ce55b006-c87f-5d33-8074-edf83aa187f4 | note | Revision Date: 19/04/2024
a50c4f8e-c7fb-50ee-9780-28768d18905b | note | ITP created by: Mike Freeman
a37fc78d-dd8d-52ea-b3c5-f9359c56027a | note | ITP approved for use by: Mike Freeman
7e5e99b7-b26b-56d6-8f7b-0c7c22e0c604 | note | 1.1 Non Dependent
9c1ea9d8-ec35-57e0-9c2d-669a825e0eda | note | Reference: VicRoads Section 610 June 2019
ee6e7f01-0353-544e-933e-cb204d982209 | note | 1.2 Non Dependent
89cfd349-5ccc-572e-a057-ee5ad65fcf5c | note | Reference: VicRoads Section 611 November 2018
94e28892-1391-5503-9cba-b1c67fb51bda | note | 1.3 Non Dependent
b7cd0ba1-33b3-50c7-9b53-11df51bbb7e2 | note | Reference: VicRoads Section 684 April 2019
a0fa93fe-1c1b-5c7d-82c7-14704e47f6ad | note | 1.4 Non Dependent
ca560439-0c93-5b01-93b7-66d053b31bb1 | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
9df0f71d-8046-5a00-92cb-b783d2508836 | note | REFERENCE: 684.04 (a), 684.04 (d) (i & ii), 684.05 (a) (i & ii) Table 684.051, 684.05 (b) Table 684.052, 610.07 Table 610.071
87b20736-7398-5125-ac26-29cd0d17e732 | note | – – – – – – – – – – – – – – – – –
46d3809d-1a29-5d0a-bbda-2122932cd579 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
be43c41d-f982-5697-b194-d0ff6b124912 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
9bb03520-64ef-5577-8f64-4443f8d09f25 | note | ○ Maximum drying shrinkage shall meet the values shown on table 684.052.
db39f867-2627-5a6f-9898-4d4e76938b78 | note | Where applicable, steel fibres shall:
64166414-9463-5af8-89c3-04a8c06a5d5f | note | i. be deformed
81cfab48-8931-5b9e-8327-faf429302fe8 | note | ii. have a minimum tensile strength of 800MPa
9d7ee70d-30ce-5354-bc25-722bd2c6e4b7 | note | iii. have an aspect ratio between 40 and 70
e007839e-9a49-5ec7-bb70-3789f0d70fea | note | iv. have a minimum dosage rate as per table 684.051
7d3fd1ab-160c-5f05-a713-a00d9137bc38 | textbox | Enter: Teambinder Material Approval number
e4a93f48-4ce9-5719-815f-642998044aa0 | note | – – – – – – – – – – – – – – – – –
6f4f20ce-ddd2-5231-96d1-273393a05b80 | note | METHOD: Document Review
bf6a9b96-275e-51e3-bf10-e3b7eeffc1cb | note | – – – – – – – – – – – – – – – – –
4580905d-6642-571d-980e-bd060d95b873 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
9aa5e8c9-f44b-59be-8a49-8bc1fa3aaedd | note | – – – – – – – – – – – – – – – – –
a6041449-204a-5bea-856d-7280a72c7d5b | note | CATEGORY: HP
ff69eea8-da32-58c9-8e7e-140a9675c07c | note | – – – – – – – – – – – – – – – – –
ea793249-e5f6-58b5-8717-df3ecf6c7e73 | note | RESPONSIBILITY: Nominated Authority
439dd05a-f137-562c-b256-892d08fa511e | note | – – – – – – – – – – – – – – – – –
72819043-16b6-5908-970d-cee8ada43673 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f9821b5a-ed0f-5ccd-af17-3b2848e93eb5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
6c7361d7-f267-526d-80c7-fe71812473e0 | note | REFERENCE: 684.04 (c), 611.05 (a)
bcccba9c-640c-5437-9ac2-dbd739017062 | note | – – – – – – – – – – – – – – – – –
9e3e96bd-38f9-5bc6-879f-02adf7ea3d9e | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
e30dc0c6-b040-5c75-bb05-7c6ef4202c35 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
f015e0aa-3841-5844-9110-716855b3a4a4 | textbox | Enter: Teambinder Material Approval number
faa9c760-4bff-53d1-b51c-1dded6c93d54 | note | – – – – – – – – – – – – – – – – –
cf4aab33-89ed-59b5-a10e-627cf0787f1b | note | METHOD: Document Review
33ea7257-61c9-5405-a766-f8390cd04887 | note | – – – – – – – – – – – – – – – – –
1f665e0f-83e6-52c7-8885-e1421a0956d6 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
54c92f9e-4026-521b-a2c4-a3ecdc5625ad | note | – – – – – – – – – – – – – – – – –
edc0b383-fd84-5849-a3f2-0340352dfa2b | note | CATEGORY: WP
eb102c54-4635-5cbb-979c-9fc344f1c949 | note | – – – – – – – – – – – – – – – – –
f8ae51ec-b9b9-52ea-998d-1a2208969cfa | note | RESPONSIBILITY: Nominated Authority
e30dd8ff-b32e-5be1-9f1d-076fe0b2d303 | note | – – – – – – – – – – – – – – – – –
39181bff-b650-563c-aa30-3afeca3194cb | note | VERIFYING DOCUMENTS: This ITP
a18df07c-1f9d-5bd7-9979-ce4b223d3af2 | date | Date Completed:
| checkpoint | 2.3 Galvanising (for Reinforcement)
c26fc4ad-d404-5621-92e0-c7162b97bee0 | note | REFERENCE: 684.04 (c)
b0502845-44b1-5553-a040-8008fa766284 | note | – – – – – – – – – – – – – – – – –
692a01af-eaa8-52f6-98db-09154ad2ee85 | note | ACCEPTANCE CRITERIA: All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680.
9078cf65-01cd-5582-a3c5-0768d39aaf6a | note | Attach: Galvaniser's Certificate of Compliance
392b448a-2bf8-59b5-9b92-5c768e8d8dd7 | note | – – – – – – – – – – – – – – – – –
422938a1-e7af-515d-b945-958c0a503785 | note | METHOD: Document Review
c4cca00b-d969-5467-a712-98259e7b89fe | note | – – – – – – – – – – – – – – – – –
54bd3a8b-b142-56bb-8dd1-5ad3deac4364 | note | FREQUENCY: For each reinforcement delivery from each galvaniser
ef2485db-67dd-57d0-9fb2-01d69a27b99a | note | – – – – – – – – – – – – – – – – –
36da5664-8f06-5e19-a29a-3ddaedaabe6d | note | CATEGORY: WP
1b14ad45-8804-509e-ab66-1b4ca59075c4 | note | – – – – – – – – – – – – – – – – –
be16d354-c7f2-5d6d-8c33-a99fe99e70d2 | note | RESPONSIBILITY: Nominated Authority
c4bc3b25-2917-58c6-ac7a-e4be144f59ba | note | – – – – – – – – – – – – – – – – –
ed21a64c-b5a5-536e-abd3-29c1217c646d | note | VERIFYING DOCUMENTS: This ITP
8cfb987b-15d1-58e1-9ef1-49dff6c6f11b | date | Date Completed:
| checkpoint | 2.4 Bar Chairs/Aspros Certification
94fbad4f-536c-5cd5-85ce-8ebab61c9f21 | note | REFERENCE: 610.26 (a)
6ef456d4-4424-594b-be48-009ce257ba82 | note | – – – – – – – – – – – – – – – – –
4ba9dcb1-a834-5372-ba37-8dd915463c51 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
1fc1dfd5-c750-58a6-9c48-8e32c5fa9b75 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
e727ca1f-7277-595d-b774-0c22fa3ef72e | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
34ceff72-fede-5a95-8a40-17057a7072ba | textbox | Enter: Teambinder Material Approval number
39f8d090-e63b-51aa-b019-9d9cb6fc2423 | note | – – – – – – – – – – – – – – – – –
5caa25e8-9721-5006-a294-895d391c4ff0 | note | METHOD: Document Review
3a3d806b-35c5-5119-9ad0-344619967b2b | note | – – – – – – – – – – – – – – – – –
8f0d7e97-40e0-53c2-94ef-5eb49c73a582 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
66fcbd2d-e724-5a53-82b1-774cb3b31e64 | note | – – – – – – – – – – – – – – – – –
2192a39c-194f-5756-9e72-994e50e33c6c | note | CATEGORY: WP
cda16fe6-07c6-5141-98bf-44fcd7bc232c | note | – – – – – – – – – – – – – – – – –
7aea55ed-c26a-56e8-b782-5ada61dd9397 | note | RESPONSIBILITY: Nominated Authority
7defe3b0-5880-5983-ae94-5cbfe481f643 | note | – – – – – – – – – – – – – – – – –
f79da547-33ba-570b-b7ef-760ae8b80cd0 | note | VERIFYING DOCUMENTS: This ITP
9d89de54-088c-54cc-a4ee-ba19e4a954f3 | date | Date Completed:
| checkpoint | 2.5 Evaporative Retardant
b87a7aca-7c83-575e-8fee-5d377cb7f283 | note | REFERENCE: 684.10 (b), 684.11, 610.17 (f)
79eac654-1f18-5011-acae-dcd53feb5257 | note | – – – – – – – – – – – – – – – – –
0fc65582-9f60-57be-8cd0-bb8c8d4edb3d | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
419cb2e5-4a37-5697-879b-ee9d78f21f0f | textbox | Enter: Teambinder Material Approval number
0c47913a-58dc-5098-b2b1-db6b327978b2 | note | – – – – – – – – – – – – – – – – –
ab720aa5-2612-5e7e-b686-1fedc0d849ab | note | METHOD: Document Review
7a729b26-f608-531c-a484-0ef520776956 | note | – – – – – – – – – – – – – – – – –
b5fee518-c224-5707-9dd7-4dd48467f13f | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
e13f1e0f-33e0-500c-8bfd-d756032b32df | note | – – – – – – – – – – – – – – – – –
a3500e6b-d04c-56a7-80f2-5d26e23cbbef | note | CATEGORY: WP
1351d24d-a8a7-54f5-8654-2811982d5243 | note | – – – – – – – – – – – – – – – – –
76cb9921-726f-5132-aee8-804649c04e90 | note | RESPONSIBILITY: Nominated Authority
c9115606-e21a-5dcf-9ea2-cfe265df9d79 | note | – – – – – – – – – – – – – – – – –
af3163ef-c946-5535-9ea3-aa7c72bc2ab6 | note | VERIFYING DOCUMENTS: This ITP
cb3de2ba-1b41-52a2-be5b-eb1bd510b7a4 | date | Date Completed:
| checkpoint | 2.6 Curing Compound
ae6b96b8-fa54-5e36-b942-9b908547a15d | note | REFERENCE: 684.12, 610.23 (d)
9df54dfe-8aa1-57de-a54d-5209e7bf7be3 | note | – – – – – – – – – – – – – – – – –
83f95aba-70ac-5034-81dd-f511795c6f40 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
a7ae6c71-1498-5c03-9f83-2b334cf9c0c5 | textbox | Enter: Teambinder Material Approval number
a1b3988d-9842-5df3-8c87-5cbf7c37ff38 | note | – – – – – – – – – – – – – – – – –
89ad8e0e-7c43-58ab-be47-d0ad34bf5f05 | note | METHOD: Document Review
7c63f5ce-91c2-54c3-bbe6-346190adc2a5 | note | – – – – – – – – – – – – – – – – –
82c2df8b-2c45-59eb-962e-96a5ae77ea18 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
f5dda133-75d0-52b9-9111-97ca24f8032a | note | – – – – – – – – – – – – – – – – –
37616d08-6931-55fd-94e3-25b848400ff6 | note | CATEGORY: WP
3a8fded5-8d49-5212-8442-e3726e80e842 | note | – – – – – – – – – – – – – – – – –
6fc2d2e5-0eda-5b0f-9bd1-3922f95f5675 | note | RESPONSIBILITY: Nominated Authority
963a71d7-3ea6-520a-acc7-7e32d21c7ff2 | note | – – – – – – – – – – – – – – – – –
87619553-744c-5ae2-bfcf-cf2f07d40b02 | note | VERIFYING DOCUMENTS: This ITP
424333e4-afa4-52bb-bc19-986fb8983647 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Shotcrete Work Method Statement
afe5f1a4-aaca-5f0d-92fc-88caafeb117c | note | REFERENCE: 684.07 (a), 684.07 (d) (i), 684.07 (d)
fd722161-8b63-5fa2-9f68-cfd6b4b64dd2 | note | – – – – – – – – – – – – – – – – –
4cd92e7e-60cd-5898-9eb0-c5d8663d581d | note | ACCEPTANCE CRITERIA: Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority.
fa40e011-a25d-5bd5-b0ee-8810c05b9d93 | note | ○ Any changes to the approved WMS shall be deemed a new Hold Point.
738b78d6-7469-5ea5-a38e-54298a1999d1 | textbox | Enter: Teambinder Approval number
e69eb363-bf9a-5cf4-a807-e6766e1e30b5 | note | – – – – – – – – – – – – – – – – –
08b79882-917e-5291-84a2-f348f7e14ccb | note | METHOD: Document Review
ac518f59-2de9-5136-92b5-dd682e9427fd | note | – – – – – – – – – – – – – – – – –
cdae47ed-3427-5685-8b04-a8216b56cc71 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
40433b88-b21d-5ac1-9248-e078292569d3 | note | – – – – – – – – – – – – – – – – –
421dc724-1d7c-5459-aded-7257fca2705f | note | CATEGORY: HP
3278f25c-fd93-56f3-b2e3-37870b78f32f | note | – – – – – – – – – – – – – – – – –
1630297d-cfc7-55b5-9e04-a6d150c91d28 | note | RESPONSIBILITY: Nominated Authority
c0de13c6-b194-522c-92a9-3310ed62807d | note | – – – – – – – – – – – – – – – – –
8d632451-5ee2-588a-b120-d422289109ba | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
b6344f35-9402-59ab-8526-a6ba9eaceda9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Contractor Competency
068625ce-980d-58d4-970a-d7a8f9f2252b | note | REFERENCE: 684.06, 684.07 (a), 684.07 (d)
f107c4df-ca2b-5eeb-9d44-47c12f6c7878 | note | – – – – – – – – – – – – – – – – –
955bdabc-8d12-505e-9fa3-4d2625f5fd0d | note | ACCEPTANCE CRITERIA: Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application.
0e01a23a-acb3-52d3-80cb-a21566341da6 | note | ○ Any changes to personnel shall be deemed a new Hold Point.
a3c3c695-68fb-5723-b62c-3249073cb72f | textbox | Enter: Teambinder Approval number
c89f0ca3-87df-5383-a0fd-6db46167c737 | note | – – – – – – – – – – – – – – – – –
3a1556a4-99c4-57d9-a570-4574c9aa42b0 | note | METHOD: Document Review
544afb22-6240-56d7-8465-0a09f215f463 | note | – – – – – – – – – – – – – – – – –
06bbea13-ce64-54c8-aee0-9dd9d74b66d0 | note | FREQUENCY: Once, 4 weeks prior to commencement of works and for any personnel changes
52b43fd4-d073-514e-908c-d5b576685bb2 | note | – – – – – – – – – – – – – – – – –
c61dc202-3c8e-5d82-98aa-3d4b3103cb23 | note | CATEGORY: HP
d059220b-43a0-5b12-b556-74082c2dfe93 | note | – – – – – – – – – – – – – – – – –
7eb7f6a8-0ae7-5642-ac6b-2d1eebf33594 | note | RESPONSIBILITY: Nominated Authority
c233aa54-3038-5a43-b3ee-e22e120fc19d | note | – – – – – – – – – – – – – – – – –
444646a8-98cb-5434-8d70-a85c27aac343 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
b4ca0ebb-d1c3-51a6-991d-fee0d0631174 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Test Panels
6a7350b7-8acd-55d2-9c1b-eb729731ec38 | note | REFERENCE: 684.07 (b - d), 684.07 (d) (i), 684.10 (a)
6ba5917b-6b84-5743-8ffb-11ec1cbb8e33 | note | – – – – – – – – – – – – – – – – –
b5ce5c2b-cf6c-589a-8005-7630e9b12601 | note | ACCEPTANCE CRITERIA: For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast.
409e4ec2-bc47-58cb-94a2-363c93728225 | note | – The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground.
abb80fb7-e1f9-58d7-b019-46f075db919d | note | – For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum.
16adc6bf-cb75-5e7e-b92d-971f288e6718 | note | Core samples shall be tested for:
4237ce29-8edc-5176-96e2-a9fe2ff285cb | note | ○ 1 no. 3 day compressive strength
090528d6-f73f-52b3-aebb-653a1f2fef3d | note | ○ 1 no. 7 day compressive strength
fce9f4f5-0a6a-5265-b215-cdf9b0e2d5a5 | note | ○ 2 no. 28 day compressive strength
b60c7d6f-fbb6-5ab9-9d90-3ccc29934eaf | note | ○ 2 no. VPV tests
b62547cf-5000-5169-868f-f80b56534c43 | note | ○ 2 no. visual inspection showing reinforcement encasement in concrete
d60e246d-19f6-5017-a0eb-9d8b660c62e8 | note | – Any changes to approved test panel combinations is deemed a new Hold Point.
35340154-be4d-52c0-9dc7-13825de66bee | note | – Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required.
9bfec23d-7a70-5147-8f3a-1ac2cdf9f5c8 | textbox | Enter: Teambinder Approval Number
70ad285f-0ec6-5616-80a2-44dc217433e0 | note | – – – – – – – – – – – – – – – – –
8ef80510-905b-5828-9fb8-aefc8166c504 | note | METHOD: Document Review
62af3624-a916-51a5-9331-3d7766250864 | note | – – – – – – – – – – – – – – – – –
8c868545-474f-5c65-9935-8f78e0bd1883 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment
b0a3fd47-8bcc-5628-97f2-0b58c797db3b | note | – – – – – – – – – – – – – – – – –
dd01138a-fbab-5031-afd6-8a86b938c9f8 | note | CATEGORY: HP
cd0f7c0b-a88d-56eb-9f87-7e52e854e899 | note | – – – – – – – – – – – – – – – – –
65c96565-0182-5936-9e06-0fdc1199b258 | note | RESPONSIBILITY: Nominated Authority
9dff91af-7cd0-59eb-89c1-aefc84bdb518 | note | – – – – – – – – – – – – – – – – –
9a039d52-bc72-518c-902a-36f4f798553d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
86ea054d-4834-5ad3-a527-3663b7a51e00 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Concrete Sampling and Testing Procedure
50080a53-5c72-5120-82c9-c2b6bc87c6a2 | note | REFERENCE: 684.08 (a), 610.18 (a) (v)
ad619734-e051-548c-b1ad-113807671b1e | note | – – – – – – – – – – – – – – – – –
b7e75692-9b29-5998-8d8a-e321eda133fb | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
9ffe508e-ae67-52c0-b5b5-3860ff85b02a | textbox | Enter: Teambinder Approval number
deb1eef0-6e07-5613-98f9-cc2aa5acd4c0 | note | – – – – – – – – – – – – – – – – –
59f361d1-4aad-5771-98a9-a6d9906acb4b | note | METHOD: Document Review
2e8de8ee-a59d-567a-adc0-ffe7319a8f6d | note | – – – – – – – – – – – – – – – – –
276411a9-f8bb-5bba-8847-d35d3169d056 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
1fc5d4a2-eb75-50f5-8bbc-5c5b58f9aabe | note | – – – – – – – – – – – – – – – – –
ad9593d9-8a37-591c-ba75-d4a48f6fdc1c | note | CATEGORY: HP
85aa96e9-57b0-5e4f-90ee-5b0310f66d0b | note | – – – – – – – – – – – – – – – – –
3b754ae3-e62b-52da-91a1-5e4809cefe0c | note | RESPONSIBILITY: Nominated Authority
a8b30256-dbbd-590f-a8e7-b31b22a07f64 | note | – – – – – – – – – – – – – – – – –
59f75502-839b-5b65-92f4-0904645bd9b5 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
453f3e18-6645-5df9-a9c6-eb5c42309a93 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Shotcrete Prequalification Toolbox Meeting
fbc1d2d5-1d11-57d7-b3a1-b8e18d974130 | note | REFERENCE: 684.07 (d) (ii)
8a27b34a-d4a0-5c43-831a-68e20470e9c9 | note | – – – – – – – – – – – – – – – – –
ad5ed471-913e-5c9b-98c9-edeb7897c3f3 | note | ACCEPTANCE CRITERIA: Shotcrete prequalification toolbox meeting held to discuss the quality requirements.
019b9039-fb2b-5e14-8f1f-177f1327adc0 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
bb92db1f-df28-5f02-84e5-8ef7295e1f74 | textbox | Enter: Teambinder Approval number
34dc10bf-7325-5fd6-b649-a7a2a61065b0 | note | – – – – – – – – – – – – – – – – –
6d77cbea-6ade-55c1-b051-ff824c3e2375 | note | METHOD: Document Review
5cae4618-adcb-50e0-8678-5b2714230759 | note | – – – – – – – – – – – – – – – – –
c757efd7-2b5d-557f-8d5f-9600ddf8ceda | note | FREQUENCY: Once, prior to placement of concrete
1cb6e8e6-c4bc-57a3-a0ae-bccfcfa61be8 | note | – – – – – – – – – – – – – – – – –
4dbb6e69-ea92-5976-bf4c-97ba818694ab | note | CATEGORY: HP
b4e1d1e6-62f4-530d-9875-8ac56118863e | note | – – – – – – – – – – – – – – – – –
5c28401e-d43e-5633-87e7-d0e77137e25a | note | RESPONSIBILITY: Nominated Authority
b5408dfd-9491-5abd-aa8f-e4bbdd17d702 | note | – – – – – – – – – – – – – – – – –
797f0350-cf55-5cd0-ad19-469ea5f5ffbe | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
395cebb0-c8c6-5794-abc3-5a7e02517e9d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Hot and/or Cold Weather Concreting Procedure
7cfc56b2-e161-5fa2-8239-3967bfc9e2dd | note | REFERENCE: 684.10 (b), 610.17 (a)
c228c623-fd97-54ff-81c2-64b6c8bfae6f | note | – – – – – – – – – – – – – – – – –
4867d063-c2dc-55dc-b511-5c2fc6cb708d | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
2fe21378-224e-59f1-b64d-c0a6a89e1d18 | textbox | Enter: Teambinder Approval number
989cfdf6-aa6e-55de-a647-c58a88985a59 | note | – – – – – – – – – – – – – – – – –
b25dc6a1-264e-5226-b70c-fc5b223fad51 | note | METHOD: Document Review
98f07f1d-92da-5373-8005-4c000c049dea | note | – – – – – – – – – – – – – – – – –
2dda1c3b-0d3a-578e-99c0-05ef8f2ea10a | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
5da6f983-ee26-5c26-bffc-d83eccf1871f | note | – – – – – – – – – – – – – – – – –
5bd52cf4-7706-5f22-a4da-ed874ce63c8b | note | CATEGORY: WP
cfffa956-8979-56ff-bd77-73892cf2a88d | note | – – – – – – – – – – – – – – – – –
c4244a79-b964-5b8c-8b6e-df2565ad44ec | note | RESPONSIBILITY: Nominated Authority
7fdb27e0-a733-5889-ad2f-b9fc17765205 | note | – – – – – – – – – – – – – – – – –
179e448f-c3cb-591d-9a62-be8e336b0daf | note | VERIFYING DOCUMENTS: This ITP
44029c85-d561-561a-a9b7-e6c7d7e44aa4 | date | Date Completed:
| checkpoint | 3.7 Curing Methodology (for Concrete and Grout)
5065707c-e88b-5dd4-aa19-41ddb9b94f41 | note | REFERENCE: 684.12, 610.23 (a)
32274d53-ca32-56dd-941b-801c47a6e1ab | note | – – – – – – – – – – – – – – – – –
4be075c4-3bb7-5606-b128-683e5cd229d7 | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
c45f34d5-b748-5318-96d2-760e57492ed2 | textbox | Enter: Teambinder Approval number
9efca5a8-2a0c-5215-966c-41e9b2f4bb6c | note | – – – – – – – – – – – – – – – – –
b6485254-b170-5580-a4ef-e24f027b7620 | note | METHOD: Document Review
f756c4db-a07d-54e5-a01a-28dfca96fe88 | note | – – – – – – – – – – – – – – – – –
e704e244-bd64-5302-8b0d-991f75de9cd4 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
2d43187c-e211-510d-bdad-85a1d3143ea8 | note | – – – – – – – – – – – – – – – – –
245d99c6-44ca-5a90-a030-af991c4a7a5e | note | CATEGORY: HP
bbda7962-3818-5dbb-91b7-a8488d0bd52a | note | – – – – – – – – – – – – – – – – –
fe93d5f3-a413-515e-b321-b6515608bdfd | note | RESPONSIBILITY: Nominated Authority
4dff10cb-5ba6-5029-bfc9-b9c005183f47 | note | – – – – – – – – – – – – – – – – –
7d614731-c711-5002-bcaa-0ecde2f1396a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e270b087-ac40-5e48-86a5-2cf889f4ebdd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
b3e87a10-2b94-526a-aa8a-f7c399470fc0 | note | REFERENCE: MRPA Quality Management Plan
89ea3363-18e0-5207-abee-55635cac2c35 | note | – – – – – – – – – – – – – – – – –
bb409bd6-1490-5fdb-9728-2b8707ae2bcc | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
416677a2-482d-5a00-ac49-43b92bf6d1b4 | note | – – – – – – – – – – – – – – – – –
10830ece-ea7b-550c-a53a-f6bc790c6ea4 | note | METHOD: Document Review
c56e7c5f-9904-5bc5-b562-7043bf0f8242 | note | – – – – – – – – – – – – – – – – –
75527c0e-e33c-514b-95fa-7fc944df97d2 | note | FREQUENCY: Prior to starting Works and at regular intervals
53431f26-07d7-5980-9d88-98d2d7fcc58a | note | – – – – – – – – – – – – – – – – –
e4f95e87-1cba-52d9-8202-97def824bcd6 | note | CATEGORY: HP*
47038905-8266-5fcf-ae18-2135dd0ee206 | note | – – – – – – – – – – – – – – – – –
adecdb1a-882e-5605-8bc7-2269086aa478 | note | RESPONSIBILITY: All
59d07c34-944a-50ce-a38c-83113c57e90c | note | – – – – – – – – – – – – – – – – –
d698124a-a706-5b22-aa6e-b3f3d07fc32b | note | VERIFYING DOCUMENTS: This ITP
1db64cee-05cc-53d1-9622-50c8804a75cc | date | Date Completed:
| checkpoint | 4.2 Substrate Preparation
3d4f8d79-2c33-5312-ac0d-24acefd75769 | note | REFERENCE: IFC Drawings, Shotcrete WMS, 684.09 (a - c)
d8f50cd7-37b7-5435-aae7-2e54eb177d18 | note | – – – – – – – – – – – – – – – – –
ff9b51be-ced6-5dfb-8804-cb92ee59df89 | note | ACCEPTANCE CRITERIA: Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete.
019312c6-e6e4-5b87-9356-b1bf15ca223a | note | ○ Any loose materials, oils, grease and coatings of any description shall be removed.
dfbad5ea-4a99-518c-976f-c70d3334c8a4 | note | ○ Smooth concrete substrates shall be roughened to create a construction joint.
f8f84b47-f5d1-5f55-9868-879294b5c429 | note | – – – – – – – – – – – – – – – – –
74de6d07-5112-5711-805c-db9df05697b8 | note | METHOD: Measure, Visual
4f81cb0a-8244-5341-9184-835f74b560cb | note | – – – – – – – – – – – – – – – – –
7739c733-e3cb-589a-9660-38799a78581e | note | FREQUENCY: Each lot
ef13ba74-0c8d-543e-8bbe-8fba21f0d15d | note | – – – – – – – – – – – – – – – – –
eebae0a1-7392-5899-935f-49e6b29529b1 | note | CATEGORY: IP
d550fd24-5308-5879-9cc7-3ff659a73360 | note | – – – – – – – – – – – – – – – – –
a4c0d236-466d-5f26-b94a-becea72add8f | note | RESPONSIBILITY: Foreman, SE/PE/SPE
a102c48b-2a22-5554-9c62-bff0490c0a0e | note | – – – – – – – – – – – – – – – – –
7c5441f7-51fa-526a-8a8d-a756fcc5ec98 | note | VERIFYING DOCUMENTS: This ITP
6ee0ba11-330c-56f9-abd5-73c695246b70 | date | Date Completed:
| checkpoint | 4.3 Subsurface Drainage
4abdd9dc-7f2a-58a8-875b-099738edf8bb | note | REFERENCE: IFC Drawings 684.09 (a), 702.03, 702.06, 702.07, 702.09 (f)
ce3d0ac8-d86a-5b01-8845-9542b78a639c | note | – – – – – – – – – – – – – – – – –
6f70b1a2-e6c9-54a1-ab48-798ee8598b06 | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
c58ab7ef-eaa9-5507-8a93-a2e15f76694f | note | ○ The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete.
6c5a0128-9c6b-5db7-9588-7a346e98be86 | note | ○ Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
a586126f-2bb4-5add-9b8d-3315fbb1d276 | note | – – – – – – – – – – – – – – – – –
5beab188-1969-5280-9aae-c165b520744b | note | METHOD: Measure, Visual
9d86c3b3-7bdd-5af4-8868-726823070c46 | note | – – – – – – – – – – – – – – – – –
3a1c5ae4-fa91-5d31-9cfc-fa026fd8ecb6 | note | FREQUENCY: Where applicable, each lot
fab60858-3ff2-5486-9733-dcac698bb906 | note | – – – – – – – – – – – – – – – – –
cbaee9e1-19eb-510c-af65-2a5f5634c930 | note | CATEGORY: IP
ea16be8a-3fa2-5f5a-b265-735ee1668d60 | note | – – – – – – – – – – – – – – – – –
d6146c58-e73d-544f-812e-b87de8011530 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
98943ada-07c2-5156-a80d-ff982e8a1de2 | note | – – – – – – – – – – – – – – – – –
a3e43997-9983-56d9-92b3-a60c38818807 | note | VERIFYING DOCUMENTS: This ITP
2c1c5ea8-33e4-5c04-884e-31d2a5bf1a50 | date | Date Completed:
| checkpoint | 4.4 Waterstop Seals, Compressible Seals & Isolation Joints
bf9c67f7-b3b4-5967-b2a4-2d87cc8a6aa6 | note | REFERENCE: IFC Drawings, Product TDS
9cf66ff2-50ad-5ca9-adc5-4dd94ce04e18 | note | – – – – – – – – – – – – – – – – –
bdfc100f-4c4b-5ebc-ac4e-4033ff774187 | note | ACCEPTANCE CRITERIA: Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
7b2aa106-1af8-5e8a-acd5-62210205eda3 | note | ○ Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings.
4e1de026-a134-5609-8284-583d58ab006e | note | – – – – – – – – – – – – – – – – –
288bc9a4-e0b3-5002-8733-2f17c2888279 | note | METHOD: Measure, Visual
d5f7149f-2219-5b4b-b697-b03d5a0a5bd3 | note | – – – – – – – – – – – – – – – – –
a75214ec-0320-59f4-ac97-650acbee3d26 | note | FREQUENCY: Where applicable, at each existing structural element
62dde248-8ec9-573b-b7dc-8ca0139cec96 | note | – – – – – – – – – – – – – – – – –
80b3c0dd-d186-5826-a059-f077bb194ad9 | note | CATEGORY: IP
ac2a9959-9313-58ce-8d2f-a286be4b758e | note | – – – – – – – – – – – – – – – – –
85cc7399-0bc4-5898-8822-c796ca74ecfe | note | RESPONSIBILITY: Foreman, SE/PE/SPE
e6903149-969f-5f49-ac7b-62c856c02dd3 | note | – – – – – – – – – – – – – – – – –
e7d82da7-f2d1-5ae1-8880-05aca89d384b | note | VERIFYING DOCUMENTS: This ITP
bf78f6a0-2d84-5a3c-b561-3a2c9788421a | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Reinforcement Placement
4ac6331c-ed82-5f0a-8107-61c56c2d81f8 | note | REFERENCE: IFC Drawings 684.04 (c), 684.09 (c), 611.06, 611.09, 611.10, 611.11, 611.12
c3b61017-4ee3-5e3c-ac83-fccfb81a0872 | note | – – – – – – – – – – – – – – – – –
9cef3854-9e55-5a5f-99ea-54e110125875 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
9864b2d7-7ceb-58c7-b682-19dfc32f4c05 | note | ○ Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm.
4bdd7da4-d6f2-5c11-b5c4-4f2bf147f1d1 | note | ○ Layers are spaced apart using bent reinforcement, not bar chairs.
31e1f601-c881-53d6-8053-2e06211d1e44 | note | ○ Projecting reinforcement is the correct length and location.
30be9767-338c-5457-8a5c-3d8c8c02cf48 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
413f4898-67d3-55b0-9ff2-b60c51f81e25 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
a2056456-4299-535a-9dc6-43786498a4e6 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application.
c4ac3cbc-e4ed-508a-b686-439b99b151ee | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
5887e86c-2540-536e-9957-4b505d05c860 | note | – – – – – – – – – – – – – – – – –
e9fa0aaf-3766-55bf-a704-12960a645f1f | note | METHOD: Measure, Visual
87646bc8-b8e7-5829-bdfc-8d7508fc9515 | note | – – – – – – – – – – – – – – – – –
014e1c87-0978-5ade-9ebd-e0c08fc1b3f1 | note | FREQUENCY: Each lot
b798e074-36a9-5efb-8466-39014b7017c4 | note | – – – – – – – – – – – – – – – – –
ac06655e-b678-53be-9d51-7c3654b1c2ed | note | CATEGORY: IP
b6f36953-a6e7-57dc-a2cb-7341fcecb4e8 | note | – – – – – – – – – – – – – – – – –
d0f1cde5-b5a6-5315-8222-a6e00b7ddae6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
ffe8b4d8-791c-5db6-9107-4884e1c12feb | note | – – – – – – – – – – – – – – – – –
12cc6b4e-9d38-5f44-b103-3b918fb61f57 | note | VERIFYING DOCUMENTS: This ITP
96d418b8-68da-5339-9d01-c64b3c47bc50 | date | Date Completed:
| checkpoint | 5.2 Cast-in Items
5513d90b-7747-5a07-9c44-2dd2334f5851 | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
c40b22b8-c3fe-5844-8205-73fe1abea2ba | note | – – – – – – – – – – – – – – – – –
28b51c68-af7a-5b86-ab85-0f23f327411d | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
91a01d8f-d45e-5184-83a8-d1b8fb4947fc | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
1b4534d1-92f7-5c86-8479-f899b2cf5729 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
5a18b200-46a2-5619-92f3-14bd31b16fdb | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
8caacb5b-f153-54fb-8035-a37f56e54a59 | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
25161706-75ea-5da9-acb7-61537b79cac6 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
a1488597-807d-5587-a903-3f3d3b5d2c7f | note | ii. Running dimensions of a group of the above = ±6mm
5b97b929-2367-5569-a460-8ad85025cf4d | note | iii. Ducts and conduit location = ±12mm
0a884b8e-e1b9-5e03-a3c1-6d0332ae65fa | note | iv. Diameter of ducts and conduits = ±3mm
f2980443-55cc-5ea9-b0e8-3344bfa53332 | note | – – – – – – – – – – – – – – – – –
41a50191-f332-5bbe-9eb0-1318b110a7b8 | note | METHOD: Measure, Visual
c13e2588-80af-57ff-ba55-fb4901512bc4 | note | – – – – – – – – – – – – – – – – –
2004649f-7eae-5051-9eff-fca231f0e117 | note | FREQUENCY: Where applicable, each element
721647df-967c-50b9-a77d-bbe31cba787c | note | – – – – – – – – – – – – – – – – –
5d79473f-1b07-5f64-acf7-eb11aa45b161 | note | CATEGORY: IP
4b6083f2-66b6-5310-b396-20f55572c321 | note | – – – – – – – – – – – – – – – – –
34037a69-5327-50d1-90ce-e57f55568fbe | note | RESPONSIBILITY: Foreman, SE/PE/SPE
4047cb0c-7909-5856-b433-fdadc39e88a2 | note | – – – – – – – – – – – – – – – – –
2b497c3b-b4f8-5a24-905e-9c8d42448663 | note | VERIFYING DOCUMENTS: This ITP
0be0c936-d70a-59eb-ab4f-c00480fbd3cb | date | Date Completed:
| checkpoint | 5.3 Pre-pour Inspection
d4176b23-89be-5a6d-90b1-a460333df9ea | note | REFERENCE: IFC Drawings, Bonded Anchors ITP 684.10 (b)
bf31c5f8-53ba-56c5-a0c2-541f85c76a06 | note | – – – – – – – – – – – – – – – – –
0fcdf0bf-d1e9-5ed7-8df7-d83ade9c8f35 | note | ACCEPTANCE CRITERIA: All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete.
4da1fb46-d36b-5b1c-8469-0b1011ebed3d | note | ○ Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings.
d25d5909-074c-5e73-9f40-c2aef3660bc0 | note | – – – – – – – – – – – – – – – – –
0ca8db37-0aa6-5b36-bd30-3d88b14548a8 | note | METHOD: Measure, Visual
4c8348a5-82c9-5b36-80c0-407925146cdb | note | – – – – – – – – – – – – – – – – –
862e4927-05d8-5a90-81e8-4ee3ccdc7545 | note | FREQUENCY: Each lot
56cb202e-c711-58fd-b31b-acd54ea61867 | note | – – – – – – – – – – – – – – – – –
9da65e91-728c-51af-936d-f230ef85762d | note | CATEGORY: HP
89fd5992-a968-5933-94fe-787cc8c8eab9 | note | – – – – – – – – – – – – – – – – –
c721f071-2652-514f-8ca1-9fec50663725 | note | RESPONSIBILITY: Nominated Authority
a6b02a8d-789f-521a-a2f7-40e72b3337dd | note | – – – – – – – – – – – – – – – – –
16acc145-68c5-5044-8140-756250b90415 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
305be4f2-d681-5427-9a9b-ac04f57f76fb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Weather Conditions & Evaporation Limits
c17ed9a1-17d7-5db5-aee0-64132eee04c2 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 684.10 (b), 610.17, 610.17 (a) & (e) Table 610.171
5ff2c03b-7e01-57b1-b728-2ae186cc5753 | note | – – – – – – – – – – – – – – – – –
5e313ce8-0030-5739-8190-253971f65e46 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
5461e051-c765-52fe-958e-6e2752572c23 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8a6f4fcd-7659-5882-b5fd-0379bfef6600 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
d659eb7e-1794-5dbe-a183-99d98006bca2 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
12aed29c-4ae1-5364-8c4d-1d5511ab0e68 | note | Record: Required information on the Concrete Pour Record.
6db7a8db-b6a2-50f1-9c4d-e63f67f47247 | note | – – – – – – – – – – – – – – – – –
959dd4d3-efbc-5eb8-8139-6946b650f15e | note | METHOD: Measure, Visual
df2aa1a2-1951-52f2-9b8b-1b516c01556f | note | – – – – – – – – – – – – – – – – –
d6771eea-4f36-5813-8ff1-84bd90045591 | note | FREQUENCY: Each lot
4c87dcfd-8240-5d17-b0a9-8ae78e1c5bff | note | – – – – – – – – – – – – – – – – –
0116a619-54b8-569d-b1f3-7c1c7bfde3b7 | note | CATEGORY: IP
e9bd898d-b09b-52bd-944e-74f918682159 | note | – – – – – – – – – – – – – – – – –
bd512b81-63de-54a4-b8e0-dbe401989f7e | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fb0661a7-6888-5e06-b640-4cc67b9569cb | note | – – – – – – – – – – – – – – – – –
e4014dfb-6ead-5a85-986f-249ab7c9f680 | note | VERIFYING DOCUMENTS: This ITP
c568262e-ed38-5081-b7b7-020e976b4747 | date | Date Completed:
| checkpoint | 5.5 Concrete Testing - Sampling Frequency
a936dba7-93b8-598b-84ec-3b156c85d4c8 | note | REFERENCE: Site Sampling & Testing Procedure 684.08 (a), RC 377.01, 610.16 (b)
a8e3ee37-adf0-5dca-a59c-e59673d41b8b | note | – – – – – – – – – – – – – – – – –
f6603bc9-450d-52ef-a755-4fcec920c26c | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
2a0bcc9d-4880-5f12-8ac0-503ce9c8c3a7 | note | ○ 0m³ to 10m³ = 1 sample
fb3cda54-8b1b-51ed-b02a-7ad865692179 | note | ○ 10m³ to 25m³ = 2 samples
35a9156b-3bb4-5612-8edb-9cde62d4367e | note | ○ 25m³ to 50m³ = 3 samples
3e0264c3-b809-59f6-a11e-ffc6cf4ec359 | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
5ff78e78-144b-5f69-85d0-4a3a4bd7ea45 | note | – For each additional 50m³ and additional sample shall be taken.
e8a011c1-ea28-5334-ac71-436cb92e9e21 | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
c53b1d93-39ec-5052-bee1-631114a122ce | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
62a3770b-e74d-536e-819f-97596f04f2bd | note | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
fcaa2e3e-724b-55f9-9d9d-8d7b6b73d1a4 | note | Record: Required information on the Concrete Pour Record.
80fba312-e78e-510a-9f06-db46c7a8f897 | note | – – – – – – – – – – – – – – – – –
6bc11daa-892f-5fa5-b96c-401f5b1da1db | note | METHOD: Test
4958b72b-8ba9-50b4-a3fc-eb0a748f848f | note | – – – – – – – – – – – – – – – – –
917b06d4-8a67-5a02-9822-77cd1c88a638 | note | FREQUENCY: Each lot
fe6f315b-55e3-525a-856d-c4042575a973 | note | – – – – – – – – – – – – – – – – –
d4780ade-7cbc-54c4-aa7c-06399cb1f25b | note | CATEGORY: IP
13ddd55d-970d-57eb-a778-583b0195b117 | note | – – – – – – – – – – – – – – – – –
c6da7c91-4f25-5f01-b989-ff9561c3270c | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
04cae994-70e5-5e09-ab25-750e812ba524 | note | – – – – – – – – – – – – – – – – –
46a7aa76-c167-56c7-b3ee-b5712c659b32 | note | VERIFYING DOCUMENTS: This ITP
54dae2c4-dfce-57c9-aae7-a682b79cf53c | date | Date Completed:
| checkpoint | 5.6 Concrete Testing - Slump
5da4be55-24a5-50ec-b697-12807bc1ee78 | note | REFERENCE: 684.08 (a), 610.16 (c)
a0b0c74e-ff0a-597d-b108-16c67266f716 | note | – – – – – – – – – – – – – – – – –
836807dd-1592-5a1a-b025-c4fb000e01ad | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
032eb7ff-c3aa-54b2-b73f-36039f80015b | note | ○ <60mm = ±10mm
816c0664-0313-5629-922b-ae0acc4fa54f | note | ○ ≥60mm to ≤80mm = ±15mm
a28a8bc5-98f4-528a-bc73-c5d074ee3da7 | note | ○ >80mm to ≤110mm = ±20mm
9fecc294-5206-5727-a5ba-c83a1dcc2895 | note | ○ >110mm to ≤150mm = ±30mm
7e36bb3d-7197-5e3f-b967-d2f86f72c3f2 | note | ○ >150mm = ±40mm
f653c9c3-97dc-5248-9759-499bcdda6a58 | note | Record: Required information on the Concrete Pour Record.
0efd11dd-2529-596e-814d-4016cfd40eef | note | – – – – – – – – – – – – – – – – –
69c8923e-e1d5-55b5-b676-48ee96099d18 | note | METHOD: Test
61696456-4567-5401-a98f-263c0322392a | note | – – – – – – – – – – – – – – – – –
da114f82-cb94-5f82-bbb1-d518aa341edf | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
01172c0b-761d-5122-b891-2803d15083da | note | – – – – – – – – – – – – – – – – –
fa26cbb9-b8d0-5f80-9d1b-9110d646bcac | note | CATEGORY: IP
0029f9a0-7e7e-5cde-a0d9-2d915be335c7 | note | – – – – – – – – – – – – – – – – –
e0d66d5b-8291-5fb4-86a4-be397ebb4835 | note | RESPONSIBILITY: Concrete Tester
5c922122-5e0a-5c1b-9240-cf7f8dd64a36 | note | – – – – – – – – – – – – – – – – –
d168c838-eebd-54fc-9944-6c5b25f56ab3 | note | VERIFYING DOCUMENTS: This ITP
beaa273c-6ea4-5bf5-8b3d-ab38762a2736 | date | Date Completed:
| checkpoint | 5.7 Concrete Testing - Compressive Strength Cylinders
d0ba5579-e5ea-53a8-842c-65d91f16674c | note | REFERENCE: Site Sampling & Testing Procedure
9ecbbfa7-9c52-5131-a82f-5ebff888678b | note | – – – – – – – – – – – – – – – – –
7b9d6f3c-ffc5-5fb9-8a30-cfd2f3549976 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
06bb274b-6dc8-58d1-9a1a-596d19de00af | note | Record: Required information on the Concrete Pour Record.
2892189a-5ed3-50da-b762-9a40c0510b31 | note | – – – – – – – – – – – – – – – – –
e7d5553e-bdf6-53d6-bfc7-c90282f4692d | note | METHOD: Test
2ec36d3f-1699-5555-9b6a-37de2496471b | note | – – – – – – – – – – – – – – – – –
9f30742a-c413-54f4-8df5-e47f9b000088 | note | FREQUENCY: Each sample
ac6045d4-55f5-5d75-ac55-d53f9c502b69 | note | – – – – – – – – – – – – – – – – –
2c5c8d92-ccac-58d3-b5ab-7e8d9aca3064 | note | CATEGORY: IP
b7381c66-f9e5-5155-a988-0af959d633ae | note | – – – – – – – – – – – – – – – – –
3255988e-b505-5393-8a87-29496eec97a2 | note | RESPONSIBILITY: Concrete Tester
378bc96b-ec40-54f5-83c3-cbf956025996 | note | – – – – – – – – – – – – – – – – –
f30682a6-cd2d-5fdf-83e0-8df586a97af8 | note | VERIFYING DOCUMENTS: This ITP
6ddb4569-0dd5-5984-a1d2-b9c4bee4b882 | date | Date Completed:
| checkpoint | 5.8 Supply & Discharge Rates
02a56564-8168-5631-821f-f3b1bd809e0c | note | REFERENCE: 684.05 (c), 610.13 (a) & (f)
d37a6a04-53dc-59cb-a445-de101dfb899b | note | – – – – – – – – – – – – – – – – –
01b7a59e-60a3-599b-8091-383801e5d94c | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
520d18ee-2bf1-51f8-8ebd-11f6dd2bbefa | note | ○ No water is to be added once discharge commences.
c129a668-27ad-5302-b6f4-3159fa8ca1fc | note | ○ Maximum time between batching trucks is 25 minutes.
948240b7-3c83-5671-ab0b-0b0842420811 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
17ba5c87-cc51-5b66-ae17-25faf438a3c4 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
b61d95a0-1b46-5a80-9530-1690b7fca015 | note | Record: Required information on the Concrete Pour Record.
53dbc419-1d0b-59b3-af65-202b4ac7980f | note | – – – – – – – – – – – – – – – – –
739761b4-7cb3-5c35-a878-447fe8a0653e | note | METHOD: Measure, Visual
ad45acd5-1c2d-5aca-a572-e74d0d0c958a | note | – – – – – – – – – – – – – – – – –
5efaf0fd-e4d4-5831-9456-6438f638363a | note | FREQUENCY: Each load
1a394d2a-6aa3-5918-9b2f-7035155ab7eb | note | – – – – – – – – – – – – – – – – –
b012832f-4cb9-5121-878a-6105e9f4000f | note | CATEGORY: IP
af66aa6c-6c89-5a47-b46c-2dd074ee9981 | note | – – – – – – – – – – – – – – – – –
175c9487-e500-5620-b406-39c22f3b1c8f | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8c99bb8a-c628-55ba-a8fd-5ff38543e83c | note | – – – – – – – – – – – – – – – – –
83594105-d613-527a-b0bc-66daae3621ce | note | VERIFYING DOCUMENTS: This ITP
c719d80a-1d5d-550b-90bd-04ca0ec167aa | date | Date Completed:
| checkpoint | 5.9 Application Process
ca1da848-fb53-5b7c-99b1-a07288c9bd35 | note | REFERENCE: Shotcrete Work Method Statement 684.10 (b), 684.13, 610.18 (a) & (b)
64b0a043-d158-5be1-84ca-a13fc22b84f5 | note | – – – – – – – – – – – – – – – – –
d6b21ae5-54f1-5267-a402-a776f859318d | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
d88b9e3c-e027-5426-9937-9593c17f728f | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
56f0cfdb-16cb-53c2-8cd9-a9199bafbe13 | note | ○ Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness.
a4e48138-2749-5c5f-91df-55a4b5301c86 | note | ○ The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement.
6689a182-2cac-507d-bdb0-fe5da421aa52 | note | ○ For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown.
cc98b33f-acc4-5890-9269-8410fb522280 | note | ○ Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm.
8ba50113-82f7-5c16-a0cd-3d225cc0f0c3 | note | ○ Concrete shall not be sprayed through more than one layer of reinforcement in one application.
3ee7e510-f0cb-508f-8390-fc5272fa448b | note | ○ Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds.
91389199-66f0-5a01-a376-d90e15783b03 | note | ○ The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer.
280f8149-d715-5b76-ad50-864543201bbd | note | Record: Required information on the Concrete Pour Record.
7a5eb97f-7e47-5678-9f22-7167e2b2fc62 | note | Attach: Concrete Pour Record
ee060396-6c11-506f-8bd4-1dc4d5a630cc | note | Attach: Concrete Dockets
fb4a990c-5e75-52e4-bbcf-dd1256c77990 | note | – – – – – – – – – – – – – – – – –
1cbb3cd6-9eeb-5db8-87cf-277a3cd457cd | note | METHOD: Visual
61f4804d-c08e-52e3-b741-ffbd1614d0bf | note | – – – – – – – – – – – – – – – – –
4c61d068-4d77-5b6d-963c-14ea43f4894b | note | FREQUENCY: Each load
b1342a29-d08c-5de4-8bcd-ccfd4765d95d | note | – – – – – – – – – – – – – – – – –
7cb14d15-a218-5f61-af86-6a86657470c7 | note | CATEGORY: SP
5ad38243-9c82-5451-8f21-0dd18bdb1c31 | note | – – – – – – – – – – – – – – – – –
97b7ff97-8837-57a5-a606-9edab17d92e5 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c09883eb-d4fb-5b9e-8a92-0ab190898a6e | note | – – – – – – – – – – – – – – – – –
2cb911bd-d2fe-50f8-819c-31ac7ee15ac6 | note | VERIFYING DOCUMENTS:
a960fb11-fcb3-51d6-a2bb-3a53056fc412 | date | Date Completed:
| checkpoint | 5.10 Surface Finishes
445243de-df21-5141-817d-7887e92d6de4 | note | REFERENCE: IFC Drawings 684.11, 684.14, 610.31, 610.20
30e026a9-c608-53cb-8a26-fd67a1155960 | note | – – – – – – – – – – – – – – – – –
5c1d17b3-a809-5a37-8f0b-5a7fdf85dec5 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
31eae22e-475f-508e-8877-6470e9b29693 | note | ○ Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking.
e8347923-d1b7-5755-8700-277ebb857ee5 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
7bc7f37f-70a0-5ac0-a559-c9ca1f0d9263 | note | – – – – – – – – – – – – – – – – –
6824382b-5afb-57cc-a54b-234be098755c | note | METHOD: Visual
be728479-6789-5693-879f-912535daff1e | note | – – – – – – – – – – – – – – – – –
7f5d2af2-c6bb-5235-a1e6-403786e2d54b | note | FREQUENCY: Each element
b3d465c4-6e78-582f-9679-16047f8cadf1 | note | – – – – – – – – – – – – – – – – –
dda030f4-53b2-524f-9a41-1543ac6a7330 | note | CATEGORY: IP
597582a1-fffe-5d54-a071-6e439349be29 | note | – – – – – – – – – – – – – – – – –
9e273683-fce1-538e-b38b-82fab97ece70 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
efb71991-105b-5b2c-965d-387888a063df | note | – – – – – – – – – – – – – – – – –
f8cc2fcb-367d-56f8-8d67-a6ad2402f656 | note | VERIFYING DOCUMENTS: This ITP
d6e17a52-d284-5f96-adf1-252e34b5b6d9 | date | Date Completed:
| checkpoint | 5.11 Curing
c36e12b3-8a15-5a97-a9f9-3898126da1b2 | note | REFERENCE: Curing Methodology 684.10 (b), 610.23 Table 610.231
6651571f-5cf4-5065-ad00-7020d19a9d04 | note | – – – – – – – – – – – – – – – – –
cf1a66ec-3952-5861-8f0f-e5ddc2eef344 | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
f7b63601-ab23-5b9b-b0e8-838d52105afc | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
71d1c437-130c-5346-8cbf-323334f632de | note | – – – – – – – – – – – – – – – – –
fa54faa8-d356-51e9-a3b0-ce9812280fe1 | note | METHOD: Visual
326926f2-5d42-5489-8cc2-7e78b23d51c3 | note | – – – – – – – – – – – – – – – – –
e35d4816-2081-5ffa-bde4-261e39a542b6 | note | FREQUENCY: Each lot
c8b53a8f-35f4-5abf-931d-cdfdfe71a7f3 | note | – – – – – – – – – – – – – – – – –
c5b46fdc-425c-5de7-8c45-124ad3d18ba0 | note | CATEGORY: SP
7e0e4804-32b9-502b-9cc9-c930a291ebd6 | note | – – – – – – – – – – – – – – – – –
a5fef641-10e4-5bfb-9adb-32c3fd53905f | note | RESPONSIBILITY: Foreman, SE/PE/SPE
da38b0a5-56d0-518e-a2a9-d16cfa26cd8d | note | – – – – – – – – – – – – – – – – –
fac596c3-6bd1-5484-8c69-f59e01ab8860 | note | VERIFYING DOCUMENTS: This ITP
29588fef-8022-5839-b9e9-7bf35850a924 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Concrete Testing - Core Sample Frequency
24c4f9d1-2707-586f-9bfd-633ffa3a9ea3 | note | REFERENCE: Site Sampling & Testing Procedure 684.04 (d) Table 684.041, 610.16 (b)
6a8aceb8-8b0f-5707-9fe9-d0ac80af14ad | note | – – – – – – – – – – – – – – – – –
53668e60-29cd-57a6-a0fa-9aeb49dba3d3 | note | ACCEPTANCE CRITERIA: 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
fb882b14-09a1-525d-9ccc-bef6bc17e9e5 | note | ○ 0m³ to 25m³ = 1 sample
9b04b934-dc4a-58be-ad2a-a43b8d0513ea | note | ○ 25m³ to 50m³ = 2 samples
47715760-7933-5cc6-ab29-8e1019f8ab29 | note | – For each additional 50m³ an additional sample shall be taken.
d4e697cb-2499-5dd6-b16e-ba046c60ebeb | note | – Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
b2eba7a9-3d73-55bf-8536-4dbf2b981b6a | note | Core samples shall be tested for:
63e4440c-8c7c-59f8-9ee2-2435c248c761 | note | ○ 1 no. 7 day compressive strength
6ef14fc9-f363-5e8b-b215-f9fd53d183fb | note | ○ 2 no. 28 day compressive strength
0d701025-e4ad-5fa7-b180-447f3d30573d | note | ○ 2 no. VPV tests
00747d17-4fbf-53cd-8f38-b8b00ea35271 | note | Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works
087be043-e582-58ad-93bf-427c981e5941 | note | See:
07c31104-bbbe-59b6-949f-719fa1299b58 | note | ○ MRP-MRPA-GNC-XCN-0096
61c0660f-bdb2-5448-b540-77d977f74ba4 | note | ○ E-mail from D.o.T 7.06.2021
b9d4f185-0906-5006-afed-4d3c8773d3ff | note | – – – – – – – – – – – – – – – – –
9ae8ef78-966b-5d97-9086-a6f175d41cd7 | note | METHOD: Test
7e5b056c-e8c6-5e30-b9ad-f2a9242f2502 | note | – – – – – – – – – – – – – – – – –
b560ac78-f813-5089-be84-80ceba01cca8 | note | FREQUENCY: Each lot
2e9a6690-74bc-5947-ab6e-f2f7327e9235 | note | – – – – – – – – – – – – – – – – –
eac0f01f-fd2c-54f6-b8c4-c4ddd1d1d816 | note | CATEGORY: IP
4bb77af0-7cd4-57d0-a786-e17eb96b26f3 | note | – – – – – – – – – – – – – – – – –
9f7cf537-f8d8-525e-87c7-fee1a0808aad | note | RESPONSIBILITY: Foreman, SE/PE/SPE
be599154-24b0-546d-be6e-8b82c0d7f4ac | note | – – – – – – – – – – – – – – – – –
3b6893eb-3f0d-51ce-89e8-39f500595c0a | note | VERIFYING DOCUMENTS: This ITP
7b53787a-789e-525d-ab2b-e6c435b1df0b | date | Date Completed:
| checkpoint | 6.2 Compressive Strength & VPV Test Results
35ddc551-0b27-568c-aba4-dfde52b8b3e1 | note | REFERENCE: IFC Drawings 684.08 (e) (i - iii) Table 610.051, Table 610.061, 610.16 (g)
00e28513-ceb2-5f3e-85bd-9e19223aa261 | note | – – – – – – – – – – – – – – – – –
e63df0b4-555d-5e52-9269-590742f721c5 | note | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
6a8bf5c7-10d1-54ed-bfc1-4afad6928805 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
bb8afcae-d127-56fd-a5ab-a51ac9f704c6 | note | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
31589206-e010-5356-b6c3-88c5b1ba09b9 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
99b814ec-b444-535e-aa5a-21bf7cd5e9d0 | note | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
523f5e24-b6c1-5e10-8db7-da1ff9d890c7 | note | Attach: Compressive Strength Test Results
308a0b50-3f64-5e3a-bd19-28193047e092 | note | Attach: Core Sample Compressive Strength Test Results
fbe493f2-5d2f-54c0-8a8c-ff52e78266ff | note | – – – – – – – – – – – – – – – – –
7f605aff-5cc5-5ed5-9ec1-18d8631833f5 | note | METHOD: Document Review
a0f8ab2b-6dcf-5df5-8959-767fa1b307c5 | note | – – – – – – – – – – – – – – – – –
0a25376b-0070-5f44-8844-330691e34fdc | note | FREQUENCY: Each cylinder and core sample
e338d642-7800-5041-bed7-0bc77cb17704 | note | – – – – – – – – – – – – – – – – –
61833915-650f-514f-aa49-ecb5239ba1a0 | note | CATEGORY: IP
cbc59c88-4a88-5189-9a87-8e6d12bbe6ea | note | – – – – – – – – – – – – – – – – –
d49d2cd9-a502-5776-a92a-523365ccedf4 | note | RESPONSIBILITY: SE/PE/SPE
ae569fab-4fa0-55cc-b0e9-d49f36115717 | note | – – – – – – – – – – – – – – – – –
d27c5264-9f28-5b9e-83f0-a5e0f09e8fc4 | note | VERIFYING DOCUMENTS: This ITP
210be3ea-65a7-54c7-98e2-917f9be1f9d8 | date | Date Completed:
| checkpoint | 6.3 Surface Inspection
06960ae1-8b04-55a3-b647-9bd329348265 | note | REFERENCE: IFC Drawings 684.08 (b), 684.15, 684.16, 610.31 (a) - (n), 610.32, 610.24
c1131f21-6175-5c78-a38d-44dbb3803ec2 | note | – – – – – – – – – – – – – – – – –
53744354-cd9d-5919-9283-77e84dfcf4c2 | note | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
c16fa879-ef15-545c-931c-ce5e5e7de681 | note | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
4eb9e20d-2c4a-5a54-9f69-3a1dbdfb6018 | note | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
0d094c1c-2ed3-5ba4-b059-464cab22558a | note | ○ No cracks greater than 0.2mm (exposure classification B1)
0ccf6d38-5216-5511-9a5d-01ed50902453 | note | ○ If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair.
14ebab71-50cd-5595-8a80-ff36bc2b3523 | note | – – – – – – – – – – – – – – – – –
b3af13dd-684b-5bae-a5fc-31365e7e9ae3 | note | METHOD: Visual, Measure
f63e661b-219c-5f18-a805-6cdba816f2cb | note | – – – – – – – – – – – – – – – – –
18288cd4-4cda-5c2e-965b-5841a041de7f | note | FREQUENCY: Each element
0e0ab124-067b-5a15-b10f-d7756edc6ac3 | note | – – – – – – – – – – – – – – – – –
b3cad2ac-5fdc-5754-8aac-ec865fb08ccb | note | CATEGORY: IP
fcb1ca40-b800-5d8b-b46c-ea921c5519c0 | note | – – – – – – – – – – – – – – – – –
a9ebb14c-900c-593f-b5a2-d854b70061d5 | note | RESPONSIBILITY: SE/PE/SPE
2b1e9147-5124-5120-86d4-516d0592cc3b | note | – – – – – – – – – – – – – – – – –
3dacdbed-6c1d-5d52-80fc-cd3f752d338d | note | VERIFYING DOCUMENTS: This ITP and/or Structural Concrete Crack Repair ITP
40a0bacc-75d6-55d6-aa9f-020eb769cb49 | date | Date Completed:
| checkpoint | 6.4 Fibre Wash-out Test Results
9ac25a4c-94e0-569b-8a27-42581ec26f55 | note | REFERENCE: 684.08 (c)
36c37f22-64d3-5439-8dba-7a3392bb5cc2 | note | – – – – – – – – – – – – – – – – –
6f26b33a-d975-5331-b418-b775764b8a9b | note | ACCEPTANCE CRITERIA: Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate.
ac9f6aca-fee9-50ac-a4f7-00c9c8018f7d | note | Attach: Fibre Wash-out Test Results
7421480d-f926-5781-9254-879ac8faa377 | note | – – – – – – – – – – – – – – – – –
34cc081c-c719-5619-9d5d-1067f86129a2 | note | METHOD: Document Review
d6c3310c-1de2-5441-9f27-0eb56d850e9a | note | – – – – – – – – – – – – – – – – –
82509180-c7b8-58b2-9bdf-ff3891c5843c | note | FREQUENCY: Where applicable, each test
cb6a145d-4f8a-59d5-9a1d-912251070d0f | note | – – – – – – – – – – – – – – – – –
3aa9c63e-2955-5f6d-bab5-6fe0eaa2c6f1 | note | CATEGORY: IP
d1e48a51-b41d-59f0-9f7d-b67a36fdde5d | note | – – – – – – – – – – – – – – – – –
61ba2f7a-f619-5dea-a258-637607bc31cd | note | RESPONSIBILITY: SE/PE/SPE
6cbdf6f9-7a77-5322-a0ec-dca8e2e6f38c | note | – – – – – – – – – – – – – – – – –
1f3c914e-d2f3-5487-9fed-cd7d896fbfea | note | VERIFYING DOCUMENTS: This ITP
e242fb32-e762-5c61-93a5-5db6f6f679c5 | date | Date Completed:
| checkpoint | 6.5 As-built Survey
d5464442-9ab1-563b-bc5c-1ba4db3e9bb5 | note | REFERENCE: IFC Drawings 684.13, 610.47 Table 610.472
014cb766-aa0f-523a-8561-e4aaa0d12186 | note | – – – – – – – – – – – – – – – – –
b0343076-88a1-5994-a57e-555c9ff9c5a9 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
436fc4e5-a1dc-5b29-8450-6e037c3eeec1 | note | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
44ce43f3-5d64-52cf-873e-2cc442cd6339 | note | Attach: Survey As-builts / Survey Report
d2808bf0-5858-5218-be34-cd24e5a66230 | note | – – – – – – – – – – – – – – – – –
d8db774f-9a72-5905-84e5-8f523fcd6bfc | note | METHOD: Document Review
f2397620-1ef6-5cd7-9fbb-7cb63203dff6 | note | – – – – – – – – – – – – – – – – –
f32140de-5b2a-5c67-b2e5-419133b3b8a3 | note | FREQUENCY: Each element
d00395b0-b649-59ea-a995-ecee1be668c9 | note | – – – – – – – – – – – – – – – – –
4acf36cc-2422-5f16-a5eb-d36837e7c735 | note | CATEGORY: IP
e54ed46d-b511-5bfc-96b7-ce3d4538b67a | note | – – – – – – – – – – – – – – – – –
c70b3878-8a6f-5890-bce4-9b8b15ad9ad6 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
74136cab-b1f7-5ac9-a7e3-d9785f8a7877 | note | – – – – – – – – – – – – – – – – –
bbe92c4f-dc75-5227-abfa-a5191e83cced | note | VERIFYING DOCUMENTS: This ITP
00c0753f-ffa4-5106-8680-ac06ae126d34 | date | Date Completed:
| checkpoint | 6.6 Non-conformance Report (NCR) Closure
853c6ba2-6060-5043-a1c0-0078a659b4ff | note | REFERENCE: MRPA Quality Management Plan
827b4977-193c-5b39-8969-fb749127fcea | note | – – – – – – – – – – – – – – – – –
8d26db77-0385-5de1-96c7-c471b8012c80 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
c2dd510f-667b-52d2-91dd-1c0e5a8bb64e | note | – – – – – – – – – – – – – – – – –
a2182702-deba-58a8-8130-7245fec25c94 | note | METHOD: Document Review
94f0347a-a1bd-57a8-85e2-7d1bcbd539c0 | note | – – – – – – – – – – – – – – – – –
244bf96c-90ed-58d2-a30f-170e1d311b4f | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
0c4e13b8-0128-576c-90b4-5edf8121e8f4 | note | – – – – – – – – – – – – – – – – –
e78e2425-a260-5a96-b61d-d02bf0777ed9 | note | CATEGORY: HP*
a8183012-ac07-5dd1-8b40-e98b55f29dd8 | note | – – – – – – – – – – – – – – – – –
53d12d7d-4e7d-5d4b-b7f2-bbe9a999201b | note | RESPONSIBILITY: SE/PE/SPE
d4888eca-e2b1-51e2-a4ad-7ab62864a9e3 | note | – – – – – – – – – – – – – – – – –
ea0d7d6a-bce0-5aed-8775-a3c7293f1e00 | note | VERIFYING DOCUMENTS: This ITP
e16bcbd4-58b8-55c3-a282-a78a76ff1422 | date | Date Completed:
| checkpoint | Final Inspection
127da40c-333e-5c09-bc85-34e1e9b94ff1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8ee6a6d0-0092-5082-858c-11deed5ffdf2 | textbox | Name:
b7f24529-373d-548a-9cea-794315aac08d | textbox | Position:
f8d2b640-fdd9-5fdf-bd8a-171649069132 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-152-STR-SSB-Post and Panel Retaining Walls-Precast Panels installation Rev 0 | itp | ITP-152-STR-SSB-Post and Panel Retaining Walls-Precast Panels installation | 14bdf1a4-8aee-45d8-ac00-9640fd869f25
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7f1117b7-9488-537c-949d-42a0c67835fd | note | Document Title: ITP-152-STR-SSB-Post and Panel Retaining Walls-Precast Panels installation
7ca312f4-4d31-5731-92f5-d2532c567771 | note | ITP Description: SSB-Post and Panel Retaining Walls-Precast Panels installation
a98d2e5c-fccc-5bfd-8b52-e2a44fc3ae7b | note | Discipline (e.g. CIV/STR/RAIL): 152-STR
07ea460b-c676-5ec7-b188-1112168966d3 | note | Revision Number: 0
52a06cae-0b0e-5d7d-9929-73a0ecbeb28e | note | Revision Date: 28/05/2024
08d36b53-7c56-5a26-b536-61a3f7006444 | note | ITP created by: VM
ca27422f-a627-52dd-b4e5-e222a273aa8e | note | ITP approved for use by: VM
a091b4f5-41e5-56e0-bd7e-5d038077863c | note | 1.1 Non Dependent
032de5ca-de07-593c-8ff6-23d9a0ffec34 | note | Reference: VicRoads Section 610
b989a085-fc7e-5850-833f-2a51b46dcc80 | note | 1.2 Non Dependent
0d8f60a3-cb8f-59fc-b3c1-38be767cfed6 | note | Reference: VicRoads Section 610
e96d44f8-ded0-5257-abe6-dd50b2c5304a | note | 1.3 Non Dependent
34f520b7-4102-537a-9e61-4b7f5194bbc6 | note | Reference: VicRoads Section 620
e817e80f-191b-5bf8-8a2f-6b359cb6b887 | note | 1.4 Non Dependent
32fa05f1-82c9-52ca-bcd6-18bac13582e2 | note | Reference: VicRoads Section 606
| section | Preliminaries-Materials
| checkpoint | 2.1 Precast Elements
f8fceb9c-391d-53e7-a8c9-116b89576a52 | note | REFERENCE: IFC Drawings
bcb46119-3376-578a-a3da-20261d52b739 | note | ○ 610.46 (a), Table 610.463
d3781bcd-89e7-529f-a823-8d1d25828f6b | note | ○ 610.47 (a), Table 610.473
8614033b-b61e-50f6-bdcd-6d2e428f2b65 | note | – – – – – – – – – – – – – – – – –
a9dd347e-6418-5862-aa23-4ee26ffefa84 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
76f0aa4d-c194-5798-83e5-3740d9716c2d | note | i. Certificate of Compliance / Birth Certificate
bd34a95a-21f4-5f55-9fdd-5be33546fef1 | note | ii. Compressive strength test results
64f1d727-f19f-562e-afb7-efc11d53679c | note | iii. Precast Lifting Design
5b86c78d-1512-5c76-90f6-ae0b0e01264d | note | iv. Pre-pour check sheet / ITP
e9387cd1-0e1a-5d69-968b-80aa7f93541c | note | v. Post-pour check sheet / ITP
f0502836-aecf-53ce-a5c6-46b499ad0322 | note | vi. Covermeter check record
5ab8230c-8b35-5f03-9e39-978ea9cf080f | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473
7ff67e6b-db87-5b24-8510-4691d2eb34e8 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
02aaa6bd-a2e3-51b8-bacd-12eebc112446 | note | – – – – – – – – – – – – – – – – –
b40b2b27-8083-5068-aaac-02eebcfa4e54 | note | METHOD: Document Review
4b41003c-412e-5b90-b98c-3fe0c84408c0 | note | – – – – – – – – – – – – – – – – –
cb15044a-2146-5482-8bbb-61ce22043f49 | note | FREQUENCY: Each element
93afb201-4e6d-5da2-bc0e-887603afd582 | note | – – – – – – – – – – – – – – – – –
e8991c81-fa44-519f-a33a-44ccb82f7f9d | note | CATEGORY: IP
b2484b2b-931d-5e42-af03-482c0630e338 | note | – – – – – – – – – – – – – – – – –
f26ba7cc-8b65-58a0-ac63-e2c04b87fb6d | note | RESPONSIBILITY: PE/SE/SPE
3592b6e4-65bc-5e8f-a63d-2cbded0036e8 | note | – – – – – – – – – – – – – – – – –
3177b0c9-8bb6-54cf-bf50-be6e60cb14be | note | VERIFYING DOCUMENTS: This ITP
2f2b2f37-0c03-5ff6-9a56-719d7fe69922 | date | Date Completed:
| checkpoint | 2.2 Grout
a7f45192-0ca4-533b-acfc-56c63f014284 | note | REFERENCE: MRPA Quality Management Plan
7a12ad7c-fb70-57c5-8db9-ba0d1f26ddf4 | note | – – – – – – – – – – – – – – – – –
c875b805-6e4c-5885-82f7-c2ddcca86ba2 | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
33be374e-bdf8-525f-b712-0d1134019857 | textbox | Enter: Teambinder Material Approval number
7e191095-9b32-554b-8dbb-3245da405d3d | note | – – – – – – – – – – – – – – – – –
3cd7c34e-8562-5e71-8f4c-9e90e4c9e1d3 | note | METHOD: Document Review
542d21c8-d1d0-5f42-97ac-dbe0f74e9b9e | note | – – – – – – – – – – – – – – – – –
faeb0bd5-459a-5e6a-9ab0-f337aa00b796 | note | FREQUENCY: Once, for each product
eb163c50-aaf2-5775-b5ab-0e51b80db52b | note | – – – – – – – – – – – – – – – – –
3187a42b-ac94-5152-a7ce-37b6e184b563 | note | CATEGORY: HP
7a81574b-e515-58d4-9273-d7f42706115f | note | – – – – – – – – – – – – – – – – –
6a81b3f4-cd56-5479-929f-e534cc0fa0b8 | note | RESPONSIBILITY: Nominated Authority
71e8aad5-f0c5-5e22-a70f-4c2a9f8603c1 | note | – – – – – – – – – – – – – – – – –
7694a20d-e1fc-53fe-bfe6-7074eac11d5e | note | VERIFYING DOCUMENTS: This ITP
f5858511-1025-5687-91c2-58395bca5597 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Procedures
| checkpoint | 3.2 Materials Inspection Checklist
8a36e5d1-81cf-58f0-b9d3-fbec44e0ed6e | note | REFERENCE: 620.06, 620.07, MRPA Quality Management Plan
01e7f825-9bb2-5738-9741-2057ab13d865 | note | – – – – – – – – – – – – – – – – –
905ce09c-6afb-5457-9ddc-e8bfff232f11 | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
cc888891-c7b5-5105-b000-8385fbb2ba35 | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
fe9e74d1-fb89-5db7-9372-8d32bc655cc9 | note | ○ Elements shall have unique identification and orientation marked (if applicable).
4365b2d0-a9b2-584f-9d4e-81a6bf87c26d | note | Complete: Materials Inspection Checklist in ConQA
8422725e-91e9-58bf-9780-83e5b3046043 | note | – – – – – – – – – – – – – – – – –
dec2d2b4-c393-528a-9bd2-aca51da799ae | note | METHOD: Measure, Visual
0a62e32b-0c3e-5c58-8ec5-60e384025aed | note | – – – – – – – – – – – – – – – – –
ab68210f-97bc-5fa4-872e-be035c9bd051 | note | FREQUENCY: Each element
7903dba7-8142-59af-881e-cc580e00f76d | note | – – – – – – – – – – – – – – – – –
0025045b-92ef-5669-ba58-e4b58425681d | note | CATEGORY: IP
6216c3b0-920c-59ea-aec4-9f8e12aacd58 | note | – – – – – – – – – – – – – – – – –
a53476bc-41c5-5a7a-ac3d-8bf3918f561e | note | RESPONSIBILITY: SE/PE/SPE
31bbde85-65fc-50cd-90a5-473821582bf9 | note | – – – – – – – – – – – – – – – – –
6472f4c6-4dc6-53c0-9181-9230930894cb | note | VERIFYING DOCUMENTS: This ITP
4cd419dc-5dfd-5fc1-8629-7dcd9966eb7e | date | Date Completed:
| section | Pre-installation Activities
| checkpoint | 4.1 Survey Set-out
b5a926b6-829c-5e00-9919-aa51321349cf | note | REFERENCE: IFC Drawings VR 606.08
df4cbe4f-c865-57ba-b303-649d1618101c | note | – – – – – – – – – – – – – – – – –
ef96ab39-06df-52b7-ada3-02ebe6fd91e7 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
dc2fde2f-6ed8-586f-9707-8aabe260d4e5 | note | ○ Survey Activities to ensure bearing plates are in correct level
424b276f-77f9-5698-b2f0-60eda3f7f698 | note | ○ Where steel posts are cast in to the concrete, ensure that these are within tolerance.
201eeccf-0348-53c6-ac4f-2d1d1375d741 | note | – – – – – – – – – – – – – – – – –
52eeb44c-07e0-5efe-b885-d0a574de7cc7 | note | METHOD: Measure, Visual
b1eaa14a-ea33-516f-9f7e-306f12eda94b | note | – – – – – – – – – – – – – – – – –
2e321caf-0d03-573e-9526-b13e8798960e | note | FREQUENCY: Each element
d2a409d6-90ca-5278-9891-536ae76ea8a4 | note | – – – – – – – – – – – – – – – – –
2c4eded4-6c08-54cf-8c73-8a189ab9349a | note | CATEGORY: IP
4915b35f-de80-53c8-8561-9ed8cd2c0f3d | note | – – – – – – – – – – – – – – – – –
2f9cd9d9-d0b6-5d48-abe6-95168a521bc1 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
c86dfb4d-5067-59da-b16d-10c52f81b782 | note | – – – – – – – – – – – – – – – – –
8a0e2c88-256a-5764-8ced-ea0a8f44e1ac | note | VERIFYING DOCUMENTS: This ITP
534fbece-15af-5714-a0be-d32ef0bfb634 | date | Date Completed:
| section | Installation Activities
| checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
abb9691e-171b-5911-9188-ee559597e7f5 | note | REFERENCE: IFC Drawings
3baa3221-d083-5753-bc27-45d19fbb4d2a | note | – – – – – – – – – – – – – – – – –
03737df3-deda-51f8-8582-62e5c93bddad | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
0030b1ec-3ecb-5e05-8300-79192bcd9a9b | note | Gap between the panels and top of piles shall accommodate for the grout depth as specified in IFC Drawing
b32a3b6c-d21f-52a4-ba1b-bafe3fd28a9c | note | – – – – – – – – – – – – – – – – –
f8765ff0-eb5d-58ac-89c4-f6d5cf430946 | note | METHOD: Measure, Visual
91778ec5-09f8-5e37-9bd7-2327958ac2db | note | – – – – – – – – – – – – – – – – –
4a03a6a8-1548-5b9e-bf94-0b41be5b54a8 | note | FREQUENCY: Where applicable, each installation location
14a70d7f-f88d-5a1b-8b58-a53bc17c4012 | note | – – – – – – – – – – – – – – – – –
16586918-2656-5769-b06c-fa932edfbd59 | note | CATEGORY: IP
116b1145-b4b8-52c8-9efd-9225ed210bdb | note | – – – – – – – – – – – – – – – – –
3df66f06-7083-5006-b7f1-b549c9e1027c | note | RESPONSIBILITY: Surveyor, SE/PE
bdfe7e79-cbda-56c4-8b94-0d9cd6fd3424 | note | – – – – – – – – – – – – – – – – –
5b3679a5-bd8a-5dcd-b4de-f3e28e01b572 | note | VERIFYING DOCUMENTS: This ITP
6a36490e-16e2-5879-be99-6e1493c7eb0e | date | Date Completed:
| checkpoint | Elastomeric rubber - Face of the Panel
3145450f-d031-5916-a384-df453f2a965c | note | REFERENCE: IFC Drawing
65132e66-3eb5-53a8-a32f-09390fd7ceb4 | note | – – – – – – – – – – – – – – – – –
39523577-29a6-562c-86e4-3515361db88e | note | ACCEPTANCE CRITERIA: 15x50mm elastomeric rubber is installed to to the steel post (Epoxy adhesive)
02964c0d-d9cf-5612-af64-6074288e55e2 | note | – – – – – – – – – – – – – – – – –
91564b81-a987-5e04-9350-d736b586d6f6 | note | METHOD: Visual
d462868b-4f23-51de-8a21-eff2576fea0c | note | – – – – – – – – – – – – – – – – –
5a358d05-edeb-56e5-aff6-403091f1c5fc | note | FREQUENCY: Each Panel
f6e187c0-3355-5205-8d57-2b5f098937c0 | note | – – – – – – – – – – – – – – – – –
0e8a4b78-f0d3-5309-99f9-cdf0a620dc75 | note | CATEGORY: IP
b8f12737-8f3d-53d2-9a58-da4a7114171e | note | – – – – – – – – – – – – – – – – –
7af59dae-6fda-53fe-9d01-ac1b730c5da6 | note | RESPONSIBILITY: SE
067c938c-03a0-52c0-a967-ff1635e72fde | note | – – – – – – – – – – – – – – – – –
73f4ecbf-380d-5698-ac3d-7f7489912240 | note | VERIFYING DOCUMENTS: This ITP
99932fb3-102b-586f-adf2-f3c1fa0571f4 | date | Date Completed:
| checkpoint | 5.1 Precast Handling
2b6d9e1e-9d0f-530d-847b-48c4d29336af | note | REFERENCE: 620.07, Crane Lift Study
d62d153e-7f4f-54d4-af40-3b75c0295db4 | note | – – – – – – – – – – – – – – – – –
6f6cdf2a-128d-516f-be8a-e4eda8197295 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
28868aa1-437a-53cd-9032-d80661d6d05b | note | – – – – – – – – – – – – – – – – –
ca312d27-a8cf-5650-9dff-0b126833e2bc | note | METHOD: Visual
801bde47-a5aa-54be-b959-4b3230b2b50e | note | – – – – – – – – – – – – – – – – –
b5935b0b-cbb1-5ff5-aca9-9bf05861e24b | note | FREQUENCY: Each element
a764d6ba-f7b2-554d-8a69-1c3f669255eb | note | – – – – – – – – – – – – – – – – –
b80f528c-1f47-5405-af4a-eaef02310207 | note | CATEGORY: IP
0288ac9a-8ea1-5caa-af6d-fcc16a093b6a | note | – – – – – – – – – – – – – – – – –
0dca9abe-9619-5cc0-81f1-ca6e44de3d45 | note | RESPONSIBILITY: SE/PE
a5a3895b-9789-5e89-bce1-11111a00f91b | note | – – – – – – – – – – – – – – – – –
5649a038-141a-5c52-96f9-1cf30d97ce95 | note | VERIFYING DOCUMENTS: This ITP
d1c03314-c9ce-5ef9-b73a-9b505e413c10 | date | Date Completed:
| checkpoint | 5.2 Precast Placement
5d4d2772-3e13-5d22-add3-88e4a21f05f4 | note | REFERENCE: IFC Drawings, Temporary Works Design, 610.27
11f61aff-0706-5762-b86d-8b8987fd1872 | note | – – – – – – – – – – – – – – – – –
cb126e1a-8295-53ef-a2b4-0f6014ea623c | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings.
c2b0a396-0431-5237-bb69-15cdb247ee7b | note | ○ Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
fb4fffe4-f03f-591a-b561-e32fabca7e20 | note | ○ The nominal gap between elements is as per the IFC Drawings.
e430a79f-eaf4-5c31-acc2-0a8c9b67f3bb | note | – – – – – – – – – – – – – – – – –
c8ad7648-6f92-57aa-815b-b5b65294c966 | note | METHOD: Measure, Visual
9cf11222-2173-52f1-a814-0c63772d5725 | note | – – – – – – – – – – – – – – – – –
7cbf91eb-8d6b-5e87-b19f-ae3e4ea32473 | note | FREQUENCY: Each element
5bb3e69a-23e7-568d-afe4-5a8e1ec0a761 | note | – – – – – – – – – – – – – – – – –
413c921b-3789-5e80-997e-13325c03012b | note | CATEGORY: IP
7e4ff8f5-aef8-5834-bc20-491d1de4ab14 | note | – – – – – – – – – – – – – – – – –
b8eb1a0b-44f4-5ec3-8a37-d6be33587638 | note | RESPONSIBILITY: Surveyor, SE/PE
00a8a0ca-d69a-578c-92db-b1ffef3af7d2 | note | – – – – – – – – – – – – – – – – –
79650707-88c1-5906-9eb1-7daf87645588 | note | VERIFYING DOCUMENTS: This ITP
a7dae0df-8c55-55e0-9b52-f75acc1f88e6 | date | Date Completed:
| checkpoint | Plastic Packer - Back of the panel
5c193dff-c256-50c5-9fa2-0e216d8f4c71 | note | REFERENCE: IFC Drawings
365f7338-9435-5107-9dd1-b50f5360765c | note | – – – – – – – – – – – – – – – – –
438e2cd8-de9f-5919-b33d-14a2ce79383d | note | ACCEPTANCE CRITERIA: Continuous Plastic packer or equivalent is installed to ensure panel is firm against the face of the flange.
93674ed4-8997-524e-80c1-8c15f859b1bb | note | – – – – – – – – – – – – – – – – –
b3cb22ce-2403-5076-8f1f-f10ffd171e7a | note | METHOD: Visual
7bf41521-2803-5e8d-9526-59e6c3eb7942 | note | – – – – – – – – – – – – – – – – –
8df59170-2123-58a1-b4c6-f42883015eb6 | note | FREQUENCY: Each Panel
f9fe64e1-0215-5de8-b4a9-f14041d626fa | note | – – – – – – – – – – – – – – – – –
0c913308-f036-5e1a-bf77-d0db30339311 | note | CATEGORY: IP
e19be8ad-07ec-51b0-b842-5f0e5e784152 | note | – – – – – – – – – – – – – – – – –
3ebb8426-4b90-5c2d-ad85-4a20cdb48bcf | note | RESPONSIBILITY: SE
2ab18e4f-b5b7-5490-8983-29236b9346c1 | note | – – – – – – – – – – – – – – – – –
a8ae1000-32a3-59a1-8d8b-03d02acb5ec7 | note | VERIFYING DOCUMENTS: This ITP
d23c3e9d-2aed-5074-915e-95e5210e30b2 | date | Date Completed:
| checkpoint | 5.4 Drainage
08faaf1d-15f7-5265-a23a-77e5e69f5ef7 | note | REFERENCE: IFC Drawings
d11c5cd7-29d8-528d-be1c-e235ca2de950 | note | – – – – – – – – – – – – – – – – –
d3a992ae-53a5-5397-9415-507d4d437029 | note | ACCEPTANCE CRITERIA: Dranage shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
8b4a09a1-9f35-511e-b137-5740fc793ba3 | note | ○ Drainage is to be installed as per manufacturers instruction.
df35dfd3-e660-5efe-8de2-20cba97c15e3 | note | ○ Slotted pipe wrapped in geotextile installed to drain to the low point.
aec1a148-a0a6-599b-97b3-520b470dd84c | note | – – – – – – – – – – – – – – – – –
3912ab35-5e61-5dd2-96be-24f634d562ee | note | METHOD: Measure, Visual
9084f774-4a23-5e8e-9812-ee8ca2233ea3 | note | – – – – – – – – – – – – – – – – –
23fcad95-9b6f-54f0-8f7f-e6debf39d873 | note | FREQUENCY: Where applicable, each installation location
61b3270c-2e09-549b-a16d-be46ed61e464 | note | – – – – – – – – – – – – – – – – –
a0497f1b-0eec-58f0-9863-db02f4fd3b70 | note | CATEGORY: IP
5db639a7-81a5-53f6-a615-aaf6008b624d | note | – – – – – – – – – – – – – – – – –
bd12fac8-041e-5a1b-8c24-ec07178391de | note | RESPONSIBILITY: Foreman, SE/PE
b0198aff-ec37-58fa-86f8-1d5043c98940 | note | – – – – – – – – – – – – – – – – –
26d69a06-3cf0-58cb-95ab-c6640be680e1 | note | VERIFYING DOCUMENTS: This ITP
060c7cfb-020c-52db-8251-c70a311f586c | date | Date Completed:
| checkpoint | 5.6 Precast Traceability
3ed38ae3-65e3-568c-9d3a-a18019d8103d | note | REFERENCE: 620.09
5be9f9cc-d0d2-5b9e-a801-39cb727ae684 | note | – – – – – – – – – – – – – – – – –
d4fb93b5-dbd0-51e7-bcc6-e36b38a5223e | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
ed27b846-f5a5-5373-95a0-c2d33047877d | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
87c50930-d044-570b-9d76-f420f9b7e5df | note | ATTACH: Lot Map
e1f0fcd0-ee7e-5280-b274-0add23bfbe7e | note | – – – – – – – – – – – – – – – – –
19122881-1b4c-5c35-82cb-d6720d7ac1f1 | note | METHOD: Visual
9c2df035-a0a4-5dba-84a5-0be854d67013 | note | – – – – – – – – – – – – – – – – –
ae3e583c-4f54-55ad-97d4-e218c4a099d3 | note | FREQUENCY: Each element
9283f3b6-901d-599e-b581-39786c92eee2 | note | – – – – – – – – – – – – – – – – –
b3b5677f-f136-5c06-a315-8fc4ef5a0f03 | note | CATEGORY: IP
4ef988d2-e0da-5c7f-aed0-f27d70b3a190 | note | – – – – – – – – – – – – – – – – –
4fb2ad8c-9116-5187-870d-c7ed40451706 | note | RESPONSIBILITY: SE/PE/SPE
55bac89a-09dd-5f20-9b57-3d744baa9474 | note | – – – – – – – – – – – – – – – – –
75626d2d-0131-5764-8dba-5c8c4b130728 | note | VERIFYING DOCUMENTS: This ITP
9b52d1ef-e0c8-55b9-8b6f-ec1633a216d5 | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Joint Sealant Application
0870ee82-b3ee-5b7e-9dbb-da624f3e6203 | note | REFERENCE: IFC Drawings
d651092e-2446-53d3-a71b-7ee1d9f8d44a | note | – – – – – – – – – – – – – – – – –
475ea1e2-d16e-5e6d-95d2-87c39d8f86df | note | ACCEPTANCE CRITERIA: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
8733676e-b163-5793-89c4-02ad868c06b0 | note | – – – – – – – – – – – – – – – – –
9fd4c0ac-5b7d-58d7-be4e-7aa85e50dc63 | note | METHOD: Visual
1bcf1b34-1a81-58e4-8a57-07f744a17916 | note | – – – – – – – – – – – – – – – – –
766e6dd4-675b-53ea-83cf-6ad7a4b6ecdc | note | FREQUENCY: Where applicable, each element
c6122e0a-4d2d-5905-aa68-bb38d185b448 | note | – – – – – – – – – – – – – – – – –
e408cca8-f2c9-5c58-9045-41232cda435a | note | CATEGORY: IP
ba46892c-2463-57aa-8b6a-ba82afe9945e | note | – – – – – – – – – – – – – – – – –
4cd57f4b-0b87-5b7d-8a61-8ca3a7fc3e47 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
bb188206-364a-5144-8d08-3bb2cca6d532 | note | – – – – – – – – – – – – – – – – –
fc6534e7-6468-5fb4-a12b-c9fae8cbb392 | note | VERIFYING DOCUMENTS: This ITP
a33560f8-120e-5c77-a921-f3ea4179364c | date | Date Completed:
| checkpoint | 4.2 Bearing Shims-Packing Grout
ccd31c56-e7e5-5e10-a48f-d0bb1ba937e6 | note | REFERENCE: IFC Drawings
7290a768-c65a-5acf-b5e1-eb795af80db9 | note | – – – – – – – – – – – – – – – – –
86055f0e-b944-5c68-a222-3fe719a13c56 | note | ACCEPTANCE CRITERIA: Gap Between Panels and top of piles shall be filled with Packing Grout.
804a2cb8-d1ea-57cc-b04b-3cba740621a5 | note | ○ Packing Grout Depth shall be according to IFC Drawings
5fa864d6-0574-5ed2-ae8b-896012172ade | note | – – – – – – – – – – – – – – – – –
29b4ea24-9b44-5aab-b284-d73187c1adb5 | note | METHOD: Visual
ecc11631-dae0-56bb-9072-f1a63206ffa4 | note | – – – – – – – – – – – – – – – – –
b2d8c96b-e368-579f-8b25-5dd0ad018de2 | note | FREQUENCY: Where applicable, each installation location
1efb530d-a081-5120-9dc0-fa1e27093752 | note | – – – – – – – – – – – – – – – – –
1ee81b3a-2264-5dfc-9c6d-230fa6202f50 | note | CATEGORY: IP
683a49ba-3d98-5543-9e38-3089a74224dd | note | – – – – – – – – – – – – – – – – –
a40ee752-90fa-598f-bfdc-2887998540e3 | note | RESPONSIBILITY: Surveyor, SE/PE
fdd94a02-f5d2-5ce5-8de9-5ac6c9d81c76 | note | – – – – – – – – – – – – – – – – –
4e5af862-aa33-592a-ae37-e7a0c41ba12c | note | VERIFYING DOCUMENTS: This ITP
4f21932b-7721-5d05-b709-e53591660641 | date | Date Completed:
| checkpoint | 6.4 As-built Survey
4a159c20-4daf-57d2-bbd2-9ab2b1993540 | note | REFERENCE: IFC Drawings
6335b59b-dd65-58a2-ad5d-c5ab5e21dbc3 | note | – – – – – – – – – – – – – – – – –
ac97b47f-280c-5720-bef4-597ed06a36ff | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances.
da1ad891-3d78-5cf4-b5c6-99b5b1a06f02 | note | Attach: Survey As-builts / Survey Report
12ebd170-c698-5d0f-9a56-7eb617f26b32 | note | – – – – – – – – – – – – – – – – –
c1818458-1521-531d-815f-d4c220a4d9a2 | note | METHOD: Document Review
d7468926-7a01-5db7-bf18-9bd46b4056dc | note | – – – – – – – – – – – – – – – – –
01348330-80d8-58c3-a7fd-1320fc1ff555 | note | FREQUENCY: Each element
3a387f7d-de4e-505b-851a-1b9e4fd810fd | note | – – – – – – – – – – – – – – – – –
a0f694ff-e582-5923-b0e9-3ea23086eca4 | note | CATEGORY: IP
bbf213d5-4a1e-5f93-8695-ef529263bc3b | note | – – – – – – – – – – – – – – – – –
9387d75c-bc70-5073-8a17-a3383fc2a563 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
0aac3267-4f42-56b9-b934-85b6538aa5aa | note | – – – – – – – – – – – – – – – – –
5725224a-787f-53b0-8c01-92f02b8ac4b6 | note | VERIFYING DOCUMENTS: This ITP
24e09988-ae6c-5481-9e96-8042f36acde6 | date | Date Completed:
| checkpoint | 6.5 Non-conformance Report (NCR) Closure
c32ccf14-2d86-591d-829c-17c46c048e52 | note | REFERENCE: MRPA Quality Management Plan
95b10081-42c5-5ca5-8345-b238c05fb864 | note | – – – – – – – – – – – – – – – – –
fb1a8efc-9404-5830-85d1-cc6e2c548ec3 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
a0da5942-81ba-55e9-bde2-c29949a2728e | note | – – – – – – – – – – – – – – – – –
dd0c31a2-cbbf-5a7e-97f8-ffc3d49e5422 | note | METHOD: Document Review
179f1aec-d8c7-5c9b-a9f7-8059f4df5e08 | note | – – – – – – – – – – – – – – – – –
5268f7f1-18ed-5fe1-8eb9-c4b08e462e1a | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
12e9f775-ca5b-5f4d-ac15-11a27a411c53 | note | – – – – – – – – – – – – – – – – –
75600c18-5c2d-530a-931f-c294aa0a0ef0 | note | CATEGORY: HP*
bbd0f478-4536-5561-a62d-07143c91ec06 | note | – – – – – – – – – – – – – – – – –
0547daf2-e443-5ddb-89e7-e8a9b5988419 | note | RESPONSIBILITY: SE/PE/SPE
4dddde72-c9ff-503c-a08b-36698954e532 | note | – – – – – – – – – – – – – – – – –
23878aa6-b60d-5a78-9830-aa145b690028 | note | VERIFYING DOCUMENTS: This ITP
73c6b6d1-66e2-548f-a0b6-beff7092190b | date | Date Completed:
| checkpoint | Final Inspection
189b2b56-17fc-5db3-9561-8abdcb2c76ec | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a9254c5d-4e99-5b70-b4c4-a0bb8df5ebb9 | textbox | Name:
dce2bd00-f652-5e02-8a14-023611c7defe | textbox | Position:
a2c85eec-1d7a-53b0-8521-bc9c889ebf49 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-153-STR-SSB-Concrete Coating Rev 0 | itp | ITP-153-STR-SSB-Concrete Coating | 510e5b50-b919-4347-ab2e-441c1105247d
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a2673a8b-fc35-50c9-aafa-ba6458fe44e0 | note | Document Title: ITP-153-STR-SSB-Concrete Coatings
b223b3d3-4ee9-58dd-a112-dffc5569e651 | note | ITP Description: SSB-Concrete Coatings
2346872e-0e0b-54b8-8dbb-214fe0a5f108 | note | Discipline (e.g. CIV/STR/RAIL): 153-STR
b62b0b25-3068-5914-b2fc-70796cec9dd1 | note | Revision Number: 0
4454e4d0-7587-5f11-9fb2-e0d5f2c8426e | note | Revision Date: 1/05/2024
9a95467f-c5dc-5207-9a3b-b81cc575c840 | note | ITP created by: Mike Freeman
1c94691a-a19c-5502-8e9f-6bfecd6800b6 | note | ITP approved for use by: Victor Mira
184094d7-5f57-5141-af0a-58b8f04235e3 | note | 1.1 Non Dependent
5941ee97-b769-5279-ba96-a5f0b5dc89da | note | Reference: VicRoads Section 685 November 2018
457e5581-c44e-5133-94a8-e8dd2a124716 | note | 1.2 Non Dependent
1caa123f-0bc7-5ebf-9711-598ae8ab1d74 | note | Reference: VicRoads Section 686 November 2018
| section | Preliminaries-Materials
| checkpoint | 2.1 Anti-graffiti System Selection
95509f3c-5aee-5c2f-9f4a-a7756cfe9bcc | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (e)
a836a56c-9ae1-57d1-9f76-73ad3447137c | note | – – – – – – – – – – – – – – – – –
607d977b-8e84-5559-a5a8-756b8e684566 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
bf53d562-f987-56ae-9715-cbf162bc6751 | note | i. be either a film-forming or a penetrant system
e1978fe7-c555-5d98-9265-5d7214918269 | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
6f5ccce5-9eb6-5ac2-a9fc-fd979919dfea | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
e2afd1be-96dc-52b0-a9e5-84295e7ec681 | note | iv. be non-yellowing, colour-fast and not subject to fading
b90c1248-8024-528b-af64-899d7117504e | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
8ffb1d21-d2d4-5fff-960f-b47614def1e5 | note | vi. application thicknesses (film-forming):
a76ce805-6087-5bc5-9c1c-352a9c18ff5d | note | ○ WFT total = 175µm min. OR
f4bb2e68-6c4b-5cb1-b704-d95a5a7ee312 | note | ○ WTF per coat = 88µm min.
89f5545e-9d7d-5be1-8f17-9cc55b742e64 | note | ○ DFT total = 100µm min.
4369a26e-90c7-5889-8cbf-52950befdf40 | note | vii. adhesion to substrate (film-forming):
0bd312e5-27cc-5294-9f19-33daa3e18246 | note | ○ 0.75MPa min.
d4244c0a-c25a-5cfb-b7b4-be2a8071b476 | note | viii. application rate (penetrants)
0b7afc0e-a04a-5617-bfde-556c3398f8b7 | note | ○ as per the minimum thickness on the manufacturer's TDS
47aa4734-43ee-5703-a284-c09e50f3a225 | textbox | Enter: Teambinder Material Approval number
6b7809b4-6c4f-56ca-985e-0957f04be31f | note | – – – – – – – – – – – – – – – – –
86839990-ef69-5ab3-916a-0240f826cd56 | note | METHOD: Document Review
742aa26f-cbac-540e-a0c8-2e930664ed49 | note | – – – – – – – – – – – – – – – – –
781a229e-87b8-5537-a6bc-87d528bc0510 | note | FREQUENCY: Once, for each coating system, 14 days prior to application
223a9a3f-3613-5ea5-8f87-db87c80de91e | note | – – – – – – – – – – – – – – – – –
0defc65f-19a7-5833-9062-859a2b6b3d4b | note | CATEGORY: HP
8744d04e-6893-5013-ab4f-a90693c9e4a0 | note | – – – – – – – – – – – – – – – – –
2dd5a0de-3264-5168-95d1-96eba2bec0f5 | note | RESPONSIBILITY: Nominated Authority
b227393b-03d8-5f00-88ec-d85e84e5e29c | note | – – – – – – – – – – – – – – – – –
ed3112c5-9727-5273-a547-11037b8cfcd4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f30adebe-651a-5faa-9469-6bde8fbaf8a5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Decorative & Anti-carbonation System Selection
912c743c-052c-5114-844e-0a56337ae8b9 | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS, 686.04, 686.05 (a) & (b) Table 686.051
1bb9af8f-d00b-5554-822f-0c53a2256e45 | note | – – – – – – – – – – – – – – – – –
bbfb9ce4-e5e9-5fe4-b013-d2fba675d242 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
18d709d4-eb1b-5c28-b519-c908001526e7 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
6931f0c3-21b0-545e-bdfe-32d10fefd182 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
ee25c631-e83d-5fe0-b92c-09d1a7583d17 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
8c18c921-b28f-5f31-8e63-8f198a69b658 | note | iv. be non-yellowing, colour-fast and not subject to fading
587e4df8-789c-59f8-8ed6-9d9e00748101 | note | v. be guaranteed to last for 10 years of outdoor exposure
f2997a82-4c7c-53f5-87cc-bec886851c6e | note | vi. application thicknesses:
d8a99468-edab-5fc9-8e24-6c9cf3475fea | note | ○ WFT per coat = enough to achieve the total DFT
404ec5a8-5604-5919-b255-de24d19e892e | note | ○ DFT total = 150µm min.
41fe288f-9254-5da5-a65c-8f0df1c63559 | note | vii. adhesion to substrate:
ae3451d2-02db-52a1-aeaa-36c8831de3bf | note | ○ 0.75MPa min.
ff0e6fd8-0c62-53f9-84ec-790d2250c0ae | note | viii. able to bridge cracks up to 0.3mm wide
ccf0ae56-114b-5d16-bcf3-064865282089 | note | ix. able to be re-coated within 24 hours
8c0da748-2ec6-5e42-a960-4ec87b0a327d | note | x. have a minimum pot life of 1 hour
08bc89f1-a260-5920-9379-808279ebc25a | note | xi. compatibility to an alkaline surface
6ec249db-05bc-5382-97c2-fb444b52405c | note | xii. equivalent air thickness >150m
df956bed-4c3a-5a53-83df-42a7fa1f9e4a | note | xiii. equivalent concrete thickness >450mm
08a28c0a-5da8-52e4-ac3c-96e546179ae9 | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
1897a424-e36b-5cda-8df1-01576c25bb81 | note | xv. Water vapour equivalent air layer <4m
84e20a3f-a198-57ec-840e-9e8c53af80c8 | note | Enter: Teambinder Material Approval number
17a4d439-8c08-5640-a59f-3fa81a115a7c | note | – – – – – – – – – – – – – – – – –
d4473971-02d6-5abb-9908-cad7425f1152 | note | METHOD: Document Review
de75356b-fbd1-5df2-9e3a-f90833e16d62 | note | – – – – – – – – – – – – – – – – –
7dc4a61d-453e-58e4-90bb-89d39b8d00fb | note | FREQUENCY: Once, for each coating system, 21 days prior to application
66f3c673-08e2-5156-b910-51951e77fc6b | note | – – – – – – – – – – – – – – – – –
7dae3b05-69f8-5c4f-9201-a4a349b51f6a | note | CATEGORY: HP
cdb84924-468b-596f-b550-2ea48a4a37ae | note | – – – – – – – – – – – – – – – – –
5cd3d650-7691-5a6e-956b-b0d07c9a88cf | note | RESPONSIBILITY: Nominated Authority
2dc50216-3f1c-5330-9061-59cecee5f7e9 | note | – – – – – – – – – – – – – – – – –
0e64b1d8-949f-56c4-aa35-68d1d51b7c2e | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
13753b8e-7e6a-5e8f-9d9a-724eceffdcd7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
beec8ade-918a-506b-a330-3399c1661e85 | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051
4a469303-9ab6-500d-9dda-f82e1d5f2ca2 | note | – – – – – – – – – – – – – – – – –
7681d75c-56a0-50db-8c0e-9b6824672110 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
5557fdfa-877a-5a02-9726-c6edc0951bd9 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
68c4f0f3-7f62-5e1f-9526-ffb2dc9107fa | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
7be5afe6-2dea-5f67-a9ab-7648b290fe4d | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
171b54d2-6709-5f52-a210-11adfaf2ebda | note | iv. be non-yellowing, colour-fast and not subject to fading
9997528f-21e0-5e1c-ba89-5e7e4f6573ab | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
7a894583-b006-5dd9-b693-9833b4a53b1f | note | vi. application thicknesses:
01efcaa7-1b9b-5fe6-850c-983cf804b1c3 | note | ○ WFT per coat = enough to achieve the total DFT
3e2ae81b-8b26-58e2-a070-7fb2e1382460 | note | ○ DFT total = 150µm min.
747eb9b9-8831-5425-a23e-86d36d0e608c | note | vii. adhesion to substrate:
87c95401-5e65-5016-b207-d4a2772145b6 | note | ○ 0.75MPa min.
754a76fe-3da8-54cd-a6df-7089a0db049f | note | viii. able to bridge cracks up to 0.3mm wide
d7bebc9b-36af-5048-b84e-ea0ca358d082 | note | ix. able to be re-coated within 24 hours
58e36c0f-b30d-5542-9793-45f7867e4c5c | note | x. have a minimum pot life of 1 hour
5099b4bf-4025-581d-b6af-d85a3848219c | note | xi. compatibility to an alkaline surface
3040170e-16b4-5add-9ee4-32d8fb4df5f5 | note | xii. equivalent air thickness >150m
4fb2e23a-4ac4-5f74-ab6b-6b99c83c9152 | note | xiii. equivalent concrete thickness >450mm
64d0c09b-1843-55c2-963b-a66cdf14f49b | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
78d4cffa-59af-506c-9d2d-b8145d523750 | note | xv. Water vapour equivalent air layer <4m
b122acef-9979-5604-aab8-cbf07c360b10 | textbox | Enter: Teambinder Material Approval number
4a1769ac-ff80-5f13-a0ad-339ded1954a4 | note | – – – – – – – – – – – – – – – – –
6556d936-a5ab-5c39-9e99-5743917d270a | note | METHOD: Document Review
98e44cbf-cc6d-5391-9996-d0cce364b5f0 | note | – – – – – – – – – – – – – – – – –
d7b7fef8-f22e-5405-b479-9956d0ae0421 | note | FREQUENCY: Once, for each coating system, 21 days prior to application
1ce65ec3-542a-51e3-9317-2945ab0c1f93 | note | – – – – – – – – – – – – – – – – –
4be87227-6b3a-5de3-beea-668d7f46feac | note | CATEGORY: HP
da070b61-e1b6-5dac-b79a-ca51a124f512 | note | – – – – – – – – – – – – – – – – –
b589efd5-8781-5085-abcd-226558ea9fa0 | note | RESPONSIBILITY: Nominated Authority
b327907a-f14d-57b0-ad5a-680517e81145 | note | – – – – – – – – – – – – – – – – –
dc64b4dd-65fa-542a-83f1-7d6382efe410 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
138e9fba-4588-558e-8316-2f4889e9b5f7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
61f637f2-5ce3-5b87-8bdd-f5f9dbd00d8a | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051, 686.05 (c) (i) & (iii)
7a96bb6d-c822-515d-ae1b-c139e6226720 | note | – – – – – – – – – – – – – – – – –
1f1a97b7-4c67-5da2-a495-f6cc8185fd8b | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
6cc71211-228a-58f7-859c-608a148d90ea | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
faa74049-20a8-5099-a819-2aa1a216a1d0 | note | ii. all coats to be compatible with each other
60cad2b9-8a7f-53c8-8557-eb275915d822 | note | Penetrants:
2d6803d4-fbce-5d31-b5e2-e177ee553cc3 | note | iii. active ingredients:
5802c75d-a6c6-56fe-8470-0886f2953915 | note | ○ Silane = at least 95%
f718d1b2-7d2e-5687-857d-df5180c4a069 | note | ○ Solid silane & silane cream = at least 80%
b02bc645-c75c-534b-90cf-05118755fb8b | note | ○ Silane-siloxane & siloxane = not specified
b7be8725-90eb-5f57-aafe-17b6e9e3dc5e | note | iv. application rates:
29a60e97-9f72-5e62-99e4-6acbde8e302f | note | ○ Silane = 2 applications of 0.3L/m² min.
0a225c0a-ac7e-5409-ace6-3e3512eee0a1 | note | ○ Solid silane & silane cream = 1 application of 0.4L/m² min.
d76b9097-4f99-5e90-bb23-b8cbd9e5a94f | note | ○ Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
61cf4a5c-f2f3-52d8-bcca-745439b0c186 | note | Film-forming coat:
4077ae14-78cc-5cb0-8449-0eb1677fcca9 | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
b7f637dd-919f-5c21-920e-a88f3db5841f | note | vi. to be water or acrylic based, solvent-free
a5c545a0-a52a-516b-85b0-a38ffbddf233 | note | vii. to be non-yellowing, colour-fast and not subject to fading
e430ab2e-31b3-5954-a1a2-f914b2305283 | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
6f4eae1f-e199-58c3-ac9b-3a3110b32ed0 | note | ix. application thicknesses:
ba31683c-14c6-5774-9495-040c7cc3bce0 | note | ○ WFT per coat = enough to achieve the total DFT
a47ca5db-1ba7-5b04-bba7-4089fe1c5d07 | note | ○ DFT total = 200µm min.
0f9210d1-3b14-5a12-a2dd-25db06a7b222 | note | x. adhesion to substrate:
6b501444-3bec-5295-8380-13a2a17499e2 | note | ○ 0.75MPa min.
df7567b4-acb1-5281-986b-fc75ed503de2 | note | xi. able to bridge cracks up to 0.3mm wide
3e8ba69d-f136-5536-a989-10bb9b29c75e | note | xii. able to be re-coated within 24 hours
d8d0971f-9cd5-5c47-99e5-37d7949df9f2 | note | xiii. have a minimum pot life of 1 hour
c6ac622b-b203-59fc-b560-b69435f50530 | note | xiv. compatibility to an alkaline surface
9cab69e9-9f64-5a1e-8123-6604687fb87d | note | xv. equivalent air thickness >150m
a4bc5bc7-0e42-54dd-a6b1-10aaa8b2d41f | note | xvi. equivalent concrete thickness >450mm
7147e4fe-fcf6-5c92-9e6e-b2d86791a327 | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
0d9d516e-5162-5819-b89c-c21411daf350 | note | xviii. Water vapour equivalent air layer <4m
a5ddb5c6-f038-5e34-8f60-c2fffd2a1aae | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
75930776-e960-504c-99f2-7a775ebb56b4 | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
04dbed72-1558-5d5e-970b-f9bbd6cea303 | textbox | Enter: Teambinder Material Approval number
13d8a373-3b82-5e86-b256-ac200be8babf | note | – – – – – – – – – – – – – – – – –
ee891446-75fb-5d0c-bfb5-8a6f6f0b112d | note | METHOD: Document Review
74bbee15-9b69-58a3-868b-83348bb079e6 | note | – – – – – – – – – – – – – – – – –
040c49b8-5aa1-5862-bc33-2e17ce599cef | note | FREQUENCY: Once, for each coating system, 21 days prior to application
be330a99-f53a-5aa3-90cc-8c0d7b47c43f | note | – – – – – – – – – – – – – – – – –
5fbfac16-fee6-5b0e-9b49-665802d80f70 | note | CATEGORY: HP
8d1b5d60-6b6b-5adc-a153-b5afc3e0246d | note | – – – – – – – – – – – – – – – – –
e1ae9fb2-39ec-59b6-b7c5-1f39f3275c26 | note | RESPONSIBILITY: Nominated Authority
e76b83af-c811-5678-b2ea-b18e8bdaea67 | note | – – – – – – – – – – – – – – – – –
0b7a12ab-804b-5798-b04c-a5de29fbfcd6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
8ef3e856-501d-53ab-befc-bcdfe791ad85 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Procedures
| checkpoint | 3.1 Work Procedures
ba12f18e-9c6b-5944-8594-376b118fe3dd | note | REFERENCE: 685.05, 686.04
28db0356-8191-5dc1-8d2a-ed500b7a9c3c | note | – – – – – – – – – – – – – – – – –
29bb2b76-2739-5261-bdd0-5172f7165b74 | note | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
9ed6fc4f-8900-5c56-9744-6c98411249b2 | textbox | Enter: Teambinder Hold Point number
15cf687a-e053-5d14-bc85-95c66db0bf32 | note | – – – – – – – – – – – – – – – – –
8c0fcd63-5534-5760-9b38-0f7fe4c95877 | note | METHOD: Document Review
5e65436f-9b90-5d01-8f90-e00c20792a57 | note | – – – – – – – – – – – – – – – – –
5b04c543-0883-50a5-ab5e-efcd22e665dc | note | FREQUENCY: Once, for each coating system, 21 days prior to application
ea427dff-0cce-5e58-927b-16fa664249ef | note | – – – – – – – – – – – – – – – – –
d0f7e176-5d5c-5799-b2b1-35fc0f5dbdb6 | note | CATEGORY: HP
6d430ad6-ef99-542b-b77b-63c666dda2c3 | note | – – – – – – – – – – – – – – – – –
2f761957-e1e9-5e86-9b3d-d8d9cf6d1539 | note | RESPONSIBILITY: Nominated Authority
33dfa5ce-2e73-5802-a4d8-0a392ab90262 | note | – – – – – – – – – – – – – – – – –
98704389-25b7-594c-949b-0f1056bc2b9a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
cd25c0d5-d5fe-52be-9739-8aa3ce48f750 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Coating Personnel & Equipment
dd0f91fc-117f-568b-804b-e575210475aa | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.16, 686.18
7610010f-92df-5251-8f30-207366d68852 | note | – – – – – – – – – – – – – – – – –
1c904d5f-db27-5ba5-a93d-466ef38462f6 | note | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
d6dac53d-1c55-5d7e-8943-5bfc51b9f337 | note | ○ Application personnel require 2 years minimum experience.
2571debd-19a4-5a3c-970c-a163d58013c4 | note | ○ The supervisor shall remain present at all times.
d186f641-c915-55ca-b007-1aacea934b77 | note | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
e4781095-8ff2-5cf4-8886-a45b58e4777b | note | – – – – – – – – – – – – – – – – –
fa69540a-7fe3-5c19-a0d4-98b72fa004c5 | note | METHOD: Document Review
4995748a-1754-5f97-bb92-bac26ec140a0 | note | – – – – – – – – – – – – – – – – –
8104c055-85bd-5a91-838c-8e6946deedea | note | FREQUENCY: Once, prior to application.
2c69c8a1-5a42-5e9b-ae8f-86044b4d897a | note | – – – – – – – – – – – – – – – – –
4df82aad-98d1-5473-bf5b-0cb8cbc49fba | note | CATEGORY: IP
0ebda2e1-d538-5176-8472-60a47625ae77 | note | – – – – – – – – – – – – – – – – –
68708fe8-1174-516b-a6f3-b955ea54fc80 | note | RESPONSIBILITY: SE/PE/SPE
c0143734-079c-5bd5-92ea-adf1868a2591 | note | – – – – – – – – – – – – – – – – –
27d9918d-1d0a-5517-8bbd-9fbb3537527a | note | VERIFYING DOCUMENTS: This ITP
1cde5c3f-ad78-536f-b31c-d3e3f140d985 | date | Date Completed:
| checkpoint | 3.3 Protection of Adjacent Works & Property
5d9fff36-d088-588b-b8fe-2f4e681991e8 | note | REFERENCE: 685.17, 686.10
3dc8d845-c789-5046-9d18-873f5ab7e75f | note | – – – – – – – – – – – – – – – – –
d9921196-f249-5733-9624-f733e12543c5 | note | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
caaff5e4-e7f7-5e42-baa9-03a2f349cb4d | note | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
9130509b-ba3f-50b3-9034-e12e55c5d840 | note | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
35d2be67-512b-5ea5-99f2-6f96778e6cf4 | note | – – – – – – – – – – – – – – – – –
9e69c358-a12c-55bb-85b3-9c5433e8c74d | note | METHOD: Visual, Document Review
df10e76e-c90e-5538-b4d6-c11f685088f8 | note | – – – – – – – – – – – – – – – – –
b3ad4109-6277-5019-b7ac-230d57d60867 | note | FREQUENCY: Where applicable, 2 days prior to application.
3a33f069-b126-5c95-832e-aec724b8193e | note | – – – – – – – – – – – – – – – – –
ca55f1dd-4622-5703-9ac4-b2f63262bff0 | note | CATEGORY: HP
22874418-4898-5fa4-b147-473bd3b25597 | note | – – – – – – – – – – – – – – – – –
10904c58-5a1d-5f57-9304-23ea23517869 | note | RESPONSIBILITY: Nominated Authority
29ac32a1-72eb-5bed-b2d8-40b80ba24539 | note | – – – – – – – – – – – – – – – – –
93c64c37-5508-5aef-8dc1-ef30e4799516 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d015f59c-d383-5ff6-96e1-0c7716eedeaf | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 Minimum Concrete Curing Period
799709de-9ea3-5fa8-be1e-10f9a5197239 | note | REFERENCE: 685.08, 686.16
172b6a33-8fe6-54c8-be55-c231ce52fe0d | note | – – – – – – – – – – – – – – – – –
51cafa55-c6d8-5a63-8c9c-c0745e39be1e | note | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
a8abf057-db39-5872-a9bb-8f0e7e002c5c | note | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
a9cd211e-5b97-5378-ab7b-623094a59005 | note | ○ Accelerated cured concrete = 14 days
4eac582d-776d-5b4d-8661-7f3ffd9b7d17 | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
edbc8d22-460c-54a5-9dc5-3a11b7fa82e5 | note | – – – – – – – – – – – – – – – – –
e2f18f6b-1bc2-51e3-98c7-356622a605ca | note | METHOD: Visual, Document Review
076313ff-b237-5292-890e-a516a5c0d6d8 | note | – – – – – – – – – – – – – – – – –
d9760de1-6fc4-515a-b1d4-24210205165a | note | FREQUENCY: Once, prior to application.
eaa7dde1-3482-5e99-9bae-202499fb71fb | note | – – – – – – – – – – – – – – – – –
1609550c-d29c-5334-a829-84edffef1db0 | note | CATEGORY: IP
6cd8c2e9-935c-5ace-9d39-69c4ab0e53fa | note | – – – – – – – – – – – – – – – – –
b2744ab8-58a1-56b8-ade3-5f66dc39c1fe | note | RESPONSIBILITY: SE/PE/SPE
80126404-7341-5e3d-89c9-27409f87e192 | note | – – – – – – – – – – – – – – – – –
3d926126-2c11-5f49-aebf-243bc4f96e99 | note | VERIFYING DOCUMENTS: This ITP
f8f5f392-18c9-55a3-b39a-b42dc0430777 | date | Date Completed:
| checkpoint | 4.2 Trial Application (or Past Performance) Inspection
001678f9-cb0f-5fdf-9efc-e4e423bd9ff1 | note | REFERENCE: 685.11, 686.13
6f8f3388-7806-5fce-bb1d-b36353418e21 | note | – – – – – – – – – – – – – – – – –
0a9c9211-2c4c-57f2-a044-56e7ddf8daee | note | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
0a59bd13-b0fb-5a27-b085-e5d8c7c0c891 | note | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
80775703-18e1-5c13-b713-61622ded5d27 | note | Attach: Inspection Photographs OR
da2b775a-312b-5d4f-8fa2-42acf6d79699 | textbox | Enter: Teambinder Hold Point number
bfce6e81-10a2-5383-8623-076c23022aa2 | note | – – – – – – – – – – – – – – – – –
53e9fbfb-7640-5223-ada0-fcb3ce7c96ea | note | METHOD: Document Review
509078a8-02e9-55d2-ac46-8866bd0c598b | note | – – – – – – – – – – – – – – – – –
68b79f99-05b6-553b-a4fb-63892a26660a | note | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
2ed03727-8277-5c51-bddf-14ae8dc1f0f3 | note | – – – – – – – – – – – – – – – – –
83bcf7df-222a-576d-bfb2-6f42ab5bff48 | note | CATEGORY: HP
1bfd4477-da4d-5b48-beeb-e995b3f5cb3f | note | – – – – – – – – – – – – – – – – –
4aa58030-d92d-5625-aad7-151e7633bea4 | note | RESPONSIBILITY: Nominated Authority
39e6ba2b-c9fa-59b7-acd3-3e8137ba58e8 | note | – – – – – – – – – – – – – – – – –
ca598a9a-911c-5e95-8ae2-bb521e62af82 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
bef1abfc-5b7c-5e0e-b794-7d6648d97718 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 Material Records
78099367-a979-548b-b658-b6668e81a82d | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.10, 685.12
985c31f9-5922-5823-9d81-aa1857247138 | note | – – – – – – – – – – – – – – – – –
f3644dc4-bfec-5a85-a48f-f8394aa63036 | note | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
872b7b90-cf64-5ccc-9008-719acfc9c7f9 | note | – the manufacturer's name & address
cf75c8e1-405c-59d8-ba54-fc6bb035231a | note | – product reference
050fcfca-1701-5fd1-8964-69ca8a7950cf | note | – batch number
921fd8de-01c1-5830-8fd5-f3aabe22405f | note | – quantity manufactured in the batch
ca940e9c-04ca-5b38-b74f-ddb7888c70c6 | note | – date of manufacture
e51eecc4-7385-50c5-87eb-9a04dc410716 | note | ○ Product beyond the manufacturer's shelf life shall not be used.
a490331e-36ea-51a2-bf12-45508552cce1 | note | ○ Each product shall be traced to final location.
05133659-9e8b-5600-9c58-5f3af6e575f0 | note | – – – – – – – – – – – – – – – – –
195db92f-7c8e-5baf-aa38-0b1f0849a4e2 | note | METHOD: Visual
5b5bae28-f905-5b0d-bade-8dd19122a432 | note | – – – – – – – – – – – – – – – – –
e51120e5-2d7a-5f2f-9061-0329d99d74b6 | note | FREQUENCY: Prior to application
3270c516-2cc5-568b-9e62-a513bc4da97e | note | – – – – – – – – – – – – – – – – –
63141df1-a95f-50fd-9e77-20a800db3721 | note | CATEGORY: IP
8bf914ee-7b9c-52f1-825e-8bedb15bf87c | note | – – – – – – – – – – – – – – – – –
3feb6a5c-eacd-5c50-9db4-343b0e975cf3 | note | RESPONSIBILITY: SE/PE/SPE
f0a0ac37-9a42-594b-9c5d-6a819292cad9 | note | – – – – – – – – – – – – – – – – –
638a4927-3ca2-5a03-a7ee-9e93521d8475 | note | VERIFYING DOCUMENTS: This ITP
4c7289e6-bec4-5c94-9419-b26ca822a583 | date | Date Completed:
| checkpoint | 4.4 Weather Conditions
2a1923c8-7810-5f04-b940-a51e0eb9a37c | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.09, 685.12 (a), 686.11, 686.14 (a) (iii)
22a98255-9f10-59d2-a067-d591a7e6bef3 | note | – – – – – – – – – – – – – – – – –
4d0631dd-a6ea-5443-bbf3-c63b45785256 | note | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
58a65a71-0736-5b53-a2af-331ea2062676 | note | i. windy conditions where spray/splatter may be generated
80d19ecc-dd1e-5244-b383-5b906c423845 | note | ii. when wind-borne debris is likely to contaminate the uncured surface
0e5abe5b-04b8-534f-864c-b54faffb6b73 | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
e7485289-9ec7-5953-8054-ebadac8ede47 | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
a9f5f853-5cbb-552f-9210-d30d8478938c | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
d8cc858e-2d1b-5aa3-a98c-0d221888e874 | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
585f7cfd-abbf-5744-8c07-841f9e96b4f0 | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
8b18a431-0ca1-5681-9de6-2d33898f427f | note | ○ Weather conditions are to be recorded.
aa04a8d4-9e8e-5cb9-a779-aaa98175b745 | note | – – – – – – – – – – – – – – – – –
94817c90-eb17-53da-81e2-3043416249ae | note | METHOD: Visual, Measure
c8547c70-6637-534b-9ad0-867a54f0e2c2 | note | – – – – – – – – – – – – – – – – –
5ccccb0d-1c92-5874-8365-5b159025eb4f | note | FREQUENCY: Prior to application and every 4 hours per shift
9d031797-8636-5970-85c4-01c0dd1d4426 | note | – – – – – – – – – – – – – – – – –
7c0f703b-c859-5f27-b56e-e7394bf699d8 | note | CATEGORY: IP
2309adb6-62a3-55ec-84b7-0f608dd426d6 | note | – – – – – – – – – – – – – – – – –
7a073671-46b3-5967-ad2d-0299c697174c | note | RESPONSIBILITY: SE/PE/SPE
21d58216-3844-54f0-97a6-dad40e0df237 | note | – – – – – – – – – – – – – – – – –
6e811cdf-0bcd-5874-81bf-cf67e70eb70e | note | VERIFYING DOCUMENTS: This ITP
5383d99f-c2dc-5d0f-85f3-62f23dde91a0 | date | Date Completed:
| checkpoint | 4.5 Surface Preparation
6cbd7899-5281-5c89-ac8e-39d5bddccf73 | note | REFERENCE: Surface Cleaner TDS, Coating System TDS 685.05, 686.06
bf4513ae-824e-5782-a6e3-1dc753644bd5 | note | – – – – – – – – – – – – – – – – –
af85e210-5a2b-5e73-822a-9c47c80d8b8b | note | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
8f81cb45-52ca-55ee-9079-afaf300ef956 | note | ○ The surface shall then be flushed with water.
88ee3d6a-1caf-54fc-a72e-0e7e467122f4 | note | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
2c077638-ada8-5bcb-85e6-7527d503eeee | note | – – – – – – – – – – – – – – – – –
61ebd095-cf78-53b2-8006-cfd316ab2377 | note | METHOD: Visual
a4db9ea5-2000-5a8e-8bc0-47be57f9611e | note | – – – – – – – – – – – – – – – – –
38dcf8f4-b2d2-5c8d-a223-001c2560bbbd | note | FREQUENCY: Once, prior to application.
334a4c46-bbfb-5934-872d-db812acbe71a | note | – – – – – – – – – – – – – – – – –
ca107e04-8df1-592c-a2fe-2c921911b8b8 | note | CATEGORY: IP
17dade0e-032f-552e-88d6-17e4794c2601 | note | – – – – – – – – – – – – – – – – –
3bc2b417-17e7-55a3-9fc0-6686be758488 | note | RESPONSIBILITY: SE/PE/SPE
600627e2-77f4-5ebc-946b-88383f05b5dc | note | – – – – – – – – – – – – – – – – –
e4cb1dbb-6b17-5ffa-b9c7-05c8187e7ed5 | note | VERIFYING DOCUMENTS: This ITP
c008557f-cb35-5eac-93e0-3bfd7b4c29f9 | date | Date Completed:
| checkpoint | 4.6 Surface Moisture Testing
91ba64d2-d71a-512f-bac1-78a07671a98a | note | REFERENCE: 685.12 (a), 686.14 (a) (iii)
125f9b05-d706-554e-829a-74b525444884 | note | – – – – – – – – – – – – – – – – –
5d6b5467-43f7-59e9-bcec-e600e598559f | note | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
d18420bd-9ff8-5b5e-a75c-7bec7c983529 | note | ○ Surface moisture conditions are to be recorded.
00577217-d922-55ea-990f-5f4a9bf61a90 | note | – – – – – – – – – – – – – – – – –
9c47e49d-d5a9-5c5e-a8bf-359cde8066cf | note | METHOD: Test
4018bb4b-d7ff-512e-b5d9-9c109316e65e | note | – – – – – – – – – – – – – – – – –
89f5eda1-3e3e-502d-a151-50ccd1fbdb15 | note | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
3d0286dc-b9f2-573b-b925-448edd574aba | note | – – – – – – – – – – – – – – – – –
3b1c02e0-278c-511c-a3a8-6cc91421d28a | note | CATEGORY: IP
90d46e62-626e-51ee-9642-744f3a26121b | note | – – – – – – – – – – – – – – – – –
9191f35c-c882-56a5-836a-61dc640b9f84 | note | RESPONSIBILITY: SE/PE/SPE
4242447e-e24a-5c96-9880-921959cd6e9e | note | – – – – – – – – – – – – – – – – –
4af4552a-aec5-589f-aec5-978935637643 | note | VERIFYING DOCUMENTS: This ITP
d99d1241-2728-57bc-be3a-8e5fd444a762 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Method of Application
0b1caafd-c127-53fa-b4ee-5ecf51d47d45 | note | REFERENCE: Coating System TDS 685.07, 686.07, 686.09
e7bfa40e-b04f-549c-8de9-1ba0c7275f73 | note | – – – – – – – – – – – – – – – – –
5b289626-d096-52a2-9c26-cd434d398c52 | note | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
6e95b0b9-553a-591c-96c2-e2fdb85b79fe | note | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
3d78037b-70e3-5ccb-8f00-f3f207b75f1b | note | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
55070f18-9be8-5ce7-8bd4-b3971c3f8713 | note | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
041e2396-0dac-5a6a-945a-40c696cb0bde | note | Attach: Coating Application Record
7637b6f9-95a4-5c5c-80b3-df373d242f86 | note | – – – – – – – – – – – – – – – – –
1a95fe37-7b4f-511c-9af5-4eb1d6be9c4b | note | METHOD: Visual, Measure
848b731a-34db-574f-9b1a-42897abf081f | note | – – – – – – – – – – – – – – – – –
e70b593c-c814-542d-9d4b-f189f56898fb | note | FREQUENCY: Each coat
af4bc6a2-3247-57da-b4a3-4b7e17855b2b | note | – – – – – – – – – – – – – – – – –
88387a0d-7238-51a9-a616-25e2d8ed32d5 | note | CATEGORY: IP
b94168fd-e4a7-554e-8899-e7881117be89 | note | – – – – – – – – – – – – – – – – –
11095350-35ab-5ac2-84a5-0797066c2d10 | note | RESPONSIBILITY: SE/PE/SPE
b4198441-d039-55f0-99d3-cbea93eebb6d | note | – – – – – – – – – – – – – – – – –
0bec1f1e-a88b-5a53-b1b2-e1f7b45ffc76 | note | VERIFYING DOCUMENTS: This ITP
62372a7e-3def-5696-9b2e-8cb540500d64 | date | Date Completed:
| checkpoint | 5.2 Wet Film Thickness (WFT) Testing
e9219d4c-d6ab-564d-ac48-1a469b2cb44d | note | REFERENCE: Coating System TDS 685.12 (b) (ii), 686.14 (b) (ii)
e7e2164c-137f-5b27-af0f-af8e1e64d45e | note | – – – – – – – – – – – – – – – – –
f53f9826-a018-55d3-9371-13c2aa97a554 | note | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
d4062a9c-e029-54e3-bd9e-04d9e480fd2e | note | Attach: WFT Test Results
79c7db84-af3e-53b4-889b-61a916fb8cd9 | note | – – – – – – – – – – – – – – – – –
83cd62bd-2daf-5f1a-ac64-ce0515e571d6 | note | METHOD: Test
9888185c-f8a1-5f60-94c8-47cc73f527b9 | note | – – – – – – – – – – – – – – – – –
7c622d23-0263-548e-9a55-0b8d7de2bd92 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
500e57e1-c9ea-5992-a484-57750f45b2a1 | note | – – – – – – – – – – – – – – – – –
3847d14f-cbee-5d49-bbb1-ee12c122de68 | note | CATEGORY: IP
4805faf3-c422-5e74-a4bf-13739e7f787b | note | – – – – – – – – – – – – – – – – –
8032bd4c-e2ba-525a-8eb5-c0b48b19a2d7 | note | RESPONSIBILITY: SE/PE/SPE
014f0be3-c83b-5c61-b916-406ba5d741b1 | note | – – – – – – – – – – – – – – – – –
8be8a128-8d4d-5f06-bca2-591d837d5d24 | note | VERIFYING DOCUMENTS: This ITP
919e3fe4-8596-5b44-b28d-5645da0110ff | date | Date Completed:
| checkpoint | 5.3 Inspection & Defect Identification
675e3620-54bc-5363-b7ca-77b31707fd04 | note | REFERENCE: 685.07, 685.13 (d), 686.07, 686.15
39cbbeb8-c955-5e71-8746-9a179b2c5586 | note | – – – – – – – – – – – – – – – – –
fb2e2d2a-cc3e-51a2-b8ef-6f37b802ddac | note | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
8ba6eb56-84b3-5ca6-8f5e-c73317bb7bfb | note | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
3c990c03-a6fb-55f8-9848-ca693ee32ce8 | note | – – – – – – – – – – – – – – – – –
f4935d89-9afe-505b-9b5b-d70be6afa1a4 | note | METHOD: Visual
384aa30e-aab1-5b6b-bdab-7cc5a1d09a0a | note | – – – – – – – – – – – – – – – – –
4b06f16b-7b98-5292-af92-e8ef33fc4347 | note | FREQUENCY: After each coat
f829aa23-02d2-5b37-b1d9-06ff877459c9 | note | – – – – – – – – – – – – – – – – –
8371dff6-7d8f-594f-9301-fbdec7a539c7 | note | CATEGORY: IP
f0e6b42a-d2e0-56cb-8f64-77993e5d71af | note | – – – – – – – – – – – – – – – – –
6854a716-20e0-5067-8c79-b22bff694319 | note | RESPONSIBILITY: SE/PE/SPE
051d84b6-7e8b-59f7-a1e6-0986cff7cbed | note | – – – – – – – – – – – – – – – – –
a462e1df-7b3c-506c-a979-20103fbb4ee4 | note | VERIFYING DOCUMENTS: This ITP
79be88bf-2b92-59cf-8af2-863c8124f554 | date | Date Completed:
| checkpoint | 5.4 Drying and Curing
8fe20414-e7a8-5bff-a79e-85fae8d403db | note | REFERENCE: Coating System TDS 685.17, 686.10
dca1bacd-7fb9-5ba1-a47b-d38b79a67672 | note | – – – – – – – – – – – – – – – – –
64892708-e9d5-54b3-bb54-08e3d8b360da | note | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
0427fb8a-9b15-5302-803e-bcbb0a8e98cb | note | – – – – – – – – – – – – – – – – –
9ce92096-43c4-5c79-9083-69462a264f14 | note | METHOD: Visual
2ee37090-2f8a-592c-9127-d9f17972af73 | note | – – – – – – – – – – – – – – – – –
4db18fc7-ebc9-5f3b-aa92-8ae897e4dcd2 | note | FREQUENCY: After each coat
c7c0102e-6a65-59e4-ab8f-8537a99d092d | note | – – – – – – – – – – – – – – – – –
e104d57a-7a49-5f64-ba3e-e1274c487826 | note | CATEGORY: IP
2ad4fc6a-8db8-5112-85c5-c26b21e3942d | note | – – – – – – – – – – – – – – – – –
4947cf6a-63df-58dc-a656-c8ad32463be1 | note | RESPONSIBILITY: SE/PE/SPE
65c8ca02-efeb-5a0e-a860-efb873989773 | note | – – – – – – – – – – – – – – – – –
4192b1bd-3571-5523-bf57-e60e795c9d09 | note | VERIFYING DOCUMENTS: This ITP
df1cffe6-9c41-5d91-a5db-5ae8cee34577 | date | Date Completed:
| section | Post-Post Construction Activities
| checkpoint | 6.1 Clean-up & Waste Disposal
d4e2fee5-0a18-592c-8f51-951b2249fc58 | note | REFERENCE: 685.09 (c), 686.10
e58be2bc-9ec8-5dd6-9b5e-478feb7746b1 | note | – – – – – – – – – – – – – – – – –
955009be-4c74-578c-80da-c2aa8fd2f0f9 | note | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
ed32fdbb-accb-56b3-ac7e-8ecced2e9ff5 | note | ○ All rubbish and remaining coating products shall be removed from site.
eff8f009-7381-5c6c-8a28-c182787ef6cb | note | – – – – – – – – – – – – – – – – –
2b9d98b5-0a7d-5a1a-9f30-89539121025c | note | METHOD: Visual
15cd90e8-e684-5f69-bd10-d20e897324db | note | – – – – – – – – – – – – – – – – –
798da41a-5ed9-5781-a687-b282c37090ad | note | FREQUENCY: At completion of Works
1c256058-1ce0-51fa-ae59-2a8d71137885 | note | – – – – – – – – – – – – – – – – –
ca97714f-06b0-5910-b921-7c9e1d5b0097 | note | CATEGORY: IP
3f7a8080-0127-54f7-95fc-9d5a95288e51 | note | – – – – – – – – – – – – – – – – –
006a7949-a572-5518-9a31-3ca2e9cfecf0 | note | RESPONSIBILITY: SE/PE/SPE
766ff7e1-e2e4-5b2c-8617-8f0300e36b78 | note | – – – – – – – – – – – – – – – – –
406b39c3-2adc-5cd9-8c49-6506cb056a28 | note | VERIFYING DOCUMENTS: This ITP
bdbe9527-49a2-56e9-9fbf-3a52825d444d | date | Date Completed:
| checkpoint | 6.2 Dry Film Thickness (DFT) Testing
0690805d-5cdf-56f3-9c7f-000bdd5360ce | note | REFERENCE: 685.12 (b) (iii), 686.14 (b) (iii)
44df36b8-cffe-538d-a503-29bc8c53e9b2 | note | – – – – – – – – – – – – – – – – –
e96e7952-e236-50e2-aa1f-6b6115534b88 | note | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
a20d5caa-307f-5e5f-8ec0-53945dba8c83 | note | i. Anti-graffiti system = 100µm
630b4510-24cb-5d5d-ad3f-6fa0d1efb978 | note | Ii. Decorative & anti-carbonation = 150µm
1f43f235-c83c-5df7-8032-b5447a46b556 | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
35423a2c-23f4-5f33-9b68-7d0055d48fd5 | note | iv. Atmospheric & splash zone (dual protective) = 200µm
065d8faa-0bc8-5435-a4b6-507b559c3824 | note | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
9d570c1e-ea63-5b1d-abb3-7159ea67f5fe | note | Attach: DFT Test Results
3c9e7d41-0d3e-5970-a535-02d6884f1ae7 | note | – – – – – – – – – – – – – – – – –
7470c1eb-d363-5746-b6ad-0f8526300284 | note | METHOD: Test
f8ebf29d-7918-5cc3-a8d7-d48293da2055 | note | – – – – – – – – – – – – – – – – –
c331c14c-e564-554f-b853-0a744fe28a3e | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
87d51e30-3c93-5988-ba9d-3899c4221c9e | note | – – – – – – – – – – – – – – – – –
9eefe6b3-c184-50c0-99dd-cb6f59fb1d31 | note | CATEGORY: IP
d589d285-252c-579b-825b-d7a11142923d | note | – – – – – – – – – – – – – – – – –
268f39b0-50d4-5e47-8104-775458379169 | note | RESPONSIBILITY: SE/PE/SPE
1df76338-08cc-5ca8-a76e-5cea192c77e9 | note | – – – – – – – – – – – – – – – – –
a90973ac-a0d7-5b52-b534-9dafe274e8af | note | VERIFYING DOCUMENTS: This ITP
71d6ffbe-baa8-57f3-a220-8cd94ad5463a | date | Date Completed:
| checkpoint | 6.3 Adhesion Bond Strength Testing
882d73a9-2e78-5409-8228-47dab9a84eb9 | note | REFERENCE: 685.12 (b) (i), 686.14 (b) (i)
22eb6114-eb00-5ed9-a05e-6cf5844f7446 | note | – – – – – – – – – – – – – – – – –
79fd3311-8b1c-5ce8-93d8-262219abcc6f | note | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
d00aac2b-c504-5582-8f70-cd592ac9bfd7 | note | i. the coating system to the substrate, and
11a84be9-d898-5c7c-ace4-32a2a6bfdaa1 | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
2363b8d9-2229-59fd-9833-8e9f7467befb | note | ○ The subsequent results shall be greater than 0.75kPa.
c7bc1759-21a9-55e7-a7c1-45ce6a2a8e3b | note | Attach: Adhesive Bond Strength Testing Results
6009e094-9dc2-52f9-9f52-e3ac327097c4 | note | – – – – – – – – – – – – – – – – –
e624640a-2220-51a4-b1fe-622f36c6cb52 | note | METHOD: Test
24d5e507-9754-59b6-9b55-1d6ad9ea8959 | note | – – – – – – – – – – – – – – – – –
f10e8d2b-4a12-5ad3-98ec-1b9728bf7379 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
173a046c-c50c-5040-8be7-40e51c7a3629 | note | – – – – – – – – – – – – – – – – –
a83ec978-d43e-571e-b10f-11340c1a6ca0 | note | CATEGORY: IP
49fcbc38-6565-53c5-b721-7ebfb47b69aa | note | – – – – – – – – – – – – – – – – –
5db85fc3-d91c-547f-8e44-bf944f26094e | note | RESPONSIBILITY: SE/PE/SPE
b03febcd-c5f2-5008-b5bb-a4312d9ff5a0 | note | – – – – – – – – – – – – – – – – –
cf20a851-0b9d-50a0-a8e6-66af0aff6e8e | note | VERIFYING DOCUMENTS: This ITP
2a990c94-75bc-5402-9231-1a1adcf12b8e | date | Date Completed:
| checkpoint | 6.4 Penetration Depth Testing
86cf5c51-3272-562f-9a94-2cc68c03b93a | note | REFERENCE: 685.12 (b) (v), 686.14 (b) (v)
4428e3d0-6d11-5f91-a403-e4ade7553c7b | note | – – – – – – – – – – – – – – – – –
840f56dd-82d3-5296-a573-992d336994e3 | note | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
725ce903-2840-551a-8895-5655de1562e8 | note | The subsequent results shall be:
e40eccc3-66ef-5c95-9f2c-2ffc25a73442 | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
647408d7-9d0e-59c2-af85-12fa91484f6f | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
a26e6d60-b588-52b0-8a65-9a0f775f13b3 | note | iii. Silane-Siloxane or Siloxane = 3mm min.
ec768c48-5e70-5f9c-9f7f-0d364894825b | note | Attach: Penetration Depth Testing Results
3770d364-11fe-5ff2-bb8b-6f1a507b27cc | note | – – – – – – – – – – – – – – – – –
dc952c5f-0e35-5fab-ba43-f0ad4c18900d | note | METHOD: Test
52c1faf3-5b38-5e5e-a8b9-71f30280357c | note | – – – – – – – – – – – – – – – – –
2469bca5-2775-5efb-860c-dbd37faa8f22 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
3bca78fa-f0d5-500d-a1b2-006d2a3b7a2d | note | – – – – – – – – – – – – – – – – –
9d515094-0556-5fbd-912f-2829a7c66d69 | note | CATEGORY: IP
6c2f8796-6f2a-53cd-8149-a1975d0fda77 | note | – – – – – – – – – – – – – – – – –
2a74e772-412d-5e75-8d33-1dbdc5870baf | note | RESPONSIBILITY: SE/PE/SPE
d017b552-7300-59d0-aa3e-03aca3974e33 | note | – – – – – – – – – – – – – – – – –
5badd70e-599b-5509-ae19-6ea81fd51ceb | note | VERIFYING DOCUMENTS: This ITP
5bb01391-1526-5f13-8621-20ededb21a0f | date | Date Completed:
| checkpoint | 6.5 Non-conforming Coatings
351bf315-014d-5007-81ea-923d499addd2 | note | REFERENCE: 685.14, 686.17
071b3c72-3350-51ab-abca-66d1ee7b3d67 | note | – – – – – – – – – – – – – – – – –
321e963c-33f0-5f23-8c0a-29194a26b579 | note | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
46d3490f-326b-5ce3-ba09-4d35dac8c81a | note | ○ Such Work may include removal of the coating, surface preparation and re-application.
a4c5658f-3417-5c88-8314-96ddf18b4ad8 | note | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
c471096d-b123-5ed6-8c8a-41fa5d55ccf4 | note | – – – – – – – – – – – – – – – – –
0636603b-fe43-56aa-8618-78656c2eac55 | note | METHOD: Visual
061a5e93-101c-57eb-b18c-6a36e4308826 | note | – – – – – – – – – – – – – – – – –
2c93f8b1-5363-56b0-8b29-7ae53f0586e5 | note | FREQUENCY: Where required
3305c8e2-e91f-52f7-9656-6fae76b23f95 | note | – – – – – – – – – – – – – – – – –
52b18e28-f0e7-5953-a7d4-60fcb5e5b509 | note | CATEGORY: IP
a1c29f46-f1ad-51b9-b152-a6964af47b85 | note | – – – – – – – – – – – – – – – – –
29a7c464-a02d-5d19-a221-c0c693f95a74 | note | RESPONSIBILITY: SE/PE/SPE
90f3f27a-9a88-542c-b60b-746c5c7875b0 | note | – – – – – – – – – – – – – – – – –
d2b034f5-9180-52b1-84a0-a7eea1f758ad | note | VERIFYING DOCUMENTS: This ITP
5a6aedfc-514f-53cf-9d0a-331d51fa415a | date | Date Completed:
| checkpoint | 6.6 Coating Application Guarantee
d238859b-edd5-59ca-8972-0810726d85d0 | note | REFERENCE: 685.06 (b), 686.05 (a)
7293d45e-d449-5292-b3b7-283508920f87 | note | – – – – – – – – – – – – – – – – –
13098313-8ff2-58ee-b2c3-3f82ac7c0a7a | note | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
94a72e2f-c4ef-582d-b1f2-d379513ccc7b | note | Attach: Coating Application Guarantee
6c18685d-b16b-59c2-80b7-b047b24c20d7 | note | – – – – – – – – – – – – – – – – –
83beabff-2e44-59b0-b797-3aac436843f8 | note | METHOD: Document Review
82791c0f-b0e2-5682-a965-802509dce493 | note | – – – – – – – – – – – – – – – – –
9d0086a3-feda-5a22-b5be-177a26b52893 | note | FREQUENCY: At completion of Works
cb96e163-9eba-5b54-8d51-f569b1b22ede | note | – – – – – – – – – – – – – – – – –
8b685bc4-ce4e-54c8-9db3-beee9b29c872 | note | CATEGORY: SP
9d0ecf68-3e29-51cc-99c4-1b239a7f0898 | note | – – – – – – – – – – – – – – – – –
899b1067-12d5-5a82-8917-823689cd970b | note | RESPONSIBILITY: SE/PE/SPE
d30f2a63-eba4-5610-883e-6e00789d006e | note | – – – – – – – – – – – – – – – – –
9de736ec-af6f-5e06-9710-b627eb034b60 | note | VERIFYING DOCUMENTS: This ITP
64a94867-fbf2-5945-9a86-36e5a2a32fbb | date | Date Completed:
| checkpoint | 6.7 Repair to Damaged Coating
10bfa162-7827-50d5-96f1-5aba26d392ad | note | REFERENCE: 686.17
16a58475-f6b2-54ba-bcc8-5f8447adb535 | note | – – – – – – – – – – – – – – – – –
89f5f481-a9ab-5f37-a290-a7c83f6c277a | note | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
626a97d8-7173-5be8-b50a-f3678d9c8683 | note | – – – – – – – – – – – – – – – – –
78353e69-4eb4-574a-accf-740ec29c25e1 | note | METHOD: Visual
1acd6a17-68d3-5d54-9ac7-28e72a438820 | note | – – – – – – – – – – – – – – – – –
9830da38-b7bf-558e-992a-702f664d1148 | note | FREQUENCY: Where required
3cd3e939-9b3c-5f94-bc53-db13acd70566 | note | – – – – – – – – – – – – – – – – –
6285c43f-ea55-5c76-8217-f88c6fef3348 | note | CATEGORY: IP
1b3238ec-a033-551d-b514-41e63016388d | note | – – – – – – – – – – – – – – – – –
7da553e3-497b-5255-90f7-f8526910a41f | note | RESPONSIBILITY: SE/PE/SPE
2544481b-bcb5-561e-803e-e4fd3fd11c5b | note | – – – – – – – – – – – – – – – – –
fd5f59b5-5b99-5072-a8e5-238590d0e4fc | note | VERIFYING DOCUMENTS: This ITP
af8d7e63-454d-534d-a2a5-7fbc9d6304f9 | date | Date Completed:
| checkpoint | 6.8 Non-conformance Report (NCR) Closure
705a32a3-cddc-5643-8081-5fab7e701903 | note | REFERENCE: MRPA Quality Management Plan
f6c8a820-7eaf-57ac-bfcb-c51fcd28744d | note | – – – – – – – – – – – – – – – – –
aeaee244-b1d3-5cdb-80d9-b67514307648 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
d979d0db-e4e5-5822-a238-4a99caf433c3 | note | – – – – – – – – – – – – – – – – –
708475be-f0d3-53d0-b6a0-abf3e1d79147 | note | METHOD: Document Review
3a82507f-4372-5e60-9e72-388d4f5b53dc | note | – – – – – – – – – – – – – – – – –
2762d346-04d5-53d0-bfc0-9e7c7e8c339e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e49620f2-12bf-5cba-89bc-0ce211d59e0f | note | – – – – – – – – – – – – – – – – –
b5806e8f-8f0a-5d21-8e0a-508401fde1c3 | note | CATEGORY: HP*
8fad31ab-36bc-50e8-b9c1-782ebcc6e6b3 | note | – – – – – – – – – – – – – – – – –
de507a4f-b4bd-59aa-bace-8e85db0cd070 | note | RESPONSIBILITY: SE/PE/SPE
a11f605f-c53b-564c-9fd7-589ba33ccbb4 | note | – – – – – – – – – – – – – – – – –
c41d41c8-917a-5d1e-a3e2-7bc77d2b9fb7 | note | VERIFYING DOCUMENTS: This ITP
109e2b71-4dd8-5b89-8507-740d851243b1 | date | Date Completed:
| checkpoint | Final Inspection
58d6aabe-6c8a-5e63-8cab-07742ef73211 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d8117cf0-8552-52aa-909c-0bd52959a01b | textbox | Name:
5ac02c4d-1b10-567a-a3d6-90f17d1a3615 | textbox | Position:
2681182d-eef2-5581-a43d-2acae8110959 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-154-STR-SSB-Precast Super T Installation Rev 0 | itp | ITP-154-STR-SSB-Precast Super T Installation | 113118e7-9644-4857-a493-18b33cb40350
| section | Referenced Documentation
| checkpoint | Referenced Documentation
2daedeab-3acb-5d7a-a07e-7fc627f8c23a | note | Document Title: ITP-154-STR-SSB-Precast Super T Installation
4780b3ef-d1c6-522d-bb75-8f31c4634f67 | note | ITP Description: SSB-Precast Super T Installaton
7c9cace8-4110-5c33-8e9a-f32024562f18 | note | Discipline (e.g. CIV/STR/RAIL): 154-STR
ad433f81-7bbe-51a7-9c85-5a6a750760d7 | note | Revision Number: 0
d081902d-743d-5d69-a4e0-d0d9403cf30f | note | Revision Date: 1/05/2024
c4ac9f6a-cd32-530b-8a42-5184ccbd04a1 | note | ITP created by: Dan O'Brien
afbc0b4f-42d4-578d-8312-ab047e342178 | note | ITP approved for use by: Victor Mira
b7a43951-e928-51b5-a934-36771c8af4cc | note | 1.1 Non Dependent
5ffcf502-b840-5ee1-b6b1-bbf188d441df | note | Reference: VR 652 June 2010
fb24bbc2-4a6c-5738-80ce-928a649f75f8 | note | 1.2 Non Dependent
a765f196-0423-574a-b73b-a8941f808827 | note | Reference: VR 656 June 2010
c7a431f5-3122-5281-8441-d156bc4bbb7a | note | 1.3 Non Dependent
d6b7d420-8edf-57aa-b4df-38e05545301a | note | Reference: VR 610 February 2020
02a2935f-758d-53af-b6ef-c077ddaaf908 | note | 1.4 Non Dependent
1b207aa2-2172-5452-9613-81f18b934157 | note | Reference: VR 620 May 2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Epoxy bedding
2d353e9d-1984-5b6f-9cfb-f00e6fd36068 | note | REFERENCE: IFC Drawings
37f1de1f-e15d-55c1-a0b7-3f44641cf5c2 | note | – – – – – – – – – – – – – – – – –
835198e7-9647-5be6-a3b0-b1152ef67f3d | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
2929e4b6-2ed7-5e53-a112-c02fbdde06a7 | note | i. Have a minimum compressive strength equal to or greater than substrate
4abc8512-5171-5692-871a-347744016787 | note | Ii. Can be applied in IFC specified nominal thickness (1mm)
4141b257-b188-5177-8a2a-8d0ebb8fe1a7 | textbox | Enter: Teambinder Material Approval number
b06d0bcc-990a-55c2-808f-f86b4f7e3ae4 | note | – – – – – – – – – – – – – – – – –
9d71e830-6db8-5586-8231-8656c06f91c2 | note | METHOD: Document Review
605e9ba8-9e6f-50eb-b042-95cdb4a408ec | note | – – – – – – – – – – – – – – – – –
1d92bb17-571a-54d2-ab2c-308227979eef | note | FREQUENCY: When applicable
7371ad9c-7d94-505f-86ee-df8dc608b2a4 | note | – – – – – – – – – – – – – – – – –
b9e3a8cc-54bf-550f-aa51-bc2c6f3e675e | note | CATEGORY: HP
615e28e0-c727-59a4-9799-60d8e3e05aac | note | – – – – – – – – – – – – – – – – –
961bf312-04b8-5ffb-a6f7-a0b48ec2f7eb | note | RESPONSIBILITY: Nominated Authority
51cd0bf0-a1ae-56e0-a7e6-743841cbecc5 | note | – – – – – – – – – – – – – – – – –
6d89b180-1ce8-56b8-8a7c-64fcbe927bfe | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
fdff2274-507a-5752-ac90-03a8b7863f6d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bolts
794489b0-ef82-5c21-a576-147757b20fd5 | note | REFERENCE: IFC Drawings
097a8e22-b990-572f-b4df-d7dff771f01f | note | – – – – – – – – – – – – – – – – –
3db30cea-e901-5ffc-bc22-6047a86b6a90 | note | ACCEPTANCE CRITERIA: M16 grade 4.6/S countersunk socket cap screw
f24aa3c1-587a-5687-9c11-f6db600ea014 | textbox | Enter: Teambinder Material Approval number
f7cef8fd-5792-558a-95a9-b468faed9f1a | note | – – – – – – – – – – – – – – – – –
61515735-9dad-5caf-a019-e1e9be489909 | note | METHOD: Document Review
c35e0d56-38b7-545a-8a6f-f9689ed41faa | note | – – – – – – – – – – – – – – – – –
cfe21c81-bf8b-5aa0-a4af-6253ca859b1f | note | FREQUENCY: When applicable
21ccd3d5-b16e-5a87-a3c0-8e7ba852564b | note | – – – – – – – – – – – – – – – – –
0098a4a4-2129-5136-842c-dcfe20ff5f0c | note | CATEGORY: HP
d8daecdb-6b70-57a8-99cb-551e101dc83a | note | – – – – – – – – – – – – – – – – –
29b854b0-27fb-5a3f-a153-b66bea686d98 | note | RESPONSIBILITY: Nominated Authority
10ab9497-6c2f-54e0-9a97-8214ecaf3649 | note | – – – – – – – – – – – – – – – – –
5abf272b-5150-5b8e-bc91-54bde562eb63 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
45d0f450-5a39-5927-ba54-aa6e25c4771c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Precast Elements
577c696c-ad21-5630-ba0e-77f6159d7b2f | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.473 (March/June 2019), 620.03
b432582b-346c-5d0e-b90c-7f6d0fa5071e | note | – – – – – – – – – – – – – – – – –
737527b2-97ed-55cb-9652-64e070788650 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
2c433ef8-b854-5040-86ab-656cf8dcf73c | note | i. Certificate of Compliance / Birth Certificate
7108b8d3-bec1-5a89-9590-1bbbce6025c1 | note | ii. Compressive strength test results
ce816d75-69dd-5076-9a7a-e724a85e1e3b | note | iii. Precast Lifting Design
7ca97125-deec-5fde-acbd-56d97201f69a | note | iv. Pre-pour check sheet / ITP
4e76e859-4446-50c0-9a4d-451820642479 | note | v. Pre-stressing check sheet / ITP
72d1464f-161b-5845-bbfa-567256cb73e8 | note | vi. Post-pour check sheet / ITP
1ae5db3d-fecf-57c2-82a5-6ae1c0fadc3e | note | vii. Covermeter check record
ec5c4958-72d9-591c-b3af-255eb6181c96 | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
c63b2cdb-18fe-5824-8292-5045e4dbe127 | note | Note: Different revisions of 610 have different clause numbers
52cdaca8-c2d5-5122-af23-3db81e99f9f4 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
0d9ab90a-55ed-548d-8ec1-867aa67b595c | textbox | Enter: Teambinder MDR Lot number
f7ba8785-b298-5909-9b16-6d6ef64607e1 | note | – – – – – – – – – – – – – – – – –
be7e4033-d2e0-517e-ad80-fc28fffb1db8 | note | METHOD: Document Review
d3165e0f-f499-57f7-b712-e93073a8c932 | note | – – – – – – – – – – – – – – – – –
3aa4328d-e3af-58ea-9e71-82cfce265165 | note | FREQUENCY: Each element
41a5f6b4-5106-58b0-9628-d22c5e63323a | note | – – – – – – – – – – – – – – – – –
287be56d-7208-5a3b-8dff-bfd5c2c0fee9 | note | CATEGORY: HP*
daa41b0d-5542-5e67-83ad-35327a95aba6 | note | – – – – – – – – – – – – – – – – –
39ad6b56-9426-504d-9e68-943b45d49cee | note | RESPONSIBILITY: PE/SE/SPE
d61e4819-3b86-5408-be8c-5749f9775df5 | note | – – – – – – – – – – – – – – – – –
2c46a065-2dd5-5eeb-ae16-703dc1864d40 | note | VERIFYING DOCUMENTS: This ITP
9b0cbceb-99ce-5945-8b11-d8f69aedd761 | date | Date Completed:
| checkpoint | 3.2 Elastomeric Bearings-crosshead and restraining blocks
0c6f1b8b-96e5-5954-8797-c43abee9816c | note | REFERENCE: IFC Drawings 652.02, 652.03, 652.04 AS5100.4
3d328fe2-6cd5-5ad9-9291-922b06967882 | note | – – – – – – – – – – – – – – – – –
0aca2049-957e-5a71-aa86-1059509f5fda | note | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
b679bb88-cdb3-52b9-aabc-a5143ef4cd64 | note | Tolerances:
ada7da69-9767-5140-a18e-1962302f8025 | note | Dimensions in plan = +4mm, -2mm
57940320-9c86-5e05-a8f4-0cda43dc8598 | note | Thickness =
5860c073-9b15-5473-b388-a88b699aa328 | note | ○ ≤100mm = ±2mm
69adc0ef-792b-593e-8cd5-ef22d4fa3af1 | note | ○ >100mm ≤ 150mm = ±3mm
0ced8879-725c-55fd-91ea-f3908b820804 | note | ○ > 150mm = ±4mm
2f925334-f587-5d15-9435-63140cb37b36 | note | Testing:
61cbbeb2-35b2-5693-9166-4efa48e8751a | note | ○ Each bearing tested under compression
80c33ab3-f77c-5e3c-8465-da5d6d8ac11f | note | ○ Batch tested for shear stiffness
f462e438-2a5e-56e5-b085-c5bb25320b8b | note | Attach: Elastomeric Bearing Test Reports
d7da37c8-bac8-53b9-b704-f9aaa781f1cb | note | Attach: Elastomeric Dimensional Records
a6dfa0d8-07ae-50c4-880a-5d0dabdf2d23 | note | – – – – – – – – – – – – – – – – –
79fd4b40-de87-5c92-9f19-0360e2db7c53 | note | METHOD: Document Review
765e373e-e2fe-5a5e-b618-6a5f5f813f5d | note | – – – – – – – – – – – – – – – – –
8f18810e-3092-54be-ba4d-7a58f5e72357 | note | FREQUENCY: Each element
9540db40-c2b2-59cc-9986-11422d13e3d9 | note | – – – – – – – – – – – – – – – – –
2102b0b8-7457-5be1-8632-45454e3aa070 | note | CATEGORY: HP
66970808-cbaf-5848-a925-7f572caf6b82 | note | – – – – – – – – – – – – – – – – –
69bd4513-4b54-5758-924e-26dc02cf35a3 | note | RESPONSIBILITY: PE/SE/SPE
12cdfacf-fa02-5f44-93ec-6a22de2a43cd | note | – – – – – – – – – – – – – – – – –
f179fc51-141c-56f9-833b-87bb2a5e765b | note | VERIFYING DOCUMENTS: This ITP
554550d9-7835-5e1a-a2b4-1ca14aa07036 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Tapper plates / Keeper Plates
bf536a25-0f6a-5ae6-81d3-d9f12858dc6b | note | REFERENCE: VR 620.05
91602662-2f26-5b76-b8e8-f366b2619332 | note | – – – – – – – – – – – – – – – – –
8730f0f0-39ac-592b-9cf1-8bb2e9932fe0 | note | ACCEPTANCE CRITERIA: Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
7e2d02b7-19cc-5d3a-8104-3e78d64f6df5 | textbox | Enter: Teambinder MDR Lot number
0ec01da7-4f16-5361-9286-2ac9cd59d71d | note | – – – – – – – – – – – – – – – – –
62120c67-255f-5a02-a9d3-446fae61aed9 | note | METHOD: Document Review
9d707118-46b7-5001-b808-25043f252a9a | note | – – – – – – – – – – – – – – – – –
3f5c5091-1be0-5d92-bdaa-870eb9cc6bf3 | note | FREQUENCY: Each Plate
5b8a643c-785d-533b-9e7d-7807e9d5a79c | note | – – – – – – – – – – – – – – – – –
bfade325-420a-54d8-bf57-31cd9172ac7a | note | CATEGORY: IP
d7d0d864-6575-54ba-8e88-a8c6112b0397 | note | – – – – – – – – – – – – – – – – –
ed8bee67-cdc2-5b2e-987d-9b372f7fbb81 | note | RESPONSIBILITY: SE/PE
466804e3-11d5-5615-8bef-090ecafbbe26 | note | – – – – – – – – – – – – – – – – –
90040ab7-f9a8-5859-9ab8-37ec6b1b440d | note | VERIFYING DOCUMENTS: This ITP
84e5e88b-22b3-5afd-801e-ef513fe88fad | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 Bearing Plates-Check
39ec4bb2-2dbe-5b93-96ab-0c0f6bde13f1 | note | REFERENCE: IFC Drawing
ba095c83-d904-5865-9613-35a72d5b2612 | note | – – – – – – – – – – – – – – – – –
0f9dcec7-b044-5ac9-b56c-8aeaeff54b6a | note | ACCEPTANCE CRITERIA: Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and bearing orientation are correct.
6e711fbd-5a0f-5654-990c-b8d857690125 | note | – – – – – – – – – – – – – – – – –
90973d43-6e6d-5114-baa5-4f643ff5bee0 | note | METHOD: Visual
9edbefcc-a49d-58b1-9d64-d4b8c51105fc | note | – – – – – – – – – – – – – – – – –
8b9e3a5e-99de-5880-bb95-4f6bfce12c82 | note | FREQUENCY: Each Tapper plate
6e1ed9b9-6daa-55fc-be4e-29ebd9db1cb9 | note | – – – – – – – – – – – – – – – – –
2b1d73c3-7c1e-553b-9000-3073ae3bcbcb | note | CATEGORY: IP
6c1bb52f-9e27-5e8f-84ce-9da506d779b4 | note | – – – – – – – – – – – – – – – – –
2805df6c-f731-56a7-9186-a9f1ce7dbda7 | note | RESPONSIBILITY: SE/PE
10412eba-8788-505c-80b1-3eeaa9938da5 | note | – – – – – – – – – – – – – – – – –
7d909814-24e7-5558-96f9-343b44520536 | note | VERIFYING DOCUMENTS: This ITP
ac322d61-aef4-5a27-b9ae-78b96744c06c | date | Date Completed:
| checkpoint | 4.2 Crosshead / Pedestal Tolerances
f8cd068e-466a-570a-ad3b-ad31a9962326 | note | REFERENCE: Survey As-builts / Survey Report
c90732fc-3c13-566d-8ebe-bc760bd907ae | note | – – – – – – – – – – – – – – – – –
a1f5618f-c618-5aa8-906f-a99cdee19861 | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
31619191-35b2-53ed-9812-52896c4d5fd2 | note | ○ Reduced level ±2.5mm
9f24ab78-c75c-5bc3-90a7-91261f49e29e | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
b17ab9ad-6fa4-53f0-b1c9-5c1179e3cd5e | note | ○ Deviation from flat surface ±1mm
f495391d-1ff0-5416-89ec-d2c9c050c892 | note | – – – – – – – – – – – – – – – – –
25ba0038-7d0d-5bb6-9bf3-6d4f9c924518 | note | METHOD: Document Review
c344bfd2-e17b-5758-9522-c0d7124a02c2 | note | – – – – – – – – – – – – – – – – –
0a35cd5a-ed2b-56ca-b14f-537feee8ea0b | note | FREQUENCY: Each element
f9de3bb4-47f3-568f-b39d-8c8e111e705d | note | – – – – – – – – – – – – – – – – –
9372c74a-a490-551e-9651-4b78866dd998 | note | CATEGORY: IP
0d4e7bfd-5378-59da-972e-45d17d2273a8 | note | – – – – – – – – – – – – – – – – –
8fcc01ea-7fea-53e7-858e-fb533236bd0d | note | RESPONSIBILITY: PE/SE/SPE
f1a68786-8585-53e3-9c01-526e899467db | note | – – – – – – – – – – – – – – – – –
6f8707e6-4d7c-5851-857e-4978336b9b73 | note | VERIFYING DOCUMENTS: This ITP
b7baf0ee-5ffd-541e-8409-a9acfe975e1c | date | Date Completed:
| checkpoint | 4.3 Precast Beam Inspection
aca2ae01-f3cb-5217-9db4-40514522d3e6 | note | REFERENCE: IFC Shop Drawings, IFC Drawings
62061305-0e7c-5a82-b57d-bec97d0eedbd | note | – – – – – – – – – – – – – – – – –
2c82d620-5b0a-5cbd-a5be-f62158542651 | note | ACCEPTANCE CRITERIA: Check that material inspection checklist has been completed for each beam.
1216c602-ead9-5bee-ad83-091a821f28ee | note | ○ Engineer to check that each beam has been loaded with each end at the specified position (truck or jinker end)
c855a3d6-7987-5d37-82a4-93e9af9688bd | note | – – – – – – – – – – – – – – – – –
d15d8033-7cce-52db-9dba-f6d35177bb95 | note | METHOD: Document Review
5a745ac6-500b-5778-bdaf-3e80d0a29296 | note | – – – – – – – – – – – – – – – – –
114eb123-599c-5abf-917e-4e65cac5b67e | note | FREQUENCY: Each element
1c17dd56-4738-5231-b943-7c4185fa9456 | note | – – – – – – – – – – – – – – – – –
fb1f7a3b-5632-5718-9e7b-4c6b841b3391 | note | CATEGORY: IP
6514a593-a481-5498-bfbf-f254d1ca68ce | note | – – – – – – – – – – – – – – – – –
f6c0fd73-424c-5357-9aa5-f0d6e62d5d50 | note | RESPONSIBILITY: SE/PE
5bfc3797-afbc-5ca4-959c-89b9656bda4b | note | – – – – – – – – – – – – – – – – –
541cd2a2-9a9b-5b52-ba88-b76e9bb07df8 | note | VERIFYING DOCUMENTS: This ITP
72094af6-4239-59e7-8d0c-018d8666896a | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Elastomeric Bearing Placement
31a8a4fe-0b40-5a22-96d5-21c13dcbca79 | note | REFERENCE: IFC Drawings VR 656.05
bb49503a-ab98-58fa-bf20-69e88f7973ef | note | – – – – – – – – – – – – – – – – –
e0e505ca-88e8-5ab6-83b1-af0fdfc179f6 | note | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
d952b1a4-4742-5043-9880-e0f3eb57d087 | note | Tolerances:
8e5742ca-8a99-5de6-b834-be49c519ba69 | note | ○ Plan position: ±2mm in any direction
8e95b4ba-977b-599e-96c5-91a5c5666bbc | note | ○ Level: ±2mm
6e41e120-e401-54bb-81cb-765016c1c44e | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
03b7ecc4-ab14-52d6-8b1f-9efb8cfdb5e4 | note | – – – – – – – – – – – – – – – – –
7a17a6ef-0575-5da5-879f-9bd6be94ff56 | note | METHOD: Measure, Visual
03f593ea-7a5d-5de9-b956-2410199bfdc1 | note | – – – – – – – – – – – – – – – – –
1323f2e6-73a0-5319-9b0e-053b86b16b36 | note | FREQUENCY: Where applicable, each bearing location
ba491f5a-94f4-5de2-ba39-6f11895a2cf7 | note | – – – – – – – – – – – – – – – – –
5eba0b99-8f97-50e4-8ee8-1a451f86b2ce | note | CATEGORY: IP
15a55514-c51f-53b1-a8b8-98f961c1c54c | note | – – – – – – – – – – – – – – – – –
70d48710-7792-5341-a686-8974172a808e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
876b13fd-e643-5e50-a749-dfdab4ab8942 | note | – – – – – – – – – – – – – – – – –
56fa7987-de1f-5631-8cea-d6efafab7f0b | note | VERIFYING DOCUMENTS: This ITP
2b6d9aa5-ee7d-5a50-8fb3-3a9f1c153c02 | date | Date Completed:
| checkpoint | 5.2 Restraining Blocks-Bearings
72bcfbef-cfad-542d-aaa8-9a8e3758e693 | note | REFERENCE: IFC Drawing
9f6bb03b-5058-53dd-be54-63937c5476b8 | note | – – – – – – – – – – – – – – – – –
9857ff72-1504-5b3c-9886-33c0cc3cba15 | note | ACCEPTANCE CRITERIA: 230x150x35mm elastomeric bearings are to be installed in designated recesses on restraining blocks.
d58b8b97-c7e4-5006-8e71-9993181e2ee6 | note | ○ Base plate 260x170x10mm cast flush into lateral restraint block with 2 x 10mm diameter, 75mm long dowels (grade 250R) cast into restraint block (4mm CFW all around to base plate)
c1e1daf9-cf70-5404-926c-662a4d5c9d3e | note | – – – – – – – – – – – – – – – – –
40351494-b6a8-5769-a732-e53129966040 | note | METHOD: Visual
cb8f0e47-e914-50b9-8934-0551209c732c | note | – – – – – – – – – – – – – – – – –
3842ecd1-5767-5792-bf72-9cc6b3ea4f74 | note | FREQUENCY: Each restraining block
6d01e91a-b9a6-51dd-a22f-39934248df54 | note | – – – – – – – – – – – – – – – – –
8880d05d-fe29-5b0c-971d-e7e3fabac40c | note | CATEGORY: IP
dbb10497-f2db-51fd-80ba-7c3bcf59719d | note | – – – – – – – – – – – – – – – – –
3b7f73a4-d27a-5e41-a39f-ac04f13ab17d | note | RESPONSIBILITY: SE/PE
00ca790e-0bcf-5ff3-9aca-2018df1a98f3 | note | – – – – – – – – – – – – – – – – –
bcfcb262-4efa-582d-98e1-7018651df410 | note | VERIFYING DOCUMENTS: This ITP
a48954be-5bd2-5d17-97d8-a3b6d7f0761b | date | Date Completed:
| checkpoint | 5.3 Precast Handling
34d3b1ef-4b66-57d4-9a6d-849d27c3863c | note | REFERENCE: 620.07 Crane Lift Study
2935a8d1-5e80-5e00-8eba-f4ed72ad82de | note | – – – – – – – – – – – – – – – – –
1b74f324-bafe-5708-93c1-ceade2632abf | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
e4d15c65-bf86-5e58-a9b8-c79cb0dffac0 | note | – – – – – – – – – – – – – – – – –
8e272f1d-1093-586f-8a69-a942cd61254e | note | METHOD: Visual
a27f3c20-796b-5b64-a286-6bef274fda52 | note | – – – – – – – – – – – – – – – – –
b0d0f9ef-695a-549a-bab3-d3ec00931007 | note | FREQUENCY: Each element
d2600fc8-773c-5831-b885-6768bcbc0129 | note | – – – – – – – – – – – – – – – – –
005002b0-044c-59b7-a5ad-da16e16ca817 | note | CATEGORY: IP
0247cd61-d5b7-52d8-a85e-2746e9e191ad | note | – – – – – – – – – – – – – – – – –
95d5a623-19a7-5e9a-a66d-9a56095af69c | note | RESPONSIBILITY: SE/PE/SPE
25bde931-32c6-5820-8dff-63ecc1ce272a | note | – – – – – – – – – – – – – – – – –
c245b9b4-bb85-50b7-b16a-1b993485a94c | note | VERIFYING DOCUMENTS: This ITP
5e7f0103-41bd-5e6a-8f9e-d432ad7a6ad9 | date | Date Completed:
| checkpoint | 5.4 Precast Placement
8be7d1bc-be80-57ef-8073-6ad4425e4b8c | note | REFERENCE: IFC Drawings 610.27 Temporary Works Design Drawings (IFC)
eab261a7-31db-5243-b777-b1bdac88ee12 | note | – – – – – – – – – – – – – – – – –
fe15d4a1-a5ee-501e-af42-1c7b323c4c7b | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
88b9ece9-5ba8-547d-9c7b-e0f1546ad17b | note | ○ The nominal gap between elements is as per the IFC Drawings.
3c2609dc-4d5b-5cb2-9ef5-8226b06eaf26 | note | – – – – – – – – – – – – – – – – –
544e027b-5572-5f72-8cbc-02437eb269f0 | note | METHOD: Measure, Visual
9cfe212b-21a4-58d6-8102-c2d748bb7941 | note | – – – – – – – – – – – – – – – – –
eb980d0a-4613-517e-99dc-c21580f6c72a | note | FREQUENCY: Each element
c426b807-7609-5b64-9ff5-db623dcb06d3 | note | – – – – – – – – – – – – – – – – –
2a909130-664d-502f-961e-6754a7e76089 | note | CATEGORY: IP
d2e95443-cb85-51c3-ac49-3d6b42f3035f | note | – – – – – – – – – – – – – – – – –
3c25b821-ff60-5e1a-8c43-76b113ff227e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fa8095b2-36aa-558d-a6ad-a1932c73dee3 | note | – – – – – – – – – – – – – – – – –
6e7f78f4-f60f-5e3d-9c59-1ecb5d566167 | note | VERIFYING DOCUMENTS: This ITP
244088de-e04c-510f-8a84-7382f6855e64 | date | Date Completed:
| checkpoint | 5.5 Precast Traceability
b6db26c4-f3bf-5e39-8a12-857be7075b71 | note | REFERENCE: 620.09
2c80a696-eabe-55b9-847a-0ab38fd4b1a2 | note | – – – – – – – – – – – – – – – – –
3d931b52-fa09-516c-b934-6f50cb2b06ca | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
e552bdf9-5b9e-5d20-8e27-be6fec873db2 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
43de5f6d-59f3-5beb-80f8-099ace121495 | note | – – – – – – – – – – – – – – – – –
dfea21cf-206a-5e7b-8655-8ce1c3c888b5 | note | METHOD: Visual
5313b84b-4e06-5aae-9a29-2d96ef1600f6 | note | – – – – – – – – – – – – – – – – –
ad3ed215-80e5-5533-8c47-8988a05b4597 | note | FREQUENCY: Each element
bcde8cca-7fe8-55dc-8943-40b69cdae208 | note | – – – – – – – – – – – – – – – – –
09ba7f2a-e3ff-5714-b4fd-395d51b76cdc | note | CATEGORY: IP
8d27c61b-7925-5993-835a-d2bbd14eda86 | note | – – – – – – – – – – – – – – – – –
523d39e8-47ee-5eea-a766-8fff6beaee95 | note | RESPONSIBILITY: SE/PE/SPE
1227c860-3022-5333-a65a-e339c9293816 | note | – – – – – – – – – – – – – – – – –
b260bd3d-c4c4-542e-9fe9-7d22fb820dff | note | VERIFYING DOCUMENTS: This ITP
741634f7-3ccf-5503-989c-d172b452edc7 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 As-built Survey
1a74fb78-55ab-59c8-887c-b6af1e6022e4 | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 (March/June 2019)
1a845510-3605-5526-a406-90360084d5cf | note | – – – – – – – – – – – – – – – – –
aeee1abb-49c5-5bb0-b3e9-06ecedbc147b | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
b2d82d9c-2614-5b32-b87f-63c3653f1fcc | note | Attach: Survey As-builts / Survey Report
801a40f9-ca52-5eaf-8f8c-4aaf0e338748 | note | – – – – – – – – – – – – – – – – –
c544ba7c-cae2-5ced-86ec-240d5640e5b4 | note | METHOD: Document Review
f7fcbb52-336b-5249-a55d-cd9f549ff9bd | note | – – – – – – – – – – – – – – – – –
a24526ec-4e8d-5365-b1a8-2b4e5956ee55 | note | FREQUENCY: Each element
a0690489-6181-520d-9856-d2ec863b08da | note | – – – – – – – – – – – – – – – – –
72345dc0-cb41-5a8c-9de4-682c89d2caad | note | CATEGORY: IP
0a447d53-951b-5a4e-ac24-6b97cbc94715 | note | – – – – – – – – – – – – – – – – –
2d13583e-44a1-55b3-bb2b-c1268a79da28 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
7a07d905-90cd-593a-96c4-256ae9979eec | note | – – – – – – – – – – – – – – – – –
f5095f4a-8a22-51aa-b858-ad8c7e4abf04 | note | VERIFYING DOCUMENTS: This ITP
fc2388ff-b7f3-58e2-b90b-7695a12fe1b3 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
5932c691-4373-564f-b64d-d0903a05e05f | note | REFERENCE: MRPA Quality Management Plan
65cf6ab8-8ed0-57f9-a8f1-f5085c44114c | note | – – – – – – – – – – – – – – – – –
3531ac38-03c4-53f2-bc28-f3a34f25247b | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
653d7060-1c5f-56e5-a86a-2095d26874ee | note | – – – – – – – – – – – – – – – – –
75310a30-9c4f-51d9-ad7d-5b74d2644fd4 | note | METHOD: Document Review
d4fecb5f-877c-5325-81a4-22ca9146da4a | note | – – – – – – – – – – – – – – – – –
10b590d1-303f-5b77-be61-04b3c522f17a | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
6a4917f7-7a29-517e-b9d8-ebe15599046d | note | – – – – – – – – – – – – – – – – –
0f814a3b-5467-597f-8894-c7d0f8da2733 | note | CATEGORY: HP*
f7576878-5af1-5c50-9318-30ccb08e3b2a | note | – – – – – – – – – – – – – – – – –
233aa0c8-e792-58cd-9d39-38a26f13e0e2 | note | RESPONSIBILITY: SE/PE/SPE
04ab15c0-8d07-56c0-ae5a-2651e6cdb425 | note | – – – – – – – – – – – – – – – – –
147e1244-60b3-5201-9243-d45dca4b8f2a | note | VERIFYING DOCUMENTS: This ITP
e67300f1-5d4b-58d2-ba77-70837d8b9a9a | date | Date Completed:
| checkpoint | Final Inspection
42e373b7-6de8-54a8-9a83-a4e7c4fa571e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
baa23426-0c64-5c22-abc0-4c0b1e974a90 | textbox | Name:
4dcbbe5e-a182-59e1-b2b6-9e930b15780e | textbox | Position:
0b4783ef-1a47-5243-a257-7fea795dffc0 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-155-STR-SSB-Misc Steel Structure installation Rev 0 | itp | ITP-155-STR-SSB-Misc Steel Structure installation | 2ec5f430-260f-4092-95d7-d108d7e91d9a
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a625f9d4-5dbb-5240-805a-f67b4c8f13b2 | note | Document Title: ITP-155-STR-SSB-Misc Steel Structures Installation
24fe5185-247e-53ce-9e68-dcb137d30e9c | note | ITP Description: SSB-Misc Steel Structures Installation
cca595b9-fcd0-52a1-a843-bfc6417ac43c | note | Discipline (e.g. CIV/STR/RAIL): 155-STR
ca898afe-ac25-5afd-829d-1f3a005e369c | note | Revision Number: 0
f24c8577-6ff8-590a-bf34-7b5c4f2d7228 | note | Revision Date: 1/05/2024
844e5a8c-7fce-51f1-8ae9-53f8712751fe | note | ITP created by: VM
5a9b3164-0ba5-5836-a9f6-b279c75feaac | note | ITP approved for use by: VM
7e936023-9e62-5bed-9375-e4b11489a8a3 | note | 1.1 Non Dependent
7cf79d5e-da88-5664-9ddf-6ba3efa3a1f2 | note | Reference: VicRoads Section 610 June 2019
cf22a2aa-b08c-5c1c-b471-2eef654c93d6 | note | 1.2 Non Dependent
66d21da9-2a94-5bbf-9ef3-29a41d3dfc30 | note | Reference: VicRoads Section 630 October 2013
eb33115b-e1ec-5cd6-b45a-d25bb63117f3 | note | 1.3 Non Dependent
fdc51747-4771-518e-8d86-26e88fd1144d | note | Reference: VicRoads Section 631 February 2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Structural Steel Components
5da01cfd-4a57-5316-99bb-b799b98a1d06 | note | REFERENCE: IFC Drawings MRPA Quality Management Plan
a45098ee-1523-532d-a2c5-3364046d9792 | note | – – – – – – – – – – – – – – – – –
57a25a3f-ab4f-5b1d-a5a9-5828a42bb630 | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
02ab29ef-64e3-53f4-b091-3201adb9f768 | note | Typically this consists of but not limited to:
fb891e4d-df6a-5282-9bca-7a2e3d218a72 | note | i. Certificate of Compliance
9a9f010d-2e3e-5fb1-a1fc-ae0ca790a9ad | note | ii. Completed ITP
b5b24806-89cd-5f47-9226-5671de05e829 | note | iii. Weld Procedure Specifications
ad31be04-c819-5593-b992-2a929e3a6cf2 | note | iv. Weld Procedure Qualifications
57c06f3e-2511-5b4e-a0e6-b6623e7c07d8 | note | v. Welder Qualifications
f61f8fa7-2391-5510-9b5b-25037c14bce6 | note | vi. Material Certificates and traceability
f17a6951-47f1-56e6-b2ce-ba82d59a25c6 | note | vii. Quality Assurance check sheets
ed46e376-94dd-5208-94b2-16aed262bb8d | note | viii. Welding Consumable batch certificates
f6d9b5fd-2ac1-59db-96b4-217f27fb3156 | note | ix. Coating certificate(s)
d696a7a5-b985-56fe-acbb-187e6caf0eb2 | note | x. Non-destructive Testing (NDT) Reports
bf6b97ce-aae7-5d66-ac08-7c1490d3f4bc | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
eb604379-031b-54c9-9bfc-96537d16cdba | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
ae1a3e93-0e30-51ba-96d3-9dd4e6992ce8 | textbox | Enter: Teambinder Material Approval number
d980874c-6186-50c9-b698-fcd3c14be96c | note | – – – – – – – – – – – – – – – – –
adac66c1-8e36-5540-938c-714eb1f5314b | note | METHOD: Document Review
c5fc8f96-b290-58ad-805c-772fee83c0ee | note | – – – – – – – – – – – – – – – – –
2a2de5e9-045a-5cfd-8a03-d7583a3eb7cf | note | FREQUENCY: Each component
70c60af8-779e-5602-9c98-da6e59393b71 | note | – – – – – – – – – – – – – – – – –
cdc28a7a-17f9-542a-962d-4ccee639e95d | note | CATEGORY: IP
09cfb55f-68b7-52ad-a8de-364fbd663411 | note | – – – – – – – – – – – – – – – – –
e60efae5-05ae-55e2-a491-f71b2784f62a | note | RESPONSIBILITY: PE/SE/SPE
bd498147-864d-5929-8015-fdc0b54648fd | note | – – – – – – – – – – – – – – – – –
1ac2e6a9-d654-5422-a9c9-07ac1bce4031 | note | VERIFYING DOCUMENTS: This ITP
14b0bf87-c090-5393-b15e-8938637157f7 | date | Date Completed:
| checkpoint | 2.2 Fasteners
4c88220b-1ab2-5dc5-ac12-d4f497af1a1e | note | REFERENCE: 630.20 IFC Drawing
ebe6eaab-e02a-5e1a-9799-f0ee02ad5aef | note | – – – – – – – – – – – – – – – – –
73368496-99ae-56fd-aaf5-984f37d8ed06 | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
a345490e-2a97-50f1-9102-e8968270dab4 | textbox | Enter: Teambinder Material Approval number
4219fc0f-2a26-5668-8a54-7cf940d78dc5 | note | – – – – – – – – – – – – – – – – –
09205496-0219-54db-bbb2-655ddb08f98c | note | METHOD: Document review
852b66bd-bf6e-58a4-aac0-3c75c0f73f92 | note | – – – – – – – – – – – – – – – – –
3f76b6f7-899f-5aa4-9dda-285fc26bd720 | note | FREQUENCY: Where applicable
849f90d3-bd8a-5957-8521-b6827d01ccc5 | note | – – – – – – – – – – – – – – – – –
c23d3fae-dc4e-5d91-80a0-92dc75c4a1dd | note | CATEGORY: IP
c268397a-2cd4-5785-91d8-21ead9182d46 | note | – – – – – – – – – – – – – – – – –
1491fb7d-d6f8-5a03-b038-3e4bdc5d4584 | note | RESPONSIBILITY: PE/Nominated Authority
df3cc2f0-e6e3-50e4-a6ce-eb62f691f61b | note | – – – – – – – – – – – – – – – – –
bc78e381-8537-5341-b0c3-0c20485db16c | note | VERIFYING DOCUMENTS:
5c48cf62-128c-5eeb-b6f6-61d8e7e469af | date | Date Completed:
| checkpoint | 2.2 Base Plate Structural Grout or Mortar
1cff9767-e358-559e-b761-75e3c306f6b9 | note | REFERENCE: IFC Drawings 610.33
b80274ff-2fbd-5c3e-a422-131705bcc136 | note | – – – – – – – – – – – – – – – – –
3fd1eb78-2039-5d81-b612-6a93e9d96c10 | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
10103e57-9985-5858-991c-db1a4dcbb754 | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
9fb799d6-01f7-5ade-b949-00de7902b6ba | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
f26fea5f-270c-5661-99d3-515de07479dc | note | iii. have a flowable consistency
ee21d4cc-ac12-5ee7-b370-fb880e342c7e | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
d6f51d63-f4ae-5ca0-956c-71f194108444 | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
c339732e-ce0c-5ae0-bb01-3dc8462c0409 | textbox | Enter: Teambinder Material Approval number
4392c0f8-ffbf-5eab-9973-ab1381058458 | note | – – – – – – – – – – – – – – – – –
c7b34fa1-fe4a-5868-8d90-07ac8dbcdde1 | note | METHOD: Document Review
847d816b-a6fe-55c1-9d12-5d05c034a3ab | note | – – – – – – – – – – – – – – – – –
f708b59e-7a9c-56cc-8a75-b69b8c60c9f0 | note | FREQUENCY: Once, for each product, prior to placement of product
2ace9b33-9ec3-5e3f-89f6-b390a15fac42 | note | – – – – – – – – – – – – – – – – –
eb46b472-d2f9-54c6-a70a-dfd1e9c6fd22 | note | CATEGORY: HP
c3771dae-a2cd-5b05-bf8f-e27ffb11c935 | note | – – – – – – – – – – – – – – – – –
c754d497-73a5-5d7c-b780-ea8c0127c8f7 | note | RESPONSIBILITY: Nominated Authority
0a64b587-0ad8-51e8-8899-0df4b5b88dba | note | – – – – – – – – – – – – – – – – –
0523bcea-7da4-53de-8f2d-1c8b4caa2df5 | note | VERIFYING DOCUMENTS: This ITP
9989d4bb-5be3-5c2b-aa27-4701b21856f6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Curing Compound
e0b8daef-0d47-507a-9fc6-63c4d270d7ed | note | REFERENCE: 610.23 (d)
8f166148-a550-59ae-ab31-20863a137956 | note | – – – – – – – – – – – – – – – – –
3b8a3de1-365a-5210-ae65-805ebc64bb02 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
7b9eeccb-b445-52dd-8abe-a3a135e84ca3 | note | Note: This may be the same product used for the concrete curing
b8dd58c6-26ee-5eaf-bb21-d38a1b14e117 | textbox | Enter: Teambinder Material Approval number
7cd3943a-ed6c-5ecc-b7f9-3b464044f880 | note | – – – – – – – – – – – – – – – – –
431c98d1-24cd-57ef-9345-27c1e07db657 | note | METHOD: Document Review
335f5b59-c08d-583c-8d50-a5e64c5b7f8c | note | – – – – – – – – – – – – – – – – –
fc63d64d-b4f0-55c9-ae2f-82bd5ed5b6e4 | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
d4083b26-5e90-52c2-a34f-db0ecba6ec92 | note | – – – – – – – – – – – – – – – – –
47ccdd45-e9ac-5050-880b-49a06b728af7 | note | CATEGORY: HP
08006a15-378a-569f-976b-5e5f0bd20901 | note | – – – – – – – – – – – – – – – – –
7babeed3-67f0-5c9d-907f-c513d9978e13 | note | RESPONSIBILITY: Nominated Authority
7dbe4a97-82d8-5b89-9af2-8f944ad7ccfa | note | – – – – – – – – – – – – – – – – –
600f32c6-f5d0-5169-8e18-c1029408a933 | note | VERIFYING DOCUMENTS: This ITP
28561b99-bebc-58dc-b80f-125d0caabd16 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures
| checkpoint | 3.1 Installation Methodology & Works Method Statement
5497412b-2efd-557f-88e6-1e58a9afad7f | note | REFERENCE: 630.20 AS5131 Clause 11.2.3
2da0ee51-cc38-52eb-b00c-d45f19864cec | note | – – – – – – – – – – – – – – – – –
4a4ec67b-61c6-56bf-baec-20a44cbd5091 | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
606b2aee-59e4-596c-938b-6af409b9e34a | note | ○ Transported to site;
c5ecd785-2d44-5889-9e7a-456c485d67b9 | note | ○ Handled on site;
c039f3fd-a80f-51f5-b8dd-43766974e8fa | note | ○ Installation Procedure (subcontracor ITP's);
f01ba61e-b383-55a3-980a-87d5893f7b46 | note | Attach: Subcontractor ITP
5940587c-44be-5867-9857-f6c9163bde8b | textbox | Enter: Teambinder Approval number
56148cde-ab55-550f-9dac-c7a15d09aed2 | note | – – – – – – – – – – – – – – – – –
a02af8a3-eefa-5c3e-a870-078685cef460 | note | METHOD: Document Review
047300e1-39fd-57cf-aaf3-d542c57cd4a0 | note | – – – – – – – – – – – – – – – – –
f28f739b-85df-5343-bd2a-d2811c0997da | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
bfe3489e-751e-5d1b-9c07-a0dfa909742e | note | – – – – – – – – – – – – – – – – –
e76dcffa-0ec3-5b68-aac1-c15eef40041f | note | CATEGORY: HP
74c4ba48-bba7-50c6-a69d-97f25daa9f00 | note | – – – – – – – – – – – – – – – – –
b5295e24-9860-5854-b110-6509c73928db | note | RESPONSIBILITY: PE/Nominated Authority
c54865ef-4034-5bfc-9b45-7cb00834e491 | note | – – – – – – – – – – – – – – – – –
982c8805-ba04-5d8e-b192-15232f0f5f21 | note | VERIFYING DOCUMENTS: Subcontractor ITP, ConQA Hold Point Release
450bb1d2-a9f3-5816-b74d-15ff1e0e3256 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-installation Activities
| checkpoint | 4.1 IFC Drawings
355c7835-7893-5bfb-b825-602e2c7a8d0d | note | REFERENCE: MRPA Quality Management Plan
477c406f-ba43-5370-92ef-e400f34edb3a | note | – – – – – – – – – – – – – – – – –
061c7e32-c8e3-59b5-b85a-f3f9309536bc | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b814fd24-2db5-5da8-aa0c-7f05b7909b97 | note | – – – – – – – – – – – – – – – – –
e9ef90e3-b081-55ec-b505-6bde8e1c8cec | note | METHOD: Document Review
e3570541-d9ac-5429-99fc-b8c63b6e9f42 | note | – – – – – – – – – – – – – – – – –
8dc1183b-19b6-5eb9-a201-25792e144a20 | note | FREQUENCY: Prior to starting Works and at regular intervals
80b3c85b-aca0-55ea-a304-9feedab2db27 | note | – – – – – – – – – – – – – – – – –
5219b563-8480-5070-b4f7-240d17f4e758 | note | CATEGORY: HP*
8ebaa06d-e094-5e73-9a45-96a973611853 | note | – – – – – – – – – – – – – – – – –
a8f02d87-fcec-5901-8a93-56d26fca5b55 | note | RESPONSIBILITY: All
83d41b60-9d5b-5e1b-87c6-70b9a4a4c6da | note | – – – – – – – – – – – – – – – – –
7fdc3c26-1fa1-549a-81eb-17a4bc21dd77 | note | VERIFYING DOCUMENTS: This ITP
e0498479-b963-59c9-b30e-dedc107b002a | date | Date Completed:
| checkpoint | 4.2 Materials Inspection
435a5b5d-08f9-5f4c-a39b-3d4a5262c256 | note | REFERENCE: IFC Drawings VR 630
78b6be4c-3c95-5821-b7e2-9f4628f56564 | note | – – – – – – – – – – – – – – – – –
34a8cd84-dbe9-543a-b02f-c42e3e19418b | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
71e9836f-a54a-518a-9842-92855f52006e | note | – – – – – – – – – – – – – – – – –
b456c106-57cd-58a9-b886-3ae249619f30 | note | METHOD: Visual
068107f0-69b1-5040-a226-cb432938f14d | note | – – – – – – – – – – – – – – – – –
954e7f54-c41d-5fab-9784-846d28e40365 | note | FREQUENCY: Each component
31ac532c-1027-56e4-8787-0546c401c411 | note | – – – – – – – – – – – – – – – – –
3ecfe6f6-290f-5b4f-a31b-2e1109956ff1 | note | CATEGORY: IP
a7020a27-0dd2-5c8e-bb44-a1e73997ee4a | note | – – – – – – – – – – – – – – – – –
d1709cff-95d8-533a-aa3f-5b1c660c8644 | note | RESPONSIBILITY: SE/PE/SPE
a06a3ccc-0d1d-5312-a591-f3d1eef4cb0e | note | – – – – – – – – – – – – – – – – –
36efe8b7-15d9-5e06-ad1a-0c0e1efc3657 | note | VERIFYING DOCUMENTS: This ITP
000d1e3c-6916-5d44-9444-9b18e652d75d | date | Date Completed:
| checkpoint | 4.3 Materials Inspection
02c74bab-7e03-5aee-9440-b63f38bcf521 | note | REFERENCE: IFC Drawings VR 630
af5863bd-8ba4-54a9-b0b4-73c9bf69c2f3 | note | – – – – – – – – – – – – – – – – –
2c084065-aa8e-5bdd-aeca-9f0492668522 | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
0f051f49-9307-50c5-8b16-fd16b70cc302 | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
ecba117d-512d-5fa2-85bd-c9ac8a5b7204 | note | – – – – – – – – – – – – – – – – –
12da203d-582d-51e2-b779-2c801185611b | note | METHOD: Visual
427edb7c-e4c1-5481-ba1e-732bc0ce6052 | note | – – – – – – – – – – – – – – – – –
eafd6caa-242f-5707-8baf-2f11671dff1b | note | FREQUENCY: Each component
d2131386-cf63-5ca0-9eb3-00ef0984a41a | note | – – – – – – – – – – – – – – – – –
b21fa651-b8e8-504c-8889-dfeaee343413 | note | CATEGORY: IP
33fed794-a37d-57a3-b565-950875e5e173 | note | – – – – – – – – – – – – – – – – –
a656d96c-f426-5a30-9f54-58a7721177de | note | RESPONSIBILITY: SE/PE/SPE
b95bea7c-ae11-5aa5-81f2-495541f5d62a | note | – – – – – – – – – – – – – – – – –
8b3479d9-ff0a-56a0-93f2-3c7ffc1c7b8d | note | VERIFYING DOCUMENTS: This ITP
2a64135d-8455-5f5e-aad7-ca9e1ecb54b7 | date | Date Completed:
| checkpoint | 4.4 Materials Inspection
700bf814-5389-58a8-b62c-791073b59790 | note | REFERENCE: IFC Drawings VR 631
d2253a71-75c8-5a38-8ee5-8d23fef0e6dd | note | – – – – – – – – – – – – – – – – –
678bce47-ccd1-5bae-9c56-2ea8ec4d6767 | note | ACCEPTANCE CRITERIA: Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
c442c009-8c73-550d-9a82-7ef963a1108a | note | – – – – – – – – – – – – – – – – –
c9814072-60b7-5c6a-be60-57198c9bb88a | note | METHOD: Visual
0f8b44cc-d5e6-563c-a650-38211a1ecfec | note | – – – – – – – – – – – – – – – – –
fe2ea460-aa86-546a-aece-5a7d71561d58 | note | FREQUENCY: Each component
3c8faadc-495d-5e48-8a29-f91dde124ba3 | note | – – – – – – – – – – – – – – – – –
c179d682-2bc1-50d2-a88d-2ff7c93b7744 | note | CATEGORY: IP
f1c08457-6d1f-5357-9170-52860e35c4ec | note | – – – – – – – – – – – – – – – – –
9406a37c-6d1a-50ec-b0aa-0a4f381200a9 | note | RESPONSIBILITY: SE/PE/SPE
cfc34b7b-b256-5d6c-9954-741e5badcc59 | note | – – – – – – – – – – – – – – – – –
e1712359-4248-5245-8931-119ccd7b751d | note | VERIFYING DOCUMENTS: This ITP
b77d32c3-f9e8-559a-a068-bc2fa40138b1 | date | Date Completed:
| checkpoint | 4.5 Materials Inspection
10a05708-9754-54ed-919d-a5800774ac76 | note | REFERENCE: IFC Drawings VR 631
50538c78-9f75-5824-905b-9c7c2bb7f556 | note | – – – – – – – – – – – – – – – – –
65d2f768-afb8-580b-a8e8-146598b5a236 | note | ACCEPTANCE CRITERIA: Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
bad66442-f130-5321-825d-d661f92c0d17 | note | – – – – – – – – – – – – – – – – –
c8fad7c7-9880-5d88-abb3-e6a087f10398 | note | METHOD: Visual
eae84acc-eec8-578e-ac88-5f325f8e3486 | note | – – – – – – – – – – – – – – – – –
2207ba82-36fc-59b6-a01d-73a4327014c0 | note | FREQUENCY: Each component
5d0e708a-40c0-51fb-9fd4-6b20c9305696 | note | – – – – – – – – – – – – – – – – –
c4f575a3-837a-5ab5-85fc-2c77b16b61ed | note | CATEGORY: IP
cde6012b-ed4d-5ffe-b2f4-64fe47723f06 | note | – – – – – – – – – – – – – – – – –
ecfdfd5f-5727-5a22-bd6d-a8847a8bcb9b | note | RESPONSIBILITY: SE/PE/SPE
2c2d8375-e222-56ae-a032-d1d0850dcf8e | note | – – – – – – – – – – – – – – – – –
a913ccfe-d0b5-5624-8d1e-b71fa9c21eff | note | VERIFYING DOCUMENTS: This ITP
3f37f985-af7f-5fa8-abbf-c27e2ac8c030 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Bearing / Mounting Surface Preparation
7abf6b15-5c55-5ca5-ab6c-a515ec920009 | note | REFERENCE: IFC Drawings, Product TDS
22391361-9c17-5927-921a-4e221df2b17d | note | – – – – – – – – – – – – – – – – –
9ac418ec-3adb-5f60-b803-32886ad115e8 | note | ACCEPTANCE CRITERIA: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts
4061ed76-be6b-5d45-9787-a7150d7a9e00 | note | – – – – – – – – – – – – – – – – –
307f142f-1616-5e29-a1dd-67e93d9d42c9 | note | METHOD: Visual
c70781d3-f3b3-5da7-b1e1-82875529a2ff | note | – – – – – – – – – – – – – – – – –
85faa7d5-7c1f-5d1c-9c1f-78dc89474075 | note | FREQUENCY: Where applicable, each installation location
14fa5f4e-c805-5887-82cc-4fd0e07d7b03 | note | – – – – – – – – – – – – – – – – –
49d87b66-6c6f-5f32-b6f5-050d97c59858 | note | CATEGORY: IP
a21c0753-82a5-5e0c-948e-a25e4fe742d7 | note | – – – – – – – – – – – – – – – – –
a5320812-6a4f-5093-87a0-c5bb01d1e73e | note | RESPONSIBILITY: SE/PE/SPE
8aa617e8-dc32-58da-909a-45d111fcb476 | note | – – – – – – – – – – – – – – – – –
eabe59ee-216b-5d84-8e78-fd18041091b0 | note | VERIFYING DOCUMENTS: This ITP
438d458f-739f-51b9-b9ef-f67bfba67f3b | date | Date Completed:
| checkpoint | 5.2 Structural Steel Handling
38b93087-d76e-5984-83ee-0b55de2a75db | note | REFERENCE: 630.09, 631.14
d87abdd8-a2fa-590c-a083-f9973461e9a0 | note | – – – – – – – – – – – – – – – – –
dfd47fdb-09d6-5349-9cde-4400a0aa17e3 | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
5414012d-9265-5c1e-9259-775211ddf575 | note | – – – – – – – – – – – – – – – – –
55638e3f-0ac7-51f3-a971-30fc87289ee8 | note | METHOD: Visual
9c3e2639-9621-5bfc-b42e-c30e1c75b64c | note | – – – – – – – – – – – – – – – – –
e450aa02-da11-5b30-9a24-ed24b9fcb5d2 | note | FREQUENCY: Each component
67ef74fc-de57-5777-933c-7a46ab1a42e2 | note | – – – – – – – – – – – – – – – – –
6d4a2a9d-80e9-5df3-9615-ddcd6a068c76 | note | CATEGORY: IP
586fe7fa-02be-56fe-9e4a-d01e9f34af26 | note | – – – – – – – – – – – – – – – – –
422f1813-8e67-540e-969a-07755619b284 | note | RESPONSIBILITY: SE/PE/SPE
0facfe05-a886-50f2-b973-ca6cdd9d35b7 | note | – – – – – – – – – – – – – – – – –
97da19df-1813-5148-af38-bea19a58588c | note | VERIFYING DOCUMENTS: This ITP
1596e7e5-8a23-5da2-ba22-17edcdea0e11 | date | Date Completed:
| checkpoint | 5.3 Structural Steel Erection
ac272e6c-f552-5f22-8eca-9fe76112e94d | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
06a799eb-49f8-55d5-8f35-2d34caf971e4 | note | – – – – – – – – – – – – – – – – –
c0a28742-65a3-51c9-8ff8-7aff75b38ceb | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
719bb433-b88e-541d-9aa3-c92a6bc3b837 | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
b6b9873a-43cc-538e-905d-c63802e16a38 | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
0a6b8f39-e301-5fab-8119-170b50d19fac | note | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
ce619503-fb48-5ccb-95c3-e3434e4f6d7f | note | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
19b52686-7357-5e40-8310-35b42e5ee471 | note | – – – – – – – – – – – – – – – – –
0106ea88-6054-57f2-aa5c-e24d3030d209 | note | METHOD: Measure, Visual
975b0a05-0424-50de-b676-77173130dbc2 | note | – – – – – – – – – – – – – – – – –
223cff2c-2580-50ff-9c1a-dcc153b7c3bf | note | FREQUENCY: Each component
c8cffc54-fcec-501b-bd6d-48fedca6c2eb | note | – – – – – – – – – – – – – – – – –
a5067551-d83c-5b71-981a-c8b6a6ceffa9 | note | CATEGORY: IP
d063cbea-f2c0-55bb-9836-95d8f6ee7145 | note | – – – – – – – – – – – – – – – – –
20e4ec96-acd8-5f7f-8267-d61dfbd47354 | note | RESPONSIBILITY: SE/PE/SPE
15159d12-d9c9-5f23-8747-e32cdce016c8 | note | – – – – – – – – – – – – – – – – –
34e5826d-53f5-5a03-b60f-0dee34ab5d16 | note | VERIFYING DOCUMENTS: This ITP
bf93df97-843d-53b2-9e89-a52456c0d538 | date | Date Completed:
| checkpoint | 5.4 Fastener Tightening - Snug Tight Condition
87474308-5f3e-5e7c-80c7-fd148e96800e | note | REFERENCE: IFC Drawings VR 630
2319a018-541a-5799-bf04-82f761ec73e8 | note | – – – – – – – – – – – – – – – – –
999bc4a7-86ff-5d9d-8d1c-28959105f770 | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
7bbebd75-b213-5c09-b5c5-3a545d55d763 | note | For posts base plates, the arrangement is to be (from the base plate):
443142cd-85e0-5bba-80f0-8200fcbe3194 | note | – Base Plate
cc417c99-b00f-5cc9-8a51-0e441305a392 | note | – Washer as specified
adfffd4a-f905-5d08-b519-350ee5a1a51b | note | – Lock Nut as specified
36db655b-8186-5db2-86b1-36c2d605920c | note | – Nut
60c3baa7-6b1c-5a69-a0c2-a2141d261677 | note | – Bolt protrusion (1 clear tread)
3d28d322-0941-5d09-94f6-80315587bd01 | note | – – – – – – – – – – – – – – – – –
3ea8c8e0-6782-50bc-9522-c777027046c0 | note | METHOD: Visual
cb0573b3-ac09-5fb8-a192-1636183243a5 | note | – – – – – – – – – – – – – – – – –
23074794-ef30-5a05-8ed2-ccdfba09b7bd | note | FREQUENCY: Where applicable, each bolted connection
10a4dd43-56b4-5450-b291-b33335f4ce03 | note | – – – – – – – – – – – – – – – – –
864eae73-d6b5-5e9e-80f6-cddf5fdbc0ca | note | CATEGORY: IP
d4b55161-6356-518c-a447-47d777f96744 | note | – – – – – – – – – – – – – – – – –
460a4458-2af1-559a-8f18-c4d7bdac1df7 | note | RESPONSIBILITY: SE/PE/SPE
19f6d0d8-ecf3-5fd6-8aeb-2d25ebc7e34c | note | – – – – – – – – – – – – – – – – –
24b23190-0b57-5ad3-8901-57173c5e83e3 | note | VERIFYING DOCUMENTS: This ITP
f3c184c6-9d06-5548-9f0e-50794544dca7 | date | Date Completed:
| checkpoint | 5.5 Fastener Tightening - Snug Tight Condition
d2b57c7a-df65-51cd-ad8b-b5c88da482d9 | note | REFERENCE: IFC Drawings VR 630
e2462959-1380-52ea-b1ed-ed37eb7a601c | note | – – – – – – – – – – – – – – – – –
6bf5342f-21f4-5ef8-94e4-430c0d3a93e9 | note | ACCEPTANCE CRITERIA: Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter.
c68f65f1-a425-555c-b14c-496cdb9800c5 | note | ○ Tapered washers shall be positioned if specified.
a7908a75-5ab0-5e73-b0be-373569c68766 | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
176e7a98-1db5-5ca6-998c-19b43f7c895c | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
40e3f500-eb74-5e61-9852-2213bb467a83 | note | – – – – – – – – – – – – – – – – –
880fa3fc-76e3-5c9c-8e93-183df15f2dd7 | note | METHOD: Measure, Visual
dc53047c-d9c0-5d31-9a02-5aa439e069bd | note | – – – – – – – – – – – – – – – – –
89d194c5-0473-51fb-abbd-3914763cc65f | note | FREQUENCY: Where applicable, each bolted connection
2f07fb7c-3c68-5f32-9d36-398f8e1a7d3d | note | – – – – – – – – – – – – – – – – –
83edf216-e8eb-539d-afa7-4b01fb28f9d5 | note | CATEGORY: IP
f9c0861f-12dd-552f-b26b-8ae9a2378dc2 | note | – – – – – – – – – – – – – – – – –
072df4a5-5003-5041-813e-193890ea29ed | note | RESPONSIBILITY: SE/PE/SPE
9a6ba226-0053-5e7e-9a4a-c7eb6a4a2b81 | note | – – – – – – – – – – – – – – – – –
413bff5c-f1e1-559a-a86b-dc7e6d29e83a | note | VERIFYING DOCUMENTS: This ITP
bd0e4285-2524-5894-9ca5-4d553a562a31 | date | Date Completed:
| checkpoint | 5.6 Survey Conformance
6cf960c3-c5cd-5c16-97d4-3fa1e34ac074 | note | REFERENCE: IFC Drawings AS4100 Clause 15.3.1 - 7, AS5131 Appendix F, Table F3
1d2b066c-4f48-5a56-a5c5-bfa8bbd32340 | note | – – – – – – – – – – – – – – – – –
e5c7ada4-a4be-5d2c-91f6-8dbf7681c6ac | note | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
b24f8e25-f8ec-5a40-9456-fd3baaa96f73 | note | ○ Departure from RL = ±10mm
84054f75-37bc-59ca-ba29-581ba51cbaa7 | note | ○ Departure from plan position = ±6mm
99d43e20-ce47-5ff3-8172-5bd59eca20e4 | note | ○ Departure from alignment = ±6mm
4c23b9ba-9ba4-5406-a30f-61e9efabeda8 | note | ○ Irregularities in alignment = 25mm in 30m
b7d07182-6382-5742-9de0-c48861635508 | note | ○ Projection of bolt = +25mm, -5mm
3a4b9e9f-105b-5117-8ee7-6f24587e9c0f | note | ○ Location of beam = ±3mm
08457c39-6cdc-54e4-8e6c-0bc3df719a93 | note | ○ Location of column = height/500
5a85e06a-9575-5af1-8b03-48dde4d16086 | note | – – – – – – – – – – – – – – – – –
7dba61e1-af16-51e8-85f0-f1dc5f6ceabf | note | METHOD: Measure, Visual
efc9ce97-c90c-58f6-9ffc-44fc197b3ddc | note | – – – – – – – – – – – – – – – – –
8e13cdf5-7372-5751-a1c0-017b5b985b20 | note | FREQUENCY: Each element
2d85e5ca-63bc-55ff-8d21-b5e03c52568f | note | – – – – – – – – – – – – – – – – –
c69c8269-d6bc-577e-9bcf-e6ef93decab6 | note | CATEGORY: HP*
cf79ba19-eb4a-5ead-94a1-cee8ab74fd91 | note | – – – – – – – – – – – – – – – – –
2cffe64d-2e17-56e9-a2d2-27ae74436f1a | note | RESPONSIBILITY: PE/Surveyour
86e79f55-8c5e-59e3-b987-2e19f6979ebf | note | – – – – – – – – – – – – – – – – –
5ffa5c1c-8ef3-5400-8a40-920a0a7a686c | note | VERIFYING DOCUMENTS: This ITP
8f1cfd19-559d-5842-8395-c70e85f681c7 | date | Date Completed:
| checkpoint | 5.7 Base Plate Formwork Construction & Placement
23562188-8a01-5f14-a286-854e695fe8c1 | note | REFERENCE: IFC Drawings
c86f1183-14e1-536a-951b-57b5406a8136 | note | – – – – – – – – – – – – – – – – –
6e43eb63-d36f-5f05-a439-de9981c40307 | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
04b96603-a775-5a6c-9756-1b519ef2779a | note | ○ Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
b57117d5-fed1-589e-9491-87b3efe2ac50 | note | – – – – – – – – – – – – – – – – –
53802d49-709e-57e8-94da-7b87940dfb99 | note | METHOD: Measure, Visual
d67d49e9-284b-53f6-8381-813c4b6c9f14 | note | – – – – – – – – – – – – – – – – –
5c2b9738-b606-56d9-96ca-9764969e504e | note | FREQUENCY: Each post location
d1719b50-1a7a-5ca5-a1d1-265af9af3b2b | note | – – – – – – – – – – – – – – – – –
83cf1e25-a6e6-5d41-a4c8-40369528b80d | note | CATEGORY: IP
d9a9007c-23e2-5ec0-b285-70edba42f8b4 | note | – – – – – – – – – – – – – – – – –
33f61635-5a46-53f2-88c0-0d950dfa3cb2 | note | RESPONSIBILITY: SE/PE/SPE
36726093-081d-5a11-bd9e-b17e5441fcf6 | note | – – – – – – – – – – – – – – – – –
4f862518-15ae-5d53-a690-e36c43ca03a7 | note | VERIFYING DOCUMENTS: This ITP
9f4328dd-b797-5462-ae0d-477371f39a51 | date | Date Completed:
| checkpoint | 5.8 Pre-soaking Concrete Surface
bd833f7d-71d2-5fdd-807c-f3bb24c29203 | note | REFERENCE: Product TDS
61302fe3-c258-5284-9caa-eee7e3d278c5 | note | – – – – – – – – – – – – – – – – –
675a1955-9eca-5fe3-89a8-3b5cea87d5dd | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
f187aa99-c384-51e2-b93d-c8bdf6cfc602 | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
b09c61be-14a2-5734-98d5-2971e16df349 | note | – – – – – – – – – – – – – – – – –
52941c6c-8654-5ef7-897b-0f12cc9d6e81 | note | METHOD: Visual
050e5f2a-efbd-59e1-a690-cfa917b4e436 | note | – – – – – – – – – – – – – – – – –
7f22f79e-95a0-57d1-afd2-e58759ca5840 | note | FREQUENCY: Each post location
e1c73ffe-4576-5a70-a7f9-180bd31ec9d8 | note | – – – – – – – – – – – – – – – – –
824f3ad1-5912-5b46-9920-164a2ffe73a9 | note | CATEGORY: IP
32d8285c-d535-51cc-b704-aba28286c7a0 | note | – – – – – – – – – – – – – – – – –
8260f04e-bb42-5666-b785-0aa4b8fb0633 | note | RESPONSIBILITY: SE/PE/SPE
f17097b9-6e9f-5dc5-bfd9-8bdeca41d275 | note | – – – – – – – – – – – – – – – – –
59e1c9c9-1e34-5553-97e5-320430f55b6b | note | VERIFYING DOCUMENTS: This ITP
6daf59c0-d113-5334-8290-6ae2fe3ced66 | date | Date Completed:
| checkpoint | 5.9 Weather Conditions
e0a57724-85c8-51e7-a4b8-ed076c7e4396 | note | REFERENCE: 610.17 Table 610.171
9713ed69-2def-51d7-97bb-311ec32c12f8 | note | – – – – – – – – – – – – – – – – –
efb52f29-8a8d-5535-87a1-4f1286fc0584 | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
0d51e4e0-6cd3-5bb3-8b8f-ab5421fe4361 | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
052aa883-8061-5e4e-b3c9-4d3e361da5de | note | Record: Required information on the Grout Pour Record.
be86540a-56e4-5ddf-a461-43304c302c29 | note | – – – – – – – – – – – – – – – – –
1fbe3851-f410-5c72-af66-db54aa112e2b | note | METHOD: Measure, Visual
3f7618c7-f990-593d-970d-167091f6e3f8 | note | – – – – – – – – – – – – – – – – –
24e32d4a-3c63-50b6-89aa-36b189a868cc | note | FREQUENCY: Each lot
2707b480-3089-5739-8d4f-c156663b801d | note | – – – – – – – – – – – – – – – – –
3f83f359-b911-51b8-9fab-0cd7f42dca52 | note | CATEGORY: IP
84770239-a699-55f1-8ed1-025e0a6c968e | note | – – – – – – – – – – – – – – – – –
5495a49e-2f8f-5df2-95de-4165f7d954cf | note | RESPONSIBILITY: Foreman, SE/PE/SPE
eb3ccae6-3391-5bc1-b7dc-ed620dec46e0 | note | – – – – – – – – – – – – – – – – –
8edd06b6-a6c4-59f7-9821-19f9f8e1a206 | note | VERIFYING DOCUMENTS: This ITP
5e379abc-c40e-5c1b-b162-7cbdb26abe7c | date | Date Completed:
| checkpoint | 5.1 Mixing Product
986d044b-0f55-545f-88b5-fbe2b8ac0845 | note | REFERENCE: Product TDS 610.28
b1cfbae4-6370-5be4-bc49-9407dc9e3078 | note | – – – – – – – – – – – – – – – – –
c5d4f277-05c1-5dec-8b77-f9845ad4757a | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
6392e226-1a6e-54ca-9c51-2157efd95430 | note | ○ Only whole bags to be mixed with potable water.
f64a80b1-7b12-538a-ba7c-fdc886a7b3e0 | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
6a01520b-ea05-567f-a50c-c24a409d776a | note | ○ Product poured into the mixer slowly.
86876427-c608-56fd-a7e1-2f7b91640004 | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
ac616716-b4f6-53f0-ad70-804849ec3c49 | textbox | Enter: Required information on the Grout Pour Record.
c5759e68-2298-5caa-a299-649e83d3021d | note | – – – – – – – – – – – – – – – – –
71f26aea-d6d5-5595-a1a4-8c1c115c5bed | note | METHOD: Measure, Visual
43e7443f-b737-5e2e-b684-731152b0fb71 | note | – – – – – – – – – – – – – – – – –
b2c15f44-4e3b-586d-841a-5eee7cf54062 | note | FREQUENCY: Each batch
feb002ea-28e0-5ad6-bbd3-e63e014f8098 | note | – – – – – – – – – – – – – – – – –
3665e4ab-d3fd-5536-b64c-a3d85967a3d7 | note | CATEGORY: IP
139848fe-80ed-58fe-aaf9-fd75039972b7 | note | – – – – – – – – – – – – – – – – –
c5ae8533-40c7-5db7-82cd-e5210dc0eca5 | note | RESPONSIBILITY: SE/PE/SPE
77c373a0-7b61-54c9-9008-79b39dc93db3 | note | – – – – – – – – – – – – – – – – –
83339b52-a428-551f-a060-c289b0891269 | note | VERIFYING DOCUMENTS: This ITP
ac6b606f-4c81-5633-99fd-077b1c2534fa | date | Date Completed:
| checkpoint | 5.11 Product Testing - Compressive Strength Cubes
9c7724d6-7477-58c8-a42c-df25edc1e4c0 | note | REFERENCE: 610.28, 610.33
3b88b0f2-2bc0-5777-a0c5-8ecbb576f1cf | note | – – – – – – – – – – – – – – – – –
56b7c1ff-ece0-5a6e-9146-b1eb0b8f62ff | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
d02147aa-ce09-5149-99fa-e6012f4bb084 | note | ○ Testing is be in accordance with the following frequencies:
c6abf53b-69c5-58d5-a403-ae96e64e4cb3 | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
974c6229-0cb3-5e85-bd45-def08ed4b941 | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
f8415fff-c3e2-5328-b9d3-6bd3bb23402f | textbox | Enter: Required information on the Grout Pour Record.
12d1f69e-3bb9-5cbf-b27f-99f6dc33dce7 | note | – – – – – – – – – – – – – – – – –
41f21175-cc2e-54b9-b091-a4165c11c4d2 | note | METHOD: Test
69de4133-01ef-55a2-8bdd-235771a6fc76 | note | – – – – – – – – – – – – – – – – –
6df9ad82-ca1f-58e3-a65e-9c803406229a | note | FREQUENCY: Each lot
f1b727e2-7974-5bdd-a6fb-a4029a6ffe1c | note | – – – – – – – – – – – – – – – – –
aa62d24b-fd88-5f08-97c9-f3edf5190a10 | note | CATEGORY: IP
28c05559-7593-5fe0-a4db-50b39db0e3c2 | note | – – – – – – – – – – – – – – – – –
0dc251cf-e8bb-5b87-b26c-2dc397fab66e | note | RESPONSIBILITY: Tester, SE/PE/SPE
9182e25b-2e42-5731-8a0f-707521f92f0c | note | – – – – – – – – – – – – – – – – –
e769b8cf-036f-52c0-858b-c1874fb88098 | note | VERIFYING DOCUMENTS: This ITP
817c8a5b-1cce-5434-bc7e-b3a7c2c0687e | date | Date Completed:
| checkpoint | 5.12 Placement & Compaction
80a56adb-3649-5db4-928b-bcb51e527dd9 | note | REFERENCE: Product TDS
8e3e9e26-be76-5499-ba30-d50a77da3279 | note | – – – – – – – – – – – – – – – – –
fcc2210c-f209-50bf-b0eb-d2eb0a8fc496 | note | ACCEPTANCE CRITERIA: All batches are traceable.
4e53bc4d-a41c-5af0-8b13-32c1b7000061 | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
b92aba03-37a7-5cef-8a34-9fb88ed0bcee | note | ○ Product should flow to all areas and self consolidate.
7b71bb9f-db70-51f3-b157-ad0cff50e02e | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
266d4040-831c-5da4-95c6-99a983b801ec | textbox | Enter: Required information on the Grout Pour Record
882376b2-e47c-57f5-af13-b9235a3f31db | note | – – – – – – – – – – – – – – – – –
6c9367b3-2cdf-55e4-9ac9-a1e0e1f5105f | note | METHOD: Visual
d5b1d200-00df-54cb-a65a-2237ecc9ab31 | note | – – – – – – – – – – – – – – – – –
97561005-a8b9-5dfe-864b-359bd455a905 | note | FREQUENCY: Each post location
629b3d3c-210e-5448-8c66-9961ef7f94fd | note | – – – – – – – – – – – – – – – – –
97c52eb6-c48a-527f-87fa-ce14dcf8d8bd | note | CATEGORY: IP
fba35a17-1bc9-52d6-9613-0ca5fcaec24c | note | – – – – – – – – – – – – – – – – –
2d194a58-80fe-5f03-8619-3d2b713b0fd4 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8acf0f57-4bc2-52ab-8de2-81adf46a406b | note | – – – – – – – – – – – – – – – – –
c334fc00-40a4-58be-aa02-d3358d3748ca | note | VERIFYING DOCUMENTS: This ITP
2373c380-5d3c-5709-827f-cd92829e997c | date | Date Completed:
| checkpoint | 5.13 Surface Finishes & Protection of Works
62f1d1d6-a6ae-53a9-9cdc-a37f233ed97d | note | REFERENCE: IFC Drawings 610.17
e775980f-aec6-566e-8a3e-cfb7a550a563 | note | – – – – – – – – – – – – – – – – –
715e90c4-7a86-514b-951c-b740c793be87 | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
b966924e-f688-522e-9207-adee97c3c30c | note | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
1a2519a3-4b5d-5f3c-b541-fc453030871a | note | – – – – – – – – – – – – – – – – –
5d74fedd-3ad2-5646-94de-10c15e6a6175 | note | METHOD: Visual
28856fc1-659d-5be3-a986-6e52c8cab56c | note | – – – – – – – – – – – – – – – – –
0e641d11-28c8-5b0c-ac76-eeb37956024a | note | FREQUENCY: Where applicable, each post location
7288a30a-31a6-5e37-b101-35ef1eceec1a | note | – – – – – – – – – – – – – – – – –
5f32c1eb-91ab-508c-9454-f5f0d6407cff | note | CATEGORY: IP
ac0742b3-963d-5ece-b3a7-c6731c441c5b | note | – – – – – – – – – – – – – – – – –
2c68f6f5-8df1-5e6b-850e-9340ec6571c5 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
10dd66b8-e379-5267-9600-1763d81566e9 | note | – – – – – – – – – – – – – – – – –
e90c2da5-a891-5439-be33-679d073ddec6 | note | VERIFYING DOCUMENTS: This ITP
e8523e2d-4403-589f-a6d6-5c6eb7b18602 | date | Date Completed:
| checkpoint | 5.14 Curing
372747e4-00bb-53a6-99f8-9c446fb5d265 | note | REFERENCE: Curing Methodology 610.23 Table 610.231
b0eaf003-48c4-512d-b034-8e8309dcbc25 | note | – – – – – – – – – – – – – – – – –
66d57a97-5e32-5c43-b64c-c343d1614048 | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
b8c7e06e-5fd6-5f5e-b936-7823a5760bac | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
05418791-9402-57e6-ab30-91f82282a268 | note | – – – – – – – – – – – – – – – – –
30c737cb-b3a9-5296-87a9-69c67b88b859 | note | METHOD: Visual
e6311a5d-047b-53f4-b48c-91285db81d84 | note | – – – – – – – – – – – – – – – – –
0ba50b34-b712-5c2c-8ca9-45f08bc87837 | note | FREQUENCY: Where applicable, each post location
13bab647-f741-51c2-bd51-72f570958e47 | note | – – – – – – – – – – – – – – – – –
fe57251b-58c0-5115-b4dc-761ec0461adc | note | CATEGORY: IP
457b6493-6644-5464-8fba-46e99dcf9007 | note | – – – – – – – – – – – – – – – – –
deece8d3-4666-5e0b-af02-eadda98b1c9c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fa3c8874-321f-5bdf-9c83-d563eb1d3b90 | note | – – – – – – – – – – – – – – – – –
53150924-cb3f-50f2-8c15-bd1e6aab72d4 | note | VERIFYING DOCUMENTS: This ITP
d663854a-9982-5b50-870a-ceabc6ed279c | date | Date Completed:
| checkpoint | 5.15 Architectural Steel Erection
cd24e8b1-deb0-583a-9bf0-be735ec9d5ff | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
3a26fc22-7844-5d3c-85e8-2f3acdef4255 | note | – – – – – – – – – – – – – – – – –
9af45f0b-e2bc-532e-bc13-0891e5db55be | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level and square
48cd99e7-5017-51e7-898e-73862a0a7d6f | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
1e9ea324-ba7b-5e48-add9-37b6bfad8c36 | note | – – – – – – – – – – – – – – – – –
1956fb79-a785-5327-ace0-1491265cfc54 | note | METHOD: Measure, Visual
01bbf5a8-8510-5e71-8a20-c2fd52588509 | note | – – – – – – – – – – – – – – – – –
a3dccf7f-e156-5644-90bf-6f746d20a89a | note | FREQUENCY: Each component
2deda90d-a231-5e06-b307-7ef842a7c614 | note | – – – – – – – – – – – – – – – – –
62936bba-fc02-5a17-85b3-715d540300aa | note | CATEGORY: IP
b0de3267-9860-5a76-8aa8-36d8719dc73f | note | – – – – – – – – – – – – – – – – –
1fff160f-7ddb-5847-b351-48d83df7f9a7 | note | RESPONSIBILITY: SE/PE/SPE
56993b4d-9e24-5f7d-8338-d533872bb7c0 | note | – – – – – – – – – – – – – – – – –
7e59b585-4bf2-5b67-baf7-f49cd156a636 | note | VERIFYING DOCUMENTS: This ITP
f0cbe122-9114-599f-834a-f09bd5cbd5fc | date | Date Completed:
| checkpoint | 5.16 Architectural Steel Erection-Fasteners
ee85d6a3-55f1-5eec-83b2-36acb077e403 | note | REFERENCE: IFC Drawings VR 630
3c4764a4-f0d2-5d58-a190-5c42e0d5e02c | note | – – – – – – – – – – – – – – – – –
f2c45cf7-0a71-5d05-99c1-9b09e892b683 | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
c4b02b34-42c1-533b-bfef-822d7822680a | note | For architectural/Security screens, the arrangement is to be (from themounting post):
6fae05b1-7d9c-5a31-9f32-63cf18a8c924 | note | – Post
6e1aae0e-c6a7-5c60-b9d0-abea9833c2df | note | – Washer (s) as specified
c5c2298c-03d3-5f7f-86c7-996f60650115 | note | – insulating washer
2e933884-110b-5402-83cd-6d99926a40b5 | note | – insulating bush
1cf4d1e4-31c4-55da-adb0-7a5fcc0302a6 | note | – Insulating washer
7f7ddc0b-8632-55e1-a11b-fb9a9cab2f02 | note | – washer as specified
18f77903-e38a-522d-a20e-bc4f401ae2ba | note | – Lock nut
6c909769-9e9b-5a1b-b39c-fb5f311bbce7 | note | – Nut
f2ed21ee-978f-5743-a564-956b3cf0cd9d | note | – Bolt protrusion (1 clear tread)
4e91c446-865a-5015-8e2b-f1d802fb130c | note | – – – – – – – – – – – – – – – – –
48459789-7104-5f2c-8dda-e4c64925d458 | note | METHOD: Measure, Visual
9e0765e6-74da-58bf-bda6-2bc14f23db89 | note | – – – – – – – – – – – – – – – – –
0dece7ee-c8f5-52ef-9408-35125e243e77 | note | FREQUENCY: Where applicable, each bolted connection
5ec67322-9426-537d-9680-507c5eb1d8dc | note | – – – – – – – – – – – – – – – – –
2f8674fa-1121-59c3-84e0-9a495f15282e | note | CATEGORY: IP
3647cdf0-19c3-564d-a17e-30f17b768315 | note | – – – – – – – – – – – – – – – – –
950bb3ee-42c0-5e1b-b9df-6d83ef5860e0 | note | RESPONSIBILITY: SE/PE/SPE
b87ef16b-e3bb-59fe-a46f-5ba6831e1583 | note | – – – – – – – – – – – – – – – – –
120e5806-9dd8-51b1-aed5-1efb613ac812 | note | VERIFYING DOCUMENTS: This ITP
fd05da25-07b0-5a4c-a8f9-1f43cf59e39c | date | Date Completed:
| checkpoint | 5.17 Installation of Electrical Isolation Materials
e9a53e29-b621-5a3c-a968-e344d34b229b | note | REFERENCE: IFC Drawings
dfcf5539-ddcc-5e35-acf3-ed42d8520715 | note | – – – – – – – – – – – – – – – – –
24667508-44e9-56fe-821c-fe59db616765 | note | ACCEPTANCE CRITERIA: Installation of Electrical Isolation Material in locations specified on the IFC drawings.
efbabcc7-466d-5b68-9187-9efe8a24c96f | note | – – – – – – – – – – – – – – – – –
896c40ec-aa6b-53e1-b679-7d7eb012bb6d | note | METHOD: Visual
8521a3aa-5d29-54d2-8541-01f79e8abf51 | note | – – – – – – – – – – – – – – – – –
26671333-d1d5-5a79-9a01-3652487efec9 | note | FREQUENCY: Each component
8428c5a5-6c15-50d5-8efa-70e341d152f5 | note | – – – – – – – – – – – – – – – – –
f873b1d6-081d-5507-8212-243b8afb9118 | note | CATEGORY: IP
99801890-c7f7-51e4-ab26-a5f4ebd76df7 | note | – – – – – – – – – – – – – – – – –
4a943141-d72a-58ed-baf0-7f42ba81ef56 | note | RESPONSIBILITY: SE/PE/SPE
a0f3a114-0638-5cba-a23a-0d19cfa72e7f | note | – – – – – – – – – – – – – – – – –
91e1c30d-19fc-5223-9a3b-01a4a89ab4ad | note | VERIFYING DOCUMENTS: This ITP
e6081f97-b28e-53f3-907c-0830f064802d | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Inspection of Coating
a2e3df91-50f4-5b56-a7f2-083be31cf0b4 | note | REFERENCE: IFC Drawings VR 630
64598970-bb46-5701-92cc-82f104d19581 | note | – – – – – – – – – – – – – – – – –
a55a3996-d2f8-5580-91f9-12999bed03b4 | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
1e99be68-d26a-5d28-ab09-6e8d68703ea7 | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
3b786f2d-5e26-5599-a5eb-ae7796f82857 | note | – – – – – – – – – – – – – – – – –
7e4341ba-cebd-5c7d-ac30-20bf2d98014d | note | METHOD: Visual
31bc6639-9ab3-543c-bda3-75ce0e618f7f | note | – – – – – – – – – – – – – – – – –
3f058c40-29cf-5937-a2ae-12c5eb44e8ae | note | FREQUENCY: Each component
7a37d74a-e7d4-5ca0-a0ae-60ff68db9009 | note | – – – – – – – – – – – – – – – – –
5c9c4488-2d0e-5890-a677-80e65384b30e | note | CATEGORY: IP
48b40435-5550-5e1b-a7ba-9dd3a7d7e675 | note | – – – – – – – – – – – – – – – – –
4cf2f07a-951c-5c4f-9f2f-a16688bbd45f | note | RESPONSIBILITY: SE/PE/SPE
e62b7cd4-27e8-5ce1-bd8e-8b7204fb9d4f | note | – – – – – – – – – – – – – – – – –
5d3aaf78-f083-531b-9217-65f4d3f29415 | note | VERIFYING DOCUMENTS: This ITP
ffa50e35-73f3-5a2a-9dcd-04a4ebe359df | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
f537c6c8-e0d7-55f5-9af0-812b1fc1dfd9 | note | REFERENCE: IFC Drawings, Product TDS 610.28, 610.33
41c64bde-0370-53df-a67b-27386dec4674 | note | – – – – – – – – – – – – – – – – –
0d605e87-30c5-5f07-b690-b1a3ef5d49a1 | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
cc200bd0-8b7e-5633-8f13-80059439100e | note | ○ 28 day compressive strength per sample comply with the design strength.
1bfb837d-eb69-5858-bd7a-d5f371ec6335 | note | Attach: Compressive Strength Test Results
4be45c64-16a9-590b-9298-d50893a79c87 | note | – – – – – – – – – – – – – – – – –
6bc8f0ca-ef69-5405-bf64-1846b8a09a74 | note | METHOD: Document Review
c35cb2d0-710f-5fdb-a1a9-01e07cf0162c | note | – – – – – – – – – – – – – – – – –
ce8465a3-ffe7-5258-8154-6a056c6bba37 | note | FREQUENCY: Each cube
dd2cd5c2-4e13-5b3c-a811-b49b7e430bce | note | – – – – – – – – – – – – – – – – –
1656d823-72e7-5cb2-90d6-9b6b956b546f | note | CATEGORY: IP
c3e4e051-f51a-5f28-9873-4cf992da04fb | note | – – – – – – – – – – – – – – – – –
525a3a6d-020b-5b02-89e6-10f41f04a20b | note | RESPONSIBILITY: SE/PE/SPE
94b34c88-3652-5d2a-aa07-8f4a003a0ee8 | note | – – – – – – – – – – – – – – – – –
e0e01d54-a33d-5feb-b9f8-8896b03e52f5 | note | VERIFYING DOCUMENTS: This ITP
f4724151-cf98-5d4d-bedb-122b820c4330 | date | Date Completed:
| checkpoint | 6.3 As-built Survey
f2ec6ef4-6ea2-54df-a0e7-413576f7fe0c | note | REFERENCE: IFC Drawings AS5131 Appendix F, Table F3
c03bfb58-708d-55e8-8870-c11d68d88b26 | note | – – – – – – – – – – – – – – – – –
7655f221-1dad-5008-bf86-d919c1b8a2d9 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
5b197d18-33ae-5afc-8c6d-00e0dda4bd27 | note | ○ Departure from RL = ±10mm
ccce2029-2f76-5543-845d-1df926611945 | note | ○ Departure from plan position = ±6mm
0bbede1f-830e-5631-8f8e-0d6a7d5adc79 | note | ○ Departure from alignment = ±6mm
fc44d600-b06a-502b-bebf-c07c2208e1c0 | note | ○ Irregularities in alignment = 25mm in 30m
ccb8e311-a6fe-50f3-af31-072b1c0b28bd | note | ○ Projection of bolt = +25mm, 5mm
87ec1a68-6cb7-5bf6-8209-b24f8cced04d | note | ○ Location of beam = ±3mm
e8eb1d72-9709-56e4-b83e-9e2ce2b66801 | note | ○ Location of column = height/500, 10mm max.
3836b889-a985-5e79-8970-0c7e17ab5681 | note | Attach: Survey As-builts / Survey Report
d8cf2cc5-d889-573f-b8a7-2a59e8858c1d | note | – – – – – – – – – – – – – – – – –
0b5d2d68-8731-5b34-9399-9c55d2b2fe44 | note | METHOD: Document Review
11f12f8c-28c3-565e-af01-88e4c50b7271 | note | – – – – – – – – – – – – – – – – –
4c7926d1-047f-5ab7-83a3-9f4b59b5b4a2 | note | FREQUENCY: Each element
ea790092-5f4e-55c6-b264-1b3645d91c53 | note | – – – – – – – – – – – – – – – – –
f973d39a-ea5d-5c3c-bd1d-c1efbe7dc92d | note | CATEGORY: IP
6d164d3c-880d-52ee-a9f1-edbb3c990928 | note | – – – – – – – – – – – – – – – – –
df60a693-f3ca-5204-b1e6-8f8b4d460ced | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
19f8e62e-5d20-5aaf-817d-2edb26893710 | note | – – – – – – – – – – – – – – – – –
53457dc3-30aa-598b-b102-89ced69ade9c | note | VERIFYING DOCUMENTS: This ITP
4e33047c-9a16-5b20-bdfe-2c7ac5604fdf | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
29c04a38-120f-55b8-97f3-f09b8fb82acf | note | REFERENCE: MRPA Quality Management Plan
eb9813af-bf12-56a7-977b-df420c8cd09e | note | – – – – – – – – – – – – – – – – –
37661999-45b9-5c07-9223-4b662c7d29c4 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
94872680-8034-5153-a4d4-0b128965947b | note | – – – – – – – – – – – – – – – – –
5d24fdf4-3be8-5987-8324-281f890f072e | note | METHOD: Document Review
922dab42-e2c1-5f56-8f79-eeda6b8b1b81 | note | – – – – – – – – – – – – – – – – –
f5d832bb-aa02-51ad-b250-11ad5753ebc0 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
a77facec-1798-5fd7-adfa-457f735c9360 | note | – – – – – – – – – – – – – – – – –
e707bd2b-6846-56e4-8901-65c10ded7572 | note | CATEGORY: HP*
6140d5b1-7759-5c25-9831-78547f596e73 | note | – – – – – – – – – – – – – – – – –
10f07ce5-6da0-5468-a8a2-1a9f591fdd8b | note | RESPONSIBILITY: SE/PE/SPE
4e5a5ef6-dd72-55f2-a6cb-884b04962aab | note | – – – – – – – – – – – – – – – – –
6658bb05-bc58-5b58-9676-1d5547e0ac0c | note | VERIFYING DOCUMENTS: This ITP
e0215d5f-ca9d-5e44-8b02-9bd58495ee88 | date | Date Completed:
| checkpoint | Final Inspection
f7363100-7008-54c6-88ff-b815d7ce76e3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1853b711-2735-5e46-8681-cda7b138d838 | textbox | Name:
dc2407a3-f055-51ef-99a5-2391f9b6d165 | textbox | Position:
424dea86-da6b-52cf-ad68-0b323dbfa159 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation Rev 0 | itp | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation | 9170ed7b-cf17-4f3c-a3f9-ff77fbe27fab
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d08aa2f1-ec01-50aa-aba1-1235a862e4ab | note | Document Title: ITP-156-STR-SSB-Precast Barriers and Kerbs Installation
9871d9a4-143e-5b28-98b0-6f9c0a613e3f | note | ITP Description: SSB-Precast Barriers and Kerbs Installation
4efa41c6-cb84-5a78-a7b5-cc4a5ed0fd44 | note | ITP Number: 156
a468f3f8-34a1-5e51-b5b2-7147b0dafae2 | note | Discipline (e.g. CIV/STR/RAIL): STR
d1c87a08-9041-5dcc-a539-800005b9fe3b | note | Revision Number: 0
374252c5-a706-5d90-ae02-d9f91d5e1eab | note | Revision Date: 1/05/2024
e303e248-a83a-59b0-8cb6-d885d48eb710 | note | ITP created by: Justin Kreinberg
a64f6df6-f028-5634-a46a-0108d18b4520 | note | ITP approved for use by: Victor Mira
33dcdf65-9d41-5ff6-bd64-5a1013d3b362 | note | 1.1 Non Dependent
f480890f-5854-554c-a91f-c8a43e079856 | note | Reference: VicRoads Section 610 Feb 2020
497d3184-110f-532d-b712-96bf99d40c9d | note | 1.2 Non Dependent
fa8c50b3-42ac-5c61-bc1a-026e1032bb2f | note | Reference: VicRoads Section 620 May 2009
fec758ce-b9ce-5217-8132-fb2e45e71115 | note | 1.3 Non Dependent
ea427b1d-5b38-535d-866a-11258e35bf2d | note | Reference: VicRoads Section 630 October 2013
7960a660-ab89-5532-9195-f73cbc838d3a | note | 1.4 Non Dependent
e58d37a1-1d95-5a6f-805e-c4748637024e | note | Reference: VicRoads Section 670 October 2013
c80244be-8808-5cb1-a5db-9e118b6ba908 | note | 1.5 Non Dependent
f3e29cf4-fd8a-531f-b5eb-4e7f89e18b76 | note | Reference: VicRoads Section 671 October 2013
| section | Preliminaries Materials
| checkpoint | 2.1 Grout
d9c31691-15db-53fe-bf0a-4460632626e7 | note | REFERENCE: MRPA Quality Management Plan
897082e3-6c5b-5c44-98e3-afa85493ba02 | note | – – – – – – – – – – – – – – – – –
cfb1fc95-65d5-5712-9174-971f195f5761 | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
5747774a-aac1-5835-9bde-8518846ab133 | textbox | Enter: Teambinder Material Approval number
1d1f6d5c-0a17-59ad-af5a-beed817951a5 | note | – – – – – – – – – – – – – – – – –
b043a557-46d0-53b8-8e3e-daad11a4d363 | note | METHOD: Document Review
59a75825-e9f0-5a82-9989-e4f8ee3668f9 | note | – – – – – – – – – – – – – – – – –
79be6cbc-aa5b-55ec-8a0c-0ea9e9194364 | note | FREQUENCY: Once, for each product
330eccba-1ecd-59bc-8705-a06820e43ee2 | note | – – – – – – – – – – – – – – – – –
2e6b0a4f-b3ac-53d6-8c5b-cf21945ac2e1 | note | CATEGORY: HP
883c18a5-dde5-5013-bce0-835e6ebf36e5 | note | – – – – – – – – – – – – – – – – –
52f4866a-e633-5efa-9845-1cd72055e0ed | note | RESPONSIBILITY: Nominated Authority
2c0aa53d-7d28-5561-a096-26b0e196f66f | note | – – – – – – – – – – – – – – – – –
296155c7-ee95-5412-a3a4-83f35e91ac8e | note | VERIFYING DOCUMENTS: This ITP
1dcaa853-6f68-5a88-b186-e38db95b9859 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Documents
| checkpoint | 3.1 Precast Elements
212db1cc-e885-5d3b-ad65-33b0f1c60a3e | note | REFERENCE: IFC Drawings VR 610
0def5f1a-2df3-5a33-b71e-984a508c9ffd | note | – – – – – – – – – – – – – – – – –
bd8076fc-bc4a-501e-bae5-6a50e4c989d8 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
42cc1acc-0590-555e-bfc4-7f98f670153b | note | i. Certificate of Compliance / Birth Certificate
58fae1c4-4758-551c-a3ae-d1a7f537315c | note | ii. Compressive strength test results
8465121e-dfff-5546-b193-a50d202c2acb | note | iii. Precast Lifting Design
35f6719c-fa3a-5e0f-afe8-c4bac0281bc0 | note | iv. Pre-pour check sheet / ITP
1765c278-d8a3-53f1-b388-0d5ac0f50e51 | note | v. Post-pour check sheet / ITP
ac14feaf-1437-5cc6-947c-f9ca29ef9ec0 | note | vi. Covermeter check record
454f2c8d-f57d-5502-bf77-919ccc5a7218 | note | vii. Record of dimensional measurements
1d36bfbe-14a7-574b-bee8-6159b1b7e46a | note | ○ These documents are typically stored in a MDR Lot in Team Binder.
415c1537-6250-5bc8-912e-e0fb7cd73a69 | textbox | Enter: Teambinder Material Approval number
baa9e7fe-c299-5f13-bc95-1a5cbfe12fd9 | note | – – – – – – – – – – – – – – – – –
769a1579-9884-5be3-9133-82006ca0b7c2 | note | METHOD: Document Review
1b4c3d04-ec91-567d-a4b3-481871314f2c | note | – – – – – – – – – – – – – – – – –
23527bdd-87dc-53e5-bccc-d2bbdb09e1a2 | note | FREQUENCY: Each element
97b69a18-9617-55c2-9688-1d91fbc2c870 | note | – – – – – – – – – – – – – – – – –
da34425f-bfbf-5e80-83d9-5808dc8399c0 | note | CATEGORY: IP
9a136184-f72e-5708-ba6c-7206b64ad6c4 | note | – – – – – – – – – – – – – – – – –
802f9335-0923-5299-8efa-e9d26936393b | note | RESPONSIBILITY: PE/SE/SPE
f4e19438-ee47-51de-8723-28fb568e22cc | note | – – – – – – – – – – – – – – – – –
36041fbb-d043-5dfc-9bc2-6d9ee2d896cd | note | VERIFYING DOCUMENTS: This ITP
22337557-5074-5de5-8881-6876117344b9 | date | Date Completed:
| checkpoint | 3.2 Bridge Deck / Foundation Compressive Strength
79b9a041-bb08-5f60-bd48-fcf36e91c1dc | note | REFERENCE: 671.03
5a86c4fb-6108-5427-b4e9-4ab7ffa5e3b0 | note | – – – – – – – – – – – – – – – – –
f8f86eb9-0d13-55fd-9ae7-eaa70fde4408 | note | ACCEPTANCE CRITERIA: For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
c7be1a32-0d1b-57c9-8875-c54d15e6570f | note | – – – – – – – – – – – – – – – – –
01af9b90-5988-5900-ae54-7ff1790f0582 | note | METHOD: Document Review
3b6436bb-c2da-5e28-a0b8-c540112a39c0 | note | – – – – – – – – – – – – – – – – –
01bc298b-6f59-562e-b709-775aab7cb097 | note | FREQUENCY: Each installation location
4a545cdb-20ab-5b08-b112-a967f8e41efb | note | – – – – – – – – – – – – – – – – –
fae8789a-97fd-5968-8c05-51a059285f3e | note | CATEGORY: HP*
ef74b91b-8204-55d4-9ba3-5254aa4f0aca | note | – – – – – – – – – – – – – – – – –
85fe9594-03c9-509a-8df7-2b8dfe96efb8 | note | RESPONSIBILITY: SE/PE/SPE
00a9bb9e-1471-5a8e-a8c2-23e864d87d22 | note | – – – – – – – – – – – – – – – – –
688d418a-735d-58f4-9d5a-5ab45fc94a83 | note | VERIFYING DOCUMENTS: This ITP
2c29e3f7-2979-546d-8bfb-8bcaf0d28af8 | date | Date Completed:
| section | Pre-installation Activities
| checkpoint | 4.1 Survey Set-out of Precast Elements
5d25c919-e0a2-5a7e-9506-d0ab67a065a8 | note | REFERENCE: IFC Drawings
4c6d807d-cc40-50f9-8f9d-25aa8237268c | note | – – – – – – – – – – – – – – – – –
f737cbb4-6927-5848-b2a2-bcbda5811f09 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
2a4cf415-344c-55ff-bbe1-b01a2d4373fa | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
072240fe-efe7-5bc8-9516-b174a3e84833 | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
4370a4df-ff61-570d-89c2-e9db6ec30c3a | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
e6dab796-f949-51b6-a2bd-3009cf069406 | note | – – – – – – – – – – – – – – – – –
f827b912-8b6a-5768-86b7-809571e960f2 | note | METHOD: Measure, Visual
376a3c45-091d-550b-8a61-2f560b6da77d | note | – – – – – – – – – – – – – – – – –
baaa1f12-722c-5ea7-b22d-a1c5d4186be9 | note | FREQUENCY: Each element
231e0b48-ff43-535a-a02c-04e4fecf470f | note | – – – – – – – – – – – – – – – – –
3eb67ac5-89f7-5fc2-9f0e-5688ba60f236 | note | CATEGORY: IP
2639531a-6e57-5d7d-9ccc-16c2b412fc90 | note | – – – – – – – – – – – – – – – – –
61fc81cd-1c65-56ac-b928-20dc66234c2e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
ceae31f5-0239-5567-ad04-f53e2205e235 | note | – – – – – – – – – – – – – – – – –
2c2fa844-93f2-5aa1-a772-201d2bbeafde | note | VERIFYING DOCUMENTS: This ITP
4be7673e-be95-5341-bd24-a8e1b963d9ee | date | Date Completed:
| checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
5a4e649e-50bc-519b-b925-dcc71559c019 | note | REFERENCE: IFC Drawings
aacc70e5-0951-5285-b16b-ba94d01e111f | note | – – – – – – – – – – – – – – – – –
5a562736-93fe-5c40-9d0f-5103feca0ff8 | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
bc9fe870-a888-559f-8f0d-7df41f6ae840 | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
17843f64-80e9-5673-868b-b58f1de294ed | note | – – – – – – – – – – – – – – – – –
f239350e-a4f9-5ee1-a47e-610d53f05a5f | note | METHOD: Measure, Visual
ad4d2245-084b-5124-ae92-ceffc214175b | note | – – – – – – – – – – – – – – – – –
2d445f2d-7370-533f-b34d-a4202d62da28 | note | FREQUENCY: Where applicable, each installation location
d07ff0c0-715c-5a2b-bad1-c894106b37d6 | note | – – – – – – – – – – – – – – – – –
15a53bac-54af-54a7-90d6-17961937e1f9 | note | CATEGORY: IP
84a2eda2-ceab-5390-9838-cc0eb3fdda8f | note | – – – – – – – – – – – – – – – – –
f9ddf73b-9a5c-59b1-99ac-254891c06763 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f18aa401-6fc8-5cd4-ae64-36fc9f95c0f9 | note | – – – – – – – – – – – – – – – – –
9a79476a-0877-5ad7-ad0b-39e4467f2fd1 | note | VERIFYING DOCUMENTS: This ITP
ed23d7ab-91c5-50e2-a15e-500f38695b2f | date | Date Completed:
| checkpoint | 4.3 Bitumen Board and Ableflex placement
d7994381-1063-5dd9-9a87-2ba869d4ad60 | note | REFERENCE: IFC Drawings
8ffb6549-30f1-5cf4-9b91-a256c6c37168 | note | – – – – – – – – – – – – – – – – –
ce3ae52c-c789-5484-bf21-fba7c17f1b82 | note | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
1c189a4a-00b1-5d4a-9aa3-82e5cadf45f9 | note | – – – – – – – – – – – – – – – – –
9bdebb63-2323-570c-a6f3-270bf8b5e863 | note | METHOD: Measure, Visual
b068b5c4-c307-5470-a032-eee631ca4091 | note | – – – – – – – – – – – – – – – – –
19933a9d-5352-541e-9bd0-b47045012fdc | note | FREQUENCY: Where applicable, each installation location
972f2260-3d66-5b69-8907-cc7b76ddabbc | note | – – – – – – – – – – – – – – – – –
1af0f8a1-d99c-5c4b-84ff-f3675f33f07a | note | CATEGORY: IP
5d492235-0f1b-5db8-a48a-c10dfdb6c88f | note | – – – – – – – – – – – – – – – – –
d1940ece-1196-5a2b-8eaa-d7ff4ec6c99d | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
7b163b6c-c2d7-5919-90cc-6add01e117a0 | note | – – – – – – – – – – – – – – – – –
b5f00aef-eb5c-5a39-b737-b51ffa0382c0 | note | VERIFYING DOCUMENTS: This ITP
11d41ad7-b1f4-5f96-8102-f0f2e82fe3f6 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
b16b9932-ea89-51fc-9ff5-04a744ab2f62 | note | REFERENCE: 620.07 Crane Lift Study
8bab09c0-78fb-570d-8343-e50a9dec5cf4 | note | – – – – – – – – – – – – – – – – –
c7ddbd2b-5684-58ff-a8bf-39ef9b21bb70 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
b16088df-bbbe-58e5-ab52-b7084b84dcab | note | – – – – – – – – – – – – – – – – –
97e27757-855c-56a1-b49a-c9b351adeb85 | note | METHOD: Visual
05aa8c2a-a691-53a5-8053-cd8b05ac6729 | note | – – – – – – – – – – – – – – – – –
814ed8ea-cf9d-504a-9ba0-f0bfee3d291c | note | FREQUENCY: Each element
6d17ae64-b91a-5724-b434-08fbb91c88d3 | note | – – – – – – – – – – – – – – – – –
6f7cc956-5061-5df2-86b2-dfe598e440ca | note | CATEGORY: IP
e4c1425f-b3dc-5550-9b21-903e516077c9 | note | – – – – – – – – – – – – – – – – –
d0bb0266-d364-5039-8db5-6b1c68608ed1 | note | RESPONSIBILITY: SE/PE/SPE
a91aa884-95a4-5318-8700-ce99d2a64a9e | note | – – – – – – – – – – – – – – – – –
e63bb492-e8e5-5b7e-9c1f-21b311541103 | note | VERIFYING DOCUMENTS: This ITP
d0d293a5-1744-5991-bf33-1281e2ee8d88 | date | Date Completed:
| checkpoint | 5.2 Precast Placement
6aa883e5-8acd-5585-ad6e-0ffe4c696c31 | note | REFERENCE: IFC Drawings VR 670.05
d377ad0a-8dd8-5ffc-8245-5ac9e6ab29b9 | note | – – – – – – – – – – – – – – – – –
acad6687-1f07-5761-846d-82f253a59d30 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
4ad4b71f-810a-58e1-b070-ce838b37f815 | note | Adjustments to be made to achieve following tolerances:
8534de93-23b7-58c7-89f7-78d9b3654166 | note | (a) Departure from plan position: 25 mm
bccd160a-0340-531e-b1b4-11f461599091 | note | (b) Departure from alignment: 5 mm
a099254a-9005-5531-9a06-ebd8ce36f245 | note | (c) Irregularities in alignment: 3 mm in 3 m
091bf512-5e11-566a-9812-08a496334368 | note | (d) Variation in joint gap width: 3 mm
010caf53-969f-5e19-bdfe-2f8d881c3802 | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
ca227fa4-f6ba-5d63-8cc8-cc3279e79ad3 | note | ○ The nominal gap between elements is as per the IFC Drawings.
2d85e32a-2680-531e-8c56-384e3c012cb9 | note | – – – – – – – – – – – – – – – – –
b70ed531-2ca9-53bf-981b-8136c03b0bbd | note | METHOD: Measure, Visual
b565ca51-2143-5551-aa3e-4fc4f99e8700 | note | – – – – – – – – – – – – – – – – –
4754f328-af4e-51d5-871c-46c1e6dfe8de | note | FREQUENCY: Each element
ae3fbde3-7121-56dd-8d5c-5acf47735c35 | note | – – – – – – – – – – – – – – – – –
9b523707-1556-5f86-bd2c-5def1d1a5edd | note | CATEGORY: IP
683fa12a-9d83-55f2-b989-e0cb2cf5df7e | note | – – – – – – – – – – – – – – – – –
6007c060-c802-52ef-854a-f9e4b42639ec | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f1f646d8-f099-5657-b543-dcdba478dea2 | note | – – – – – – – – – – – – – – – – –
1198d8e1-e3aa-5cda-94d2-f5fe7e0d479e | note | VERIFYING DOCUMENTS: This ITP
bece71ad-a5c3-5144-b212-8c4a06d861f0 | date | Date Completed:
| checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
909f7494-e7df-57b0-8a9a-ed9ac09a2c97 | note | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
5fd9c675-1e69-5d67-8b98-76627cc80e40 | note | – – – – – – – – – – – – – – – – –
96d55797-09a6-5c28-88d6-625c90e62b19 | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
bc19aaa1-e2fa-5c36-8143-a792557d8c40 | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
b5d53a8a-fef6-52c6-aa86-0823e510b865 | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
3756e90c-fd11-5c34-a01e-9dd5669f78ac | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
cc802dea-3dc5-5597-a48e-31d77e4483b1 | note | – – – – – – – – – – – – – – – – –
b5e5db21-ef9d-52bb-a72b-cd7ff0f3e4e6 | note | METHOD: Visual
9d73bf7a-24e1-5891-91bf-d81824955b37 | note | – – – – – – – – – – – – – – – – –
b6c0a596-ceee-5586-8fa4-4b59d63d5263 | note | FREQUENCY: Where applicable, each bolted connection
55ee017b-24c0-550b-bfb7-648ff00880fb | note | – – – – – – – – – – – – – – – – –
ea566c8e-b421-5b0e-ab37-979ac5d6c032 | note | CATEGORY: IP
3394fea0-e4db-5f90-93bd-caaf2080a8a2 | note | – – – – – – – – – – – – – – – – –
5dd0161a-d6b5-50f2-b415-1776e3391669 | note | RESPONSIBILITY: SE/PE/SPE
4e532713-bc88-5efd-aef0-7980d4b2b8b4 | note | – – – – – – – – – – – – – – – – –
ef525d8f-accf-5fe2-b12b-3adf52dd0805 | note | VERIFYING DOCUMENTS: This ITP
6d31b18d-f9c5-536e-8762-81fd753be5f9 | date | Date Completed:
| checkpoint | 5.4 Precast Traceability
c1899c43-9a47-51cc-8e15-c8bfd545c225 | note | REFERENCE: 620.09
cfee65c2-d6e9-5d26-9115-39233f1bcce8 | note | – – – – – – – – – – – – – – – – –
cff6bc53-941a-5349-9721-27a754ba0e98 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
4efdc115-9825-5711-a5f2-b360d30a54fd | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
577cc9e9-ce93-5691-8049-74a28af7b194 | note | – – – – – – – – – – – – – – – – –
de4635fd-3637-5a64-8849-586c2cf9b6f7 | note | METHOD: Visual
3d8dbe0b-4620-5eda-a480-bd695a0bca59 | note | – – – – – – – – – – – – – – – – –
928dd693-3fd8-5490-8e38-bd8183d97203 | note | FREQUENCY: Each element
a757e125-83c7-5a8f-9236-133eefeb848c | note | – – – – – – – – – – – – – – – – –
c40c0019-2f99-5471-ad40-c5678207d0bc | note | CATEGORY: IP
f2b0e0df-923c-52d8-b0af-b6ef388ae9eb | note | – – – – – – – – – – – – – – – – –
2abe1246-0a14-5b25-9f02-6e0c4e3a121a | note | RESPONSIBILITY: SE/PE/SPE
8a725725-5d44-5855-b3e8-ec04f8fdb78c | note | – – – – – – – – – – – – – – – – –
51150713-db35-561e-aafb-af68c7eb4ecc | note | VERIFYING DOCUMENTS: This ITP
f0a7ed74-e3f8-50ba-8131-e97149d257fa | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Flowable Grout Pour
f1f8cf08-6279-514b-92c8-1867252d693d | note | REFERENCE: IFC Drawings
f99d29e0-b9cd-51ad-a1af-0c6c008f3768 | note | – – – – – – – – – – – – – – – – –
bd5c9479-1e77-5ac0-b7d1-44a4c7ab17e0 | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
7d1d44e4-1ac5-5b09-99dd-779ee4bc9fdf | note | Complete: Grout Pedestals & Bearings ITP
f0f3b92d-4ae6-5976-a4d2-6d9d3a29edcf | note | – – – – – – – – – – – – – – – – –
f768359e-c10c-5e59-844b-de35132f0bbe | note | METHOD: Visual
b7897e26-03fd-5346-b296-6f38b1d12ff5 | note | – – – – – – – – – – – – – – – – –
835cb4be-00d2-5517-a846-f4b3f7075927 | note | FREQUENCY: Where applicable
212d676f-1221-5437-a4c6-6cd531dcb51c | note | – – – – – – – – – – – – – – – – –
4f40ca37-c1bd-5f8b-a31c-ea0c6e167614 | note | CATEGORY: IP
9eec3ac5-14d5-5bfc-bb70-0197c801deb5 | note | – – – – – – – – – – – – – – – – –
c33cd5c6-fec7-5e72-9e60-d1c42c6309b1 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
47d2ea2c-58d1-565c-9e5d-7c16da81aeec | note | – – – – – – – – – – – – – – – – –
d004b9c0-54a1-5b6d-a1a9-b09d52e707d2 | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
dc208a95-ff11-5411-9af0-9ccf2b3a6e70 | date | Date Completed:
| checkpoint | 6.2 As-built Survey
8fcfdf65-933c-59df-8e9b-058928d8312b | note | REFERENCE: IFC Drawings VR 670.05
b7b10e6d-39ec-50e7-ac13-637fb0c0fd4b | note | – – – – – – – – – – – – – – – – –
86bbb73f-64c8-5773-a337-ec54ef846dc2 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
e1082462-4e1e-573c-97e7-043ec18d1ae4 | note | (a) Departure from plan position: 25 mm
1562e99c-1ac1-5d60-8c0f-b1f55b5c9f8f | note | (b) Departure from alignment: 5 mm
e1c2c53b-9fd7-525d-80d1-ede57b4d2c7e | note | (c) Irregularities in alignment: 3 mm in 3 m
eaadc785-478e-52fd-af39-7c8cfb9d7868 | note | (d) Variation in joint gap width 3 mm
fd080306-5d79-5b17-84e3-cad41fca6b10 | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
d811c141-2967-5d90-ac52-d28d61fa27ff | note | Attach: Survey As-builts / Survey Report
b60eec08-fd40-5245-a01a-cab9f9c40d66 | note | – – – – – – – – – – – – – – – – –
1650f1e5-3c8e-5845-88e4-b410b2346d89 | note | METHOD: Document Review
98067528-dc50-5cb6-8c87-85d0bd686291 | note | – – – – – – – – – – – – – – – – –
def1f1ab-0f5f-50c3-95f1-fe55e118529e | note | FREQUENCY: Each element
40ad0144-3650-52e0-9bc8-8030cf7e9944 | note | – – – – – – – – – – – – – – – – –
9304a1f9-d068-5d21-9655-fdd52ee9d20a | note | CATEGORY: IP
23e39ba4-13df-560b-b5f3-e01fbd8905d5 | note | – – – – – – – – – – – – – – – – –
38f1e46f-499a-559b-bcde-bf30d06666e8 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
d5f196b5-52ed-5fc1-9109-f15b736caf1c | note | – – – – – – – – – – – – – – – – –
9eaaa39e-0e62-56ca-ac3c-e6947a5b7632 | note | VERIFYING DOCUMENTS: This ITP
4b0fed15-e5dc-5857-84c8-e44b2c546b1f | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
a2e0d750-7939-54cd-9045-c6755dbc0c46 | note | REFERENCE: MRPA Quality Management Plan
96ae413c-aad3-5dee-ab3c-b11bbea989dc | note | – – – – – – – – – – – – – – – – –
ae721f22-ba9c-545d-8e01-27fc431cad25 | note | ACCEPTANCE CRITERIA:
672dc227-e7db-5d6b-a9e1-c4cd279c9918 | note | – – – – – – – – – – – – – – – – –
67e870b8-56be-54e1-98ac-0931edb04821 | note | METHOD: Document Review
fba245fd-b344-53a8-bc4f-b45ce8a3acee | note | – – – – – – – – – – – – – – – – –
a4117d6b-2996-5ceb-b9d7-17f5902f0770 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
4f983282-98ab-57c2-90f5-ccf4567347f9 | note | – – – – – – – – – – – – – – – – –
b95009bf-07e8-535e-a4cf-cc28e1d8d1b2 | note | CATEGORY: HP*
0cbfd7ce-6138-54d1-8f49-3dad56493898 | note | – – – – – – – – – – – – – – – – –
34e1ac67-ba10-5b42-a7b7-a1f8b8274b72 | note | RESPONSIBILITY: SE/PE/SPE
5e03a34d-37c6-5be9-92ca-1123beaac769 | note | – – – – – – – – – – – – – – – – –
77f000d0-44a4-5d43-9884-8cc135541602 | note | VERIFYING DOCUMENTS: This ITP
b42b793a-0796-5d50-95a8-58e4596219ad | date | Date Completed:
| checkpoint | Final Inspection
7facc496-327f-5b68-8e2e-9122e2e8d486 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9c049553-31f9-5ce2-aeef-fdb4150a70c5 | textbox | Name:
7f90c40f-d5db-57a9-b2e4-447187cf8d85 | textbox | Position:
9aaa9282-67dd-5ec8-ad41-4f2070c41acd | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing Rev 0 | itp | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing | aa2068ed-2461-4feb-8e4f-a110771b75e0
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0973ea16-b617-529e-bd02-919b4601e762 | note | Document Title: ITP-163-RAIL-SSB-Rail Delineation permanent fencing
70456dba-cf02-50cf-a3c5-42e45ebf0d1b | note | ITP Description: SSB-Rail Delineation permanent fencing
78827f5a-03d1-56d9-be46-3d7bd88edca8 | note | Discipline (e.g. CIV/STR/RAIL): 163-RAIL
2c1ac98a-930e-5563-bc51-682ffa830fe8 | note | Revision Number: 0
b00fbc29-2cf3-5348-aae4-bde31293a3d6 | note | Revision Date: 10/05/2024
8830dca6-031c-5cf3-b99c-ad89f549a048 | note | ITP created by: Yasna Nicker
2738c1e4-e160-57e3-b0cd-e56b58688211 | note | ITP approved for use by: VM
f47a4248-f769-5cd5-97b3-f394765c2a58 | note | 1.1 Non Dependent
ee29c56a-402c-5fd7-95d6-7e0b5db808bc | note | Reference: IFC Drawings
| section | Preliminaries-Materials
| checkpoint | 2.1 Concrete Toe Beam and Head Beam
aeacb59b-2de6-50c4-8c7e-5aabef16b59f | note | REFERENCE: IFC Drawings
88fbc1a3-ee32-50f6-95be-f23035070b21 | note | – – – – – – – – – – – – – – – – –
40e4c2b1-b977-55bf-9753-dbdee6f8589e | note | ACCEPTANCE CRITERIA: Minimum of 60 MPa concrete shall be used as per IFC drawings.
4b84db25-85c9-552c-b581-5337fe5ca8a0 | note | – – – – – – – – – – – – – – – – –
b661bd4b-2984-59c2-9c73-66227f188a0f | note | METHOD: Document Review
fcbbdf42-57fb-59af-abc1-44bcf65c78fb | note | – – – – – – – – – – – – – – – – –
f7a00750-f003-57ab-9ddf-b02af705e085 | note | FREQUENCY: Each Mix
5f0c01af-2b48-54cc-94a7-593c694acb2f | note | – – – – – – – – – – – – – – – – –
add96c8f-165b-579f-a686-e3ada62d1cd9 | note | CATEGORY: HP
9a9a27ea-9ea0-5a6b-95d7-c6a077fb4a86 | note | – – – – – – – – – – – – – – – – –
0cd2a428-ab24-5374-ac32-12418226a70b | note | RESPONSIBILITY: SE/Site Supervisor
9c75f429-3128-5833-a42e-8cdd2d156379 | note | – – – – – – – – – – – – – – – – –
019b3a17-df41-5c0d-a66c-54c00affa4fa | note | VERIFYING DOCUMENTS: Certificate of Compliance
6575f4fd-0b32-5155-9e9a-a4080644f2eb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Steel components
66efabc6-e5b4-5d10-b623-37550c6e9371 | note | REFERENCE: IFC Drawings AS41000, AS1163
4f9f609f-1a0d-54ec-a7ad-1de1c4028b08 | note | – – – – – – – – – – – – – – – – –
bd9291cc-2be0-5355-ae10-8e708c1905b4 | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
796051dd-1beb-5d50-a570-96349fa834fe | note | ○ Steel section sizes must be checked on site.
192b5f09-4195-5e00-8429-3ed08dd0c042 | note | – – – – – – – – – – – – – – – – –
baa4127e-c72d-50d4-86ae-65467273328d | note | METHOD: Document review, Visual and Measure
704cee83-4185-53e3-9194-0b0b4af60bd7 | note | – – – – – – – – – – – – – – – – –
7c6cc7e6-3a0e-5b31-a1c4-f1b8dc565272 | note | FREQUENCY: All elements
cba66196-f9fa-5218-9f1d-0868da7c5ed4 | note | – – – – – – – – – – – – – – – – –
bd20d227-a1f5-5fda-8541-127b8bca0ecb | note | CATEGORY: IP
258633c1-350a-5295-bd3e-f293247365a3 | note | – – – – – – – – – – – – – – – – –
7d0114c8-5be6-5ac6-9d5a-236a6ec581aa | note | RESPONSIBILITY: SE/Site Supervisor
e35b2bea-f060-5d58-a0f6-7cd11ace545f | note | – – – – – – – – – – – – – – – – –
fe5a8f48-37b4-5466-8467-fa629744eaab | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
ba011d2c-42cf-5257-8960-4325e0401c34 | date | Date Completed:
| section | Preliminaries-Documentations
| checkpoint | 3.1 Excavation of toe and head beam
10c2825d-de0c-52fa-92a2-f2f408e18c3e | note | REFERENCE: IFC Drawings
6be806a5-8cdb-53bc-b643-73b57bab83af | note | – – – – – – – – – – – – – – – – –
e8137548-c4f4-5bbf-a008-d2be0b3c617f | note | ACCEPTANCE CRITERIA: Excavation for beams must not undermine track and comply with PTDT requirements.
de516e91-27c3-5566-b3ac-667faf82d7f8 | note | ○ Follow asset owners guidelines for work around their service.
948f383e-b488-5418-afe1-1468f65b1bfa | note | ○ Excavation must use Non Distructive Digging in the rail corridor
25eff27d-0887-581e-9603-d0ff58540a2a | note | – – – – – – – – – – – – – – – – –
d6edae67-8a12-5e49-bdf6-e8b22b15b9e8 | note | METHOD: Visual
b5ecc2a7-98ec-52e8-9ea4-11e9b58ab762 | note | – – – – – – – – – – – – – – – – –
010c1ff5-fde4-59cc-b034-9ab8bcf1fe34 | note | FREQUENCY:
c3c39d71-97cc-54bb-9c8c-5fc248dd5e17 | note | – – – – – – – – – – – – – – – – –
3aaa5fdd-53d3-5ffc-8d23-631861b2c2b8 | note | CATEGORY: IP
fd31971f-1a1d-5d00-b14f-a593f09cfbfc | note | – – – – – – – – – – – – – – – – –
0b0e0fcf-dcc5-538f-9d15-9a171b9698ff | note | RESPONSIBILITY: SE/Site Supervisor
f7fa60d5-7cb5-5d99-a8b4-d541af45b9f9 | note | – – – – – – – – – – – – – – – – –
46004f3d-aab6-50c7-a759-7ab05891fd0b | note | VERIFYING DOCUMENTS: This ITP
202a2de4-ed31-5a21-ae14-2c6286096035 | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out
20387637-472a-522e-b41b-7c0637148e3e | note | REFERENCE: IFC Drawings
0ff8fecf-8155-5535-9739-18f7b7b004c2 | note | – – – – – – – – – – – – – – – – –
59583c7a-10d2-5cb6-aecc-a160097954ff | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
f2800f91-e0d4-56af-9b16-2d3466397c33 | note | ○ Offset checked against the running edge prior to installation of posts.
a0a1e99f-ff26-5b58-8fdf-d0a0fd382231 | note | ○ Engineer to verify alignment of posts using string line or equivalent.
75ec1c8b-26ad-583e-bc79-febd5f631967 | note | – – – – – – – – – – – – – – – – –
765852ec-f7f8-5a7d-9c62-fad7ef800d52 | note | METHOD: Measure, Visual inspect
7b0ca519-d5b6-5b7e-bd8b-8179cdfef62a | note | – – – – – – – – – – – – – – – – –
dc1018a4-5ad0-5f97-9ccb-bd32c57d8f62 | note | FREQUENCY: Each element
020ceb06-7a93-56b5-9dbd-36e55ac9a6fb | note | – – – – – – – – – – – – – – – – –
8b9761b2-6bce-5b92-9526-16a57651fb3f | note | CATEGORY: IP
5ced95d6-ad8d-5aca-bcf1-27a37e4628fd | note | – – – – – – – – – – – – – – – – –
b7c4c896-156e-5333-946d-ef41c97985a2 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fd3dca32-c7cf-5b3f-b9f4-fb04ff87a48d | note | – – – – – – – – – – – – – – – – –
49d1b134-117e-5d1d-89e6-9fd264cdc5ba | note | VERIFYING DOCUMENTS: This ITP
75ea2762-4cb5-5aeb-b605-345f4139d8e0 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Ground Conditions
661d53c8-0a00-5563-a8c8-700888ff9ba3 | note | REFERENCE: IFC Drawings
a7b0af25-6c13-59d4-829d-500ee6dcb5a3 | note | – – – – – – – – – – – – – – – – –
ab743e7c-c100-565f-9b90-3c8a6df9b23a | note | ACCEPTANCE CRITERIA: All post foundations/ beams to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
332b379c-e29c-52db-aa4e-ce58c5b63698 | note | – – – – – – – – – – – – – – – – –
a46497ba-96de-53b4-b946-e2bc0c503ffd | note | METHOD: Visual
bf06e5d1-0f76-5457-900f-adabb5fa6a50 | note | – – – – – – – – – – – – – – – – –
5cc17515-04e2-5414-8fc5-e18a7da35b3f | note | FREQUENCY: Each post
f333f2e4-dcc1-568c-bab9-45d197985135 | note | – – – – – – – – – – – – – – – – –
0a1f7685-cbc4-5775-9b10-6332d26d8fa4 | note | CATEGORY: IP
17582ea2-e008-508f-ac62-b68269ca979d | note | – – – – – – – – – – – – – – – – –
34042069-df58-5214-bf20-b39d8f2b2990 | note | RESPONSIBILITY: SE/Site Supervisor
582bf95d-f409-5bb2-977e-ed2c003acd2e | note | – – – – – – – – – – – – – – – – –
db29b96a-e7ca-5ea5-bf7e-f95f4dfe8ee8 | note | VERIFYING DOCUMENTS: This ITP
2354aa0e-f278-54e1-b669-f8101b18f5cd | date | Date Completed:
| checkpoint | 5.2 Toe and Head Beam Formwork Design and Construction
561e9bd6-9c2f-5ea1-b352-4985be1e1a81 | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
4313aaaf-e6fd-53c1-9054-1f85917cd53e | note | – – – – – – – – – – – – – – – – –
49d2d9cd-c19b-5be9-ba40-c5e3366ffdb9 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
ea4d9de1-27f1-5858-bc51-26fc1efc8817 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
bac4f096-b2ae-59cc-8bb3-98e323ac52f5 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
b8606ad6-d159-52ab-9a9d-fb26f80cadba | note | – – – – – – – – – – – – – – – – –
b9831a60-22d8-5638-bd1e-f3f349429745 | note | METHOD: Document Review, Visual, Measure
17f20886-6dd1-565e-8cd0-b6160b744201 | note | – – – – – – – – – – – – – – – – –
51c3fdd0-065e-577c-a308-4f4b41c38155 | note | FREQUENCY: Each type of element
4200c11f-6b5f-58fd-8a1c-2366e4871a81 | note | – – – – – – – – – – – – – – – – –
58a2f593-44c8-5edc-93ef-e88909baec9b | note | CATEGORY: IP
def5e369-16f7-5573-9cc4-0fba6542120d | note | – – – – – – – – – – – – – – – – –
594743c0-0933-5ccf-a12f-9667e6cade8d | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
fb36e443-78e6-5fb5-ba7c-0c7ef18c6dd5 | note | – – – – – – – – – – – – – – – – –
fd389c36-1456-5420-a650-d269516f5f09 | note | VERIFYING DOCUMENTS: This ITP Signed Off
e1276e81-7afb-5442-b80b-edc627836cc3 | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement (Toe Beam and Head Beam Steel)
ff6d145d-d963-522d-bacb-d29ae7f756cb | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
ff3e61bb-25e0-5871-a67e-8733e71686a7 | note | – – – – – – – – – – – – – – – – –
0b5331e1-d088-5913-bf98-0898bcda9ead | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
51b64561-13e8-555b-9274-2b350c2ed90c | note | ○ Projecting reinforcement is the correct length and location.
ab641928-0043-5004-bcf2-1fc7030ca303 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
1e6e835c-87d6-5327-ac7d-2ad15b695ecc | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
ae490e7d-e8be-5ea7-be37-cc0a17cd4a64 | note | – – – – – – – – – – – – – – – – –
82645212-f618-5dca-bddd-7c3600597b28 | note | METHOD: Measure, Visual
841bbe94-dc72-55b0-89ab-65ba9ceef64f | note | – – – – – – – – – – – – – – – – –
2185a663-ad6c-5e7d-b4d5-af0774410be4 | note | FREQUENCY: Each element
baebb152-c5f2-5482-b353-1f939892d988 | note | – – – – – – – – – – – – – – – – –
ed890e63-054f-5689-af6b-49abd920bcf8 | note | CATEGORY: IP
364478e5-2510-5056-95cb-609a8d3e18e9 | note | – – – – – – – – – – – – – – – – –
c3a40a59-cbfa-5193-b8a6-7dfa00f80eec | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8c7357db-ecf1-5b02-8e48-84b4345018a7 | note | – – – – – – – – – – – – – – – – –
a249ef93-8ffd-57ee-ac3e-f387f9a15f87 | note | VERIFYING DOCUMENTS: This ITP Signed Off
00f5931a-7090-5412-b478-f2548d352939 | date | Date Completed:
| checkpoint | 5.3 Toe Beam and Head Beam Foundation
f5b7f70e-697a-59b5-a5a4-fff9be500ab1 | note | REFERENCE: IFC Drawings
6ff87759-9e00-590a-a5fa-2119cad87a80 | note | – – – – – – – – – – – – – – – – –
95e87dbe-2ed5-54b2-8d1c-89fb1f90d0c6 | note | ACCEPTANCE CRITERIA: Toe Beam Dimensions (Fencing Post Foundation)
4bec0b4f-d3d7-5fc1-8b89-f74230001f79 | note | ○ 600mm Depth
00bff26c-574b-5805-8252-6347d8793d8e | note | ○ 600mm Diameter
43e6fbc1-f3b4-5f5f-8e2f-a9923bc75613 | note | ○ 2405mm c/c Spacing
08c33ab4-6771-53e2-b942-e9014d47c505 | note | Head Beam Dimensions
8e5a62de-83cf-5158-af47-682847bd2344 | note | ○ 600mm Depth
71436ae2-efec-5d3e-baa0-3ee54c813180 | note | ○ 600mm Diameter
6e7b3a47-fc0a-57a4-ac6f-a67ec88716e9 | note | – – – – – – – – – – – – – – – – –
3bb16361-c255-5acc-8994-449bc4d6f879 | note | METHOD: Measure
c5177835-5238-5ae7-b258-1e510a12629f | note | – – – – – – – – – – – – – – – – –
d63bbc7d-2913-51e5-a3e1-0a5a1cfe81d4 | note | FREQUENCY: Each footing
05099656-2a44-5df4-8560-4dcca2a15346 | note | – – – – – – – – – – – – – – – – –
c21128e4-dfac-58a9-8d2f-30e0443f3d33 | note | CATEGORY: IP
2ac08ac5-4d82-572f-96a1-b296118bde55 | note | – – – – – – – – – – – – – – – – –
f7c7efb3-6b3a-50c3-b748-f078971e32dc | note | RESPONSIBILITY: SE/Site Supervisor
752c6b6c-b030-5bb2-82b8-9de1e258f93a | note | – – – – – – – – – – – – – – – – –
dc3d8b7c-4b46-59b7-b3b0-278de8a15259 | note | VERIFYING DOCUMENTS: This ITP
6a3fd8ae-30d4-58ac-9eaf-845dddb96116 | date | Date Completed:
| checkpoint | Concrete Toe Beam and Head Beam
d4864059-543d-5f56-a84a-188c57cfc73d | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
e4a5fe1c-ed07-54ea-ac90-42413f532d7c | note | – – – – – – – – – – – – – – – – –
017f5038-577b-58ec-94c9-f093896a1128 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
3e1cb172-9314-5311-9bd9-4fded1824b31 | note | ○ 0m³ to 10m³ = 1 sample
ba0b0cfd-429a-58cb-b47f-2789dd094a18 | note | ○ 10m³ to 25m³ = 2 samples
5f08b246-9e40-53dc-b110-b87cd1015f19 | note | ○ 25m³ to 50m³ = 3 samples
9479aa4c-4a44-51bb-bfd5-ad4cbcb9be5f | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
3411c44c-3cb4-5c76-b475-36d22822e167 | note | – For each additional 50m³ and additional sample shall be taken.
42af09ee-2b4e-5048-9828-0b7978ac263c | note | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
d1e66519-8c3c-5fef-888d-112771346f65 | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
6c4e5824-d752-56f9-98f0-ac2426989eb6 | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
0795a373-9627-57f8-9681-77b1c5e14284 | note | – – – – – – – – – – – – – – – – –
e3db4cb3-72f3-5b09-9a38-f2e1bc751b7a | note | METHOD: Test
421ee960-e460-59ef-bef1-eba082046bea | note | – – – – – – – – – – – – – – – – –
0fb5d2ec-a577-5902-b47e-b3f426df6b71 | note | FREQUENCY: Each element
1cd70b9a-f8d6-5501-989d-7cbdb8331430 | note | – – – – – – – – – – – – – – – – –
177c9303-ee40-58a7-8022-cdcc58fedb3d | note | CATEGORY: IP
7c725aed-ab84-5acd-be37-670d066696ca | note | – – – – – – – – – – – – – – – – –
a2395f8a-f739-56da-bf84-d402015d09f0 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
c963d195-319d-55a1-b621-a3bdc3d48053 | note | – – – – – – – – – – – – – – – – –
4312ff3b-aa66-581a-82d7-e76bb1ca7299 | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
fc102a83-e40e-5725-b12a-4142e5cdb2ea | date | Date Completed:
| checkpoint | 5.3 Post Installation
7be0e97e-4883-5935-86fe-335e091b6079 | note | REFERENCE: IFC Drawings
a7b594ab-48bf-5ba9-8ff0-2d65cee2723a | note | – – – – – – – – – – – – – – – – –
269da9cd-b587-53c2-9cd3-1eb100133996 | note | ACCEPTANCE CRITERIA: Maximum fence post spacing to be 2405mm
92dd1cca-6db9-53ca-a2d2-4999c47b07b4 | note | ○ Max. post height 1800mm above ground level
aea03d3a-efc0-508c-8d6f-967ddee2ee75 | note | ○ Vertical Tolerance: ±20mm from the design line.
2887e71f-f076-5d0e-8224-ede89d44cc15 | note | – – – – – – – – – – – – – – – – –
21e536dc-2314-5985-a031-69b559d7d314 | note | METHOD: Measure
5dfb8add-3504-5f04-ac00-d4da44871076 | note | – – – – – – – – – – – – – – – – –
828f277c-b0ae-597a-a71c-ecc13d8c08c5 | note | FREQUENCY: Each post
1e4add52-d557-59dd-8f50-f713fe230061 | note | – – – – – – – – – – – – – – – – –
be635949-b9bd-5d41-bee9-db56c5ad7a9e | note | CATEGORY: IP
e5a96c5a-7ff4-5c95-87fb-a24283feef05 | note | – – – – – – – – – – – – – – – – –
ab757f79-bb39-5709-8b92-bfb5a9beb1ee | note | RESPONSIBILITY: SE/Site Supervisor
885e4fc3-e443-5d8f-8041-fbef380da26c | note | – – – – – – – – – – – – – – – – –
b5cc3da9-5579-5fe4-a3e6-f858663d47a1 | note | VERIFYING DOCUMENTS: This ITP
9d96f368-40f5-5d0e-89d6-5fa1e985baab | date | Date Completed:
| checkpoint | 5.4 Fence Panel Installation
80e3b523-80e3-555c-992c-f3166ab7f84b | note | REFERENCE: IFC Drawings
b164ced7-9bdd-5685-8d64-e20a91939ad2 | note | – – – – – – – – – – – – – – – – –
6a37cf4d-959b-53e4-90cd-6ad7ad2b1479 | note | ACCEPTANCE CRITERIA: Galvanised fence panels 1820x2405x55 to be fixed to fence post with 25mm U-clip, using TEK screw. A minimum of 2 brackets must be used and fastened to each post.
fffa8d16-11e2-5409-80e8-14457ab5fdef | note | ○ Minimum ground clearance under panels 50mm
ef82ab79-2a76-52bc-a476-0e3d773ae964 | note | ○ Maximum ground clearance under panles 150mm
772a9283-254d-57c1-ac88-be0c562af865 | note | – – – – – – – – – – – – – – – – –
d0993eea-a94d-5f63-bd48-5669bbaaff0b | note | METHOD: Visual
aa8af15b-90a8-554d-846b-e4909f483152 | note | – – – – – – – – – – – – – – – – –
b2b606af-8bb7-5bb1-940d-44df0d415952 | note | FREQUENCY: Each element
43be585c-b9ec-5794-8de3-8e0eaf9c19b2 | note | – – – – – – – – – – – – – – – – –
b9373452-96f4-589e-9e4a-720b74028433 | note | CATEGORY: IP
fed68a3e-6699-57e0-8060-1f0fd948a9d0 | note | – – – – – – – – – – – – – – – – –
f2eb4f60-312d-5346-b720-5eca542c3161 | note | RESPONSIBILITY: SE/Site Supervisor
4b76186a-1a69-5941-b439-e45cdd3f94ee | note | – – – – – – – – – – – – – – – – –
55e1a19a-02b4-5b84-8020-1b2524a6a5c2 | note | VERIFYING DOCUMENTS: This ITP
f5ddfad8-7b06-5d2e-b637-929d8b0cb105 | date | Date Completed:
| checkpoint | 5.5 Bracing
893f7922-7e8a-5692-822b-0d9c936e5319 | note | REFERENCE: IFC Drawings
98353516-01b1-50ce-9a9c-a9edd3c86eb9 | note | – – – – – – – – – – – – – – – – –
7f944f95-b498-544a-beb8-23713f1159a8 | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
305b03c4-0a5e-5a1a-aaab-155e9b02d3e5 | note | ○ Bracing to be installed on both sides of the fence at the fence corners
73096c2e-4c83-5d42-ac58-202886b91216 | note | – – – – – – – – – – – – – – – – –
c62cbf9d-cf1e-5b2f-81ea-07147d347cb9 | note | METHOD: Visual
e5fcf79a-f237-56c1-a1a3-4412b08da91b | note | – – – – – – – – – – – – – – – – –
d8104b95-218a-56ad-903d-6b5ac81bfb5c | note | FREQUENCY: Each element
07f662c5-1d73-5219-99ec-ef7a61208980 | note | – – – – – – – – – – – – – – – – –
a7328410-fe8f-577f-b34c-ad1a546d9b8c | note | CATEGORY: IP
d5ec3b50-51d6-54b9-b76c-abea0be336f3 | note | – – – – – – – – – – – – – – – – –
1a728f77-dd0f-5e94-9022-8fb6cca93d73 | note | RESPONSIBILITY: SE/Site Supervisor
8630fc16-909c-5865-9cdd-85058f254c0e | note | – – – – – – – – – – – – – – – – –
790af7e3-59c4-537e-adb8-14df5d6add40 | note | VERIFYING DOCUMENTS: This ITP
4e30d332-652e-5aa9-8882-8b4cefa6a1bb | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Fence Height and Track Clearance
985d91c1-9c8e-53a8-a1c2-927b578554b8 | note | REFERENCE: IFC Drawings
54b93a11-521e-5379-b39e-9563dbaf998f | note | – – – – – – – – – – – – – – – – –
294bf2f6-282e-5e50-ade4-c1e874d6a1cd | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
9e6a2699-8f24-5dc4-a5d2-27960cfed271 | note | – – – – – – – – – – – – – – – – –
7b21073b-b50e-5fbc-9e28-3aaa764904be | note | METHOD: Measure
71e28655-d65c-5d3a-8a10-3e39a3f2eba3 | note | – – – – – – – – – – – – – – – – –
ae2366aa-d5f8-5710-9958-71898105e6a3 | note | FREQUENCY: Each lot
451d53e8-06b2-5d1c-91ee-8f96e2056828 | note | – – – – – – – – – – – – – – – – –
685819b6-552c-50fc-a613-26169bedbb88 | note | CATEGORY: IP
4a0522b3-b862-5463-8804-c6f0d28c297a | note | – – – – – – – – – – – – – – – – –
f390108c-b1d5-5994-8a09-0e6596129aa2 | note | RESPONSIBILITY: SE/Site Supervisor
f3efbd69-a3b7-52c2-81ad-1c67ef4ecb1c | note | – – – – – – – – – – – – – – – – –
cd427421-e464-5eb0-bfde-a031f742768a | note | VERIFYING DOCUMENTS: This ITP
23529bbe-9cfa-5bca-8a01-13e1c1ff6d3a | date | Date Completed:
| checkpoint | Final Inspection
32fefd8a-277a-5027-8123-b9e40fc5a18b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
adabfadb-b493-59ba-bddc-c71ada7f8de4 | textbox | Name:
b0105938-e6c4-55c5-b060-aa8e4c6c4855 | textbox | Position:
e14a806a-20cf-523c-8a3e-a9bb7b85086e | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation Rev 0 | itp | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation | 14f7f739-a33c-4452-8ac1-15630ee3ba65
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7140b100-c3b1-50ea-b735-c0492424df85 | note | Document Title: ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation
b5a36515-3de6-5e8c-ae1e-b2892a1a5ebf | note | ITP Description: SSB-Post and Panel RW-Piling and Steel post installation
bfe8b5c0-6076-5274-a11b-ad7af79a1567 | note | Discipline (e.g. CIV/STR/RAIL): 171-STR
9a8df709-cd89-54cc-888b-be5dd0701e25 | note | Revision Number: 0
1e009a7e-a356-519c-bf33-e8c053e4fd91 | note | Revision Date: 29/05/2024
0f5cfda5-14fd-5b2c-abf0-ea42f54a7330 | note | ITP created by: Victor Mira
8b1cf9bb-0759-5561-9116-6426a1d20906 | note | ITP approved for use by: Victor Mira
48cc6efc-4f72-5859-82c6-7b695ed73ad2 | note | 1.1 Non Dependent
4b2d4d68-fab0-51bc-810f-107236c623bd | note | Reference: VicRoads Section VR 606 July 2017
6c2c79bc-ef2f-5d5a-923b-d6b82acf0b94 | note | 1.2 Non Dependent
49013930-edd6-5b87-a44e-43b0c31feb6e | note | Reference: VicRoads Section VR 610
30599074-7c21-57cf-beb0-acde7295d50b | note | 1.3 Non Dependent
d93a748b-7a09-5f2f-ae68-c6ea4944dacb | note | Reference: VicRoads Section VR 611
41fb889a-790c-5b44-9784-dc6274d29e67 | note | 1.4 Non Dependent
9e4ae9a4-87fb-571e-afed-b3fa095a21be | note | Reference: AS2159-2009
ec4378bf-7ffb-599d-b6ce-6b82e1d63c66 | note | 1.5 Non Dependent
065a6145-00a0-52ed-9a66-5d77579908e5 | note | Reference: VicRoads Section 630
4dc4958b-dffb-58b4-b7d9-76e5399b4eb4 | note | 1.6 Non Dependent
60d93e04-8a50-5224-a30f-3ff6741e5bb2 | note | Reference: AS2159-2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
4d01fde1-df6c-5797-9959-97a486034266 | note | REFERENCE: VR 610.07 Table VR 610.071
ed0e169b-01b0-5258-b707-b41ac5f13377 | note | – – – – – – – – – – – – – – – – –
45660aa8-09e4-5fe4-83cc-13978c6e364f | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
e440e2ba-151b-5dc3-b27e-436c11b25144 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
204c4921-b8b0-5bb1-b48d-86eca8390a59 | textbox | Enter: TeamBinder Material Approval number
7efde954-f89c-5fcf-9737-2d4ee4d069f8 | note | – – – – – – – – – – – – – – – – –
acf2dbea-f147-5437-985b-652f7c65593f | note | METHOD: Document Review
a4ebef05-450e-5c8c-8453-a4e5fe64967e | note | – – – – – – – – – – – – – – – – –
ac48882c-8cdc-5b2a-bc50-de3a2f4129b2 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
165776ce-885b-50f8-80d3-801283712003 | note | – – – – – – – – – – – – – – – – –
6b913a7b-6dd9-5644-a09d-178d6d6233c7 | note | CATEGORY: HP
cc777502-3599-5449-b01b-61a6af62329f | note | – – – – – – – – – – – – – – – – –
e9828e8c-cdf6-52cb-a725-6664fe54af73 | note | RESPONSIBILITY: Nominated Authority
80c1e2c4-002d-5fa3-a6b5-e723a0e3d366 | note | – – – – – – – – – – – – – – – – –
e983ef49-eb9e-55cf-bcb6-4dff9e57ea86 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f0bc8dfb-1a2a-5bf8-b138-fbda53cb9463 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
a1306511-a7e4-5059-be1f-1850ec69d2e5 | note | REFERENCE: VR 611.05 (a)
f664906a-0074-5804-b05a-a1810f37ac41 | note | – – – – – – – – – – – – – – – – –
44c774f2-dbcf-5622-a77a-0e7a6ffd34b3 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
22e49f5d-cc11-5f87-b43a-168ad86fffd6 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
7bd8f8d2-b348-5454-aaab-8033170b7d64 | textbox | Enter: TeamBinder Material Approval number
a5b44336-7085-5070-8e44-5ecb57ab83ca | note | – – – – – – – – – – – – – – – – –
5ce904d5-a25d-54f8-9bfc-fb5197b1a608 | note | METHOD: Document Review
174659b0-1a9f-5faf-adbe-18f7e9dc3acb | note | – – – – – – – – – – – – – – – – –
f293f669-5ab4-5b92-b088-5e2dda292b03 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
6b31b6dc-d7cf-5aed-8c9c-16e90df5c6c4 | note | – – – – – – – – – – – – – – – – –
f5bb3c33-40f0-5015-8075-7ec24415d920 | note | CATEGORY: HP
f5f2f0ff-a4f3-51b3-bbe0-7afed80bfa45 | note | – – – – – – – – – – – – – – – – –
3ce22be3-f9d1-5794-8c6c-d5c8ee52fa8a | note | RESPONSIBILITY: Nominated Authority
9b7ce79d-5950-5dbe-bcd4-ef7000eddf48 | note | – – – – – – – – – – – – – – – – –
7368ddbb-2cbd-57c9-b3b9-0082bd806eaa | note | VERIFYING DOCUMENTS: This ITP
9b155f05-478b-5f07-bd98-db59675d1497 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
e75ef907-3f3b-5b75-9463-4f03f8060199 | note | REFERENCE: VR 610.26 (a)
1b0ea237-c34d-56fe-baa0-7fc48328bedf | note | – – – – – – – – – – – – – – – – –
4638bd85-948e-5bf5-b17f-252c9b425975 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
ec5c04eb-e89c-509c-8d90-b4067fc80449 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
2b845e8d-4e8c-5414-9b3a-789a5a76abdc | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
65d7e147-7185-5907-a7d8-a32d8a47dc4a | textbox | Enter: TeamBinder Material Approval number
98396374-2d72-50aa-b4df-166320a3e811 | note | – – – – – – – – – – – – – – – – –
4d155396-ee5c-5fb7-b8d5-e517546ac791 | note | METHOD: Document Review
f6fc7b6a-6557-5969-aa77-ddb69ec5f2fa | note | – – – – – – – – – – – – – – – – –
08478185-3947-56c1-91da-6ba40f1e6d58 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
4664b749-92a6-56d0-9f38-85b296e68684 | note | – – – – – – – – – – – – – – – – –
05da2a88-f06d-5cf2-9d9c-d8f0dd310afb | note | CATEGORY: HP
81457136-660a-517c-9635-60826cbc0736 | note | – – – – – – – – – – – – – – – – –
61b53150-dee2-5437-ae1b-7314f70ad678 | note | RESPONSIBILITY: Nominated Authority
6f40b961-4175-57dc-936e-a63caa95c920 | note | – – – – – – – – – – – – – – – – –
c13e5734-70e4-58a5-8cfc-665bc13b27ad | note | VERIFYING DOCUMENTS: This ITP
c66e313c-ff10-53f9-9295-b58badffb647 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Steel Post
3a696e59-4384-5b6d-8d82-96c3f45d676f | note | REFERENCE: 630
d330c328-0070-5d3a-81a4-4988ae34b07a | note | – – – – – – – – – – – – – – – – –
20cad741-733c-539f-b71c-9313e8c0868a | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
6a46ffce-6de1-59d5-adb4-3a954f0476ba | note | Typically this consists of but is not limited to:
51e1d173-c9fe-50dc-b304-3ef297486e6e | note | i. Certificate of Compliance
0af4f554-e8ce-5b40-9063-ccbb92859bd9 | note | ii. Completed ITP
f9d2075c-3c37-56cc-9180-588bf4ffeb57 | note | iii. Weld Procedure Specifications
a4f511cc-96e9-5732-9671-c51bfc817307 | note | iv. Weld Procedure Qualifications
fc696e01-bd64-5cde-a87e-efc9eae045fe | note | v. Welder Qualifications
b073615d-c6ea-5d65-a02d-a55f4b065a94 | note | vi. Material Certificates and traceability
c97d888b-15f2-5fbd-9f72-1655fed40b60 | note | vii. Quality Assurance check sheets
31ac30f6-7261-5abd-9820-c1bdc7cf3173 | note | viii. Welding Consumable batch certificates
e6f9ac8f-1010-5650-8dfe-0d45b925f0f5 | note | ix. Coating certificate(s)
32d4b54c-6029-5318-83e7-52b5b73e9bc8 | note | x. Non-destructive Testing (NDT) Reports
762c979a-48a9-5486-a26d-1b1a46dc01f9 | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
fc512458-7141-55bc-81eb-3216df17002c | textbox | Enter: TeamBinder MDR Lot number
dd1de0c3-c647-5104-bdaf-a1c6a7f70d78 | note | – – – – – – – – – – – – – – – – –
0f6d3265-1ae6-554f-b9f2-1246bb1827ec | note | METHOD: Document Review
42d5c766-ede0-5eb2-a22c-cbeb1d075a2e | note | – – – – – – – – – – – – – – – – –
28909ae8-de28-54f1-ab59-1a727f04a4d1 | note | FREQUENCY: For Each Element
ebd565d6-377c-5a80-b92e-a5371b1c4c3d | note | – – – – – – – – – – – – – – – – –
bc27519e-349e-568d-82fd-f8e64db8ae12 | note | CATEGORY: HP
66d1ff0a-fff2-5c34-9186-5a08a4e8b121 | note | – – – – – – – – – – – – – – – – –
3ca3c407-fc2f-50e3-bea2-b78a47afb6a6 | note | RESPONSIBILITY: Nominated Authority
d214910d-6ce5-52ff-9a2c-e1a4c1b26e66 | note | – – – – – – – – – – – – – – – – –
927c3f06-5cb3-536b-aea4-ba1afdf98242 | note | VERIFYING DOCUMENTS: This ITP
9aeb307b-45cc-5e56-9a34-6637e5f791e0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.2 Piling Operations Work Procedure
2b52d7a4-d599-5a3f-90be-7f50f3298056 | note | REFERENCE: VR 606.03 (a)
71e4f91f-a5b3-579b-9ef3-0062babfc700 | note | – – – – – – – – – – – – – – – – –
ae913888-0907-5a57-8756-172378cbac0e | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
ef296558-7d8c-5ea7-8617-47e47c710cca | textbox | Enter: TeamBinder Approval number
4c79b510-fe23-5522-b45b-990bd3e813dd | note | – – – – – – – – – – – – – – – – –
b11a64cb-263f-577e-b202-f2ee22678da2 | note | METHOD: Document Review
60e67c4b-6e28-5c7d-a6d4-ea638375eb6f | note | – – – – – – – – – – – – – – – – –
0e10947b-3028-5381-ac18-0b7045f8fe24 | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
c9f934bc-1d51-5512-891d-551451d3c8bc | note | – – – – – – – – – – – – – – – – –
032d3f8e-c780-54eb-9551-65573e468c05 | note | CATEGORY: HP
3240c919-db6a-5bd1-bbad-aff00a6c7911 | note | – – – – – – – – – – – – – – – – –
ff42f41e-875a-5426-af91-f1e68eaf1df7 | note | RESPONSIBILITY: Nominated Authority
539cccee-efcf-5299-b957-197869e9f54d | note | – – – – – – – – – – – – – – – – –
ff920fb6-fc5d-5fd5-8288-388544101dd0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
442a967b-e016-579a-be4c-d155debff5dd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 Pre-qualified Pile Testing Consultant
c26dbb76-cdcb-5b58-97a2-56cf0be746ed | note | REFERENCE: VR 606.07
307d6d08-cf00-5972-b992-3496c8c77f01 | note | – – – – – – – – – – – – – – – – –
cd8fe6ea-13c1-56cb-9f4d-58e9d63f6451 | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
a6558e30-fc1f-5505-880d-6c5c17413109 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
82bf37dc-1eee-5b0c-960e-0dae3078f47c | textbox | Enter: TeamBinder Approval number
d46c4d00-bbfc-5cf5-9f23-43c3edfbbc81 | note | – – – – – – – – – – – – – – – – –
ac4fca68-296e-5f90-bf6a-9dac5e2a4061 | note | METHOD: Document Review
7cd656c5-4226-551f-9048-d074e506c34b | note | – – – – – – – – – – – – – – – – –
88de1d14-ed3a-578f-8f3b-737d8e5b7ea8 | note | FREQUENCY: Once, two weeks prior to testing
859fa1ea-d146-5ce5-8f29-07095a435c78 | note | – – – – – – – – – – – – – – – – –
646615a9-5539-50a2-a388-3a2dfc028229 | note | CATEGORY: HP
184f7512-3325-532a-ade3-029beb2a5572 | note | – – – – – – – – – – – – – – – – –
dc8fc8ef-c516-59ab-b852-7206f76e20cf | note | RESPONSIBILITY: Nominated Authority
a4e9ef1d-442f-56fe-ba6b-398c8e41dc00 | note | – – – – – – – – – – – – – – – – –
96666436-912f-57b1-b724-ebf04e81a9d6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5a103932-2147-5405-908b-096f430315ce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
e15f48b3-3044-564f-b1e6-ed98309b95b8 | note | REFERENCE: MRPA Quality Management Plan
6868a5ec-9848-52ba-b653-3fddd04d258a | note | – – – – – – – – – – – – – – – – –
7b71ad5d-9961-513e-ac7d-939ae1388f77 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on TeamBinder)
7eb928d2-ef6e-533b-9ed6-5de1215e2d6c | note | – – – – – – – – – – – – – – – – –
745393f9-1cd1-581a-b7f0-eb73f1b1de50 | note | METHOD: Document Review
b673b002-e60a-507a-8449-7626fec3e34a | note | – – – – – – – – – – – – – – – – –
c5f8db7d-50b3-5b82-a27c-dd1def3e8002 | note | FREQUENCY: Prior to starting Works and at regular intervals
0afd4ed6-b376-5604-acce-f5f776454a18 | note | – – – – – – – – – – – – – – – – –
3ccf6d39-e5ed-5d03-a8e1-992a8c1782a9 | note | CATEGORY: HP*
71434425-4ff9-507c-ad77-add02a4df2c8 | note | – – – – – – – – – – – – – – – – –
4f13e597-fb5d-5be5-9150-8d56ead96f78 | note | RESPONSIBILITY: All
57a54c4e-f38a-5668-b547-cd77515d44e3 | note | – – – – – – – – – – – – – – – – –
00bac684-a8c7-537b-98c7-8afb7f1968b6 | note | VERIFYING DOCUMENTS: This ITP
4f1fc353-d8ec-5d8b-b9fb-b7aab4b7fee7 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
382a811e-5864-5ecd-b10f-45b33bb394ee | note | REFERENCE: IFC Drawings VR 606.08 (a - c)
60fb1aed-9d53-5254-83cb-9b7402f3804f | note | – – – – – – – – – – – – – – – – –
574567ac-daed-53d0-bfb1-3dde29c506b7 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
4c6b6199-cdcc-534f-b0d3-4b1887c2b8ce | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
30c1f699-4669-5ba4-a723-92112570b9a7 | note | – – – – – – – – – – – – – – – – –
d17f8307-eb2f-5b29-8aed-96029b439ec0 | note | METHOD: Measure, Visual
9c1badc0-1286-5a8b-a7d9-4c01da17cd72 | note | – – – – – – – – – – – – – – – – –
8056dd1f-548d-5ce0-bfba-16d31e5999f5 | note | FREQUENCY: Each pile
f7117a85-3320-597a-b2dd-cc86f7ad09e0 | note | – – – – – – – – – – – – – – – – –
77805517-86f0-51d1-bd95-681b60374f1e | note | CATEGORY: IP
f4e6d03f-2730-5f69-971b-ab9920de03f1 | note | – – – – – – – – – – – – – – – – –
81515dc9-813b-5ccb-8b96-a51ed75ce02c | note | RESPONSIBILITY: Surveyor, SE
2feedf07-287f-5aea-a131-acab1dba5e5d | note | – – – – – – – – – – – – – – – – –
36ae7eb4-1557-5a84-a101-85545ecc77bf | note | VERIFYING DOCUMENTS: This ITP
0ae8f736-415b-51e0-a96d-efaf17e9f4bb | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
2869b4ae-fcbd-513e-ae46-f6153985e8d2 | note | REFERENCE: VR 606.04
a155a8d4-261f-5569-867f-47255c7d45bc | note | – – – – – – – – – – – – – – – – –
e3561f02-83e4-5199-86bb-8fa42abf4678 | note | ACCEPTANCE CRITERIA: Pile construction shall not:
08a7f770-cff8-55c5-b908-995c6b2f033c | note | i. result in damage to adjacent newly cast piles due to ground vibration.
b7f4057c-dcfc-576b-8b0d-89166f680dd1 | note | ii. commence within 2.5m clear distance from newly cast piles if that pile concrete strength <15MPa
4b9b25da-cd14-534f-a187-3283007da12b | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
f1dc81ac-afd7-5256-b86f-b49a9aacb54b | note | – – – – – – – – – – – – – – – – –
8f2f98d5-cb37-5c72-81f2-6726788e89ae | note | METHOD: Measure, Visual
10b76026-a6ca-59e1-83c9-16c1b24a0b12 | note | – – – – – – – – – – – – – – – – –
cbd1e818-ba12-5e5a-879e-f2e92236b422 | note | FREQUENCY: Each pile
0110935a-fc51-5869-a59e-aca8c603b8ec | note | – – – – – – – – – – – – – – – – –
858bdeea-e8dd-5a43-9ca0-d590385b09d8 | note | CATEGORY: HP*
e1b34ee0-2635-597d-9b9b-ef372ea03dad | note | – – – – – – – – – – – – – – – – –
68705dc0-4dab-5d42-9c8a-292f392f356c | note | RESPONSIBILITY: SPE/PE
c0e72493-f6d7-5c26-88de-d32a224fc6ed | note | – – – – – – – – – – – – – – – – –
301e7bb5-fa48-51d2-ae39-a34ec13c22a9 | note | VERIFYING DOCUMENTS: This ITP
f9f77b81-9f01-5fa5-97e6-63ff7a241038 | date | Date Completed:
| checkpoint | 4.4 Steel Post Material Inspection
fe156f90-243e-5741-a58c-e9f459be3b44 | note | REFERENCE: IFC Drawings
d155614b-ec87-518c-8b7f-130316ad9516 | note | – – – – – – – – – – – – – – – – –
7d99e472-6e30-5974-a8d4-761349bf241c | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for:
1a59105c-cd5a-588e-bae0-136ac6ae9d8e | note | – Damage & distortion, twist
e58b500a-8655-5a33-8d65-7da192ac168f | note | – Defect to the coating.
49c213aa-0259-5efd-9695-f692769ba51f | note | – Defects to welding between bearing plates and the profile
421978e4-5f0d-5293-bbdc-5c6ace4cef00 | note | – – – – – – – – – – – – – – – – –
b2de9571-0e50-5300-bef1-00586488409f | note | METHOD: Visual
5f3e4e41-acff-5e59-a028-e3624361eb07 | note | – – – – – – – – – – – – – – – – –
a8dee5d1-3f6f-554b-8529-643887ba851b | note | FREQUENCY: Each delivery
339c6929-3313-5156-bb9a-1e01ca9ce47e | note | – – – – – – – – – – – – – – – – –
a4b132ff-d4ca-58a1-8ddb-9e30a56409ea | note | CATEGORY: IP
9014f903-4f8c-5f15-bbba-dbd60da5aec6 | note | – – – – – – – – – – – – – – – – –
bd8dad89-39b3-5f24-b8b9-2223aedb5c11 | note | RESPONSIBILITY: SE/PE
bf876baf-73d9-5401-9336-ee1f13ff504a | note | – – – – – – – – – – – – – – – – –
e853e839-7cb2-5be4-9ce9-8fae05cff4c0 | note | VERIFYING DOCUMENTS: This ITP
53fcc659-a7c5-5e10-9740-825fdc0513d6 | date | Date Completed:
| checkpoint | 4.5 Steel Post Material - Correct post
10713a82-c2a4-584f-9c5c-aba95e911d42 | note | REFERENCE: IFC Drawings
44e0f7c8-49c4-516f-88db-19d22a8a32f9 | note | – – – – – – – – – – – – – – – – –
02287c80-c479-5afe-ba6d-306233a2c8e7 | note | ACCEPTANCE CRITERIA: For each post:
1e37c07a-0fc4-527d-bfa9-187080b870fa | note | – Check the profile of steel post (Type and Size)
c99646f3-f0e9-53b7-8d36-16cc01f55f1a | note | – Check the length
701c4b45-b7f7-56b6-8a66-35f012f118eb | note | – Check the Bearing plates number
de3524f7-602f-5788-b0d6-ee324ae63ef9 | note | – – – – – – – – – – – – – – – – –
14db8f2b-4db2-5d9a-8a09-d46f0ab88c68 | note | METHOD: Visual, Measure
938c6ba7-5277-5762-ac0a-cc1d99c8aa01 | note | – – – – – – – – – – – – – – – – –
2562ba4a-7b02-5385-ab43-01538330e7cf | note | FREQUENCY: Each Element
67c1fd4e-85ef-599a-ac77-10343dc26402 | note | – – – – – – – – – – – – – – – – –
e3b411af-0cf1-58e8-ac3c-7c386bc527ea | note | CATEGORY: IP
6c9ae534-d243-585b-b54c-2ed7f90b4b8a | note | – – – – – – – – – – – – – – – – –
aca245df-752d-5fa9-9678-3461517317b0 | note | RESPONSIBILITY: SE/PE
1172b581-73c0-56da-8200-d2af5985f700 | note | – – – – – – – – – – – – – – – – –
3c0917d7-39a9-5449-89b0-a04f33e70d94 | note | VERIFYING DOCUMENTS:
09c412fe-5c32-5c34-8039-cae1e1269b17 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Boring Operations
64463eef-7f0e-5152-a52e-e63e137313e9 | note | REFERENCE: IFC Drawings VR 606.03 (a)
3b0128f2-2271-584d-a48b-36fc6d3c88b4 | note | – – – – – – – – – – – – – – – – –
bfe64dfa-9bba-508f-80e2-e7b76865ac17 | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
a3bf4a23-76a7-5f2b-9044-a5b68ef19667 | note | ○ Excavation clean and de-watered (where applicable) for inspection.
06be78e8-1867-5d11-b7c7-b73930f56e5e | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
d3d4f165-48d8-5274-b5ed-e710329ea45d | note | – – – – – – – – – – – – – – – – –
eca18119-61ee-5c6d-a8f0-9776b83cfb50 | note | METHOD: Measure, Visual
baba1778-c8ed-51cc-9580-866305ccbc38 | note | – – – – – – – – – – – – – – – – –
6f3789db-9665-5e72-bbf6-2c4125d2fdd6 | note | FREQUENCY: Each pile
9df92a5a-ba26-52d8-9588-6c1aed133c17 | note | – – – – – – – – – – – – – – – – –
137936fc-a8ee-50c1-ade7-4a8431d0957d | note | CATEGORY: IP
1e90f30e-9cc6-583f-a9c8-96e6f4019e21 | note | – – – – – – – – – – – – – – – – –
37894879-aec6-5944-af04-eb4a04ea6e67 | note | RESPONSIBILITY: Surveyor, SE/PE
00604b07-708d-56c0-8160-0af4cce350de | note | – – – – – – – – – – – – – – – – –
21eeee03-f5a1-5fcd-aafb-e32f02f8857e | note | VERIFYING DOCUMENTS: This ITP
c1242fa2-f679-5a09-b427-9f31e3190653 | date | Date Completed:
| checkpoint | 5.3 Inspection of Pile Excavation
85368da5-a0e4-505b-8ca1-8ac6603df827 | note | REFERENCE: VR 606.05
517d3240-2140-5f2e-b3fd-8e7933feeaa2 | note | – – – – – – – – – – – – – – – – –
16577933-8fb9-50e6-9bd6-778746c04810 | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
a8579572-90ff-50c8-91cc-1ce1434691e6 | note | Attach: Geotechnical Field Sheet or Report
d7cb0187-e94e-5052-bff9-2642b55bdde1 | note | – – – – – – – – – – – – – – – – –
bb1fe919-32e8-5605-b2a0-82cd5ebad42c | note | METHOD: Measure, Visual
5862d057-7dc8-51d1-ab8e-45272981473a | note | – – – – – – – – – – – – – – – – –
36c47ba5-99ec-5605-af00-7417b8a4e3ad | note | FREQUENCY: Each pile
9726b9b6-f3bd-567c-b38d-119984f8b0ff | note | – – – – – – – – – – – – – – – – –
658c91a3-670c-5706-bfd3-376c0f6a1007 | note | CATEGORY: HP
8cc10b7f-6283-5f51-84b4-b8db13a7933d | note | – – – – – – – – – – – – – – – – –
5e86cb93-ad05-5128-a413-2f72b1e12931 | note | RESPONSIBILITY: Geotechnical Engineer
2a7e8a8b-5aa3-5886-bc94-7a2d2137bec9 | note | – – – – – – – – – – – – – – – – –
36891f8e-2ae7-585c-bbb7-879de3cceb20 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
6903b545-f9b6-56c9-9134-c1ba09ac0fb1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 Reinforcement - Placement
239b1518-d78c-5847-a5c4-719c404bc77b | note | REFERENCE: IFC Drawings
117e3712-a140-5778-ba26-6c253fd1556c | note | ○ VR 611.06
34d1bdee-a54e-553f-8750-9c6864e52db5 | note | ○ VR 611.09
a90a3be6-1732-5e91-b4cc-302202fcaebf | note | ○ VR 611.10
653efdb7-796f-5fd6-9a4e-b460488b4f04 | note | ○ VR 611.11
5e90495e-7484-56db-bb93-ab6326c6e891 | note | ○ VR 611.12
94aa25e2-5b2e-50d7-a3c8-54f3e29fd0d1 | note | ○ VR 606.06 (a)
3b9e51d5-071e-5239-885e-f79ef87cce52 | note | – – – – – – – – – – – – – – – – –
63d8d4b9-706c-5439-a909-280a8f1b2f43 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
9c823025-7f91-56a9-bb2c-a48f57eecada | note | ○ Projecting reinforcement is the correct length and location.
345064fb-28e5-5243-a466-746f793acd51 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
ac35d507-2280-5979-8565-55b768ac062b | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
6ba45e03-3042-5dcd-ace2-4787ee3220bb | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
7fb2edd7-4b77-5e8b-abd8-905d39245e48 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
07e60652-ae90-526d-b59a-6866242130a4 | note | – – – – – – – – – – – – – – – – –
02cfbed7-04cd-5681-a22a-c2349379f1e4 | note | METHOD: Measure, Visual
207605d5-b399-5320-bffb-0d9bb1d3dc9d | note | – – – – – – – – – – – – – – – – –
ba1e3d82-731f-5ca5-be05-7d926aa6e3d3 | note | FREQUENCY: Each pile
1885385a-b93b-5db6-9c05-cd827d4d1959 | note | – – – – – – – – – – – – – – – – –
b72453a0-f34e-50e2-bbb8-9a711fc15dd5 | note | CATEGORY: IP
5e2a7821-ef4e-5619-9fd0-e92fd5c4cce5 | note | – – – – – – – – – – – – – – – – –
ffa4182a-a4b6-50d9-ba61-f4146969b5a4 | note | RESPONSIBILITY: Foreman, SE/PE
60e00d43-673f-551d-b873-31dc8dc9ace0 | note | – – – – – – – – – – – – – – – – –
2ab608f1-48b6-5674-9d48-c3d9cae21af0 | note | VERIFYING DOCUMENTS: This ITP
e58a5383-3b7f-546b-ac99-e03e7462f39f | date | Date Completed:
| checkpoint | 5.6 Cast-in Items-Steel post
2755dacb-2475-54a8-bef2-e3bebb9cfe64 | note | REFERENCE: IFC Drawings
ba8e822b-9535-5141-9774-4af8beb1cdb4 | note | VR 610.46 (a), Table VR 610.462
fc51d21a-ffbe-5a1e-8097-b5a8654e07bf | note | VR 610.47 (a), Table VR 610.472
deba91d1-4fe3-54fa-aabc-7f9829c65a5e | note | – – – – – – – – – – – – – – – – –
b9292f24-3dcd-50b2-a776-a8508582e187 | note | ACCEPTANCE CRITERIA: For each post:
a601757e-a826-5114-98a2-b4288ca91bae | note | – Check the profile of steel post (Type and Size)
1853042a-3de4-55fa-b5d7-2c6846b34fb7 | note | – Check the length
454b0e1f-bfe2-5a33-8599-3008404f519a | note | – Check the Bearing plates
1862e553-fe6e-541b-851b-0fe4d25b4354 | note | – – – – – – – – – – – – – – – – –
77d0fad8-8b6b-56ff-bdc9-73448bee56e6 | note | METHOD: Measure, Visual
99f8c40e-0718-56a5-b7cf-0f0770044543 | note | – – – – – – – – – – – – – – – – –
ace41e41-e4b9-502d-88db-dfbd0ac635ab | note | FREQUENCY: Where applicable, each pile
90ced542-5126-5b5c-ade8-80da9d46db6f | note | – – – – – – – – – – – – – – – – –
b7c79e12-4c4d-503d-8eda-c62e61a1273a | note | CATEGORY: IP
fb8198e2-2d66-5dbf-96a6-baf0ed9ec858 | note | – – – – – – – – – – – – – – – – –
15c3a258-cb56-547a-9a1b-2914aea6de41 | note | RESPONSIBILITY: Foreman, SE/PE
1fafc9f2-cae2-5777-a2fc-80e0fa7b6bba | note | – – – – – – – – – – – – – – – – –
050f3820-12e1-590e-b1fd-c8262788e357 | note | VERIFYING DOCUMENTS: This ITP
6d4e8341-5951-59cd-b629-eee7761ab47f | date | Date Completed:
| checkpoint | 5.6 Cast-in Items-Steel post installation
1d545ff2-b1e8-57a2-a3fa-8a106b3d043b | note | REFERENCE: IFC Drawings
fe40d45b-a931-5b3e-946d-69532ecaf9c1 | note | VR 610.46 (a), Table VR 610.462
b5a6ec51-2e41-5b9f-9fb7-75d9023218f9 | note | VR 610.47 (a), Table VR 610.472
61d9385d-ccf0-554b-9084-1e527cb62944 | note | – – – – – – – – – – – – – – – – –
321f7330-596e-55e9-b233-8df2c4b1829f | note | ACCEPTANCE CRITERIA: For each post:
30e82f82-bc34-5760-b4ec-cb2fc3e1858c | note | – Check the orientation/Rotation
5b97d3c3-ad8f-5fc6-894a-afb3dcf4a1d7 | note | – Check the Rake/Plumbness
f94afd17-c60c-558f-9665-49139845f14a | note | – Check the embedment and above ground height
09acf390-4599-5997-8abe-4f339155f3ab | note | – Check the level of bearing plates to accommodate for the panels to be installed horizontally
14037e15-7539-580c-83cd-d20349073a46 | note | – – – – – – – – – – – – – – – – –
e4d2f7d9-f65d-5992-bbc6-746c2093272e | note | METHOD: Measure, Visual
86024723-d82b-542c-b904-11f802ae59a0 | note | – – – – – – – – – – – – – – – – –
3bbfb51d-dd3d-569c-9dac-7ad93fc35234 | note | FREQUENCY: Where applicable, each pile
66d2153b-e264-513a-b9be-bfe6afa0d4d7 | note | – – – – – – – – – – – – – – – – –
7abaded4-a6fd-596e-ab74-77b2b8f46bb0 | note | CATEGORY: IP
f8ce6f28-24f1-5bf6-bed1-b38f221378e8 | note | – – – – – – – – – – – – – – – – –
a7dfe08d-9974-5686-bf9a-1dfbc42c7ca4 | note | RESPONSIBILITY: Foreman, SE/PE
7c56b5ec-d97a-5a70-a455-ae8f0a278e08 | note | – – – – – – – – – – – – – – – – –
aa0e929d-a02c-5062-be40-92316e0d17d7 | note | VERIFYING DOCUMENTS: This ITP
4f86e12d-e8e0-514b-aafe-5bbee42e4cb0 | date | Date Completed:
| checkpoint | 5.7 Pre-pour Inspection
3cf48b78-ba2c-5975-a1e5-0e6bbdad3169 | note | REFERENCE: IFC Drawings VR 610.18 (a) (ii) & (iii)
78be15d6-51c3-5fa6-9d80-5e1056721fe7 | note | – – – – – – – – – – – – – – – – –
333e42bd-03df-51a9-910e-089e45171c86 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
39d20eaa-950f-5d1a-ae0f-6a174e595ccf | note | ○ All foreign material has been completely removed from the excavation.
b1374d7e-b937-5e3c-bad3-1d4b428912f2 | note | – – – – – – – – – – – – – – – – –
d83919ef-a908-5cbd-a371-9b462df11486 | note | METHOD: Measure, Visual
ace6d1f5-a634-5f45-86dc-2b991f729b0d | note | – – – – – – – – – – – – – – – – –
4c74a63e-3f44-5b08-a90a-429193a95222 | note | FREQUENCY: Each pile
3860077e-9027-5112-937f-036e24675824 | note | – – – – – – – – – – – – – – – – –
1761344a-e0e7-5340-aa04-15c67c5f8f9d | note | CATEGORY: HP
0d31f4d8-a903-5b59-be37-117b679d4c83 | note | – – – – – – – – – – – – – – – – –
b2bb3971-1d17-5adc-9629-42683ab1bcb2 | note | RESPONSIBILITY: Nominated Authority
5dfae186-8796-5289-bcb4-f652001fe177 | note | – – – – – – – – – – – – – – – – –
f918decd-0e91-5d59-9cc4-d4a3820d416d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c5a7da07-578f-5b71-8843-4dcf2e39fc5b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 Weather Conditions & Evaporation Limits
448a25ab-8153-5412-bf57-8f296d8f28c9 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
1310a9d6-6c2b-52c3-8860-d919f26994e2 | note | VR 610.17
b8b9df02-a4d1-5b41-bd54-830bcd573ab2 | note | VR 610.17 (a) & (e)
6a7e27ed-65b2-544f-bce8-27a08a29cf1e | note | Table VR 610.171
ded4a581-f42d-5d67-8ded-8be71c1927a3 | note | – – – – – – – – – – – – – – – – –
f6a6dce0-8024-55db-ba33-08a1ac1175bb | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
54e820e8-d383-5a5b-975b-aeefcec9261f | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
4782fd62-d659-5b2b-ae10-31db44eaeac3 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
1f168883-03ff-5985-a404-d0f83c3e9875 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
05bcef1d-8672-55e8-9c92-3599987bb829 | note | Record: Required information on the Concrete Pour Record.
5cf03152-ce08-5da3-80f8-f2ffe7ed37b6 | note | – – – – – – – – – – – – – – – – –
e7e24418-9427-58e4-a02f-f593bd8bcf02 | note | METHOD: Measure, Visual
b87fd7b3-a7be-58e4-8b0d-4167b65cf11a | note | – – – – – – – – – – – – – – – – –
d6aa7779-87ca-570a-97a3-3f13a3b8dcbd | note | FREQUENCY: Each pile
b1ccc87d-5b9a-5678-8cc8-cb90f91ac09c | note | – – – – – – – – – – – – – – – – –
c94396c9-251f-50bf-ab46-b4ab16fbf2c0 | note | CATEGORY: IP
cbcfc5f9-31c0-58a0-8748-d1fed2954684 | note | – – – – – – – – – – – – – – – – –
ac90f665-c3ea-5356-999d-d4f1d17e9239 | note | RESPONSIBILITY: Foreman, SE/PE
cf713eaa-c132-53b9-9147-752a12620a83 | note | – – – – – – – – – – – – – – – – –
16e6d1b1-ba76-5bea-a472-4f81b66c3007 | note | VERIFYING DOCUMENTS: This ITP
f99735fd-9955-50f7-be81-6180324e9582 | date | Date Completed:
| checkpoint | 5.9 Concrete Testing - Sampling Frequency
966c9ee2-6535-557e-850d-82b0b721ee02 | note | REFERENCE: Site Sampling & Testing Procedure VR 610.16 (b) Table, VR 610.1, VR 61
1f4e1dd2-2653-5b77-a205-80f436119f88 | note | – – – – – – – – – – – – – – – – –
545e4c13-aa74-59da-8a54-b07d2f6184e3 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
50b79361-51b4-5c53-b0da-5feea8999eaf | note | 0m³ to 10m³ = 1 sample
f9fef681-b6c6-5e0c-ac2e-780ff7ed7744 | note | 10m³ to 25m³ = 2 samples
195fb19b-95cd-5cdd-b2ee-3331ae77b6d2 | note | 25m³ to 50m³ = 3 samples
4c1ef7ed-9ea6-54c3-a49b-27101bdb9a04 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
35bbd97e-ddce-51fc-9704-614ce95cca16 | note | ○ For each additional 50m³ and additional sample shall be taken.
e0f9cb1a-6062-5369-9e53-4d9cca9ab6ce | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
c29bc44d-f491-5ec0-bde9-7088622811f9 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
d92b95a5-8c32-5110-a8d1-a1ff6a6fd57e | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
f79dfdb6-355a-5c0b-a0bf-8fc0f4829c78 | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
3e4eb771-08c2-5c2d-8287-4d7a1d8173b8 | note | Record: Required information on the Concrete Pour Record.
e293a2b7-1d1f-5b6f-bcf1-1df5833d45c3 | note | – – – – – – – – – – – – – – – – –
ebce1f93-5a51-5cf3-a106-a228adcb4c03 | note | METHOD: Test
8e6cec3b-4446-55ed-84f8-9797d5bd6b9c | note | – – – – – – – – – – – – – – – – –
2a7bec0f-0184-5346-981f-3e81a1079ec3 | note | FREQUENCY: Each pile
91a70a6a-0f6e-55f0-9213-e948233780fc | note | – – – – – – – – – – – – – – – – –
e41dd3a4-b7b4-52bf-9545-92191b4a22a6 | note | CATEGORY: IP
7cceec54-7e4b-53ab-8164-8646323e3319 | note | – – – – – – – – – – – – – – – – –
775cbfb5-5aaa-5558-8a06-e2064b6b857c | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE
0d3f066d-bd8d-56fb-b0cc-80373a342154 | note | – – – – – – – – – – – – – – – – –
bd4de3d3-b00e-53d7-af3d-924414fb15ae | note | VERIFYING DOCUMENTS: This ITP
2b8d62fb-9265-5271-ba5a-168eeb1a9a7e | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
0a22386a-c3a7-5087-af06-32a36722f7ee | note | REFERENCE: VR 610.13 (b)
8e93cd67-d97e-5aa5-a967-2bb0cddf1e39 | note | – – – – – – – – – – – – – – – – –
73f3f150-a35f-54cf-b84a-cb770f746cc9 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
5a36121e-630e-5b69-8a46-abbe68acae62 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
35a7e0a1-8515-5630-bd7e-82296dc4fd4e | note | ○ Passability = ≤10mm (aggregate height differential)
210af2dc-b0d4-577d-8e68-9489a3119e15 | note | Record: Required information on the Concrete Pour Record.
60bd29b5-0bb5-5415-9f78-5a8ccf5db073 | note | – – – – – – – – – – – – – – – – –
43e73991-d161-51ac-8652-ea18a5992f94 | note | METHOD: Test
e800b447-0edf-55b4-ab5f-d8bda7a6198d | note | – – – – – – – – – – – – – – – – –
63085646-59cc-5cd4-94b7-464f3889a6b8 | note | FREQUENCY: Each sample of Self-compacting Concrete
12c01ed3-a487-57a5-903f-405632aef06d | note | – – – – – – – – – – – – – – – – –
de25ca48-8d9a-541e-88fc-28bf259721e2 | note | CATEGORY: IP
5e81bf42-bc0c-5843-9ae5-badc3ff380cb | note | – – – – – – – – – – – – – – – – –
1e8827b6-52bc-5e0d-ba84-c373f88f9c32 | note | RESPONSIBILITY: Concrete Tester
b1884462-9696-5151-b874-ed7a6ec20b5e | note | – – – – – – – – – – – – – – – – –
7e8ccb66-c000-5aed-8b52-7f5479e95385 | note | VERIFYING DOCUMENTS: This ITP
38476caf-d168-54cf-aaa1-4c14ef4e37b5 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
6333830b-1c5e-59db-a4de-c0a0517d5ed2 | note | REFERENCE: Site Sampling & Testing Procedure VR 610.16
7d27840e-7e00-521d-ad5a-c43e2dad842c | note | – – – – – – – – – – – – – – – – –
61dc7057-2fbe-53db-8e9b-ea1ae7f3bba2 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
79c0d5ab-4c6e-5597-8bf6-80000f140cc4 | note | Record: Required information on the Concrete Pour Record.
a7c05c3e-2aa2-583f-a953-4445afc66d7e | note | – – – – – – – – – – – – – – – – –
948c52ae-f2de-543d-8fac-8b7caf22d344 | note | METHOD: Test
d743a972-3468-5429-a8ab-fb4084e0afa3 | note | – – – – – – – – – – – – – – – – –
4aca3269-b415-591f-a5f6-2f5bac98b661 | note | FREQUENCY: Each sample
1ca5b41b-ddad-5a0f-9e6e-7f35537d46a8 | note | – – – – – – – – – – – – – – – – –
e50d8140-cd5a-5358-b2da-f8dbc927263d | note | CATEGORY: IP
62c886cf-1adf-54ed-8c85-d135e8c5773c | note | – – – – – – – – – – – – – – – – –
3ba86e0f-7449-554b-815e-9a887ace3d09 | note | RESPONSIBILITY: Concrete Tester
263bcbf4-990c-5a63-a8a4-229d4c83b98e | note | – – – – – – – – – – – – – – – – –
d4340efc-d79f-51f9-b399-3498e9480bf2 | note | VERIFYING DOCUMENTS: This ITP
92b7dd20-a40d-58bd-96d0-716448fb3526 | date | Date Completed:
| checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
68997334-aec8-5ef2-bbd2-99e2ebfde4b4 | note | REFERENCE:
f86343e5-720a-5781-ab0d-bbfe8928b38d | note | VR 610.18 (a) & (b)
e98853b1-a8ad-5096-953a-3a668b80781b | note | VR 610.18 (d) (i)
f875c851-3f31-5d6c-b424-8062e82b5a18 | note | VR 606.06 (a & b)
3745e9a1-63d0-5dd9-8d2f-a5af69533135 | note | – – – – – – – – – – – – – – – – –
6c600c4d-337e-58a9-831a-f4d68ee97cbd | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
788c168d-2678-53b4-875a-e86ed01354f8 | note | ○ All concrete batches are traceable.
4e57e955-4d89-5e79-ad22-2325107e0f77 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
7b915a41-3d97-5bf3-96fe-629960d2096e | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
7a6285dd-d05f-5b8e-b452-04b1b703b7c7 | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
300dcd15-ac67-52f4-be22-07507f787361 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
ac0b9a2a-f0e0-5020-a6ec-1f5b8ef1ab63 | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
24ccb69f-c94d-5ff4-9ba3-e61600929dbf | note | Record: Required information on the Concrete Pour Record.
5741c7c9-cc9f-5f16-bcfa-e630695666fc | note | Attach: Concrete Pour Record
711f7603-5afa-53d2-9381-ed8de029ea0f | note | Attach: Concrete Dockets
00f54863-975d-5900-8fec-a11eb584c3c6 | note | – – – – – – – – – – – – – – – – –
794e7f6e-77d5-5ac7-b5ca-c3ed989c96d3 | note | METHOD: Visual
a70ccff7-f704-5962-ac5c-29994d46a70e | note | – – – – – – – – – – – – – – – – –
899832b6-e93e-56a4-b1a9-4c905c330b52 | note | FREQUENCY: Each load
dd819fec-a9b7-56ce-9d55-4867b8497da5 | note | – – – – – – – – – – – – – – – – –
3ca61870-64df-52b7-a978-a586af064600 | note | CATEGORY: SP
dfd49709-7599-59c9-84fc-1a8e6c20516a | note | – – – – – – – – – – – – – – – – –
aa08d87c-09a3-5620-8b8e-25a69d4c5aa1 | note | RESPONSIBILITY: Foreman, SE/PE
e450e448-2f47-5b9c-a5d2-90995bf4d939 | note | – – – – – – – – – – – – – – – – –
533dec9f-dc20-5080-9552-7aa1bcbb3617 | note | VERIFYING DOCUMENTS:
2916ba73-825b-5015-b69f-917bcee8a1bb | date | Date Completed:
| checkpoint | Surface Finishes-top of the piles
7424d6c0-dcde-5664-b202-da0b3afbeed0 | note | REFERENCE: IFC Drawings
2ff61f34-dd66-57da-b0dc-4f6bddec6cba | note | – – – – – – – – – – – – – – – – –
95f7c28a-701d-5980-9697-e6bf6ceecca0 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
4b4e6637-c79e-567a-b70d-e00ade3c4253 | note | ○ Provide nominal fall to top of the pile towards outward edge
fe01f8b1-8d9c-552f-99d1-96dcba06ebba | note | – – – – – – – – – – – – – – – – –
ed5081af-c643-57dd-afba-dde1a4494866 | note | METHOD: Visual
c0714e3b-8c55-5c20-9257-fbc35e97a805 | note | – – – – – – – – – – – – – – – – –
ebd4cdaa-7212-5a16-955e-4add9d30b095 | note | FREQUENCY: Each pile
eac981c9-a6a6-520e-9eff-9795f18d62fb | note | – – – – – – – – – – – – – – – – –
e9047e94-6df4-5b1d-9a10-5962734e960e | note | CATEGORY: IP
058c12b4-228a-53ec-be05-629e777af4b6 | note | – – – – – – – – – – – – – – – – –
d0e74042-ccbd-520b-8761-50909679db41 | note | RESPONSIBILITY: Foreman, SE/PE
0d05e758-e7aa-553a-95c4-39d99a03fbc3 | note | – – – – – – – – – – – – – – – – –
5164ced5-eb4d-5ab6-a1c1-397478541ee2 | note | VERIFYING DOCUMENTS: This ITP
5b24603c-dab6-57db-a350-8a30cc09918f | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.2 Compressive Strength Test Results
2b745e41-42f8-5bfc-b7a2-386636c9b0b9 | note | REFERENCE: IFC Drawings Table VR 610.05.051, VR 610.16 (g)
8be2cf52-ad45-5aad-a450-48d5ae58cbf8 | note | – – – – – – – – – – – – – – – – –
9a58bc40-0a71-5552-a3dd-ceae2a1d0c19 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
ac28aee1-2c9e-57ca-b6ab-ea483f331eb3 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
5e737474-82f9-5363-a36c-ad012af938ff | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
650bf853-ae0e-5161-bf14-ada0921f7326 | note | Attach: Compressive Strength Test Results
ccde3bec-e843-5af8-9c69-c5192231ad7d | note | – – – – – – – – – – – – – – – – –
6d72a8fc-6626-5bd1-b766-8609899df474 | note | METHOD: Document Review
79bca243-efaf-56a4-9fb3-4d8dc7e2204b | note | – – – – – – – – – – – – – – – – –
b9b26f3e-a70b-577b-a755-96609fdd55fe | note | FREQUENCY: Each cylinder
fc45a153-2067-52f9-a734-db868ebed8cd | note | – – – – – – – – – – – – – – – – –
9d74e5ac-70f6-59a5-bff6-df955f3356d4 | note | CATEGORY: IP
3bbd35ef-b412-5fb6-9c91-c1daecda7c5b | note | – – – – – – – – – – – – – – – – –
e5eacc17-7a70-5c4f-aa46-3fda3a0e821a | note | RESPONSIBILITY: SE/PE
aea4870b-4f7d-5810-a6c2-43190a66e891 | note | – – – – – – – – – – – – – – – – –
6d0f36d3-8e59-5afa-8c95-938189f6d989 | note | VERIFYING DOCUMENTS: This ITP
e3591bd9-8972-5216-94db-9c5b9107a602 | date | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
e20dcbe5-ea37-5162-bb5a-8dda4d0e4be3 | note | REFERENCE: VR 606.07 (a, d & e) AS2159 Clause 8.8
71ef47e7-817c-55e0-9e57-2dd5d97f7e12 | note | – – – – – – – – – – – – – – – – –
019f7858-cacd-5e45-bf00-0e03a7490003 | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
8e784805-4859-5daa-b3fd-e44f2b20ce9d | note | ○ Cross-sectional area = ≥95%
7785bb29-21aa-51cd-b09d-a5dc997a5f91 | note | ○ If any test fails, all piles shall be tested.
0b9bc60e-79c0-5d92-aaa8-5a3fe2ae1aea | note | Attach: Pile Integrity Test Report
17d8f78f-f26d-5c47-a00e-0fee5418aadd | note | – – – – – – – – – – – – – – – – –
ad3d9dab-c025-5895-ba5f-fb20a0da0ab7 | note | METHOD: Document Review
43011c3a-60d9-55f5-95c8-0ae6240c35af | note | – – – – – – – – – – – – – – – – –
00778f2d-d587-5bc0-a0d2-675cb263bff0 | note | FREQUENCY: Piles #1 - #6.
596feca4-62fe-5fed-a8ac-c3109e560692 | note | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
120744c0-4d16-5e42-a2cd-44fefddfb46e | note | – – – – – – – – – – – – – – – – –
590e2274-9315-5ea9-92b8-37b55ca0eb10 | note | CATEGORY: IP
1014b85f-3825-57ed-b31f-6766862c2b19 | note | – – – – – – – – – – – – – – – – –
1b20a77f-5047-5493-8126-ba84536afbb1 | note | RESPONSIBILITY: Testing Consultant, SE/PE
ec15426e-0043-5937-9db7-76783b3fdcd6 | note | – – – – – – – – – – – – – – – – –
7c477621-e0c0-5184-a2ee-2e1dcda14937 | note | VERIFYING DOCUMENTS: This ITP
27d8a8d9-0825-5482-b453-07c2b562a258 | date | Date Completed:
| checkpoint | 6.6 As-built Survey
c573d89a-2a5f-5cb1-9088-5ca79e1073fa | note | REFERENCE: IFC Drawings VR 606.08 (a - c), AS2159 Clause 7.2.2
99ad81d9-3b41-5eda-b5f8-10c08d081dd8 | note | – – – – – – – – – – – – – – – – –
dfee99f2-896f-5c12-a2f0-e09e478b57b5 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
b8a7e2e3-4fa5-55d0-b531-a7d8a102ed2f | note | i. Pile head plan location = ±75mm
9b3273b1-1d6a-553d-873a-0b4fbac686d9 | note | ii. Variance from vertical or rake = 1:100
f661dfb8-35be-58a1-91ec-6bcb9db9b2e7 | note | iii. Irregularities in straightness = 1:100
3833015b-ca10-5eb8-9bbb-912b71632b39 | note | iv. RL = ±25mm
36dfb5d8-2858-5bee-9200-664ba2e18676 | note | Attach: Survey As-builts / Survey Report
21f288fc-4ab9-5e7b-a57d-f6fe221ea7b1 | note | – – – – – – – – – – – – – – – – –
ae6feecd-2735-5a08-baec-206bd11eace9 | note | METHOD: Document Review
b9a42594-1dbb-534e-aaea-5ef488032a80 | note | – – – – – – – – – – – – – – – – –
b6cb0efc-4c99-5fbe-990f-5de8fdbf100f | note | FREQUENCY: Each pile
672a99e8-5f89-5671-8438-97c8643c2c8e | note | – – – – – – – – – – – – – – – – –
95f78443-915f-50d8-917c-babb333d047d | note | CATEGORY: IP
eb6abb7c-35b0-509d-9386-b0adbbf53571 | note | – – – – – – – – – – – – – – – – –
a32d1206-d779-5fb8-b8b0-2f7caa7a624c | note | RESPONSIBILITY: Surveyor, SE/PE
e3828f99-097d-50a8-a87b-1d487b8010d6 | note | – – – – – – – – – – – – – – – – –
180ec103-40c5-50c9-b26f-15893da27a44 | note | VERIFYING DOCUMENTS: This ITP
7b2e125e-7abd-540d-b7e0-ce6889b93242 | date | Date Completed:
| checkpoint | 6.7 Non-conformance Report (NCR) Closure
ecf501b4-a451-5ab0-b80c-0f80ed3f3200 | note | REFERENCE: MRPA Quality Management Plan
a808e1d0-363a-5598-a703-23f744876b68 | note | – – – – – – – – – – – – – – – – –
6026d9c9-a39c-5de6-83d7-3a034c75929b | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
cf96180d-b0fd-5b8d-9246-7e6636db66dd | note | – – – – – – – – – – – – – – – – –
d5aa3bcf-8e14-5af8-ba8e-ab06de6e2885 | note | METHOD: Document Review
807d93b0-e52f-5b26-a010-c0b586692e95 | note | – – – – – – – – – – – – – – – – –
9ff413df-3b9a-59f6-b2b8-8a5ae18acb01 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
4a624b08-09a1-589d-b2c1-78a24f4935b0 | note | – – – – – – – – – – – – – – – – –
47cb1eda-754c-551f-bf28-14154fe6c8f6 | note | CATEGORY: HP*
1dcd8fcb-8bf3-569d-a9e2-629e3d1107df | note | – – – – – – – – – – – – – – – – –
c50a2439-6588-530b-82d8-e56b929c937a | note | RESPONSIBILITY: SE/PE
71d53156-62a9-58a5-8891-b5d5bed123f4 | note | – – – – – – – – – – – – – – – – –
840fd802-527d-5114-8916-d70fde293605 | note | VERIFYING DOCUMENTS: This ITP
b8da4c83-0251-59f4-8f03-c753add32f9e | date | Date Completed:
| checkpoint | Final Inspection
3277118f-7c80-50f0-9406-e3f0515c320d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
81c0b322-3822-51c3-9663-06575f3ea9e0 | textbox | Name:
e1ae85d9-02b8-5896-8921-e9f66cabb5c0 | textbox | Position:
64b3748d-a9ec-5608-9746-4c5d43ad10c4 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-174-STR-SSB-Bonded Anchors Rev 0 | itp | ITP-174-STR-SSB-Bonded Anchors | 8bab2abe-e25e-4023-abb9-8666f55683bb
| section | Referenced Documentation
| checkpoint | Referenced Documentation
754b5312-9913-5f75-83f5-2fce03f13d5c | note | Document Title: ITP-174-STR-SSB-Bonded Anchors (100 Year Design Life)
011006d8-e881-5f7a-a815-7c0794a9ee8c | note | ITP Description: SSB-Bonded Anchors (100 Year Design Life)
31d47398-adbb-54f9-ab05-ee85e1dca4e1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
f4b284d1-e1f6-5a9b-a50b-f07aca68f101 | note | Discipline (e.g. CIV/STR/RAIL): 174-STR
f04fb802-c348-57f8-a349-e8defeb0efc8 | note | Revision Number: 0
0e88edee-96cf-5653-80e8-61964c555665 | note | Revision Date: 12/08/2021
4f093fcb-489f-5773-bf02-88de8ac7caca | note | ITP created by: Mike Freeman
481ae5cb-47a4-5130-bdbb-aebe12099b72 | note | ITP approved for use by: VM
43948d0e-7100-59f2-be05-73d8bf374d37 | note | 1.1 Non Dependent
6afb5230-af74-5f9b-8e08-a957ebf14f71 | note | Reference: VicRoads Section 680 November 2018
8576d607-8a23-5f53-97b6-a7e66f513b1f | note | 1.2 Non Dependent
d4164200-b5bc-53af-a87e-aa1eea21fcf7 | note | Reference: VicRoads BTN 006 January 2018
b9123447-2085-50b3-815b-beffab5ff371 | note | 1.3 Non Dependent
cb69876c-0386-58b3-a351-6cbe0806866d | note | Reference: Teambinder Correspondence Number MRP-MRPA-GNC-XDM-1346
71be157e-82af-5ad7-b5ab-b28829f05edf | note | 1.4 Non Dependent
6aa5cfda-a442-5ce0-ad65-e91e129159ac | note | Reference: Teambinder Correspondence Number MRP-MRPA-GNC-XDM-2385
| section | Preliminaries - Materials
| checkpoint | 2.1 Bonded Anchor System - Chemical Adhesive
4f551a3a-7c56-5a99-b38c-acf6e5111fda | note | REFERENCE: IFC Drawings 680.05 (a), 680.05 (b) (i - vi)
1de145aa-434a-5b1c-8c1f-fd279cbdf430 | note | – – – – – – – – – – – – – – – – –
04b85d29-9cf5-5dc3-a8ba-bd78404d26f3 | note | ACCEPTANCE CRITERIA: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
ae66d17b-3e97-56c9-a6fe-c0f8725a3a87 | note | i. ATIC SPEC 38
e693929a-92aa-5a50-8f36-ddd4ca185b17 | note | ii. EOTA EAD 330499-00 or 01-0601
ac956b03-a759-528e-aec9-f0b8ab41ff9b | note | iii. ICC-ES (USA)
610a4205-c92c-59ce-b1c7-18244d6173ad | note | ○ Note: MRPA has D.o.T direction and approval to use only Hilti HIT-RE 500 V3 or Iccons BIS PE Gen 3
fe0b90f9-6866-51fb-b454-587d46e5dbfc | note | ○ Teambinder Material Approval number: MRPA-MA-000192 (Hilti HIT-RE 500 V3)
25f0cefc-9ce0-529d-b45f-4b85251b0389 | note | – – – – – – – – – – – – – – – – –
4402f8ab-64a8-561b-97a4-c24971f6c50c | note | METHOD: Document Review
6215ea1f-f48a-5c5d-bd91-0c04bd3d7279 | note | – – – – – – – – – – – – – – – – –
6e9c15f2-dcb8-5515-80ad-3287fc48e8c5 | note | FREQUENCY: Once, per product, prior to commencement of Works
b0d9743e-42a9-51a6-8416-261f37f18419 | note | – – – – – – – – – – – – – – – – –
c4a03fec-5619-518d-a44b-486c227ef5c3 | note | CATEGORY: WP
21f5cd72-38eb-5024-b8af-0ae3af25e34e | note | – – – – – – – – – – – – – – – – –
b2a7b4b0-f945-5a35-85e1-48f60cf8634e | note | RESPONSIBILITY: Nominated Authority
69739a5f-694b-5174-a29c-32c3b21aa62d | note | – – – – – – – – – – – – – – – – –
1b601864-0e7f-58ca-a2e2-31b8ec5c549e | note | VERIFYING DOCUMENTS: This ITP
af824cea-8457-5c41-b984-bdb2c82a425d | date | Date Completed:
| checkpoint | 2.2 Bonded Anchor System - Reinforcement
4050d6bd-d271-5886-9290-884c1397afab | note | REFERENCE: IFC Drawings 680.05 (c), 611.05 (a)
0a420878-17a8-50d0-8fb3-bc49e1946460 | note | – – – – – – – – – – – – – – – – –
291df2c4-e5e1-59f1-a115-62da1463d28f | note | ACCEPTANCE CRITERIA: Where applicable, current ACRS certification for materials and for bar processing.
2500ef46-2be6-51dd-8d3f-17c96cfdd28e | note | ○ Anchor bars need to remain uncoated (black) for durability purposes.
355e14ca-840a-568b-b05a-d165105125ca | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
693964d1-5561-5b26-b941-02ed19f6cfe7 | textbox | Enter: Teambinder Material Approval number
6cb9d205-4043-53b0-907c-a7d0bc1c7c6e | note | – – – – – – – – – – – – – – – – –
815d3d7c-e7f9-5664-ad89-5b4d0a9f8d69 | note | METHOD: Document Review
37f97186-6a37-5a0d-bdfc-e90f15e5ddf8 | note | – – – – – – – – – – – – – – – – –
1f73c280-5a9e-52b4-bf3d-db44ea6bc8e1 | note | FREQUENCY: Where applicable, once for each supplier, 14 days of award of contract
25c05fcf-6bd0-5dd7-a3fb-400e834d9ee0 | note | – – – – – – – – – – – – – – – – –
2ac4082d-02f7-5023-aca1-d800b8777ff3 | note | CATEGORY: WP
f585f941-c59e-59b7-8a51-72a0b7280ad0 | note | – – – – – – – – – – – – – – – – –
cf9b1b40-d368-5937-91e2-ae49429140f3 | note | RESPONSIBILITY: Nominated Authority
eec19668-c7c0-5e5d-85a9-20e032fdbd6d | note | – – – – – – – – – – – – – – – – –
3f372809-5607-51c0-b814-0cd9cad54014 | note | VERIFYING DOCUMENTS: This ITP
17b80399-e81f-5fb2-8768-1b4cde236f89 | date | Date Completed:
| checkpoint | 2.3 Bonded Anchor System - Stainless Steel Anchors
13e27c25-e6a9-5519-8370-a198ee995222 | note | REFERENCE: IFC Drawings 680.05 (c)
7971903d-96ef-5676-a002-daf69ae932bd | note | – – – – – – – – – – – – – – – – –
5f57f42f-130a-53db-9942-a4a092f7f272 | note | ACCEPTANCE CRITERIA: Where applicable, stainless steel grades 1.4401, 1.4404, 1.4362 and 1.4571 (marking A4) may not be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
638e3b0b-3cae-5130-b6bb-9dab45c89753 | note | ○ Stainless steel grades 1.4529 (marking C) may be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
3c2f3d98-2508-5310-a515-f49eaddcc312 | textbox | Enter: Teambinder Material Approval number
ff8209f2-28e1-504a-980f-f744308c0e8c | note | – – – – – – – – – – – – – – – – –
b7b92e60-f769-5238-8e18-974cbfa8bdbb | note | METHOD: Document Review
3dc5bb54-49b5-53d2-b7ec-46162f8547d8 | note | – – – – – – – – – – – – – – – – –
1ba9041e-0aea-5dd5-85eb-e58149668b1e | note | FREQUENCY: Where applicable, once, prior to commencement of Works
7ca18f64-0a91-5ce0-87f7-a29f0915f1f2 | note | – – – – – – – – – – – – – – – – –
5233e91e-08e2-5008-8d7c-45e89a810773 | note | CATEGORY: WP
215ae1e1-4286-515e-8e2a-485b367ad569 | note | – – – – – – – – – – – – – – – – –
62c448b2-a65d-5eab-a73b-696bfab5978f | note | RESPONSIBILITY: Nominated Authority
4d5c2cb2-5f4c-5dd3-b020-2c27d367e66b | note | – – – – – – – – – – – – – – – – –
14a3c9ba-15df-5dd7-9495-cfa5851b4704 | note | VERIFYING DOCUMENTS: This ITP
49283ae0-ee95-5b17-974a-a56eaf4d9cde | date | Date Completed:
| checkpoint | 2.4 Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
ab862701-67bc-5e69-8875-2d2b823a472e | note | REFERENCE: IFC Drawings 680.05 (c)
f271292a-218d-5a68-8d70-ceebddf9510d | note | – – – – – – – – – – – – – – – – –
29fea016-e6d1-575d-a376-59257a529195 | note | ACCEPTANCE CRITERIA: Where applicable, bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
df0b68f6-6353-51b7-8dfb-c4bfb8a28f1a | note | i. ATIC SPEC 38
bf190aab-d1de-55dc-963c-9ca30b5d2590 | note | ii. EOTA EAD 330499-00 or 01-0601
cfd5f135-12bb-57c4-99a0-71a9cd8ba4e2 | note | iii. ICC-ES (USA)
08bc9090-f7e8-5d7c-9ccf-1a40878cec9a | textbox | Enter: Teambinder Material Approval Number [free text box]
723afa4e-cb78-5fc8-90ef-fba4c5bc7cae | note | – – – – – – – – – – – – – – – – –
224d5f9b-6a20-55c6-aab4-2e23e2c4c8b6 | note | METHOD: Document Review
dc5c7165-c84f-5b5f-a304-d27a2147826c | note | – – – – – – – – – – – – – – – – –
d4c997ab-418b-5c9b-aef7-a1038b12331d | note | FREQUENCY: Where applicable, once, prior to commencement of Works
4baa3810-c892-5546-aa04-ba5fa70b8048 | note | – – – – – – – – – – – – – – – – –
fda260c5-d9c2-5185-a4f0-7eefcc46318b | note | CATEGORY: WP
18144fed-53f4-53ac-91ca-cab161720991 | note | – – – – – – – – – – – – – – – – –
579d9cc7-8c47-523e-8473-0323e86d4fe5 | note | RESPONSIBILITY: Nominated Authority
a1cae982-2558-5a3c-9592-b46adb66dd9f | note | – – – – – – – – – – – – – – – – –
522c8e29-f834-5f28-aeab-f58e3e6a91fb | note | VERIFYING DOCUMENTS: This ITP
4ed928af-03e3-5564-b842-88e45397eeb9 | date | Date Completed:
| checkpoint | 2.5 Alternate Product, Product Certification or Changes to Existing Product
e51c965a-a619-55ba-943f-e06b9ddb1050 | note | REFERENCE: 680.05 (a), 680.09 (a) & (b)
dcd55bbf-5c70-5f0e-899a-f43812413be3 | note | – – – – – – – – – – – – – – – – –
e7d59296-6473-579f-83b6-bc0ea7ec3c60 | note | ACCEPTANCE CRITERIA: Where applicable, if an alternative system is proposed, where a bonded anchor system falls outside the scope of certification or where directed by the Superintendent, ultimate tensile load testing shall be performed to validate the bonded anchor system meets or exceeds the intended durability and load capacities.
b3bf35ac-d11b-549b-a2e9-556660476065 | note | ○ A sample of 5 no. anchors per combination of adhesive type, anchor orientation, type, grade, diameter and concrete grade shall be installed in accordance with the manufacturer's installation instructions, load tested and results reported by a third-party accredited testing authority.
dc42b192-8381-5a7b-b1d1-5cca992e9a39 | note | ○ Results of the ultimate testing to be submitted to the Nominated Authority.
2690ce49-06a1-58aa-93a8-0a5208ab8eed | note | Note: MRPA designs are following the ETA certification of the adhesives.
3cb0d9cf-3a57-5161-bffd-dde9a999ac1d | textbox | Enter: Teambinder Approval number
92f8f44e-cf21-5fde-9335-2ed19c9a6cf2 | note | – – – – – – – – – – – – – – – – –
0560fdda-acb5-5e63-aca1-e6efc9b44322 | note | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
682e21ff-afba-5bf8-bfcd-0677a9224445 | note | – – – – – – – – – – – – – – – – –
db3550c7-8422-505d-8b2e-3080f80c45dd | note | CATEGORY: HP
fcdd1153-4122-57c4-a5ab-939190476daf | note | – – – – – – – – – – – – – – – – –
66d437b0-d106-562b-be4d-aa889b063c43 | note | RESPONSIBILITY: Nominated Authority
7aa36913-f059-5e37-8a4e-bead4309af6a | note | – – – – – – – – – – – – – – – – –
5a224369-d1ce-54e8-960a-cc0d14106f68 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9d031512-4fbb-5f1f-b8f1-8cd6d36d5c33 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Documentation & Procedures
| checkpoint | 3.1 Design of Bonded Anchors Subject to Tensile Forces
ef81bff1-90ab-58fb-ade1-e18c3abc7ce9 | note | REFERENCE: 680.04, BTN 006, Clause 2.6
f14a5592-6932-53cf-af87-7b9583751f14 | note | – – – – – – – – – – – – – – – – –
e57a492a-46a8-54b9-a958-9376955d8e19 | note | ACCEPTANCE CRITERIA: Where applicable, if it is proposed to use bonded anchors in full or partial tension, submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
6f12512a-dfe7-5d70-90f7-580744a8cbfe | note | – – – – – – – – – – – – – – – – –
f27ff658-483b-53a0-93e9-ce65e61f4257 | note | METHOD: Document Review
eb015846-ba6d-5925-a692-1120e2cab5fa | note | – – – – – – – – – – – – – – – – –
951d6fb6-9475-58f9-8f62-d124e124400a | note | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
c6d5f300-9d35-5143-835b-4c083f0cf6bc | note | – – – – – – – – – – – – – – – – –
461bc50d-12fb-54b8-aea7-79dc9a9e352d | note | CATEGORY: HP
458aeb4c-546e-58ff-9357-3edaf3168878 | note | – – – – – – – – – – – – – – – – –
7306f94a-6ae7-5a98-ad29-9c9c28e02a4c | note | RESPONSIBILITY: Nominated Authority
b93653cd-6cdb-5490-b1a5-1b8c83a3aa11 | note | – – – – – – – – – – – – – – – – –
3ac7b1dd-c137-57f4-8bc6-92d1cc28bcb0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
7acd080d-9b9f-5163-9ff0-e981e50d441f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 Bonded Anchor Work Method Statement
419a856b-1e3d-5dd3-808b-5a79184ee101 | note | REFERENCE: 680.11, 680.07
4bdfdea6-2567-5b5c-b1e3-62c4ff214468 | note | – – – – – – – – – – – – – – – – –
854dc308-6a22-5a0b-9305-1079750d1828 | note | ACCEPTANCE CRITERIA: Bonded anchor WMS, detailing the method for locating reinforcement/tendons/services, equipment to be used, load testing regime and repair of concrete (spalled and cracking) to be submitted for review to the Nominated Authority.
2bb74da3-1cae-5cf8-bb3b-475b69216e69 | textbox | Enter: Teambinder Approval number
c3e0b33b-0b3c-5afa-aaf4-d28c6390ba52 | note | – – – – – – – – – – – – – – – – –
b460a15f-5fae-5110-b6fc-7ccb6ea8144f | note | METHOD: Document Review
7543e2ca-d26b-5217-afeb-57337f81ced7 | note | – – – – – – – – – – – – – – – – –
ead887c5-0f09-5208-927d-87808ec6d881 | note | FREQUENCY: Once, prior to trial installation
c6bf504a-b540-5530-841d-8da1b5ce66b8 | note | – – – – – – – – – – – – – – – – –
895e0804-e16c-51d7-9c43-35d2982bf418 | note | CATEGORY: HP
8726a42c-eb77-5b57-9dc4-309e28f85be8 | note | – – – – – – – – – – – – – – – – –
707bb82a-10fc-536e-bd49-63a3fa2b3751 | note | RESPONSIBILITY: Nominated Authority
3d65f5f7-089d-5adf-ae11-b1a2e3b721c9 | note | – – – – – – – – – – – – – – – – –
3a37b0c2-c13c-5279-af6c-99322fd2045e | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4a5b46d6-497e-5fe5-9b49-99622c1922b8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Load Testing Work Method Statement
0f7bf259-96c3-5ec3-9e2e-066fbb72a5fe | note | REFERENCE: 680.09 (a)
1afdc5ce-10f3-5159-843e-1e3883f2d472 | note | – – – – – – – – – – – – – – – – –
5c7c4223-415b-57b3-9068-737a634bcf6b | note | ACCEPTANCE CRITERIA: Load Testing WMS, detailing the target loads (1.5x or 2x the design loads), load increments, duration for the load to be stained at each increment, testing frequency, measures if fail occurs and equipment to be used.
45e201ac-103d-5f8b-97b5-99e69234adb4 | note | Additional testing equipment requirements:
efe7c004-5400-5cde-a772-9f7aa07ac1a5 | note | i. capable of measuring the applied force to an accuracy of ±2%
7a5a4c1a-350e-5347-9d1a-5317b78d5617 | note | ii. capable of measuring the elongation with an accuracy of ±0.02 mm
24965aab-a29b-5bef-9ae8-90217df38b54 | note | iii. have a valid calibration certificate
d84d91e1-555a-5683-a9d4-de3b1320183f | note | ○ The above is to be submitted for review to the Nominated Authority.
4ac982e3-6e26-580a-89ba-cab7e01b090d | textbox | Enter: Teambinder Approval number
1a287a32-1c24-56d9-9c2d-412d80bfcb74 | note | – – – – – – – – – – – – – – – – –
ca7d2065-d602-563d-bb36-449f677e862d | note | METHOD: Document Review
a8829f9e-9bb9-52f2-9318-4e49bbad3be6 | note | – – – – – – – – – – – – – – – – –
f157f5b9-ffe3-506a-a956-ec7fb1b48bc1 | note | FREQUENCY: Once, 1 week prior to prior testing
7601eca1-1ef1-5191-b55b-e515a1ccde0d | note | – – – – – – – – – – – – – – – – –
8b3ef856-8487-5dd9-a458-c8bd158f3532 | note | CATEGORY: HP
05993fbc-f401-518b-a2eb-4201c6ba288c | note | – – – – – – – – – – – – – – – – –
e7ae50c9-a0e5-5fa9-8e69-2eb0d2e10d21 | note | RESPONSIBILITY: Nominated Authority
ac5a0915-88f0-5d9f-b543-5a4aa8c387b9 | note | – – – – – – – – – – – – – – – – –
48e99fa2-62b3-5a17-a55c-e9b51e28ac41 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
0295cc78-d3d1-5946-b0af-2f8c1d3a80bb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Competency & Training of Personnel
b954c9c5-d3b3-50da-8243-187b0ab4be7a | note | REFERENCE: 680.06
002fd807-6878-5f73-b63b-60b5217b7bdc | note | – – – – – – – – – – – – – – – – –
d323f48c-9839-5177-8e58-db27ee5d193a | note | ACCEPTANCE CRITERIA: All bonded anchor installation crews and direct supervisory personnel shall be listed on the "AEFAC Certified List of Installers" and evidence of this submitted to the Nominated Authority.
a792316f-bbc6-53ba-95c7-e17b4f2b1a51 | note | – – – – – – – – – – – – – – – – –
cc40fac1-0b88-5c39-9692-2720d9e94d41 | note | METHOD: Document Review
1df64458-d210-5f8e-87b9-e75d534aeedd | note | – – – – – – – – – – – – – – – – –
a6ab327f-4df6-5e7d-87ab-04c2328f61ea | note | FREQUENCY: Once, prior to commencement of Works
725ee383-93f8-5318-a18c-1a3ed9250c07 | note | – – – – – – – – – – – – – – – – –
664d430f-aaa9-566d-95ab-57dc1d2f79ce | note | CATEGORY: HP
7ebb4378-48b2-55d2-ba7a-0b610b09d850 | note | – – – – – – – – – – – – – – – – –
efb1de78-aac1-5520-80b0-077ae10894ee | note | RESPONSIBILITY: Nominated Authority
cd507644-1854-5d70-b606-4466b815496a | note | – – – – – – – – – – – – – – – – –
f3f492c5-85e4-56a7-9ec7-d7a2fbfd3bb1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
bf4e7512-879d-569c-8f45-8a9764b4ed78 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 Chemical Adhesive Training Toolbox
a162842a-d03d-5aab-94bf-51e39919df6d | note | REFERENCE: 680.11
77fe57dd-b05e-5859-903a-cb86053830be | note | – – – – – – – – – – – – – – – – –
b227047a-3489-537f-979f-7bf73da29098 | note | ACCEPTANCE CRITERIA: Works shall not proceed until a toolbox is conducted by each chemical adhesive manufacturer, covering the specific installation, quality and testing requirements relative to the approved adhesive.
bbc8138b-c6b1-5848-9f5f-c2df05a9b6c9 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
6ce45714-e1ea-5b7d-bbde-30ae533a9769 | note | Note: A D.o.T representative should be in attendance
278bdb82-5e90-58ae-8783-9580f1d3a5ab | textbox | Enter: Teambinder Approval number
210c651e-5396-544f-88f0-f9f58d971554 | note | – – – – – – – – – – – – – – – – –
99ffce16-6c5d-5053-b8d4-a63c7222b6c3 | note | METHOD: Document Review
0c6e5cd9-b29b-5601-b704-329a4c154e75 | note | – – – – – – – – – – – – – – – – –
3b69471f-0c80-5880-9170-648af173e302 | note | FREQUENCY: Once, for each work crew, prior to commencement of Works
a94c4bf2-14ae-5ccf-ac1b-80feebec8cba | note | – – – – – – – – – – – – – – – – –
fc6bafa0-37e4-5e7e-a4be-2702dedfe236 | note | CATEGORY: HP
dc421532-1485-561c-9801-325c863fdace | note | – – – – – – – – – – – – – – – – –
9fd8a06e-5b3d-54d2-ac67-66a9d05335ae | note | RESPONSIBILITY: Nominated Authority
ecd07439-144c-5661-9c87-6eace1689599 | note | – – – – – – – – – – – – – – – – –
b7fe42c2-f589-56b9-81d0-5214bfff2ccb | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e125d35c-f3d2-5b35-8c24-85fd1175c1ba | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 Trail Installation
aac2c417-b06c-5473-9951-d4f56f37c1f5 | note | REFERENCE: 680.12
68177403-40c4-5b67-9b58-a73be6b962cc | note | – – – – – – – – – – – – – – – – –
3c53c840-8698-5580-ad00-2fea1492d4cd | note | ACCEPTANCE CRITERIA: Works shall not proceed until each work crew assigned to the project site can demonstrate compliance with the manufacturer's installation instructions by installing a sample of 5 no. anchors per combination of anchor orientation, type, grade, diameter and concrete grade as per the IFC design.
a9481eba-b593-5f89-af52-092b8ca9b6b2 | note | ○ Where the presence of cracks exist or are to be expected, an additional 5 no. bonded anchors shall be installed in each combination to the above.
3ba6b949-19f4-56ad-ba60-a065521120c4 | note | ○ Evidence of this trial and attendees to be submitted to the Nominated Authority.
a0f316e4-6b50-556a-9864-53e67aa55c98 | textbox | Enter: Teambinder Approval number
5617c2f8-0615-598f-b0bd-c46ff2ad74a3 | note | – – – – – – – – – – – – – – – – –
3a88aed4-5784-5944-8633-abb28c8ef92f | note | METHOD: Document Review
c2cc24ea-adde-5acd-a7c3-5fe0b9f0f3c8 | note | – – – – – – – – – – – – – – – – –
325d0612-6126-5d2a-ba81-c9f4e5cc0e0c | note | FREQUENCY: Once for each work crew, 14 days prior to commencement of Works
d4d107b2-6492-5bcc-8b0a-e23f3b0ac5f9 | note | – – – – – – – – – – – – – – – – –
4150275f-4e2c-55e8-870f-e06ddab75de5 | note | CATEGORY: HP
2ceeae4a-5a9b-51b0-9ebc-67a0440b7524 | note | – – – – – – – – – – – – – – – – –
46b6f45d-a7b8-5f17-b712-86b1d12216e6 | note | RESPONSIBILITY: Nominated Authority
8302da87-25db-56bd-aa95-15999e6483cd | note | – – – – – – – – – – – – – – – – –
d4f38d2a-f3a7-5a6d-ac1a-ba299af7f3a1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c1c7811d-ad52-5f29-923b-a6ded5d8df47 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-installation Activities
| checkpoint | 4.1 Installation Equipment
b33b181d-ffbe-5a24-95d1-4e3ae809c26b | note | REFERENCE: 680.07, Manufacturer's Installation Instructions
c222e6e4-a5d5-5e62-8348-e7bd4be0e1b5 | note | – – – – – – – – – – – – – – – – –
875dae45-ff25-5e07-a48b-21292a0e3561 | note | ACCEPTANCE CRITERIA: Bonded anchors shall be installed using the equipment specified by the bonded anchor system's installation instructions.
4efc127a-35c9-540c-9609-0e7e615eea39 | note | ○ This includes drill bits / dustless drill bits, diamond cores, roughening tools, cleaning brushes, mixing nozzles, piston plugs and extensions.
30c55fcb-c8ae-5cd5-9ca5-84f934d1a0ff | note | – – – – – – – – – – – – – – – – –
e94d7fbb-653e-50d5-9160-fa026c80c672 | note | METHOD: Visual
0b00b27f-4a2d-541b-8a9a-d183e9be9b14 | note | – – – – – – – – – – – – – – – – –
4cd173ad-07f2-5f2f-8590-2576b2e7083a | note | FREQUENCY: Each discrete population
7ab00dcb-2d89-55f3-8294-f0ef6f086770 | note | – – – – – – – – – – – – – – – – –
250c1f60-5c3f-5c28-b491-01ea43d29d0b | note | CATEGORY: IP
20637fa3-68f8-5d09-ac9b-846bc5aa683a | note | – – – – – – – – – – – – – – – – –
c79de66b-e946-5a67-a368-0e8fcf9572d4 | note | RESPONSIBILITY:
02031f93-35ce-56e5-bcf8-1cf1243e1663 | note | – – – – – – – – – – – – – – – – –
a471f327-0d76-5558-83fd-7812f02bb7a3 | note | VERIFYING DOCUMENTS:
33cee52f-948c-59a2-87fe-e34f02605121 | date | Date Completed:
| checkpoint | 4.2 Setting Out
358d93d5-c422-5be0-8374-7b2c5b15fb78 | note | REFERENCE: 680.08 (a), Bonded Anchor Work Method Statement, 610.46
335c71b3-c636-58b8-b912-03f2d0d86090 | note | – – – – – – – – – – – – – – – – –
57564dfd-700b-5019-a16d-04f79d9f7252 | note | ACCEPTANCE CRITERIA: Locations of bonded anchor holes shall be positioned at the design spacings and angles using a calibrated covermeter or ground penetrating radar (GPR) to ensure that no damage occurs to reinforcement, pre-stressing strand, ducting and embedded services.
9cafc368-ed1c-52ad-97b8-4b02bcbf314b | note | ○ Where clashes are detected, adjust the anchor spacing locally if able to do so, maintaining the maximum and minimum spacings, edge distance and cover requirements.
427bf2a2-9947-5dc2-81eb-1564f9552f97 | note | ○ If unable to adjust the locations, consult the designers to provide updated locations.
2a5777ca-054d-5116-84c5-61cc1cd75d05 | note | Note: The marked out locations shall be traceable to determine a discrete population of anchors and installed by the same work crew.
6ad10f22-da04-54fc-9491-8bbf2522999d | note | Note: Installation of anchors must not occur until the concrete is both 28 days old and the concrete strength has achieved the 28 day strength.
a81736b7-ed8b-50e1-b44b-8aeaf5bc0ada | note | – – – – – – – – – – – – – – – – –
6d8947dc-deba-5461-9b56-1c8c331041eb | note | METHOD: Measure, Visual
d5f852f4-7b17-53b6-a23e-0101a9e4f54d | note | – – – – – – – – – – – – – – – – –
79aed672-4544-5e01-b380-73af323cf3b8 | note | FREQUENCY: Each anchor
be8e8830-e712-5bbe-89f3-91a38dad8066 | note | – – – – – – – – – – – – – – – – –
9bfb06b4-d89f-5d2e-bf23-aaeaa5dd5372 | note | CATEGORY: IP
af45df22-c58f-548e-8541-6aa3d521e980 | note | – – – – – – – – – – – – – – – – –
b5925397-be17-5d66-adbd-7b19204f105f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
47c3b693-61e5-55c1-ab0b-dd4c9c34d068 | note | – – – – – – – – – – – – – – – – –
90d27210-c848-50b3-9039-7e76efcda859 | note | VERIFYING DOCUMENTS: This ITP
0e5d2edc-6161-57b9-890f-fd43b75db5a8 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Hole Drilling/Coring
3c76554a-d73f-5f56-a72e-cdd5fe1606d7 | note | REFERENCE: 680.08 (a) & (b), Manufacturer's Installation Instructions
116b526b-2438-5d6f-b73a-c42d7847efd1 | note | – – – – – – – – – – – – – – – – –
78802f2a-bf4d-5d26-a200-6d264cb361ad | note | ACCEPTANCE CRITERIA: Holes shall be drilled or cored in the orientations, angles (if not perpendicular to the concrete surface) and depths shown on the IFC drawings.
3076ebd7-306a-5957-a15f-b33d21a20d64 | note | ○ Drill or core diameters shall be those shown in the manufacturer's installation instructions..
acb4b9d9-b59c-5417-95d1-8eda2e51e62f | note | ○ Coring may require the internal surface of the hole to be roughened.
7df326e7-b903-5685-9a68-8682b260630b | note | ○ If reinforcement is encountered during the drilling or coring process, cease drilling immediately and relocate the hole.
59ca0642-f55b-51eb-bc8d-acaca18dd0ca | note | ○ Refer to section 6.4 for repair of abandoned holes.
3509efad-6ecc-5460-8420-632462fd3944 | note | ○ If reinforcement is damaged, consult the designers to provide a clear direction moving forward prior to continuing installation of that discrete population of anchors.
d0e53f7a-d5ef-57a5-9d32-c84d90e0e7b8 | note | – – – – – – – – – – – – – – – – –
e206096e-d451-5fd9-8e7a-48ac92959a35 | note | METHOD: Measure, Visual
5b26ece3-c7ff-5eeb-a074-a613822a7aba | note | – – – – – – – – – – – – – – – – –
c76bcc75-da15-5ec0-b396-41857ee61bbb | note | FREQUENCY: Each anchor
eef8307f-0a6b-5728-9f6d-e06b07d2af17 | note | – – – – – – – – – – – – – – – – –
05ca3b54-90cd-579c-8349-67c2d5cf045b | note | CATEGORY: IP
a167a035-0db9-5b9c-98ee-5fb5f553efef | note | – – – – – – – – – – – – – – – – –
b663b512-9794-5a7c-b8f7-bcabe1a8d3ed | note | RESPONSIBILITY: SE/PE/SPE
5693aba0-652f-5f80-81f0-2f79617c6ef1 | note | – – – – – – – – – – – – – – – – –
50b5ab0b-9e8e-5b60-9833-5678cca6771f | note | VERIFYING DOCUMENTS: This ITP
6d6a5893-95ac-5588-abd9-3f141bacd0e6 | date | Date Completed:
| checkpoint | 5.2 Hole Cleaning
60945b18-e94f-541c-93bf-bed471ba90e1 | note | REFERENCE: 680.08 (a) & (b), Manufacturer's Installation Instructions
3aac0539-9a27-5ac2-8714-515476097540 | note | – – – – – – – – – – – – – – – – –
44ef08ea-720b-5929-8acc-dd81202b8ab1 | note | ACCEPTANCE CRITERIA: Hole cleaning shall commence as soon as practical following the drilling / coring process to remove debris, dust particles and moisture / free-standing water (where required).
cd808f26-aa3d-5678-8636-2f4e57c20df3 | note | ○ The process shall follow the manufacturer's installation instructions which is a repetitive sequence of brush cleaning and air flushing, resulting in no dust detected on a finger-tip when in contact with the internal wall of the hole.
d9abd342-e8e8-515e-9042-93fcad67823b | note | ○ The minimum hole depth shall be verified before proceeding to the next step.
d7acbb3e-08b0-55aa-85b9-af58a26c0b0e | note | Note: Where hollow-tipped drill bits are used in conjunction with a vacuum drill, cleaning may not be required - consult the manufacturer's installation instructions.
4881fd67-c601-5a2f-8742-b0803354ef7a | note | – – – – – – – – – – – – – – – – –
ac0dbd50-e610-5ce2-b153-059c097a3f8d | note | METHOD: Visual
7cd5e51f-4bf4-5b57-9e61-999b7097e6cd | note | – – – – – – – – – – – – – – – – –
8910400c-79c9-52d4-b0c3-2229dfb30801 | note | FREQUENCY: Each anchor
28d822cc-b2e9-562c-baf2-f2e47337460e | note | – – – – – – – – – – – – – – – – –
d7982b9d-345c-5c47-af71-27db9e745790 | note | CATEGORY: IP
37249772-43cc-54ff-bb2f-8c6c0b78b428 | note | – – – – – – – – – – – – – – – – –
2e80bb8c-139a-57b7-8963-f0716e1ceeda | note | RESPONSIBILITY: SE/PE/SPE
c73436e9-fd51-5dab-99c6-3b7f76f85005 | note | – – – – – – – – – – – – – – – – –
02c7c850-df23-5651-8055-2d9696db4073 | note | VERIFYING DOCUMENTS: This ITP
d7308f18-6bd5-556e-9896-19ed65fb6020 | date | Date Completed:
| checkpoint | 5.3 Substrate Temperature
c310223a-4c33-57c8-8deb-1b6ec423669b | note | REFERENCE: 680.08 (b), Manufacturer's Installation Instructions
17877f12-2d40-5a6c-973b-8a2dc1a1e1c7 | note | – – – – – – – – – – – – – – – – –
a6b7dd38-4177-5950-8bb3-7f97be15dd65 | note | ACCEPTANCE CRITERIA: Bonded anchors shall not be installed where the temperature of the concrete is less than -5°C, or greater than 40°C or outside the limits shown on the manufacturer's installation instructions.
bd086d7f-1032-51d3-99c6-843b787cabc7 | note | Record: The substrate temperatures at the time of commencing the discrete population, the corresponding available working and curing times and the temperature at the completion of installation.
d80db81c-9fff-56b6-a2f6-3f1df7c411ab | note | – – – – – – – – – – – – – – – – –
ef8d0278-e561-5ec0-a49e-a55c95ec69a4 | note | METHOD: Measure, Visual
2bf1c7dd-c859-5b89-a6f0-be3a33b9a0e8 | note | – – – – – – – – – – – – – – – – –
cd951886-1f64-54d5-9a19-aa6b875e570e | note | FREQUENCY: Each discrete population
94ccd7f8-3a90-53e8-b7b4-7506f3090233 | note | – – – – – – – – – – – – – – – – –
35c26390-5bc3-5d27-bf7a-2bcd34096869 | note | CATEGORY: IP
ef622359-9f89-5997-af3a-86eb0486e641 | note | – – – – – – – – – – – – – – – – –
a2af7e73-f75e-534b-938d-15469d6f96f4 | note | RESPONSIBILITY: SE/PE/SPE
372ec81e-7365-5de9-9869-4c3ef81e0c3b | note | – – – – – – – – – – – – – – – – –
fecec92e-1a0b-5ee0-b85c-fc4d179ec52e | note | VERIFYING DOCUMENTS: This ITP
1e236064-449c-5ea5-837b-519a015846e0 | date | Date Completed:
| checkpoint | 5.4 Anchor Surface Condition
7e9dc3eb-fb6c-5287-b51d-7e2befd0d854 | note | REFERENCE: 680.08 (b), Manufacturer's Installation Instructions
461227b1-35a2-505e-a9f1-a4fc9c862e69 | note | – – – – – – – – – – – – – – – – –
523d969f-0165-5aca-af50-6bde31e9421d | note | ACCEPTANCE CRITERIA: Anchors shall be clean, free from debris, oil and other contaminants.
ca3b2606-8224-59af-a834-d9146b3bfc86 | note | Note: Any coatings have been factored into increasing the embedment depth
16238c5b-65a0-56f9-a525-65599040871e | note | – – – – – – – – – – – – – – – – –
10c8d1b7-8900-5646-8e9f-4dfe8a50b277 | note | METHOD: Visual
a6f1fc03-b472-51b3-be0a-2a046e9f5d85 | note | – – – – – – – – – – – – – – – – –
d9c1ac84-022a-5579-841d-a78d316c8327 | note | FREQUENCY: Each anchor
ed60681a-113e-5757-b298-f4bc6c1ecf7b | note | – – – – – – – – – – – – – – – – –
6e29a958-fa3e-517b-8370-4bb10440dbfd | note | CATEGORY: IP
9adaf555-266a-5349-9129-30d6d1d5ce4a | note | – – – – – – – – – – – – – – – – –
fc899612-da84-5605-b8ef-f2c583152ddd | note | RESPONSIBILITY: SE/PE/SPE
163faada-b37f-53a7-81c9-9e4a6b8008d2 | note | – – – – – – – – – – – – – – – – –
1c79e81e-9714-5891-837a-e9ea8931fce5 | note | VERIFYING DOCUMENTS: This ITP
5432a803-1706-5810-acfe-b2c233265d1d | date | Date Completed:
| checkpoint | 5.5 Adhesive Injection
5ca0b147-f325-53f3-a137-bb735df9628b | note | REFERENCE: 680.08 (a) & (b), Manufacturer's Installation Instructions
41876d01-b8bf-5dfb-b0de-806dd66a8a7a | note | – – – – – – – – – – – – – – – – –
454cdf95-b536-58c2-ab5e-72b81a8635ef | note | ACCEPTANCE CRITERIA: Connect the specific adhesive, cartridge gun and required injection equipment (nozzle, tubes, piston plug and valves) for the task and discharge the initial adhesive to waste to ensure that only fully mixed product will be used in the Works.
dcef213d-a5a7-5318-99ae-022d58c84faa | note | Note: Repeat the "initial discharge to waste" for each new mixing nozzle used and do not modify the nozzles.
12c6ca63-2601-5d4d-bb3a-f5e07bbe4988 | note | Inject the adhesive into the hole, starting from the base working towards the substrate surface at a rate that prevents the creation of air voids, until approximately 2/3 of the hole depth is reached, checked visually prior to the insertion of the anchor.
69cf0bd7-87df-5ab7-9ba0-38dba579f72f | note | – – – – – – – – – – – – – – – – –
a402146c-477d-5401-a1a1-a647c92a4bca | note | METHOD: Measure, Visual
e12be685-1e0d-5cf9-8683-97f78ad5529d | note | – – – – – – – – – – – – – – – – –
3501a4da-15e9-5ab4-a045-3a98c175fe4b | note | FREQUENCY: Each anchor
2df9e542-d2df-5dab-8eb3-a4220ab718f1 | note | – – – – – – – – – – – – – – – – –
4ac7a1c9-1393-5add-b99e-e966a87f8ef3 | note | CATEGORY: IP
a513ea6a-5b4f-5a37-b484-a50a9f2800ee | note | – – – – – – – – – – – – – – – – –
866b1ce2-147a-5b8d-b4c1-aad0e62d1228 | note | RESPONSIBILITY: SE/PE/SPE
190c6811-f0bc-567a-94d0-8904184bd293 | note | – – – – – – – – – – – – – – – – –
7c1fcaf9-efee-509c-b115-25e46e62e139 | note | VERIFYING DOCUMENTS: This ITP
5a45fffd-fa7a-5ead-8c18-673ea7728118 | date | Date Completed:
| checkpoint | 5.6 Anchor Insertion
4d59afc3-3046-549d-823a-750c1c2b8511 | note | REFERENCE: 680.08 (a) & (b), Manufacturer's Installation Instructions
40874ad8-803f-5c0c-963b-edfc5c74582a | note | – – – – – – – – – – – – – – – – –
b4d207d5-dcb3-5d4e-b69a-41c7ab3727e7 | note | ACCEPTANCE CRITERIA: While the adhesive is within the temperature dependent working time, the anchor shall be inserted and verified to the minimum embedment depth with a singular twisting motion, to ensure that the adhesive completely surrounds the anchor.
54b097f6-6830-5adc-86fb-fef9633e172f | note | ○ Where required, the anchor shall be centralised within the hole using temporarily supports to provide a uniform film of adhesive around the anchor and Excessive adhesive shall be cleaned from the substrate surface.
b8d904c7-ddee-5e37-a038-f15c99acd08d | note | ○ Loss of adhesive during the working time shall be prevented by sealing around the anchor as required.
8b1385bb-2b30-53fd-82b1-1643241957b0 | note | – – – – – – – – – – – – – – – – –
137ade5b-c13a-57de-b359-d7a95c6f2c81 | note | METHOD: Measure, Visual
ac341e44-1da3-5cf8-81e9-c0c29429c7d8 | note | – – – – – – – – – – – – – – – – –
9086946a-9f8f-5bda-8f53-1491b37d6385 | note | FREQUENCY: Each anchor
40ce61b6-2df4-547b-9fbe-cd2136c3ecbf | note | – – – – – – – – – – – – – – – – –
f98d8924-273b-5e4d-a8b6-f6ed84264933 | note | CATEGORY: IP
11104d14-9f5a-5889-b196-5509d751b06f | note | – – – – – – – – – – – – – – – – –
4696f068-da5a-563b-986a-429991513b0c | note | RESPONSIBILITY: SE/PE/SPE
585f0ea8-8ce5-5582-a8f9-3a22cdbc21c4 | note | – – – – – – – – – – – – – – – – –
cbc21abf-1009-5eed-b029-4385d97498eb | note | VERIFYING DOCUMENTS: This ITP
b06e7c57-eeb5-54e4-9722-51dd61873b31 | date | Date Completed:
| checkpoint | 5.7 Adhesive Curing
25a78c6a-2ba3-54b9-9915-859adc2a3040 | note | REFERENCE: 680.08 (a) & (b), Manufacturer's Installation Instructions
0d059179-8486-5b54-8122-8fc0eb6bd6b3 | note | – – – – – – – – – – – – – – – – –
294831f3-d4ac-5061-87d3-3bcf5bef60aa | note | ACCEPTANCE CRITERIA: The anchor shall not be disturbed, moved, loaded or torqued during the specified temperature dependent curing period before proceeding to the next step.
9941f127-5007-5aa8-bab5-e4cc90f4e7b2 | note | – – – – – – – – – – – – – – – – –
348d3de3-59b2-56c4-8ced-8e385e9116a7 | note | METHOD: Visual
1cb6db94-7a29-5d5e-adb1-fbaf79f38247 | note | – – – – – – – – – – – – – – – – –
8938872c-3971-5ae2-a9d3-fc0446d5d11b | note | FREQUENCY: Each anchor
aaf9e27d-b47d-560f-96ae-eb01e7a6eb97 | note | – – – – – – – – – – – – – – – – –
7dc18ad8-f7ff-5516-8341-fa5d9882fbac | note | CATEGORY: IP
f3786000-6df2-5749-9ed6-fda0f422b3ab | note | – – – – – – – – – – – – – – – – –
84142a0b-411e-547a-9a54-6aec4682968e | note | RESPONSIBILITY: SE/PE/SPE
da90e301-c734-53c1-a480-023e4e72cb1b | note | – – – – – – – – – – – – – – – – –
617111b2-3fed-516a-a5cd-6e2d140b1569 | note | VERIFYING DOCUMENTS: This ITP
de8069d5-a376-5ba6-a200-f382de1d41aa | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Proof Load Testing
0eecde49-c362-5dcd-9e2f-d745313158c6 | note | REFERENCE: 680.09 (c), Load Testing Work Method Statement, Manufacturer's Installation Instructions
f582149b-90ba-53b4-91b4-56b6a8df6bd2 | note | – – – – – – – – – – – – – – – – –
873536e5-bc9b-57c5-ba8e-0d421e15d129 | note | ACCEPTANCE CRITERIA: After completion of the curing period, bonded anchors shall be subject to proof load testing, as outlined in the approved Load Testing WMS.
4abc0236-16bc-5f4c-966e-e1303e4e14a4 | note | Anchors subject to tension shall be tested at:
ec0bbb92-5968-50e3-b186-9b50ede755d2 | note | i. 100% of the lot
3fc8f3fd-eff1-5224-89e8-55cbd21dd05f | note | All other anchors not subject to tension shall be tested at:
a32dae52-0aac-5da5-8d2b-19d98196d56c | note | ii. 5% of the lots
4c3c9a17-8121-5771-a289-93cd2f73d80f | note | ○ Test results shall be equal to or greater than the factored tensile or shear loads and equal to or less than the maximum displacements shown in the Manufacturer's Installation Instructions.
926b1dea-7389-5a23-b235-84cb8d9c7166 | note | ○ If any anchor fails the proof load or is displaced beyond the limits, the entire discrete population shall be tested for compliance.
648f3652-9283-5d1c-ab4e-bdcb1d62239d | note | ○ Refer to section 6.2 if the entire discrete population fails.
1f857d31-3a54-5f2f-9879-3cd7744e6fd0 | note | Attach: Proof Load Test Results
1e84c080-78ac-5e2c-beb1-a30d2136eea0 | note | – – – – – – – – – – – – – – – – –
e854a77e-57ff-5d0e-9d25-2b738f3f2287 | note | METHOD: Document Review
a6fa05f5-c9f8-5cf5-9b8e-6f35b9a3c839 | note | – – – – – – – – – – – – – – – – –
577a0c2f-af07-536d-99dd-a7f6c0f6dfce | note | FREQUENCY: Each discrete population
3ad2be5a-dcab-5dae-bb7e-3dfb75b94d3c | note | – – – – – – – – – – – – – – – – –
f8660ff2-3b93-5e6c-b72b-388a99c4bcbd | note | CATEGORY: IP
f3759702-802d-50a5-9a0d-77b6b074278f | note | – – – – – – – – – – – – – – – – –
56c803ed-3a3d-56a9-852e-d1421f2f6b63 | note | RESPONSIBILITY: SE/PE/SPE
87e381f8-a427-520b-ab27-89815015e13e | note | – – – – – – – – – – – – – – – – –
e3563f8a-920f-5e4f-9832-a732d408760c | note | VERIFYING DOCUMENTS: This ITP
e0dca700-33ca-5377-a4a7-52c2061fb3c4 | date | Date Completed:
| checkpoint | 6.2 Failure of Proof Load Testing
a7426eb4-5d7c-5f50-b0aa-5485fc1af2df | note | REFERENCE: 680.05 (c), Load Testing Work Method Statement
3f1d2239-362d-5dba-88e6-d83f9eca6ba4 | note | – – – – – – – – – – – – – – – – –
412eefbc-fa13-5b16-b693-0522e07266f6 | note | ACCEPTANCE CRITERIA: Should an anchor fail an ultimate tensile test, or an entire discrete population fail a tensile proof load; rectification proposals must be provided to the Superintendent for assessment prior to any further installation.
31c5c3c1-36fb-5f9c-a6da-cc5d63d79fec | textbox | Enter: Teambinder Approval Number
8e90ed19-61b5-5a60-a48c-e38b6fd3ac1c | note | – – – – – – – – – – – – – – – – –
0d03d08d-9fe3-555c-a99a-f879deb32feb | note | METHOD: Document Review
daa55f81-e111-52ba-b86d-73ba52fb331f | note | – – – – – – – – – – – – – – – – –
42b759ed-8e94-5c2e-adec-6926bb7f0819 | note | FREQUENCY: Where applicable
66a58055-bb11-569b-bf52-5a30a3f796e6 | note | – – – – – – – – – – – – – – – – –
e94fd752-0baa-579d-8b36-99671e3a27e9 | note | CATEGORY: HP
2d0495b6-b300-5d84-a1dd-c3c91b514d14 | note | – – – – – – – – – – – – – – – – –
3bbb913e-7b0f-57fe-b58c-dc3cd4aaa68c | note | RESPONSIBILITY: Nominated Authority
91fec112-a99f-5417-84dd-97645ddcd323 | note | – – – – – – – – – – – – – – – – –
0bc930f7-1062-54ea-8884-f9f18b88961c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
3284d2cc-3814-5a60-af37-b87f4c45a7b5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 Surface Inspection - Cracks
728a6692-f7b5-5d7a-b07f-51cc54b5a504 | note | REFERENCE: Structural Concrete Crack Repair ITP
3be2db36-25d8-5bac-a289-5bbdc0a73532 | note | – – – – – – – – – – – – – – – – –
fadff84c-8681-53a6-9dab-2a60c340fd00 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.1mm.
0d165e7b-ed9f-597d-a356-775d6c3d3baa | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP (Specification 687), for investigation and repair but repair methodology MUST be via the injection method.
6c36d5ee-f3af-5a6f-8014-e257a3c68c78 | note | – – – – – – – – – – – – – – – – –
979b0768-72ac-5522-aa15-706936f78ccf | note | METHOD: Visual, Measure
cb879b66-7e75-5ab6-ab25-a39bc147033a | note | – – – – – – – – – – – – – – – – –
c8e1a86f-b205-57a2-b6e3-f97704e8ecf2 | note | FREQUENCY: Where applicable, each lot
44d0253b-5022-5f0c-9e38-c41d829e4ecf | note | – – – – – – – – – – – – – – – – –
1676ebb9-61d3-5436-a387-72b5e5800296 | note | CATEGORY: IP
3a7778bf-6c83-511b-9b56-b5ee7610c1cf | note | – – – – – – – – – – – – – – – – –
7dffd7b0-726c-5fd9-954f-d8b0280b5dab | note | RESPONSIBILITY: SE/PE/SPE
1d760386-b6f7-5855-98fa-a8fef70347aa | note | – – – – – – – – – – – – – – – – –
5b433f46-8075-5ccc-ba56-a005cf85aff5 | note | VERIFYING DOCUMENTS: This ITP
6f0e4063-80b0-57c9-84b8-e0f9bb53f58e | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Abandoned Holes & Post-testing Spalling
909a15fe-ef82-5800-891d-408dfaa1fe66 | note | REFERENCE: IFC Drawings, Structural Concrete Patch Repair ITP, 610.31 (a) - (n), 610.32
276a7d20-82eb-5368-8df2-6fb5168519e9 | note | – – – – – – – – – – – – – – – – –
6ec1e870-f28d-55cb-9ed8-59a7b628a88c | note | ACCEPTANCE CRITERIA: Where holes have been abandoned, follow Structural Concrete Patch Repair ITP (Specification 689) for repair.
1fb3c537-a0dc-5c3a-af31-ec8e58a4f40e | note | ○ Where spalling around a tested anchor has occurred, preparation of the repair shall follow the Structural Concrete Patch Repair but the repair may allow for the newly cast concrete to create the cover.
537b4699-e525-5e63-ada8-085f2646622c | note | – – – – – – – – – – – – – – – – –
c197aa60-5ba5-5750-a4eb-113937395533 | note | METHOD: Visual
3e9ea3e0-4467-5994-9063-1c0cb2bfe02e | note | – – – – – – – – – – – – – – – – –
a28b11a6-8e38-53d7-ba55-596706f7bb3e | note | FREQUENCY: Where applicable, each lot
5f9fd8cf-d0d9-5e25-b715-a21109dee58d | note | – – – – – – – – – – – – – – – – –
6a76fee2-0814-58a3-8ac6-bba8f7d9b2e7 | note | CATEGORY: IP
205ba1db-fc84-58cc-a4df-1e4f80f8492c | note | – – – – – – – – – – – – – – – – –
ed69ebcb-cde1-5e5d-9602-133e731c8d45 | note | RESPONSIBILITY: SE/PE/SPE
a1d6fabc-de98-57bb-a532-2d4d2e0f499e | note | – – – – – – – – – – – – – – – – –
c535e856-2703-5dda-ac22-15a2bb38c19e | note | VERIFYING DOCUMENTS: This ITP
07d69d2d-dcf1-5daf-81ef-faff77f862f1 | date | Date Completed:
| checkpoint | 6.5 Non-conformance Report (NCR) Closure
58496431-d5b3-5b42-b52f-2d59ccedc4a9 | note | REFERENCE: MRPA Quality Management Plan
380a7795-1afe-5572-be2d-c20836942599 | note | – – – – – – – – – – – – – – – – –
f255af92-29a4-5e86-9071-0392ee20efae | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
e73aef80-9e00-5be2-a7cf-506149d4f3ed | note | – – – – – – – – – – – – – – – – –
627ce228-ef06-52a7-bd4e-03e31014b6ad | note | METHOD: Document Review
79fb4981-f95a-5431-962e-07d51c70e081 | note | – – – – – – – – – – – – – – – – –
29e79fed-b7d8-56a8-86fd-6a37b2d22a7a | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
6eab8b34-de65-5f5f-947c-b59e371593ef | note | – – – – – – – – – – – – – – – – –
b4f86148-517a-5c60-8db6-a579cd107d59 | note | CATEGORY: HP*
0d429556-f50c-52bb-847d-04e8646231d6 | note | – – – – – – – – – – – – – – – – –
c793eed9-7512-56be-9112-2d3915f79abe | note | RESPONSIBILITY: SE/PE/SPE
0c202dd3-2804-5ab7-979e-426ca51226d3 | note | – – – – – – – – – – – – – – – – –
5929c734-c8cd-5670-a23a-109862d51c97 | note | VERIFYING DOCUMENTS: This ITP
45fadbbd-eb16-5f65-9b3e-d6e78c1aff6c | date | Date Completed:
| checkpoint | Final Inspection
5dbd5de7-dff6-59d1-9c23-892edf38d9be | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
417a11dc-470c-57ea-94c0-7b369557c20e | textbox | Name:
1b1b8b99-f18e-5dc6-b1a4-64cc932eaca1 | textbox | Position:
eb0bb93b-f289-59bc-b54d-deb11745f422 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-177-CIV-SSB-Type A Fill-Structures Rev 0 | itp | ITP-177-CIV-SSB-Type A Fill-Structures | f537dc88-f137-442a-9b3d-93a04c8cfc7c
| section | Referenced Documentation
| checkpoint | Referenced Documentation
2d418f15-f4a7-5aa4-aa50-2923bab5843f | note | Document Title: ITP-177-CIV-SSB-Type A Fill - Structures
cc4cd48b-69ba-5b99-bde5-03decf5fd9f2 | note | ITP Description: SSB-Type A Fill - Structures
a3ff778a-5fea-5148-bbb2-1ae92ac220e1 | note | Discipline (e.g. CIV/STR/RAIL): 177-CIV
783ec578-c93f-5f4b-9dbd-9d19c85aa559 | note | Revision Number: 0
75875bc6-5436-5dd9-9ca7-526a935536a9 | note | Revision Date: 3/06/2024
72f219e5-8092-5131-ae08-c6552a934682 | note | ITP created by: Jay Bradley Power
f615e1c6-979e-5502-b1cd-ac8c063a6638 | note | ITP approved for use by: Victor Mira
5092e85b-c4cc-5045-8f9d-64e4971cebf3 | note | 1.1 Non Dependent
85218291-ca54-5a1c-b58c-c95b1fe23ada | note | Reference: IFC Drawings VR 204, RC500.20, RC500.5
| section | Preliminaries-Materials
| checkpoint | 2.1 Material Conformance
7983fe3f-cddb-5142-a590-009e17396fc9 | note | REFERENCE: VR 204.04 b) Table 204.041
5c3f4708-69d3-54c6-b15f-764fe0232691 | note | – – – – – – – – – – – – – – – – –
94d36137-5f1e-5053-b671-6e201131bfb6 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
77e2e8ad-4395-53d1-8bbe-ee06bc91ea4d | note | ○ Assigned CBR≥ 6%
a65bd6f4-1354-5e89-bce8-1744b948ec37 | note | ○ Swell ≤ 1.5%
54703b3a-cddc-55eb-b2bc-35be691610b4 | note | ○ Permeability N/A
1c5e4add-acfa-5797-82e1-f612908f8544 | note | Grading:
176a88a0-2abb-5ccc-ac19-35d82e75ae39 | note | ○ 75.0mm 100%
7b07a0db-2769-5e36-b49d-d25e9e2e9dd9 | note | ○ 4.75mm 40-80%
5301597c-829a-5410-a845-4f4a78b651e2 | note | ○ 0.075mm 10-40%
7cd721e0-ea4f-596e-a549-3e6e31984679 | textbox | Reference: Material approval in Teambinder:
b66d7c7b-66d1-5e65-882d-1d83ea925854 | note | – – – – – – – – – – – – – – – – –
cda38ae6-e122-586b-ac44-d3a37d3c4298 | note | METHOD: Document Review
e4dac011-d12b-5b10-bd3f-f44edaf382fb | note | – – – – – – – – – – – – – – – – –
4f4b93de-e08d-5a17-be0b-e017ffcee561 | note | FREQUENCY: Document Review
df7ee8a6-c279-5bf4-986b-2bff831e757d | note | – – – – – – – – – – – – – – – – –
f08a8aa1-0875-5bc3-a79e-d7af50a0df93 | note | CATEGORY: HP
7646f254-e939-58f9-b398-b4dfe44a66d7 | note | – – – – – – – – – – – – – – – – –
73134405-e7f0-5145-b208-2f550ade043c | note | RESPONSIBILITY: SE/Nominated Authority
94f86c19-39fc-57b4-8f6b-aaced7251815 | note | – – – – – – – – – – – – – – – – –
9354898f-5337-5a30-ad68-7a18a4b20d37 | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
85f652dd-e996-5adc-984d-a9b1ab467f50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Pre-Commencement of Fill Works
92f7a7fe-643c-5184-8239-8818c5bb7592 | note | REFERENCE: VR 204.10 (b), VR 204.11 (b)
56c1d378-c4fa-536c-9e9f-71e607d3518e | note | – – – – – – – – – – – – – – – – –
37fdfb7a-13e8-52e3-99ee-f5d554cdd1e5 | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
0971e730-e38b-5d4a-ba0a-6f29c51f05ee | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
295e42dd-1830-59d2-b42c-8726361bd6c6 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
de51bc52-5881-5a00-89b6-9f6c9dd9ecd4 | textbox | Reference: Previous layer Lot Number:
312e18d5-2bd4-55fb-b10c-a1329b91aeb8 | note | – – – – – – – – – – – – – – – – –
6c364eef-52ef-5127-a2a0-0ef1206744d8 | note | METHOD: Visual Inspection
5c8c492c-1aee-558e-9cd2-5d81692c209c | note | – – – – – – – – – – – – – – – – –
0362fee7-0a92-5af7-a85b-4922b085c2dd | note | FREQUENCY: Prior to commencement of fill works
7a231ef4-051f-5f81-899d-78e899001511 | note | – – – – – – – – – – – – – – – – –
cf14b610-181d-5030-af02-051ad7c37a67 | note | CATEGORY: HP
e7962852-76f2-5ec5-92bf-4780f84ca0d5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set Out
430fd31a-69e2-5660-9ee2-380c7c61641c | note | REFERENCE: Design Drawings
c7477355-0aca-557a-9013-31c3d73303ef | note | – – – – – – – – – – – – – – – – –
4c757d18-11e0-5b74-9872-5ffdc93223ee | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
04f26c9e-1860-5dcd-b589-3a42afda0ebe | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
51e5d153-2d1d-557d-bee2-d584cf010df6 | note | – – – – – – – – – – – – – – – – –
5ee78005-2fb0-521f-a8bc-54579b6e90dd | note | METHOD: Visual Inspection
d16f0fad-28b8-5183-9091-91726422168b | note | – – – – – – – – – – – – – – – – –
4affe157-0891-51c4-b399-e6a4e77c1a78 | note | FREQUENCY: Each lot prior to commencement
04dfb599-9e39-50f5-94a9-a3d9b913df17 | note | – – – – – – – – – – – – – – – – –
09dcd6b6-238f-561f-92d3-ca09ed3be432 | note | CATEGORY: HP*
2004c099-948e-5945-86a7-9e72eb5fd942 | note | – – – – – – – – – – – – – – – – –
0f80ea45-2131-5d52-9098-b8cfad9a22b9 | note | RESPONSIBILITY: PE
0983af7b-ddba-537d-9262-34f231a9ee9b | note | – – – – – – – – – – – – – – – – –
e63db1ad-0d19-539d-bbc1-0b2811d2e635 | note | VERIFYING DOCUMENTS: Signed ITP, Lot Map
46f61307-1ea2-55ee-a19d-20e1b99fbb3b | date | Date Completed:
| section | Type A Fill/Verge Activities
| checkpoint | 5.1 Placing of Fill
d03992a7-b6e3-52ac-87e1-f29b60775b04 | note | REFERENCE: VR 204.10
93e8e571-090b-5713-8c9d-0621cbf57832 | note | – – – – – – – – – – – – – – – – –
41670159-f1f1-58c4-8254-16e361df701e | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
0b691eb8-0be4-52b2-9bcc-30e7dd125628 | note | – – – – – – – – – – – – – – – – –
b3f0950a-8c9c-5c58-9c32-c0d22fb98a32 | note | METHOD: Visual
0d3212de-bc88-5955-9f73-07b7ae009c5f | note | – – – – – – – – – – – – – – – – –
3b8a5ec1-305d-5aa6-bc0b-f68d86b860bc | note | FREQUENCY: Each Lot
20824725-01a8-5c5a-8e5e-127e8e135f07 | note | – – – – – – – – – – – – – – – – –
a777bbcc-725a-50a2-ae33-8ee4b7f6312d | note | CATEGORY: WP
75526e70-e022-5029-a33a-60d4b3942914 | note | – – – – – – – – – – – – – – – – –
7b0df6c2-958a-5b1a-b22d-ae714f39c1d3 | note | RESPONSIBILITY: SE/Site Supervisor
743c3f16-db11-533e-bfe1-708835a1ea9e | note | – – – – – – – – – – – – – – – – –
ef9ac797-58e9-5d97-8a95-ed44a7876dcb | note | VERIFYING DOCUMENTS: Sign ITP
b7134c18-5920-55dc-b454-a8b0ce1636a1 | date | Date Completed:
| checkpoint | 5.2 Test Roll
00817c88-7839-5260-aa21-39554009042e | note | REFERENCE: VR 173.03, VR 204.12
74bf7087-3503-504e-bc14-193567204bbf | note | – – – – – – – – – – – – – – – – –
85096875-2dbd-59ba-b25c-44fe68f47bba | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
7d965e93-5665-55d1-985b-aec0c5e3f2e6 | note | – – – – – – – – – – – – – – – – –
638a48c5-c59c-525c-8ef8-a748eb747022 | note | METHOD: Test Roll as per 173.03
d144035c-1ccd-58fb-a6db-4552bd7c5077 | note | – – – – – – – – – – – – – – – – –
770fbb8c-94d9-5d8f-9c13-12ef6ed62762 | note | FREQUENCY: Each Lot/Layer
deb9fdb1-0ac0-53fb-b85e-dfb71fceab4a | note | – – – – – – – – – – – – – – – – –
217f2d31-6f74-572d-a935-326c6608e4df | note | CATEGORY: HP
4d219967-255c-5e51-aa1e-6b075003bf7c | note | – – – – – – – – – – – – – – – – –
603fe05e-1fd1-56cc-b3fb-430c28311b2e | note | RESPONSIBILITY: SE/Nominated Authority
92c489f7-9811-5cbc-bd72-09d2f03dc4bb | note | – – – – – – – – – – – – – – – – –
934cbcaf-84a4-5d3b-8d9d-54d6a9ff31dd | note | VERIFYING DOCUMENTS: Sign ITP
6d42233c-50fd-50f3-882e-10a38cf76209 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 Compaction Testing
7d101277-7a5c-5bbb-b001-94a6492b3e2d | note | REFERENCE: Table 204.131, VR 204.14 c) Table 204.142
68d79a2d-e134-5be0-bb36-30e5f07e69e4 | note | – – – – – – – – – – – – – – – – –
bf0a05e0-5b43-5be6-a7b3-dbad0f4cf9fd | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
1f6facd6-8330-57c9-82ec-a2e87f105b9c | note | Standard Compactive Effort
e1fd452f-18fa-5e0e-b4b1-9f13c7083fa7 | note | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
be07452e-5920-5615-9d0a-cdf2bf011544 | note | Compaction and Moisture content
ef8cad7f-fe69-5e44-9bcf-d78d45bb8e98 | note | ○ Scale A: Characteristic Density Ratio 99%.
7ee6dd64-e348-58db-9e34-85278c7cd628 | note | ○ Scale B: Characteristic Density Ratio 98%.
8b2df58b-d9f0-5fe9-a95f-f88eb48c0828 | note | ○ Scale C: Mean Value of Density Ratio: 100%
8b483601-ee60-59f8-9b63-0f52a217184e | note | Lot size - the leser of one day's production or 5,000sqm
35b0f23f-d6a2-57e3-8a72-5500cd15f966 | note | ATTACH: COMPACTION TEST RESULTS
6bd35665-eed4-5487-b7c2-c7ce8d5fc34f | note | – – – – – – – – – – – – – – – – –
16afb45e-3cba-53e5-92ff-30019c19ef88 | note | METHOD: Review Document
9fb83fc4-5986-5f71-8d11-751c6c83aef1 | note | – – – – – – – – – – – – – – – – –
8f0c4c80-760f-5c22-96e4-c4c601846a0f | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
0c3fa76c-396a-5184-bdf3-b89de0762d58 | note | – – – – – – – – – – – – – – – – –
d6cded80-1534-5f30-a97d-a0d89a72dec0 | note | CATEGORY: IP
1280e360-f466-50d5-8488-a23a1a98dde2 | note | – – – – – – – – – – – – – – – – –
009a3800-41b4-50a0-9c9b-77897f25b60e | note | RESPONSIBILITY: SE/Site Supervisor
739a8721-e9c5-5ae1-a326-7d2bb7f52944 | note | – – – – – – – – – – – – – – – – –
3ee4d4ae-73bb-5375-acbd-d97fb95cf547 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
243220db-1a92-5e1e-ab00-b2b8b8c1d9a0 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.2 Survey Conformance andPreparation of final surface
13f1433d-12c1-5de8-b6f9-1fc642226eb0 | note | REFERENCE: VR 204.15, VR 204.03f,g and h
0e60c832-6f98-5d3b-af01-e9d418e5e58b | note | – – – – – – – – – – – – – – – – –
9e3b180b-75b7-5193-96de-d791efa28c9d | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
add67eff-e6df-5650-a6b7-ff3ae758a1b9 | note | ○ The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
25864ca8-71de-57d1-ba58-403ca3d6b87e | note | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
19e36419-3c3c-55ab-908d-38815871a595 | note | – – – – – – – – – – – – – – – – –
85017af5-248b-52cf-acd5-350fbdf66467 | note | METHOD: Document Review
9065ec0e-6afd-5ec9-9500-af19152aee20 | note | – – – – – – – – – – – – – – – – –
768d5b5e-3571-5344-85b7-8cdcf405cfff | note | FREQUENCY: Top of Type A/Verge
f8ad5dbc-3ac2-5282-9ce9-6537fef2fbe4 | note | – – – – – – – – – – – – – – – – –
9e4a91a5-e51f-582d-82d7-c7438f7a2f7e | note | CATEGORY: IP
abd8e272-c8d7-562f-abfe-1699bc7aa8c6 | note | – – – – – – – – – – – – – – – – –
f3248163-3250-59f9-bf33-efdedac0d30f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
76de361d-6e17-5dd3-a3c4-14c7fde64bfa | note | – – – – – – – – – – – – – – – – –
d24f5fb1-1743-54d7-b1c2-2bfd18880008 | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
6c005380-cdf7-5cae-b4c2-3dabf101711f | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
fc2647a9-779c-5171-9120-55f93251841b | note | REFERENCE: MRPA Quality Management Plan
2eb94fb0-1e32-5128-8511-202d1c608a20 | note | – – – – – – – – – – – – – – – – –
2a0decc8-d066-5dec-a0a9-0f4a93f5af5e | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
598a02bf-c848-599c-9c07-2df848bfd243 | note | – – – – – – – – – – – – – – – – –
6bc81a30-ca77-511b-ac38-9b9a1a11ad8c | note | METHOD: Document Review
52c20496-d1da-58ff-9a75-b01493ba6023 | note | – – – – – – – – – – – – – – – – –
31b66a9e-a349-576c-9458-93154d5d9cd2 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
12e11ef1-2fce-5eee-9902-6c43dfe9e056 | note | – – – – – – – – – – – – – – – – –
d57929ee-451e-5088-a213-4c06ef5dc266 | note | CATEGORY: HP*
b7156284-3c4b-5b42-9df0-c2e227f439b7 | note | – – – – – – – – – – – – – – – – –
6104e7e8-c1ae-5455-a794-f062e7e1aa49 | note | RESPONSIBILITY: SE/PE/SPE
e886e724-fc05-5210-b0a2-13c6897cfd70 | note | – – – – – – – – – – – – – – – – –
6cda02a4-e184-56c0-87d7-acc33ed40924 | note | VERIFYING DOCUMENTS: This ITP
07fa2106-5ffa-5d09-be19-85429a38d9d0 | date | Date Completed:
| checkpoint | Final Inspection
d71359e1-9487-5b07-8123-46d99d44da91 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
454a14c5-679d-5a67-b8b9-c28476126244 | textbox | Name:
b9d3141a-f20f-5ad2-8dae-b8ce987ab496 | textbox | Position:
a6773e95-05b0-55b4-8c04-ff9410c6a52e | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-178-STR-SSB-L-Shape retaining Wall Rev 1 | itp | ITP-178-STR-SSB-L-Shape retaining Wall | dd20f4ef-c915-4e2e-8001-d30736cfb8ac
| section | Referenced Documentation
| checkpoint | Referenced Documentation
cb64ffdc-d99c-5f8d-9f3c-c3ef9fef2c1a | note | Document Title: ITP-178-STR-SSB-L-Shape Retaining Wall
c267726f-f02c-550a-a33c-6a7f51acb915 | note | ITP Description: SSB-L-Shape Retaining Wall
d4fa89e2-c0c3-539a-ab00-aacc3a0bd90c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
5b5d7149-d56b-59e9-ae49-79206d9b73d5 | note | Discipline (e.g. CIV/STR/RAIL): 178-STR
fe27d8aa-c71c-5e4c-a293-f3828330add7 | note | Revision Number: 0
c7a76891-c72c-5804-8445-db70f9edf97e | note | Revision Date: 13/06/2024
da7234f8-2406-5320-8244-11fe7037c26d | note | ITP created by: Victor Mira
56a4b9df-5da5-51e2-96b9-4c80df574540 | note | ITP approved for use by: Victor Mira
ec169ed9-517f-51a4-9132-426a4029e454 | note | 1.1 Non Dependent
4bf7549e-b339-5880-867e-0d0d3e2f2470 | note | Reference: VicRoads Section 610
661fe70d-fbc8-5ab7-85a5-0de82203f033 | note | 1.2 Non Dependent
4623d69e-7b11-5713-9a87-3514a3a5a25c | note | Reference: VicRoads Section 610
0f864b0d-174a-5396-9d9a-eca4d80d316e | note | 1.3 Non Dependent
0cb559ef-d256-5a4f-933f-b11956ddff70 | note | Reference: VicRoads Section 620
8e0124f6-e1bb-5f6f-b7b6-ce37a2c47e08 | note | 1.4 Non Dependent
1ee85812-f42c-57dd-9d70-d0c8a481b574 | note | Reference: VicRoads Section 630
1a730210-f150-5c9d-83b3-0cfaaa48521b | note | 1.5 Non Dependent
9df7a175-362d-5c75-a5e9-945bb929f44c | note | Reference: VicRoads Section 614
8800c92a-2042-536f-bdbe-0b28369efd74 | note | 1.6 Non Dependent
72e5608b-0a36-50f0-af0c-187cb91ccdaa | note | Reference: VicRoads Section 611
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
9235ec0f-2ebc-55f7-96af-e889af2aa580 | note | REFERENCE: 610.07, Table 610.071, IFC Drawings
8fd2e96a-1b48-5002-9431-3ea095992b76 | note | – – – – – – – – – – – – – – – – –
2ec0f416-edf5-5ec0-b454-5d2c38911ce3 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
cefe4caa-cd17-5dfa-a187-ecd2beb34468 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
c56f5f0a-77b4-5665-8bbd-963e4afca48f | textbox | Enter: Teambinder Material Approval number
1a0e7522-9294-5e5e-a813-083b47407817 | note | – – – – – – – – – – – – – – – – –
50ae9807-ac02-5ac4-8b0e-422648cfacec | note | METHOD: Document Review
325999e9-c1a6-5db0-b970-f0be6d4a1578 | note | – – – – – – – – – – – – – – – – –
585c99c8-cae2-5851-8d73-07c3a582789a | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
ffd75401-17ab-532b-8509-ba1f6abb05b5 | note | – – – – – – – – – – – – – – – – –
79fbc906-26d6-5284-977b-8bb18bfd3e9e | note | CATEGORY: HP
a1cf59ec-b7b4-5545-b1dd-2fcf9decec54 | note | – – – – – – – – – – – – – – – – –
366f2992-bc55-523b-ab57-a6a108986342 | note | RESPONSIBILITY: Nominated Authority
394c3178-b4c3-5678-8ded-5a4dd25a3a34 | note | – – – – – – – – – – – – – – – – –
f971a571-b131-50da-8c3d-8ac375bff29b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9ab6d6c2-8004-5e99-8ec5-b0fd177b90df | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
069f294c-e01d-50ed-8c6e-e0403a2faa1a | note | REFERENCE: 611.05 (a)
a9782507-a496-57d4-8b96-b3658e7a40fd | note | – – – – – – – – – – – – – – – – –
beb3650a-a952-5273-a923-90ef55e47860 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
42464bfd-03e4-532e-9a65-1e72b7d91342 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
0078d265-8527-5f4e-a73c-c625c4058935 | textbox | Enter: Teambinder Material Approval number
b447faf9-9f84-5993-9c02-ca22d2a43edc | note | – – – – – – – – – – – – – – – – –
313c9766-f05f-54c1-9258-fa1c9211d885 | note | METHOD: Document Review
14a71e98-ebed-5aac-a93e-8aa9e0e3ccb2 | note | – – – – – – – – – – – – – – – – –
c3ccc22d-4928-5626-b89d-188b839818ff | note | FREQUENCY: Once for each supplier, 14 days of award of contract
5551466d-37b4-50e5-ade9-7b89939763e2 | note | – – – – – – – – – – – – – – – – –
3371e61e-2648-5646-a988-63c07889afb6 | note | CATEGORY: HP
ce5c25fb-2189-5df0-8e1a-c27e16a50fe9 | note | – – – – – – – – – – – – – – – – –
635c6118-b9a4-54a4-9be1-0a9431257427 | note | RESPONSIBILITY: Nominated Authority
cafc5fe0-c982-582e-a751-084b6cbfe090 | note | – – – – – – – – – – – – – – – – –
a3c5ccdc-b924-5b44-b1c6-0f0cc8619c06 | note | VERIFYING DOCUMENTS: This ITP
997b77e4-ec53-5e0e-8f63-98d6e002954f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
36ae669d-8eab-5999-9ed4-5812792a2e5a | note | REFERENCE: 610.26 (a)
9318727c-61ce-5053-8038-0ab58b19cbfb | note | – – – – – – – – – – – – – – – – –
3118680f-e460-5a75-8a99-a1c3d095fcc9 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
3b5ec471-a5ae-5157-ae9d-50b77a8b7fcb | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
763655ff-d49e-50c6-aaee-fee4453ae496 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
33b959f1-0cee-554f-9106-83432dd5cd42 | textbox | Enter: Teambinder Material Approval number
a3543dd5-e3b0-5691-943a-add7ac287173 | note | – – – – – – – – – – – – – – – – –
5e55b5d1-12cd-530c-87b3-57d3644c87ce | note | METHOD: Document Review
22d6c030-f7bf-5cbd-8acb-1ebd75f77b76 | note | – – – – – – – – – – – – – – – – –
59961428-6053-50b4-8e61-621f0950c448 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
89115247-2b4a-5342-ab4d-b2b831b152e7 | note | – – – – – – – – – – – – – – – – –
922718fd-cc7c-52dc-8e11-b921a60d06b7 | note | CATEGORY: HP
a288a3c2-9382-5e40-a5cf-b32cc57c3cec | note | – – – – – – – – – – – – – – – – –
ad443d41-64ac-5290-8d61-25785874bf94 | note | RESPONSIBILITY: Nominated Authority
a11cafec-c4bf-5b05-920f-1ddd027ab4b2 | note | – – – – – – – – – – – – – – – – –
25bb91b0-2b92-5e23-90c6-448bb76e18a4 | note | VERIFYING DOCUMENTS: This ITP
323a5c56-da67-5c04-a954-b43ded00a89c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
0403f2b8-a761-5ce9-974d-7a94d6db1d6a | note | REFERENCE: 610.17 (f)
bfb414e1-2604-5b07-9c11-b92ff433d2bb | note | – – – – – – – – – – – – – – – – –
17d2338a-bfe6-5763-86a0-922bbb0ff147 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
c8e58cf9-2da7-5ff7-a683-8a59482fea8f | textbox | Enter: Teambinder Material Approval number
6e356e71-e382-552e-903d-854c65d64629 | note | – – – – – – – – – – – – – – – – –
8ee24997-0f09-5188-99b9-ff3382b21dbd | note | METHOD: Document Review
c6ca37a5-3399-5a35-b038-8a4ce60c6a2a | note | – – – – – – – – – – – – – – – – –
f2eead5f-0777-59df-8a67-058cd179dd0a | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
7f6f584f-3f93-56d6-8e5d-9b962a35b705 | note | – – – – – – – – – – – – – – – – –
1de6115a-ba37-5af3-b490-6f329ac9361a | note | CATEGORY: HP
2514ffe0-564f-534a-8eb8-c7083fbaa8e6 | note | – – – – – – – – – – – – – – – – –
0f99695c-6f57-5734-a4fc-a1c4d649e620 | note | RESPONSIBILITY: Nominated Authority
89e1066e-3fa3-5856-9447-0f0287d96160 | note | – – – – – – – – – – – – – – – – –
be41d328-e599-5480-8b7c-afe57ca438fb | note | VERIFYING DOCUMENTS: This ITP
2ccf3ee1-1726-5c21-bca0-49b7f26b5933 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
d59021cc-ac9d-5ee9-9b2c-6f5c2ea45d3a | note | REFERENCE: 610.23 (d)
f7016ed4-dcb9-553c-b5d1-dacb53aaee48 | note | – – – – – – – – – – – – – – – – –
9eea0323-4f6f-55fe-8a9e-fc9b2ba0169d | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
6a66fc67-2bba-5a6f-b140-ec39604e7fcd | textbox | Enter: Teambinder Material Approval number
5f5c5216-3b7d-5d84-8b0e-f8b34d599b28 | note | – – – – – – – – – – – – – – – – –
7b692915-b4ba-52ad-a3ac-04b597ef4b30 | note | METHOD: Document Review
dcc3dbc0-825c-5ab5-b2ad-9ce06eccc488 | note | – – – – – – – – – – – – – – – – –
9e86661f-3f1a-5340-a2fb-6233b9100c55 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
d8790599-7da8-5c1e-9a3a-baaac3f5bab4 | note | – – – – – – – – – – – – – – – – –
dba6d01e-07f7-586d-9bf6-954937387f1b | note | CATEGORY: HP
b1146fa1-c51d-5142-ac93-182195d77164 | note | – – – – – – – – – – – – – – – – –
87888b91-5285-5c43-85cc-af6725f8677d | note | RESPONSIBILITY: Nominated Authority
5be27272-bf94-5a62-9d5a-8064d8b49039 | note | – – – – – – – – – – – – – – – – –
f92f1e28-9bc9-5179-bff1-8b111df36f45 | note | VERIFYING DOCUMENTS: This ITP
4ee5d4da-8403-55f6-ae9d-9b1a8f39e268 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 Joint Sealant
55e7f112-caf5-5ff8-a253-2f40df8af6f1 | note | REFERENCE: MRPA Quality Management Plan
ecc3f8d5-417b-5afd-aa3d-76248300bd33 | note | – – – – – – – – – – – – – – – – –
1a7fdb12-ec43-5911-ba26-43190a0263fa | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
7d7eaf21-0ea1-56b2-b466-4349912adc5e | textbox | Enter: Teambinder Material Approval number
1dd98ec9-5cc3-56f0-b8ea-53b2894405de | note | – – – – – – – – – – – – – – – – –
3a212f89-8d0a-50ab-9a88-fc9a4c7ca681 | note | METHOD: Document Review
9892a19d-771e-5ab0-9686-b5251788ac1a | note | – – – – – – – – – – – – – – – – –
f899b73d-feab-52f0-8635-091fc602c8dc | note | FREQUENCY: Once, for each product
4f0f7909-7a9f-54e0-b476-c942505419c4 | note | – – – – – – – – – – – – – – – – –
a60a7a45-5cdf-57a0-9d93-15e9c461cb35 | note | CATEGORY: HP*
7d57198e-1e00-550e-916c-c21f71780991 | note | – – – – – – – – – – – – – – – – –
f74e7615-5ea1-5153-a08e-f2fb896173cb | note | RESPONSIBILITY: Nominated Authority
8e6a4607-da79-5702-9d0a-ae244a0135ed | note | – – – – – – – – – – – – – – – – –
76230635-39f6-593d-a492-f582d7e171b8 | note | VERIFYING DOCUMENTS: This ITP
011b0bdd-6af5-5a16-97a0-9a592c0f9bcf | date | Date Completed:
| checkpoint | 2.7 Subsurface Drainage
30582ae3-932d-508f-94d5-a721a9daa8c4 | note | REFERENCE: IFC Drawings
589325e3-e34a-5179-9aaf-7135095f8146 | note | ○ 702.03
9312bef0-3237-5b0d-b145-05f1644a6685 | note | ○ 702.06
4735cdbf-286b-50c8-be9c-268345a61bbb | note | ○ 702.07
1cc4abf7-2168-5d42-bd00-56daf54a15c5 | note | ○ 702.09 (f)
6bc12795-1e98-553a-99be-d26a13d485e7 | note | – – – – – – – – – – – – – – – – –
ef3d5f18-baab-5e00-926f-a9566e9b8aa4 | note | ACCEPTANCE CRITERIA: Details of subsurface drainage as per IFC drawings
611213af-3554-5160-85ba-86c432cb2c95 | textbox | Enter: Teambinder Material Approval number
2a098440-f9d0-5e5c-8fa3-f51ed7b7af2b | note | – – – – – – – – – – – – – – – – –
1bd7e440-62a0-56c1-abf5-6d99306cd9be | note | METHOD: Document Review
d4bfe771-a3ca-5b82-9a8b-ff9c7d80fb28 | note | – – – – – – – – – – – – – – – – –
0f55254b-93fd-510a-9f1b-feaf79befb70 | note | FREQUENCY: Once, for each product
f4f4076c-1203-5d9d-bdee-2e1508ad720d | note | – – – – – – – – – – – – – – – – –
d5983c45-8583-5450-b75c-bdc9e7e2af22 | note | CATEGORY: HP*
965cbbad-e86f-5e53-a7c5-a67fe7bb1e64 | note | – – – – – – – – – – – – – – – – –
40462bc9-ff4d-5b08-9c57-4b91143167cf | note | RESPONSIBILITY: Nominated Authority
883216b9-d248-5f2b-beed-dea72ac69055 | note | – – – – – – – – – – – – – – – – –
0e026ba2-8c53-5808-b31d-9515d1766050 | note | VERIFYING DOCUMENTS: This ITP
b4e917d4-bef8-5208-9ec3-3f09f35ba6c2 | date | Date Completed:
| section | Preliminaries - Procedures and Documentation
| checkpoint | 3.1 Precast Elements
d9d551a3-48c9-5713-8346-39c3dc9527bc | note | REFERENCE: IFC Drawings
696a59c9-8080-5d2d-9ad8-a6554f938f01 | note | ○ 610.46 (a), Table 610.463
5ebff8db-7bde-5eb4-85c6-d4ec59b49ec0 | note | ○ 610.47 (a), Table 610.473
cfdd6fdd-4424-5a10-b1f2-0b77465f5dc1 | note | – – – – – – – – – – – – – – – – –
3c010f15-6e8f-5eee-be3a-b7c524b5d517 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
35ff87ca-9224-5ed0-9e41-a6aa7a1b58db | note | i. Certificate of Compliance / Birth Certificate
615e80af-7186-5dcf-ad79-c674edc86a72 | note | ii. Compressive strength test results
33dbe9b5-380a-5271-8d73-6f2a1f5f803e | note | iii. Precast Lifting Design
287521aa-4b76-5d45-b6de-44835163a75a | note | iv. Pre-pour check sheet / ITP
39b5491a-e227-5c44-8a15-fd1be844c2ff | note | v. Post-pour check sheet / ITP
bfd52700-d589-5c69-993a-ed96992668dd | note | vi. Covermeter check record
b7c33463-eb4d-5ff7-89de-21911b53722b | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
57e8f6fb-96fa-5f35-b3d3-b1a3f0e540cb | note | Note: Different revisions of 610 have different clause numbers
c93fb9f2-275a-5724-91ba-9849d6f554dd | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
b784b495-c1cf-5958-aaf5-b73866eeef5c | note | – – – – – – – – – – – – – – – – –
f5eb2c00-5caf-5ce2-a945-9cbcb1a42d10 | note | METHOD: Document Review
bb14213b-5f57-5072-9b7a-cfa3698eba7f | note | – – – – – – – – – – – – – – – – –
5e982469-a1f5-522b-95b4-3c079619ccdc | note | FREQUENCY: Each element
522992c3-247b-5408-a852-584e412f1f6c | note | – – – – – – – – – – – – – – – – –
bfb2c646-fd98-5e41-8af4-d6ec58c6888c | note | CATEGORY: HP*
81b08e6f-534c-5fe8-b41f-ac2032ca7c31 | note | – – – – – – – – – – – – – – – – –
9089697b-1d7e-5340-80b1-c269af692e84 | note | RESPONSIBILITY: PE/SE
f6b9898d-bad7-5a96-9685-0e75aad582a5 | note | – – – – – – – – – – – – – – – – –
161eb75f-8fda-53f4-8fb1-18ce800a8f8a | note | VERIFYING DOCUMENTS: This ITP
207e1653-a826-52ff-adc5-f51f5f119a16 | date | Date Completed:
| checkpoint | 3.2 Precast Base Slab Founding
cf2348c8-14b0-530e-9b34-eb1362e01b77 | note | REFERENCE: IFC Drawings, Temporary Works Design
52e30033-45cb-57b8-9862-03e617541555 | note | – – – – – – – – – – – – – – – – –
ab11d4e3-dcd9-5dd4-9ee1-c93f7f38a45e | note | ACCEPTANCE CRITERIA: Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters:
e8d9695e-65cd-5b65-b0cf-f769710d556b | note | Attach: Test report or Geotechnical report
1ac7c8d4-3d1c-52c6-a034-290c891b0e77 | note | – – – – – – – – – – – – – – – – –
90535829-dfbb-59f2-b274-874334d0c963 | note | METHOD: Document Review
70df7687-4857-558f-b9b5-fd5c78c11bd1 | note | – – – – – – – – – – – – – – – – –
2f4b920a-99e6-5b39-8d2b-7e64b2bef52d | note | FREQUENCY: Each installation location
a7244e86-5dcf-53dd-9273-b71b31652a60 | note | – – – – – – – – – – – – – – – – –
7a245c14-1933-584d-90a9-889f8158acd9 | note | CATEGORY: HP
475b767f-ceb8-5d5d-8673-a61eccc3b592 | note | – – – – – – – – – – – – – – – – –
eccc89ae-1d8d-51d6-8792-a9cdf930adba | note | RESPONSIBILITY: Geotechnical Engineer
12e93c03-d61e-5a92-b792-d5e6c2d9bbc3 | note | – – – – – – – – – – – – – – – – –
5dbae1f8-a624-5490-abf3-446fae84bd7b | note | VERIFYING DOCUMENTS: Attached Report
8683a51e-a840-511a-973a-38867d8f1de5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Work Method Statements
eef04af2-193b-5dbe-b963-f14ff7c05bbf | note | REFERENCE: 610.18 (a) (i)
3de87349-d6cd-56fe-b954-455e1100bdf3 | note | ○ 610.18 (a) (v)
ae3e278c-0563-5e8e-b927-38985446e0c6 | note | ○ 610.18 (a) (iv)
6366f9e1-7718-5d0a-b361-63385159f110 | note | ○ 610.17 (a)
aa8f292b-22cf-5b9a-ad82-aaa417cbfd5d | note | ○ 610.23 (a)
15b458f6-2775-53f4-a395-c831a006640a | note | ○ 610.46
82d1131b-141d-52f5-b0fb-6fea737272c5 | note | – – – – – – – – – – – – – – – – –
d658a1d7-058f-5118-8293-13e9cf7f4952 | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
04760545-ec16-532f-9206-47021104f31c | note | ○ Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
29c08872-d201-507a-b27b-576be5c6bbb6 | note | ○ Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
2a532233-be03-5c0c-ba62-d9f6c6d3d9bc | note | ○ Minutes of this meeting to be submitted to the Nominated Authority
faee8813-f58f-5f9d-81d8-ce103e8fc5b1 | note | ○ Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
e6f80a2f-86b8-5444-9b6b-e86963db454f | note | ○ Curing methodology/procedure to be submitted for review to the Nominated Authority.
a69a8ec6-a488-5976-ba89-87e61e7421ff | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
10faa5be-8360-5354-a4df-12c1be1f1466 | textbox | Enter: Teambinder Approval number
28109860-50fe-53ff-b240-5300b58b1cbd | note | – – – – – – – – – – – – – – – – –
68923494-a096-51fc-a3c9-82154b845975 | note | METHOD: Document Review
713ec634-bdf8-5758-9425-06b79a136840 | note | – – – – – – – – – – – – – – – – –
00384b53-fdc4-5164-bf55-6cdabd5e9f56 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
de432047-726b-5c87-bedb-5ac113105410 | note | – – – – – – – – – – – – – – – – –
aa0df165-93f9-5870-8b16-04a20b5f2bdd | note | CATEGORY: HP
2bffb13f-3476-5788-a2fc-c7f3f297f35f | note | – – – – – – – – – – – – – – – – –
f6409d43-b151-59bd-9160-b3b631607d54 | note | RESPONSIBILITY: Nominated Authority
8c8bb512-81d2-59fd-8026-79e0b750e938 | note | – – – – – – – – – – – – – – – – –
4c1832f3-ff6b-51ff-bfe1-92331e6987ed | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5c0db1d4-587c-5684-8bd6-de862349916b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 Temprature difference measuring-Calibration
cea3a495-4e19-5987-b148-4b74456790f3 | note | REFERENCE: MRPA Quality Management Plan
b5da3522-7ace-5d57-979e-46532bea475d | note | – – – – – – – – – – – – – – – – –
8601b7b7-2482-50f7-a3e6-96ef9632a0ba | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
23a322e0-02db-5474-bd0a-7da6415139e3 | note | Attach: Calibration certificate
455e5416-b2ca-5aa8-a1c5-51c856fa2c82 | note | – – – – – – – – – – – – – – – – –
c83b9f29-a440-571c-be85-e3323866d71a | note | METHOD: Document review
68a0de5f-d7bd-5cc2-a2db-8454177051a8 | note | – – – – – – – – – – – – – – – – –
9eeec542-3a80-5320-8466-b322ec2a5aaa | note | FREQUENCY: Where applicable
eac68ad0-22ed-5221-bd1e-e7c295346636 | note | – – – – – – – – – – – – – – – – –
dcf0662f-8a3f-5456-8014-6456c7491edc | note | CATEGORY: HP*
ee4edc4e-afe0-5c16-9da1-c8d426b332a4 | note | – – – – – – – – – – – – – – – – –
501e0de6-ba7f-5f72-aee8-e0e4cd544d61 | note | RESPONSIBILITY: PE
18c94fef-0b46-5a58-aa8d-29d4d59d7eba | note | – – – – – – – – – – – – – – – – –
9b3cf36b-31b2-5b75-ae62-ea7c904cdad4 | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
e3b52437-c0e1-5e4b-a704-8aeb41c4e470 | date | Date Completed:
| section | Pre-installation Activities
| checkpoint | 4.1 IFC Drawings
b28b8e05-84e0-5847-80ec-0de65ab35db2 | note | REFERENCE: MRPA Quality Management Plan
3bcd9465-a004-5944-a437-e744258188b6 | note | – – – – – – – – – – – – – – – – –
9387d243-47f6-537f-98e8-941c7c253a99 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
72b348b3-6657-5f13-b6b8-94f406ef0c7c | note | – – – – – – – – – – – – – – – – –
c1130e16-2135-57fd-8cba-c2452174ff02 | note | METHOD: Document Review
9e5ecfe7-b400-5422-a165-df0208272581 | note | – – – – – – – – – – – – – – – – –
f686baf8-91b8-5aae-8c69-84d9384cfa97 | note | FREQUENCY: Prior to starting Works and at regular intervals
fda34dee-64f4-53c8-870b-3604aae01611 | note | – – – – – – – – – – – – – – – – –
fff012e1-9532-5936-a324-44a6dbbbb795 | note | CATEGORY: HP*
ca58b76b-fcd0-585b-b9fe-2d85d670d964 | note | – – – – – – – – – – – – – – – – –
dddc3744-ba40-5e46-9137-1337b274cc5c | note | RESPONSIBILITY: All
9c303a0a-8710-50e2-8c0f-f4b64376dcb3 | note | – – – – – – – – – – – – – – – – –
1ef639a0-44d3-5d32-9f89-a0aaf6c604dc | note | VERIFYING DOCUMENTS: This ITP
064eb7db-e893-54cc-b567-18b3bbe46f6c | date | Date Completed:
| checkpoint | 4.2 Materials Inspection Checklist
5957494b-915a-52ad-9021-ffab11cdd3de | note | REFERENCE: 620.06
0fadd0bb-0054-52a7-bd41-7e07a96c19a5 | note | ○ 620.07
5d3f9d78-599c-5bb1-be08-099184c7e684 | note | ○ MRPA Quality Management Plan
4bbf41d6-a8b2-54ce-9fd9-7ca8fe940ea4 | note | – – – – – – – – – – – – – – – – –
ca30c212-00e1-5ebc-9288-0668bf6026a7 | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
d95deb4c-21da-5634-a655-b11e4e2b4004 | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
4a6854e0-0616-5239-beb5-c26c910bd496 | note | ○ Elements shall have unique identification and orientation marked (if applicable).
70fc7346-7f6a-581c-a912-3168c37eb670 | note | Complete: Materials Inspection Checklist in ConQA
38982745-4436-5947-b38f-098789bd9578 | note | – – – – – – – – – – – – – – – – –
c318477e-5880-5710-9bac-773e3d7a6d64 | note | METHOD: Measure, Visual
9265dacd-63e3-5a10-95f6-336a2e2884e4 | note | – – – – – – – – – – – – – – – – –
921990f2-0113-5d6c-9506-0a5ab1709522 | note | FREQUENCY: Each element
cbba49ec-7b45-5097-828a-bf651c073db4 | note | – – – – – – – – – – – – – – – – –
bea61db6-8b0f-538b-a3ca-cc46a35d12af | note | CATEGORY: HP*
bb3f7451-0a06-5bc8-9549-b0b72fa4fc0d | note | – – – – – – – – – – – – – – – – –
a1dbe079-6cad-58db-ad92-308ac1713d0e | note | RESPONSIBILITY: SE/PE
07782291-ff4f-59bb-80cc-bb1c458071bd | note | – – – – – – – – – – – – – – – – –
cffbb564-efcf-5c9e-941a-f620e70a4eb9 | note | VERIFYING DOCUMENTS: This ITP
6f77e608-3734-5a41-af1c-e9610fedeaf2 | date | Date Completed:
| checkpoint | 4.3 Survey Set-out of Precast Elements
eb63557c-e7f3-5597-bd55-0ddbadf521eb | note | REFERENCE: IFC Drawings
ba950781-feca-56d0-a5d3-ba5ebe71004e | note | ○ 610.46 (a), Table 610.462
c6401f13-2440-5a17-bd49-9af146d847a1 | note | ○ 610.47 (a), Table 610.472
648dfe78-f918-5977-b185-bdb35eb0355d | note | – – – – – – – – – – – – – – – – –
db44b9c5-f1d4-56e2-9165-474e89b6d9d1 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
4c7bba19-b6f1-51ba-a506-f638fa899d78 | note | ○ Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
0e591ae3-4adf-5287-a73b-4592b9e5848f | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
fb4f6400-d3c8-54be-9928-71108ad1ac81 | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
efa932f3-f7fd-58e7-82fe-9d826d3705ec | note | – – – – – – – – – – – – – – – – –
0815eee9-7c1d-53c3-8fdc-04feb3a565e2 | note | METHOD: Measure, Visual
315f93e8-a7a8-59c5-ada2-4475c7649b6e | note | – – – – – – – – – – – – – – – – –
773e5b01-b922-5012-b2f0-0e9de4673cca | note | FREQUENCY: Each element
68af4eea-b302-516d-9c2d-d3e6db2e40db | note | – – – – – – – – – – – – – – – – –
fd69d85a-975e-5cea-9b18-559901d97e93 | note | CATEGORY: HP*
17b82524-a3f9-5366-b23d-7d7fead4911a | note | – – – – – – – – – – – – – – – – –
d6854089-e217-5fc3-b667-9a9ceb1d374d | note | RESPONSIBILITY: Surveyor, SE/PE
8b558f10-9041-5e42-8196-cd2617a0c83c | note | – – – – – – – – – – – – – – – – –
4c34e86a-7f62-527c-8847-c0bc6e745fb4 | note | VERIFYING DOCUMENTS: This ITP
aaa44360-31e4-5319-ac9a-1e826fae2cb7 | date | Date Completed:
| checkpoint | 4.4 Shims Placement
5176470f-ed3a-54fd-9615-c07c298c2af0 | note | REFERENCE: IFC Drawings AS 3850.3
bfb5a1dd-5f03-53bc-a8bf-0f116bd78688 | note | – – – – – – – – – – – – – – – – –
737e8dc8-cbc7-5f40-b5a4-3c82a20b962f | note | ACCEPTANCE CRITERIA: Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
3742fbf3-5be6-56d0-8dde-2b4f3951f698 | note | ○ Shimming should be a maximum height of 40mm, a minimum length of 150mm and a minimum width of 100mm.
aa8b2555-49c5-5586-99bf-1790e2651190 | note | ○ Shims should be located at least 200mm in from the ends of the concrete element and bearing support.
c01686db-f0eb-542a-be72-255fe14be313 | note | – – – – – – – – – – – – – – – – –
53d2287a-c438-56aa-8801-a4422e76606c | note | METHOD: Measure, Visual
35da7e62-7655-52b7-8288-6620d10fce43 | note | – – – – – – – – – – – – – – – – –
7ec94f7c-2420-5666-9235-84b055b7af7f | note | FREQUENCY: Each element
2903fd5a-6098-5e66-a79f-3201fe0a0f09 | note | – – – – – – – – – – – – – – – – –
5f896768-bbe0-5f70-bb34-5d2633679f74 | note | CATEGORY: HP*
8b1ea18b-631b-52ad-8f69-1efd71564ef6 | note | – – – – – – – – – – – – – – – – –
ddf5a472-c322-5703-9e7d-8fa669e85ca2 | note | RESPONSIBILITY: Surveyor, SE/PE
2e635c9f-3d10-50ff-82c3-2739adfe4ad4 | note | – – – – – – – – – – – – – – – – –
8346dce5-7ce8-5991-83af-52d1896c78c5 | note | VERIFYING DOCUMENTS: This ITP
9cc4e971-93fe-5215-98d8-15f5c7a612d3 | date | Date Completed:
| checkpoint | 4.5 Survey Set-out-Concrete Slab
ca095fa2-9017-5459-883e-33f8ed25b415 | note | REFERENCE: IFC Drawings
0444a0cf-e930-5f44-89c7-fc2f4161f6a0 | note | ○ 610.47 (a), Table 610.472
a5df3ded-d29f-54eb-b8c2-80b1853e9704 | note | – – – – – – – – – – – – – – – – –
17b441f1-2389-55d8-ae88-528df3ccf276 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
151da105-693a-5d44-a2aa-a249ab220c7d | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
12df7c54-1820-5ecf-ad0b-6be0a3ffc276 | note | – – – – – – – – – – – – – – – – –
210dc240-d774-5e14-a96e-4439a35853b7 | note | METHOD: Measure, Visual
f66eca1c-5679-523b-b44d-b6613477947a | note | – – – – – – – – – – – – – – – – –
49489142-b5ac-57c0-a8e3-3425b61162ad | note | FREQUENCY: Each element
440764bf-273f-584a-bbee-c16f24664408 | note | – – – – – – – – – – – – – – – – –
86122e85-f0c0-5b18-9ea2-96425df94048 | note | CATEGORY: IP
c08c98e4-c30e-5b81-9b41-7a88c47f3c2d | note | – – – – – – – – – – – – – – – – –
945cb082-99d6-5f05-a062-5de9ae646303 | note | RESPONSIBILITY: Surveyor, SE/PE
ad4a6810-231e-5893-b458-add41839a4c5 | note | – – – – – – – – – – – – – – – – –
fbda8545-06b0-5b6b-805d-c69682de7ab0 | note | VERIFYING DOCUMENTS: This ITP
1c8506ce-6494-5785-96dd-3c75c0bea1bc | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
f267e2d7-390e-53cb-84e7-567fa2da9dc6 | note | REFERENCE: 620.07, Crane Lift Study
acbd1aca-3931-5d5d-8cff-9e7d823d63fb | note | – – – – – – – – – – – – – – – – –
01962a27-b43b-56ff-866b-5a6defcb0ea5 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
e0e916fc-07da-5d7c-84e2-a62abc428971 | note | – – – – – – – – – – – – – – – – –
41224cbb-5da7-5a0a-b35a-1104937fd2f1 | note | METHOD: Visual
1c83e31e-8c59-5b3f-abf1-051dcf6652e3 | note | – – – – – – – – – – – – – – – – –
4a46fcb1-6d9d-5df9-a4ff-059ab98da153 | note | FREQUENCY: Each element
b875bb2e-eb09-51d8-9d64-93a5e47848d3 | note | – – – – – – – – – – – – – – – – –
c427ffd8-f87f-5457-af75-48182bb9c665 | note | CATEGORY: SP
6d425fb4-c557-5445-bc80-9baa6bb2bf2f | note | – – – – – – – – – – – – – – – – –
e5c2f195-9c15-5bc6-a27a-5cf853b99655 | note | RESPONSIBILITY: SE/PE
ca3daa04-b34f-5258-a350-8c6302a5dae8 | note | – – – – – – – – – – – – – – – – –
d15b8115-6d7c-55f0-844d-9f888651c78f | note | VERIFYING DOCUMENTS: This ITP
0024cb02-5589-59c2-abdf-c3dd0c471eb8 | date | Date Completed:
| checkpoint | 5.2 Precast Placement
ca6dd52d-51cc-5c9e-9b5c-70c8247f6734 | note | REFERENCE: IFC Drawings, Temporary Works Design, 610.27
6c3f5938-e4e9-5495-b37f-0182aee9639f | note | – – – – – – – – – – – – – – – – –
bec4275f-5344-548c-9c7c-9c93918361b7 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
7b11f599-cc93-5cee-b0da-9de23e949ee1 | note | ○ The nominal gap between elements is 20mm as per the IFC Drawings.
b3f2f5f7-db99-5aa0-a909-0695679df95b | note | – – – – – – – – – – – – – – – – –
dd53b661-c8e5-594d-afb1-44d9486806d1 | note | METHOD: Measure, Visual
ee3273a2-1de8-5acf-9c1f-51c72786eddc | note | – – – – – – – – – – – – – – – – –
f6af60c3-8af7-58f7-8e80-665b043831f6 | note | FREQUENCY: Each element
293a8a66-3c84-5db2-b172-eecb6875ee9d | note | – – – – – – – – – – – – – – – – –
318aa8f7-c7b3-55f9-a98b-213b53a1f02d | note | CATEGORY: SP
bc74f146-f92c-5c0f-b341-f0037eefac6d | note | – – – – – – – – – – – – – – – – –
8476a33c-7e34-514b-aef7-37552649f71f | note | RESPONSIBILITY: Surveyor, SE/PE
f7673578-1217-5112-aa70-aa0a22beefbe | note | – – – – – – – – – – – – – – – – –
a71b6e81-fbfd-516a-9153-1dd5997e7cd9 | note | VERIFYING DOCUMENTS: This ITP
d7ced664-69a6-5866-93b0-3c7f565ecf2b | date | Date Completed:
| checkpoint | 5.3 Formwork Design and Construction
ea7065b4-5687-51db-aaab-8808c19cf80d | note | REFERENCE: IFC Drawings
4b1ec504-3b5c-5244-8471-c74a65fb504e | note | ○ 614.04
93f7ef91-f558-5905-afba-c9bda425cd5f | note | ○ 614.05
375b6b5f-64c6-5a09-a842-af225124e375 | note | ○ 614.06
8f4b0bde-65d4-59d3-87e6-ada92efa9fd1 | note | – – – – – – – – – – – – – – – – –
3936d8d0-8267-506e-afe2-bdbbc56524f9 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
3e7b7da4-1bc7-56bf-bc6a-d4a87deb1243 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
c36b9c01-188c-52eb-afcd-663b15f6800c | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
46bc78e8-e92d-5925-86f2-2c22ce65841b | note | – – – – – – – – – – – – – – – – –
c5c52310-8e28-514f-9e0c-e20aca5621c3 | note | METHOD: Document Review, Visual, Measure
ef8b62e2-6afb-5af2-8e0b-245803078b90 | note | – – – – – – – – – – – – – – – – –
3fd79247-736a-5197-aee4-4e70c9bf9df0 | note | FREQUENCY: Each type of element
4914661e-56be-537c-a14a-c1678c383599 | note | – – – – – – – – – – – – – – – – –
64096380-5a65-5a95-a47a-d3faea23e565 | note | CATEGORY: IP
a3a0e6e0-3d64-5f96-8146-ab9f0fc0c0a3 | note | – – – – – – – – – – – – – – – – –
8fa4588b-c001-57eb-a390-8aaad2e4bf19 | note | RESPONSIBILITY: SE/PE/SPE
cb49de9d-c04c-5556-87cb-c3eedfcbbb18 | note | – – – – – – – – – – – – – – – – –
df2deba2-6fd6-54cd-b023-835efec346e9 | note | VERIFYING DOCUMENTS: This ITP
4b08ef40-f91c-5538-9e38-fc8f960bf2bb | date | Date Completed:
| checkpoint | 5.4 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
2e3c3800-918c-5ef9-9de3-9451e780c984 | note | REFERENCE: 614.08
d0394eb8-cd87-5593-a8c8-d59adca4a6af | note | – – – – – – – – – – – – – – – – –
21b1d413-7907-5734-9cdf-1d54543daf74 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
49fc97b3-2339-5215-a510-f50a478dcfd0 | note | ○ Walls with heights less than 2.0 metres
8fe5d593-61cf-570c-b5cb-33e6a1835174 | note | Attach: Attachment C
85edc233-2d82-59c5-a5ed-73d7b5ebfaf1 | note | – – – – – – – – – – – – – – – – –
25485837-1da7-529d-bda0-c54189bfe82e | note | METHOD: Document Review, Visual, Measure
a3a61c8e-61c8-5479-8b16-bd1fc14f0207 | note | – – – – – – – – – – – – – – – – –
7ef28e09-85e6-5713-9e2c-36a45f6722fc | note | FREQUENCY: Each element (where 2m or less)
34de0fe5-35f3-59cf-afd6-f8676afbf4f0 | note | – – – – – – – – – – – – – – – – –
986f60d2-1379-59b2-ad8b-74f80e023073 | note | CATEGORY: HP
b950f3c7-b236-5dad-831e-123f873bda4f | note | – – – – – – – – – – – – – – – – –
5f03d716-64d9-5b4d-8d59-9a86f7338e1b | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
843a3cb2-73b9-5212-be18-7c22dad1a790 | note | – – – – – – – – – – – – – – – – –
4d6b8a6c-2587-5688-9655-00d08ea315c2 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d65782e6-82a9-5d1e-91c4-627f235c3a6f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 Pre-pour Survey
050d18b7-6066-52c2-99fe-5fb0b2ff2d90 | note | REFERENCE: 610.47 (a), Table 610.472
4ba6a57a-936f-5c92-b2f4-907d6fbe570a | note | – – – – – – – – – – – – – – – – –
eb53a9a6-83d4-533c-91a3-60b331b1a513 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
853cc9dd-6238-5076-8cf3-5bedee9b8b96 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
5694b236-105b-5599-9dc7-26a020ae533e | note | – – – – – – – – – – – – – – – – –
4090eb69-2a50-521d-8051-df5773de8331 | note | METHOD: Measure, Visual
3932dba6-b781-503c-b69e-f5c7c11e97d6 | note | – – – – – – – – – – – – – – – – –
4f904670-e398-5458-a8a4-79021d90403a | note | FREQUENCY: Each element
9af19350-7cdc-5cb1-8bdf-7b38ae34e24b | note | – – – – – – – – – – – – – – – – –
51cbb48c-84eb-56d8-8369-fc770d9ab11e | note | CATEGORY: HP*
0698f85d-fc4f-5f1d-a042-ecee09d1e03d | note | – – – – – – – – – – – – – – – – –
003a5941-5a44-5f5f-8d57-a335befcccc5 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
1d60b783-5e2b-52c2-b842-a5fcfb87fc55 | note | – – – – – – – – – – – – – – – – –
98fec0d5-4a20-5376-b8bb-47c03942dca8 | note | VERIFYING DOCUMENTS: This ITP
d0e45c7b-c65a-571d-852c-a874fb07756e | date | Date Completed:
| checkpoint | 5.6 Reinforcement Placement
259b6de5-2ea8-512b-8240-58d6ba39bf4d | note | REFERENCE: IFC Drawings
41705c74-d17c-5e11-baea-bfc82d3c100f | note | ○ 611.06
3854fc77-8a1b-5e82-b9b5-11f27c8d3fa7 | note | ○ 611.09
7470aa92-bef6-5270-9630-38048554eada | note | ○ 611.10
681319f3-e8bc-561e-8ee7-3c7f408845f4 | note | ○ 611.11
1268eea7-b489-5d03-8fc9-e282303dee24 | note | ○ 611.12
047c9225-3898-53b2-8d98-feb78a5261cc | note | – – – – – – – – – – – – – – – – –
324e60ce-57e4-5b2f-baf4-1a48ab4920fb | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
ad16d8b0-88f8-5bc4-9f2d-9ef173ffd695 | note | ○ Projecting reinforcement is the correct length and location.
ba190742-e5f1-5d11-b7f9-902aae0ae5b6 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
1e6c6f37-279c-546d-a898-77601a3efc1d | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
75c568bb-083e-5b67-ad2e-8663c82ced07 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
24c69232-7075-5c34-bff7-2274bc543dbb | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
c3aa3618-6516-5732-ae15-24d099caa02d | note | – – – – – – – – – – – – – – – – –
a914ac0c-e9f6-5754-b69b-1dd2e2785325 | note | METHOD: Measure, Visual
b98a017c-4dcf-5ea3-aeba-e7df472d9839 | note | – – – – – – – – – – – – – – – – –
a60b5151-6d19-565a-bebd-39be46458dee | note | FREQUENCY: Each element
92f5621d-393f-5de2-a44e-0c0e613e109d | note | – – – – – – – – – – – – – – – – –
e29483cf-273b-58ac-a5a7-8cd0a332b541 | note | CATEGORY: IP
7aff9bfe-47d6-5261-926f-03c0e2952394 | note | – – – – – – – – – – – – – – – – –
024677b5-41e3-5ca9-842a-a9ed21e874bc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9bd9ffa8-bb35-5798-9f69-77a222e51afb | note | – – – – – – – – – – – – – – – – –
60a67482-bfa9-580b-92ee-0d2c61827edd | note | VERIFYING DOCUMENTS: This ITP
a66fb8b5-9ebb-5b8a-8c26-f1beab65a2d3 | date | Date Completed:
| checkpoint | 5.7 Thermal Differential Monitoring
353dd007-7c16-5028-8e14-c1316f6a70d6 | note | REFERENCE: 610.22
0a22ceb5-9c47-5b7a-b86e-68d62a1118d4 | note | – – – – – – – – – – – – – – – – –
11961e3a-d619-512b-b14f-8417e39c387d | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
29bb5fb8-ce86-5e27-8fc0-00143049e8cb | note | Only applicable if the element has:
981fe39e-2659-56ed-a785-cc5b794cb452 | note | i. the smallest sectional dimension exceeding 500mm
5b2d5e59-1f2c-515b-a6e8-12b594b4c3f5 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
a3a42c30-7aa5-522f-ac5b-8d98be7f19bc | note | – – – – – – – – – – – – – – – – –
09a838fe-3019-5c5c-a29b-451519560596 | note | METHOD: Measure
fd6d2e38-5a7a-5d52-90f6-c8f62ba3a6ae | note | – – – – – – – – – – – – – – – – –
0027c979-3558-597c-97af-20a509f13f4a | note | FREQUENCY: Where applicable, each element
775849b5-d2e8-533d-887f-b0f084ec52b0 | note | – – – – – – – – – – – – – – – – –
1608bc31-39ca-596c-8387-13ae68869109 | note | CATEGORY: IP
95c6c76a-06bf-57b4-825e-3cd278e40bae | note | – – – – – – – – – – – – – – – – –
87b492ab-246c-5f8b-bec8-6e4093b27b8c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7e436bdb-7996-546e-aeb0-020aeae09834 | note | – – – – – – – – – – – – – – – – –
26e46219-cdf4-52cf-af63-04858aa034a9 | note | VERIFYING DOCUMENTS: This ITP
4bf6e4d4-b7c0-5116-a53b-6fa311e83124 | date | Date Completed:
| checkpoint | 5.8 Pre-pour Inspection
c2efd976-2474-59f7-b511-3ba7b7c06ca8 | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
23448fc6-1125-5dbf-87e2-a328a5ea2d40 | note | – – – – – – – – – – – – – – – – –
e05094c8-7fc7-507b-9816-85440cc2c9e0 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
087359c9-3aa9-5db1-850f-542d77771ab9 | note | ○ All foreign material has been completely removed from the forms.
71dad9fd-63e7-509e-9a41-17a2c79897ff | note | ATTACH: Pre-Pour Checklist
513d05d7-80ee-55e1-98d6-57bc0e93e460 | note | – – – – – – – – – – – – – – – – –
e6fe4816-1eee-5867-a02f-b571b6205567 | note | METHOD: Measure, Visual
fc736a99-2c72-50b2-8680-d878cbeeaa65 | note | – – – – – – – – – – – – – – – – –
1054e57a-25cf-568e-a7a9-271471b7e759 | note | FREQUENCY: Each element
f31e653e-e314-50a0-9bb6-8dc998ebd549 | note | – – – – – – – – – – – – – – – – –
d8ddb4b7-50e3-55b0-b34a-57fa9efdfddf | note | CATEGORY: HP
722c1e7c-1b25-5032-b132-33909110c30c | note | – – – – – – – – – – – – – – – – –
924617d2-2da2-5ddb-a22c-c584079899f4 | note | RESPONSIBILITY: Nominated Authority
8ae0a0ee-d112-5c9b-b9dd-34342231d95c | note | – – – – – – – – – – – – – – – – –
649efb0c-a347-5d7e-be40-6cec9e78c7f8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
5e8bc58f-563a-5774-9d03-45abeaecca86 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
6b73345f-dc0b-5ad2-81f4-e37f90f9497a | note | REFERENCE: 610.17
d5aebaf6-42b7-574a-91d1-1c336959cd93 | note | ○ 610.17 (a) & (e) Table 610.171
c3ef7e3f-9825-5b1a-b873-3864f1e70769 | note | – – – – – – – – – – – – – – – – –
3b1f1d3d-29a7-5c80-baf0-61eee5fd870e | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
b1c6f5b8-e007-5997-9bbc-823f01e1be36 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
49d0fcaa-ac67-542b-97e6-a96af684ea34 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
27d6c43b-3449-536d-83b3-5977ce6d1fa8 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
2ee74e0c-38d3-5ed4-af79-132bf446bfcb | note | Record: Required information on the Concrete Pour Record.
94843a25-1a63-54a8-81ca-51b9cb84cfc0 | note | – – – – – – – – – – – – – – – – –
123facd3-0c4c-58f1-924e-ce36abf9657a | note | METHOD: Measure, Visual
4cb9fa0d-a33d-5a49-a15b-cc964abe8d64 | note | – – – – – – – – – – – – – – – – –
0fa81020-ebbf-5792-9de2-69f20abf87e3 | note | FREQUENCY: Each element
84667e41-7ac0-560d-a4e4-6372b8c8fbff | note | – – – – – – – – – – – – – – – – –
464e8b45-77dc-5441-96a1-eae46d313365 | note | CATEGORY: IP
237db09e-8410-5d5e-9dd9-50465083f3e4 | note | – – – – – – – – – – – – – – – – –
55be25d7-b572-5343-9390-99b668f5714c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
ce664c6e-a30a-5f11-b84d-665b897d73b1 | note | – – – – – – – – – – – – – – – – –
b14e8ba8-2f03-5c89-9092-048c55739602 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
13920a9f-3294-546b-8103-4bfa1d193097 | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
ecc9f95b-5983-5e0e-8e1f-72c0e6350cd7 | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
434b50c6-4a75-5760-b587-cecfdce737e5 | note | – – – – – – – – – – – – – – – – –
398dfdbb-5e29-507c-91c7-2797cf96edfe | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
8551e7e0-5146-5eb1-9d98-f835c567fd51 | note | 0m³ to 10m³ = 1 sample
2e6dc9b3-f9fa-58c8-ba2f-e938fec6ac4c | note | 10m³ to 25m³ = 2 samples
a29ffb97-9288-5533-858f-f47e40289c2b | note | 25m³ to 50m³ = 3 samples
59c15745-4cfb-56e0-a42b-97c6e335a81b | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
cf2505f6-e0db-58f4-af40-5e73f6a922fc | note | ○ For each additional 50m³ and additional sample shall be taken.
6ac16164-a4f0-51cd-b884-de18e8bf54c1 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
b8cd0932-f3b9-5089-bb6c-9b80a05b519f | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
e413c8b4-3cc0-5fee-968a-138b4c13f8db | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
12e28d8c-596d-54b5-8426-beb289fa8aae | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
02a30d0b-66c5-5f38-933b-6372e8778de3 | note | Record: Required information on the Concrete Pour Record.
7e5cabe1-0741-5165-955b-879b1a7c5809 | note | – – – – – – – – – – – – – – – – –
d3f1354d-4509-5cf1-ba15-59a8b1f4867b | note | METHOD: Test
4295f3ef-1fa7-50be-8c2a-7153d43509a0 | note | – – – – – – – – – – – – – – – – –
b73fc6a7-32c1-55bf-9571-cb01dfbd771c | note | FREQUENCY: Each element
97f30522-5f00-5227-9f01-9e9d94734530 | note | – – – – – – – – – – – – – – – – –
e6fd55b9-8a55-524f-b986-866442f28993 | note | CATEGORY: IP
cf0db193-ed47-54ef-9e4f-d9be16432d5c | note | – – – – – – – – – – – – – – – – –
0712586c-1d13-549b-bc60-394628043cba | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
69baf57d-f37d-59c6-87a1-48b873235a05 | note | – – – – – – – – – – – – – – – – –
7e3b713a-ded9-51ba-ab98-8a1e0e46697f | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
b9e97524-597b-588a-a490-a6f73e5a0a1e | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Slump
fe720f31-25ae-533f-93b1-191c3247e8f4 | note | REFERENCE: 610.16 (c)
9140dcf6-7020-5bdc-9756-1280efa9432e | note | – – – – – – – – – – – – – – – – –
a68f4922-7e24-5703-a14e-b1f2d69a53ce | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
22dda8d3-b537-5f7f-b5d8-7018d026341f | note | <60mm = ±10mm
d813f8e0-06c9-5bf1-a26f-ad0e88edc31b | note | ≥60mm to ≤80mm = ±15mm
f310cba7-1805-5286-97ed-412502018be5 | note | >80mm to ≤110mm = ±20mm
83fcf051-3741-5fff-bc0c-b7ff6a61de83 | note | >110mm to ≤150mm = ±30mm
31a01582-8be2-529e-b716-49a6ad950552 | note | >150mm = ±40mm
7b9718c9-5644-5f42-baad-2d787a402f00 | note | Record: Required information on the Concrete Pour Record.
fdff5d11-17da-5c05-8ad9-5fea1d0f7965 | note | – – – – – – – – – – – – – – – – –
4b69b4bb-7623-52ee-ba48-f8df5a27ca02 | note | METHOD: Test
4d988a84-c413-5a0a-b7c2-99404bd0688d | note | – – – – – – – – – – – – – – – – –
7fa6538c-ddd4-513d-8abc-f5a6793617ff | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
ee2e92f9-e84a-5aab-a7df-9102cc3e4f1a | note | – – – – – – – – – – – – – – – – –
6451a09a-45bc-5574-ab5a-5ae941fd32d7 | note | CATEGORY: IP
4049b088-0d0c-52a2-81dd-1867a935af8e | note | – – – – – – – – – – – – – – – – –
f128e5f5-a1fd-50a9-a716-e2b84882677d | note | RESPONSIBILITY: Concrete Tester
bc532acc-ce53-51c0-a0d7-64d1064f7413 | note | – – – – – – – – – – – – – – – – –
c2704598-0f78-5112-bec8-b09bbeb2595e | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
d04ab70b-931e-5d95-b0c7-fcb097acdf82 | date | Date Completed:
| checkpoint | 5.12 Supply & Discharge Rates
140559e0-882b-51b0-8098-5ba843612f98 | note | REFERENCE: 610.13 (a) & (f)
fb4a393c-d287-5284-b053-249310f70305 | note | – – – – – – – – – – – – – – – – –
24ae368c-034a-5cfa-afec-1a61c0b088c7 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
941a4e7a-b224-5716-ae75-41c45c09b0d8 | note | ○ No water is to be added once discharge commences.
dd6505b9-a58c-541c-b0e1-7376a1fdb101 | note | ○ Maximum time between batching trucks is 25 minutes.
569dc6f8-b538-5a3b-ab72-1a789f2a0dab | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
906be2f8-d81e-5cf4-b334-7d18ae059e3b | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
152478e8-ecca-5a2b-832e-95446924283e | note | Record: Required information on the Concrete Pour Record.
9c548c13-2450-5ac5-805b-e104d0c997dc | note | – – – – – – – – – – – – – – – – –
a75e05ff-740b-5d58-afe7-f74421d9364e | note | METHOD: Measure, Visual
a10f1e8d-fa28-52d8-bea5-2fab803a837c | note | – – – – – – – – – – – – – – – – –
3ca97617-4384-53d3-ab7a-9c72c11c26e8 | note | FREQUENCY: Each load
2d608249-8bea-5e26-b6f9-66820e255e48 | note | – – – – – – – – – – – – – – – – –
5c15d01b-1ff5-5f93-a74d-cd855734a670 | note | CATEGORY: IP
2ff3699b-6f34-5c18-b1f9-7747d9a02425 | note | – – – – – – – – – – – – – – – – –
8d58a458-69dd-5a7c-b580-7f8df06e4d23 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3405f023-2ed5-54eb-9b70-32c142ca2469 | note | – – – – – – – – – – – – – – – – –
ca5c0b30-b0c8-56e7-aed0-171b3784833c | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
611f7744-1e0e-51ec-b296-49ee3425d908 | date | Date Completed:
| checkpoint | 5.13 Placement & Compaction
3d42b03f-d338-5bb2-9242-52cc4f3b08ee | note | REFERENCE: Placement & Compaction Work Procedure
358a4507-a108-5a33-8495-edb97ad9b589 | note | ○ 610.18 (a) & (b)
b5ad5122-e0f9-5120-a8f3-89c2946adafc | note | ○ 610.18 (d) (i)
a24b964a-5bf7-598f-8bd0-53784e0e4888 | note | – – – – – – – – – – – – – – – – –
1264c9db-0466-5982-a99e-d24c30ffc486 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
abbf86e3-83aa-5479-ab52-16ed95d44f41 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
668eea19-6eb6-5778-b539-6babc1026d9c | note | ○ Concrete is not dropped freely from a height exceeding 2m.
ea8e2c65-0276-5bc2-8817-342d6c04969f | note | ○ Concrete is not moved horizontally by use of vibrators.
39b7ead2-28f9-5826-9fb2-ad1a1c15c206 | note | ○ Adequate compaction is ensured
c98c014a-3ebb-5aea-a9f2-2f9038483c0f | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
e8a8c752-69c3-506b-a522-41f0c2b6734b | note | ○ Concrete layers are not more than 350mm
594ce28e-e060-58cd-a3a1-6aeb35dbb7b5 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
d4c226d4-81d2-5267-8570-3ac8e73ed506 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
d7ad1f59-793f-53a3-a73b-4c374e21f525 | note | Record: Required information on the Concrete Pour Record.
f7141135-fd93-5d97-9586-7786e18804e5 | note | Attach: Concrete Pour Record
62891d10-ee84-565a-8a55-372badd6d192 | note | Attach: Concrete Dockets
a316e1e2-8d82-5937-916f-2451e38855fd | note | – – – – – – – – – – – – – – – – –
ad4b70ee-5f96-5822-b1c8-5c7d0cf8fedb | note | METHOD: Visual
d52ea48c-6eab-5479-ad79-96892b72cc91 | note | – – – – – – – – – – – – – – – – –
b45dad8b-3c8f-5b42-831e-c4336247bc10 | note | FREQUENCY: Each load
4e296031-98fe-5e35-9f1a-70bf59cf9ebb | note | – – – – – – – – – – – – – – – – –
907b3cc5-9137-5109-a967-af63f1832e6c | note | CATEGORY: SP
d4cf9162-d270-5abe-93cb-790466897f1b | note | – – – – – – – – – – – – – – – – –
d034f07e-234c-5202-9c99-fb5181e13dd2 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b2c7a043-85bc-560d-95ba-77f837331862 | note | – – – – – – – – – – – – – – – – –
174e5b09-f860-551c-b446-a10b1281ae43 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
034b7327-4e09-5bf7-983a-5553fc0ad64e | date | Date Completed:
| checkpoint | 5.14 Surface Finishes
358e37dd-dcaf-5621-907e-733a86654bee | note | REFERENCE: IFC Drawings
dc010447-74d3-52a3-919c-480e48a52df8 | note | ○ 610.31
2c2f4134-4837-529d-91cc-894b8747a955 | note | ○ 610.20
becb5225-0c24-5a75-9c8e-09b3e24e5e2c | note | – – – – – – – – – – – – – – – – –
b2deb971-f157-51db-aee2-2e78092b4b84 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
b1e51558-0d02-5acd-a13d-b2f4fb1e3081 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
55c02a54-5332-5be4-b9c5-b7c1f38a13dc | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
c1ca91d6-11c4-54c3-8b1e-a8641cd88704 | note | – – – – – – – – – – – – – – – – –
3fc69f60-6d38-5be9-91f6-97c9c73fbdef | note | METHOD: Visual
4717db2f-1d2b-512f-a6e4-ec90d1493906 | note | – – – – – – – – – – – – – – – – –
52d3b902-164a-5f12-bbb7-e2c50e344356 | note | FREQUENCY: Each element
3bb2e780-4784-590e-8e28-0b5db6e9f5ff | note | – – – – – – – – – – – – – – – – –
1f9678f4-bec3-571f-af82-4cf299698a49 | note | CATEGORY: IP
9d9fb5a3-e0a0-59c3-84da-09d4233af6d8 | note | – – – – – – – – – – – – – – – – –
93db8d59-28ca-5e38-9660-4b2bbf616565 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
eacf622d-f831-5e2b-85f2-47e1f6a4f038 | note | – – – – – – – – – – – – – – – – –
72baf4bf-03ab-5bd8-9027-13eca1c9bb7c | note | VERIFYING DOCUMENTS: This ITP
13313893-f59f-5460-8451-16bfd92cb919 | date | Date Completed:
| checkpoint | 5.15 Curing
726cb3e1-586e-5cd9-b853-782638f70ef3 | note | REFERENCE: IFC Drawings 610.23 (f)
2d54c81d-e51e-5e61-8548-cf39794f5139 | note | – – – – – – – – – – – – – – – – –
e6ad31fa-1aa8-5544-886e-26213eae5fe0 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location.
bf1b0ac6-f61e-5df9-8397-fb6f266736fd | note | ○ Where formwork is removed prior to the completion of the curing period, curing shall recommence within half an hour.
f1f6c726-81b4-53e7-b368-6a0bffbb8311 | note | – – – – – – – – – – – – – – – – –
5a3d12ba-461f-5d3a-a834-b72fdee70ff0 | note | METHOD: Visual
7d917535-08e2-5b59-9368-f01587f9e8a1 | note | – – – – – – – – – – – – – – – – –
d8944d30-251e-52f7-a866-92af9afd821f | note | FREQUENCY: Each element
4e33f87e-b155-5f15-aaef-6bd5797cfb4a | note | – – – – – – – – – – – – – – – – –
05b148aa-821a-5b94-be3b-76e619be20a6 | note | CATEGORY: IP
d6577c29-8c7d-5606-81fc-557120bc3500 | note | – – – – – – – – – – – – – – – – –
63ad9bae-f6bc-5ac8-ab27-de270a825d8a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1463dd5d-8309-5e2a-8e82-c1d2c7a72b45 | note | – – – – – – – – – – – – – – – – –
c4a119c8-2f77-53e9-a50c-024cd4924464 | note | VERIFYING DOCUMENTS: This ITP
822cf95d-8125-53b0-afb5-274474e81a8e | date | Date Completed:
| checkpoint | 5.16 Waterstop Seals, Compressible Seals & Isolation Joints Application
4011e623-b8d0-5ede-9ab8-a46d3b3a1fce | note | REFERENCE: IFC Drawings, Product TDS
68094d91-c00a-51ac-9317-e2c877136595 | note | – – – – – – – – – – – – – – – – –
f29b64ed-0b43-5781-8ab7-5632486527ed | note | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
62003a7c-fb22-5c2d-9889-0c95a4d556c2 | note | ○ 300mm wide Bituthene placed centrally over joint. Bituthene to cover retained height of upstand and extend 100mm along top of base slab.
8bb3aab4-ea0e-5719-8b2a-4b3ccb80cd44 | note | ○ Compressible filler with backing rod to be installed on both faces
c21bee7c-6f0d-5183-8602-405bd84c7263 | note | ○ Fabric Geosheet CS15F or equivalent to be installed over retained area of upstand, and over the 300 wide granular backfill for subsurface drainage, as per IFC drawings.
69a51f0e-20c0-551a-b1b8-9255792cb0ed | note | ○ Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
545c8165-fa3f-51b4-b9e9-54933ac18860 | note | – – – – – – – – – – – – – – – – –
24fcef0f-ef72-5bb9-9dfd-5c956bdbb55b | note | METHOD: Measure, Visual
2ddf328b-4132-5294-8eed-4f48662b8c0e | note | – – – – – – – – – – – – – – – – –
762e52fa-dd89-5d24-a90b-2a80f00d5b8f | note | FREQUENCY: Where applicable, each installation location
86a38f60-2c53-5f9e-aab9-122eabc50387 | note | – – – – – – – – – – – – – – – – –
e1b2e06f-2390-593e-866f-6319aca453ac | note | CATEGORY: IP
6e1b063a-37c4-589e-998a-e2f2829b7393 | note | – – – – – – – – – – – – – – – – –
fbed0688-fdbe-5da7-b281-036cac3c264e | note | RESPONSIBILITY: Surveyor, SE/PE
81f73384-f149-53be-a32e-f429c921bde5 | note | – – – – – – – – – – – – – – – – –
bfae607c-97b5-5ab4-aefa-855dc17d1509 | note | VERIFYING DOCUMENTS: This ITP
75884dc4-a120-569f-8918-a73175eca15c | date | Date Completed:
| checkpoint | 5.17 Joint Sealant Application
91f93b9d-a075-5da8-87ec-6df43279ea03 | note | REFERENCE: IFC Drawings
4ca56165-bfa1-5c95-a42a-5efdd14aad9d | note | – – – – – – – – – – – – – – – – –
a85f5bf2-3662-5484-9fb9-7c4a8f25ec86 | note | ACCEPTANCE CRITERIA: Compressible filler with backing rod to be installed on both faces.
2886e4c7-5a10-5ac3-8b27-55c5c3aa925f | note | ○ The gap between each precast element on the retained side to have 300mm wide bituthene placed centrally over the joint. Bituthene to extend the retained height of the upstand and extend 100 along the top of the base slab
944ac60d-2cc3-51fc-b1ea-2246d29e6eb0 | note | – – – – – – – – – – – – – – – – –
1fb5e5ba-866b-51c8-9dbe-5bd1875fada1 | note | METHOD: Visual
6705e5c3-6843-5675-b83c-9e280e4811f1 | note | – – – – – – – – – – – – – – – – –
86aca170-29f7-5015-823c-e41291a25e43 | note | FREQUENCY: Where applicable, each element
cafb0324-4b94-5a2e-9e6d-73b4fe93e5e3 | note | – – – – – – – – – – – – – – – – –
3d6023ce-1b80-5231-9ce6-584c40c96b06 | note | CATEGORY: IP
6f8b0981-3237-5b7c-ae41-d8e37b34fdfc | note | – – – – – – – – – – – – – – – – –
f79b5c23-5325-5263-9558-55e70c2537db | note | RESPONSIBILITY: SE/PE
1ef7d229-b730-57ac-90fd-f596216e0fc0 | note | – – – – – – – – – – – – – – – – –
3051821c-8d57-5909-9ad5-53b12ee32921 | note | VERIFYING DOCUMENTS: This ITP
0c0b70db-a119-58bf-af8c-a219eb28410b | date | Date Completed:
| checkpoint | 5.18 Subsurface Drainage
b5f0b679-e93c-5e36-861f-f18d32d8af10 | note | REFERENCE: IFC Drawings
e9865c8a-0492-5374-95d6-5043676d5a16 | note | ○ 702.03
93d33ba0-f3c5-50c8-ba7c-9e209dd547ab | note | ○ 702.06
5ad166e0-c401-5047-bf65-6f77df156530 | note | ○ 702.07
a415c34f-c832-5e34-96d3-1651d7adae99 | note | ○ 702.09 (g)
a2249142-1b2f-5606-a31a-8a601f730a95 | note | – – – – – – – – – – – – – – – – –
cca777d9-a31c-5ca9-bdd4-71d0f74ed2da | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - 150 dia slotted subsoil drain.
57c2f8e8-f9c0-5312-ae54-cfe792fc585d | note | ○ The drainage shall be backfilled with 300mm wide No Fines Concrete in Geotextile A64 as shown on the IFC drawings. No Fines Concrete to be compacted within 1 hour of mixing
4bc6f3f6-3398-5714-b35e-bff1942aa69b | note | ○ Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
3790368c-afb6-5e99-ac5b-968548ab6fd6 | note | ○ Weep holes shall be checked for obstructions.
2f98fa20-6bee-537d-84e3-b363449f4f77 | note | – – – – – – – – – – – – – – – – –
24e18d24-a169-52cb-aff0-c52ed07f6e90 | note | METHOD: Measure, Visual
8ebb2f11-7bf4-50ba-b054-070a16cacefb | note | – – – – – – – – – – – – – – – – –
bd93e2eb-44d7-534c-84d7-44ed0fe650d2 | note | FREQUENCY: Where applicable, each installation location
16b3d4cb-9cfa-5466-9fe8-ec04763e2165 | note | – – – – – – – – – – – – – – – – –
6ae26150-1865-594d-9fbc-8bccd59eba1d | note | CATEGORY: IP
49cdcaeb-9bb1-5c06-94c8-b06ad3f2cee1 | note | – – – – – – – – – – – – – – – – –
b8a3e2ff-9d93-5c68-ab0b-a23163302bb5 | note | RESPONSIBILITY: SE/PE
9048b77c-473a-5a63-9a6b-cb7d6430e72f | note | – – – – – – – – – – – – – – – – –
28adf461-e203-5e06-8272-827f80c84741 | note | VERIFYING DOCUMENTS: This ITP
7a6e4b6e-fbf7-5869-8611-2c05756bd52c | date | Date Completed:
| checkpoint | 5.19 Flowable Grout Pour
8bbfc7b4-8f3e-58e3-9b95-4b466574fa9a | note | REFERENCE: IFC Drawings, Product TDS
7b8f1c6b-f45f-563f-9812-18b5be34025f | note | – – – – – – – – – – – – – – – – –
88168674-3285-5431-8521-e04dd4360b9c | note | ACCEPTANCE CRITERIA: Grout shall be poured in the gap between the bottom of the precast element and blinding layer below. Utilisiing shims to ensure 50mm thick of grout.
61dd96b6-e795-58aa-b996-77e7909bb5c8 | note | ○ Grout to be mixed and poured in accordance with manufacturer specification.
d0ee610b-62e6-598f-a374-a49a35939170 | note | – – – – – – – – – – – – – – – – –
3d3ce2c6-ed9d-5dd6-9235-c057d4c9ca64 | note | METHOD: Visual
507b7316-5eda-5370-85f5-d73e8e68023e | note | – – – – – – – – – – – – – – – – –
d8fe68cf-a455-5ae2-84d7-e73fce1399ae | note | FREQUENCY: Where applicable, each element
17dab380-2695-57dc-b227-43f7b48451bf | note | – – – – – – – – – – – – – – – – –
4d5a49d0-770f-5ccd-a80d-5eef3d05182c | note | CATEGORY: IP
3de61a44-4101-5ae7-9ebe-16a8486f1be7 | note | – – – – – – – – – – – – – – – – –
400bb294-d56f-532c-9891-b80c49a419ca | note | RESPONSIBILITY: SE/PE
d8345c78-7cc6-5d50-8fc1-28c26413980f | note | – – – – – – – – – – – – – – – – –
3b929a6d-fa1e-5ded-979e-d5edb78b8c63 | note | VERIFYING DOCUMENTS: This ITP
3ad32907-7b8f-5f1e-9459-f9b65a8de6ef | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Thermal Differential Monitoring
b9b0781c-7c3e-54a9-8d8e-b1fc3624c8c5 | note | REFERENCE: 610.22
1aa0f841-8218-5146-bba6-f1b00b1e1776 | note | – – – – – – – – – – – – – – – – –
4ad51ae1-029c-57da-b3df-eb8ef1541ff3 | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
b82a98b4-1b1f-5642-9e1c-e93b65d394b3 | note | Only applicable if the element has:
363e3062-dc32-5810-85ac-90da9f647e14 | note | i. the smallest sectional dimension exceeding 500mm
e07ec9f2-8656-55fd-bfea-dcaa80d962ce | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
5734558c-13fb-524f-a800-a41567fdf865 | note | Attach: Thermal Monitoring Report
32359d20-78e0-508d-b58a-e1bbc0725ef7 | note | – – – – – – – – – – – – – – – – –
cd7930c2-13f4-5cec-a6a9-ae2bd174e6f4 | note | METHOD: Document Review
c5a958a0-63f2-52ca-acfb-d6f9f819b965 | note | – – – – – – – – – – – – – – – – –
479da34e-ee00-57bb-9529-b7eb5d598f79 | note | FREQUENCY: Where applicable, each element
71d80e76-8dfe-5f5a-9551-b8d522287a33 | note | – – – – – – – – – – – – – – – – –
430e5524-c2e6-512d-bf60-85df2c8c5f28 | note | CATEGORY: IP
2469597f-10ea-5a80-8507-aae53e250630 | note | – – – – – – – – – – – – – – – – –
41ef1013-f416-5e08-8d68-b29d720a86cb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8f935a23-4f1c-5f3d-871b-bba264be0b26 | note | – – – – – – – – – – – – – – – – –
2fa6cff1-b455-5d0e-9c45-23e725ca9a58 | note | VERIFYING DOCUMENTS: This ITP
0a10c5bb-e86d-513c-a6b3-58acb39a6b7e | date | Date Completed:
| checkpoint | 6.2 Removal of Formwork
0bd34715-571b-568f-8df1-8d2d5a5f195a | note | REFERENCE: 610.25
afe78fdc-e6c9-5de1-aa59-c2109e740dd0 | note | – – – – – – – – – – – – – – – – –
0960af81-9bbd-5629-9c85-27744dce3376 | note | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in Table 610.251 have elapsed, after completion of the placing of concrete.
07a1f1bd-5e22-5670-b99f-96b3075b9e80 | note | – – – – – – – – – – – – – – – – –
391232c4-42a5-5815-9011-8ef124c0b25a | note | METHOD: Document Review
65ab8454-40ec-57b5-b2cd-1319758ae773 | note | – – – – – – – – – – – – – – – – –
3f09697d-214f-5d90-936e-a6cd9b357ace | note | FREQUENCY: Where applicable, each element
7e23c34e-942f-58ad-8595-61c2fa0b1226 | note | – – – – – – – – – – – – – – – – –
1cf9480a-aba9-5e52-bc02-87f8f1566b2d | note | CATEGORY: IP
caea5927-9c16-5ad7-93e7-f83b6bf8b417 | note | – – – – – – – – – – – – – – – – –
c3c3d4ea-b8ef-500f-828c-e8f9531fe7b8 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
0c793abd-559f-51bc-86b0-f9d92176b340 | note | – – – – – – – – – – – – – – – – –
cdb496d6-6c74-54ae-82cd-b2386f999c1a | note | VERIFYING DOCUMENTS: This ITP
1e0af366-9f2d-588c-8065-5aae14db0ca1 | date | Date Completed:
| checkpoint | 6.3 Surface Inspection - Cracks
fc2105c4-8d83-50e9-a27d-58563507d004 | note | REFERENCE: 610.24
fcdf1d15-2059-53a8-9b75-9cb0918c47ba | note | – – – – – – – – – – – – – – – – –
1e0d44bc-379b-567d-abee-95306496ce14 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
98d881b9-043f-5751-8090-c094fca16d7d | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
50ba5e51-b74b-5aaf-8259-2da197c268b7 | note | – – – – – – – – – – – – – – – – –
e9857000-4b0f-5f5e-934c-4bde5a210b9a | note | METHOD: Visual, Measure
88d4d8d0-abf7-5210-8a3c-8224d8c5282d | note | – – – – – – – – – – – – – – – – –
51a01dc7-6a58-5356-b60c-8de2b1524f54 | note | FREQUENCY: Each element
ad2d67cc-d2d2-55c4-b9b5-65cd59c3499c | note | – – – – – – – – – – – – – – – – –
e7d129aa-c88a-5952-91f8-473046267ed6 | note | CATEGORY: IP
13cd128c-d754-5a66-bd2e-bae5c15d2dff | note | – – – – – – – – – – – – – – – – –
638bdfd4-6603-5380-82e1-afc14f885274 | note | RESPONSIBILITY: SE/PE/SPE
1b48c01e-7a9c-52d6-a1fc-cd27fcae90fe | note | – – – – – – – – – – – – – – – – –
a86566c7-cdc3-5a4c-8bb8-886f2fbef86f | note | VERIFYING DOCUMENTS: This ITP
856dec70-b7a2-5b04-bf3e-13ada2645ff7 | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Surface Finish
98213ed3-12b3-55b8-bef5-3a0a674bdc67 | note | REFERENCE: IFC Drawings
3e75b276-51ac-537a-a71f-d1f888893ed8 | note | ○ 610.31 (a) - (n)
a289b46a-f68c-5c68-b141-5546dd68e35b | note | ○ 610.32
447528f9-bd20-5867-a661-7a40ae8037b7 | note | – – – – – – – – – – – – – – – – –
a0605beb-eeb9-5017-bc4b-8851cedc6bc5 | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
3e8efd95-9adb-5caf-b8b5-f2840eeb7d8b | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
7f9e0bf9-6f32-5f29-bf18-883309d20483 | note | – – – – – – – – – – – – – – – – –
948d1322-d777-5252-af97-933519f84db1 | note | METHOD: Visual
4ce4f805-e95d-5ecd-b46d-7c40fdb4010b | note | – – – – – – – – – – – – – – – – –
4c43e642-9276-5860-8e3e-a57f921f4ca1 | note | FREQUENCY: Each element
3df3a7d4-0ea2-5c1f-aeb0-f407da79c483 | note | – – – – – – – – – – – – – – – – –
5b6fc3a0-6b59-5c51-8a44-2372f32163a6 | note | CATEGORY: IP
e489af52-5936-50c9-806e-919f3fecc0af | note | – – – – – – – – – – – – – – – – –
cbb8eca6-9d9e-5442-8ad2-8eaf0f1edb54 | note | RESPONSIBILITY: SE/PE/SPE
4ec467eb-b6ff-5f14-9bb3-9febeb608362 | note | – – – – – – – – – – – – – – – – –
a5c797d5-6250-5e46-b926-6752cfca12cd | note | VERIFYING DOCUMENTS: This ITP
c146df03-d84c-5103-a85b-94f687186796 | date | Date Completed:
| checkpoint | 6.5 Measurement of Concrete Cover
498712c2-1a9c-5fa9-9943-6fe20153b831 | note | REFERENCE: 610.34
bab5c9ed-4964-5d41-9ec9-edad1f04057a | note | – – – – – – – – – – – – – – – – –
79205036-db4c-53ba-bbb9-02c65bb09b73 | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
2793dd5b-69c1-53c3-b931-cab95a0020ac | note | ○ Minimum 10 no. measurements recorded in each area.
867efd26-5ff1-5eb2-b8a6-7f4df97763cc | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
86ec90ed-e077-5a1e-89d9-58c7dc9b02fd | note | Attach: Covermeter Check Record
ad0e4b6c-249e-52d4-aadf-8ee003651461 | note | – – – – – – – – – – – – – – – – –
50227c7c-cda3-5aa8-9953-4bebfaf293ea | note | METHOD: Measure
49afa996-ce58-5197-bea8-36cd4daba435 | note | – – – – – – – – – – – – – – – – –
2910e332-4dc4-5b82-a56f-e0640acf8e09 | note | FREQUENCY: Each element
e01e2ee9-2110-5b63-ae5d-48bf248bf036 | note | – – – – – – – – – – – – – – – – –
089e3198-d718-5703-90b0-93ce2c877c7c | note | CATEGORY: IP
f347f6fc-30f8-5eb2-8a35-a960233c6b59 | note | – – – – – – – – – – – – – – – – –
d12b087b-36bc-573c-a0e1-1f0a79da80a2 | note | RESPONSIBILITY: SE/PE/SPE
0677026f-80c0-599b-827a-0e1729c2ee7f | note | – – – – – – – – – – – – – – – – –
34cbe3d2-1c20-5fdb-ae0f-91efc8a2b0ae | note | VERIFYING DOCUMENTS: This ITP
0f1691dc-0ac7-5eae-bee1-78e0f95125dc | date | Date Completed:
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
2e9c73f3-8fd5-5694-ae7b-2fc04445f06e | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
b21de803-f193-5cb6-ba0a-314ad6e9b79b | note | – – – – – – – – – – – – – – – – –
8bc828ca-be94-5c31-9db4-d237b6592b7b | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
2c4695fb-fd98-5298-b21f-fba97596bcda | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
f145c3d3-4ce0-59a9-b3fd-2b66c6338630 | note | Attach: Concrete Test Results or Maturity Test Results
7b7c54bf-01b1-562f-8469-9efbce545f49 | note | – – – – – – – – – – – – – – – – –
55784106-731f-525d-bc5c-9a7cd395dbfd | note | METHOD: Document Review
028919d7-e802-5197-9406-48b891a25bab | note | – – – – – – – – – – – – – – – – –
bac7a7d7-000a-5bb9-8d54-5e9fc611649e | note | FREQUENCY: Where applicable, each substructure element
815abe7a-4414-5067-aa2b-36b71b09eb32 | note | – – – – – – – – – – – – – – – – –
8f3ac53b-a19e-5ecd-8f95-9b3905438e91 | note | CATEGORY: SP
a6fdfbcc-d363-588c-87a4-3c4c5f022b82 | note | – – – – – – – – – – – – – – – – –
40122d3c-e554-581a-be78-daaba0985446 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
86419d54-7b58-5a91-8b71-a5836178fd87 | note | – – – – – – – – – – – – – – – – –
63f6b4d2-2eac-57ca-aaaf-97dae7a633ae | note | VERIFYING DOCUMENTS: This ITP
d420f20c-e9cb-5ef9-9c12-2bd71d64f4a7 | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
6e483f42-0ef9-50bb-af43-dba6252e36cd | note | REFERENCE: IFC Drawings
3756cb43-2594-54d6-a473-3bea8262d595 | note | ○ Table 610.05.051
10a86698-6673-51d9-9e39-a88cd84c64c5 | note | ○ 610.16 (g)
59be7bbf-633b-51f6-a89f-aaba304eed63 | note | – – – – – – – – – – – – – – – – –
07189b29-f4a3-508a-9d91-fc9525226a77 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
579ec305-9b49-51a3-b22b-1ba4a9251b46 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
62ba125b-949c-5e33-aa9e-b42b6e61ea79 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
80f106dd-c817-5ab2-a809-682f2070487f | note | Attach: Compressive Strength Test Results
810d0ffc-98fd-5139-860b-4ff3e3f7f998 | note | – – – – – – – – – – – – – – – – –
cf34d2f9-46c7-5ed5-a01f-8fc358df9553 | note | METHOD: Document Review
7f2fa9f3-c058-576a-943d-632be0242179 | note | – – – – – – – – – – – – – – – – –
42386edf-552a-53d8-a3b9-c33f6ac3796f | note | FREQUENCY: Each cylinder
55668db4-3d4a-5c24-b7e2-17f6e81e81fa | note | – – – – – – – – – – – – – – – – –
4515877a-6aad-5440-b606-836f88df0989 | note | CATEGORY: IP
295a3a44-b3f7-5d31-a981-8025dd945adc | note | – – – – – – – – – – – – – – – – –
7349e627-e966-5300-980a-2060b2503899 | note | RESPONSIBILITY: SE/PE/SPE
cd78b4ac-aa62-59e0-8a85-4695aff5900b | note | – – – – – – – – – – – – – – – – –
1f5ecd12-5599-5607-a580-5d674b55e8fc | note | VERIFYING DOCUMENTS: This ITP
6c06da7e-b8ac-5040-8fdf-54961dc47244 | date | Date Completed:
| checkpoint | 6.8 As-built Survey
dbfaa57a-a6bb-5dca-b209-df0fa1eee902 | note | REFERENCE: IFC Drawings 620.09
19c86cab-58f8-510a-9591-38847802f188 | note | – – – – – – – – – – – – – – – – –
200c9179-f0b4-5e50-94aa-c3a6d50f9262 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
583f0ecc-9219-52ed-9cf6-901135884d3a | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
af8ecafd-a9f4-5c6e-b3b3-547cf01c1456 | note | Attach: Survey As-builts / Survey Report
fa47cada-296d-57d0-8c23-ad0e2e48c1db | note | – – – – – – – – – – – – – – – – –
d7908e1c-a940-54c9-aca0-86deb80432ce | note | METHOD: Measure, Visual
de3c4e56-35c8-5436-afa0-c02898e33ef5 | note | – – – – – – – – – – – – – – – – –
508c4772-75d3-5e75-b06f-a2174f8ef7d8 | note | FREQUENCY: Each element
23c69fd9-3c38-5062-baff-600ecb1e1353 | note | – – – – – – – – – – – – – – – – –
e4a66620-e799-53cc-9865-a7f413737345 | note | CATEGORY: HP*
347cd559-602f-5291-b208-108bd8b82fa2 | note | – – – – – – – – – – – – – – – – –
732d3ba5-8c6b-5c8a-9fb9-e56c491e010e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
3b516b8a-a105-526e-ab7b-43749085d7d4 | note | – – – – – – – – – – – – – – – – –
b4b27c61-6086-5488-99a9-c5a129506507 | note | VERIFYING DOCUMENTS: This ITP
1c65da34-6970-51aa-b68d-2c672442ea2a | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
f71aff9f-2235-54d4-8da5-4abd1ed20ab8 | note | REFERENCE: MRPA Quality Management Plan
ab07e576-a29f-54f8-b3f7-00757f055125 | note | – – – – – – – – – – – – – – – – –
898be3ee-6373-5fa1-9d02-22856ae9391d | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
782088b9-6ee3-5aed-9458-5fc24107b229 | note | – – – – – – – – – – – – – – – – –
37867d3d-db44-532f-ba60-acae1516b372 | note | METHOD: Document Review
bc6c99b0-001a-5c52-a7f5-c415438dcda6 | note | – – – – – – – – – – – – – – – – –
4d9b337b-a834-542b-890c-a0042ad05620 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
629f2603-65b8-5af2-bd96-6c925f9d8113 | note | – – – – – – – – – – – – – – – – –
1dce5cb8-aae4-5e96-9250-56e81c13019c | note | CATEGORY: HP*
10ff8b45-2e31-5ea0-8943-f797f639e364 | note | – – – – – – – – – – – – – – – – –
77db68a3-8a62-5935-8842-4779795733b5 | note | RESPONSIBILITY: SE/PE/SPE
fbd481f9-b591-5f23-bde4-a866be2d6e23 | note | – – – – – – – – – – – – – – – – –
7b18cf1f-4b0b-5686-b15b-8c91ed4f06b5 | note | VERIFYING DOCUMENTS: This ITP
d92b7053-7b2c-536a-a8a0-960952f79f45 | date | Date Completed:
| checkpoint | Final Inspection
4b2e6bac-1061-56eb-b3e0-58a5ef1d46b0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c0824d75-70c5-502f-aeb5-29e6fa085b43 | textbox | Name:
2481499e-2116-5748-b0c9-0d7bc11f6229 | textbox | Position:
a460b5f6-cec2-5543-86f2-48b07b96f7f8 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-182-STR-SSB-Concrete Coating-Protective and Decorative Rev 0 | itp | ITP-182-STR-SSB-Concrete Coating-Protective and Decorative | b980e347-4083-40a0-80b2-c8548d1b7398
| section | Referenced Documentation
| checkpoint | Referenced Documentation
1212c2be-cec5-54d8-86f7-c6afbfcefee0 | note | Document Title: ITP-182-STR-SSB-Concrete Coatings (Protective &/or Decorative)
ef8dec4b-3420-5bd5-b964-5ad55e504945 | note | ITP Description: SSB-Concrete Coatings (Protective &/or Decorative)
8d921958-8fb4-5e31-aa82-856b5e3f2f76 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
39a9ea96-68e7-58c2-976f-88fa6e01146f | note | Discipline (e.g. CIV/STR/RAIL): 182-STR
07ab895f-b7ae-5b89-b61b-420f39157fa4 | note | Revision Number: 0
52122b83-4f85-53ba-9190-2ce9ec395a22 | note | Revision Date: 14/04/2021
fa10bec2-6a12-5f52-a48c-f3510809fc46 | note | ITP created by: Mike Freeman
16f0ec1f-32ec-5cef-a081-c8504d6f9836 | note | ITP approved for use by: Mike Freeman
105f0543-35b9-5584-98aa-c05cd1c886a5 | note | 1.1 Non Dependent
7eb3a8ab-7803-5089-a300-ab5976c0ed5f | note | Reference: VicRoads Section 685 November 2018
1a74bb7e-12be-5471-b3ad-612d7c4f2b0f | note | 1.2 Non Dependent
76e2358c-8bad-5334-bf9f-7800ffa118a9 | note | Reference: VicRoads Section 686 November 2018
| section | Preliminaries
| checkpoint | 2.1 Anti-graffiti System Selection
620a949e-1c33-582e-a3f8-9acbceaade9a | note | REFERENCE: IFC Drawings
b0060d46-84aa-5a07-a8ae-92e54265f67a | note | ○ Coating System TDS
41d5a86a-4a4b-55d8-8114-213e388d3e5f | note | ○ Surface Cleaner TDS
e277912e-849d-5d8f-a924-3c408ef20fc9 | note | ○ 685.04
597f015e-29b8-54aa-ae59-66833f1c5c37 | note | ○ 685.06 (a) & (b)
336f1b67-fe37-55e1-ad3a-86bebbd4ede6 | note | ○ 686.04
e671535e-d82e-5ea6-97b3-5a1af760102d | note | ○ 686.05 (a) & (e)
f0a7ea6a-d0db-5a8c-9f2e-00e672c0be52 | note | – – – – – – – – – – – – – – – – –
60be121d-af04-59bd-a141-c09e63ad65ec | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
dc1218c1-ce00-5f78-991a-3d9cc285c7d4 | note | i. be either a film-forming or a penetrant system
b01ffbe9-4823-5ce7-9cea-65f1e8426339 | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
a2f57ecd-bbd8-5af5-8559-df620ba9d679 | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
911963de-81d8-511d-bcb4-3895db79a3e7 | note | iv. be non-yellowing, colour-fast and not subject to fading
20e32ae7-e607-5d06-b09b-33ec6785fb00 | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
83c3c32d-6466-5329-becb-b5e3f29cfba3 | note | vi. application thicknesses (film-forming):
0cbfe555-67cc-5e58-b101-a53a9752054e | note | – WFT total = 175µm min. OR
0378864a-e995-52a5-8adf-f958ae03439e | note | – WTF per coat = 88µm min.
8613b7e8-f1bc-5042-b7a7-2894477d8085 | note | – DFT total = 100µm min.
9574b32a-dcdc-5e41-b9f9-3a9b5857c4bf | note | vii. adhesion to substrate (film-forming):
2b5bd007-e34f-5a06-a03e-467d447d1c3a | note | – 0.75MPa min.
313b7069-279d-569e-ad05-7ad9b3903891 | note | viii. application rate (penetrants)
78389982-4d6b-5e09-a514-3b31dedd5c0e | note | – as per the minimum thickness on the manufacturer's TDS
dec32fe9-b378-5f12-9d05-867f37f7615b | textbox | Enter: Teambinder Material Approval number
c723a6db-be4e-5f55-a970-ea20681b88dc | note | – – – – – – – – – – – – – – – – –
037deace-3a3f-5677-a786-d282ad785c2e | note | METHOD: Document Review
ede55729-8aaa-53a4-9a16-3524867bef35 | note | – – – – – – – – – – – – – – – – –
431b751b-85f2-55df-800a-a84b19f93b9b | note | FREQUENCY: Once, for each coating system, 14 days prior to application
9889449d-e8b8-5018-9936-e4173e83b8aa | note | – – – – – – – – – – – – – – – – –
7fd6965b-5ec5-5690-9692-2d7392ce2cd6 | note | CATEGORY: HP
69bfc2cc-26ca-50ea-a4d5-ef32f81963bb | note | – – – – – – – – – – – – – – – – –
756b2e7c-3e73-58de-a479-81b59900e109 | note | RESPONSIBILITY: Nominated Authority
217b9b98-6b5a-5461-bdc7-7f6d4372795a | note | – – – – – – – – – – – – – – – – –
586131ce-1e5b-5625-b1d4-09b4f2206fea | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
1a8153a6-4ef4-505f-969e-09f96ea10570 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Decorative & Anti-carbonation System Selection
3f376b1e-21f3-5096-bc3c-1f06f1e983f8 | note | REFERENCE: IFC Drawings
39b6903c-f72c-5605-820a-1c685f5cff13 | note | ○ Coating System TDS
eaecea66-edfd-5c1e-a60f-505125aad886 | note | ○ Surface Cleaner TDS
e6738555-cd82-5545-9945-33c7050d6938 | note | ○ 686.04
48304aff-569f-5c6d-a99c-67b9adce9f2e | note | ○ 686.05 (a) & (b)
35ce4883-9a82-58ce-aa48-8f490be5ed68 | note | ○ Table 686.051
5ca3d413-558b-58e0-ab19-1ccfe9960a3c | note | – – – – – – – – – – – – – – – – –
d5c56816-461d-58a4-b449-deec6b554c9c | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
21e93590-3a1f-5eae-9451-015f0de47289 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
73a1b915-732b-5f44-b419-3a5996a9947e | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
f48e0618-66a2-511c-bf46-b5ad5244ff37 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
7262d87f-aa5e-5e15-beef-90dc97221483 | note | iv. be non-yellowing, colour-fast and not subject to fading
aaff81d7-3d10-55b6-bff1-22d65679bda4 | note | v. be guaranteed to last for 10 years of outdoor exposure
31cc017d-09df-5a6f-83e2-edf216ffabab | note | vi. application thicknesses:
8b09875c-5595-5132-8e6b-9b0387a0dd94 | note | – WFT per coat = enough to achieve the total DFT
621aa563-2364-5e59-9531-6bf42a3abc7a | note | – DFT total = 150µm min.
74a6a525-7fd9-587d-8fdc-2e8e6c347f89 | note | vii. adhesion to substrate:
7a439d58-9534-5334-9a5a-967c293885ce | note | – 0.75MPa min.
5aa6c488-d6c0-553f-9108-1bc8aeddcce0 | note | viii. able to bridge cracks up to 0.3mm wide
2d7da49f-9866-55f9-b053-02f4077d88c2 | note | ix. able to be re-coated within 24 hours
6608b160-021e-538d-a218-214428b37438 | note | x. have a minimum pot life of 1 hour
fb11c8b0-5b02-5098-8d21-73b49ead3ac8 | note | xi. compatibility to an alkaline surface
e57dd3e0-218a-5054-93de-be075b5e41a5 | note | xii. equivalent air thickness >150m
671d9762-a46e-5f79-aaba-af5dc1a9fcd6 | note | xiii. equivalent concrete thickness >450mm
823da641-acb3-5778-adbc-7ee5486a2acc | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
c521fb0b-5b04-58b8-b0d3-8c019581b465 | note | xv. Water vapour equivalent air layer <4m
06a52d8c-0be1-5dad-bc01-f3774cf27248 | textbox | Enter: Teambinder Material Approval number
71b7eccc-8c86-5ec7-90b0-ed1d8b652269 | note | – – – – – – – – – – – – – – – – –
9333981b-6f83-517a-b7d5-1236c034b2fa | note | METHOD: Document Review
e095f189-ee42-504b-8a16-71be3ca8ffdf | note | – – – – – – – – – – – – – – – – –
9d8bcd19-daf1-5975-aee4-f60934415f7d | note | FREQUENCY: Once, for each coating system, 21 days prior to application
7deab5fd-aba6-58e0-a054-439b9c8b225f | note | – – – – – – – – – – – – – – – – –
40cd80f7-5b85-5e67-9f7e-e4ea2299240e | note | CATEGORY: HP
509b697f-44d2-50a3-a669-2b3d510ba95d | note | – – – – – – – – – – – – – – – – –
67f3e070-64e5-5e33-b925-4cde3c168a27 | note | RESPONSIBILITY: Nominated Authority
2f8e6f08-95fe-5747-9738-4ab726933852 | note | – – – – – – – – – – – – – – – – –
7f9cecf2-fe70-508b-acc8-5f98dd3fd5c9 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
8f5ca17e-518a-5245-897c-bc6224727e0b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
237d8859-7587-55e8-993f-bd08460f6398 | note | REFERENCE: IFC Drawings
b801caee-c965-5d8a-a0b2-94fdeb1f1a46 | note | ○ Coating System TDS
4da4a86f-add2-57a4-9f90-fcc492ad223d | note | ○ Surface Cleaner TDS
70c25957-8a1a-578a-a5d9-7b61b8b23bdf | note | ○ 685.04
e1a77846-817d-55c5-88e8-c160831c0143 | note | ○ 685.06 (a) & (b)
9160048e-778a-508f-b627-5123359dbbc7 | note | ○ 686.04
4bfa7fd4-463e-599b-82c8-39f888147a84 | note | ○ 686.05 (a) & (b)
a5ea90fe-ed17-5042-862c-aaee9552f5e5 | note | ○ Table 686.051
6ee8f85f-ea52-5d04-95ba-744a877fc435 | note | – – – – – – – – – – – – – – – – –
8a125301-4ebb-5e7a-8ddf-b4cd8bdfc407 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
5a253cf6-819a-5d79-92b5-73f96c20a3f8 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
39011455-7f8c-5862-b168-3121b30cf6ef | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
5967dd49-b8c7-5c6e-95f2-c3f2e3a5314a | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
a5fb7232-3bc2-511a-9e0a-94825f34ea39 | note | iv. be non-yellowing, colour-fast and not subject to fading
18f0eadf-14e8-5477-8c05-70ccda692f4e | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
fe3b129f-498f-5296-805b-ed69cfbc8bfe | note | vi. application thicknesses:
4d50c5d5-177e-54fa-a314-5c1580f3cef3 | note | – WFT per coat = enough to achieve the total DFT
0c6d5f1d-c565-5ed5-99e6-51f87fbe2979 | note | – DFT total = 150µm min.
2334c526-545b-53e7-8555-9dea5ced2936 | note | vii. adhesion to substrate:
d9ee07eb-9fb8-50fe-9858-ceed3128caf5 | note | – 0.75MPa min.
6f1f3e9f-461f-5161-8157-eed945db0a76 | note | viii. able to bridge cracks up to 0.3mm wide
02b80fa0-170e-55ff-b8ad-e3dca6695bfc | note | ix. able to be re-coated within 24 hours
0bbefa15-fbb2-5704-a853-236c836ec161 | note | x. have a minimum pot life of 1 hour
24bec4d0-e749-56b0-9070-fb5146495d05 | note | xi. compatibility to an alkaline surface
3485e28b-6d8b-510e-badc-00aa3e1d54fc | note | xii. equivalent air thickness >150m
8123f4c9-9f91-511c-8d21-8d599c431204 | note | xiii. equivalent concrete thickness >450mm
8b42723b-2bda-5571-8edf-69b3b0b4c1ae | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
7d7ce331-d608-5084-8925-3edc9fe5b0e1 | note | xv. Water vapour equivalent air layer <4m
e5ea4667-f02a-5194-8cc9-e14df52c9ab5 | textbox | Enter: Teambinder Material Approval number
894d9c58-9c74-5091-95c5-e59b9d7c66d8 | note | – – – – – – – – – – – – – – – – –
5f66161b-a9d8-57e2-bba2-f7249d9a778e | note | METHOD: Document Review
641c037f-61ca-5cd4-9841-be1516d4936e | note | – – – – – – – – – – – – – – – – –
295f4ca8-0b1d-577d-b951-8d5bac5cd4f7 | note | FREQUENCY: Once, for each coating system, 21 days prior to application
d7494d25-04ad-5058-b182-f86f0335cc6c | note | – – – – – – – – – – – – – – – – –
6a3fb801-b401-55ec-befd-8022d56953f8 | note | CATEGORY: HP
a6c3446b-4934-572f-ac75-9dcf5c261651 | note | – – – – – – – – – – – – – – – – –
f52bb165-b964-5e65-83e3-8e0700899a37 | note | RESPONSIBILITY: Nominated Authority
990d2d6d-7bf9-57df-8faf-f56b37bed23e | note | – – – – – – – – – – – – – – – – –
a19faed0-9e0f-5c4f-8833-2f056fa28950 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
80a861d9-4467-5b8f-9f09-90893b42a9d3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
8dcfedfb-7239-5a0c-98ed-6dc04b70cbbc | note | REFERENCE: IFC Drawings
c8d4b656-1b88-5dc1-bda6-234c46971836 | note | ○ Coating System TDS
d39bb6a7-5587-5e18-8530-821038558eae | note | ○ Surface Cleaner TDS
8e6160be-afb5-5c61-b9f3-233650ad987f | note | ○ 685.04
341f180c-26ab-5d80-9b90-2417684df4ae | note | ○ 685.06 (a) & (b)
77136563-37e5-5fb4-a0d6-dbadaa66b62f | note | ○ 686.04
69dec685-fbbc-500b-8cff-b6d6609d2474 | note | ○ 686.05 (a) & (b)
154be932-d0de-50de-826c-a3203bd5a818 | note | ○ Table 686.051
d498e4ac-f189-502c-b6ab-eca3bab28715 | note | ○ 686.05 (c) (i) & (iii)
d270ad7b-3699-5785-ab85-c611c6d13f31 | note | – – – – – – – – – – – – – – – – –
54a4b95e-07ba-5631-b16a-6d79ed99e889 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
fc33c903-6381-51d9-a3fe-8aceb29eb224 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
328667e6-d58e-5e48-a3af-44afd937953a | note | ii. all coats to be compatible with each other
4c8a3578-5568-5c37-9e47-635480efe46b | note | Penetrants:
c8e4c548-01a4-555a-be37-468d0e7cbab5 | note | iii. active ingredients:
5c344642-a558-535d-9b13-ee19f6ceba10 | note | – Silane = at least 95%
50edb2bb-de48-5da6-8601-7b8dbebee9aa | note | – Solid silane & silane cream = at least 80%
725573cb-53cc-5e2d-9baf-e7e140cc514b | note | – Silane-siloxane & siloxane = not specified
52ca68dc-2d67-50d1-bcdb-42125657a45a | note | iv. application rates:
bd43a72c-8892-52ce-92a2-daee8aea9932 | note | – Silane = 2 applications of 0.3L/m² min.
84814423-d4fe-5569-b316-192f42d658a4 | note | – Solid silane & silane cream = 1 application of 0.4L/m² min.
db49e10b-49e8-5a9c-a558-9863ca0b345c | note | – Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
31ae8df5-c105-5156-9f74-42b043dfbe87 | note | Film-forming coat:
535e2c2e-5f65-562d-9cd0-a3e6e598669a | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
0282a5ab-60a4-5b72-a3a3-24fead636c4a | note | vi. to be water or acrylic based, solvent-free
c94db668-005e-5b63-af9e-77353865da77 | note | vii. to be non-yellowing, colour-fast and not subject to fading
52c035d9-c3b9-57c4-8599-9d3ebc171d5a | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
b9ea04d3-a7df-59e3-8c26-7034c80a3fae | note | ix. application thicknesses:
9e38a2ac-a3f0-5803-9740-9d7541fc499a | note | – WFT per coat = enough to achieve the total DFT
b9778fad-c851-53a6-b6a2-2d314d680579 | note | – DFT total = 200µm min.
1846e364-8650-51ce-9969-d7af374435e0 | note | x. adhesion to substrate:
b7aa626e-7256-5035-9e58-6371eaa32a1f | note | – 0.75MPa min.
ab07c1e5-ba64-5c62-935d-5bbaba3771bd | note | xi. able to bridge cracks up to 0.3mm wide
b9795a70-1657-5a75-afef-148ab6ab8389 | note | xii. able to be re-coated within 24 hours
5fa1f262-6d7c-5390-9cbb-ebb0a0b0ad37 | note | xiii. have a minimum pot life of 1 hour
f3735bc3-4d44-5b82-a397-160d81e542ba | note | xiv. compatibility to an alkaline surface
e54a4e30-8c72-5b4c-8615-728c46bc08b7 | note | xv. equivalent air thickness >150m
c7d35f79-0b93-5b57-a051-508586ce4ea0 | note | xvi. equivalent concrete thickness >450mm
b199f607-9b47-59ba-8d53-6fd2b3124999 | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
aa5b2211-0423-5c44-a447-3dfdccfb218a | note | xviii. Water vapour equivalent air layer <4m
4fb201a2-a5f7-5684-8072-0bfdbd3b27a0 | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
fe02c9fd-f85b-5511-9efd-c6751c51a99d | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
5a3cb3e1-2cde-5480-ac4f-79d04cf9e0ec | textbox | Enter: Teambinder Material Approval number
1d27f636-94c8-5f77-b052-5bf0c7e1837a | note | – – – – – – – – – – – – – – – – –
cd132283-380f-5676-8647-9d8c3b0877ed | note | METHOD: Document Review
08c2daca-326d-5d19-a36a-ab875d1cdfe4 | note | – – – – – – – – – – – – – – – – –
102d2644-7eaf-58c9-956a-32ad93610e0d | note | FREQUENCY: Once, for each coating system, 21 days prior to application
161086d6-9b60-58a1-8bfd-854883cbdc38 | note | – – – – – – – – – – – – – – – – –
39a98b5a-47c0-5b10-b9d7-9e1431b56b20 | note | CATEGORY: HP
7bc8e883-1570-5792-8c9b-05dfe559ad9b | note | – – – – – – – – – – – – – – – – –
2e9ae246-60c9-5659-8ee9-2e41f6801ce1 | note | RESPONSIBILITY: Nominated Authority
bb75e70b-d40c-5f60-b521-2563ce8ba3c4 | note | – – – – – – – – – – – – – – – – –
87f39407-57db-5b8c-8467-fbb444425b6f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
2e19890d-9c6f-5ad7-8349-e3a18c157b85 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Work Procedures
5a90bfbd-30bf-5045-bb2c-662e35983887 | note | REFERENCE: 685.05, 686.04
0b37790a-af34-5dd3-8dc2-aa412fe18138 | note | – – – – – – – – – – – – – – – – –
3905a0b8-0397-5b3f-b5f8-ce0353554cae | note | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
f82c91f6-ad79-5650-8939-d643937f5233 | textbox | Enter: Teambinder Hold Point number
e668b7cf-46f2-5fec-8bf6-d35dde7f6aeb | note | – – – – – – – – – – – – – – – – –
d060a61b-b0fc-5d9e-adef-3c9c75dd3c3a | note | METHOD: Document Review
df363b29-a92c-5410-b4a1-17a97aaad15b | note | – – – – – – – – – – – – – – – – –
6dc59e71-f73e-5592-b0db-184ed47c5e39 | note | FREQUENCY: Once, for each coating system, 21 days prior to application
8583b423-4d87-5afb-baf7-895a829cfd43 | note | – – – – – – – – – – – – – – – – –
39713a5d-4793-54dd-ac25-fb117cc2e4f0 | note | CATEGORY: HP
ae0e0620-500f-52e4-bf58-cea64cdf345c | note | – – – – – – – – – – – – – – – – –
637d0abc-cf15-5716-abce-3b56d00115b6 | note | RESPONSIBILITY: Nominated Authority
3ed0ff34-6f6b-5c34-9e17-d747008e20c2 | note | – – – – – – – – – – – – – – – – –
a71988eb-744d-5e64-8611-43ee94e24300 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e4e90004-6cb6-5ace-8198-cc5b3e819c27 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 Coating Personnel & Equipment
c2764338-ce3e-5899-8844-7e42049e7277 | note | REFERENCE: Coating System TDS
48bd6958-99f1-513e-869d-1019f154ad0a | note | ○ Surface Cleaner TDS
019ff713-ab2a-53ff-bf34-099b3cdf8c55 | note | ○ 685.16
dae832ce-e60a-5b4c-87a7-02210a528aba | note | ○ 686.18
3016f0c1-6574-5a18-8c4d-0ad9218f8feb | note | – – – – – – – – – – – – – – – – –
2916c261-3c4b-5ae1-bdfd-b3eeac3fbcb9 | note | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
6bf1ddac-d2fe-55f7-bc23-442782aa8c71 | note | ○ Application personnel require 2 years minimum experience.
bafc5b80-a3f2-5ac0-9bfc-7a283839d879 | note | ○ The supervisor shall remain present at all times.
338100a7-cd7d-5b40-a3a2-d47fb677840f | note | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
450e1504-244c-5fce-bd7d-0d12c7e005b4 | note | – – – – – – – – – – – – – – – – –
5074584d-dd33-52c1-8919-b197a2055c5e | note | METHOD: Document Review
b6af3615-a71b-51df-80d8-35e43ab10612 | note | – – – – – – – – – – – – – – – – –
67bf9bed-5823-5902-81b8-dec5b59c7062 | note | FREQUENCY: Once, prior to application.
770d4367-05cf-5ae9-b1d1-d8751e317e86 | note | – – – – – – – – – – – – – – – – –
99d7e132-f03b-552b-97dc-29009b80df8b | note | CATEGORY: IP
1a81e2db-de97-50c2-b2c6-b50ba097c8ad | note | – – – – – – – – – – – – – – – – –
d30b9468-4b03-510c-ae52-41d6815759d0 | note | RESPONSIBILITY: SE/PE/SPE
265b6f31-91e5-5b92-b783-c57e9df1b861 | note | – – – – – – – – – – – – – – – – –
7cecead3-f842-5eab-82f0-cd422f406838 | note | VERIFYING DOCUMENTS: This ITP
1f7061d1-0bcd-5fb2-b1ec-76f5e211851a | date | Date Completed:
| checkpoint | 2.7 Protection of Adjacent Works & Property
e19d725a-414a-5c9f-97ed-448f2efd6a58 | note | REFERENCE: 685.17, 686.10
f1ce35c8-8c88-5a80-a5de-21732bce5dc3 | note | – – – – – – – – – – – – – – – – –
ebb1493f-efd0-5979-8b30-5eaadbcb6c58 | note | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
6156f258-81db-5606-a569-0718e0055847 | note | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
442e301d-dfbc-5cfb-873f-e6a8912125ed | note | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
6e705581-ae00-5af6-aa99-fc92730caae1 | note | – – – – – – – – – – – – – – – – –
251df005-4ccb-5977-9e5e-ab9256ecf5ec | note | METHOD: Visual, Document Review
bcc64640-5fcd-5fb9-95e0-f6582ec236f8 | note | – – – – – – – – – – – – – – – – –
4a048b04-4a33-50d5-a808-6e2a76cd132c | note | FREQUENCY: Where applicable, 2 days prior to application.
89d42afe-3fc6-5acc-9037-5c69eeb06e5a | note | – – – – – – – – – – – – – – – – –
bc2d395a-50cc-5bd9-a0dc-aa47f5140611 | note | CATEGORY: HP
8a282407-7d9b-571c-a914-f8dfb3d7783e | note | – – – – – – – – – – – – – – – – –
064414be-add9-54df-94ac-8ba298623bb5 | note | RESPONSIBILITY: Nominated Authority
9938d979-c2aa-51a1-8615-ee649d0db6c9 | note | – – – – – – – – – – – – – – – – –
912f2484-9b85-509d-bd9f-e552da8ad4d6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
c7ac3ebb-954b-536c-8fc5-06d15223df17 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 Minimum Concrete Curing Period
d77840d8-6ebc-5b07-8d32-85cf139a7b44 | note | REFERENCE: 685.08, 686.16
db33b42d-935c-58b7-85ed-4593cf86fc14 | note | – – – – – – – – – – – – – – – – –
58dd804c-bd9a-5263-b61b-163a2d275906 | note | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
f0601704-47ad-5f80-a67a-bc42bbc4f7ee | note | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
4f3b8db2-57aa-5540-99ec-3e7f816bdcb2 | note | ○ Accelerated cured concrete = 14 days
44f64189-e117-5f6c-a276-e561eb969a8b | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
0c6668db-1ed8-5c63-aea4-8535e95d50fb | note | – – – – – – – – – – – – – – – – –
89784611-47d7-5727-a915-489b77f50f17 | note | METHOD: Visual, Document Review
91e4f51e-8c77-5eaf-8224-7e55076422d3 | note | – – – – – – – – – – – – – – – – –
d71caa7d-1d3e-58f3-bcac-bb1fcec99fba | note | FREQUENCY: Once, prior to application.
2115d0f5-9ed0-530f-94ed-26fc47de121f | note | – – – – – – – – – – – – – – – – –
fa7306d2-1975-5622-ad75-7858f94e7c81 | note | CATEGORY: IP
4bf6fac2-d270-51fb-b110-7891f29969df | note | – – – – – – – – – – – – – – – – –
ecd7b44d-3325-5bf8-9ec6-4205b21ebf6d | note | RESPONSIBILITY: SE/PE/SPE
a24b4e80-80cf-5f2b-aa31-c17b5dc4160a | note | – – – – – – – – – – – – – – – – –
70eae9a9-fa9c-5304-8b34-48d3d4728d65 | note | VERIFYING DOCUMENTS: This ITP
8adf67c5-7079-571a-91af-c94d1a08a109 | date | Date Completed:
| checkpoint | 2.9 Trial Application (or Past Performance) Inspection
28d69403-6665-5ae5-b07a-bbb66a708184 | note | REFERENCE: 685.11, 686.13
53e54b55-4328-55ba-be33-f21fe63060c4 | note | – – – – – – – – – – – – – – – – –
858f0745-1ae6-5785-a60d-9c13d3df0eb4 | note | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
09130120-75a7-5dba-a6fe-96c054507718 | note | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
0098ce1c-04ec-5bfe-ae7e-b78c7f938217 | note | Attach: Inspection Photographs OR
fbf5516f-78f4-5974-bbf5-dea8d10d9931 | textbox | Enter: Teambinder Hold Point number
dc671ed8-207c-5537-8c35-4c1cd0e3f619 | note | – – – – – – – – – – – – – – – – –
cb59ed83-2d0d-5458-81a3-9533acdbe458 | note | METHOD: Document Review
b1ab526f-43ad-5d94-939b-b32148565a16 | note | – – – – – – – – – – – – – – – – –
a94ed9a7-0a20-5968-b65e-48f9df64b5d3 | note | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
4f2a94c5-569d-5686-942d-3f981605ff69 | note | – – – – – – – – – – – – – – – – –
40737da3-3f62-5b99-b3bc-5c68e8552fad | note | CATEGORY: HP
07c907bf-26da-5905-b46d-3123de34a3b2 | note | – – – – – – – – – – – – – – – – –
e89e15f6-bf72-5e34-a0d3-53747e12dd88 | note | RESPONSIBILITY: Nominated Authority
923f7222-155a-5f6d-b950-ec42492c8efd | note | – – – – – – – – – – – – – – – – –
7c78d337-a75b-5eef-8124-54f1c6b07391 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ceef0a44-9953-58a2-aa64-fcb89ea26623 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-application Activities
| checkpoint | 3.1 Material Records
0705906c-ebb3-5204-9e26-f9785860827d | note | REFERENCE: Coating System TDS
0e396f18-e9fc-5cdb-8c95-f6f84936c2dc | note | ○ Surface Cleaner TDS
b68aa655-001f-52b7-81be-e623bb7fa5fe | note | ○ 685.10
1906d5a8-aefc-5e0d-b9a8-e64d2821163c | note | ○ 685.12
7dc5a27f-088d-553c-9fba-bbdb06e66c89 | note | – – – – – – – – – – – – – – – – –
5d40f99d-b608-5930-a6ea-31fc11fcfd4b | note | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
cc2a6d14-222f-540f-8bd3-275a15d80b6d | note | ○ the manufacturer's name & address
4e51a341-f674-5f40-8619-0de8232d36e0 | note | ○ product reference
3e3a6e60-77c2-5062-ad5b-e39edde8ae63 | note | ○ batch number
1bfa75f1-86a3-5c62-baff-1ad954a1f890 | note | ○ quantity manufactured in the batch
3d38d021-35b3-56c8-be6d-20e9f14e07f4 | note | ○ date of manufacture
f325d21b-b538-5273-9fd2-8ec21ab4a69b | note | ○ Product beyond the manufacturer's shelf life shall not be used.
ee402eb2-6d4b-53e7-a53f-316d74794e56 | note | ○ Each product shall be traced to final location.
2e5c4798-5567-588c-b44e-0b5a51e808b2 | note | – – – – – – – – – – – – – – – – –
539abbf8-b5f8-56c3-8891-39c9e3c92cde | note | METHOD: Visual
f78ed88d-ce9c-57c5-8de5-525493c5ba1f | note | – – – – – – – – – – – – – – – – –
9378faa7-35f5-5c3f-b643-33caba5c6748 | note | FREQUENCY: Prior to application
31063868-5ec5-59b6-9179-2f7cd99367a1 | note | – – – – – – – – – – – – – – – – –
3c09ac8f-2fbc-519e-878d-52184d504c5d | note | CATEGORY: IP
8ea05d5e-6974-5172-9688-9ef2c8b11f7e | note | – – – – – – – – – – – – – – – – –
b6d5a1b3-7b3a-507c-91d9-a0e5f7ffa99b | note | RESPONSIBILITY: SE/PE/SPE
c9352727-b9ef-5770-a7cd-f574dc7fcc62 | note | – – – – – – – – – – – – – – – – –
29f0a82c-5cc7-5f19-abd1-9d92cad26d85 | note | VERIFYING DOCUMENTS: This ITP
8918420a-df2e-5357-8784-39a728d1b897 | date | Date Completed:
| checkpoint | 3.2 Weather Conditions
325cc82b-ad7a-556a-8fd4-2105641b23f4 | note | REFERENCE: Coating System TDS
e0d6aed4-b61d-5218-b845-eb26c1faebba | note | ○ Surface Cleaner TDS
72363ebc-dd49-5d92-bd9c-77d8957f67f3 | note | ○ 685.09
07c8c5aa-efb2-54b7-8340-45ed277c7bd3 | note | ○ 685.12 (a)
7c2b2cb7-3b3f-5b64-ab28-9fbd5bfd307c | note | ○ 686.11
230972cb-37cf-5d77-9cdf-9a9edb0bb32d | note | ○ 686.14 (a) (iii)
13019048-5aaa-51b8-ab40-49986d906b92 | note | – – – – – – – – – – – – – – – – –
278dc637-e9c8-550f-849e-634871135fdf | note | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
4cd1c892-2194-5b57-a9a0-19635e306725 | note | i. windy conditions where spray/splatter may be generated
65ecf432-ef21-5efa-880c-92f584aa52d9 | note | ii. when wind-borne debris is likely to contaminate the uncured surface
0c385a7d-a157-5414-8dd0-f9ea67dd3437 | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
f9ebad4d-0779-5c77-972c-2ece7daf4454 | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
43ca2e23-aa90-5740-be06-6ceb4c3a6bd9 | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
adba2a2a-14fb-59f5-8b18-1ec9d0c4dfdf | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
a5593103-6abf-5ef3-bc5e-a436b9eab3ff | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
15028954-e9b7-593d-bdef-6e62580cd03f | note | ○ Weather conditions are to be recorded.
ab33b7e2-117f-5ff0-8f73-605885ffc86f | note | – – – – – – – – – – – – – – – – –
8b27ae47-6c5d-5453-a816-9f0c8eab6be9 | note | METHOD: Visual, Measure
455234d8-5e82-5248-9ac1-71e12976c98e | note | – – – – – – – – – – – – – – – – –
3fd7a7a4-a07b-573e-aa55-a903dde21d38 | note | FREQUENCY: Prior to application and every 4 hours per shift
0199232d-759c-5215-96b0-f5b62cd3f4d9 | note | – – – – – – – – – – – – – – – – –
8cf02382-3468-5b41-900a-97257e9d484e | note | CATEGORY: IP
3ffe6bcc-bd13-51cf-b3ef-4c72018f7202 | note | – – – – – – – – – – – – – – – – –
dea9b41c-d528-5a8f-9fa3-1c9b6989c284 | note | RESPONSIBILITY: SE/PE/SPE
3c8be2b9-8462-5f1a-b8b7-9584a01d32b5 | note | – – – – – – – – – – – – – – – – –
92a10607-e91d-535f-899f-d6ec6e14f27b | note | VERIFYING DOCUMENTS: This ITP
2eb266d2-48da-55df-99d8-58f81bba4656 | date | Date Completed:
| checkpoint | 3.3 Surface Preparation
e2bb9537-fa59-5091-9fa0-953e64218c05 | note | REFERENCE: Surface Cleaner TDS
b64b19a9-d7ab-578b-9f20-2d74e838c974 | note | ○ Coating System TDS
0718185e-0ee0-5dc2-b618-e56f378afe09 | note | ○ 685.05
1d00ace0-8739-5cbc-88b8-e41983c8b955 | note | ○ 686.06
fdc6f013-15dd-5f50-885e-41ff39ad649e | note | – – – – – – – – – – – – – – – – –
3cccd4f0-1e68-5d29-b37d-7f96d49e3b42 | note | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
7a554f20-3fbb-59e5-aadc-589dc6127fe1 | note | ○ The surface shall then be flushed with water.
c0309b3a-35e2-5bfd-a514-b0f269f9b58a | note | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
74aa0e9d-81e8-5f18-9243-72ca26ec93ae | note | – – – – – – – – – – – – – – – – –
b1984fed-b139-597c-931f-4359aa791bde | note | METHOD: Visual
43cb88e2-5099-5e0b-a4f3-ae742275585c | note | – – – – – – – – – – – – – – – – –
c679e287-8102-5a23-96a8-fb2a6d2749b6 | note | FREQUENCY: Once, prior to application.
b4a34233-6685-513a-94c9-6f1dcd8b39fb | note | – – – – – – – – – – – – – – – – –
517814a9-6e3d-5b64-8553-2e282c6f0d1e | note | CATEGORY: IP
5947150f-89cd-534e-ba08-d390c50c67e6 | note | – – – – – – – – – – – – – – – – –
39db3d9e-2f82-5d82-9b9a-5bab6faa9929 | note | RESPONSIBILITY: SE/PE/SPE
044214c4-248e-5055-8f84-12f8679f0d48 | note | – – – – – – – – – – – – – – – – –
31f27abb-93c2-53b6-a44c-f688d5b8546d | note | VERIFYING DOCUMENTS: This ITP
c41a1335-4498-5845-ba8d-9c4ecee4e268 | date | Date Completed:
| checkpoint | 3.4 Surface Moisture Testing
16e9ca7a-2767-5f2e-9bb1-3b7794a94143 | note | REFERENCE: 685.12 (a), 686.14 (a) (iii)
14efafc7-3d81-5e3b-bb3b-d88d18207f19 | note | – – – – – – – – – – – – – – – – –
f717a30a-27b8-52f8-9132-5940869dba35 | note | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
7ffc9f5b-794f-5c46-abfe-a605a6e2fed0 | note | ○ Surface moisture conditions are to be recorded.
926a4210-579a-5a4d-8492-b8b338df8da6 | note | – – – – – – – – – – – – – – – – –
229072c9-438d-57bb-b42f-93baf0fe99c6 | note | METHOD: Test
8993618e-2442-58f0-8574-4acd4b82a32f | note | – – – – – – – – – – – – – – – – –
2e2d0b3a-6c9b-5316-a02f-dd7ac0382938 | note | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
67f0a1ce-f739-5a02-a436-69f448419ca9 | note | – – – – – – – – – – – – – – – – –
4d6e3be1-1ff5-5fe5-817f-db493fe98e08 | note | CATEGORY: IP
1f344610-d34e-5284-94ef-9a51ef258c05 | note | – – – – – – – – – – – – – – – – –
b8825a72-f91f-5c25-9438-501a9351226b | note | RESPONSIBILITY: SE/PE/SPE
74e6f4b6-fd33-5f0e-985a-4fcc76efb79f | note | – – – – – – – – – – – – – – – – –
0da73759-e62b-54aa-ad01-ec78a8af5988 | note | VERIFYING DOCUMENTS: This ITP
3bdd84a8-da0c-5a0d-9c71-9d48fd2e64bb | date | Date Completed:
| section | Application Activities
| checkpoint | 4.1 Method of Application
d252a1e6-0a28-5ae2-8711-10bb83f601c4 | note | REFERENCE: Coating System TDS
7ae3d6b3-0069-5f3f-9e18-ac8b8678ab99 | note | ○ 685.07
8bec52e9-2c16-55bf-aec5-ae2e0c146e49 | note | ○ 686.07
7f0aafa7-0ea7-546d-83c2-4b3502d00452 | note | ○ 686.09
909314f8-cf88-5d08-b1aa-9377d999e174 | note | – – – – – – – – – – – – – – – – –
b84487ac-5b3a-59a4-8ee9-fb730bf2f559 | note | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
4d57c967-243a-5c49-9ae4-8b7324a22d05 | note | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
580b87d2-6c75-5129-a73e-baa41e69b214 | note | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
7585a5c0-77b9-5e5d-b438-f6055619bd0d | note | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
1a4a7ac5-f414-5fe7-89a5-147c9f4d934c | note | Attach: Coating Application Record
9e96f541-11e8-5ee4-9ec6-b3fdfe9a9cad | note | – – – – – – – – – – – – – – – – –
fa4413b2-6ccc-5c76-b393-981b17a13585 | note | METHOD: Visual, Measure
d7b9d964-6552-58be-8d1f-11ea916ff8bd | note | – – – – – – – – – – – – – – – – –
0502c99d-a28b-5d31-9e3f-613403872f87 | note | FREQUENCY: Each coat
0566ce6a-48bf-5393-bdb9-7a02be70bebc | note | – – – – – – – – – – – – – – – – –
c07448bb-01da-5737-b229-70a1b5e0ed64 | note | CATEGORY: IP
25b2f7a1-162d-5a0b-8769-834009ff0d4f | note | – – – – – – – – – – – – – – – – –
0556d125-e4dc-584a-8ea2-d30bda1c2c08 | note | RESPONSIBILITY: SE/PE/SPE
a533f7f1-5f46-5496-bca4-b29b2a18b366 | note | – – – – – – – – – – – – – – – – –
915eeb50-1835-5c9e-9690-6c2d548ee3f4 | note | VERIFYING DOCUMENTS: This ITP
82901460-687c-541d-a28b-3424e8090e3f | date | Date Completed:
| checkpoint | 4.2 Wet Film Thickness (WFT) Testing
0bc4484e-dbb0-574a-bef2-a1308f9a9852 | note | REFERENCE: Coating System TDS
83f50213-f5a0-5ac5-9558-a7256000d834 | note | ○ 685.12 (b) (ii)
e804e3ad-575e-5af9-92d5-32581d7b7df5 | note | ○ 686.14 (b) (ii)
2430324a-b35d-59a7-9811-a5a5df09b0e6 | note | – – – – – – – – – – – – – – – – –
2565b1fe-ad0a-57bc-9f2b-6febe7de3dd5 | note | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
e5bf49cb-9cc0-5f0c-8e42-3b77e9f025db | note | Attach: WFT Test Results
44de164c-93c5-5df8-a902-aa3472e23348 | note | – – – – – – – – – – – – – – – – –
8029e447-9990-560b-8377-867ad4869116 | note | METHOD: Test
c030a7aa-3776-5560-9978-f2b1b38e8d54 | note | – – – – – – – – – – – – – – – – –
60042d2f-0e26-5c38-bef5-8229457dee70 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
b982b6ef-01e4-597e-ad7a-71bfe71bafaa | note | – – – – – – – – – – – – – – – – –
e4a758bd-5e46-5d40-836d-c516cc97b8ff | note | CATEGORY: IP
f7a5789c-9395-51f0-9e36-5f7afbe3925a | note | – – – – – – – – – – – – – – – – –
6c918e25-7501-5ab5-80e4-2df3a4da8a43 | note | RESPONSIBILITY: SE/PE/SPE
58d26a4a-6348-5dd2-8400-3c5877b926e4 | note | – – – – – – – – – – – – – – – – –
a0181c53-b40a-54c0-b6e8-974e29d32354 | note | VERIFYING DOCUMENTS: This ITP
66fcb653-917f-5e32-a41e-3af6f96ac2ab | date | Date Completed:
| checkpoint | 4.3 Inspection & Defect Identification
a26120a9-2e25-53cf-89bf-7cd491d09ae5 | note | REFERENCE: 685.07
70237b09-e6a6-5518-a454-063fb7337123 | note | ○ 685.13 (d)
1284baa0-60d7-5031-8dd4-c8f4aa486164 | note | ○ 686.07
507d6ea9-ddd7-544a-9386-6e14369c723d | note | ○ 686.15
fb98f924-8f2d-5fa1-abbb-8ab1f98b7bf4 | note | – – – – – – – – – – – – – – – – –
cbc2c6c1-86ed-52a6-83f2-356c9b20eb4f | note | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
6f56981a-8948-5055-8528-7e7a6fb0e640 | note | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
c7c92464-1937-5c5f-9cac-441867215b7a | note | – – – – – – – – – – – – – – – – –
ef6311c4-4399-5e8b-9604-3deb45fec861 | note | METHOD: Visual
3ef7f958-83c7-5e89-b8e3-8d656ed09fa1 | note | – – – – – – – – – – – – – – – – –
91685ccf-32f9-5a2e-870d-8d091505bd25 | note | FREQUENCY: After each coat
639bb6c0-d964-5c24-a828-b6e7e7d25933 | note | – – – – – – – – – – – – – – – – –
6b82ed99-1631-5988-b463-50df8650840c | note | CATEGORY: IP
b678c300-05ab-5a50-be87-811eca2c66db | note | – – – – – – – – – – – – – – – – –
4eb0ed0f-0fa1-5dfb-86b9-f5f20a61a152 | note | RESPONSIBILITY: SE/PE/SPE
608097bb-5cdc-51a6-b56e-a80c05dfd763 | note | – – – – – – – – – – – – – – – – –
c6afa77c-49b2-520e-b3f3-9ab72c3d6a8f | note | VERIFYING DOCUMENTS: This ITP
ff571b3c-6750-5933-a8cf-1a81965b2927 | date | Date Completed:
| checkpoint | 4.4 Drying and Curing
4b1bba26-5ea7-5ecd-9ce5-7ab8c062a81e | note | REFERENCE: Coating System TDS
d09be76d-b6d4-5988-a040-0b50c597983a | note | ○ 685.17
087c8807-8ea2-5d64-9260-d9e365602e95 | note | ○ 686.10
4f222387-afc3-5509-ae90-b4a135d4ff68 | note | – – – – – – – – – – – – – – – – –
6bc2e27c-037d-5043-bc1c-7354cccd8027 | note | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
e158fcca-ca84-5243-b1ee-7ff20f8fb88c | note | – – – – – – – – – – – – – – – – –
b7cd9b67-a6fc-5a24-87bc-17cf5665796b | note | METHOD: Visual
579a463c-da77-5e60-9750-7180ef37cc0f | note | – – – – – – – – – – – – – – – – –
9fa92ad8-f635-5b9c-89e2-c08439803a2e | note | FREQUENCY: After each coat
f25d4f00-964f-5523-9eb8-102493622801 | note | – – – – – – – – – – – – – – – – –
32bd47a9-4cc6-522c-b1d7-648723ee52d1 | note | CATEGORY: IP
4ac882fc-1f26-5055-8651-e02c3b815417 | note | – – – – – – – – – – – – – – – – –
1c6344dd-6b65-56d3-81be-ed4c730581a6 | note | RESPONSIBILITY: SE/PE/SPE
2964f134-b384-5c1c-8391-69d5772a9244 | note | – – – – – – – – – – – – – – – – –
045b9f1e-52ce-5135-b400-13fb543f278a | note | VERIFYING DOCUMENTS: This ITP
b0849f69-8696-5fa3-a5af-aee64e8593ab | date | Date Completed:
| section | Post-application Activities
| checkpoint | 5.1 Clean-up & Waste Disposal
b679cb28-0c08-5898-a077-23423ab3d213 | note | REFERENCE: 685.09 (c), 686.10
b65ddd00-944d-5e41-917e-35944ee149ed | note | – – – – – – – – – – – – – – – – –
154afbce-5600-5aed-97cc-29783e6fb00a | note | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
148e537e-6392-5d94-928a-70950cb8d812 | note | ○ All rubbish and remaining coating products shall be removed from site.
0b6cad78-2cc4-5c66-95f2-215f92a899e6 | note | – – – – – – – – – – – – – – – – –
cf65fe38-f492-5a04-a46f-5c7f37db1cb8 | note | METHOD: Visual
3e82b43b-04d7-5a5a-b69c-8d481606921f | note | – – – – – – – – – – – – – – – – –
0a776647-65a7-5700-869d-9f3e8a4842c7 | note | FREQUENCY: At completion of Works
a24f8815-00de-5277-b2b9-1c865691f953 | note | – – – – – – – – – – – – – – – – –
742b4f69-3d6e-58bf-ae6c-cbcd02fe52af | note | CATEGORY: IP
104e685a-feae-57ac-b1a5-216d5bb345db | note | – – – – – – – – – – – – – – – – –
6482434a-b02e-5539-9b2f-dd080abbb819 | note | RESPONSIBILITY: SE/PE/SPE
245bfe56-3152-5a3b-97d2-5bb30bf743a6 | note | – – – – – – – – – – – – – – – – –
1df44dac-712f-5168-9270-9dc2cfa2e4ac | note | VERIFYING DOCUMENTS: This ITP
edca47b2-0b4b-5cb4-b8b0-4fe13f57cdfe | date | Date Completed:
| checkpoint | 5.2 Dry Film Thickness (DFT) Testing
d26baef4-3a7f-5f2b-bf1a-fb970b57c72b | note | REFERENCE: 685.12 (b) (iii), 686.14 (b) (iii)
e64c2a07-39f5-524a-acfb-23b193b0e29d | note | – – – – – – – – – – – – – – – – –
bb6173a7-6727-582d-b9eb-80e3bfcdd9f3 | note | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
fb658fae-066c-5f78-8612-9534fb9e4ba7 | note | i. Anti-graffiti system = 100µm
f0de7332-529d-57b0-8e5a-3c2fb3aa8d61 | note | Ii. Decorative & anti-carbonation = 150µm
ddf91926-e5e4-5936-9f26-99f4ec46f292 | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
aafbd9d9-0500-5c66-93a9-77f071b7975c | note | iv. Atmospheric & splash zone (dual protective) = 200µm
86fdc6ff-bedf-5649-bd50-a7f5233faba0 | note | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
91862986-c795-50cb-9e25-2bead3a05f0d | note | Attach: DFT Test Results
acd61764-1aae-57ae-b0ad-bd2862b046c0 | note | – – – – – – – – – – – – – – – – –
a1da6603-4617-5b0f-add9-c1a161aa24a9 | note | METHOD: Test
f0e5aa35-4506-504e-9043-c532ecf34eb2 | note | – – – – – – – – – – – – – – – – –
924120f7-0b48-524b-b927-87adebb5da9e | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
b82abd95-291b-581e-a4f8-966b07827c93 | note | – – – – – – – – – – – – – – – – –
08bd8f4d-a501-5dfd-b25b-6582127c669b | note | CATEGORY: IP
8d78e61a-3c99-58b6-9942-ddcf631e615a | note | – – – – – – – – – – – – – – – – –
beaed717-3752-53e9-a1d5-54bdf549298a | note | RESPONSIBILITY: SE/PE/SPE
a98c9500-347b-57be-8b74-cf1f78f66aed | note | – – – – – – – – – – – – – – – – –
b93c6234-4b98-574a-94c0-8a047fbd0435 | note | VERIFYING DOCUMENTS: This ITP
cf0779fc-5275-574b-a227-265e04b7e078 | date | Date Completed:
| checkpoint | 5.3 Adhesion Bond Strength Testing
e81aeda8-c99d-566c-9c30-d92c576c557b | note | REFERENCE: 685.12 (b) (i), 686.14 (b) (i)
aab58d9d-39bd-504a-a2a5-4b0ad89ed166 | note | – – – – – – – – – – – – – – – – –
80e0eb93-4e91-5b9c-9fff-c2f1f9b00e13 | note | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
5b54e35c-17c3-53dd-8ad1-30906cc22bde | note | i. the coating system to the substrate, and
1997703a-b21c-572f-8d74-cb3f58b01c94 | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
35014701-cfce-51ca-8e59-d9b6021f0d39 | note | ○ The subsequent results shall be greater than 0.75kPa.
20fad336-a87b-5ea4-a8d6-5e304a113f19 | note | Attach: Adhesive Bond Strength Testing Results
ebda03d1-a096-5a48-9673-f50a89b532de | note | – – – – – – – – – – – – – – – – –
8dbbadf3-5fe2-5c71-9d85-fb224dfb7675 | note | METHOD: Test
3aeb3e55-dc88-5d69-9410-0a2ec3b2e219 | note | – – – – – – – – – – – – – – – – –
3966b485-2515-5cd2-9c89-4f82822544fb | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
831fabfd-4be7-5229-99cb-dd7227eafa49 | note | – – – – – – – – – – – – – – – – –
68bd336b-ea64-5b89-bc9a-895a167838d4 | note | CATEGORY: IP
4ab9eed3-ae48-59fd-b5f5-d2e5c43e62cf | note | – – – – – – – – – – – – – – – – –
f8d3b03f-5801-509d-bddd-d719761b2f77 | note | RESPONSIBILITY: SE/PE/SPE
5ae09b9b-b2d9-5333-b3e2-6930a907fbac | note | – – – – – – – – – – – – – – – – –
e9f19c47-c739-5b1e-9d04-257b57d8ec84 | note | VERIFYING DOCUMENTS: This ITP
b0e89e49-fb77-5cf3-8d87-9165d95027bc | date | Date Completed:
| checkpoint | 5.4 Penetration Depth Testing
f4054f54-9c13-54a9-a9aa-e41f20755bba | note | REFERENCE: 685.12 (b) (v), 686.14 (b) (v)
c0149247-8a21-5384-86b0-fc46b95d6994 | note | – – – – – – – – – – – – – – – – –
4288c334-023b-5c34-88a8-8730385fcf27 | note | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
4902e3f6-503e-56ab-a211-78d0130888a3 | note | The subsequent results shall be:
11e35241-34f7-52d8-a4e1-3c0b8d4de8a7 | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
fe9e32f8-5f0a-5632-a044-204b4afab60c | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
5201e587-36fd-572a-ace7-adcd0d927a1d | note | iii. Silane-Siloxane or Siloxane = 3mm min.
0dcb0be9-67cd-59a3-a958-61b174739673 | note | Attach: Penetration Depth Testing Results
ee62b6dc-3876-5896-8de9-916b0ad1157f | note | – – – – – – – – – – – – – – – – –
59071baa-547b-563b-8519-1e7c36b78272 | note | METHOD: Test
0eb3a63e-66ec-52f0-9927-338772e2105e | note | – – – – – – – – – – – – – – – – –
a74fd6cb-b35e-5bb0-8569-a95dac34d9c2 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
90120b2d-978d-564c-bbdc-51a328b6ade9 | note | – – – – – – – – – – – – – – – – –
d4c77b6b-2f41-5087-aa95-7dfa6820b5d9 | note | CATEGORY: IP
1349ef72-1a0f-5a6f-af1d-d8f243846605 | note | – – – – – – – – – – – – – – – – –
71a976e8-22f3-5755-a571-cd9b18ee60e8 | note | RESPONSIBILITY: SE/PE/SPE
06d63ea9-11a4-5a87-8583-58fb0bcb5c03 | note | – – – – – – – – – – – – – – – – –
6218eb98-f323-54f5-958d-41e9d7f9af0b | note | VERIFYING DOCUMENTS: This ITP
23ee3eac-e88e-5d17-9cef-2708d59cccc7 | date | Date Completed:
| checkpoint | 5.5 Non-conforming Coatings
13f22f85-9f10-5ea3-bb2c-355402382c7b | note | REFERENCE: 685.14, 686.17
29aebb88-5ef7-5adc-ac55-8c13ec756e43 | note | – – – – – – – – – – – – – – – – –
386dfb62-348c-5628-ada4-f22ed6135603 | note | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
82e73747-c3bb-53d5-ae37-7321c817706c | note | ○ Such Work may include removal of the coating, surface preparation and re-application.
33cffb40-d9b1-55c5-8d59-c830005b6956 | note | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
0faf4232-db74-53e1-b9d6-73409a4bc6d6 | note | – – – – – – – – – – – – – – – – –
223cdf4c-be5a-524e-aa0b-65b9b5ada70e | note | METHOD: Visual
8418490c-aaaa-583b-8eab-4def0e4f1713 | note | – – – – – – – – – – – – – – – – –
a47694f9-5b28-5600-8231-f96478f28740 | note | FREQUENCY: Where required
23874331-488e-54b6-aea3-18738329a457 | note | – – – – – – – – – – – – – – – – –
01d359a1-e517-5e45-bf60-f79008da8785 | note | CATEGORY: IP
b6742012-516e-5d08-b5db-e6bebb9a006c | note | – – – – – – – – – – – – – – – – –
141f9e1d-ee46-58e1-9166-87ce6d5faf59 | note | RESPONSIBILITY: SE/PE/SPE
1eab28ff-30b3-5403-9cdf-f45807a1b79f | note | – – – – – – – – – – – – – – – – –
94e46d52-acb1-575a-986b-b11c7cecf0f9 | note | VERIFYING DOCUMENTS: This ITP
d6e26728-e9c2-5313-8dc0-b7a546886ba7 | date | Date Completed:
| checkpoint | 5.6 Coating Application Guarantee
44eb85d2-c9bb-52b9-a999-f74f1950e2c7 | note | REFERENCE: 685.06 (b), 686.05 (a)
64be1a66-314d-5322-8771-dc0a49969cab | note | – – – – – – – – – – – – – – – – –
900bca9e-94fa-532d-9212-ccf4706dc496 | note | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
6ebbf06d-ce98-50c2-ad39-dbcb5aaa631b | note | Attach: Coating Application Guarantee
1fdad638-fda2-5109-bfb6-7ad87c6c3be8 | note | – – – – – – – – – – – – – – – – –
514b2cb6-a97a-5521-ab6a-f0c5a09857cd | note | METHOD: Document Review
d7668a19-c651-5ed6-b5f2-eb8e91c6b464 | note | – – – – – – – – – – – – – – – – –
8a151ba1-0c30-5f15-9e4a-c2201ff27860 | note | FREQUENCY: At completion of Works
058bff23-a7c0-5aa7-8fc0-ae3478b470d1 | note | – – – – – – – – – – – – – – – – –
aa75d580-717b-5ae6-8b9d-2f555bdc2293 | note | CATEGORY: SP
4620da56-9b8c-5a81-9831-2cd965b89bbb | note | – – – – – – – – – – – – – – – – –
4c5a4925-19d7-5ec9-9e7a-322208618d12 | note | RESPONSIBILITY: SE/PE/SPE
2453c1d7-958c-5360-9ab8-c94a5a71f687 | note | – – – – – – – – – – – – – – – – –
895081c2-e2d6-5b8f-9229-5b714160625f | note | VERIFYING DOCUMENTS: This ITP
473e65ce-0ed1-53e4-98f7-6e51fb7a4793 | date | Date Completed:
| checkpoint | 5.7 Repair to Damaged Coating
bb04f3d3-a70f-568d-ab18-e86d65d7c49f | note | REFERENCE: 686.17
5b8560e2-9b98-5614-92da-160a54933d2b | note | – – – – – – – – – – – – – – – – –
12242897-bcfd-5053-b5ad-5e7e19fa6fea | note | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
87eab4ab-0390-5ff0-a713-a329dcd5bb9c | note | – – – – – – – – – – – – – – – – –
e4a527e4-e339-5188-83cd-35cb429c8523 | note | METHOD: Visual
ea7771f7-5087-5f21-9ac9-ca4570e061e6 | note | – – – – – – – – – – – – – – – – –
e5caa8c3-6be9-543b-b3b3-4350e60821b0 | note | FREQUENCY: Where required
b86cd4c6-30aa-5d6c-a4a4-c37eb4597252 | note | – – – – – – – – – – – – – – – – –
975e31c1-811d-5091-8581-074a8ba0975c | note | CATEGORY: IP
6efb6c63-a329-5e3d-8862-785fef299d92 | note | – – – – – – – – – – – – – – – – –
4e0c9e04-307a-55bf-b86e-bf2fc99dc1a8 | note | RESPONSIBILITY: SE/PE/SPE
53ddc78c-d900-5478-a259-75c7e2bede99 | note | – – – – – – – – – – – – – – – – –
269ec074-e623-5da0-9c66-00d7f03dfe7a | note | VERIFYING DOCUMENTS: This ITP
40433b51-7a49-5590-972c-70db258129d0 | date | Date Completed:
| checkpoint | 5.8 Non-conformance Report (NCR) Closure
8f2b068b-f91e-5f1b-9a46-ce3c8bfc3d3c | note | REFERENCE: MRPA Quality Management Plan
40d2f5eb-f82c-5c99-b467-a1c4d03a23d5 | note | – – – – – – – – – – – – – – – – –
74cdadcf-0479-5404-882d-1e7b35887849 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
a67190e7-a936-54f0-ba84-78973f619e71 | note | – – – – – – – – – – – – – – – – –
bfa43524-f1a0-55bf-b87b-01f0355739a6 | note | METHOD: Document Review
0570aca7-fbe9-5cbc-b28d-9b57a77b043a | note | – – – – – – – – – – – – – – – – –
5855ad06-d625-5740-b08a-ef448b0c98e6 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
c544629e-5326-533f-8081-08e949979616 | note | – – – – – – – – – – – – – – – – –
1260d7f8-011d-50ee-b59b-aa8bcafc84dc | note | CATEGORY: HP*
c05aeb88-ea2d-58b0-8a2d-0e5f2a41718d | note | – – – – – – – – – – – – – – – – –
d3d490ad-d1e2-53fa-981d-2776540785fa | note | RESPONSIBILITY: SE/PE/SPE
7faa776d-2b6d-5812-9e94-e16e99165f20 | note | – – – – – – – – – – – – – – – – –
98da3e5f-80b1-5ccc-9e92-0eb286bffc16 | note | VERIFYING DOCUMENTS: This ITP
3c3eda7c-aaae-54b5-bec7-0827189fa618 | date | Date Completed:
| checkpoint | Final Inspection
185928b0-75ef-5316-a333-b9f140218ac4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3babc9b9-0d6a-50b3-9e7c-9ebb746d9d4c | textbox | Name:
51fd4024-a0d6-5e86-af5b-a0467324a4b6 | textbox | Position:
4eb9ad09-a0d2-58d9-b785-03e6413b9a36 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting Rev 0 | itp | ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting | 2661fb23-2aee-4845-814e-e8864e463c43
| section | Referenced Documentation
| checkpoint | Referenced Documentation
e2244fec-5183-5f9a-9c36-5ac00e3dba1f | note | Document Title: ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting
2979158f-2070-5005-9c4f-46f716adadac | note | ITP Description: Conduit and Pits- MTM Car Park Lighting
3e27c054-116a-5d45-95f0-01295927a430 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
85e846b5-f408-5124-ad03-8e7356bf61a1 | note | Discipline (e.g. CIV/STR/RAIL): CIV
71a4c3e2-35ca-56c6-b5c2-4fbb553da0ec | note | Revision Number: 0
0e5a9c37-3625-599c-aa4c-5bec9fa0cca2 | note | Revision Date: 13/11/2023
a70fd7af-dc23-5812-9cb7-254b943b9e15 | note | ITP created by: Romualdo Magpantay
93566322-adbf-5fb0-b6b2-d2cb3e1ec911 | note | ITP approved for use by: Victor Mira
8deb2df1-73d5-573c-83ad-7b3a49fda37e | note | 1.1 Non Dependent
44b0d450-3ab3-5a8a-8e4e-8585d9c58823 | note | Reference: L1-CHE-STD-035
43ed6362-e30e-5103-acf1-414d05677f5f | note | 1.3 Non Dependent
eb365727-a5a7-5d81-90d5-645faae7ca5f | note | Reference: AS /NZS 3000
| section | Preliminaries
| checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
95eb9964-3af5-54f4-87d4-f6bdc02d21ee | note | ○ LV + HV Conduits
8e795f50-4e75-5a86-a859-41bd16c477ef | note | ○ Communication Conduits
7889228a-8065-5263-937c-957b4b1df66b | note | ○ Fixing and Supporting Materials
99ad9666-ddf3-5113-aa57-4a5018f3100c | note | ○ Pits
abf805b3-e8ab-506b-ba17-d0a375400904 | note | REFERENCE: IFC Drawing, Supplier Specification AS /NZS 3000
aca26145-34c7-59bf-b33b-7e248c5e2af3 | note | – – – – – – – – – – – – – – – – –
6c8a2137-6ff4-56c1-b793-c03a54e95413 | note | ACCEPTANCE CRITERIA: Materials comply with relevant specifications.
2fc3fd36-8861-506e-bd7f-40fc31389d29 | note | ○ Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
60fadcff-0843-5a5e-9e4e-572ce2910c07 | note | – – – – – – – – – – – – – – – – –
493999e8-1849-5017-8091-c7694bb93653 | note | METHOD: Visual
dbfe3aa2-5609-5c5a-85cf-7ba3d708c006 | note | – – – – – – – – – – – – – – – – –
9b8e4070-1c9d-507a-be3d-0800bdb419f2 | note | FREQUENCY: Once
8e85539b-b32d-5b7e-bb42-287fe62417cb | note | – – – – – – – – – – – – – – – – –
86a2bc43-f139-5dca-9c6e-d1cbf5054228 | note | CATEGORY: HP
e50372cc-390f-583e-8000-6520f6bc2f27 | note | – – – – – – – – – – – – – – – – –
68458b12-2305-5858-8024-c68525e0d6bd | note | RESPONSIBILITY: Nominated Authority
f6362f8f-496d-54b0-9c43-dafb0ee6860e | note | – – – – – – – – – – – – – – – – –
6a5c563b-320d-56dc-b3b1-2ff93f1db055 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4b41aeb8-cb47-5b1d-8f64-cc51b3fe7fe6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Inspect supplied items upon delivery
ba255c02-6e79-5a94-afcf-2e4c0c7ce1dc | note | REFERENCE: IFC Drawing, Supplier Specification AS /NZS 3000
cfe453e8-f909-5116-9342-6ea68976f85f | note | – – – – – – – – – – – – – – – – –
2e6606a8-7b2f-5820-8dc7-4ad6a94bfa61 | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
7e0e5666-d843-5d73-8250-925c0cfa4d4b | note | – – – – – – – – – – – – – – – – –
8fd231ec-2171-5014-bade-ec96fe607aa9 | note | METHOD: Testing
e245d4d2-7e19-5d6b-ba51-c91d8f8a802b | note | – – – – – – – – – – – – – – – – –
ac4f5bb5-7faf-5a18-ac05-037f79e57d4e | note | FREQUENCY: Once
76c9a602-c73e-598b-b265-086ac84c337a | note | – – – – – – – – – – – – – – – – –
e592df50-4b6f-53a1-be9f-60e06b184d41 | note | CATEGORY: IP
2bb778b5-3d82-57bd-ae48-7723589bfcbd | note | – – – – – – – – – – – – – – – – –
fe4b525c-642c-5763-bba2-42b689c3b4c1 | note | RESPONSIBILITY: Electricians, Site /Project Engineer
4f22525c-e6a4-5580-b22c-bbb66bcfe083 | note | – – – – – – – – – – – – – – – – –
0cb3b19d-1d92-5fc5-945b-ef6448e0b30c | note | VERIFYING DOCUMENTS: This ITP
760d758f-8edb-50c5-9e07-5edf7cd7fac2 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 3.1 Excavation of Conduit Trenches & Pits
67deb7cc-b247-5968-8d41-aebcfbe1a1bb | note | REFERENCE: AS/NZS 3000 clause 3.9, IFC Drawings
57afeda5-ac78-5f47-b56e-8a2b641a3062 | note | – – – – – – – – – – – – – – – – –
6cc1a9e1-a58d-53cb-87a5-39964a0e4431 | note | ACCEPTANCE CRITERIA: Install the conduits after earthworks have been completed to subgrade level.
5ec59e46-df10-5b06-8513-3b6469125012 | note | ○ Installation of the conduits must be in accordance in the design dwgs.
547e61d8-a6b8-565a-a197-c9b74ae9ba4d | note | ○ Where the conduits run beneath a road, provide a minimum cover of 500 mm from the top of the conduits to the underside of the pavement; in all other areas, provide a cover of 500 mm to finished surface level.
5273e5c1-9179-5eac-bfab-0a35124efe4c | note | – – – – – – – – – – – – – – – – –
6dae9f28-a626-518b-989b-6a16730c95af | note | METHOD: Inspection
30e6875e-f9fc-59f7-9732-dc68d835986e | note | – – – – – – – – – – – – – – – – –
51ca9cd4-e787-5bea-a038-48ada04fba4f | note | FREQUENCY: Once
f714d3f2-fee0-5b69-a6e5-bc21837a9ca1 | note | – – – – – – – – – – – – – – – – –
146ef163-ca5d-5fa9-942b-01d870027871 | note | CATEGORY: IP
a57b7fc4-bff7-5875-bba2-fe5fb685e224 | note | – – – – – – – – – – – – – – – – –
282ae33e-5071-55da-b692-867a9a66f411 | note | RESPONSIBILITY: Supervisor /PE/SPE
2553c093-3030-5ec5-ac3e-832f2682c3a7 | note | – – – – – – – – – – – – – – – – –
acbd06bb-8fc0-541f-8c00-c9e2c64bc38d | note | VERIFYING DOCUMENTS: This ITP
e6b9ccbc-a246-5eb7-9a02-127ac01cf8a1 | date | Date Completed:
| checkpoint | 3.2 Sand bedding, laying and backfilling
23c56ba4-9096-52a9-9070-1d9b866456d1 | note | REFERENCE: AS/NZS 3000 clause 3.11.4.5, IFC Drawings
1914c2cd-96e4-5570-90aa-7bce14be4f5c | note | – – – – – – – – – – – – – – – – –
32e88f86-89ca-55c2-a30d-db3feff21f55 | note | ACCEPTANCE CRITERIA: Use a min. 50mm compacted sand for bedding if not shown on the design drawings.
736d3311-8cbe-592d-9ae2-f525e8187e7a | note | ○ Lay the conduit on a straight grade and line
c739a934-367f-50bd-870c-1e3f110d805b | note | ○ Compact backfill over the conduits to 100% relative compaction or depend on IFC drawing & pavement design requirements.
401f0a69-d3da-5efb-937f-29c3b53da6ab | note | – – – – – – – – – – – – – – – – –
4f072cd3-c60c-5b9c-adb6-d9a798071f24 | note | METHOD: Inspection
37120ff3-e959-5340-abda-b14864d75b22 | note | – – – – – – – – – – – – – – – – –
9e5a3874-68f8-5e56-aa13-65b66298350c | note | FREQUENCY: Once
4865fdb3-ee69-54c8-a919-0a940f7dcbd6 | note | – – – – – – – – – – – – – – – – –
0ea8b072-4c61-54bf-8dc0-156cef4c71bf | note | CATEGORY: IP
73b14048-ef82-5d0f-9538-0dd928f67b43 | note | – – – – – – – – – – – – – – – – –
d8d537cf-122f-5018-b5cd-b5cd4874ca6c | note | RESPONSIBILITY: Supervisor /PE/SPE
c7e4c367-a84c-5219-8b04-2f7d7f51a8c7 | note | – – – – – – – – – – – – – – – – –
f37736e8-d9cc-5bb7-b64d-4f3bf2488a7c | note | VERIFYING DOCUMENTS: This ITP
fee221c9-827e-5aa6-bd3d-aa330263388d | date | Date Completed:
| checkpoint | 3.3 Install conduits according to manufacturer’s instructions, relevant drawings and Standards
57d4c778-98d5-5390-bdef-f0351e997004 | note | REFERENCE: AS/NZS 3000 clause 3.9, IFC Drawings
dab66a69-a97e-5a78-92a1-749a27757397 | note | – – – – – – – – – – – – – – – – –
9fb1800c-4e6d-5213-a872-4c81a46951aa | note | ACCEPTANCE CRITERIA: The works are constructed in accordance with AS/NZS 3000 Wiring Rules and Services and the installation Rules of AS 2067.
88bbbdd1-23cd-52f6-b9b0-47b9c2a97a01 | note | ○ Conduits are joined together with solvent cement, generally in accordance with clause 4.2 of AS/NZS 2032 and all joints are water tight and free of foreign matter
821247cd-303d-5177-8dc5-f119d1b965a7 | note | ○ Conduits are inline & positioned evenly
071a88bd-632d-54a0-bea4-0aaaa6f43898 | note | ○ Location of each conduit is as per Design Drawings
b21d95b3-2a06-500b-8d38-028143363975 | note | – – – – – – – – – – – – – – – – –
dadce159-89b9-570a-a07d-8dcdc3ffe3c8 | note | METHOD: Inspection
7122f4d7-b3f5-5e04-b72b-830401dd493c | note | – – – – – – – – – – – – – – – – –
b9c5c80a-bd4c-5bfd-92ff-21487654790b | note | FREQUENCY: Once
a636775b-ffdd-54b8-9467-261aea160df1 | note | – – – – – – – – – – – – – – – – –
c560f1fd-bacf-5553-8fd3-36499ae8caa8 | note | CATEGORY: IP
b5265381-63b3-51ca-a7b2-d571bfce98b7 | note | – – – – – – – – – – – – – – – – –
c46bdf91-fcdd-5995-90a0-22e45b8b6c49 | note | RESPONSIBILITY: Supervisor /PE/SPE
bb84d69b-a64a-5795-9f81-1e8511513bb4 | note | – – – – – – – – – – – – – – – – –
f81c4538-9088-5f0f-aba4-04b620d304fc | note | VERIFYING DOCUMENTS: This ITP
b5aab88e-fff2-56f8-be35-a0fcb7f62ad6 | date | Date Completed:
| checkpoint | 3.4 Installation of Electrical and Communication Pits
d40d5b5c-c593-53a8-89c8-a1595d4d6a29 | note | REFERENCE: IFC Drawings, L1-CHE-STD-035 section 12.6
3ab9cbed-7f8a-5647-899b-4511fd14bb28 | note | – – – – – – – – – – – – – – – – –
cd8caafc-69ea-52a9-a1ee-2ae98fade1ab | note | ACCEPTANCE CRITERIA: Compliance to IFC Drawings, Schedules & relevant specification:
250292bf-7db8-5bfb-92df-2e7ebb968c09 | note | ○ Correct pit as per the IFC drawings
7c551151-3d88-570b-b6c3-fb22463f235d | note | ○ Soil underneath pit bedding is to be firmly packed prior to install
d3caf4d8-f04a-5926-a192-febaf7c8ae0e | note | ○ Bedding according to IFC drawings to be placed
4f142170-ddb6-5ef2-9387-a23d0e5747d4 | note | ○ Pit orientation is correct
9206337d-2f1c-543c-aadc-7a07725f7791 | note | ○ Lids & covers to comply with technical specification
a405176c-33ce-5061-b8ea-ee326508e041 | note | – – – – – – – – – – – – – – – – –
41a24140-eb1a-58cb-b27c-edca6998a937 | note | METHOD: Inspection
aacdb432-9928-5a71-9143-dd9a70e3ff9f | note | – – – – – – – – – – – – – – – – –
37a25bcd-4e53-568d-bdf6-76dbea79a383 | note | FREQUENCY: Once
67d35015-cf3a-5e22-ac56-891f9adddae9 | note | – – – – – – – – – – – – – – – – –
7ae1468f-9356-53bd-b8dd-2eae8003d924 | note | CATEGORY: IP
4b6a9063-13f9-5954-982c-4a0604b08766 | note | – – – – – – – – – – – – – – – – –
f6ec7caf-8fbd-50ab-ba30-6f1bee6e04b2 | note | RESPONSIBILITY: Supervisor /PE/SPE
7eee9a33-8290-5879-a128-2fcce1d3a794 | note | – – – – – – – – – – – – – – – – –
b7040eac-df9f-57b6-84de-d35519fc4f5a | note | VERIFYING DOCUMENTS: This ITP
1af44098-6cdb-5d90-8957-a080bfa3bd38 | date | Date Completed:
| checkpoint | 3.5 Marker Tapes
9f436ded-d4a4-5bd7-828a-fb8048540ef0 | note | REFERENCE: AS/NZS 3000 clause 3.11.4.5, IFC Drawings
b6ea60f5-ba0f-51bb-a0ee-0d31bcfb77a0 | note | – – – – – – – – – – – – – – – – –
d3a02505-73c7-5bb0-91c9-94b8d2ca007d | note | ACCEPTANCE CRITERIA: Wiring systems installed underground shall be identified by an orange marker tape complying AS/NZS 2648.1. Positioned at approximately 50% of depth cover above wiring system or any additional mechanical protection provided that system.
160839f2-0dee-5dc1-b70c-17cab119024f | note | – – – – – – – – – – – – – – – – –
00e4fbdd-98a9-5f94-969a-1acf848c14fd | note | METHOD: Inspection
60189c80-98da-51d2-86bb-a15e386902a7 | note | – – – – – – – – – – – – – – – – –
1d8d8c0c-516a-51e4-aac4-b56202b11495 | note | FREQUENCY: Once
0ae875bd-28d9-507b-bb20-08432da1caca | note | – – – – – – – – – – – – – – – – –
0ec69acb-3c0b-50df-9d17-2c0e7b8129a9 | note | CATEGORY: IP
c257dcb4-d452-5bf6-ae3b-80f04d9d8cb8 | note | – – – – – – – – – – – – – – – – –
49ceef46-8eac-514c-8fa7-241d49396758 | note | RESPONSIBILITY: Supervisor /PE/SPE
1c7b3679-d36f-5e98-a7cd-57b4accd05c8 | note | – – – – – – – – – – – – – – – – –
23cbc449-91e6-5e68-8650-d288ee19c122 | note | VERIFYING DOCUMENTS: This ITP
12ee8503-a343-580c-b042-de2ce0c71ff2 | date | Date Completed:
| checkpoint | 3.6 Install draw-in rope to all electrical conduits(if applicable)
8e9ac1ac-0683-555b-8c26-25f4cae7af45 | note | REFERENCE: IFC Drawings, QA & Work method of statement
bd7b4ced-6212-5751-8d61-8dff16c8b736 | note | – – – – – – – – – – – – – – – – –
47c623cd-ef29-5be8-be16-4ed302e8f473 | note | ACCEPTANCE CRITERIA: Polypropylene draw-in rope consisting of one continuous length of not less than 4mm dia. in all electrical conduits or specify in methodolody
d68398c8-1a2a-554a-8590-785dc6398981 | note | – – – – – – – – – – – – – – – – –
dd1e9f3b-00ac-52fa-8ee8-5353eaea0d02 | note | METHOD: Inspection
c1881f9b-a643-5bb6-8efa-7699560c083d | note | – – – – – – – – – – – – – – – – –
b17893da-57ac-50c0-8e0f-408cf41b3091 | note | FREQUENCY: Once,
7f9fef02-90a9-5cef-a90d-3c3798e081e4 | note | – – – – – – – – – – – – – – – – –
8db17811-9e71-566d-8268-6c2953366292 | note | CATEGORY: IP
3e43a079-daa6-59a8-8e7c-dd33aa7d017a | note | – – – – – – – – – – – – – – – – –
eb095616-8056-5958-b2df-f11435d012ed | note | RESPONSIBILITY: Supervisor /PE/SPE
dd759cf2-65e2-57f5-a16f-90edb10c0afb | note | – – – – – – – – – – – – – – – – –
5e3153b5-3dc5-5385-b81c-f3b53a2f79c5 | note | VERIFYING DOCUMENTS: This ITP
2cfdaea8-9bc9-5d54-b723-f1ff6f96216a | date | Date Completed:
| section | Post Construction Activies
| checkpoint | 4.1 As-built Survey (if required)
5d1baf4b-e1fc-5e29-8dd1-9de918b71caa | note | REFERENCE: As Built Drawings, Asset Change form
59772590-22a7-550a-b767-eaeabc9349b7 | note | – – – – – – – – – – – – – – – – –
75e430dc-d1f7-5fba-812d-5d3d83b0edf5 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
459e5afa-3209-59b3-b3c1-1887296e0e3c | note | Attach: Surevy Report, Engineering Asset From
b74a7a0c-6e57-5e37-8640-c1527df24de9 | note | – – – – – – – – – – – – – – – – –
9246c13d-ac98-57cc-a94a-ea5c73d9ff98 | note | METHOD: Survey, Document Review
b09b96fd-e342-55a4-bf21-ad77dd4e8bde | note | – – – – – – – – – – – – – – – – –
104019c3-1e45-5c28-9588-7711434834cd | note | FREQUENCY: Per lot
ff6d41c8-3d92-5379-a4e2-7d65ca6f11b4 | note | – – – – – – – – – – – – – – – – –
3a489b3e-ac65-5f39-8660-dbfaebeb70ea | note | CATEGORY: IP
f70b83d5-cae8-51de-ac77-3166bc05b423 | note | – – – – – – – – – – – – – – – – –
6a3e5032-f9a2-5177-8bca-afe51eeea58e | note | RESPONSIBILITY: Supervisor /PE/SPE
08a409ef-6ebc-5935-aca9-3326de4b3369 | note | – – – – – – – – – – – – – – – – –
f8805cf7-0cf3-50d7-9b7d-912c350b05f2 | note | VERIFYING DOCUMENTS: This ITP
5affc9af-d3b3-5fb8-b9a4-234a1adfd11d | date | Date Completed:
| checkpoint | Final Inspection
78715c94-eb0c-5eac-85bd-f33a49af03d4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1dbd0aaf-17f2-5d41-b86a-f0679a8d730c | textbox | Name:
8e3e2467-3eb8-5b4d-9c76-ba9177296603 | textbox | Position:
5e102049-c6a0-5a31-943d-73e4bec76143 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-184-CIV-SSB-Conduits and Pits-Road Rev 0 | itp | ITP-184-CIV-SSB-Conduits and Pits-Road | 7384f326-7199-42e8-9e1d-e4d4d3f2817f
| section | Referenced Documentation
| checkpoint | Referenced Documentation
499f1348-4a9f-5310-8908-dfceddd1980e | note | Document Title: ITP-184-CIV-SSB-Conduit & Pits
b51ebead-4060-5587-bd2a-8931777e0c47 | note | ITP Description: SSB-Conduit & Pits
2a7924c9-98ca-5dee-8c07-fc5ef969b72b | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
bce7e328-ec26-529d-a6d9-fdf4d67bdb3e | note | Discipline (e.g. CIV/STR/RAIL): 184-CIV
9f79c2e6-b2cd-5354-88c5-701d73a156a2 | note | Revision Number: 0
bf67c436-b246-56c3-9f81-e6256a245189 | note | Revision Date: 13/01/2024
8933fa68-6d8e-5d1f-929b-8b7213591d94 | note | ITP created by: Victor Mira
e261951c-971a-5172-b2d4-c3ec0db70c9a | note | ITP approved for use by: Victor Mira
afc90829-a9cb-553c-9081-5b7b5468fe05 | note | 1.1 Non Dependent
5f1d0592-fb7d-54d9-b4cf-df1555fff494 | note | Reference: VR 733 November 2023
a8d30605-468a-52ec-b3f9-8d75c1811fd0 | note | 1.2 Non Dependent
005224e5-5e32-509b-931e-b7a0699fc5f8 | note | Reference: AS/NZS 3000:2018 Wiring Rules
| section | Preliminaries - Materials
| checkpoint | 2.1 Conduits-Electrical
81149d0c-3035-5d2e-9464-1f7a427990fb | note | REFERENCE: VR 733.04 (a), Table 733.041
e9e1e7f2-9d3e-5e64-a01a-d2a34639063f | note | – – – – – – – – – – – – – – – – –
4f94177d-64da-5f46-87f8-ebbe7595078c | note | ACCEPTANCE CRITERIA: Unless otherwise specified, the Contractor shall provide all plastic conduits which shall comply with the following standards as appropriate:
3730a9de-94be-5fa3-a436-93b06631b236 | note | – AS 1345 – Identification of pipes, conduits and ducts
c672d4a8-4fd6-52d9-b6a1-07734dd1d49f | note | – AS/NZS 2053 – Conduits and fittings for electrical installations
3f71e157-f8b7-5513-a08b-212dac29366c | note | ○ All conduits installed underground for electrical wiring, traffic signals and traffic services shall be heavy duty grade, rigid, solid wall, orange, UPVC conduit to AS/NZS 2053.2.
f88e67d3-3870-5ab9-bf0a-94adfc6b6cc5 | note | ○ Conduit sizes shall be according to Table VR 733.041
8fac6c1f-70fc-586d-953d-4a30ea6cf5f5 | textbox | Enter: TeamBinder Material Approval Number
b66985ea-51cf-5539-af33-ef15874913cf | note | – – – – – – – – – – – – – – – – –
abaa219c-59f8-5818-a4c3-1eabed39795a | note | METHOD: Visual, Document Review
8ff986c1-49f7-537d-94f4-346686a5b5fe | note | – – – – – – – – – – – – – – – – –
0b3d9a46-2ba2-591a-b615-4de975b0bf89 | note | FREQUENCY: Each Material Type, Where applicable
7b6ca5e3-a1a2-5676-8822-2aa04e26d239 | note | – – – – – – – – – – – – – – – – –
07cb422f-7fde-5c83-8d95-8c39cd830dbd | note | CATEGORY: HP
44a67dc2-48d7-552a-a3f1-bf4a8b6774ed | note | – – – – – – – – – – – – – – – – –
01d85967-c911-595d-b425-0d9c00d0630b | note | RESPONSIBILITY: SE/PE, Nominated Authority
81da5bd2-49b7-5ea9-ba05-a00ab30927e6 | note | – – – – – – – – – – – – – – – – –
43a8eb68-d9e0-5694-b55c-f5c2fae404c3 | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
684a1811-d896-53b9-985c-28d18e6fc228 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Conduits-Comms
5269aafd-350c-5278-96be-c6314edd743e | note | REFERENCE: VR 733.04 (a), Table 733.041
1de365ff-80cf-5028-9ba4-7940692a3640 | note | – – – – – – – – – – – – – – – – –
fbcff917-394a-59dd-8d0a-6d12e5752b2e | note | ACCEPTANCE CRITERIA: Unless otherwise specified, the Contractor shall provide all plastic conduits which shall comply with the following standards as appropriate:
6c35aac9-55f8-5fc8-b7ea-176f64e67ae7 | note | – AS 1345 – Identification of pipes, conduits and ducts
cccb20fd-8539-5f22-80c1-d41fc25b63f8 | note | – AS/NZS 2053 – Conduits and fittings for electrical installations.
82cd36c0-cdad-5a6a-a593-5b2296395a3f | note | ○ All conduits installed underground for communication cables shall be heavy duty grade, rigid, solid wall, white UPVC communication conduit complying with AS/NZS 2053.2 and complying with all relevant Australian Communications and Media Authority (ACMA) publications and standards.
f489e4e6-4bc1-5349-9ac7-cbd05911702c | note | ○ Conduit sizes shall be according to Table VR 733.041
358864c9-575c-5dd8-b4be-d2b7f91c7b61 | textbox | Enter: TeamBinder Material Approval Number
839c1a98-9d96-5518-9106-f52c0b0f9f35 | note | – – – – – – – – – – – – – – – – –
762852b7-8430-5efa-af00-f716d0e70182 | note | METHOD: Visual, Document Review
c3d716c3-8b7d-5783-a8a2-d174a8e49ef8 | note | – – – – – – – – – – – – – – – – –
9b5a41f2-3b90-596c-8af3-849f4e9a80ef | note | FREQUENCY: Each Material Type, Where applicable
d4c8ae0d-8361-552a-966a-88a0587bd06c | note | – – – – – – – – – – – – – – – – –
63eb6b86-8f94-5a18-839f-75d295c109e2 | note | CATEGORY: HP
3ba1a7f8-c248-52be-a29b-2cb102eff9ca | note | – – – – – – – – – – – – – – – – –
6f7420b6-b5e6-565f-8595-0b3c552b662e | note | RESPONSIBILITY: SE/PE, Nominated Authority
271ed6e2-0c00-5954-93ab-1464ee60820a | note | – – – – – – – – – – – – – – – – –
3e77cd9e-57c1-52ee-8148-5714c8b73582 | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
b06cac32-c1a8-53b6-a5b4-fffa0b029d8b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Conduits-HDPE
a69fba94-7aeb-5db9-a13c-041dbfef193a | note | REFERENCE: VR 733.04 (a)
0d4835c8-0c60-5730-abba-8d71ac1707eb | note | – – – – – – – – – – – – – – – – –
8a2e6140-c51c-58e7-80f9-738dfe16cc84 | note | ACCEPTANCE CRITERIA: The use of HDPE continuous conduit for bored road crossing is permitted.
728119be-e7b6-5d77-b8ee-add34050be2a | note | ○ Where HDPE continuous conduit is used for electrical cables, it shall not be smaller in internal diameter than the specified UPVC heavy duty conduit.
559a9d96-1cc2-5aa9-b484-d6a566c400e7 | note | ○ Conduit sizes shall be according to Table VR 733.041
e6f39d61-6b2c-5988-8573-db7c5b97ca2d | textbox | Enter: TeamBinder Material Approval Number
234273f6-4d7c-5b10-81de-fde33b02449c | note | – – – – – – – – – – – – – – – – –
44c5b21f-cedd-5a07-84d8-8c3200f69253 | note | METHOD: Document Review
acd66046-41a9-5a24-b2e0-a873066c2849 | note | – – – – – – – – – – – – – – – – –
924fd8a7-c2e5-5c86-b781-6b57fcd6237b | note | FREQUENCY: Each Material Type, Where applicable
01b814a6-b9e9-52b1-bffa-621cfe165acf | note | – – – – – – – – – – – – – – – – –
a1a2dc1f-4924-563b-bb5a-fb73c7d7e90e | note | CATEGORY: HP
7ec3a788-59f0-51b0-ab57-3277f6955482 | note | – – – – – – – – – – – – – – – – –
f19f738e-00cb-54c8-8793-233a9ca12d81 | note | RESPONSIBILITY: SE/PE, Nominated Authority
2c2aeb24-6db9-5147-9226-9e3746bb8f1b | note | – – – – – – – – – – – – – – – – –
91fc1cc2-9e55-5f4e-a248-a968fbdafe22 | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
5c0be849-3e60-5526-909b-454cf4426a8a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 Pits and Pit Lids
69cdbc28-d10b-51a7-aa17-3dbd2fa49c48 | note | REFERENCE: VR 733.09 (a)
aba101e4-b231-59e7-a374-aeb715882e6a | note | – – – – – – – – – – – – – – – – –
d8213286-dc0f-5443-a7a6-77e18ebfad7e | note | ACCEPTANCE CRITERIA: All cable pits, cable pit lids and preformed cable pit lid surrounds shall be DTP Type Approved.
9efac0ab-01e5-5b04-8e72-d11b763d2474 | textbox | Enter: TeamBinder Material Approval Number
462e7e1d-cf83-5ecb-9d1c-200740749dd0 | note | – – – – – – – – – – – – – – – – –
5f7ca981-9a98-58ff-a5e4-df31330c30a7 | note | METHOD: Document Review
7a2f0364-ee15-5def-a65a-8a7dd1e85f1d | note | – – – – – – – – – – – – – – – – –
c6d72b4b-e33c-59ae-bab1-89bbcd88e62a | note | FREQUENCY: Each Material Type, Where applicable
7db09d1d-52c2-56ad-8b97-36100775be52 | note | – – – – – – – – – – – – – – – – –
9ea60944-2978-58b9-9ddc-30d0ae0ebeb1 | note | CATEGORY: HP
6fd89003-95bd-5876-b61c-304f83f706df | note | – – – – – – – – – – – – – – – – –
7f7d7677-5973-575c-94f2-7e0b2e95f1e0 | note | RESPONSIBILITY: SE/PE, Nominated Authority
d4b22a52-58e5-5232-a812-828fc64471ae | note | – – – – – – – – – – – – – – – – –
425f41de-8809-544e-9f21-cd8e4f1a7c65 | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
867d853c-a70a-5b74-bbda-cc7f12dba91d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Backfill and bedding Material
b97d8a07-f31a-5d09-9ee3-107fe7ae4ffd | note | REFERENCE: VR 733.08 (a)
14f0db89-20da-5c84-a4b6-78d3febf49e5 | note | – – – – – – – – – – – – – – – – –
0eecde09-8e5c-58e9-9f3b-e9a0efcd7732 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, materials used for bedding and backfilling shall be free from perishable matter and shall conform with the appropriate grading and plasticity index requirements specified in Table 733.081
2c5f5224-2b97-5412-a6db-4c7ee0591aed | textbox | Enter: TeamBinder Material Approval Number
fac1d83c-c76e-5475-90f3-848becb085f8 | note | – – – – – – – – – – – – – – – – –
1b77d5e7-4cac-571f-9cb0-4cbbef0314c5 | note | METHOD: Visual, Document Review
10cbd592-93a2-573d-917a-8816e29af597 | note | – – – – – – – – – – – – – – – – –
33dd8b08-eb31-55c1-afcc-5db5ff52fcaf | note | FREQUENCY: Each Material Type, Where applicable
76ff7c71-e48c-5041-9f40-47cb132e0e85 | note | – – – – – – – – – – – – – – – – –
c9cfec48-c1a3-5fad-80c0-fa70ba3d8e67 | note | CATEGORY: IP
f45d1596-cfc9-5cbe-9f4b-756b206b2e4c | note | – – – – – – – – – – – – – – – – –
5b86ecb6-377c-5835-a879-622a46ac361f | note | RESPONSIBILITY: SE/PE, Nominated Authority
c7f00925-129a-5ad8-bd4c-8075d44b1086 | note | – – – – – – – – – – – – – – – – –
77554a61-6a71-52b8-a40d-aa7a4931befa | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
62dcc203-fd00-5f66-968b-72a828cd9d7e | date | Date Completed:
| checkpoint | 2.3 Warning/Marker Tape
21897f67-7165-5430-9bcf-193dc77b5935 | note | REFERENCE: AS/NZ 3000, VR 733.06 (c )
7bcc277d-440f-596f-8cef-e6c29f88ee59 | note | – – – – – – – – – – – – – – – – –
63558dfb-9252-5972-aeb6-647ae8df38a5 | note | ACCEPTANCE CRITERIA: Warning/Marker tapes shall be selected as per wiring rules.
4e09d83c-836a-5755-a960-4a767d5dcc6a | textbox | Enter: TeamBinder Material Approval Number
a9b0e472-7e83-576d-95bd-d1a1c3c93925 | note | – – – – – – – – – – – – – – – – –
1d143ba3-ac61-5c25-b47c-307ea32e0608 | note | METHOD: Visual
634c1d7b-591c-5f23-9fa0-4af490d5bfd5 | note | – – – – – – – – – – – – – – – – –
1954aeac-54e5-5fce-ba2d-7b8a965a5b7e | note | FREQUENCY: Each Material Type, Where applicable
fe20abd0-79bd-5558-a909-de2863f8a63f | note | – – – – – – – – – – – – – – – – –
8965d5b3-db05-5e4d-abf6-16f38464ae1f | note | CATEGORY: HP
00d71f43-e8f5-5e42-9f65-2d5024126f50 | note | – – – – – – – – – – – – – – – – –
7aa85f28-048d-5fc7-9120-47ee07b5ce68 | note | RESPONSIBILITY: SE/PE, Nominated Authority
ba22366e-3d74-5d61-a4fb-7f6e132e5e43 | note | – – – – – – – – – – – – – – – – –
3b667fd3-1f3c-57d0-970a-0f29ceb8d805 | note | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
3e8ad65c-1ca9-558d-a308-205b99de509a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 Draw Wires
fbfd1d28-6e9e-5489-868c-931e58988add | note | REFERENCE: VR 733.07
cd8ae8eb-7b00-5b06-b8fa-9b2169610b7b | note | – – – – – – – – – – – – – – – – –
8141183c-5afe-5b42-ae90-f27b6e448b6e | note | ACCEPTANCE CRITERIA: Each conduit for electrical wiring and communication cables shall be provided with one synthetic draw cord not less than 3 mm diameter and with a minimum breaking strain of 1.6 kN.
3b1ed699-9f7f-5922-8c92-0fe51ee26857 | note | ○ Inspect materials upon delivery and attached delivery dockets.
cbe05451-9990-5563-b388-6a8ad3a5b5e3 | note | – – – – – – – – – – – – – – – – –
653adf29-b321-5e31-975e-3367fef5e34f | note | METHOD: Document Review
2057a2dd-d773-5cda-9425-c6e30c8e5379 | note | – – – – – – – – – – – – – – – – –
3bba8bae-79c8-531d-b74b-c506b51104c6 | note | FREQUENCY: Each Material Type, Where applicable
6bfcd726-ca2a-5ce1-b32f-7ea3310e899c | note | – – – – – – – – – – – – – – – – –
f8d40e2f-0a6d-5536-b304-ab23530a92f0 | note | CATEGORY: IP
70397c1a-9f07-5d7d-8882-547ec228da25 | note | – – – – – – – – – – – – – – – – –
718e5125-0bb0-5ddf-a7f1-3d9d84f3c062 | note | RESPONSIBILITY: SE/PE, Nominated Authority
3a62ec9f-c4ec-56f0-badb-93599d73c43e | note | – – – – – – – – – – – – – – – – –
6366fa71-4201-5e5c-b64f-07025d0eeda9 | note | VERIFYING DOCUMENTS: This ITP
0cfe82e2-dd50-5e6b-af03-e30677eb4104 | date | Date Completed:
| checkpoint | Grout
8b000eaf-bba7-50c3-835f-9c81f5dda809 | note | REFERENCE: VR 733.05
dbb89144-b550-57ec-8440-351cb49ce304 | note | – – – – – – – – – – – – – – – – –
7ccee492-ae7c-5f2e-91d6-c0ad877ec616 | note | ACCEPTANCE CRITERIA: The grout mixture shall be suitable for backfilling around conduits carrying low voltage electrical cables and shall have the following properties:
bda3eb67-c422-53b9-95d4-3ee49fffeec1 | note | – low exothermic temperature generation during curing.
450d623f-42f4-5183-847f-b4cabee8dfff | note | – a thermal resistivity (TR) value of less than 1.2K.m/W when fully dried.
ff2b562c-dcf9-5b08-ba27-c253a3243145 | note | – a maximum grout flow time through a standard flow cone test of 30 seconds in accordance with AS 1478.2.
9ab4e74b-98a3-5b34-b942-25fd424728f2 | note | – compressive strength in the range of 0.5 to 2.0 MPa at 28 days.
1c3aca93-3f64-583a-a962-172a1969a537 | note | – a maximum heat of hydration of 35ºC when tested in an insulated 300mm x 300mm cube
d6d47f9e-102f-55df-8779-488bf965ed81 | textbox | Enter: TeamBinder Material Approval Number
eb47915e-08a4-5df0-a2e6-9821ad63a289 | note | – – – – – – – – – – – – – – – – –
45b1a764-72b0-512b-85ac-6fa56d6035ed | note | METHOD: Document Review
405e8bfc-5615-53fa-9876-e15c02358f98 | note | – – – – – – – – – – – – – – – – –
116864fc-8078-5b0f-8d61-9564fad0979c | note | FREQUENCY: Each Material Type, Where applicable
80a35917-4c47-5971-bf15-3428fcb6cb37 | note | – – – – – – – – – – – – – – – – –
2648f7f2-4425-58d5-8ad5-025cdc31343a | note | CATEGORY: IP
3d2284f7-fb54-5f04-9e2a-2b6e22601c59 | note | – – – – – – – – – – – – – – – – –
e6a01001-80f6-56e1-a351-bcdabea57194 | note | RESPONSIBILITY: SE/PE, Nominated Authority
943de11f-88b4-5dd4-8859-bf2ddf4f53a5 | note | – – – – – – – – – – – – – – – – –
472cfbe3-0370-5c8e-a033-185651a6d33c | textbox | VERIFYING DOCUMENTS: Enter: TeamBinder Material Approval Number
601ff8ad-af31-53e1-922a-c57900687abf | date | Date Completed:
| section | Prelimnaries - Procedures & Documentation
| checkpoint | 3.2 Prequalified Contractor
6f2217f0-def3-5005-82a4-4b49532b2545 | note | REFERENCE: VR 733.01 (c), VR 733.02 and table VR 733.021
3f26d78d-9faa-541c-8e07-6e7812e1c84e | note | – – – – – – – – – – – – – – – – –
cf97ea78-dc6d-502f-bad2-d993a054ae42 | note | ACCEPTANCE CRITERIA: All works associated with the installation and of all conduits and pits covered under this specification shall be undertaken by contractors that are appropriately pre-qualified as detailed in Table 733.021
4b81da9e-3a78-5c7d-b0cd-1189304d06eb | note | ○ Electrical conduits, and associated cable pits, installed as part of an electrical installation MUST be installed by, or under the direct supervision of a Pre-qualified and Registered Electrical Contractor.
0f6682a5-587b-54e1-8fb2-f146f579d588 | note | Attach: contractor qualifications
2720376c-97e7-532b-9d42-35bf1050299b | note | – – – – – – – – – – – – – – – – –
a51f2a95-d97f-52f3-8617-63129a965834 | note | METHOD: Document Review
82b9a8b5-92cd-556c-9ad1-9835a4929ba2 | note | – – – – – – – – – – – – – – – – –
6ce355f2-e4a8-54ec-a248-007aba8182ec | note | FREQUENCY: Prior to commencement of works
bc589089-0001-57e0-8c5e-729ab28df9e3 | note | – – – – – – – – – – – – – – – – –
0858ee38-0d3f-5365-a772-988914045db7 | note | CATEGORY: HP
53a27f34-5667-5fc4-94c7-b51a5dff3ab9 | note | – – – – – – – – – – – – – – – – –
b390f027-ea9a-57aa-be80-2313add965d4 | note | RESPONSIBILITY: SE/Site Supervisor
e869a677-e96a-5600-9866-356ccd1a973b | note | – – – – – – – – – – – – – – – – –
8c780c38-5ec1-5b67-9847-9a74e77373df | note | VERIFYING DOCUMENTS: This ITP
21f147c2-3cee-56a0-b25e-40128d325c38 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Boring
e934aa68-6033-57b6-acb9-ddab6b2b2784 | note | REFERENCE: VR 733.05
0d2cd46e-5571-50c7-8ac5-2874390e8e8b | note | – – – – – – – – – – – – – – – – –
ae084a2a-55da-5482-af8c-c4cf8e27887b | note | ACCEPTANCE CRITERIA: Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
81a93511-b27b-5949-8e4c-e8f0a96d2442 | textbox | Enter: Team Binder Approval number
b8068004-377f-5a49-a4e3-c7f65cc5540f | note | – – – – – – – – – – – – – – – – –
41fbcd4b-353d-5f68-888a-26a6eb8c5215 | note | METHOD: Document Review
9a9ba4ae-3d77-58ca-8c0b-ec9d2e8f7252 | note | – – – – – – – – – – – – – – – – –
f2798dbe-b097-5f02-911d-63b73c14101f | note | FREQUENCY: Prior to commencement of works
d21f9312-e092-5aad-b083-2f300d5339fa | note | – – – – – – – – – – – – – – – – –
5f01e9b2-0f14-5810-af70-359ce194125e | note | CATEGORY: HP
647a7320-d6d1-5280-bea9-2af4c3a6a5bc | note | – – – – – – – – – – – – – – – – –
f15c7e5f-26fa-53f1-9106-060d7f10f973 | note | RESPONSIBILITY: SE/Site Supervisor
d4de9fd7-4eee-57fd-b12d-90488159d2e6 | note | – – – – – – – – – – – – – – – – –
9ee708b7-b481-5a2a-80eb-3267fd4a735f | note | VERIFYING DOCUMENTS: This ITP
565d4e12-d3be-55bb-bf25-672633eab434 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set-out
8dc33d62-546d-5c1c-b1c7-04923a872a65 | note | REFERENCE: IFC Drawings
5a4ff8f1-a8b9-5a09-b3ea-b30fd8723dde | note | – – – – – – – – – – – – – – – – –
a3ae3eff-f2dd-58f4-8ad9-42a182e1274f | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
1129e81e-da25-5fbb-aea7-764d10d76531 | note | – – – – – – – – – – – – – – – – –
9d8e68f8-777b-5cdc-8611-554ec924862e | note | METHOD: Measure, Visual
51405575-f2bf-5812-9d5e-d5b890b172f9 | note | – – – – – – – – – – – – – – – – –
acec13db-c575-5bef-b4b3-3abecb20226a | note | FREQUENCY: Prior to commencement of works
35776b6c-0702-5138-9049-828d4c84fd2d | note | – – – – – – – – – – – – – – – – –
aa253c35-3846-5399-8069-5a389df0a8c4 | note | CATEGORY: IP
0e832342-8b8e-5f53-81cd-5d2d2c62dad4 | note | – – – – – – – – – – – – – – – – –
b8943ad3-addc-509c-ba44-856342144880 | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
2928e19a-88ce-57ed-ab32-e99c9e85cf6c | note | – – – – – – – – – – – – – – – – –
b2126c68-8c32-550d-bfb8-c4af6d57ab25 | note | VERIFYING DOCUMENTS: This ITP
24cf5c67-9b83-503e-930f-2206850726d0 | date | Date Completed:
| checkpoint | 4.2 IFC Drawings
9e1a5819-beaf-502d-88d0-76878b1fdaf8 | note | REFERENCE: IFC Drawings
bcf8c931-25dd-5b2d-af8b-658425461fc0 | note | – – – – – – – – – – – – – – – – –
55e70d5b-1996-56d4-836e-1635ea886907 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b63ae0dc-2e36-501e-8827-e58058f37d38 | note | – – – – – – – – – – – – – – – – –
1bbaacd8-51cd-5e31-875e-ff71ccda6d4f | note | METHOD: Document Review
d0440bd2-be54-5759-b7fb-9d7a8498f765 | note | – – – – – – – – – – – – – – – – –
a8f9fd3e-9eb6-5ee9-8543-f525372de123 | note | FREQUENCY: Prior to commencement of works and at regualr intervals
ac77d0cf-82bc-559c-826e-d5e7ca30c352 | note | – – – – – – – – – – – – – – – – –
e073920d-a876-53bf-ab53-c3e79fc17bb8 | note | CATEGORY: IP
81078b7a-a8ba-5141-98b8-674c0d755e20 | note | – – – – – – – – – – – – – – – – –
56bfab39-025c-562f-8017-57c0c6cd3474 | note | RESPONSIBILITY: SE/Site Supervisor
4d0e944a-e04a-51b0-9f72-d645659b0f9b | note | – – – – – – – – – – – – – – – – –
dea52193-a8a5-56a3-94b7-12bb694f37ae | note | VERIFYING DOCUMENTS: This ITP
661b0836-1840-5e2d-b0db-a4deba48491a | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Trench/Bore-Depth
2a09e167-7535-5239-87d5-0188b4535668 | note | REFERENCE: VR 733.05
acfa7bbb-ca57-5b7a-9ee8-cda5094edf21 | note | – – – – – – – – – – – – – – – – –
b566221b-4d33-57da-a293-078b1c0fa529 | note | ACCEPTANCE CRITERIA: Unless otherwise shown on the drawings or specified, borings and trenches shall comply with the depth requirements specified in Table 733.051.
239a919a-d824-558d-8bc8-f6f20a965301 | note | – – – – – – – – – – – – – – – – –
bf306a43-77df-5d1e-a250-ba12c03b24bd | note | METHOD: Measure, Visual
9a2b8156-486f-5a80-a2fe-1cb123143610 | note | – – – – – – – – – – – – – – – – –
608337cd-2b26-5c05-af37-7d5ba3defcd2 | note | FREQUENCY: Each lot
82edd46e-8315-5725-8381-e6c5c537b5b0 | note | – – – – – – – – – – – – – – – – –
1256a5f5-cab2-5d2c-a2e6-b584fff36f79 | note | CATEGORY: IP
65bad271-825b-5d09-9ec1-af6da3dcf67a | note | – – – – – – – – – – – – – – – – –
b64f104f-2dda-54ba-88fc-1d229835731b | note | RESPONSIBILITY: SE/Site Supervisor
bf667387-380b-5cf3-9c6b-ef430f3e5a9f | note | – – – – – – – – – – – – – – – – –
d50d4c18-cda7-52c8-93c8-35082a106314 | note | VERIFYING DOCUMENTS: This ITP
6859ebd1-34d5-5540-8c6e-821620188b06 | date | Date Completed:
| checkpoint | Trench excavation-Grade
0ae7bd71-90e0-55e3-921e-fcde8f1706a1 | note | REFERENCE: VR 733.05
b16301b8-ec7c-5b67-be88-625badb69e3a | note | – – – – – – – – – – – – – – – – –
da20aa8b-713e-5ba4-937b-5727c189a5d8 | note | ACCEPTANCE CRITERIA: Trench/conduit depth shall be maintained between pits and graded to avoid low points in the conduit run
e526942b-b510-5833-9cf2-6cf2650d1f86 | note | – – – – – – – – – – – – – – – – –
7b034a86-932d-524c-8cf7-51be9d0d3ae3 | note | FREQUENCY: Each lot
be890b96-c7bd-5c12-afbd-e62e9a9b6eb4 | note | – – – – – – – – – – – – – – – – –
67c530d8-2956-5bfb-937b-df19d0fa8a98 | note | VERIFYING DOCUMENTS: This ITP
7b65ceb7-ae7e-546a-8115-101b8490695a | date | Date Completed:
| checkpoint | 5.3 Placement of Bedding Sand for Conduits
b8466edc-b8a4-54bd-a075-3937f623c9e7 | note | REFERENCE: VR 733.08 (b) (i)
0f1322ea-e052-561b-ba07-53d0540638bc | note | – – – – – – – – – – – – – – – – –
070f8964-f207-5adf-a799-ede5e608fae8 | note | ACCEPTANCE CRITERIA: Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation. Following compaction, the bedding material shall be shaped sufficiently to maintain the conduit in line as the sections are placed in position. Shaping of bedding material is not required for conduits less than 100 mm nominal diameter.
6c283321-c1c2-59b7-ae66-a44a1819c909 | note | – – – – – – – – – – – – – – – – –
0a1ba7bd-05af-5561-aa45-e66642102e8c | note | METHOD: Measure, Visual
2c09facd-6cdf-525b-8361-4a86275640f6 | note | – – – – – – – – – – – – – – – – –
2094a141-6fa1-5260-9acf-1dd736644f2f | note | FREQUENCY: Each lot
eac50ae6-244b-5f67-b5ef-4618e441ea32 | note | – – – – – – – – – – – – – – – – –
fb93b89b-769b-50d4-a479-6036390e49a4 | note | CATEGORY: IP
d88b78cb-5979-5630-9847-a8b302c2b095 | note | – – – – – – – – – – – – – – – – –
e55abe8d-0d96-5f61-891f-0d793354e40f | note | RESPONSIBILITY: SE/Site Supervisor
5335ef58-f6bc-5fb6-8eb6-dd57abba8789 | note | – – – – – – – – – – – – – – – – –
f60a6cdf-49a8-5b6b-b062-ccfda74c099f | note | VERIFYING DOCUMENTS: This ITP
77b751ce-4c88-57d6-a496-4ab9b39d1a95 | date | Date Completed:
| checkpoint | 5.4 Conduit Placement & Configuration
1e11fa3e-1ddc-5a72-9449-d068325b19d0 | note | REFERENCE: VR 733.06 (a)
e22fdd3c-ac4a-5ee9-8256-a9aae5ea2d3b | note | – – – – – – – – – – – – – – – – –
af250e16-bbc7-5d78-98b2-f288b88725a8 | note | ACCEPTANCE CRITERIA: Conduits installed for DTP works shall be installed to the following requirements:
f8999134-1604-5a3f-a638-24b8c9806aca | note | (i) all conduits shall terminate in a pit.
f77886d6-6762-518d-83c2-0fcf6f828dbb | note | (ii) only one size and type of conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
0a64cac4-f46c-5c9b-8055-5584789e00b7 | note | (iii) all conduits shall be temporarily sealed prior to cabling to avoid blockage.
afba6e7b-947e-5965-a6e6-fbd2a0538f77 | note | (iv) changes in direction of conduit shall only be made at approved cable pits.
5652f1f2-33c8-5826-9298-4c3d9fb0df25 | note | (v) changes in conduit direction to enable entry into the base of a cable pit may be by means of a sweep bend:
e3c5521c-4de0-5b59-9dd8-4838f7dd4d4f | note | ○ Minimum Bend Radius for Electrical UPVC: 600mm
de8fed03-126e-5251-98b2-e765f9ad464c | note | ○ Minimum Bend Radius for Communications UPVC: 500mm
e2a6176b-2720-57f6-9168-ebe1762b5afa | note | (vi) elbows and ‘tees’ shall not be used.
ed1d5b34-ca64-5fcf-8e6a-e50b4f8b7b68 | note | (vii) all conduit joints shall be correctly prepared and sealed with approved solvent cement.
de634781-a4ee-50da-9eb2-3ade834ad24e | note | (viii) conduits for detector cables shall be installed as shown in Standard Drawings TC 1207 and TC 1320.
9c276453-d25b-514a-87da-46c810c71069 | note | (ix) a 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in Standard Drawing TC 1207.
36f5b843-12a4-50f9-a331-8ba87701914d | note | – – – – – – – – – – – – – – – – –
7a226f49-1d41-5284-8ed5-861ce2fb9da4 | note | METHOD: Visual
1019fe13-0c91-5dfb-a239-0184379b8e9e | note | – – – – – – – – – – – – – – – – –
b1d13af5-4d5f-5aac-a69e-7d1d4f2bb9ce | note | FREQUENCY: Each lot
24c944df-5033-57b0-a749-871324b49a9e | note | – – – – – – – – – – – – – – – – –
54f88f90-fc3e-50b7-b274-0f52d6d9ca21 | note | CATEGORY: IP
7dae0fe6-5011-504b-9687-97ab7a126e30 | note | – – – – – – – – – – – – – – – – –
a4ebf9b3-bf03-5aa3-92e7-87439eea0c5d | note | RESPONSIBILITY: SE/Site Supervisor
54c12218-1ad6-5852-b5ae-77f70f2ac78e | note | – – – – – – – – – – – – – – – – –
fb79ecd7-8a93-53aa-96c5-7b9f131bebcf | note | VERIFYING DOCUMENTS: This ITP
7cdd954c-6ae9-54fd-9a1b-b9506bb5b962 | date | Date Completed:
| checkpoint | Conduits Installation
0c56b87f-2533-536d-9404-985ffe0c245e | note | REFERENCE: VR 733.06 (b) (c )
ace3d6fc-ef1e-53b2-b8ad-3ca780d19b45 | note | – – – – – – – – – – – – – – – – –
5225146b-21ed-5ce1-99b6-020de655b4d4 | note | ACCEPTANCE CRITERIA: Conduits installed for traffic signals and other on-road electrical installations shall be installed in accordance with this standard specification, DTP Standard Drawings detailed in Table 733.032 and individual contract documents.
f1832c13-82dc-5c13-9f95-7a1e8250af3a | note | ○ Conduits installed on Managed Motorways and freeways shall be installed in accordance with this standard specification, DTP Standard Drawings detailed in Table 733.033 and individual contract documents.
e8998a5f-ce7c-55b3-ae79-b35464cdf6d0 | note | – – – – – – – – – – – – – – – – –
d03ecb49-8e43-5c72-9481-235c1e0e7eed | note | METHOD: Document Review, Visual
d719e06a-6c2e-5220-8d9b-31790c2e6cdf | note | – – – – – – – – – – – – – – – – –
2d7fb542-f6a3-5e35-9479-22c851539215 | note | FREQUENCY: Each lot
94c93470-f069-5ccd-8ba5-9c183bd1237b | note | – – – – – – – – – – – – – – – – –
f3259758-3fc7-5a2d-a8b4-a89dc277b25c | note | CATEGORY: IP
ad52330a-42d0-5c2a-8cf3-304bfb76a1ec | note | – – – – – – – – – – – – – – – – –
b9a633d3-8b33-55f6-a0ee-a8fc1bd3b16c | note | RESPONSIBILITY: SE/Site Supervisor
aa70ae33-40da-5450-a091-e0efe028bcec | note | – – – – – – – – – – – – – – – – –
4277732f-7722-5a44-bae6-8424adacbf41 | note | VERIFYING DOCUMENTS: This ITP
3cbebb06-8103-56d4-89d5-dfeb139cf1fa | date | Date Completed:
| checkpoint | Conduits installation-Inspection
cbd58a4c-4f69-5485-b423-896bfbf0f486 | note | REFERENCE: VR 733.08 (b)
b67a5522-b283-561b-9bf6-976e4a24ea84 | note | – – – – – – – – – – – – – – – – –
cfde4ffb-3e40-5a8a-915b-933a2fc87ec7 | note | ACCEPTANCE CRITERIA: Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
46e97fad-7c43-5ce0-8b72-87969e3dfddd | note | – – – – – – – – – – – – – – – – –
6a1d61ab-d65d-5f88-b50e-87b4abc5d6eb | note | METHOD: Visual
11fae83b-4e57-561b-99ff-aa8618b79970 | note | – – – – – – – – – – – – – – – – –
e52541f3-d23a-5b3f-a147-ecf536b9e0e8 | note | FREQUENCY: Each lot
77e7ef0c-65d6-5f78-a184-3bb329d4a568 | note | – – – – – – – – – – – – – – – – –
658c683f-131e-580a-bd88-8b0474b35f43 | note | CATEGORY: HP
a63a91b3-86b7-58be-9301-5a76448d3c60 | note | – – – – – – – – – – – – – – – – –
43c80fd3-647f-5791-ae1d-3559324e0696 | note | RESPONSIBILITY: PE/Nominated Authority
f5f2a4ef-cf21-5571-9d14-2451a3238ab1 | note | – – – – – – – – – – – – – – – – –
9a049737-a865-5521-846f-3c93d63b7fb2 | note | VERIFYING DOCUMENTS: This ITP
18096f9e-2d17-5ce6-9e30-24877c6adc76 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Backfilling Bore access
ebd7d9f1-916a-512b-b232-9aff9b761263 | note | REFERENCE: VR 733.05
fed36192-b2cd-5424-85f4-a6e9c53bec8a | note | – – – – – – – – – – – – – – – – –
7b0e3732-7b59-507d-b687-d46b84eb135d | note | ACCEPTANCE CRITERIA: before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
36995a6b-3af6-5cb2-941f-9ffbb468b71c | note | – – – – – – – – – – – – – – – – –
791838e1-911f-59bc-aa39-88302ee9d39a | note | METHOD: Vicual
83b5bfbe-b975-54d3-9907-43716030c2bb | note | – – – – – – – – – – – – – – – – –
1fd07e1f-3184-53ee-9387-bc959637846c | note | FREQUENCY: Each lot where applcable
b3389cab-82c1-5d08-b340-6ab6995562d1 | note | – – – – – – – – – – – – – – – – –
8df1ef62-cf6a-5b7b-aa71-c5a6c043e880 | note | CATEGORY: HP
7f90a4c6-207c-525a-baa6-ffb3965f287d | note | – – – – – – – – – – – – – – – – –
20e5b300-86f1-5d1b-a606-bf34eefbd5e9 | note | RESPONSIBILITY: PE/Nominated Authority
faafa0cb-3369-5e99-93d4-c99e2cee1767 | note | – – – – – – – – – – – – – – – – –
953c1af4-d724-585c-add0-4975744c055f | note | VERIFYING DOCUMENTS: This ITP
c75661ba-c00f-5834-af79-5c84bec4920f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Backfilling
187ef5d7-9e41-5807-b55f-16e77a20841c | note | REFERENCE: IFC Drawings, VR 733.08 (b) (c)
1ab3da45-a814-594b-b62c-a02f337760e5 | note | – – – – – – – – – – – – – – – – –
88002873-ce46-5034-8653-f36b8629584e | note | ACCEPTANCE CRITERIA: When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
4d2c4a1e-522b-55e9-8eb5-7f8c5f7ed7ae | note | ○ Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded.
d926bbc3-618e-50b2-b380-cc0ec4d6433d | note | – – – – – – – – – – – – – – – – –
ab6f5b79-056c-5afb-aee7-927b1d2ec32b | note | METHOD: Visual
f54ef7eb-dbf2-55f9-a948-2df03dc7cb2f | note | – – – – – – – – – – – – – – – – –
c07b3492-7849-562b-8b02-9794add22bef | note | FREQUENCY: Each lot
c5c374fe-4c89-5a6f-821a-37c4006d1307 | note | – – – – – – – – – – – – – – – – –
8d553f44-e14f-51c3-a225-2a44278d9179 | note | CATEGORY: IP
fd662493-5927-5ce9-b09d-4588444830e6 | note | – – – – – – – – – – – – – – – – –
720267bd-37b8-5cd0-87eb-d219d3d73040 | note | RESPONSIBILITY: SE/Site Supervisor
e49635df-376a-56e5-aa9b-1c1567ca4ffc | note | – – – – – – – – – – – – – – – – –
6c9044e4-0582-5413-9b06-e31b52bd05c3 | note | VERIFYING DOCUMENTS: This ITP
b4b94392-85b8-5e29-a6cb-c4557b356f17 | date | Date Completed:
| checkpoint | 5.9 Marker Tape
91306e88-5e78-5712-9bd2-3699c59b14d0 | note | REFERENCE: VR 733.06 (a), AS/NZS 3000
067e1f8d-166e-5b58-bd5d-799902ef031b | note | – – – – – – – – – – – – – – – – –
ea8e7095-e43d-5d3e-9a1d-6b94e77bc150 | note | ACCEPTANCE CRITERIA: A marker tape with trace wire shall be placed above all conduits in accordance with the Wiring Rules.
cdf74c0d-0484-5c26-b0f3-284a2509e37a | note | – – – – – – – – – – – – – – – – –
a05ec629-2cf1-51cc-9ba0-5954761fc767 | note | METHOD: Visual
e94285f6-131f-5ce4-873c-0d3566deefec | note | – – – – – – – – – – – – – – – – –
eefbdd37-715b-5621-8536-39d8479715fd | note | FREQUENCY: Each lot
7f860185-c65b-5479-a9da-e2826cc816af | note | – – – – – – – – – – – – – – – – –
9a7b12eb-fc52-5720-9915-42534a5d079d | note | CATEGORY: HP*
3ef42f87-d33c-5eaa-bd8a-b0c13c3baff6 | note | – – – – – – – – – – – – – – – – –
1484a7e9-bd6a-5005-b0d1-511c8e895e1e | note | RESPONSIBILITY: SE/PE
5b260139-a79d-59c4-922a-f6f1a9ad12d8 | note | – – – – – – – – – – – – – – – – –
84596a8f-90a8-5ef4-9260-6f5a889f987f | note | VERIFYING DOCUMENTS: This ITP
46c9a602-085d-504d-b1b0-b6e858615445 | date | Date Completed:
| checkpoint | Backfilling-Compaction
67592f48-2a67-57ac-a368-8816b8f9fda8 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, bedding and backfill materials shall have during compaction, a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard Compaction test.
4e85a251-faab-516b-a8ea-cd0eaeb29bfb | note | ○ Bedding and backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted in layers to a density ratio of not less than 95%.
e6bd26a0-681f-5601-a35c-bc129d17b823 | note | Attach: compaction test results
eb6c2514-8822-5702-90bc-595ce91a08f0 | note | – – – – – – – – – – – – – – – – –
82486b74-c3a4-5366-994f-9e5b4e7e4582 | note | METHOD: Measure
01331ca3-aa39-5c0a-bb71-dfca436e6f03 | note | – – – – – – – – – – – – – – – – –
8720a0b3-0647-5aa3-b3b5-b7e4adacafe0 | note | FREQUENCY: Each day production
ecac7479-7603-55c7-8483-8ab64db88cd2 | note | – – – – – – – – – – – – – – – – –
2cf64720-c0f7-5b47-8473-908f6903c44b | note | CATEGORY: HP*
b1d57a35-4d71-5ba1-b2e1-1a938dffe6f3 | note | – – – – – – – – – – – – – – – – –
b93592fc-0334-5221-9894-07b640b2b1aa | note | RESPONSIBILITY: SE/Site Supervisor
68f3e01d-5555-53ab-a9c0-d45029673a7c | note | – – – – – – – – – – – – – – – – –
b5c55c24-dffa-5182-82c7-295dec461b71 | note | VERIFYING DOCUMENTS: This ITP/Daily compaction test results
4a038404-4c3a-58fe-8a7c-f53ed4fb64cc | date | Date Completed:
| checkpoint | Pits and lids installation-Cable pits-Traffic signals and general works
16a16138-3f57-55b0-a965-f0c58f5cb98c | note | REFERENCE: VR 733.09 (d)
970a4351-3205-5300-8129-7ab424c928f3 | note | – – – – – – – – – – – – – – – – –
06c6a151-a1b8-5b2c-8955-87aae2ebbba4 | note | ACCEPTANCE CRITERIA: Cable Pits and Lids for Traffic Signals and other on-road electrical shall be constructed and installed as shown in the drawings detailed in Table 733.091
19da3a1b-77f7-5f7e-89a0-2c8b0e3a311e | note | – – – – – – – – – – – – – – – – –
ce550675-ce51-5862-8948-22c655693930 | note | METHOD: Document review, Visual
0ae28342-614a-5b17-8d08-937842ce4375 | note | – – – – – – – – – – – – – – – – –
85cf9c9b-feef-5347-870a-250498a3227a | note | FREQUENCY: Each pit
b6c1c4cb-3322-5b27-ab7f-491ea4cc6c20 | note | – – – – – – – – – – – – – – – – –
b13e88ec-5f72-5b04-837d-78d673082b03 | note | CATEGORY: IP
04c80417-758d-59ff-8fc4-c6c36d213ad7 | note | – – – – – – – – – – – – – – – – –
1d96fc81-3c3f-59cc-8737-3ac8a69a29d1 | note | RESPONSIBILITY: SE/Site Supervisor
1fc47aa4-2378-5ab1-afe9-6edf67b725f6 | note | – – – – – – – – – – – – – – – – –
dcb381d9-79b1-5e18-b575-4d55b4b80c92 | note | VERIFYING DOCUMENTS: This ITP
884441bf-0d7b-516a-b663-13f8f22150d5 | date | Date Completed:
| checkpoint | Pits and lids installation-Cable pits-Managed Motorways and freeways
baf138a3-f8bb-5ed5-8d89-0e7f547c49d5 | note | REFERENCE: VR 733.09 (e )
3f932686-37da-5963-9e1f-c4da58d6c677 | note | – – – – – – – – – – – – – – – – –
89796a71-90bd-5e9e-a5f8-8a6affdc75b5 | note | ACCEPTANCE CRITERIA: Cable Pits and Lids for Managed Motorways and freewaysshall be constructed and installed as shown in the drawings detailed in Table 733.092.
49e73349-d5a6-5d9b-b1f5-5ece148626fc | note | – – – – – – – – – – – – – – – – –
8c6a2735-dde3-5d94-9ab5-4ca6cf15474c | note | METHOD: Document review, Visual
44c6b4d3-fc45-5683-bfbc-b991f2edde44 | note | – – – – – – – – – – – – – – – – –
5b5540e6-2e85-57d8-b67f-a9b274fff7f3 | note | FREQUENCY: Each pit
a961d2b6-1af5-5cb8-a593-a8ad6aab2fce | note | – – – – – – – – – – – – – – – – –
641b144b-e090-57c2-ba4e-abb55aec4d9f | note | CATEGORY: IP
5cbe37e7-602d-5dbb-af5e-bf4e70472e20 | note | – – – – – – – – – – – – – – – – –
fd9351d4-3e3b-5ed3-a5ae-9822648a18f8 | note | RESPONSIBILITY: SE/Site Supervisor
f9a4ad8e-d8b1-5806-b2ae-4a0ded7ff452 | note | – – – – – – – – – – – – – – – – –
f4a8e396-8379-58cb-a2b7-243727403f36 | note | VERIFYING DOCUMENTS: This ITP
6daa693a-4023-565f-ace9-e60423694f89 | date | Date Completed:
| checkpoint | Communication Pits for Managed Motorways and freeways
a2e4a718-ff6a-51cd-9b06-ef73dd89d16f | note | REFERENCE: VR 733.09 (f)
d5b0f9ef-720c-5a91-a8c1-7d6c3d964f18 | note | – – – – – – – – – – – – – – – – –
9bf44293-e958-54bd-a15f-17a9b6d591bc | note | ACCEPTANCE CRITERIA: Communications pits shall be constructed and installed as shown in the drawings detailed in Table 733.093
a7825463-4f53-56b7-98a6-22d29e96f955 | note | – – – – – – – – – – – – – – – – –
1ee0f33d-522e-5814-99b5-02b1897ba246 | note | METHOD: Document review, Visual
31416a50-ae7b-5a35-8650-8438633a79a1 | note | – – – – – – – – – – – – – – – – –
53f410a0-97d1-5e75-8f61-1ef7b7ad71b0 | note | FREQUENCY: Each pit
762383d7-b237-5f99-bf16-58900d61675b | note | – – – – – – – – – – – – – – – – –
d36d2085-70b1-5073-82a6-9bf894b638f9 | note | CATEGORY: IP
69412714-b2fb-5cb0-b1c0-97a470a27832 | note | – – – – – – – – – – – – – – – – –
1056f4c6-9171-502f-9475-62d9061e0e34 | note | RESPONSIBILITY: SE/Site Supervisor
86aa5c31-95cd-57f5-92d4-1f870d3885f4 | note | – – – – – – – – – – – – – – – – –
1cb9d505-240a-5bbf-be4e-2cee0846575f | note | VERIFYING DOCUMENTS: This ITP
6aa9eea3-640e-51cc-80a5-2bdc331ba8e1 | date | Date Completed:
| checkpoint | Communication Pits for Arterial Roads
bc7e16ba-c48a-5774-8480-875a507c81fd | note | REFERENCE: VR 733.09 (g)
7e10532d-d24a-5609-b8e6-a335e2c0f606 | note | – – – – – – – – – – – – – – – – –
6229002c-ed2b-5d1e-9567-48648215fdb9 | note | ACCEPTANCE CRITERIA: Communications pits shall be constructed and installed as shown in the drawings detailed in Table 733.094
edcfbc86-fcd7-5e16-b1da-fb102401f709 | note | – – – – – – – – – – – – – – – – –
8f61825b-9205-5756-acd8-3da4461f3882 | note | METHOD: Document review, Visual
31a863a8-cafa-55db-9cee-f705df287909 | note | – – – – – – – – – – – – – – – – –
56d44edb-9bbd-5478-8796-3a5b8daa790a | note | FREQUENCY: Each pit
41d240d7-043e-5030-b4ed-33c6d54dec4b | note | – – – – – – – – – – – – – – – – –
6246dbd9-ec5f-57f8-87ef-47a74158e4dc | note | CATEGORY: IP
1bc119eb-4629-50fe-808b-72ba1c0f575e | note | – – – – – – – – – – – – – – – – –
22f6024c-02c0-51b7-9888-9187bc1544df | note | RESPONSIBILITY: SE/Site Supervisor
744e8b06-36ae-5993-9d35-321e14f69a5b | note | – – – – – – – – – – – – – – – – –
b0170ca4-c91a-566e-897b-679fea051cbd | note | VERIFYING DOCUMENTS: This ITP
b31ee304-cce4-5fb7-87b6-38d26d0374b7 | date | Date Completed:
| checkpoint | Detector Pits
b592b0c6-3930-53f2-94c3-8a12ba606e1f | note | REFERENCE: VR 733.10
b8673311-2543-5df6-8ebb-a2b69d89d259 | note | – – – – – – – – – – – – – – – – –
dc686034-698e-5261-ac15-dc7d8786f6a6 | note | ACCEPTANCE CRITERIA: Detector pits for traffic signals shall be installed as shown on the traffic signal plans and as detailed in individual contract documents.
416d5a3c-f037-53df-b677-f04822156f76 | note | ○ Detector pits for freeway data stations or other required purposes shall be installed as detailed in individual contract documents.
32a503d9-6269-5838-8a1a-0057bf4da7b6 | note | ○ Detector pits and detector pit covers shall be constructed and installed in accordance with Standard Drawings TC 1310 and TC 1320.
327bf077-1595-5df1-885c-846992f079f5 | note | – – – – – – – – – – – – – – – – –
83e0d5bb-2ae5-5662-9c7c-e529775b28fb | note | METHOD: Document review, Visual
96416b27-60e0-5447-b772-08d226615579 | note | – – – – – – – – – – – – – – – – –
4a133237-00f5-520a-8c8d-ecd00cba6cd6 | note | FREQUENCY: Each pit
2ddcb175-0e90-568a-9382-d1273cc07141 | note | – – – – – – – – – – – – – – – – –
42f3e844-6fd1-543a-b48f-b47cc0822c17 | note | CATEGORY: IP
3d01646b-78e4-543f-88d5-a7449d05956f | note | – – – – – – – – – – – – – – – – –
30d33038-40ec-5626-8132-8638745a7015 | note | RESPONSIBILITY: SE/Site Supervisor
82bb272e-41ee-5b43-afec-f3c55cdd6d11 | note | – – – – – – – – – – – – – – – – –
70ca66a7-1768-5510-b070-475a4eb34c10 | note | VERIFYING DOCUMENTS: This ITP
08c0dce8-6e20-5777-9340-653cfaa15b41 | date | Date Completed:
| checkpoint | 5.5 Conduits connection to pits
742448fd-462c-5f6f-8b42-402ee7b823a4 | note | REFERENCE: VR 733.09 (a)
5cab0879-af5d-5be1-b5c3-f41a5fe8c8f6 | note | – – – – – – – – – – – – – – – – –
7e4223d0-5ebd-5677-b619-fe26fae66bfd | note | ACCEPTANCE CRITERIA: All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and deburred to prevent damage to cables. Pits installed for Managed Motorway installations shall also be fitted with a conduit bush. The area between the conduit and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
2d80921a-6573-5cb4-87ae-163953191d27 | note | – – – – – – – – – – – – – – – – –
4fd06925-40b5-51fe-a008-10eed6d2f336 | note | METHOD: Measure, Visual
ce02630d-dc71-5359-ae65-8e0d9d0ead0f | note | – – – – – – – – – – – – – – – – –
6c5b4b8b-aa58-586d-925f-2361237864ef | note | FREQUENCY: Each pit
d6d44ca8-f623-5ad3-9830-38ccadf70e10 | note | – – – – – – – – – – – – – – – – –
1e834988-8e4e-5551-87a9-2396422a6ed5 | note | CATEGORY: IP
38e916c8-ad54-5bc3-a978-3c2ec414f2ad | note | – – – – – – – – – – – – – – – – –
61017a3b-0e56-55e5-abbc-111f48e7cf4e | note | RESPONSIBILITY: SE/Site Supervisor
f040735a-75f7-5574-91ed-b6504a22328e | note | – – – – – – – – – – – – – – – – –
09b90ad5-b2c6-5ab4-9123-3ec245533bc3 | note | VERIFYING DOCUMENTS: This ITP
b88630a9-29fb-5ec6-b1d5-9156e453683a | date | Date Completed:
| checkpoint | 5.7 Pit installation-Inspection
11d99804-293a-5324-8a7c-61a1b1a9589f | note | ACCEPTANCE CRITERIA: Before the pit lid surround or pre-formed collar is cemented into position an inspection by the superintendent or representative must be carried out.
4826ea61-b69d-52d0-9515-48aaa60f5321 | note | – – – – – – – – – – – – – – – – –
098bd1f1-d815-521f-8e73-e4733decfc5f | note | METHOD: Visual
1423d525-1d89-50e1-ad0f-c3b40bb58aa9 | note | – – – – – – – – – – – – – – – – –
d29426bf-276a-5200-b071-69ed3fbd8917 | note | FREQUENCY: Each lot
19495549-b585-5c2c-a283-68834ee32c69 | note | – – – – – – – – – – – – – – – – –
ededd827-c29f-5c79-bb62-6e227b13ea22 | note | CATEGORY: HP
c2a1769e-684c-5c43-9116-753e10681562 | note | – – – – – – – – – – – – – – – – –
8ae2b573-8281-5473-a1e3-6d058ad7c68b | note | RESPONSIBILITY: Nominated Authority
94967705-d25f-5b55-a89c-153ecf0e390b | note | – – – – – – – – – – – – – – – – –
3c8f7d43-e6e3-5e07-b208-4770dd1e85f6 | note | VERIFYING DOCUMENTS: This Itp
67b5418b-7d40-5269-b449-5deb94c24cbe | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 Identification
778c1a57-f059-5a3c-8254-ff895fb7b7bf | note | REFERENCE: VR 733.12
c23039d1-3449-5953-a803-a7e236f4a150 | note | – – – – – – – – – – – – – – – – –
daa6ff1e-6915-5fbd-bf5e-ad1359fb990b | note | ACCEPTANCE CRITERIA: All conduit locations not identified by pits immediately installed at the ends shall be marked with 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow stakes, or as otherwise agreed by the Superintendent. Conduits under road pavement shall be marked with stakes clear of the road pavement. Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
8ea8df76-1b6c-5841-804f-3713e5346d4b | note | – – – – – – – – – – – – – – – – –
bf7947c2-e4e2-57c1-873f-db49cf304073 | note | METHOD: Visual
13ceac84-6207-5499-ae0b-d747551f8280 | note | – – – – – – – – – – – – – – – – –
301415c2-0fb5-50fe-95f3-b7a9b0c726d8 | note | FREQUENCY: Each lot
fae45dbf-62c9-57a7-87eb-ad5b0362b3d6 | note | – – – – – – – – – – – – – – – – –
edf01ee1-241d-5ad4-a38d-fbad48f7c2d3 | note | CATEGORY: IP
a7a6ddf3-4be0-5242-bf24-71e3c079d5a4 | note | – – – – – – – – – – – – – – – – –
93372b5b-d226-586a-a0d8-68cafcfabb63 | note | RESPONSIBILITY: SE/Site Supervisor
d9fee3fa-f4d5-503b-9ee4-107799410db3 | note | – – – – – – – – – – – – – – – – –
90f61c00-d24d-571a-a889-50a8d5441f7f | note | VERIFYING DOCUMENTS: This ITP
73f5cc40-9c6a-5fdb-bb3e-f59bd844d51c | date | Date Completed:
| checkpoint | 5.19 Draw Ropes
d032d086-8d6e-582d-8389-2fd8d131a755 | note | REFERENCE: VR 733.07
7e240b86-e9ae-500d-93e3-cd6c55535579 | note | – – – – – – – – – – – – – – – – –
25645fc9-16ec-50e7-bd44-2e1d28e4dcf0 | note | ACCEPTANCE CRITERIA: Each conduit for electrical wiring and communication cables shall be provided with one synthetic draw cord not less than 3 mm diameter and with a minimum breaking strain of 1.6 kN.
b9f4a18c-ee5f-534f-91a1-50f214910817 | note | ○ Where the conduit terminates in a pit, not less than 500 mm of the draw cord shall be tied to a marker peg 25 mm x 25 mm, not less than 300 mm long, and left coiled in the pit. A length of 100mm diameter conduit not less than 200mm may be used.
d66e1c95-c760-5b16-989c-15c8b4ba3d1e | note | ○ Where the conduit does not terminate in a pit, the draw cords shall be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
93d5ba69-68ca-50a2-9985-1bed6eeecedd | note | – – – – – – – – – – – – – – – – –
1ceec8fa-fa66-5103-bed3-e89f927ededb | note | METHOD: Visual
06b5b5b1-073d-57e8-b217-8960119f6f51 | note | – – – – – – – – – – – – – – – – –
22d9057e-4f17-5662-baa8-d4f9cb95947b | note | FREQUENCY: Each Pit
147cfb97-cd70-5b91-b46f-3bab94518a76 | note | – – – – – – – – – – – – – – – – –
8ec43f96-58c8-5b04-9ba1-dbc2f8d43b64 | note | CATEGORY: IP
221a4059-3b73-5193-b7df-460422297689 | note | – – – – – – – – – – – – – – – – –
48717f5c-c6bc-5eb6-a728-dad01812ea67 | note | RESPONSIBILITY: SE/Site Supervisor
018383bb-f7cd-5716-b63a-f7cac05f3263 | note | – – – – – – – – – – – – – – – – –
f062c646-66ff-5d66-b902-b34d937468f7 | note | VERIFYING DOCUMENTS: This ITP
2d5ed2b3-f92e-5a89-81b8-1245a936e0c3 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
4814980e-09e4-543d-816b-4941297a1407 | note | REFERENCE: VR 733.13 (i) (ii)
15764873-18f8-5d73-8f2d-aaa7a8b078e6 | note | – – – – – – – – – – – – – – – – –
8258f4e5-54e3-52a3-9e4c-6d0b29f079c3 | note | ACCEPTANCE CRITERIA: the contractor shall provide:
59fc73e5-ed9e-5677-bae7-728aa4c9a66f | note | – As-built’ drawings showing the complete conduit network including conduit types, sizes and depths.
c160e1ed-d424-5579-a9d9-fbddbf30e7e3 | note | – The above ‘As-built’ drawings shall also show all pits, pit types and pit sizes.
6f05d7e5-8bfd-54ab-a0a5-909182634ee8 | note | – – – – – – – – – – – – – – – – –
5c7e65b4-9ab9-538b-98ed-6e8f1b60f317 | note | METHOD: Document Review
09d2e672-f623-5cf6-a88b-562e23ac9b44 | note | – – – – – – – – – – – – – – – – –
76ae3522-10f4-5d9d-be3f-f69932245248 | note | FREQUENCY: Each Lot
aa58ed24-a320-52ab-ac3a-ea2eaa4b8c5c | note | – – – – – – – – – – – – – – – – –
48ec6a7f-b14f-5db3-b4fb-b144070eff7f | note | CATEGORY: IP
c48a77f9-699b-548c-9ebc-d91877b5d10d | note | – – – – – – – – – – – – – – – – –
d68f023e-6787-5bb4-bff7-2e6db5bccc7a | note | RESPONSIBILITY: SE/PE
3873bb16-c4c0-523d-8a2b-f61c35508277 | note | – – – – – – – – – – – – – – – – –
5cc6a144-9cd0-5dbc-a301-738d83034f0f | note | VERIFYING DOCUMENTS: This ITP
62c532c5-c02f-5ef9-885d-38b43b849761 | date | Date Completed:
| checkpoint | 6.2 Certification
afedbb6e-c383-5be0-b6a0-e86ad13de319 | note | REFERENCE: VR 733.13 (iii) (iv)
0049058b-aac5-5777-bcfb-c5e2c1b27a09 | note | – – – – – – – – – – – – – – – – –
69e85d02-bbcc-5de9-b824-e167dfa61204 | note | ACCEPTANCE CRITERIA: the contractor shall provide:
0c9c0786-3ab0-50f1-b35a-f3fbcbe863db | note | – Certificates of electrical safety for all conduits and pits installed.
584b9cde-987e-5273-8731-141a37e6f869 | note | – Documentation demonstrating that all pits and conduits installed, have been installed in accordance with the requirements of this specification.
1f9c334d-23c3-5db0-bc51-e2780d9a9e34 | note | – – – – – – – – – – – – – – – – –
811199dd-1cab-5fe5-bea8-9e00fdca1806 | note | METHOD: Document Review
71b6f9ee-46bb-55c9-ab2e-7283dd853417 | note | – – – – – – – – – – – – – – – – –
8826c6b6-d6a2-555e-b27f-a2866c47c98c | note | FREQUENCY: Each Lot
017fdec4-671b-554e-b033-25c76ab83fb6 | note | – – – – – – – – – – – – – – – – –
1b464d18-3144-5589-a547-cd920a781a5a | note | CATEGORY: HP*
25efa92c-ff5e-573a-bb82-302e3c971644 | note | – – – – – – – – – – – – – – – – –
566e980f-3a15-560f-8cd9-b41a799cfb05 | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
cf434471-38fb-52f9-87c7-b6a24f0f1c27 | note | – – – – – – – – – – – – – – – – –
d5c31123-b552-59d5-af16-4adf4f64bef0 | note | VERIFYING DOCUMENTS: This ITP
63b553b4-c1a7-554d-a40a-f2dac49ac088 | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
b3215a65-8c24-5082-9e8d-856e8f07da48 | note | REFERENCE: MRPA Quality Management Plan
2c2c23fc-ede4-5cf5-9420-08743ebc0317 | note | – – – – – – – – – – – – – – – – –
4da2e9fd-9f88-570a-92f2-fc5d3be7a9e9 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
b24c2d92-5f63-5957-aeca-21c560740a15 | note | – – – – – – – – – – – – – – – – –
d374c853-986c-51f5-a296-a754e879ea3c | note | METHOD: Document Review
aaede310-f064-55ac-992c-8c33a9a5c166 | note | – – – – – – – – – – – – – – – – –
4e2e3c4c-639f-5254-bf3b-e5ac932f05ca | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
b2d776c2-6eac-5eff-9fc1-5eec308d2978 | note | – – – – – – – – – – – – – – – – –
572b2cb6-54dc-5e84-bb0f-133f5e871d80 | note | CATEGORY: HP*
c52570d2-e044-50e5-b6d4-61f356e52ac6 | note | – – – – – – – – – – – – – – – – –
3e963890-c741-5192-bcab-bf985ec993c3 | note | RESPONSIBILITY: SE/PE/SPE
f1ea35d5-3bd4-5fa7-91a0-61b7834bafca | note | – – – – – – – – – – – – – – – – –
2755123d-d640-5d20-982a-4f915a6597d7 | note | VERIFYING DOCUMENTS: This ITP
aab81bfb-bdc7-59bf-8e81-be4039db0a08 | date | Date Completed:
| checkpoint | Final Inspection
931f82f8-b4dd-5fef-95f6-ae45e5f64404 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3b5d80cb-1144-59ed-8426-c2bb90a0e614 | textbox | Name:
7443a96c-0897-524e-a03a-dcafae26f26f | textbox | Position:
687b03e9-ba3c-5ada-a55b-3bb55a17f656 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-186-STR-SSB-Bridge Expansion Joint Rev 0 | itp | ITP-186-STR-SSB-Bridge Expansion Joint | c0dc393b-d0a1-483e-b30a-ee394bc3972b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0cd65e6b-3a21-5d3f-9fb2-8506c72c1274 | note | Document Title: ITP-186-STR-SSB-Bridge expansion joints and waterproofing
66c5e92b-121f-5197-8504-6e98e0265e76 | note | ITP Description: SSB-Bridge expansion joints and waterproofing
a895f1e4-bba8-5ee3-8932-c1671a4ac4b9 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
62bc6e76-b454-5e84-bee8-ede32e6ac7cb | note | Discipline (e.g. CIV/STR/RAIL): 186-STR
a5b73df5-ecc5-59ff-8148-b506813d9e07 | note | Revision Number: 0
fafaab40-c479-5abf-bf95-1ab7edede94d | note | Revision Date: 24/07/2024
c5622378-6e9b-5537-a347-a022778635ba | note | ITP created by: Isaac El Zayat
0337e4cf-690c-516f-9ef7-aa0a7e88b350 | note | ITP approved for use by: Victor Mira
b7a8db86-3a1c-5d85-8e70-29cec88eece8 | note | 1.1 Non Dependent
ec890ebc-f1f0-5a94-ac6e-287890ad4d2c | note | Reference: VicRoads Section 660 January 2018
d2e84065-a6f6-5c7a-8f8e-263a669515e2 | note | 1.2 Non Dependent
366607f6-abc7-5814-8569-ef1b60c4e8b7 | note | Reference: AC-AR Installation Guide
| section | Preliminaries-Materials
| checkpoint | 2.2 Expansion Joint Components
7c94f3bc-8fd4-5a84-9505-df1b97327d4a | note | REFERENCE: IFC Drawings, VR 660.03
92e6c651-0838-58ab-870c-0fe69b9ba667 | note | – – – – – – – – – – – – – – – – –
ffd01a3d-48a6-5ad3-8074-21976315098a | note | ACCEPTANCE CRITERIA: The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations.
d69f19dd-ad56-531e-9504-fa632b72e361 | note | ○ Attach Delivery dockets/Proof of purchase
6daa7f11-3e4a-5a8d-ac73-e92e11480427 | note | – – – – – – – – – – – – – – – – –
3d7dc4c4-c6e1-5007-968d-d74dea91ea49 | note | METHOD: Document Review/Inspection
9011858c-741c-5a2e-b0ee-a1f1367bbeb8 | note | – – – – – – – – – – – – – – – – –
471a4220-ae3a-53a2-8cd8-d8c9500d0691 | note | FREQUENCY: Where applicable, for each element
f0d63565-8dcc-508a-a9c0-b1f83f62243b | note | – – – – – – – – – – – – – – – – –
bc524b38-d308-5e8d-9311-13f42dc5d9d6 | note | CATEGORY: IP
54d29e3e-29cb-5cc2-beb6-9b1352052ecf | note | – – – – – – – – – – – – – – – – –
ce67f79f-53bd-5041-8f8a-d7e3951e09b2 | note | RESPONSIBILITY: PE/SPE
e7d3c14c-ae03-533c-abff-91c33f11e60d | note | – – – – – – – – – – – – – – – – –
b9ff8c88-a5ea-51a7-a1ca-2f4471cf5049 | note | VERIFYING DOCUMENTS: This ITP
464c7401-3b22-5636-938b-95a35d739ab4 | date | Date Completed:
| section | Preliminaries-Procedures
| checkpoint | 3.2 Expansion Joint Design
b94759ac-3bef-5f94-a7d1-3c178a2e598c | note | REFERENCE: IFC Drawings, VR 660.03
3f9a0afa-d028-5992-a543-c833e5621a74 | note | – – – – – – – – – – – – – – – – –
244a611a-59a5-5d69-800f-d26210d48112 | note | ACCEPTANCE CRITERIA: The expansion joint system shall match the drawings.
47b9bd6e-3cb5-5d99-9f42-71f12642ea63 | note | ○ Where applicable, the joint sealant shall match the Drawings and installation manual
b9231948-8e3b-5c03-9fd7-87453d331a5c | textbox | Enter: Specify the Joint type:
81fed8a8-1745-522e-b69d-d0d4bef3b658 | note | ○ AC-AR-125D for road
ac7ba9c6-7c83-5188-8bca-655a270306b4 | note | ○ P2-100D for SUP and Footpath
3c6670bb-3f14-5bfc-89ad-d43df60d6819 | note | – – – – – – – – – – – – – – – – –
3c20a1a5-66d1-5f66-aae7-bf10f6b2d8f1 | note | METHOD: Document Review
a3165d37-2ced-5e48-be33-0a746ecc9ba6 | note | – – – – – – – – – – – – – – – – –
163790c5-5b98-5d3d-b6bf-025b9bcb270c | note | FREQUENCY: Where applicable, once, within 4 weeks of acceptance of tender
7da8e0cc-fb4f-50d0-9704-5905386b5201 | note | – – – – – – – – – – – – – – – – –
8a8f011f-995b-54fe-bf3e-9add435b315e | note | CATEGORY: WP
551fa206-9af7-51c9-8db7-8301498e183f | note | – – – – – – – – – – – – – – – – –
084848f5-4b9d-572e-aae4-d0f1e1eccbc6 | note | RESPONSIBILITY: SE/PE
29889ab4-7075-5c90-a68d-1ad29cd19911 | note | – – – – – – – – – – – – – – – – –
42ae72f7-722c-59d2-9f37-455b1fad9b9b | note | VERIFYING DOCUMENTS: This ITP
0fa84d5a-e679-5a0b-9130-ddca1263cc88 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 Expansion Joint Installation Temperature
3b7df771-1407-5ad2-84a0-7e2385ddc347 | note | REFERENCE: VR 660.04
606e5a99-2a98-5668-b42b-9198eebb7eb8 | note | – – – – – – – – – – – – – – – – –
0a1de014-01cf-5587-a32b-eee617250961 | note | ACCEPTANCE CRITERIA: The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
a5d75ac1-9529-55fc-8bae-2afab2d041c6 | note | ○ For installation tempratures outside 20±5°C, the gap shall be adjusted by ±3mm per ±50°C
a2cb0ee2-10ce-57bd-8e13-5b8bade7520e | note | ○ Installation Temperature = [free text]
9e8953ff-f14e-5cd7-88c5-5c83a6f82f17 | note | – – – – – – – – – – – – – – – – –
8dc620a3-2b33-55f8-aa1f-76e3e369503f | note | METHOD: Measure
739138bc-bdef-5434-b864-52f70229ee0f | note | – – – – – – – – – – – – – – – – –
90ef2d78-981b-57be-8e9d-a013348d8eae | note | FREQUENCY: At the time of installation
4bd1d592-5eb7-5bdb-a7d3-468c4654f212 | note | – – – – – – – – – – – – – – – – –
a59790c1-160e-58ba-9c24-46d8497192a2 | note | CATEGORY: IP
51825c3d-c338-5d83-8e90-8c98c001d635 | note | – – – – – – – – – – – – – – – – –
0c910187-ad87-5dfe-8733-5b0831d351fb | note | RESPONSIBILITY: SE/PE
d4f8d203-cbe8-599b-92f0-8f59cfcec6a5 | note | – – – – – – – – – – – – – – – – –
187e0c3a-65d4-5b01-95b3-1c348b1cecd6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
0e2f6c28-e8cc-5851-9a19-92df4cf8194e | date | Date Completed:
| checkpoint | 4.2 Post-pour Inspection of Expansion Joint Bearing Surface
79619426-d76e-5ced-b61e-5f0114936aed | note | REFERENCE: VR 660.04
ae80daf0-541a-54c3-958f-eba7f9e4e9c0 | note | – – – – – – – – – – – – – – – – –
cab89b6b-babb-54fb-992a-7284082279a4 | note | ACCEPTANCE CRITERIA: The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
c5a7bc66-f5bf-556d-83d3-1ea546039850 | note | – – – – – – – – – – – – – – – – –
edfebe26-4f3b-5f3a-952e-f05d6f9096af | note | METHOD: Visual
af3e8e40-66c5-5786-be17-96fecf0f6791 | note | – – – – – – – – – – – – – – – – –
3fd63418-b4cf-58f4-af6c-57a7c372d8f0 | note | FREQUENCY: Prior to joint sealant (where applicable)
163a1c2f-8e40-503a-9063-d085d2a9240e | note | – – – – – – – – – – – – – – – – –
34b12356-e58d-5015-bc41-7343cb2db8d8 | note | CATEGORY: IP
afc64622-9353-59c5-85ca-1b14aa95dea4 | note | – – – – – – – – – – – – – – – – –
7e1d7325-dd4f-58f7-97be-7df4e6c862e3 | note | RESPONSIBILITY: SE/PE
e9fd90fc-26be-54f4-886a-0aae4b63925c | note | – – – – – – – – – – – – – – – – –
b17ae8b4-5d24-576a-929d-98351f11880b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
22ad767f-1f65-5b0d-966d-d3ea9839f5fb | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Expansion Joint Placement- Anchor Bolts
609f9ec1-4e98-53dd-bbcd-fe5138410ee6 | note | REFERENCE: IFC Drawings, AC-AR Installation Manual
ea33d0c2-f6b8-510a-b39c-4e187bea3009 | note | – – – – – – – – – – – – – – – – –
552bd0e7-b46b-5286-be23-8f1a8ad3523b | note | ACCEPTANCE CRITERIA: After concrete strength is in excess of 30MPa, the anchor bolts can be tightenedvia the snug tight plus part turn method or with a claibrated torque wrench.
d1bf32d3-45ff-53d8-915b-17346f6835c7 | note | As per installation manual:
42c729a2-9914-50de-ba24-a6b79b423d93 | note | ○ Part turn method: Snug tight + half turn
b4b5b26f-dd4b-5221-9857-e8ca0b28c8a9 | note | ○ Calibrated torque wrench: 400Nm
17b6eb90-5c55-5ca0-8592-f8b5a068d613 | note | – – – – – – – – – – – – – – – – –
c2012b93-87e6-5cf0-ae8f-fa3b305beff5 | note | METHOD: Measure, Visual
715626b3-674e-5406-a09f-725368d3e55e | note | – – – – – – – – – – – – – – – – –
3c1e1155-f313-5675-940a-c1c190ef7e0a | note | FREQUENCY: AC-AR 125D (Road section) joints
723361b5-dd36-52e4-820b-6e428b33f84f | note | – – – – – – – – – – – – – – – – –
fe0b4654-1ca9-5b8f-8d89-cad29d10f1b0 | note | CATEGORY: IP
804bebf3-8f04-5d07-88e2-3a5360003343 | note | – – – – – – – – – – – – – – – – –
b96e1b8e-72e0-507b-ab84-5251177346c7 | note | RESPONSIBILITY: SE/PE/SPE
c8d766de-5eb2-5ea9-9799-dcf0024dfe1e | note | – – – – – – – – – – – – – – – – –
82df0356-cb33-5720-9094-f09b49411864 | note | VERIFYING DOCUMENTS: This ITP
596c2be1-6229-504d-8ebb-016ba0d9bc6b | date | Date Completed:
| checkpoint | 5.2 Expansion Joint Placement-Coverplate
5e75f51c-b504-5bdd-a5b7-f6844728f123 | note | REFERENCE: IFC Drawing
0363dd52-1da6-5ee9-a581-1f5115e786c0 | note | – – – – – – – – – – – – – – – – –
5f62867c-0eb4-5e73-9298-422dfd3d1a81 | note | ACCEPTANCE CRITERIA: Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings
6d78f9f5-f3ae-5284-8e63-326935f4c61d | note | – – – – – – – – – – – – – – – – –
c6cf03d7-dd94-58f5-9429-6a4c9d1fe65b | note | METHOD: Inspection
0544264a-0d85-5aff-ba4a-3102ab72b086 | note | – – – – – – – – – – – – – – – – –
fc7580f7-df21-58b0-9130-72d268eeab1a | note | FREQUENCY: P2-100D (SUP and Fottpath) Joints
f21ad6c2-2c99-56bd-85b6-d8b44f3ab0e6 | note | – – – – – – – – – – – – – – – – –
949a91a9-d8da-505b-8894-d7ebb52ef5cf | note | CATEGORY: IP
665a0c91-3572-53ff-b7c4-cfd0c69c91e9 | note | – – – – – – – – – – – – – – – – –
317415ab-892c-5945-85fa-3ad76c27f10b | note | RESPONSIBILITY: SE/PE
138956b1-85ad-55fc-8060-56e7af54d78d | note | – – – – – – – – – – – – – – – – –
5de3250c-5b4b-5dae-a2d3-d87817b04cee | note | VERIFYING DOCUMENTS: This ITP
f4549eeb-dee2-5ad3-ac76-45d9455c6cad | date | Date Completed:
| checkpoint | 5.3 Expansion Joint Placement
40bdb29a-8a02-5ebf-bb95-9a9981f48d59 | note | REFERENCE: IFC Drawings, AC-AR Installation Manual, VR 660.04
97d0a577-f714-5a89-b69a-a8f0a79ae16b | note | – – – – – – – – – – – – – – – – –
90ab0bdd-67ce-5c04-a54b-824f252cad8f | note | ACCEPTANCE CRITERIA: Check compliance with the Drawings, installation manual and tolerances:
92dad8c3-5e69-5c17-b0f8-2d8ef7a12370 | note | ○ Joint gap = ±3mm (38mm is specified on the drawings)
5912c37b-89d1-54e3-9d3d-9f4df9fc7153 | note | ○ Deviation from plan alignment = 5mm max.
64591c37-e3a3-5ae3-8842-47f6799420de | note | ○ Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
b274bac3-e527-5fc2-b0ec-92d0b4e440fc | note | – – – – – – – – – – – – – – – – –
9f6cee5a-7ba8-5a44-b809-b813e212705d | note | METHOD: Measure, Visual
364361ef-3744-5c45-b781-d032d3e9f81c | note | – – – – – – – – – – – – – – – – –
4e18fee7-3565-50a4-be39-6d7b1c9814e4 | note | FREQUENCY: Each element
eceb70de-13d9-552a-b1cc-53172d265006 | note | – – – – – – – – – – – – – – – – –
b75aed6b-24b8-5416-bfc3-064b9638230d | note | CATEGORY: IP
706b43be-6e32-5e06-9a55-0c1910301531 | note | – – – – – – – – – – – – – – – – –
d026f8e9-072e-5bd7-a4ac-61f1bcd85326 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
8c8c194d-ec49-50d4-a197-ecdfda6f7d1c | note | – – – – – – – – – – – – – – – – –
cd76b1f2-9722-5c4f-bec1-6a1718abfbcf | note | VERIFYING DOCUMENTS: This ITP
277033df-7c6a-50dc-a691-151aa370a8e0 | date | Date Completed:
| checkpoint | 5.4 Compression Seals, Inserts and Membranes
dcbedd01-29cf-58ce-9e29-b39f31693f85 | note | REFERENCE: VR 660.04
4fdfa87b-31ed-5b0d-8e46-78f341eca283 | note | – – – – – – – – – – – – – – – – –
7a1b1362-66e5-5459-9622-1cb0910e2f1c | note | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
7d34a3c3-ab48-57b4-bfdc-e41c79642299 | note | ○ Completed joints shall be watertight.
c1c10d16-4742-539b-b8b0-0567094af8d0 | note | – – – – – – – – – – – – – – – – –
305eb9db-f48c-5c37-9723-4407f3822029 | note | METHOD: Visual
b179d595-bbe3-5939-980b-648ebcb43419 | note | – – – – – – – – – – – – – – – – –
dbd541b2-4865-5100-857d-053bdd01c6b0 | note | FREQUENCY: Where applicable, each element
af3dac6e-ce8a-5ed0-9480-e56448f8d8d3 | note | – – – – – – – – – – – – – – – – –
3f575790-7a89-52be-9160-ec50e2e1f548 | note | CATEGORY: IP
577ed6e7-7680-5f6d-818d-62f74989629e | note | – – – – – – – – – – – – – – – – –
214de17d-d6ea-595a-95d8-aee2c78cb944 | note | RESPONSIBILITY: SE/PE/SPE
dc6cd637-9f11-5ef1-b406-0cdd4eaabb4e | note | – – – – – – – – – – – – – – – – –
978fd4d2-4b01-525e-b08b-87f76e52efa1 | note | VERIFYING DOCUMENTS: This ITP
1b058d42-b19a-592a-8965-3d4faae37e9d | date | Date Completed:
| checkpoint | 5.5 Final Inspection of installed system including all accessories
f851b6fa-cdd9-59ad-afc3-b8f769d1f813 | note | REFERENCE: IFC Drawings
2cb44acd-0b23-56a3-8f85-39416157ccc3 | note | – – – – – – – – – – – – – – – – –
3d951cb2-7da9-5167-81b5-d53676ba534d | note | ACCEPTANCE CRITERIA: No visual damage to the installed system
5ada8750-0559-5edb-af54-3ad79af9cdc8 | note | – – – – – – – – – – – – – – – – –
deed24ff-7e4e-574b-b45c-7cf466b11cdd | note | METHOD: Inspection
8f4ea049-9bc6-5b26-abf5-6539eb988ee5 | note | – – – – – – – – – – – – – – – – –
bff32e7a-6218-5ed4-b002-d0813afe11a4 | note | FREQUENCY: Once per Lot
92b61d19-5366-5d46-acbf-93faf953b45e | note | – – – – – – – – – – – – – – – – –
9fcda8b3-8254-5cfb-b2b6-a94250496f04 | note | CATEGORY: IP
ef98fc32-c46f-5fb2-8c83-ff1e330d59b5 | note | – – – – – – – – – – – – – – – – –
fa719654-01b3-5aab-8998-b0edc67272e2 | note | RESPONSIBILITY: SE/PE
fe3d23a8-ad9f-5f6c-977b-d83f9c12c2a7 | note | – – – – – – – – – – – – – – – – –
22e9c2d1-7add-5735-8964-1f298ae5bc1f | note | VERIFYING DOCUMENTS: This ITP
8a500a68-1d4c-5b7d-a197-204382164981 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Trafficking of Joints During Construction
22a04ce7-dac7-55f5-adff-33513f391d9d | note | REFERENCE: VR 660.04
6cdba678-85a2-5570-9c85-d300d145c9fb | note | – – – – – – – – – – – – – – – – –
b85c3b2c-7c99-53e2-a5e6-f5228e5cb08b | note | ACCEPTANCE CRITERIA: Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
31c3dbd4-5595-5297-93f1-16a961917efd | note | – – – – – – – – – – – – – – – – –
04653e51-5661-5980-a3c3-8225115cc69c | note | METHOD: Visual
dd783b63-636d-54f6-a019-52f36e033276 | note | – – – – – – – – – – – – – – – – –
93cdae26-cd70-5326-842e-41daa065a570 | note | FREQUENCY: Where applicable, each element
eff7d432-9a12-5173-b33b-e0c2e9be7642 | note | – – – – – – – – – – – – – – – – –
9156f22c-221d-5c76-b0ec-63d428b07b3d | note | CATEGORY: IP
ecde689e-0eeb-56a4-bd8e-f23645ceef23 | note | – – – – – – – – – – – – – – – – –
afd7364a-fac2-5d84-b257-882e6935df7e | note | RESPONSIBILITY: SE/PE/SPE
6438dc60-6836-5f33-809a-3e8e11b0abbe | note | – – – – – – – – – – – – – – – – –
c6e387dd-5067-5ce0-9aa7-4d75fa58dff6 | note | VERIFYING DOCUMENTS: This ITP
506a1bb9-e2b1-51b2-8c03-d0be5f94ebf8 | date | Date Completed:
| checkpoint | 6.2 As-built Survey
20a85c71-537e-5f51-bb58-25d4dc0b4a0f | note | REFERENCE: IFC Drawings, VR 660.04
fea77ec8-0f23-50d5-b9a3-a0ac6e96c759 | note | – – – – – – – – – – – – – – – – –
892188eb-2592-5afc-9b9d-17c69c264b7c | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above.
3280eb95-ced0-532d-9ce0-04075eba28f3 | note | ○ Attach: Survey As-builts / Survey Report
20638c63-24c6-5f2a-a707-7b649f4b0de0 | note | – – – – – – – – – – – – – – – – –
43fb5e13-f907-589c-a0f6-905d177c003b | note | METHOD: Document Review
688ae9ff-6b5f-511f-b606-26387494cc72 | note | – – – – – – – – – – – – – – – – –
29b50486-fac3-5062-b86f-a976fcdc9c18 | note | FREQUENCY: Each element
0875d042-3af8-5914-8129-31a47ab271b4 | note | – – – – – – – – – – – – – – – – –
7a023a0a-e8d4-5785-a810-2433d5f18501 | note | CATEGORY: IP
077a919f-4f43-56e0-93f0-40a7718bee35 | note | – – – – – – – – – – – – – – – – –
e744252e-9f7c-5349-acda-bfec8314119a | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
790f39cb-d73d-533d-acc8-617382a6fd36 | note | – – – – – – – – – – – – – – – – –
5a657b47-c61c-516f-8f75-76932c7a552f | note | VERIFYING DOCUMENTS: This ITP
2a4e0379-bdeb-5b66-b614-22b3c4848059 | date | Date Completed:
| checkpoint | 6.3 Subcontractor Product warranties obtained
cbcace35-1149-540f-a83f-d80e53093ff7 | note | REFERENCE: Work Method Statement, IFC Drawings
034f018e-9fc9-589b-a83b-d1c124dbf8bf | note | – – – – – – – – – – – – – – – – –
40eba5e9-f742-50f6-bbe7-1021dc342f09 | note | ACCEPTANCE CRITERIA: Product warranties obtained and are compliant with what is specificed in IFC Drawings
fceedf4e-b8c1-50f5-8661-ef9d81e0c3f7 | note | – – – – – – – – – – – – – – – – –
31c1e400-8952-5acb-8361-488547d84ff7 | note | METHOD: Inspection, Document Review
ce138890-7ad0-53af-87a1-1b946bbc2a77 | note | – – – – – – – – – – – – – – – – –
b89dbc72-4cde-55c0-9c53-4229d544f90b | note | FREQUENCY: Once per Lot
d7d5138d-234f-5853-8cb4-b88686cf81de | note | – – – – – – – – – – – – – – – – –
6962d708-e580-5111-8e54-49b2a651a6a4 | note | CATEGORY: HP*
6011f1da-f3ab-599a-bba4-32f361d90f27 | note | – – – – – – – – – – – – – – – – –
25326456-9790-5c82-b040-b5cfdb674c93 | note | RESPONSIBILITY: SPE/PE
29f9a64d-4ad9-50c5-a42a-c9757c3c4792 | note | – – – – – – – – – – – – – – – – –
3134de69-df0a-54c9-9747-a423827e9816 | note | VERIFYING DOCUMENTS: Copies of product warranties
b297b40a-a554-502c-aa43-91753bcc1985 | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
195de280-1cf7-5324-b490-812af75426c1 | note | REFERENCE: MRPA Quality Management Plan
56810b46-e1f5-52a3-abde-b95f88d6e87c | note | – – – – – – – – – – – – – – – – –
3f037e33-7e80-532c-b2ad-56b648c7d749 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
012ce7e1-f097-50bf-9d1a-1099652d2709 | note | – – – – – – – – – – – – – – – – –
0119d5f0-60cc-59f1-a6cd-be049d0f262b | note | METHOD: Document Review
5d8b6abd-a378-5ca3-a6e4-f84b9747226a | note | – – – – – – – – – – – – – – – – –
e4231245-8c5e-547a-8766-6f1efee4bd28 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
6f9eeb14-8ea3-5212-ade7-887588f5813d | note | – – – – – – – – – – – – – – – – –
419962b9-29a4-5922-a4f9-5befd8906126 | note | CATEGORY: HP*
7388da2a-cf5d-582c-a9db-17cfe190b15e | note | – – – – – – – – – – – – – – – – –
a6500b58-094e-55f0-a909-58afa6379234 | note | RESPONSIBILITY: SE/PE/SPE
d0825e43-b23f-56e6-825c-713edae35a03 | note | – – – – – – – – – – – – – – – – –
3c3c6deb-c00e-57cc-9444-a81c151793eb | note | VERIFYING DOCUMENTS: This ITP
a0700549-d55f-5fb5-be5a-6755a24b9576 | date | Date Completed:
| checkpoint | Final Inspection
f8374532-1e26-5315-8f6b-495f528ae46d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fd53f77f-ba14-5da9-9bad-af509eadf5f4 | textbox | Name:
dfad3227-d4f1-5db8-85c0-f1983b5f8935 | textbox | Position:
b7ce4ab6-030d-5d42-8cc9-de3eda69f1f9 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-188-STR-SSB-Precast Material Inspection Rev 0 | itp | ITP-188-STR-SSB-Precast Material Inspection | d7ca48d3-767b-497f-8ab1-8aca9cca0a49
| section | Referenced Documentation
| checkpoint | Referenced Documentation
27de393b-e11e-5acf-beed-f7f5595517f7 | note | Document Title: ITP-188-STR-SSB - Precast Material Inspection
a19843e3-0719-5122-9359-895baa35a8a1 | note | ITP Description: SSB - Precast Material Inspection
102dccf9-d3fb-5ed6-86fb-ca7d360b3143 | note | Discipline (e.g. CIV/STR/RAIL): 188-STR
8b2861c0-d0a6-58fd-8eda-ec246c7b9bc5 | note | Revision Number: 0
ded66c1b-4d74-55b2-926d-2b45aef8f09f | note | Revision Date: 30/07/2024
3bb226c2-b1c5-5413-8327-4bbf16379d2e | note | ITP created by: Dan O'Brien
fe8dcd1f-e0be-5c17-806c-559ef797a5fe | note | ITP approved for use by: Victor Mira
| section | Precast Deliveries
| checkpoint | 1 - Delivery Details
df388eb0-de49-5858-964a-73130d36ac9a | textbox | Enter: Delivery Docket Number:
8af4e247-dc5c-5948-a3d9-93333eeab694 | textbox | Enter: Delivery Date:
444ca24b-c9ef-5572-8855-436551558faf | textbox | Enter: Element ID (s):
de0508be-5d7e-579c-b2ac-1e06466da6f2 | note | Attach: Delivery Docket and packaging Slip
bfc62381-6f80-5844-92d7-382d7e82df74 | note | – – – – – – – – – – – – – – – – –
db1fd6e4-4403-51f9-b671-f65bdf1f5e73 | note | METHOD: Document Review, Visual
cfbc7251-01eb-58ee-8f95-fd25f611f95d | note | – – – – – – – – – – – – – – – – –
0bcb28d9-b723-56b6-b9fe-9728f5ed8ee1 | note | FREQUENCY: Each Delivery
ca099ed7-5b5c-51bd-97e2-73643eef1f4f | note | – – – – – – – – – – – – – – – – –
14d0ccdb-eca4-57f6-bb35-e84bd3d77cbc | note | CATEGORY: IP
55ec882b-b93a-5331-9169-200b2c185981 | note | – – – – – – – – – – – – – – – – –
0f30d1b1-d7c0-5ee3-ae65-a3c94016a077 | note | RESPONSIBILITY: PE/SE
e8c16b1d-392c-5a88-bd31-fc2654f4e717 | note | – – – – – – – – – – – – – – – – –
8e963511-1dde-5779-81d7-4def76a2726f | note | VERIFYING DOCUMENTS: This Checklist
b9ba2073-ab05-5313-9e5c-b7a77871612d | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
d806e450-11df-5a61-a73a-498df03a21c1 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
6db9955e-5006-5e55-9e09-d8033c7dabed | note | – – – – – – – – – – – – – – – – –
05b635aa-fa8b-5d12-84ec-9b73956e1972 | note | METHOD: Visual
e2118e66-b026-5586-b0df-6978befca6e2 | note | – – – – – – – – – – – – – – – – –
362819f0-4b78-5561-8312-e83fab8540fc | note | FREQUENCY: Each Delivery
759a6b19-8d4d-5df2-b841-ce2e980ad220 | note | – – – – – – – – – – – – – – – – –
93856efb-cd71-514a-b034-edf5fb6971c6 | note | CATEGORY: IP
18e0e7f4-344d-5229-b9af-3280a1e823a7 | note | – – – – – – – – – – – – – – – – –
1c0983a6-5a2f-55c8-9d13-7cb915c22104 | note | RESPONSIBILITY: PE/SE
dc3b1f61-1fa5-5d59-90a6-535f88c1bdfb | note | – – – – – – – – – – – – – – – – –
41270169-0101-5e02-b7d1-8eb3cbe72bec | note | VERIFYING DOCUMENTS: This Checklist
ffde6a47-a556-59fe-bd50-387acfec6b4f | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
ccb1e60a-ca9f-5af3-a32d-cea0ac46d412 | note | ACCEPTANCE CRITERIA: Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
4257c174-90cf-58ca-8045-0a698f80e3db | note | – – – – – – – – – – – – – – – – –
47f0bf2c-e6a8-5d4e-b3db-d33f90ef2823 | note | METHOD: Document Review, Visual
a71d1496-9f9e-5471-b390-db79517efc01 | note | – – – – – – – – – – – – – – – – –
04c8d33b-a225-545b-85c8-c5f1e5e64d1f | note | FREQUENCY: Each Delivery
cdfe35a8-9a0c-51a0-baeb-ad06163c5e34 | note | – – – – – – – – – – – – – – – – –
48410922-0e27-5079-8056-4aa93bd5f35d | note | CATEGORY: IP
6abe8edf-2018-50e2-bd56-c47d6c0da1a6 | note | – – – – – – – – – – – – – – – – –
7730bd06-b7e1-53aa-b40b-8d9e50de83a3 | note | RESPONSIBILITY: PE/SE
c6b84f3a-d098-545b-a8fe-55466d4051d3 | note | – – – – – – – – – – – – – – – – –
8defbeaf-5072-5da0-b110-852d73645cf9 | note | VERIFYING DOCUMENTS: This Checklist
fa3324fb-b05f-54c7-8e4c-abe7ba9f9ee3 | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
25538d7e-ff2a-5f34-ac76-95d4734cb3af | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
583f292c-6a69-53ec-ae26-278236ebac1a | note | ○ Precast components are to be marked on the birth certificate.
05050268-f8cc-5ac6-becd-f6b30c86b383 | note | ○ Cast date and lot are to be marked on the birth certificate.
46ccae18-e573-50cc-ab72-1da0f6c8f3cc | note | ATTACH: BIRTH CERTIFICATES
cf03a21c-b8e6-5776-85a1-a5d191f30d64 | note | – – – – – – – – – – – – – – – – –
38f15461-d920-526d-a0c5-d9e6aad8fcc8 | note | METHOD: Document Review
2e1a05aa-ca91-5b3b-9f7c-8eb7f6fec287 | note | – – – – – – – – – – – – – – – – –
b8ab9274-0fe5-5e50-932b-a945a7968130 | note | FREQUENCY: Each Precast item
d69986d0-1ee9-5a72-8cd0-0e0318a56db3 | note | – – – – – – – – – – – – – – – – –
06da3c2a-9ba1-5120-aa4e-804beb2574c7 | note | CATEGORY: IP
8f5a73ec-2e7d-57be-9b09-57b24d0a41f9 | note | – – – – – – – – – – – – – – – – –
2a7ab87c-3ede-54b9-addb-803fa1f8dfb3 | note | RESPONSIBILITY: PE/SE
01478bd8-45d6-5368-9a52-d65795eeb7ae | note | – – – – – – – – – – – – – – – – –
d7f472bd-abb0-5bb9-9dbd-0ab7d53b79f6 | note | VERIFYING DOCUMENTS: This Checklist
aead1429-f793-5905-9f20-468b1989be57 | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
85ada224-ab21-54c2-9625-0011212b5b36 | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
02736fa2-f3bd-523d-8d6d-99d772db241d | note | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
9bb734ca-4538-5c67-ba68-f84cec4bfa38 | note | – – – – – – – – – – – – – – – – –
17841c8d-ef50-530e-972b-f65f5f6dfc2b | note | METHOD: Visual
f366edd8-7f52-57c3-be70-e85329e8e066 | note | – – – – – – – – – – – – – – – – –
5f7a1738-7c8d-51ad-9218-c06f14be9c13 | note | FREQUENCY: Each Precast item
5d70da08-cceb-517d-a267-d8ed0bbece94 | note | – – – – – – – – – – – – – – – – –
f3e67a7c-b96c-5fe8-aa74-0db269f5c33c | note | CATEGORY: IP
dd2bd290-acd0-5ee0-9439-3a2a9c481ab2 | note | – – – – – – – – – – – – – – – – –
7135566a-5243-50bd-8bae-539c798099a1 | note | RESPONSIBILITY: PE/SE
b03a53a0-dfe3-5a53-bf0f-de3bb0b3c814 | note | – – – – – – – – – – – – – – – – –
36afdc88-2470-5f76-9045-15d17f048c9c | note | VERIFYING DOCUMENTS: This Checklist
e37d41ef-30c1-5901-9c9f-bc94e3d0e5fe | date | Date Completed:
| checkpoint | 6 - Pre-Lift Inspection-Transport
f2e8a427-c2ee-5184-8700-af93d715532d | note | ACCEPTANCE CRITERIA: Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
ae442c58-c3ee-5d2e-aea1-a0bf2f216df6 | note | – – – – – – – – – – – – – – – – –
4312e570-cbf4-54be-a8f9-6d51484caf5a | note | METHOD: Visual
7e7f5c19-2f44-5740-9cb6-1c7a32e59b1e | note | – – – – – – – – – – – – – – – – –
8e63b5d5-dc15-56d8-898b-5983ac6c708f | note | FREQUENCY: Each Precast item
c430f922-1911-599b-9355-b62058995374 | note | – – – – – – – – – – – – – – – – –
0bb15b09-0ded-5f65-83ba-b2cf69c5af13 | note | CATEGORY: IP
11ccb81e-4867-57ff-a20d-5ccf91f2cabb | note | – – – – – – – – – – – – – – – – –
1347eef2-2483-5767-815e-65db9bc951f5 | note | RESPONSIBILITY: PE/SE
26012f35-0bf0-5e7e-bd08-1da24596c61f | note | – – – – – – – – – – – – – – – – –
f3945336-9b5c-5075-b1ad-e5715113e51f | note | VERIFYING DOCUMENTS: This Checklist
963222ba-a4aa-5444-b5bb-e4dad556f768 | date | Date Completed:
| checkpoint | 7 - Fault IDs:
fd0c7022-1156-520e-875a-65dbbe6e55f3 | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
37da5dc4-5b64-5eaf-8ff8-2110bedab148 | note | 1 - Identification markings match the panel type
7c0a6244-026d-5f61-9249-4547be483709 | note | 2 - Element fabricated as per drawings
5ad6fc1b-4f64-52e4-bc0d-e6231826a0f9 | note | 3 - Cracks
3422bf6f-f594-57d8-bb25-2684b2925210 | note | 4 - Spalling/Damage to concrete surface
9605a832-d2e3-5c71-b7f2-9608c96b1651 | note | 5 - Exposed Reinforcement
028e8e9f-fb27-521a-97a0-868fbaf66ac0 | note | 6 - Damage to Anti-Graffiti coating
b810cdfb-7140-56cc-83c9-55b14447c39a | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
9d4b0cb8-f10b-5f51-b71c-add383b45ad7 | note | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
b8006c10-89dc-5362-8e40-90f29d36c2db | date | Date Completed:
| checkpoint | 8 - Check for Faults - 1
23866723-7cb6-5a92-a6c2-aa99bf576c9d | note | REFERENCE: Item 7 on this Checklist
ed597335-be3a-5ef3-87f9-f6ca2815d12e | note | – – – – – – – – – – – – – – – – –
a6c059c7-a3b1-5834-8384-45b0430573ff | note | METHOD: Visual, Measure
8a91ceac-69ed-51ec-86de-5e4847295b76 | note | – – – – – – – – – – – – – – – – –
2c66e5ca-b469-5709-8c6e-9c527026a629 | note | FREQUENCY: Each precast type delivered
b06fc030-0c09-5cf2-9b34-12deec090af3 | textbox | Enter: Panel Identification:
5be33f69-cdaa-5679-a3f5-c5daf9bdac83 | textbox | Enter: Quantity:
0cc01265-0f59-5ead-9271-860e3d87320f | textbox | Enter: Fault ID if any:
5ea6d526-928e-5bb1-88e5-40f36c88449c | note | – – – – – – – – – – – – – – – – –
99334931-7e4c-5d69-a943-1fd1a1d8626b | note | CATEGORY: IP
7e9f450b-5d83-5c0b-870f-fee3c9c23bbb | note | – – – – – – – – – – – – – – – – –
69d3d7b0-0e56-52c4-bab5-3ede9ef2b910 | note | RESPONSIBILITY: PE/SE
4237d995-8bae-5c86-aac1-9656ba2a635a | note | – – – – – – – – – – – – – – – – –
4b40e97f-2d7b-5da0-a3f3-f61ccb320f55 | note | VERIFYING DOCUMENTS: This Checklist
add6ef6f-9a6a-555b-b584-6f58e18bed0c | date | Date Completed:
| checkpoint | 8 - Check for Faults - 2
0cad4cee-598c-56d6-a454-64aa9cbdb57f | note | REFERENCE: Item 7 on this Checklist
b58b89db-74fe-5a7f-bb33-f9233459988c | note | – – – – – – – – – – – – – – – – –
4120da6e-ace5-52fc-8648-58bdbcdde36c | note | METHOD: Visual, Measure
01bfa8bc-6bbe-5b69-a39a-adc27be3e240 | note | – – – – – – – – – – – – – – – – –
dd561dc8-e6b4-5e3b-803d-4cb514a098b0 | note | FREQUENCY: Each precast type delivered
3e215a56-6a6b-54d4-9459-b11ac31fd3ae | textbox | Enter: Identification:
d4deef68-6b4d-5788-a733-9031a879797e | textbox | Enter: Quantity:
746220d4-85c1-5eb5-998d-fbcdf45def8a | textbox | Enter: Fault ID if any:
6741c3e5-94c9-5614-ae57-93018160e9c9 | note | – – – – – – – – – – – – – – – – –
852d8797-6f9f-58b8-8fc2-dd74e20c2c14 | note | CATEGORY: IP
ee4b1941-6894-575a-b4f2-248003d6ae57 | note | – – – – – – – – – – – – – – – – –
0471dbd9-ab4f-50ba-9188-a299865d5e3c | note | RESPONSIBILITY: PE/SE
e2ad23b0-e865-5fa7-b007-66ebb007fdbf | note | – – – – – – – – – – – – – – – – –
bab3176d-4380-525c-91c5-9385a1a361da | note | VERIFYING DOCUMENTS: This Checklist
d7f4ef09-c851-5ea4-9914-116b0791d339 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 3
b7def3fa-2b49-5a1e-8a7b-bb57df7f4a1f | note | REFERENCE: Item 7 on this Checklist
e00756b1-97c1-5874-873d-9daa0b5ceb70 | note | – – – – – – – – – – – – – – – – –
c4928e97-89cb-5d00-b094-9157ec36b2a4 | note | METHOD: Visual, Measure
af065b34-878c-5d24-a040-3a13b3a2877a | note | – – – – – – – – – – – – – – – – –
fe4b2073-2f87-5d90-8ad7-d092f36a33f7 | note | FREQUENCY: Each precast type delivered
b1de8a40-f40a-5bf6-a632-0e502f3ede20 | textbox | Enter: Identification:
ff331983-18f7-5c8e-9fc4-850216c087fe | textbox | Enter: Quantity:
2558c287-2da6-573c-811b-e0ad19e7ef2c | textbox | Enter: Fault ID if any:
f6cd7f3e-26ee-5cd1-9acd-3b80ba7094fc | note | – – – – – – – – – – – – – – – – –
a3624652-ee80-5124-99a9-ead53b4245af | note | CATEGORY: IP
035cbead-3613-53d5-98e3-22d435fcb129 | note | – – – – – – – – – – – – – – – – –
4e5b87c6-980c-5fc1-bff1-40565e46e1d1 | note | RESPONSIBILITY: PE/SE
25c842bf-d306-502d-9960-99f45a5df252 | note | – – – – – – – – – – – – – – – – –
64126ec4-91f5-50b6-80a5-78eb2fd2c7ae | note | VERIFYING DOCUMENTS: This Checklist
a0991618-99a0-5f54-b4a2-e2a021f4f548 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 4
f0d3cd82-c29b-5fb1-9d64-f9e1263b7e14 | note | REFERENCE: Item 7 on this Checklist
cb6521bc-c9b1-5439-801a-7f399f185fc8 | note | – – – – – – – – – – – – – – – – –
57629909-0a18-58bf-bdeb-01b489be273c | note | METHOD: Visual, Measure
e961ee35-8d9c-5d9d-ad61-5a193b0a7f68 | note | – – – – – – – – – – – – – – – – –
18813622-889e-5f2c-af49-89f8d4be6840 | note | FREQUENCY: Each precast type delivered
b9ec9449-681e-5ff4-99fb-b2b82b58d827 | textbox | Enter: Identification:
03aaecdb-5dde-58b2-8201-d2f19056a601 | textbox | Enter: Quantity:
80f568c8-331e-5081-87f0-0f6c30de62b1 | textbox | Enter: Fault ID if any:
a1d0ad2c-d757-5066-ba87-fd729b9d862d | note | – – – – – – – – – – – – – – – – –
6495e760-729b-5e1f-81fa-6832217b4e72 | note | CATEGORY: IP
d08a81bf-bd54-5d29-80d3-177aba6ea36f | note | – – – – – – – – – – – – – – – – –
b2f24c1c-c388-592b-9ebe-11d71ec4a5e8 | note | RESPONSIBILITY: PE/SE
5664d850-e1a9-58b4-ba78-32356452b1f2 | note | – – – – – – – – – – – – – – – – –
a7a124a3-3653-5d16-9473-f3059ebeb5d3 | note | VERIFYING DOCUMENTS: This Checklist
6490e0d9-0c08-5e89-a335-f17e7960226b | date | Date Completed:
| checkpoint | 8 - Check for Faults - 5
1ada277f-41ba-5849-a8e5-568f21501fef | note | REFERENCE: Item 7 on this Checklist
bcf06e50-d1ab-50dc-9149-f66a81d53584 | note | – – – – – – – – – – – – – – – – –
6e114fd3-9c2e-51c4-b613-7c870537a1a2 | note | METHOD: Visual, Measure
ae739c69-4126-5ba7-a650-34d0fe51e03f | note | – – – – – – – – – – – – – – – – –
c5389314-d2d6-53f3-91c4-2058a2f831ac | note | FREQUENCY: Each precast type delivered
725fa131-8235-5496-871e-936239c6ed3a | textbox | Enter: Identification:
e029852f-569e-5d6d-8a98-ec0492d9440d | textbox | Enter: Quantity:
5d60cd21-fa7f-50d9-be21-eed3d59b091b | textbox | Enter: Fault ID if any:
e58aa3e0-f943-5b95-bd21-ce19314aa861 | note | – – – – – – – – – – – – – – – – –
16d8e59b-b02f-5590-8277-8a3f584ef6f2 | note | CATEGORY: IP
225d7b87-6885-58be-bc89-a229c6e9e706 | note | – – – – – – – – – – – – – – – – –
88727f32-efd4-53fe-9948-25bb386112f4 | note | RESPONSIBILITY: PE/SE
005fe62a-261e-5ee9-be7d-687a3c02662c | note | – – – – – – – – – – – – – – – – –
452bffd5-b7d0-53a6-994a-a70614b8947c | note | VERIFYING DOCUMENTS: This Checklist
c3df4f75-9ecc-5ed1-8cea-6a416b88e1f4 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 6
a0b975af-dc3a-54b6-b2a7-b173debeb7d0 | note | REFERENCE: Item 7 on this Checklist
dfed9ba3-b836-5196-a754-5b607f76e8c8 | note | – – – – – – – – – – – – – – – – –
276bee29-fa85-53c7-b1d6-4ebf6b472148 | note | METHOD: Visual, Measure
57b2e3d7-97a9-5685-ac79-569170049941 | note | – – – – – – – – – – – – – – – – –
a6675800-0f17-5943-b1bd-930dd1e473eb | note | FREQUENCY: Each precast type delivered
3dab4fba-0ff2-57c3-9093-3dd07d865200 | textbox | Enter: Identification:
631891ec-6373-5733-8aeb-6ee8bb9cc530 | textbox | Enter: Quantity:
e516fe6a-e410-5b4a-be55-3c10d60653df | textbox | Enter: Fault ID if any:
09206164-ea51-53a2-ad33-0075c2283dd1 | note | – – – – – – – – – – – – – – – – –
70485c26-531f-54c0-a423-28b0ec67a390 | note | CATEGORY: IP
4a9c40af-23ae-575e-85bb-8922390b6294 | note | – – – – – – – – – – – – – – – – –
e00a821f-7c18-5536-be9d-38b9b06b0533 | note | RESPONSIBILITY: PE/SE
e8fa0e9a-44d9-5b77-8c94-b11cdb336699 | note | – – – – – – – – – – – – – – – – –
ebc2e839-8d91-5d72-b131-8cdae125c0f0 | note | VERIFYING DOCUMENTS: This Checklist
1e39841b-9afd-512f-b622-75961a2aebdc | date | Date Completed:
| checkpoint | Final Inspection
2c46cca8-8d23-5a2c-9b7f-3d05e0c34064 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
18285de7-a1cb-5826-9a15-5655bdd730ea | textbox | Name:
2a58dc20-8605-5c1e-abe9-a3049645ed5e | textbox | Position:
9f3d5735-afff-5d68-9e01-48824e801f7d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | df1b0790-d11a-44ae-aaf5-24e136b391f5
| section | 1 - Referenced Documentation
| checkpoint | Reference Documentation
6d4675ab-d88e-5714-8fa6-4fdff71aac86 | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
b541da8f-ec87-5d69-b686-206cd3c6b470 | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
9f51500c-0f2d-5ca1-9bfc-e558927202f1 | note | Discipline (e.g. CIV/STR/RAIL): STR
8ffb0368-d968-5575-b29b-fefb08b51fba | note | Revision Number: 2
bbb04446-cfa8-5f95-8bdd-7bd537a31f63 | note | Revision Date: 11/12/23
0cc18cf2-8dc8-5a5b-ba70-735460e906d2 | note | ITP created by: Mike Freeman
53449ce0-3165-5820-b59a-9fd4db8f03d7 | note | ITP approved for use by: Mike Freeman
42470bf6-7387-56f7-b789-c7e61e2d3be6 | note | 1.1 VicRoads Section 685 November 2018
2595fe17-a24f-5ca3-ae1e-09167da3fe57 | note | 1.2 VicRoads Section 686 November 2018
| section | 2 - Preliminaries
| checkpoint | 2.1 - Anti-graffiti System Selection
0f949bc6-e731-5ea0-a72b-34b753600861 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
6fdcbe77-0afa-5a8e-8e78-2bc3b04e2b8f | note | – – – – – – – – – – – – – – – – –
2d6ba170-bb1d-58aa-8cfd-11fa20b11174 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
98d23cea-5429-5046-a2fd-f54af705a6ab | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
1e354bc6-fb9e-547a-8894-238f23d91a18 | textbox | Enter: Teambinder Material Approval number
58729775-5b81-5bd2-8452-ca9d8636dda3 | note | – – – – – – – – – – – – – – – – –
580b046b-418f-5b0c-b350-23c0a6ca2db4 | note | METHOD - Document Review
2f089821-a06b-5407-b15d-655c70317f5b | note | – – – – – – – – – – – – – – – – –
3a61e1f7-ced3-5852-a1fc-924938ee7c8f | note | FREQUENCY - Once, for each coating system, 14 days prior to application
d59ee688-f686-5964-9d1a-158d74de895a | note | – – – – – – – – – – – – – – – – –
311f8f95-d75c-54e8-a867-f615a6a03542 | note | CATEGORY - HP
688fb48f-c6bb-592b-ab98-a8b2888e83d9 | note | – – – – – – – – – – – – – – – – –
b71d7735-3849-5547-a312-4509c7d0d0ce | note | RESPONSIBILITY - Nominated Authority
0b619de2-cda9-5224-9c45-d342a34cd052 | note | – – – – – – – – – – – – – – – – –
350f4d6b-8b86-5d9e-8d5f-96b5cb0364a2 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
ffd1deaa-4378-570b-a865-c852f3cd1d1e | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
87f53de2-4ed0-5aa0-94c0-d1912fa66ad8 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
4b11c74c-af03-51c4-b398-e23cc9a11a22 | note | – – – – – – – – – – – – – – – – –
b03609f6-c13e-5703-9373-2d040da217a5 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
16995d71-70b6-5d67-8c58-e663f8f8a48e | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
18d2b163-5d65-5cab-b04c-1511385e9770 | textbox | Enter: Teambinder Material Approval number
60691b7d-a891-59a4-a5e8-8fc991703ca7 | note | – – – – – – – – – – – – – – – – –
c5f95fdf-5f4b-598a-8df8-a953de087178 | note | METHOD - Document Review
e3611eca-ba9a-5722-afbb-07aff3fc53b5 | note | – – – – – – – – – – – – – – – – –
2689a03b-94d7-5776-9ce4-2731cadfaae7 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
ec8fd45b-d79e-5b93-bf91-0b53feba2d69 | note | – – – – – – – – – – – – – – – – –
ebafb50c-236b-5f17-8256-a5e76fbd6225 | note | CATEGORY - HP
55ca036e-7465-5961-a463-b731e9e98c35 | note | – – – – – – – – – – – – – – – – –
56d79b77-b739-5fc2-96de-1b74a179052a | note | RESPONSIBILITY - Nominated Authority
a7cd8852-b9e4-5e8d-aa37-5bbb692ef4aa | note | – – – – – – – – – – – – – – – – –
34bf93b7-e65e-58f9-b96b-920a0b1090e2 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
eadf3a0b-a5d2-5af5-a8c6-88d9a148d9a4 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
3b5b5683-fc4a-58b7-9b9c-919662227e44 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
e6b85902-0622-5f3a-adb3-03bad19724cf | note | – – – – – – – – – – – – – – – – –
4f7581cc-9dcd-5b8b-b45b-f10cf34a5a7c | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
bc9f0600-db1a-58ff-9165-3bd45e2727cb | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
216135f6-ce72-51fd-a4cc-16caed19cc73 | textbox | Enter: Teambinder Material Approval number
28d8091f-9be6-55ab-b69d-42ce45560548 | note | – – – – – – – – – – – – – – – – –
9afc8648-19f7-5e62-82cb-1ce3f8a59a73 | note | METHOD - Document Review
ac62028a-7f7b-54b0-a4a3-81502aa840ce | note | – – – – – – – – – – – – – – – – –
8983baea-f114-51e2-9083-3a3058242b50 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
8612cde3-81d0-5a86-af56-bc01f41a13ce | note | – – – – – – – – – – – – – – – – –
827239be-56fb-5614-805f-bb50912cca71 | note | CATEGORY - HP
e2839f30-9f43-5207-83d3-fad947a809ef | note | – – – – – – – – – – – – – – – – –
0dc292e9-eeaf-5ae7-9852-eb4db1a88423 | note | RESPONSIBILITY - Nominated Authority
46413889-5243-5aa1-a70e-b29c0cc288b9 | note | – – – – – – – – – – – – – – – – –
142b7f5d-2260-52f4-a863-429c8e70dcd2 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
2c0b3645-8a9a-599b-8df6-aab5079eb386 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
909fb6e5-1055-5a7b-8f0c-b281a0885601 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
1fd1868f-5605-516d-b739-84e123aab6c1 | note | – – – – – – – – – – – – – – – – –
a268ccf8-41d3-5fd0-92b6-14b55772ba52 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
fcd0624c-9bbe-5727-b860-1d0301b09621 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
fb2ca039-137a-5e38-bf6a-2f9d5a8a56f0 | textbox | Enter: Teambinder Material Approval number:
ce496800-f39d-599c-9a22-746a58f09a04 | note | – – – – – – – – – – – – – – – – –
ef221d62-2de8-5919-b4f7-70217e80d599 | note | METHOD - Document Review
3d7729e7-03af-5779-970f-bcd7a8f5cc96 | note | – – – – – – – – – – – – – – – – –
4a5c873a-94bf-53d9-bd1e-f31c758b5492 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
8361444e-9a7d-5397-8ded-3f6b7d558722 | note | – – – – – – – – – – – – – – – – –
a4634a42-7d24-5653-a08e-518ed916ce00 | note | CATEGORY - HP
899d51f1-dae8-5aff-af90-c58429864602 | note | – – – – – – – – – – – – – – – – –
9b92e548-f3ee-5a73-b8e4-9dc9d786d59b | note | RESPONSIBILITY - Nominated Authority
0a29cfe9-588c-5b3e-b1ae-0d83131b5917 | note | – – – – – – – – – – – – – – – – –
bd68ac4c-060f-5186-bebb-b56a0b356578 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
1f60d6d1-4844-529d-b844-b419fb5b39dc | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Quality Documentation
553b4af1-19da-57f6-a670-d0b2d7e8f084 | note | REFERENCE - 685.05 686.04
ebc73fe7-f3e8-5249-a8bb-911d61052413 | note | – – – – – – – – – – – – – – – – –
32bcb69b-50bb-5883-9e76-f8073ac449f6 | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
b42e5005-a611-58a5-aef6-ade832bd6e4c | textbox | Enter: Teambinder Hold Point number
6eea7c98-f6ab-59c2-a27a-ab6a9d6a2cf2 | note | – – – – – – – – – – – – – – – – –
9adbd7fb-4d9c-5433-a103-d428fd791ea9 | note | METHOD - Document Review
d7ac7456-2d55-56c0-acdb-6d7565a9ee29 | note | – – – – – – – – – – – – – – – – –
5fbc3542-5540-5238-b930-4d1e2c0123ae | note | FREQUENCY - Once, for each coating system, 21 days prior to application
4359368f-49a4-5ce3-9bfa-1dbf92fb8c39 | note | – – – – – – – – – – – – – – – – –
3ffda72c-5bcf-5da6-853f-3c1fedd400a5 | note | CATEGORY - HP
40010cc3-f242-5598-a96b-ce3e5eabaa8c | note | – – – – – – – – – – – – – – – – –
27f3e7da-442b-504f-aed4-5516ddf46703 | note | RESPONSIBILITY - Nominated Authority
961b8434-bea2-5383-ad1b-bd49a363c414 | note | – – – – – – – – – – – – – – – – –
b43ab333-754a-5749-85ad-7076730cca72 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
71100b96-31b4-5257-95fb-d5a2a180b669 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Coating Personnel & Equipment
b037c35d-bb25-5a6d-9875-314482cac723 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
d8adb728-e56c-56ab-a579-1de3fb18da76 | note | – – – – – – – – – – – – – – – – –
2f56f074-1e5d-5e8f-9526-958d6bb8f668 | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
4de1b36f-b757-55af-89c4-551ccc0b0a74 | note | – – – – – – – – – – – – – – – – –
5ca7f56b-f021-5fae-99fa-e4dd56b3fc46 | note | METHOD - Document Review
41c7753e-466b-5216-a2e9-4e824f02edd7 | note | – – – – – – – – – – – – – – – – –
f142cee1-f244-51fa-8ac1-928a453ea662 | note | FREQUENCY - Once, prior to application.
804c30e9-24d2-5200-9a23-da17027ae457 | note | – – – – – – – – – – – – – – – – –
d04a5dd8-c74a-5b3f-986b-7c665e70dcd9 | note | CATEGORY - IP
df68eca1-6797-5c24-bbd7-852014ebf7ad | note | – – – – – – – – – – – – – – – – –
55bc128b-ec96-5417-927e-7fceb1ab1db6 | note | RESPONSIBILITY - SE/PE/SPE
425b04ed-cb30-537e-b731-bc285d03dff9 | note | – – – – – – – – – – – – – – – – –
df3a04e8-46c9-5e70-ac53-a8841989864d | note | VERIFYING DOCUMENTS - This ITP
b3282d02-e420-5cde-a2c6-8131b258388b | textbox | Date Completed:
| checkpoint | 2.7 - Protection of Adjacent Works & Property
0c4f106f-2a0e-58fa-a69f-ac78570fbd82 | note | REFERENCE - 685.17 686.10
fd3dd1c5-a369-5a69-9d74-c0d117844baf | note | – – – – – – – – – – – – – – – – –
f1724b42-4349-5534-b68a-6817907b4dcf | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
3a65ab1d-7e25-5a9b-b902-718981b624cd | note | – – – – – – – – – – – – – – – – –
f9071711-7232-599c-9037-b82f4edad10e | note | METHOD - Visual Document Review
c0f4ef38-f762-5272-8fd7-b5d2c8f0915d | note | – – – – – – – – – – – – – – – – –
47480554-38da-5eb6-b49c-3e010ead5c14 | note | FREQUENCY - Where applicable, 2 days prior to application.
f7d690c1-bf4e-531f-b0f3-5f977e8cd1a6 | note | – – – – – – – – – – – – – – – – –
f7b48262-052d-5d17-ade8-3ed103037dbf | note | CATEGORY - HP
6c7384d5-71ee-58f0-910a-386fde33489f | note | – – – – – – – – – – – – – – – – –
c9db20e8-81cf-565a-a30f-e6abe6f9545e | note | RESPONSIBILITY - Nominated Authority
637d703c-9b12-5f9e-9751-634bb8296e7a | note | – – – – – – – – – – – – – – – – –
5a2dd8ff-9c14-5df2-8824-987e5c9cc03f | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
4b23cedd-6af0-59b0-bc6f-616941c72da4 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Minimum Concrete Curing Period
bd92d7f4-5f89-5bef-8c87-818046bc63ba | note | REFERENCE - 685.08 686.16
b52cbf3d-6417-5476-8eaa-12b583498c8f | note | – – – – – – – – – – – – – – – – –
fdd95f05-deca-5267-9d0b-7cdcb8999c5d | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
2642feeb-2aff-5cea-b882-ca2463f18609 | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
720175d8-c723-57c8-8040-18d1a886ae40 | note | – – – – – – – – – – – – – – – – –
5d6ae32a-5da9-54cd-831f-1d12f58797cd | note | METHOD - Visual Document Review
89eb59a3-4495-55e8-85c3-d6fa34092dc6 | note | – – – – – – – – – – – – – – – – –
35305b24-5fbd-597e-ad33-bbce5e0067f2 | note | FREQUENCY - Once, prior to application.
4290101f-0abb-5cf9-aa03-ed1eff8507a0 | note | – – – – – – – – – – – – – – – – –
33578b1f-0de8-5aac-97fa-8b28ebc8f9ff | note | CATEGORY - IP
124f7212-2926-58d4-98f2-17aa0c0d8f43 | note | – – – – – – – – – – – – – – – – –
ae69c80e-7a10-5fcb-9db4-8032653537bf | note | RESPONSIBILITY - SE/PE/SPE
385a50f5-c033-5bd9-97b2-46d2f4a704c8 | note | – – – – – – – – – – – – – – – – –
01978cd2-83db-574a-adff-6ca504271782 | note | VERIFYING DOCUMENTS - This ITP
4ee6fdf7-70da-5675-8602-4df7275ea99b | textbox | Date Completed:
| checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
3bbede8b-3288-56e1-b804-39241229eaaa | note | REFERENCE - 685.11 686.13
4a6bbcdc-b901-52ac-9bae-2b36286c636e | note | – – – – – – – – – – – – – – – – –
29046c8e-438e-5350-b1ac-a183e785dbd9 | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
26df53a4-2d7e-5f5a-8509-4da724f5ced5 | note | Attach: Inspection Photographs OR
71abb8ca-d7ea-572b-8129-40710c4e7c3e | textbox | Enter: Teambinder Hold Point number
04ec3a58-8f89-5683-81f2-55eb6ac5b8b7 | note | – – – – – – – – – – – – – – – – –
e5043226-5750-5c03-b201-660f45e2a824 | note | METHOD - Document Review
594ac971-acdf-57a6-a0f3-ae05b6470eaf | note | – – – – – – – – – – – – – – – – –
f291e3ce-71dc-5e2e-aae4-785014bfa30e | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
7ce9dda0-087d-5103-ac66-8cd6a3b8e3f6 | note | – – – – – – – – – – – – – – – – –
230cf319-f840-5d85-8891-14328c8969ca | note | CATEGORY - HP
03f53e49-226c-5bc9-b8db-5152d8af7732 | note | – – – – – – – – – – – – – – – – –
7e85ba6d-1fe4-5104-8cd5-e09c108ca76d | note | RESPONSIBILITY - Nominated Authority
df812984-7720-578f-9545-795108628169 | note | – – – – – – – – – – – – – – – – –
0ea75d2d-09e9-599b-8c9d-3c2bcea7e8ec | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
c7503ab3-eef0-55eb-8e94-f53e5e2f5363 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Pre-application Activities
| checkpoint | 3.1 - Material Records
c8e0e6b8-c51f-56c5-a71c-cfd0d8b9568b | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
d0eb2b36-4e7d-52ab-abd9-acba2fdf36f6 | note | – – – – – – – – – – – – – – – – –
23f79383-3122-54cf-a9f8-728d7182fed2 | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
6c03152a-9fe4-5b23-99cf-a8abe085ef7f | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
6987770f-7c02-5e5c-b3f4-5f64885ec211 | note | – – – – – – – – – – – – – – – – –
0538df22-5124-59a7-aee2-af39b487401c | note | METHOD - Visual
79a0ff21-746e-597a-8938-78a9bca4a135 | note | – – – – – – – – – – – – – – – – –
6829c902-f673-55f7-86bc-7cd500b43577 | note | FREQUENCY - Prior to application
fd3b030d-b6dd-519c-afa5-c4ea78c144e2 | note | – – – – – – – – – – – – – – – – –
2a3ac776-8456-57ec-bfe1-3b8276be3a76 | note | CATEGORY - IP
d04da30a-8238-5157-a501-5a6e031813f8 | note | – – – – – – – – – – – – – – – – –
70b23c23-ee63-5d15-98dd-7d34f8498923 | note | RESPONSIBILITY - SE/PE/SPE
ded2b8b3-5755-5258-804a-a4eb4b7a0827 | note | – – – – – – – – – – – – – – – – –
21cdd6af-37f2-5be4-b0eb-2163ad7cd8c7 | note | VERIFYING DOCUMENTS - This ITP
437fff6f-e0e1-56ee-ad54-6cf6cf5f7bdb | textbox | Date Completed:
| checkpoint | 3.2 - Weather Conditions
0d806c1a-5c50-5a24-84d7-6827088c30fc | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
8d889ee5-521b-52ab-a91e-14640a17451a | note | – – – – – – – – – – – – – – – – –
1c711db8-b195-5849-b58c-936912bd2f1e | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
d01e1f86-d1c3-559d-8cfa-7b754dcf4877 | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
0fc5f6ed-b712-5bb8-9b83-0b5f20f7df72 | note | Weather conditions are to be recorded.
e809766e-d308-51bc-bdf9-d1bd53ef3b07 | note | – – – – – – – – – – – – – – – – –
2bad80dc-c31f-5c8a-9311-508859624c28 | note | METHOD - Visual Measure
92b075f9-1c0d-5e74-bdf1-50322c2fda6a | note | – – – – – – – – – – – – – – – – –
bdf0650f-cdc2-58bd-b688-fc4993cd63ee | note | FREQUENCY - Prior to application and every 4 hours per shift
257cb3ee-6052-54e5-a9f3-65bb65b6da22 | note | – – – – – – – – – – – – – – – – –
b6fe9d5f-576f-5a91-87e5-3d71bb5f0c6b | note | CATEGORY - IP
0d77c98b-acf1-5df6-b3ec-4368fa37d60b | note | – – – – – – – – – – – – – – – – –
2b99fe02-db09-5243-9bca-a76c605ef715 | note | RESPONSIBILITY - SE/PE/SPE
ba362a12-3b9c-5297-9fdf-9e05b9d3f17c | note | – – – – – – – – – – – – – – – – –
af799b65-70b9-5989-93d7-04b0986fd4b8 | note | VERIFYING DOCUMENTS - This ITP
190c156a-8c5f-503c-9614-cb532cb78c62 | textbox | Date Completed:
| checkpoint | 3.3 - Surface Preparation
4f8cc284-b926-5df6-b957-7ce248236f41 | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
db8b7cf9-a012-54bc-8305-2dabacb1f72c | note | – – – – – – – – – – – – – – – – –
32939c0c-cbb8-57c4-b3b2-fc289fcbbdd9 | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
660da809-d65f-5b58-bb6f-98475fba8bf8 | note | – – – – – – – – – – – – – – – – –
7b467fe4-e507-56de-bf42-ddc83de55368 | note | METHOD - Visual
4a41d0f9-8be8-587c-bff1-5e2ab90f265f | note | – – – – – – – – – – – – – – – – –
b86c03ea-9eef-5fa0-b630-b265b22e1c70 | note | FREQUENCY - Once, prior to application.
83cdabbd-0fe0-5e00-8c3c-a6ac6ea260a9 | note | – – – – – – – – – – – – – – – – –
b5d26318-f151-5803-87f7-f277635b78eb | note | CATEGORY - IP
515702db-f7ed-5adb-a95a-4b794c29f185 | note | – – – – – – – – – – – – – – – – –
13f9f8c6-3aa1-5067-89c9-82d26758519a | note | RESPONSIBILITY - SE/PE/SPE
b5eee343-b608-5695-b5c9-662b5aa41492 | note | – – – – – – – – – – – – – – – – –
8d5be1d5-6c28-5828-be5f-0e6a2f4f6e5b | note | VERIFYING DOCUMENTS - This ITP
b030126d-6752-5e36-a0e9-7355360f0779 | textbox | Date Completed:
| checkpoint | 3.4 - Surface Moisture Testing
c7824685-c947-557e-aa26-a00045f93281 | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
518f6249-63fe-516b-affe-f72306916a58 | note | – – – – – – – – – – – – – – – – –
a5744b53-0438-513f-820e-259cf67bb153 | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
ca4bba93-0654-50f4-a7e1-b028ff8be256 | note | – – – – – – – – – – – – – – – – –
f9da52f8-b527-5630-9bf5-52b51819bd79 | note | METHOD - Test
62a48b4b-a169-55cf-ad98-93694c91b61f | note | – – – – – – – – – – – – – – – – –
84ae067f-6c40-5b0f-9185-50f5c9ed4c71 | note | FREQUENCY - Immediately prior to application, test 1m²
46548bb2-69ac-55f6-9d2e-9bd41ff6d37c | note | – – – – – – – – – – – – – – – – –
41429650-e3a9-54ba-91be-bc201490833b | note | CATEGORY - IP
5520f87f-e046-597b-81df-ed1826726b54 | note | – – – – – – – – – – – – – – – – –
978833fe-c15d-5e0e-aea6-8e0a9257582c | note | RESPONSIBILITY - SE/PE/SPE
e9be829a-fcb7-51d5-92fe-2305509829ee | note | – – – – – – – – – – – – – – – – –
f47163db-60f7-5cdc-b017-5a6dde1c5373 | note | VERIFYING DOCUMENTS - This ITP
4c0d1ecc-c981-5463-88e1-79a08ccff2ca | textbox | Date Completed:
| section | 4 - Application Activities
| checkpoint | 4.1 - Method of Application
655720ad-d82e-54e4-a0cc-d7fd5a31743e | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
af121610-bb68-55a4-8eb2-2176e6e90107 | note | – – – – – – – – – – – – – – – – –
69bc8ae9-c0d1-5723-afdf-095789d6ac31 | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
c1adaa0a-4d3a-5f6e-98b5-389677687e32 | note | Attach: Coating Application Record
3033d845-deb4-5a72-9b83-79a99479d523 | note | – – – – – – – – – – – – – – – – –
f3a55f24-f00c-5c07-82f4-a18235f4b8b8 | note | METHOD - Visual Measure
fc096312-ac29-5d35-8a92-7f67d9118f58 | note | – – – – – – – – – – – – – – – – –
2e91c6e6-099c-5fcb-94ab-df0836d14a49 | note | FREQUENCY - Each coat
86e151e6-84ef-56fd-a6f4-1a1a1c1cc298 | note | – – – – – – – – – – – – – – – – –
641c5595-8814-5e62-9558-4d62eef0edce | note | CATEGORY - IP
c6b5b327-afb4-5e75-bc89-d8e4233a69f5 | note | – – – – – – – – – – – – – – – – –
38641917-a54a-5aa1-8e15-c4ab76ce48eb | note | RESPONSIBILITY - SE/PE/SPE
0ad6481b-102a-5e40-9224-5add89afa529 | note | – – – – – – – – – – – – – – – – –
df63b177-5557-5219-946e-55a46ead8aae | note | VERIFYING DOCUMENTS - This ITP
7432d4ef-cff9-5807-94af-5bee581c61e9 | textbox | Date Completed:
| checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
708a7795-5704-5a6c-8b9a-095cc8b0ce3a | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
53960aeb-4658-5381-bed9-9a9bf50066af | note | – – – – – – – – – – – – – – – – –
a0dfcbf5-7bfb-561f-a3aa-24d1cf6e9edd | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
eec0a537-7881-525c-bfff-378ef4f98166 | note | Attach: WFT Test Results
f36e0fd0-0427-5961-9d65-8711b44a1848 | note | – – – – – – – – – – – – – – – – –
46030ed1-1509-59d3-afd0-ac7f9019869b | note | METHOD - Test
0461134c-4a19-5ff8-b1c2-5b20feb0e126 | note | – – – – – – – – – – – – – – – – –
8244e37e-5af2-5355-95bc-a0505002eef9 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
ad4bf1ca-f788-5bf2-98e6-a13871fb3194 | note | – – – – – – – – – – – – – – – – –
dcd32a9a-95bf-51ad-917a-ecad462b0cfa | note | CATEGORY - IP
685bc9ea-6186-514c-8cb8-af54ff36ca1d | note | – – – – – – – – – – – – – – – – –
0029a2f8-01e1-5523-9ecd-63ec8313fd99 | note | RESPONSIBILITY - SE/PE/SPE
724ab3ab-9857-5ab3-9023-f17a6dff81b2 | note | – – – – – – – – – – – – – – – – –
4b564209-3f79-5030-819d-b2d3f8536809 | note | VERIFYING DOCUMENTS - This ITP
3559d0be-f72e-5786-9d90-1f8ef8750942 | textbox | Date Completed:
| checkpoint | 4.3 - Inspection & Defect Identification
5bc8e40b-388a-5cc2-b5d5-673573b089d1 | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
5d5ddc9c-cd8f-5fe6-845c-35bbab177a51 | note | – – – – – – – – – – – – – – – – –
96c21147-64d4-5bb1-a4f1-363d2c4cc603 | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
42fe5049-6fe4-5fea-a31d-64dad81401de | note | – – – – – – – – – – – – – – – – –
583d2564-8a31-5c59-9be2-7b87d59b8329 | note | METHOD - Visual
204c8799-d0bb-5b3e-a9d5-9d4774a0deb2 | note | – – – – – – – – – – – – – – – – –
16028530-22ad-5112-9028-c81bfbe5e1a9 | note | FREQUENCY - After each coat
fca1ec1c-10bd-5d16-86fa-43c6294a42b9 | note | – – – – – – – – – – – – – – – – –
f8f3e756-18fb-5949-a50b-484d415e97af | note | CATEGORY - IP
811b2f10-f475-51e4-992d-19b5e873659e | note | – – – – – – – – – – – – – – – – –
b516472f-e389-5b74-ac4f-28044370f69f | note | RESPONSIBILITY - SE/PE/SPE
307e9447-0404-5099-acf7-ac132d98763c | note | – – – – – – – – – – – – – – – – –
b57faf58-2427-5a44-b053-edef5d919948 | note | VERIFYING DOCUMENTS - This ITP
5f85318f-17db-582f-b424-f34d5281ea0c | textbox | Date Completed:
| checkpoint | 4.4 - Drying and Curing
392ead22-baaf-5dd4-bc84-1b2ae7c402cc | note | REFERENCE - Coating System TDS 685.17 686.09
b9d95df1-b463-545b-a1aa-6cd4f39527be | note | – – – – – – – – – – – – – – – – –
1f7b3cda-ecdc-51b2-9c9a-2fe7a5637bfa | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
36854694-25da-5335-becd-c67534cdb264 | note | – – – – – – – – – – – – – – – – –
8b0362f7-94af-5b83-9757-e67efb125f55 | note | METHOD - Visual
2af83e2f-f831-55fb-b092-1b0a651fa439 | note | – – – – – – – – – – – – – – – – –
a625602b-3f0a-5394-ae17-4a39ce62fc09 | note | FREQUENCY - After each coat
41fb79d4-a155-5a7c-917a-1d57777dd541 | note | – – – – – – – – – – – – – – – – –
64e7b141-cc82-56ab-90e7-dc5db9c30212 | note | CATEGORY - IP
78db3937-8902-50b7-934c-550ab7130230 | note | – – – – – – – – – – – – – – – – –
fe9ecb23-665a-5ebf-8485-67dcc2dad435 | note | RESPONSIBILITY - SE/PE/SPE
831ed0c2-9bf2-5fb6-bd58-c8a624f8402e | note | – – – – – – – – – – – – – – – – –
c669c9f7-76b9-53c1-a174-ab28d4f82afe | note | VERIFYING DOCUMENTS - This ITP
18e2dee1-7a57-5763-9f56-fdddc385234d | textbox | Date Completed:
| section | 5 - Post-application Activities
| checkpoint | 5.1 - Clean-up & Waste Disposal
c6002fa7-a387-5f0f-8755-7d6bcbc41caa | note | REFERENCE - 685.09 (c) 686.10
e443cb22-8578-5a41-8d57-79b1b4245d40 | note | – – – – – – – – – – – – – – – – –
3f84001f-00d0-5e74-8d1e-34c094238f2b | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
9dd349aa-1a5a-562c-a584-001e084cb427 | note | – – – – – – – – – – – – – – – – –
554fa485-50c4-52a7-a130-e550d1085df9 | note | METHOD - Visual
bdc7227d-f077-5d8a-a3bb-b9c90f2cdfc8 | note | – – – – – – – – – – – – – – – – –
b8fd0e18-05ba-577a-bbd0-d187859da305 | note | FREQUENCY - At completion of Works
1d3c129b-ecb7-5e50-95fc-76e57db4001c | note | – – – – – – – – – – – – – – – – –
06783472-e872-580d-b3f0-6f96b7199b99 | note | CATEGORY - IP
8cc1bc23-f9ae-5a5e-9355-022c3167bad4 | note | – – – – – – – – – – – – – – – – –
a77ca6ba-e48f-55fa-b5ae-493fb7daa7a5 | note | RESPONSIBILITY - SE/PE/SPE
a4abd4f9-caf2-5783-81a8-803e079dbccf | note | – – – – – – – – – – – – – – – – –
dc93b825-4cd5-5e8b-83b5-ed50673e1d4c | note | VERIFYING DOCUMENTS - This ITP
e8aea563-2d40-5c6b-a0c9-e8026333ff07 | textbox | Date Completed:
| checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
be4e403d-2640-5d45-bdbd-9fc3f8b524da | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
b5f88c05-5bc5-597b-9fd0-5c2287f2bb9c | note | – – – – – – – – – – – – – – – – –
deb87bea-1816-56bd-bfd2-34453ae894a5 | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
4ec336cc-4890-5b87-821f-750b8044503e | note | No more than 15% of the readings shall be less than 90% of the required thickness.
e42b0b17-b2b1-543f-b905-114f18619c38 | note | Attach: DFT Test Results
88143cf4-7f48-5d57-9819-3305f9a9c926 | note | – – – – – – – – – – – – – – – – –
6d961fd0-7e47-5a96-8e6e-a2886a131eaa | note | METHOD - Test
b3a2ae24-4859-5e3c-9491-b1be2fe43e82 | note | – – – – – – – – – – – – – – – – –
0cdb4d2e-bc0d-56fa-8a7c-746a396d14d6 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
cc13de75-1e34-58f8-bdd3-7880e357c922 | note | – – – – – – – – – – – – – – – – –
6f780589-51eb-5b58-8a73-3b247d052dfc | note | CATEGORY - IP
cb495448-85ef-5c87-90be-a3a78338d70f | note | – – – – – – – – – – – – – – – – –
6c4e2a7a-e486-500d-b0cf-64f5b82a0f92 | note | RESPONSIBILITY - SE/PE/SPE
b8d8a558-3b3d-574c-9ef2-7fda0496c000 | note | – – – – – – – – – – – – – – – – –
235a3374-4abb-58dd-9d10-1cb65b9073de | note | VERIFYING DOCUMENTS - This ITP
15107dfd-6152-5881-b3fa-3965ad0c70d4 | textbox | Date Completed:
| checkpoint | 5.3 - Adhesion Bond Strength Testing
cc100967-76d9-5c22-9b68-14083be16bb5 | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
fff70190-e1c5-56a0-ba0d-10e9c9c40915 | note | – – – – – – – – – – – – – – – – –
3f433876-7787-5b27-a836-d5fcf2d1b1d3 | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
e3b349d1-ef1d-507f-8195-a44cbf4f1bbb | note | Attach: Adhesive Bond Strength Testing Results
d79a3afa-c2ce-5d8a-908e-8e80b88c3531 | note | – – – – – – – – – – – – – – – – –
fbac51f5-9798-53f5-86ee-a4ef9408d189 | note | METHOD - Test
846f7ee0-9457-536b-a0e1-4703ddd8229f | note | – – – – – – – – – – – – – – – – –
9dde5978-e0b2-51a4-84dd-1f6321f1caed | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
f8ab95a6-ece1-5cad-bba4-109e65d8ead5 | note | – – – – – – – – – – – – – – – – –
b1030132-dfa6-559d-a7f2-5bedf80588dc | note | CATEGORY - IP
036f6f00-79d2-5a7e-900b-15adb7e6a912 | note | – – – – – – – – – – – – – – – – –
310a958f-6a25-5909-b33a-4f7c00633728 | note | RESPONSIBILITY - SE/PE/SPE
b843a549-d745-5b72-af6c-465bc457877f | note | – – – – – – – – – – – – – – – – –
6881c750-5def-50f1-8b35-118100edbd61 | note | VERIFYING DOCUMENTS - This ITP
6664a0e4-b320-5926-950a-8db0d8abf545 | textbox | Date Completed:
| checkpoint | 5.4 - Penetration Depth Testing
acbe54ad-56eb-593e-88cc-fe23b708bb5c | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
45db9d31-41bb-5259-b76c-e81c462a0f73 | note | – – – – – – – – – – – – – – – – –
4e2d59c5-98e0-54e1-b4eb-dee95edda7d5 | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
5fd4fb10-3f03-5c65-b145-c8c6c08e0061 | note | Attach: Penetration Depth Testing Results
8c358ab4-dd4e-55d4-9a3c-6a32485f6e7a | note | – – – – – – – – – – – – – – – – –
de28b52c-0bfb-5342-b318-474c7bc62b50 | note | METHOD - Test
ab2a8965-693b-560b-bcfc-6c741c198c83 | note | – – – – – – – – – – – – – – – – –
abeae67d-4a78-5f3a-934f-b2026efb123e | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
2c50dcbf-bb17-5402-bc35-4205d157d346 | note | – – – – – – – – – – – – – – – – –
caf9fd23-0065-5f31-a61c-05e3e36e73c4 | note | CATEGORY - IP
389dedca-0d40-5f49-a045-9bc3c98dca6a | note | – – – – – – – – – – – – – – – – –
bdd0c5de-2aa5-5b1c-a613-79ee0dcd00cc | note | RESPONSIBILITY - SE/PE/SPE
0e809e38-8361-5a40-83a0-83642bd0f0e3 | note | – – – – – – – – – – – – – – – – –
0bc49c4e-9366-5701-b7f1-12bf85f237c8 | note | VERIFYING DOCUMENTS - This ITP
1bce364b-a644-5376-ad48-c5cb2646c06a | textbox | Date Completed:
| checkpoint | 5.5 - Non-conforming Coatings
9c65e037-dc63-5c3f-a3d9-59ce9a4e0a59 | note | REFERENCE - 685.14 686.17
6b2f3141-60c1-5fa9-8c7c-2e867dd61ca0 | note | – – – – – – – – – – – – – – – – –
9888dc17-0a1f-5393-8ca7-fa8350a08c93 | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
900833be-990b-53eb-b85e-e46124b3616a | note | – – – – – – – – – – – – – – – – –
01fc1c91-8d77-5fed-af84-d2dac2fdce16 | note | METHOD - Visual
be1b1b83-db62-5c80-83e6-72eb188e0ba6 | note | – – – – – – – – – – – – – – – – –
5da2174c-595a-50de-8fdc-5456ff853cd6 | note | FREQUENCY - Where required
3a9f7d94-8cc6-5c13-b279-f2c90a14a9f6 | note | – – – – – – – – – – – – – – – – –
172ee638-2228-5923-ae94-91c51107e68f | note | CATEGORY - IP
32fe57c7-f194-5edd-95be-74c9016c9a5b | note | – – – – – – – – – – – – – – – – –
3301536c-ce1e-51ba-9f7d-21009824cbcf | note | RESPONSIBILITY - SE/PE/SPE
fe603225-34c9-5628-b4d8-8788c62e71ce | note | – – – – – – – – – – – – – – – – –
e2b0cc1c-7311-5454-b90c-ad6ef431e882 | note | VERIFYING DOCUMENTS - This ITP
d1a43ad9-3bdc-5e42-8984-3f8a122de493 | textbox | Date Completed:
| checkpoint | 5.6 - Coating Application Guarantee
3fe5b8bb-7878-5fc3-8333-15cc698b5961 | note | REFERENCE - 685.06 (b) 686.05 (a)
03c3e7c4-8424-5016-87fa-1ce6aa778786 | note | – – – – – – – – – – – – – – – – –
88e959ac-50a8-55b4-a1d7-824e593c8f11 | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
33c00d73-fadc-578a-bd45-a751f761096d | note | Attach: Coating Application Guarantee
2d4fc0b6-a7e9-56c1-b10a-94247cfbd283 | note | – – – – – – – – – – – – – – – – –
806db9e1-1a88-53a1-8404-8e7bdabbe13d | note | METHOD - Document Review
c9ed8533-c6b2-5d31-b8a6-9a150ff744d7 | note | – – – – – – – – – – – – – – – – –
a98fe3bb-9efc-5821-8f09-029955bf69c5 | note | FREQUENCY - At completion of Works
f9e4ab0a-47c6-5b41-9463-2c820d4dc8b5 | note | – – – – – – – – – – – – – – – – –
ada7e861-b51e-500d-8630-a05f73b88abc | note | CATEGORY - SP
c0c831d7-0e6a-5bf7-b58e-bec0b44cc9a0 | note | – – – – – – – – – – – – – – – – –
4b1a485e-cdca-500c-b3f5-25b538b9e034 | note | RESPONSIBILITY - SE/PE/SPE
08aeef1f-5a2d-5cff-8704-c5603a1bc9d4 | note | – – – – – – – – – – – – – – – – –
5e779657-ffa0-516c-bfed-074ca33a7f2f | note | VERIFYING DOCUMENTS - This ITP
2d4d9431-7bd9-5ba0-9bf5-f9e1fa032eb1 | textbox | Date Completed:
| checkpoint | 5.7 - Repair to Damaged Coating
180b6c84-2811-5fc6-b57b-a6916ff4f64b | note | REFERENCE - 686.17
98d2513a-4131-540d-9ae8-883494a1c8cd | note | – – – – – – – – – – – – – – – – –
14bce53e-2ee5-58b3-8d7e-96b05922d708 | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
2873c5f3-d146-5836-9707-0882950645b7 | note | – – – – – – – – – – – – – – – – –
f3a6d425-1c36-590c-b2be-855de5e5f477 | note | METHOD - Visual
18ffdec1-b2a4-5073-8217-a0216c5ac7d2 | note | – – – – – – – – – – – – – – – – –
3ee96ce2-5c48-55b9-981b-0a4c3441284a | note | FREQUENCY - Where required
6f1e03dd-da28-530b-8135-db346c8b62fe | note | – – – – – – – – – – – – – – – – –
d5348f04-d4b1-5a46-adc4-f172988d6b82 | note | CATEGORY - IP
b50d1ed4-9753-55f1-999f-579a1d64ff09 | note | – – – – – – – – – – – – – – – – –
1e92013e-cae1-5540-adf3-da2b0f1c5a36 | note | RESPONSIBILITY - SE/PE/SPE
50973968-a9dc-5262-b9ef-aebee2cade1a | note | – – – – – – – – – – – – – – – – –
e271e26f-7287-57c5-b631-8d11515d6ffe | note | VERIFYING DOCUMENTS - This ITP
112cf0f9-3cc6-569f-b2dc-473744572672 | textbox | Date Completed:
| checkpoint | 5.8 - Non-conformance Report (NCR) Closure
e4f1475e-9b1f-5d6b-8dbd-c2ea03ebf8d2 | note | REFERENCE - MRPA Quality Management Plan
ef38f786-9da7-504b-a772-1160ab1196c0 | note | – – – – – – – – – – – – – – – – –
a15d6906-45f3-59cd-9200-c0b90b496def | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2ba6d1e5-66f1-5b08-9932-6c45b6adc43d | note | – – – – – – – – – – – – – – – – –
c63b6447-b969-55bd-9b08-68bf16d883f0 | note | METHOD - Document Review
e88b7b01-22d7-58dc-9209-910aa490c1cc | note | – – – – – – – – – – – – – – – – –
3b9be799-59fc-561f-af02-7d8acdda258f | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
01b11717-4eb7-53c3-984c-34920a04138e | note | – – – – – – – – – – – – – – – – –
c5c066c7-6b9b-5e6c-a0de-76ee09d427b7 | note | CATEGORY - HP*
7b0024c8-2b9d-5f15-9654-e42ed01aece0 | note | – – – – – – – – – – – – – – – – –
83fa62fe-bf6b-530e-8228-c271eac74777 | note | RESPONSIBILITY - SE/PE/SPE
6226290c-42e6-53aa-bd18-395dfffeef0e | note | – – – – – – – – – – – – – – – – –
a892a54d-ae9f-5780-8d6a-a1dc61278210 | note | VERIFYING DOCUMENTS - This ITP
0d409500-2de3-577a-a3df-2d7663fbe01a | textbox | Date Completed:
| checkpoint | Final Inspection
5330004f-ca7b-5538-9b2c-054d5fe4eb8b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f79e6845-cc61-589b-b2c2-6a49c1e124ee | textbox | Name:
b44f7681-4ea5-5ce5-86d6-03e57cd78467 | textbox | Position:
38b344b0-e14c-582f-ae1a-0ab118b8c05b | date | Date Completed:
| signoff | Sign ITP