## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-190-CIV-SSB-Subsoil Drainage | itp |  |  |  |  | ITP-190-CIV-SSB-Subsoil Drainage Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-190-CIV-SSB-Subsoil Drainage
label | ITP Description: SSB-Subsoil Drainage
label | Discipline (e.g. CIV/STR/RAIL): 190-CIV
label | Revision Number: 0
label | Revision Date: 14/08/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 702 (May '19)
section | Precast Deliveries
checkpoint | 2.1 Pipes
label | REFERENCE: IFC Drawings VR 702.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Granular material: Filter Sand
label | REFERENCE: IFC Drawings VR 702.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accredited with Vic Roads.
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Granular Material: No Fines Concrete
label | REFERENCE: IFC Drawings VR 702.05 (e)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No Fines Concrete: Shall comply with 702.05 e)
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Geo textile
label | REFERENCE: IFC Drawings VR 702.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with table 702.061
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Subsurface Drain Pits
label | REFERENCE: IFC Drawings Section 702.04, 702.05 & 702.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: As per SD 1631
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set Out
label | REFERENCE: Section 702.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Trench Excavation
label | REFERENCE: IFC Drawings Section 702.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Trench Excavation
label | REFERENCE: Section 702.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Nominated Authorith sign off ThisLine
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Placement of bedding
label | REFERENCE: Section 702.09 c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Traficable Pavements
label | REFERENCE: IFC Drawings SD 1601, EDCM 201
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Choose pass when applicable
label | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and EDCM 201
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Outside trafficable pavement
label | REFERENCE: IFC Drawings SD 1601, EDCM 201
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.6 Pipe and Geotextile Installation (if required)
label | REFERENCE: Section 702.03, 702.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding.
label | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.7 Backfill Installation (Granular Filter Material)
label | REFERENCE: Section 702.09 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
label | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Doc. Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 Backfill Installation (No Fines)
label | REFERENCE: Section 702.09 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ATTACH: No Fines Delivery Dockets
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 Install Pits and Flushouts
label | REFERENCE: Section 702.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.8 Marker Points
label | REFERENCE: Section 702.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each outlet
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.9 Flushing
label | REFERENCE: Section 702.09 (h)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Record Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10 CCTV
label | REFERENCE: Section 702.09 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Record Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Post-construction / Post-installation Activities
checkpoint | 5.1 As Built Information
label | REFERENCE: Section 702.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP