## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 003 (ITP003) - Earthworks | [5 empty] | A181 - West Dapto - ITC 003 (ITP003) - Earthworks
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted, required SWMS completed and signed, Safety Plan approved
label | • ERSED controls installed on site, air quality visually monitored for dust etc due to construction activities, Environment Plan approved
label | • Contact DBYD and complete excavation permit, extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Inspection of Foundation
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • Upon reaching designed floor level, an inspection between Principal & contractor of the foundation is required
label | • Promptly notify the Principal of areas determined to be unsuitable
label | • WITNESS POINT: Notify Client 3 days prior to inspection of foundation
text | INSPECTION:
text | WITNESS POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Existing CBR Test Results
holdpoint | WITNESS POINT
checkpoint | 3 - Excavate Unsuitable Material
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Where unsuitable material is found, excavate to the extent directed by the Client and inspect prior to backfilling
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Inspection of Ripped Floor
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: In the event of recompacting, rip material in the floor to a minimum depth of 150mm. Inspection of ripped or loosened material to be carried out with Client
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Inspection of Compacted Cut Floor
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Recompact cutting floor and notify Principal of completion before placing subsequent layers. Inspection of compacted floor
text | INSPECTION:
text | HOLD POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Compaction Test Results
holdpoint | HOLD POINT
checkpoint | 6 - Proof Roll Inspection
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Inspection of subgrade/pavement movement observed under roll test – after wet material and subsoil treatment applied.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Cut / Fill Transition
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Survey to mark intersection line. Inspection of intersection line between cutting and embankment
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 8 - Embankments Foundation Inspection
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Inspection of embankment foundation area following removal of topsoil
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Embankment Foundation Treatment Details
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: If either loosen and compact, bridging layer, working platform, geotextile/geogrid layer, drainage layer or other treatment is proposed, submit details 3 days before additional treatments
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Inspection of Trimmed and Compacted Embankment
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Inspection of trimmed and compacted embankment prior to placement of subsequent layers
text | INSPECTION:
text | HOLD POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Compaction Test Results
label | • Embankment Material CBR Test Results
holdpoint | HOLD POINT
checkpoint | 11 - Embankment Proof Roll Inspection
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Inspection of subgrade/pavement movement observed under roll test – after wet material and subsoil treatment applied.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 12 - Steep Slope Inspection
label | REQUIREMENTS / REFERENCE: 1112
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: For slopes steeper than 1:1, Client to inspect the stability of the batter before excavation below it
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature